Annual Review Performance Overview (max 2 pages

This information is being published instead of the DFID Annual Report, during the period where UK Government preparations for Brexit (“Yellowhammer”) are in effect.
This programme is not being reviewed under the standard DFID Annual Review process. This is a risk-based decision taken by the relevant Director for the programme.
Programme Title: Reducing poverty through Local Economic Development (LED) in the Commonwealth
Programme Value £ (full life): £3,900,000					Review Due Date: / 21/10/19
AMP Number: 204043-101		Start Date: August 2017				End Date: July 2020
Year	2018
Programme Score	A
Risk Rating	Low

Performance of the programme over the last 12 months
The Commonwealth Local Government Forum (CLGF) was established in 1995 and works to promote and strengthen effective democratic local government across the Commonwealth through local investment opportunities, job creation and improving the environment to do business. / Under an earlier £4.5m DFID funded programme (2012-2016), CLGF successfully piloted a local economic development (LED) approach, raised awareness for LED and demonstrated the potential impact of LED. / CLGF’s current programme is on track to deliver expected outcomes and to further deepen and embed their approach further throughout Commonwealth countries. CLGF will focus their efforts in Botswana, Ghana, Sri Lanka, South Africa, Eswatini (formerly Swaziland) and Zambia. / CLGF’s quarterly reports and regular catch ups with the programme team, indicate satisfactory progress is being made against outputs. Targets have been met for most log frame indicators and exceeded in several others, namely: (1.3) target councils demonstrate increased capacity to develop bankable projects and successfully leverage investment. This target has been exceeded: 13 pilot councils have developed bankable business plans aligned to their LED strategies and; and (4.4): 40 percent of funding leveraged against DFID contribution by Dec 2019. This target has been exceeded. CLGF have successfully leveraged £3.7m for project work from a mix of regional, national and sub-national sources. / CLGF have requested a short three month no cost extension to the programme to consolidate progress on national roll out of LED at country level. A formal proposal will be submitted to the Head of Department for approval in the coming weeks. / CLGF have carried out enhanced Due Diligence and presented DFID with their policies on / Safeguarding policy / Safeguarding register / Whistleblowing policy / Recruitment policy / Risk management policy / Code of conduct / There have been no changes to the log frame, theory of change. CLGF’s risk register has been logged on AMP and the overall risk rating remains low including the risks associated with this exemption.
Director approval comments
I have noted the progress made and that the risk register has been updated to mitigate risks associated with this exemption. I agree this makes sense to delay, given Commonwealth team pressures.
Date of next Annual Review/PCR: 2020