Annual Review – July 2019

Title: Support for the Economic Recovery of Somalia (SERS)
Programme Value £ (full life): £69.4 m		Review Date: June 2019
Programme Code: 204313	Start Date: 4th July 2014	End Date: 31st May 2020

Summary of Programme Performance
Year	2014/15	2015/16	2016/17	2017/18	2018/19
Programme Score	A	A	B	A	A
Risk Rating	High	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204313/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204313/documents

A. Summary and Overview (1-2 pages)

Description of programme
Support for Economic Recovery in Somalia (SERS) is the programme through which the UK funds the World Bank (WB) administered Multi Partner Fund (MPF). This is DFID’s fifth Annual Review (AR) of SERS. The SERS’s performance measurement indicators and targets[1] are taken from the World Bank’s Project Approval Documents (PAD) and the MPF’s Portfolio Results Framework.
[1] vault no 13156356
The MPF was set up in 2014 (up to 2024) to provide a platform for coordinated financing for the sustainable reconstruction and development of Somalia, with a focus on core state functions and socio-economic recovery, and a vehicle for coordinated policy dialogue with the Government. It has pooled funding from eleven donors and served to test different entry points in new areas/sectors e.g. service delivery and infrastructure development. In the last year, and based on the recommendations from a systematic country diagnostic carried out by the WB, the MPF has consolidated its interventions into three pillars: (i) effective and accountable government ($160.1m disbursed, $139.5m grants); (ii) enabling economic growth ($33.9m disbursed, $54.5m grants); and (iii) urban infrastructure ($10.5m disbursed; $24.5m grants). In 2017, an additional trust fund managed by the International Finance Corporation Trust Fund (IFCTF) was set-up, to which the UK also contributes through this programme. The total fund value currently stands at US$448.6m, of which the UK has committed $96.2m and disbursed $83.5m, making the UK the second largest contributor after the EU. Our contribution has not been earmarked except for: £2.4m to enhance integrity and security of the UK-Somalia remittance corridor; and £3m for the new International Finance Corporation (IFC) managed Trust Fund (IFCTF) to accelerate private sector development in Somalia.

Summary of Progress since the last AR
The programme is assessed an A, with milestones on average meeting the output targets relevant for this AR. The score reflects on average good progress by the MPF against technical reform and knowledge production, despite limited progress against political dialogue objectives such as strengthened dialogue towards federalism.
	Outputs	Score	Weighting %
1	Strengthened fiscal and public finance management capacity	B	40%
2	Strengthened public sector management capacity	A	20%
3	Enhanced economic and sectoral policies and enabling environment for economic development.	A	30%
4	MPF is effectively managed.	A	10%

Progress towards strengthening core state institutions has continued. Under the first two outputs, achievements include expansion of civil service salaries to all Federal member States (FMS); commitment by the Government to take on the financial responsibility of Capacity Injection Mechanism (CIM) recruits (described in output 2), demonstrating increased fiscal responsibility and further consolidation of the Somalia Financial Information System (SFMIS), through which all Public Sector non-security sector salaries and payments are now made.

The MPF has also contributed towards building the basic foundations to support economic development. The Central Bank has issued licenses to the Banking Sector and Money Transfer Businesses, carrying out independent supervisions. Some important pieces of legislation have been approved, although many remain stuck between the Lower and Upper Houses of Parliament. Private enterprises have been supported through grants, leveraging additional private and family finance. And, finally the Private Public Dialogue has opened an important avenue for the Government and the private sector to communicate and prioritise reforms to support economic growth.

Good progress has been maintained towards new work on urbanisation. The WB led urbanisation review is progressing and is due for completion in early 2020. The review is multi-disciplinary and has completed a political economy analysis of seven urban centres in Somalia. Following the review, the WB will define its portfolio for urban investment, which is highly likely to have a strong infrastructure focus.
However, during this last year, progress by the MPF has undoubtedly been challenged by the persistent difficult context of operating in a country emerging from over two decades of conflict and anarchy and by the deteriorating political environment. The continued breakdown in relations between the FGS and FMS has stalled progress on agreeing on a federal model and the process of transfers from FGS to FMS level to cement the financial model. Whilst there have been some efforts to facilitate dialogue on fiscal federalism and strengthen foundations for increased inter-governmental transfers, progress has been slow.

Context
In the last year, the political context in Somalia has become much more complex. The relationship between the FGS and FMS has deteriorated, exacerbated by contentious elections at FMS level. The stalemate in dialogue with Somaliland continues. Tensions between the FGS and the International Community emerged, following the expulsion of the UN Special Representative of the Secretary General (SRSG). And a fast-evolving regional context with the election of Prime Minister Abiy in Ethiopia has set a new precedent for dialogue and realignment of political incentives that could lead to both better or worse outcomes.
As the current Government approaches the end of its term, the FGS leadership is under mounting pressure to deliver visible progress touching the lives of the Somalis on the ground, including service delivery, jobs and inclusive growth. The offer of potential debt relief through the HIPC[2] Initiative has served to focus the FGS’s attention on achieving the benchmarks agreed with the IMF through the Staff Monitored Programme (SMP). Somalia concluded its 3rd SMP and negotiating a 4rd SMP at this point in time. While highly technical and vacuous in terms of incentivising political progress, this process has allowed the FGS to gain international support. At the recent WB/IMF Spring meetings, a roundtable co-hosted by the UK brought various international partners together to agree on the next steps necessary for Somalia to gain access to the HIPC initiative and debt relief. If both the Somalis and the International Community meet the required steps, Somalia could start the process for debt relief as early as February 2020. This will enable greater access to IDA resources altering the WB’s incentives and importantly their appetite to coordinate policy dialogue with other donors.
[2] Heavily Indebted Poor Countries Initiative established in the 1990s to assist poor countries with no prospect of getting out of debt distress.
In fact, the WB has already made an Initial investment of US$140 million from IDA’s Pre-Arrears Clearance (PAC) grant facility to support and accelerate the Government’s progress towards HIPC. Three MPF projects have benefitted from additional financing with more projects in the pipeline. In parallel the WB approved a comprehensive Systematic Country Diagnostic (SCD) and a Country Partnership Framework (CPF) for Somalia for the first time in over 20 years. The CPF is a four-year strategy for the WB, IFC and MIGA to address extreme poverty and increase shared prosperity, focusing on two areas: a) strengthening institutions to deliver services; and b) restoring economic resilience and opportunities. The EU also made its first round of budget support disbursements, having linked their disbursement linked indicators to those monitored by the WB and IMF.
In this changing context, the UK will have to consider how best to work with the WB, taking into account how the WB’s incentives will change once Somalia gains access to IDA; how the Government’s incentives will change as they access IDA and command a greater control over the use and allocation of donor funds against a persistent and urgent need for greater policy dialogue to assist the FGS to address many of the critical political questions unresolved and necessary for lasting stability to emerge in Somalia.

Key recommendations for the year ahead
By end October DFID will propose a strategic discussion with the World Bank Leadership (Country representative ad senior operation manager) along with other key donors (e.g. EU and Norway). The aim of this meeting will be to (1) agree on how to join-up policy and political dialogue with the Government on priority areas, (2) agree on the WB’s future outlook and (3) explore how best to work together to address Somalia development priorities in a complex political environment with a shift to toward greater use of IDA and the associated delivery risks.

SERS SRO to convene internal DFID programmes DFID discussion by end September, and then on a quarterly basis to collate key policy priorities across DFID’s portfolio that require discussion with the WB. Priorities will relate to current WB portfolio as well as mechanisms for working together as DFID designs its new set of programmes and WB enters IDA where the scope for policy dialogue could be further restricted. The WB’s existing operating model limits their ability to engage in meaningful policy dialogue once programmes are underway, risking their ability to deliver outputs but importantly weakening the link between outputs and outcome level goals.

By end of October SERS SRO will compile constructive suggestions for how to improve working with the WB at project and portfolio level. This will build on the discussion that DIFD has already started with the WB. The WB’s existing operating model limits their ability to engage in meaningful policy dialogue once programmes are underway, risking their ability to deliver outputs but importantly weakening the link between outputs and outcome level goals. DFID should continue to press the WB on this risk and together find a solution to incentivise and enable greater dialogue with Government, monitoring of assumptions (that affect the transmission between outputs and outcomes) and surveillance for key projects.

## B: DETAILED OUTPUT SCORING

Output 1	Strengthened fiscal and public financial management capacity
Output number per LF		1	Output Score	B
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator	Milestone	Progress
1.1 Federal government finances an increased share of its civil service wage bill (non-security sector)	60% of eligible salaries are paid for by the Government	Overall A / 77% (RCRF baseline); 58% (once additional finance through the surge support scheme is also considered)
1.2 Fiscal federalism dialogue facilitates FGS- FMS agreements. / (i) # of annual intergovernmental fiscal dialogues and knowledge sharing events / (ii) Evidence provided of FGS-FMS decisions and agreements made at fiscal dialogues (qualitative).	(i) 3 / (ii) qualitative	Overall B / 3 / Mixed evidence of quality and impact of the FGS-FMS discussions.
1.3 Foundations for fiscal federalism strengthened as demonstrated by increased inter-governmental transfers. / (i) # of FMS receiving transfers / (ii) % increase in total volume of transfer compared to previous years outturn	(i) 4 / (ii) 40%	Overall B / 5 / 8% according to FGS figures
1.4 Improved treasury management, budget execution and procurement in FGS, regional member states and SL	(i) register for moveable fixed assets included in annual financial reports / (ii) Basic payment system operational	Overall B / (i)Fixed assets reported in financial reports but not updated automatically. WB awaiting formal request from Government to develop interface with SFMIS / (ii) operational

Briefly describe the output and provide supporting narrative for the score
This output monitors progress by the core Governance projects funded through the WB MPF which account for roughly 78% of committed MPF funds. The Governance Troika projects consist of: The Recurrent Cost and Reform Financing Project (RCRF II); the Public Financial Management Capacity Strengthening Project (PFMCSP II), the Capacity Injection Project; and the Somaliland Civil Service Reform Project (SLCSR). These projects were designed to reinforce each other and together contribute to strengthening core public financial management systems, improving integrity, transparency and effectiveness of public finance. During the period under review additional financing for the RCRF II and PFMCSP II was approved by the WB Board, combining MPF and IDA funds for the first time in Somalia. Note that the projects aimed at civil service reform (the Capacity Injection Project and the Somaliland Civil Service Reform project are monitored under Output 2 of this Annual Review.

Crucial achievements under this output include expansion of civil service salaries to all Federal member States (FMS); commitment by the Government to take on the financial responsibility of CIM[3] recruits, demonstrating increased fiscal responsibility and further consolidation of the Somalia Financial Information System (SFMIS), through which all salaries and payments are now made. Whilst there have been some efforts to facilitate dialogue on fiscal federalism and strengthen foundations for increased inter-governmental transfers, progress has been much slower. Partly due to the broader FGS FMS breakdown in relations, but partly also due to a lack of targeted interventions from the WB. Overall this output is scored at B, with two indicators meeting their milestones and two underperforming.
[3] The Capacity Injection Modality is the mechanism through which additional talent is paid. Eventually the Government will have to take on this responsibility.

  1. Federal government finances an increased share of its civil service wage bill
During 2018, RCRF paid salaries in all four emerging states and Capacity injection modality (CIM) recruits in Puntland, totalling $4m in 2018 for roughly 2,474 FMS civil servants and 105 CIM recruits in Puntland. The represents an important step forward towards strengthening core state functions at State-level and would not have been possible without the work carried out by another DFID-funded programme PREMIS. In addition, RCRF II has expanded support to health and education sectors, financing 298 teachers in Jubbaland, 2,115 in Puntland and 265 in Benadir (BRA) - totalling $1.97m in 2018.
Overall, the Government continues to reimburse a significant share of core non-security civil service salaries accounting for 77% of eligible expenditure under the wage bill - i.e. wage payments that have been approved by the WB as meeting their eligibility criteria for reimbursement. The wage bill is greater than those salaries deemed eligible and so the Government’s share is greater than 77%. In addition, the government has agreed to take on greater responsibility for financing under the Capacity Injection Modality (CIM) where WB financing is planned to decline to $6.6m in 2019 and $1.4m in 2021. The FGS has already stopped recruitment of additional CIM recruits to relieve pressure on the wage bill.
Given the low level of revenue collection and the growing wage bill, fiscal affordability is a growing concern, particularly as the RCRF expands support to new sectors such as Health and Education, implicitly committing the Government to policy choices regarding service delivery in Somalia. To date, there has been very little analysis or discussion on what a sustainable growth rate of the wage bill should like look like. The forthcoming (autumn 2019) Public Expenditure Review (PER) will provide choices for the Government to discuss as well with the Medium-Term Expenditure Framework required as part of the National Development Plan. The WB is providing analytical support for both these products. However, a key recommendation must be to coordinate with other influencing instruments such as the IMF Staff Monitored Programme and open a frank discussion with the Government on options for fiscal sustainability in the medium term.
  1. Fiscal federalism dialogue facilitates FGS- FMS agreements.
Despite a breakdown in the relations between the FGS and FMS since late 2018, three technical meetings covering various aspects of fiscal federalism during the review period have taken place; two fiscal forums led by the FGS with inputs from the WB and one inter-governmental meeting with Education Ministers convened by the WB. While none of these meetings have led to any specific agreement some technical ground relating to revenue sharing agreements was covered:
- Various tax reforms including a paper funded by DFID carried out by WB on options for modernising Customs across all three major Ports was discussed at the 2nd fiscal forum in July 2018 in Nairobi, bringing together Finance Ministers from the FMS and FGS.
- At the 3rd fiscal forum in November 2018, DG-level representatives from all FMSs discussed a Fiscal Transfers Policy Paper drafted by the FGS, outlining the process and requirements for FMS to benefit from fiscal transfers. The paper was however not well received by the FMS, who continuously feel like that demands are being made on them without corresponding offers in return.
- The WB’s work on education, including a discussion on functional assignments for the sector was presented to Education Ministers in December 2018.

On resource sharing, the Financial Governance Committee (FGC) prepared an advisory paper on international experience in natural resource revenue sharing which was translated into Somali and presented to the Economic Committee of Cabinet. In the case of fisheries an agreement has been reached but only for one year, in the case of petroleum, a proposal has been approved by the lower house, but critics claim will be too complicated to implement in any practical way.
As identified by the Financial Governance report there are substantial risks associated with inappropriately designed revenue sharing agreements, particularly in sectors such as petroleum. Efforts should focus on agreement of high-level principles, rather than percentage shares, which has not been the case. The FGC also highlights the need for agreements to incorporate scope for adjusting in the future to consider changing circumstances.
  1. Foundations for fiscal federalism strengthened as demonstrated by increased inter-governmental transfers.
Fiscal transfers have increased between 2017 and 2018 by 8% (including transfers through the RCRF, the RCRF Surge component and direct FGS transfers). While this doesn’t meet the target set in the logframe, given the poor relations between the FGS and FMS this demonstrates some level of progress.
The allocation between States remains ad hoc and inequitable, with Benadir (BRA) receiving more funds (51%) than all the other FMS combined (which may be partly explained by the existing agreement to allocate 15% of Mogadishu Port collections to Benadir), and Jubbaland and Galmudug experiencing a reduction in transfers in 2018 with respect to 2017 (see graphs below).
Fiscal transfers to each FMS as share of total FMS transfer
Total Fiscal transfer to FMS (including Benaadir), and as share of total FGS spend
million $ USD
Source: FGS data from Fiscal Transfers Policy Paper
Through the Surge Support mechanism disbursement linked indicators (DLIs) were agreed covering various priority policy areas including inter-governmental fiscal relations, once again these refer to the policy paper referenced above, that was not agreed; and a fisheries agreement, which is expected to hold for a year.
More work is needed to design and agree on a rules-based, predictable and transparent approach to managing fiscal transfers across FMS, and between FMS and BRA. The FGC has provided some advice on strengthening intergovernmental fiscal transfers support by participating in the few meetings between that took place between FGS and FMS in 2018. They have recommended that the FMS and BRA provide basic reports to FGS on transfer utilisation which was reflected in the Fiscal Transfers Policy Paper drafted by the FGS and discussed with FMS in November 2018; and that a clear set of criteria be developed for 2019 transfer allocations, which does not appear to have happened.
This remains an area of huge importance where the WB has yet to gain traction with the Government. Greater collaboration between the FGC and programmes supporting FMS such as PREMIS could provide some headway. Discussions led solely by the FGS are unlikely to satisfy the needs of the FMS and so the strained dialogue between FGS and FMS will continue, limiting progress on fundamental issues such as equitable resource allocation across States.
  1. Improved treasury management, budget execution and procurement in FGS, regional member states and SL
The WB has supported important progress on all fronts of PFM for the FGS, Puntland and Somaliland. Progress on developing the functionality of the Somalia Financial Information System (SFMIS) has continued. The payroll module is working, and civil servant staff are being paid through SFMIS. Also included in the SFMIS is an Asset module where departments can manually input when they purchase new assets. In January the WB discussed the possibility of developing an interface between the purchases module and assets module so that all new assets are automatically registered on SFMIS. The Asset department is currently discussing this with the Accountant General’s office and will make a formal request to the WB.
The payment system is operational. There is an SFMIS outlet at the Central Bank of Somalia (CBS) where requests for payments can be accessed and processed by CBS staff. The full integration between the core banking system and the SFMIS is on-going, with payments from SFMIS being manually processed through the core banking system. This has an important positive impact for the integrity and scalability of the FGS payments system. The next step is to strengthen inter-bank payments through establishing an automated transfer system (ATS) to facilitate large payments and a national switch to facilitate interoperability of retail payment systems in Somalia. Procurement of both started in October 2018 and is being led by the IFC.
In terms of procurement, the most significant support has come from the FGC, who have been directly advising on the re-tender of key concessions such as the Port and Airport, and SNA rations contract. The FGC has also advised on operationalising the 2016 Procurement Act, recommending a set of regulations to minimise the risk of a highly decentralised procurement system and enable contract awards above a certain value to be subject to approval by a third party within Government. The regulations have been approved by the Council of Ministers, which represents an important win.
In Puntland the PFM programme is supporting domestic resource mobilisation (DRM), focusing on strengthening tax policy by setting-up of a tax policy unit to provide performance analysis and revenue forecasting; tax administration, focusing on business processes and automation as well as tax payer registration to encourage voluntary compliance; and tax education, targeting registered taxpayers to comply with tax laws through media campaigns. The project is also providing support on audit management, procurement and support to the Puntland Public Accounts Committee.
In Somaliland the Authorities were less welcoming to support from the WB PFM II programme given that the principle recipient is the FGS and that the WB extends support to SL through a no objection approach. The PFM programme is providing a full review of the PFM action plan, support to procurement although there are complications with implementation of current Procurement law as it has been drafted. WB also providing support to DRM collaborating closely with the PREMIS funded tax programme in SL.
Lessons identified this year, and recommendations for the year ahead linked to this output
1. DFID will continue to work with the WB to combine technical support with sustained policy dialogue to strengthen progress on agreeing to a rules-based fiscal transfer mechanism. Targeted technical work combined with the analysis and open discussions that the FGC have demonstrated are possible could accelerate progress towards a rules-based mechanism. This requires greater coordination between the MPF projects and even other partners such as the IMF, EU and PREMIS.
2. DFID will continue to work with the Governance team at the WB to hold policy discussions on the size and role of the civil service essential for sustainability of the State in Somalia. The WB have confirmed that there will be two new positions of a Senior Governance Specialist and Senior Economist, who will lead on carrying out a Public Expenditure review.

Recommendations from previous AR	Status
Fiscal affordability of the wage-bill - the expansion in size of the civil service needs to be calibrated to longer term affordability and sustainability.	in progress see above recommendation II
DFID should intensify engagement with the Bank and EU on if and how the additional funding through the proposed budget support and PACF can be leveraged to energise the political processes to solutions to more complex issues such as functional and revenue assignments at federal, state and district levels.	Achieved. benchmarks have been aligned through support from DFID’s PREMIS programme
Leverage surge to initiate a serious policy dialogue between the WB, donors and FGS on the medium-term reform priorities e.g. on (a) role and size of public sector, including the wage bill and (b) implementation of the road map for revenue mobilisation	in progress see above recommendation II
DFID should work with the Bank towards building greater consensus and convergence around reform efforts at federal and state levels. This may require a more structured approach than is currently not the case.	Progress achieved through DFID’s PREMIS programme that have been working closely with the WB on bringing on board FMS salaries.

Output 2	Strengthened public sector management capacity
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator	Milestone	Progress
2.1 Staff appointed to key positions in FGS and regional member states through approved CIP procedure (cumulative, % women)	FGS: 130 PL: 70 (20%)	Overall: A+ / FGS: 169 / PL: 112 (26% women)
2.2 Ministries/agencies with operational HR / FM functions[4]	FGS: 3 / PL: 3	Overall: A+ / FGS: 10 / PL: 9
2.3 Improved civil service management functions	• Basic human resources data management system established in Puntland / • Comprehensive payroll audit completed for FGS	Overall: A / Part of SFMIS / HR audit complete for FGS
2.4 Transparency & Accountability: / i) # of monthly payroll reports published on the MoF Website. / ii) # of fiscal summary reports published on the MoF Website	12 / 12	Overall: A / (i) Revenue and expenditure reports published monthly http://mof.gov.so/fiscal/ / (ii) Fiscal reports published on quarterly basis on MoF website
[4] A ministry/agency is considered to have an operational HR and FM function in place when at least three of four criteria are met: i) organigram developed, ii) Unit staffed (at least 60%) iii) staff are trained iv) unit produces key outputs (e.g. financial reports, HR records).

Briefly describe the output and provide supporting narrative for the score
This output is mainly delivered through the Capacity Injection Project (CIP). It aims to help federal and member states improve transparency and efficacy of public service recruitments, and also build capacity of the government departments and institutions. This output is scored at A, with two indicators exceeding the milestone and the other two meeting milestones.
Staff appointed to key positions in FGS and regional member states through approved CIP procedure (cumulative, % women)
Recruitment through the Capacity Injection Mechanism (CIM) is now complete. There is no more funding available through the project for any additional CIM staff (beyond original targets). This has been an important mechanism to fill critical positions across the FGS and FMS. Payment of salaries of staff in both FGS and Puntland (PSS) are compliant with the harmonised capacity injection modality (CIM) pay scale approved by the steering committee.
  1. Ministries/agencies with operational HR / FM functions
Good progress on this indicator, in fact demand from Ministries outstripped the WB’s original plan and as such 10 institutions rather than 3 at the FGS level received the re-organization and change management support and in Puntland 9 rather than 3 institutions (all ministries except for the Ministry of Finance). As a result, the FGS has formed a technical team to review developed policies and develop rules and procedures for cabinet approval. Puntland has already approved HR rules and procedures which are ready for roll-out, and Somaliland is in the process of translating its HR rules and procedures ahead of presentation to Cabinet.
  1. Improved civil service management functions
HR management modules are included on the SFMIS, which allows for the basic data on employees to be stored and updated. There has also been good progress on HR audits: Puntland and Somaliland have both completed their audits and post-HR audit activities are being implemented, e.g. payroll cleaning. At FGS, the data collection process for the HR audit has been completed and the final data clean-up is on-going. There have been some delays in validating the final data, partly due to the bomb attack at Ministry of Labour in Mogadishu in April. Linked to the Audit, the FGS has requested support to develop a Public Sector Reform Strategy, which should start in approximately 2 months
In addition, the project has been supporting key Civil Service training Institutions. The FGS has established a civil service training school (School of Management and Public Administration – SOMPA) at the Somalia National university to undertake training of civil servants locally and on a continuous basis. Whereas Puntland is working on an Establishment Act for the Institute of Public Administration and Management prior to procuring services from the Kenya School of Government. Similarly, Somaliland is in the process of procuring services from the Ghana Institute of Management and Public Administration-GIMPA
  1. Transparency & Accountability:
A decision was made by the Government to change the nature of reporting away from payroll reports to broader revenue and expenditure reports. These are published monthly on the Ministry of Finance’s website as a report on expenditure by Ministry and expenditure type (wages & salaries, general expenses, fixed asset acquisition). Fiscal summaries however are published on a quarterly basis and provide a qualitative summary of revenue and expenditure. These are not published on a monthly basis as they take longer to collate. This is in practice with international fiscal guidelines.
Lessons identified this year, and recommendations for the year ahead linked to this output
1. DFID should urge the WB to expand work on institutional support building on the success so far and extending to greater number of MDA and FMS where possible. This reflects a growing recognition from Government entities on importance of well organised and structure institutions.
2. Before end of 2019, DFID should consider whether this output remains critical to Theory of Change and whether it should maintain weighting of 20%. As the work on urbanisation scales up DFID will want to consider whether to shift its focus away from this output towards the urban agenda.

Recommendations from previous AR	Status
Follow-up on HR audit findings	The Pillar Working Group (PWG) has been following progress very carefully and provides an ideal forum for Government and donors to effectively follow-up on progress.
DFID should continue to focus on greater transparency around the government’s budget and other fiscal processes.	Good progress made by Government, by publishing monthly revenue and expenditure reports on website

Output 3	Enhanced economic and sectoral policies and enabling environment for economic development.
Output number per LF		3	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	NO

Indicator	Milestone	Progress
O3.1. Operationalisation of the SBCF and SMEF: / (i) grant applications received; and / (ii) awarded, by region / (iii) Private sector investment (committed as co-payment) by Catalytic fund recipients	i) SC: 500 PL: 500 SL: 500 ii) Granted: 201[5] iii) $2,000,000	Overall: A / i) SC 522; PL 476; SL 752 / ii) Granted: 101 (value US$6.5m; $5.3m disbursed) / iii) $3.5m (from grantees) + $1.1m in loans from Somali financial institutions and $2.1 in private loans from family, and others
O3.2 Training: / i) # of individuals receiving subsidized BDS, TVET or other forms of training financed by the SCORE project / ii) Total annual increase in revenue of firms supported by SBCF and SMEF that received training and advisory services	i) 800 / ii) 5	Overall: A+ / 1,162 / 69% (average cumulative quarterly increase in firm revenue)
O3.3 Improvements in the regulatory environment for private sector development / i) # of diagnostic reports on legal, regulatory, institutional and infrastructure setting aimed at supporting private sector development (cumulative) / ii) # of new business licenses issued under the Licensing Act during the SCORE project	i) 8 / ii) 200	Overall A / 10 / Data not available – as no longer collected by WB
O3.4 Supervisory capacity within the remittance sector: Trusted Agent operations, including # MTBs supervised (on or off-site)	No longer active	No longer active
O3.5. Greater contribution of ICT sector (through taxes and license fees) to public treasury enabled.	Regulatory Authority described in the communication Act established and regulatory framework drafted including tax regime	Overall A / National Communications Authority (NCA) formally created in Jan 2018. Board members appointed in May 2018. Initial set of regulations, guidelines and a national spectrum allocation table produced and posted to NCA website: www.nca.gov.so.
O3.6 Feasibility and preliminary design studies for specific urban investments completed. / (Primary roads in Mogadishu and Garowe; secondary roads in Mogadishu; solid and liquid waste in Hargeisa)	Completed in previous AR	Progress has been made on urban review.
O3.7 Total number of direct jobs created in enterprises supported by the SCORE project (Cumulative) / i) Total / ii) Women / iii) Youth	i) 2000 / ii) 650 / iii) 800	Overall A / Exceed / i) 2217 / ii) 634 / iii) 1,343
[5] The target number of grants awarded should have been revised downwards as the scale of grants was revised after the SCORE MTR – WB MPF target is 85. Of 101 selected, 19 dropped out as they couldn't meet performance-based conditions

Briefly describe the output and provide supporting narrative for the score
This output comprises a portfolio of projects aimed at enhancing economic growth: (a) creating an enabling environment for economic growth, (b) spurring growth in the productive sectors, (c) increasing access to finance and sustaining remittance flows, (d) supporting inclusive resource sharing arrangements, and (e) supporting the development of urban infrastructure. This output is scored at A, with of a total number of 7 indicators; one exceeding expectations, four meeting expectations, and two no longer relevant as they were achieved in the previous AR and should have been removed from logframe.

  1. Operationalisation of the Somalia Business Catalytic Fund (SBCF) and the Small and Medium Enterprise Fund (SMEF)
The SBCF was a matching grant scheme that operated from July 2016 - January 2019 and managed by a private sector implementor - DAI. 82 enterprises (out of 1,750 initially eligible applications) across the Somali peninsula were approved for grants worth a total of $6.5m. Of these, 67 projects were completed within SBCF’s lifetime. The main subsectors funded were light manufacturing, agriculture, livestock and construction with a total of $5.3m in grant financing. SBCF grants were mixed with direct financing from grantees to the tune of $6.5m (slightly short of the $7m target) and an extra $1.1m in loans from Somali financial institutions and $2.1m in private loans from family and others. Other results include: 69% increase in average cumulative quarterly revenue across all firms, and 54 innovative products sold by grantee enterprises some 10% below the project target.

Given the lack of financial products and services in Somalia, SBCF received a high level of applications, with the result that many were rejected. Most of those rejected were from start-ups, suggesting that there is a huge gap in the market to support start-ups. And only 12% of projects approved were from female-owned enterprises, suggesting that these vehicles are not adequately designed to address the constraints met by women and the types of businesses they operate in. To fill this gap in knowledge, the WB commissioned a scoping study on women entrepreneurs’ access to microfinance, looking at the demand for and supply of services and a diagnostic study of microfinance. The lessons from this research have informed the design of the WB SCALED UP and IFC FIDEP programmes, which have just been approved by the WB Board in June.

  1. Training
The SMEF operated from July 2016 - April 2019. It was established to build the capacity of Somali SMEs, including applicants and grantees from the SBCF through provision of technical assistance business development services to launch, manage and grow businesses. In total the fund supported 30 SMEs that were successful in gaining grant finance from the SBCF and 65 non-SBCF SMEs. In addition, 533 individuals (between July – Dec 2018) received skills training in trades such as mobile phone repair, fish net repairs, post-harvest handling, and storage of agricultural goods.

  1. Improvements in the regulatory environment for private sector development
There have been a few achievements in the regulatory environment including: the Companies law was passed by the parliament of the FGS in May 2019 but still awaits approval by the Upper House and Presidential assent; and the Mobile Money Draft Regulation was completed in December 2018 and expected to come into effect in June 2019. However, the Somalia Bureau of Standards Bill is still pending a first reading in the Lower House; and the Investment Law and Electricity Act are still in drafting stages. In Somaliland, the draft Somaliland Investment Law has been reviewed, in line with the tenets proposed in the national Investment Policy Statement.
The Public Private Dialogue (PPD) held its first meetings in Mogadishu and will hopefully be an important forum for discussing means to improve private sector development. The first economy-wide PPD was hosted in November 2018 in Mogadishu to discuss a range of issues: establishing an insurance market, correspondent banking relations, lower lending rates, telecom interoperability, ID requirements for SIM card registration, sales tax at ports, high cost of energy, women-friendly lending products, protections for import-substituting domestic start-ups in light manufacturing, and standards for livestock exports. The PPD also contributed to the tabling of the draft Companies law. In Somaliland the PPD has facilitated an agreement between the public and private sector on reforms such as the Electric Energy Act in Somaliland. This was returned to Parliament by the President in October 2018 for amendment. Although these are the first attempts to formally bring together the Government and the Private Sector to discuss specific policy priorities, it is still early days to assess how effective these mechanisms are in incentivising meaningful dialogue.

  1. Supervisory capacity within the remittance sector: Trusted Agent operations, including # MTBs supervised (on or off-site)
This component was concluded in August 2018 and should not have been included in the log frame.
  1. Greater contribution of ICT sector (through taxes and license fees) to public treasury enabled.
The National Communications Authority (NCA) was formally created in January 2018 and Board members appointed in May 2018. The Initial set of regulations, guidelines and a national spectrum allocation table produced and posted to NCA website: www.nca.gov.so. This will importantly provide the basis from which to start collecting greater revenue from the ICT sector. As a very nascent institution, the NCA will require a lot of support to develop the capacity and credibility to implement the sector regulations. While an important first step, there is still some way to go.

  1. Feasibility and preliminary design studies for specific urban investments completed.
The WB led urbanisation review is progressing and is due for completion in early 2020. The review is multi-disciplinary and has completed a political economy analysis of seven urban centres in Somalia. Following the review, the WB will define its portfolio for urban investment, which is highly likely to have a strong infrastructure focus.
  1. Total number of direct jobs created in enterprises supported by the SCORE project
Overall the project has exceeded the target for job creation. However, in general these figures should be treated with caution given the lack of clear definition of what constitutes a job and the lack of external verification. This relates to a broader concern of how the project defines progress and monitors this. More specific recommendations are made in section G: monitoring evidence and learning.
Lessons identified this year, and recommendations for the year ahead linked to this output

1. DFID should work with the WB and other development partners working in economic development to take a broader approach to supporting the development of financial services in Somalia. Whilst SBCF and SMEF have delivered good outcomes for businesses in Somalia, they were neither scalable to others nor sustainable in as much as providing lasting financial service options. Through its new SCALED UP/FIDEP programme WB Group will support the development of Somalia’s financial service sector to provide a greater product offering to SMEs. Along with other key partners such as USAID, DFID should work closely to define common goals and approaches.
2. DFID should encourage WB and partners to deepen our joint understanding of economic marginalisation faced by women and young people. Economic marginalisation remains a major challenge that Somalia needs to. The percentage of successful female SBCF businesses demonstrates that more must be done to support these groups to access economic opportunities such as those that will be on offer through SCALED UP and FIDEP. Future WBG programming is seeking to deepen the understanding of this area, such as the Bank’s analytical work on women’s access to microfinance and on microfinance providers.
3. Discuss with the WB how they can adapt project activities based on their comparative advantage and activities of other programmes. For example, a second round of grants did not go ahead because it was identified that others, such as USAID’s GEEL programme and DFID’s PIMS programme were delivering strong projects in this space, and that the Bank’s comparative advantage was in providing policy and regulatory support. This discussion is already happening through the new Scaled -Up project, the IFC trust fund line of activities and should continue.
4. DFID will push IFC to identify a pipeline of investable projects by March 2020. DFID is working closely with the IFC to accelerate activities to support an IFC investment in the Private Sector once arrears with the WB are cleared. The IFC needs to leverage existing work on strengthening financial sector through the WB and IFC to enable Somali access to DFIs.

Recommendations from previous AR	Status
DFID and WBG to jointly conceptualise, design and fund more targeted programme to address some of the challenges identified in the WBG’s SCD and RRF.	Underway – DFID and WBG are liaising closely on the development of SCALED UP, FIDEP and DRIVE – the new DFID programme.
MPF to continue to progress the establishment of key economic legislation, but to grow focus on implementation of legislation	Underway – Events such as the economy-wide PPD demonstrate that the WBG is moving in this direction. The above-mentioned new programmes articulate the desire to focus on this in key areas in which the WBG is well placed to offer support, such as to the Central Bank. This is positive and should continue to be strengthened.
DFID team should engage with the WB and IFC in exploring how to strengthen the gender focus by integrating interventions specifically targeted at women and including women business leaders in the PPD.	Underway – WBG is making efforts to mainstream gender within its future programming, with a view to developing a specific programme at a later date. Strong evidence collection (disaggregated) and periodic analysis should underpin all future WBG programming. WBG should take the lead in sourcing and applying lessons learned by DFID and other MPF partners into WBG programming.
DFID and WBG Team to provide timely revisions to logframe assumptions and targets	If DFID undertakes an MPF replenishment the logframe should be updated up to six months before the next annual review.
Transfer the remaining SBCF budget to the Scaled-Up programme	Under discussion by the WBG

Output 4	MPF is effectively managed
Output number per LF		4		Output Score		A
Impact weighting (%):		10%		Impact weighting % revised since last AR?		Y/N (if Yes, indicate if ↑or ↓)
Indicator			Milestone		Progress
O4.1 Implementation of an effective MPF wide approach to risk management [revised] / i) # of annual Risk Management Group meetings (for the three SDRF funds) / ii) # of quarterly reports and corresponding donor briefing sessions by Monitoring Agent / iii) Evidence of risk management response to issues raised / iv) External review of Joint Risk Management Strategy (JRMS) conducted / v) DfID and World bank work collectively to improve strategic implementation of Joint Risk Management Strategy (JRMS) (qualitative)			i) 6 / ii) 4 / iii) Yes / Additional qualitative indicator: External review of Joint Risk Management Strategy conducted		Overall B / i) 1 - failed to get quorum of donor members after several attempts by fund administrators to call meeting. WB/UN completed analysis for deep dive event on preventing GBV. / ii) 3 produced, 2 used internally. The 4th was put on hold pending change in CBS Governor. To be finalized in 2019. / iii) fraud cases followed up on / iv) no as JRMS dropped – see below / v) Some progress - see below
O4.2 MPF disbursement and commitment ratios / of signed project grants (signed more than 4 months prior to the end of the calendar year. / i)Disbursement ratio of signed project grants (signed more than 4 months prior to the end of the calendar year) including RCRF/ Excluding RCRF / ii) Commitment ratio of paid-in donor contributions (transferred more than 4 months prior to the end of the calendar year)			i) 55% / 45% / ii) 70%		Overall A+ (exceeded) / i) 75% / 62% / ii) 85%
O4.3. Consultation and transparency / i) # of consultative group meetings held with both donors and Minister of Finance / ii) Publicly available documents available on the MPF website / iii) # of annual consultative group meetings with donors addressing fund, sector or project-level issues / iv) Annual consultation on the quality of dialogue and fund management between World Bank and donors hosted and minuted by DfID (Introduced in 2018)			i) 1 / ii) Yes / iii) 12 / iv) none		Overall A / i) 2 / ii) Yes / iii) 12 / iv) 1 – resulting in constructive letter to WB sent on 22nd May 2019
O4.4 MPF portfolio is gender and conflict sensitive / i) % of RE projects with WB gender flag and accompanying justification / ii) % of MPF projects that utilize conflict analysis to inform project management, going beyond basic World Bank requirements for project preparations			i) 70% / ii) 35%		Overall A / i)75% / ii) 100%

Briefly describe the output and provide supporting narrative for the score
The focus of this output is on the effectiveness of the management and implementation arrangements of the MPF and its portfolio of projects, including the Bank’s procedures and ways of working. The output as reflected in the choice of indicators covers risk management, the MPF’s financial performance (proxy for pace design and implementation of activities), integration of cross-cutting issues such as gender and conflict, donor engagement and inclusion etc. The output is scored A. Out of a total of four indicators, one has exceeded the milestone, two have met expectations and one underperformed.

  1. Implementation of an effective MPF wide approach to risk management
The MPF relies on the Bank’s apparatus and policies and procedures for managing fiduciary and other risks related to implementing the Fund’s projects. The Bank used to coordinate its approach to mitigating risks along with approaches of administrators of other Trust Fund Windows in Somalia through the Joint Risk Management Strategy (JRMS) forum. However due to a lack of quorum from other fund managers and donors this group has not been effective. Instead the WB has commissioned a review of how it manages risk from Abrynt (the Third-Party Monitoring Agent), which has been discussed across the MPF portfolio and with donors. The review assessed various types of risks and is discussed in more detail in the risk section of this AR.
  1. MPF disbursement and commitment ratios of signed project grants (signed more than 4 months prior to the end of the calendar year
The MPF’s annual disbursements have persistently increased since the start of the trust fund, as have commitments which demonstrates that the trust fund is getting much better at planning activities and implementing these.

  1. Consultation and transparency
Consultation between the WB and the donors has improved and is testing different approaches to ensure that meetings are targeted and useful for both donors and the WB. During the review period there have been two meeting along with the Minister of Finance. The most recent one took place just before the Spring meetings and was a very useful opportunity for donors to raise their concerns over the deteriorating relation between the FGS and the International Community as well as between the FGS and FMS. The Minister was made aware that his role should stretch more than achieving technical reform, but also incentivise dialogue and cooperation across State entities.
Monthly consultative group meetings have continued although their content and structure have not always been conducive to constructive dialogue between WB and donors. In May this year DFID organised a meeting with Donors to explore options for making meetings more useful to both sides. In response to our requests the Donors have re-instated the project-level focal point system whereby appointed focal points will reach out to Task Team Leaders (TTLs) for technical updates, while consultative group meetings will focus at a portfolio level, focusing the discussion on lessons learned, priorities looking forward and delivery options.
Finally, on transparency, the WB does publish all publicly available documents on the MPF website. Where there have been delays in sharing these (e.g. the high-frequency survey results) this is usually due to delays in Government approval. On more internal analytical pieces such as those produced by Abrynt, the Bank has been slower than in previous years to share. This is something the Donors have raised with the WB and await a response.

  1. MPF portfolio is gender and conflict sensitive
The MPF projects and analytic activities are reviewed and assessed by the Bank to systematically consider and address gender inequalities. The WB is currently undertaking a safeguarding assessment of all its projects.

Lessons identified this year, and recommendations for the year ahead linked to this output

Consultations with donors have significantly increased since the last AR both in terms of frequency and quality. Making consultations more focussed and action oriented should be a focus. There have been improvements in flow of information and more efforts are needed on the part of the Bank in coordinating efforts with other relevant programmes on the ground. Key recommendations for the year ahead:

1. DFID will continue engaging in consultative group discussion in a meaningful way. Use key opportunities to contribute and shape the future of the WB portfolio in Somalia. Upcoming opportunities include: The Mid-Term Review of the MPF (happening in July). For the purposes of IDA reengagement, the results of these discussions will be consolidated into an internal document, the Performance and Learning Review (PLR), that will be presented to the Board for endorsement. The PLR will update the Country Partnership Framework that was endorsed last year. The Bank could also consider organising consultative group meetings around thematic clusters.
2. DFID will continue discussions internally to define which of our business planning priorities can be best achieved through working with WB either through direct funding (through MPF) or through side funding (e.g. EFO).
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year

The SERs programme was designed on the assumption that Somalia’s low level of income and wide-spread poverty is down to low levels of investment. This, in turn, is due to a dysfunctional state, weak governance, poor security, unregulated private sector, low-level of human capital, and inefficient financial intermediation. The programme assumes that a capable and well-functioning state is the single most important precursor to Somalia’s economic stability and prosperity.

The results chain and key assumptions depicted in the diagram below illustrate how activities related to: (i) improved core state functions, (ii) public finance management, (iii) capacity building for economic policy formulation and implementation. (iv) enhanced public institutions for enforcement of laws and regulations, and (v) better ability of the private sector will contribute to the objectives of increasing domestic resource mobilisation, investment, income generation, and creation of more and better jobs. Whilst there is evidence that capable and well-functioning states are needed to underpin economic progress, there is insufficient sector level evidence to take a firm view on prioritisation and sequencing of activities, the M&E&L section provides recommendations on how to strengthen this.

SERs Theory of change (from 2017 business case extension)

In April last year, the WB completed its first Systematic Country Diagnostic (SCD) for Somalia which presents a more dynamic understanding of the constraints facing development in Somalia. The SCD refers to a “dual development trap” that links the difficulties facing institutional development with the additional vulnerability Somalia faces due to natural disasters, trade and geopolitical shocks, which all contribute to a constant undoing of development gains, further deepening exclusion. This helps to untangle some of the complex assumptions linking institutional reform to effective states (outputs 1 and 2) and socio-economic recovery in a context of consistent external shocks exacerbating vulnerability and exclusion.

Firstly, the SCD identifies a fragility trap whereby a lack of trust in state institutions (driven by a historical absence of trust in formal institutions, exacerbated by conflict, and endemic corruption), undermines reform efforts resulting in inadequate political solutions and financial decisions further weakening public confidence. For many state and non-state actors there is a vested interest in continued institutional weakness, which constantly works to undermines reform efforts. Understanding these interests is essential to enable sustained reforms in public finance accountability and transparency. But also, directly contributing to a greater sense of trust through dialogue is critical to reinforce and strengthen institutional reform efforts.

In parallel, a resilience trap in which natural disasters, and trade or geopolitical shocks, undo development gains and deepen exclusion. This cycle is evident in the pattern of droughts and floods that severely damage rural livelihoods, impacting the most vulnerable, and generating high levels of forced displacement and unplanned urbanization. Given the absence of a reliable and targeted shock-absorptive safety net, single shocks can impact huge numbers of people, sustaining high levels of poverty and shifting the burden to humanitarian agencies. The need to address the structural drivers of vulnerability is becoming more urgent as climatic shocks intensify.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Key to the success of a portfolio approach such as this one is a strong theory of change and framework with which to verify and test results. This approach leans heavily on output and outcome measures that are not best placed to tell the story of whether interventions are helping to unlock elements of the development trap that Somalia finds itself in.

There is also a gap in monitoring the assumptions which is putting achievement of outcome level goals at risk. The WB is operating at an operational level, not always engaging in policy discussion. If we also assume that this is happening and being effective, when actually it is not, we risk not achieving outcomes.

Based on the indicators at impact and outcome level, the programmes appear to be on track, with all of the milestones for December 2018 either achieved or over achieved (except for GDP growth, which at 6% is unrealistic given persistent droughts and dependence on agriculture). However, this does not give us an accurate sense of actual change or progress towards credible institutions or a more resilient economy. Future programming should provide a clear articulation (perhaps in diagrammatic form) of the outcomes to be achieved rather than solely focus on the outputs delivered. This could potentially include more qualitative beneficiary feedback on the result of interventions.

Impact	Milestone / (Dec 2018)	Progress
I.1. Nominal GDP per annum ($, current prices)	US$6.8 bn	US$ 7.4 bn / (IMF projections)
I.2. Real GDP growth per annum, % [new indicator Oct 2016]	6.0%	3.1% / (IMF projections)
I.3. Nominal value of domestic revenue collection at federal and regional member state level ($, current prices)	US $139.99m	US $183.4m
Outcomes
O.1. Government demonstrates progress on key governance reforms and benchmarks, as demonstrated by achievement of an increased % of RCRF annual review benchmarks.	70%	100% - 12 of 12 RCRF benchmarks met
O.2. Federal government demonstrates improved fiscal discipline, revenue generation and cash management, as evidenced by more regular salary payments. / (i) # of months of civil service salary payments outstanding at the end of year / (ii) average days between payments during year	(i) 2 / (ii) 35	(i)0 / (ii)29
O.3. Increased uptake of Financial Governance Committee (FGC) recommendations. / (i) # of contracts/concessions reviewed by FGC (cumulative). / (ii) increased # / % of FGC confidential assessments with evidence of FGC recommendations being implemented (Cumulative)	(i)27 / (ii) 18	i) 35 / ii) 26 / 74%

Explain major changes to the logframe in the past year
No changes made

Describe any planned changes to the logframe as a result of this review

At outcome level:
1. Broaden the scope beyond PFM (wage bill, fiscal credibility and contracts oversight) to include indicators that reflect credibility of institutions, progress towards the critical federal questions such as revenue sharing and resource sharing and trust in institutions possible through perception survey.
2. Explore options for shifting measures for economic recovery beyond jobs, to include measures of economic inclusion and strengthened resilience.
At output level:
1. Remove output indicators for components that no longer exist and update all output indicators according to the WB results framework (removing those that are no longer monitored).
2. Consider introducing an additional output monitoring progress under the Urban agenda and merge the civil service reform into the first output.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The MPF has provided a mechanism to pool donor resources and coordinate policy dialogue across donors with the Government. On the former, the MPF has continued to provide VfM by attracting resources from eleven donors (with new financing agreements signed with Norway, Germany, Sweden, Switzerland). Pooling resources has effectively reduced fragmentation of donor efforts. The MPF has also been helpful in supporting coordination between the partners working with Government or within Somalia’s private sector. In some cases, strong partnerships have been forged that have led to the development of joint/ synergised policy/programming work, notably on SCALED UP and FIDEP.

On effectiveness the MPF has achieved progress on the state-building agenda, particularly in building the systems able to process payment of civil salary wages through country systems. There has also been important progress on building the institutions to regulate Somalia’s critical financial sector., work on mapping out investments in urban areas to stimulate urban economies However given the breadth of the Fund’s focus and its expansive activities, it is difficult to aggregate the Fund’s impact and develop a meaningful unit cost indicator to represent the Fund’s portfolio, especially given the lack of meaningful comparators. In terms of internal measures, the WB’s internal project-level scores find that 100 % of active operations have been rated moderately satisfactory or higher.

On economy, VfM is demonstrated if fees are recovered by investment income and remain comparable to other administrative fees charged by multilaterals. In the respect the Investment income from the MPF ($5.6 million) has nearly netted out the total fees paid by donors ($5.7 million). As of April 2019, investment income is expected to exceed fees in coming months based on the pace of accumulated interest. In addition, the MPF continues to achieve economies of scale by investing in services at the fund level, such as the monitoring agent and security and logistics platform.

Efficiency is measured by the Funds disbursement ratio which has improved by 17% in 2018 compared with 2017. US$75.7m was disbursed in 2018 against $64.7m in 2017. Disbursement ratios of signed projects have also improved, reaching 75% in 2018 (or 62% not including the RCRF) compared with 73% in 2017 (or 58% not including the RCRF). This demonstrates an improvement particularly for the RCRF which represents the bulk of MPF payments.

Finally, on equity, the fiscal transfer component of the MPF, although relatively small at this stage, has helped in progressing equity considerations, especially the MPF’s outreach to different Member States of Somalia. Fiscal transfers to the regions have scaled-up significantly through WB resources (RCRF and Surge support) from US% 6.7m in 2017 to US$11.8m in 2018, representing a 75% increase. But has not resulted in a more equitable distribution between FMS. Access to civil service jobs for women is being monitored through the CIP component, while still low, women recruits to civil service posts reached 26% in Puntland.

E: RISK (½ to 1 page)

Overview of programme risk and mitigation
Overall, we assess the risk as major. Operational, reputational, financial and political factors inhibit achievement of project purpose in this highly fragile context in which this programme operates. Enhanced controls applied to the management of this programme have worked to bring the overall level of risk down. Some of the key control measures include (e.g. third-party monitoring, RCRF payment on reimbursable, monthly donor consultation groups where administrative agreements are discussed as well as risk mitigation). Overall risk rating: Major

Overview of programme risk

DFID used to maintain a risk matrix specific to SERs, however given that many of the risks are those identified in the DFID Somalia portfolio-whole risk matrix, the two were merged. DFID used to be an active member of the Multi-Partner Risk Working Group led by the WB and the UN. However due to a lack of quorum from the donors, this group has not met since mid-2017. Despite a request from DFID to re-establish the group, once again there was a lack of availability from other donors. Along with the mid-term review the WB has agreed to discuss how to take forward the recommendations from the TPMA’s risk assessment and incorporate into monthly Consultative Group meetings. A summary of these are below.

At project-level. The report finds that: on average MPF projects outperform global programmes implemented by the WB in terms of implementation and progress towards development project objectives; and despite higher risk ratings, fewer problems are reported in the Somalia portfolio than compared to Africa portfolio. The fiduciary risk of both project financing and financing directly through Government systems is managed through policy design and tight structures and systems in place. In addition, ex-post reviews of transactions have been used to identify issues with project expenditure, demanding repayment from government where necessary, but also identifying areas in need of improvement.

At a portfolio level the report highlights four other types of risks:
- Delivery risk, given WB standard procedures and the shift away from strategic design to managing fund flows once projects move to implementation. The WB’s institutional constraint to continue policy dialogue during implementation is particularly risky in a difficult and complex environment such as Somalia. In some cases, projects have found ways of actively engaging with delivery, actively guiding and advising government on the implementation of programmes. But this is not standardised across projects and not always addressed.
- Dependency risk – as in not making the most of the positive impact projects can have on another – this is most relevant institutional development projects.
- Physical infrastructure projects. The institutional risk is currently managed through PIUs and tight controls, but procurement procedures have presented challenges, which will only increase as projects go to larger scale. Issues include verifying business information, track records and ownership, as well as environmental and social risks as Government frameworks are insufficient
- Expanding scope of social protection. Comes with heightened risks also: limited data to monitor discrimination and long-run conflict and violence impacting behaviour, and minima public trust in state mechanisms for addressing grievances, especially for issues of sexual exploitation and gender-based violence.

Recommendations from the TPM risk assessment report:
- Further strengthen front-line risk management by focusing on delivery risk and dependencies – this means even more portfolio level management. Two new positions to the WB country team should help bridge this analysis – A senior Governance and Economic Adviser.
- Mitigate residual institutional and technical risks, by considering how to strengthen government change management capacity at portfolio level and using prior-reviews to support active involvement and quality assurance of implementation.
- Stepped-up knowledge production and dissemination. In the case of Somalia, it should be a higher priority than elsewhere to produce codifiable knowledge. The report recommends building in an analytical component into each project and encourage multiple depositories and dissemination channels.

Outstanding actions from risk assessment
Ensure safeguarding is embedded in risk work by December 2019

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)
The total budget for SERS programme is £69.4m, of which £57.4m has been spent to date, equivalent to 82.7% of the total business case approved budget. The budget is made up of contributions to two trust funds: £64.4m for the World Bank multi-partner fund and £5m for the IFC trust fund. The total spend during the review period is (July 2018 to June 2019) is £13.7m. Forecast spending is on track with £5m due for release in June 2019. Overall, the financial management has been satisfactory to date with accurate forecasts being met. The final payment from the SERs programme will be made in March 2020. The programme is on track to fully execute its budget for the review period. The breakdown of spend by component during the review period is as follows:
Component	Description	Partner	Budget June 2018-2019	Spend to-date
204313-102	World Bank Multi Partner Fund for Somalia	World Bank	10,000,000	5,000,000
204313-103	Safer Corridor Initiative to Support Remittances flows to Somalia	World Bank	704,759	704,759
204313-105	International Finance Corporation (IFC) Trust Fund	IFC	3,000,000	3,000,000
			13,704,759	8,704,759

As at end May 2019 donors have pledged a total of $448.6 million and paid in a total of $335.2m, of which 90% has already been committed to fund various projects and 70% ($234.4m) already disbursed. DFID has pledged a total of $96.2 million making the UK the second largest contributor of which $83.5m (87%) has already been disbursed.

Most of MPF funds are spent through project grants of which 84% or $226.3m are executed by the Government through WB Project Implementation Units following strict WB rules and yet only 7% of committed funds are held for project preparation supervision and the monitoring agent. In contrast only 7% of grants are Bank Executed and used to meet objectives specifically by the WB. This is consistent with the findings from the earlier risk section of the shift away from strategic design to managing fund flows once projects move to implementation.

Quality of financial management
World Bank provides six monthly reports which are accessed through the World Bank portal and are used to compare actual spend against the planned spend. A statement of assurance was completed for the MPF in February this year, which found that although the risks remained high, the WB was making progress to strengthen the Governments Systems through which the majority of the MPF funds are executed. The recommendation from the recent due diligence carried out in March 2019 indicated that online financial reports are not updated in real-time with the commitments made and hence affecting reliance on the same for DFID internal reporting on the project. DFID will in future remind WB to share these and where relevant discuss to encourage take-up at programme level.

The WB has taken measure to ensure good financial management. These include: regular financial management supervision missions, use of externally staffed External Assistance Fiduciary Services (EAFS) to prepare withdrawal applications, reimbursements and procurements, fund held in separate designated account in central bank and risk unit review payments and risk level on regular basis.

Advance thresholds are based on risk assessments. Expenditures are deemed eligible for reimbursement based on actual amounts expensed. Use of external audit firm to conduct audits has led to better transparency. WB has also shared with us the last audit received in October 2018.Finally there have been no exchange rate risks given we disburse funds in pounds as set out on DFID systems.

Date of last narrative financial report(s)	June 2018 - Vault Number 32329827
Date of last audited annual statement (s)	September 2017 No particular issues raised in this audit statements

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring
DFID directly engages with the Bank at different levels, including through:
- DFID Somalia’s Senior Leadership Group, to shape the strategic focus as well as performance of the Fund. For example, two meetings have been held bringing Senior Leadership Teams from WB and DFID and key programme leads to discuss the WB CPF and future direction given IDA.
- MPF Consultative Group Meetings (some involving the Somali government), organised by the Bank around the MTRs of the various MPF projects and the WBG’s SCD and CPF.
- Focal points at the project level to cover technical areas of the portfolio, and in some case thematic working groups such as the Health Group, led by the WB that brings together the various donors working on Health.

The MPF’s results are measured through a compilation of indicators drawn from project-level reporting by the Bank. The results framework distinguishes two levels of indicators in line with standard World Bank procedures: Project Development Objective (PDO) level indicators and Intermediate Indicators. The former tends to be more outcome focused, while the latter are often related to outputs. The Fund’s operational performance is measured through indicators measuring operational and organizational efficiency and effectiveness such as those included in Output 4 of the DFID Logframe.

More could be done to improve the quality of the indicators that are being measured. For example, it is not enough to monitor jobs created without an understanding of what a quality job is, are these truly additional, sustainable and who is benefitting. The key issues such as economic marginalisation and gender are not readily monitored in a meaningful way. With a deeper understanding of the dynamics that contribute towards marginalisation, it could then be possible to define indicators that measure change in these dynamics, and a sense of progress towards overall outcomes. Similarly, there should be some attempt to ensure activities and achievement of outputs is not leading to harm and say more entrenched marginalisation.

Systematic reporting requirements are also in place to monitor financial management, quality, progress and risks. The financial information related to the MPF can be accessed through the Bank’s Clients’ Page, including periodic audit statements. The Bank provides detailed annual progress reports setting out areas of achievements, challenges and emerging priorities.

MPF uses an external third-party monitor to complement the Bank’s internal supervision of the MPF projects. The agent is directed to report on how MPF funds are executed by the Somali authorities, confirm utilization for the purposes specified in MPF grant agreements, and monitors the flow of MPF funds from the World Bank through the government systems. The monitoring agent also advises the World Bank on trends, developments, and emerging issues that relate to the MPF portfolio.

Evidence
The WB does have a knowledge production component which has been used to provide the High-frequency survey covering key socio-economic indicators for Somalia. While hugely important to further our collective understanding of the context and state of development in Somalia, the WB has been very slow to secure approval from the Government and release results.

In addition, the TPM is commissioned on a quarterly basis to provided discrete analytical pieces, such as the risk assessment report covered in the risk section. In the period under review most of these reports have been used to advice internal WB operations and have not been shared publicly. As the risk report recommends - knowledge production and dissemination should be a higher priority and an analytical component should be included in every project.

A greater focus on monitoring and evaluation would make an important contribution to the fairly weak body of evidence of the context and development initiatives in Somalia. In some cases, such as with Private Sector Development initiatives, greater monitoring and evaluation capacity would have strengthened the weight of the evidence produced, for example the reliability of jobs numbers, and provided insights into relative impact in terms of productivity and added value of the elements of support provided i.e. TA, BDS, grant.

Learning
There have been dissemination events to share learning from TPM reports, but more could be done to discuss learnings with donors, but also to ensure that learnings are internalised into project design. In some cases, there has been evidence of shifting project implementation according to learnings, for example, a second round of grants from SCORE did not go ahead because it was identified that others, such as USAID’s GEEL and DFID’s PIMS were delivering strong projects in this space, and that the Bank’s comparative advantage was in providing policy and regulatory support.

Lessons identified this year, and recommendations for the year ahead linked to this output
DFID will work with the WB project-level team to build on their evidence work. Generating evidence will also be built into conversation about future collaboration as a potential opportunity where DFID and WB can work more closely together.

Progress on recommendations from previous reviews (1/2 page)

Recommendation	Status
Strategic
Engage with the Bank on improved coordination with new sources of funding and instruments in Somalia, in particular PACF, EU budget support and funding from non-traditional donors (Turkey, Qatar, UAE and Saudi Arabia) offers opportunities as well as risks surrounding (a) absorption capacity, (b) sustainability, (c) alignment of spending with RRF priorities and (d) fiscal transfers to FMS and to Somaliland, Somalia’s region with aspiration to be an independent country not recognised by the international community.	Ongoing. Discussion have ben held throughout the year.
Engage with the WB’s planned Public Expenditure Review, to support Government make fiscally sound public expenditure decisions, support fiscal federalism, manage expansion of service delivery	DFID has met with lead Governance Adviser to discuss
Engage with the Bank in providing thought leadership and coordination of the policy dialogue with the Somali government	DFID has participated in two WB /Donor meetings with MoF
include non-traditional donors in policy coordination and dialogue	Qatar was involved in WB meeting with MoF
DFID should increase its focus on developing the path towards concessional financing for private sector development e.g. from IFC and CDC	In progress
DFID will need to consider how to engage with the WBG in a new context of PACF	DFID has met with WB Country Rep and TTLs to discuss future priorities
Operational
DFID to agree on three to five top strategic and operational objectives to be pursued through funding through the MPF and continue holding periodic (six weekly) structured internal discussions to monitor progress against the agreed objectives, identify challenges and opportunities, and agree on approach for tackling identified challenges.	Those reflected in logframe
DFID should continue to contribute to strategic discussion over the design of the “Surge” additional financing component of the RCRF	DFID provided comments on RCRF II PAD, fed in concerns to UKDel ahead of WB Board discussion
DFID should continue to engage with the WBG to build on recommendations of the Bank’s MTR of the SCORE project to strengthen the project’s focus around supporting systemic changes, especially for scaling up financial access as a means for strengthening economic recovery	DFID has maintained dialogue on design of new programme SCALED-UP
DFID to continue to provide technical leadership to donors in engaging with the Bank and IFC and agree on the division of roles and responsibilities between the Bank, IFC and other actors (e.g. IMF and market development programmes) in financial sector development.	In progress