Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Aitebaar / Peacebuilding Support to the Post Crisis Needs Assessment programme (PSP)
Programme Value: £24.78m / (Incpetion: £4.1 + Implementation: £20.68)		Review Date: October 2014
Programme Code: / 202368	Start Date: / October 2012	End Date: / December 2016

Summary of Programme Performance

Year	2013	2014
Programme Score	B	B
Risk Rating	High	High

Summary of progress and lessons learnt since last review

Aitebaar scored a ‘B’ in its 2013 Annual Review (AR). That review concluded that progress against the logframe was not as advanced as expected and that intensive in-country programme leadership and management would be required by Coffey International Development to ensure that the programme delivered. The AR specifically recommended that a Performance Improvement Plan (PIP) be put in place for six months to oversee remedial activities.

It is clear that the time invested from both parties in the PIP has delivered significant dividends. The progress made in the past six months has been extremely impressive. Significant improvements in recruitment, staffing, leadership and management have resulted in far more robust structures, systems, processes and direction. The staff retained and newly recruited are motivated, high quality and delivery focused. It is clear that the existing programme team is now more than capable of delivering against the agreed milestones.

However, despite the significant improvements the limited number of logframe indicators ‘met’ means that it was not possible to score the programme higher than another ‘B’. There are numerous reasons for this which constitute lessons from this AR process, and which merit further discussion between DFID and Coffey. This is not unduly problematic, as it is clear that the programme now has a far more robust likelihood of success as a result of the firmer foundations upon which it is based. However, there is a clear need for both Coffey and DFID to now focus on swiftly agreeing a revised logframe with appropriately worded, realistic and attributable milestones with accompanying clear means of verification. This logframe should be based on an updated theory of change (ToC) which identifies programme outputs, outcomes and impact along with clear causal pathways connecting these. Next year’s payment milestones should be drawn from the revised logframe and agreed by all parties before the end of the calendar year. The process for developing this logframe provides an opportunity to secure collective buy-in to the programme from the large number of Aitebaar staff recruited in the past year.

In summary, despite the overall score not changing, the significant improvements made internally over the past twelve months should not be underestimated. Both DFID and the Aitebaar team deserve a huge amount of credit for what has been achieved in a relatively short space of time. The programme now has a far more robust leadership and management platform upon which to deliver its objectives, and after a difficult year, there is now a need to keep it simple, do the basics, and focus on delivery. We are confident that, should the necessary revisions be made to the logframe, the programme will demonstrate improved performance at its next formal assessment.

Summary of key recommendations for the next year:

- Aitebaar team to facilitate a collective all-staff revision of the programme’s Theory of Change and agree with DFID by 15 December 2014.
- Aitebaar team to facilitate a collective all-staff revision of the programme’s logframe based on the Theory of Change and agree with DFID by 01 January 2015.
- Logframe revision should generate collective agreement between Aitebaar and DFID on sources of independent means of verification to avoid over-reliance on programme generated data. These MoVs will need careful consideration to ensure that data is available and aligned with future AR processes.
- As part of the logframe review, the Aitebaar team should consider developing a detailed meta-data sheet, to include methodology notes for all results lines of the programme.
- In light of the revised theory of change and logframe, a revised and functional VFM strategy needs to be devised and implemented to enable VFM to be assessed, at outcome level at a minimum.
- In light of the difficulties in accessing beneficiaries, consideration should be given to conducting a third party impact assessment carried out prior to the next annual review. This process should be directly contracted by DFID with ToRs which reflect the revised theory of change, logframe and VFM strategy.
- The programme should continue to expand as planned into Nowshera district, though prior to any further expansion, careful consideration should be given to appropriate adaptation of the model police unit concept, which may be better suited to urban, middle-income environments. Stronger partnership with other implementing agencies (particularly UNDP) will be required as the programme expands and the AR team would expect to see significant progress on this by next review point.
- Despite the challenges DFID has encountered with Aitebaar performance to date (suggesting the original programme design was overly ambitious) the AR team feels DFID should continue to engage across the ‘criminal justice chain’ in KP (police, investigations, prosecutions, corrections, alternative dispute resolution), particularly as there are good opportunities deliver tangible results in the latter two sub-sectors
- Coffey to continue to improve consortia management by rationalising the shape of their current consortia / delivery / steering partner set up to ensure relevant organisations are being used in ways that best meets programme needs.
- Aitebaar’s policy work could be one of the most important legacies of the programme but currently appears under-resourced (e.g. behind schedule delivery of milestones, much deeper and broader consultation needed to translate policies into institutional reform). Coffey to consider whether a Criminal Justice Policy Adviser is required.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202368/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202368/

Outline of the programme

The Peacebuilding Support Programme (PSP) or Aitebaar (meaning ‘trust’ in Urdu and Pashto) is supporting the Government of Khyber Pakhtunkhwa (GoKP) to implement its peacebuilding strategy based on the 2010 Post Crisis Needs Assessment (PCNA) for the province and the Federally Administered Tribal Areas of Pakistan (FATA).

The programme focuses on strengthening both civil security (police, prosecutions and correctional services) and the formal and informal justice sectors in Khyber Pakhtunkhwa (KP) province in ways that will make these institutions more accountable and responsive to citizens. Aitebaar is designed to complement DFID’s multilateral support to the PCNA being provided through the Multi-Donor Trust Fund (MDTF). Whilst Aitebaar was also intended to support local governance and security and justice needs in the Federally Administered Tribal Areas of Pakistan (FATA), this was subsequently amended when this element of the programme (Output 1) was placed on hold in 2013. The review team found no cause to reassess this decision over the course of the 2014 Annual Review.

Aitebaar / PSP aims to increase levels of citizen satisfaction with governance, security and justice provision in three districts of KP. The theory of change for the programme is that this, in turn, will boost trust in the state and thereby create a context for better governance, greater stability and poverty reduction. Whilst this broad theory of change remains extant, as noted in the recommendations, there is a need to review the Theory of Change to ensure greater clarity between the different causal pathways, spell out the assumptions for every level and cite evidence (or lack of it) relating to each causal pathway.

The contract for Aitebaar / PSP was awarded to Coffey International Development and the inception phase began in October 2012 with £4.1m support and was scheduled to end in April 2013. Coffey established the programme administration and logistics, recruited staff, designed ten projects for the three programme Outputs and the programme’s Research, Monitoring & Evaluation (RME) component, and worked on delivering 25 milestones. In a bid to strengthen engagement with the GoKP and to mitigate delays arising from recruiting key staff, DFID approved a no-cost extension up to the 31 July 2013 for the inception phase.

The implementation phase began on the 1 August 2013 with £20.68m support. Due to Output 1 relating to FATA being on hold and contract negotiations on overall budget for KP, Coffey reduced the implementation budget by £5.1m.

Implementation is divided into two phases: the first 15 month phase (1 August 2013 - October 2014), focused on implementation in Peshawar and the second 26 month phase (November 2014 - 31 December 2016) will extend the programme into two other KP districts (to be mutually agreed with GoKP). This phase is scheduled to end 31 December 2016. During Aitebaar’s first phase, it focused on two outputs plus work on research, monitoring and evaluation.:

Output 2,
Strengthened rule of law (security and justice) provision in Peshawar through:
(a) Strengthening Police Investigations Capacity
(b) Police Prosecutions
(c) Gender Responsive Policing
(d) Community Policing
(e) Strengthening Correctional Services
(f) Alternative Dispute Resolution

Output 3
Increased and effective engagement between citizens and the state through:
1. Awareness Raising
2. Government Citizen Engagement

Research, Monitoring and Evaluation

This Annual Review (AR) covers the second stage of the programme (October 2013 - October 2014) and assesses progress against the April 2014 revised log frame agreed between DFID and Coffey. There have been subsequent discussions between Aitebaar and DFID regarding revisions to some of the means of verification (MoVs) over summer 2014, which where relevant, have been incorporated into the progress assessment.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Aitebaar scored a ‘B’ in its 2013 Annual review (AR). That review concluded that progress against the logframe was not as advanced as expected and that intensive in-country programme leadership and management would be required by Coffey International Development to ensure that the programme delivers. The AR specifically recommended that a Performance Improvement Programme (PIP) be put in place for six months to oversee remedial activities. The four objectives of the PIP were to; 1). Strengthen the focus on the programme’s core objectives and log frame; 2). Significantly strengthen programme leadership and management; 3). Improve external engagement (including consortium partners and other agencies active in the KP rule of law sector; and 4). Achieve full integration of the programme (across projects and outputs, as well as between local / district / provincial and federal levels).

It is clear that the PIP process, and the subsequent transition to a Performance Improvement Agreement (PIA) was management and resource intensive for both Coffey and DFID, but the time invested by both parties has delivered significant dividends. For almost six months of the AR year Aitebaar continued to operate under previous leadership, but the progress made in the past six months has been extremely impressive. Significant improvements in recruitment, staffing, leadership and management have resulted in far more robust structures, systems, processes and direction. The staff retained and newly recruited are motivated, high quality and delivery focused. The recommendations of the 2013 AR have been largely delivered, and the AR team are pleased to confirm that procurement processes, asset management, and risk monitoring and mitigation structures follow best international practices and DFID principles. The Overseas Security and Justice Assessment (OSJA) accompanying the programme is one of the most comprehensive that the AR team have encountered to date, and its mitigating measures, whilst still in the process of being tested, appear sensible with appropriate divisions of responsibility, if a little slow to implement. Consortium relationships have also improved, with those partners we consulted now far clearer of their various roles, and the contribution they can make both to specific programme delivery, and where relevant, to the wider strategic direction of the programme. The newly developed Research Implementation Unit has put together a comprehensive strategy to generate evidence which will feed into the programme design. In summary, structurally progress has been nothing short of remarkable against the 2013 AR baseline, and it is clear that the existing programme team is now more than capable of delivering against the milestones set.

However, despite the significant improvements in leadership, management, structures and systems, facilitated by the PIP and PIA processes, and whilst significant progress has been made since the summer on delivery, the limited number of logframe indicators ‘met’ means that it was not possible to score the programme higher than another ‘B’. There are numerous reasons for this which constitute lessons from this AR process, and which merit further discussion between DFID and Coffey.

Firstly the timing of this annual review was unfortunate in that it was conducted several weeks before many of the milestone delivery dates were due (31st October). Whilst DFID is corporately understandably reluctant to allow annual reviews to be continually postponed, particularly for programmes deemed to be ‘under-performing’, it will be important for the timings of subsequent annual reviews to be coordinated with future milestone delivery dates.

Secondly, the AR team were hampered by the absence of key MOV data to assess particular deliverables, the majority of which are due to be generated by the programme itself via its Knowledge, Attitudes & Practices Survey (KAP) and Citizens Report Card (CRC) processes. It will be important as the programme moves forward to reduce the over-reliance upon internally generated MOV data as the primary means of assessment, and ensure that where this data remains appropriate, that it is generated in advance of the annual review process. There is strong potential to use existing data from credible secondary data sources to monitor programme performance, particularly at the outcome and impact levels. Using secondary data sources will help rationalise the programme monitoring and transaction costs. Cutting down some of the surveys will result in cost savings and free up Aitebaar staff time . We have suggested some alternative means of verification, but these should be explored more substantively as part of the logframe refresh process and agreed between Coffey and DFID without delay.

Thirdly, the majority of the indicators at all levels of the logframe seem composite and verbose which, when combined with the challenges listed above, created a source of ambiguity and confusion for the review team to evaluate performance. There are inconsistencies in what the indicators aim to measure and their corresponding milestones which make it difficult to ascertain progress. Additionally, the logframe suffers from fundamental structural issues: it has only two outputs with up to 11 indicators underneath each. The current structure of the logframe makes the programme vulnerable to the programme rating system. By distributing the impact weighting between only two outputs, if one outputs is not achieved, it undermines the overall rating of the entire programme and may not completely reflect wider successes. The high number of indicators under each output makes it difficult to ascertain the contribution of that particular deliverable to the achievement of programme’s intended outcome.

Finally, our discussions with the Aitebaar team also revealed that the logframe and payment milestones are not always fully aligned, which also contributes why some of the logframe indicators not being met. Payment milestones are explored further below.

Despite these process issues however, the AR team conclude that one unintended consequence of the PIP and PIA process, combined with the decision to proceed with payment milestone based contract, has been that the time invested in securing the significant leadership and management improvements has been at the temporary opportunity cost of programme delivery focus. The review team encountered some confusion during the review period in which it was not always clear which version of the logframe various output leads were reporting against. However even in instances in which ambition had been lowered from previous milestones, the revised deliverable had not always been met. As a general rule, those indicators that were entirely within the ambit of the programme to deliver (training, publications, infrastructure etc.) were achieved, and those that relied upon others to play a role were less successful.

Nonetheless, it is clear that the programme now has a much higher likelihood of success as a result of the firmer foundations upon which it is based. There is a clear need for both Coffey and DFID to rapidly agree a revised logframe with appropriately worded, realistic and attributable milestones and accompanying clear means of verification. This logframe should be based on an updated theory of change (ToC) which identifies programme outputs, outcomes and impact along with clear causal pathways connecting these. The ToC’s underlying assumptions should be clearly set out at all levels. We strongly recommend that this process is undertaken in as consultative a manner as possible within the Aitebaar programme, to ensure that staff are aware of their deliverables, how their workplans relate to the outcomes for which they are responsible, and how they ensure that the outputs which require external stakeholders to deliver can be planned for sufficiently far in advance of the milestone delivery dates. Many output leads have clear ideas as to what their outputs should constitute and their contribution to this process would be highly beneficial. Finally, it will be important that the work undertaken to support wider processes not currently captured in the logframe (Rule of Law Working Group support etc.) is either incorporated into the revision process or deprioritised. Some suggestions for what should be included within the revised logframe, and the balance of effort between various components can be found later in this document. Broadly there is a need to disaggregate between activities with an institutional reform / policy focus, those which facilitate more effective and expanded delivery of security and justice services, and those aimed at building trust between the Government and its citizens. Limiting the number of outputs to two inadvertently conflated these three areas of activity, and there is a need to address this.

Once the logframe has been revised and approved, DFID and Coffey should agree a set of payment milestones for 2015 which are directly linked to delivery against the revised logframe. This will avoid the distraction from programme delivery experienced in 2014, and align the various occasionally competing management processes (PIP, PIA, Payment Milestones and Logframe) into one unified delivery monitoring mechanism. Mutual clarity of the deliverables will also hopefully improve the level of trust between DFID and Coffey, which has been adversely affected by what has been a difficult reorientation process over the past year. We would strongly suggest that the first milestone is the delivery of the revised theory of change, logframe and suggested milestone payments, and that this should be provided by early January at the latest. The remaining milestone payment criteria should be balanced across the revised output areas and avoid purely chasing ‘targets’. Given that the implicit aim of the Aitebaar programme is to support political change and shifts in cultural mindsets, it will be important that consensus is struck between focusing on the long-term aims of the programme and the need for short-term delivery impact.

In summary, despite the overall score not changing, the significant improvements made internally over the past twelve months should not be underestimated. Both DFID and the Aitebaar team deserve full credit for what has been achieved in a relatively short space of time. Rule of Law programmes are messy, complicated, political and resource intensive, and the likelihood of success in an extremely challenging environment should never be over-estimated. The programme now has a far more robust leadership and management platform upon which to deliver its objectives, and after a difficult year, there is now a need to keep it simple, do the basics, and focus on delivery. We are confident that, should the necessary revisions be made to the logframe, the programme will demonstrate improved performance at its next formal assessment.

Summary of recommendations for the next year

Theory of Change (ToC)
Currently there is lack of clarity in the ToC as to what exactly the interventions are, how they will feed into the outputs, what assumptions must hold true to achieve specific outputs and what is the evidence base to support the causal linkage between outputs and outcomes. The programme would benefit from a more robust ToC which clearly maps out different causal pathways, spells out the assumptions for every level and cites evidence (or lack of it) relating to each causal pathway- this will help develop a more coherent and logical LFA which is underpinned by solid evidence and captures the successes of the programme.

Recommendation:

Aitebaar team to facilitate a collective all-staff revision of the programme’s Theory of Change and agree with DFID by 15 December 2014.

Sub-Recommendations:
- Revise the ToC (using one of DFID’s approved ToC as a reference) in a flow chart format, so it’s consistent with the programme’s results chain. ToC should clearly identify programme outputs, outcomes and impact along with clear causal pathways connecting these. The underlying assumptions should be clearly set out at all levels;
- Cite the evidence (or the lack of) to support the causal pathways in ToC. RIU should focus on areas where evidence in weak;
- The ToC should be revised through a consultative/iterative process along with clear plans from RIU on how to address the evidence gaps.

Logframe Logic & Logframe Structure/Process

The logframe needs a substantial overhaul, and the logical connection between outputs and outcomes needs to be strengthened as part of this process. In the current logframe, it is not clear how the delivery of outputs will result in achievement of programme’s intended outcomes. This links closely to the aforementioned gaps that the proposed Theory of Change (ToC) presents. The logframe suffers from fundamental structural issues also: by having only two outputs with up to 11 indicators underneath each the programme is vulnerable to the programme rating system. The high number of indicators under each output dilutes the weightage of each indicator hence making it difficult to ascertain the contribution of that particular deliverable to the achievement of programme’s intended outcome.

Recommendations:

Aitebaar team to facilitate a collective all-staff revision of the programme’s logframe based on the Theory of Change and agree with DFID by 1 January 2015.

Sub-Recommendations:
- Indicators should be SMART (Specific, Measurable, Attainable, Realistic and Timebound) with clear, realistic and measurable milestones
- Avoid tracking multiple things in one indicator
- Milestones should be consistent with wording of indicators i.e. using numbers when tracking amount and percentages when measuring extent of something.
- Use the right mix of quantitative and qualitative / process-oriented indicators. Process milestones should be clearly set out and appropriate MoVs included.
- Aitebaar team should consider dividing up the logframe into 3-5 outputs instead of just two- the programme should consider general themes around which outputs can be constructed such as (but not limited to): state capacity to deliver security and justice services, accountability of state service providers, state responsiveness, citizen perceptions, community empowerment, communication etc.
- Each of the new outputs should be weighted on the basis of output’s contribution in achievement of outcome
- DFID best practice suggests each output should not have more than 3 indicators. This practice should be adopted when revising the logframe.
- All indicators should have milestones that are disaggregated by gender (and other categories of marginalisation as relevant e.g. youth, minorities) wherever possible.
- The logframe review should also look at the impact, outcome and output statements to ensure they are clear, succinct and capture the breadth of information captured in underlying indicators. For instance the impact statement doesn’t specify which MDGs will be achieved- also it is not clear what ‘Poverty Depth’ means here. Team should explore provincial poverty measures from source such as provincial MDG reports, MICS surveys etc.

Means of Verification

The logframe is heavily reliant on management data coming out of the programme itself. There is potential to use existing data from credible secondary data sources in order to monitor programme performance, particularly at the outcome and impact levels. Using secondary data sources will help rationalise programme monitoring and transaction costs: cutting down some of the surveys will result in cost savings and free up Aitebaar staff. As revealed during the review, MoV related data for several indicators was either delayed or not available Over-reliance on programme-generated data puts DFID at risk of not being able to ensure robust programme management.

Recommendation:

The logframe revision should generate collective agreement between Aitebaar and DFID on sources of independent means of verification to avoid over-reliance on programme generated data. These MoVs will need careful consideration to ensure that data is available and aligned with future AR processes.

Sub-Recommendations:
- The Aitebaar team should thoroughly investigate the pool of credible secondary data available to monitor progress. A case in point is impact level indicator number 2 which currently relies on a programme-administered survey to monitor perceptions of people across the province. This data is available on an annual basis in the Pakistan Standards of Livelihood Measurement (PSLM) Survey published by Pakistan Bureau of Statistics (PBS). Similarly at the outcome level, similar data can be obtained at a district level from PSLM.
- The Aitebaar team should consider credible data sets generated by government systems (such as: PSLM, HIES, Multiple Indicator Cluster Surveys (MICS), Pakistan Demographic and Health Survey (PDHS), National Nutrition Survey, BISP data set, other local or international surveys etc) and present a set of options whereby they can use existing data to monitor progress.

Meta Data

Although the current logframe has explanatory footnotes for some of the indicators, there is no supporting meta-data sheet containing methodology notes for each result line in the programme. Having a supporting meta-data sheet will be very useful for robust programme management and assessing progress in future performance reviews.

Recommendation:

As part of the logframe review, Aitebaar team should consider developing a detailed meta-data sheet. This will have methodology notes for all results lines of the programme.

Sub-recommendation:
- The meta-data should include for all indicators:
  - Clear and concise definitions of all logframe indicators
  - Data collection routines
  - Objectively verifiable means of verification
  - Assumptions (any lags, margins of error in data collection etc)
  - Risks and mitigating strategies if assumptions change or don’t hold true
  - Rationale and trajectory of milestones

Research, Monitoring and Evaluation

Following are some issues for RIU consideration as its research, monitoring and evaluation strategy develops:

Balance in Mix Methods: The current strategy is inclined towards qualitative evidence generation. Moving forward, RIU should consider balancing qualitative with quantitative analysis as it will allow for complex statistical analysis (multivariate regression analysis etc) which will help test the Theory of Change and establish more robust causal linkages.

Alternate data sources: At the moment, RIU is not following a true random-sampling approach in their quantitative surveys (notably KAP) as they do not have access to the latest sampling frame, which prevents them from identifying households in targeted areas. One would expect RIU to investigate alternate sources of data to identify households but annual review discussions revealed no such plans. The Aitebaar team should explore using the BISP data set to identify targeted households - DFID can facilitate Aitebaar in procuring the BISP data set at subsidized rates.

Counterfactual Analysis: Neither the research strategy nor our discussions with RIU revealed any plans for a counter-factual analysis. The Aitebaar programme needs to focus on the scope of impact evaluation-type studies for some of their components which should include a robust counterfactual analysis. This will add to the rigour of the evidence collected by the programme.

Demonstrating wider level outcomes: The programme can benefit from a strong results narrative which can demonstrate the impact of the programme in various areas of intervention. To achieve this, the RIU should consider streamlining the way they measure interventions. A case in point is the way the programme evaluates their training programme. Currently the emphasis is on pre-and post- feedback from trainees along with an assessment of learning 6 months after the trainings. What the RIU needs to focus on is the wider-level behavioural changes in trainees and their organizations (e.g. improved turn-around time for cases, increase in the number of cases resolved etc) as a result of the trainings.

Staffing & Value for Money: RIU has recruited over 20 full time staff, most of whom will be doing field work including qualitative / quantitative data collection. While noting the benefit of an in-house capability, there could be Value For Money (VFM) concerns around the number of people hired. The RIU should work up a resource optimization plan which ensures that all M&E staff are being utilized optimally with stretching yet realistic workloads. This plan will help the team rationalise staff costs and outsource some field research functions (with RIU providing a strategic and quality-assuring role).

Value for Money:

Recommendation:

In light of the revised theory of change and logframe, a revised and functional VFM strategy needs to be devised and implemented. We understand that the nature of the interventions makes inclusion of quantitative measures difficult but it should be ensured that revised measures allow the next annual review to assess and present VFM at least at the output level i.e. where a cost benefit analysis is not possible a cost effectiveness analysis can be carried out.

In light of the difficulties in accessing beneficiaries, consideration should be given to conducting a third party impact assessment carried out prior to the next annual review. This process should be directly contracted by DFID with ToRs which reflect the revised theory of change, logframe and VFM strategy.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Rule of law (justice and security) strengthened in 3 districts of KP.
Output number per LF		1	Output Score	B
Risk:		High	Impact weighting (%):	60%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of model police units (MPU) move to scale and are evaluated.	3 MPUs up and running (all 12 steps) in Peshawar benefitting 150,000 people. 1 model unit assessed.	B / Whilst the AR team was unable to visit any of the three sites, there is evidence that considerable progress has been made in getting the three Model Police Units up and running with several of the twelve step process completed. Considerable work remains to be done to get the policy / SOPs through to final approval and implementation. The final means of verification relates to an assessment report of one model unit. This had not yet been started at the time of the AR. It was noted that the milestone required that 150,000 people in Peshawar were benefitting from the three Units. This is a higher leveI of impact than would be useful and any revision may wish to use the phrase “affording access to 150,000 people”. There may be an opportunity to try and assess the extent to which citizens are benefitting when the citizen report cards (CRCs) and the Knowledge, Attitudes and Practices (KAP) survey are completed.
1.2 Number of disputes settled outside of the formal criminal justice system (CJS) under ADR mechanisms without the need to access the formal CJS (disaggregated by sex, location)	500 disputes (10% of women’s cases) mediated outside formal CJS.	B / To date, 125 people have been trained as mediators. Records so far indicate that eighty cases have been mediated by these people. Whilst the milestone is unmet, there is an expectation that the number of cases will rise with the number of trained mediators in place. It is noted that much of the work undertaken has occurred in recent months and there was inadequate documentation for the review team to be sufficiently reassured this activity is currently ‘doing no harm’ / human rights compliant.
1.3 Percent increase in case diversion / settlement of cases through ADR, which have entered the formal CJS at all levels including police, prosecutions and courts (sex disaggregated data)	10% improvement over baseline	B / Whilst much activity has been undertaken in this area, at the AR, it was noted that the final stage in securing approval of the standard operating procedures was not completed resulting in a delay to establishing the baseline. A policy dialogue on ADR is scheduled.
1.4 Percent of eligible persons granted bail, probation or released on parole (disaggregated by sex, age and location).	10% of eligible persons released on bail and probation from Peshawar Central Jail.	B / A prison census conducted for Aitebaar has indicated that 169 women and children were eligible for release creating a milestone target of 17. Initial indications are this will not be met, although the implementing partner organisation expressed confidence in achieving sixty releases by January 2015. It is noted that the contract for this work only commenced in September 2014 and is due to finish early in 2015. If successful, consideration should be given to collaborating further with the relevant NGO due to its deep experience in this field.
1.5 Number of women applicants to become police officers in KP.	100% increase over baseline in women applicants who have applied through Aitebaar supported interventions.	A++ / The number of applicants in a previous recruitment round was reported to be 69. 245 applications have been made in the latest competition thus exceeding the milestone significantly. Whilst this is to be welcomed, it does raise the issue of how to effectively assess the contribution of Aitebaar activity to the surge in applications. It was noted during the AR that there has been considerable work in this component and that the gender responsive policing plan has been drafted although not yet approved. It would be useful to examine if the applications are coming from across the Province so as to get some idea of how to focus future work. Looking at the extent to which the applications are successful, would seem a natural next step for evaluation.
1.6 Percentage increase in women respondents (having interaction over the last 12 months) who perceive policing services in the MPUs as satisfactory.	3% improvement over baseline.	B / The means of verification is expected to be a report using data from citizen report cards. Although planning has taken place, the report is not yet available. There is some anecdotal evidence of females from other districts coming to the MPUs to access the services now on offer. Aitebaar staff had reservations about the utility of having a baseline increase within the statistical margin of error.
1.7 Percent increase in number of cases transferred to prosecutors by the MPUs that meet prosecutorial guidelines (disaggregated by sex and location).	3% increase over baseline	B / Although the milestone has not yet been met, there was anecdotal evidence of progress in this component with closer police / prosecutor liaison taking place. The baseline has yet to be established due to the relatively recent final drafting of documentation to assist communication between police and prosecutors. It could be expected that evidence of the improved processes might be available before 2015. The indicator highlights the challenge of the current log frame where Aitebaar has devoted effort to supporting the development of GoKP procedures but are then reliant on others to approve and sign off the work. Work on a revised log frame should seek to minimise this risk where possible.
1.8 Percent increase in which offenders are brought to justice passing the model unit’s standards (sex disaggregated data).	3% improvement over baseline for cases prosecuted / compromised through the MPUs and Prosecution Co-ordination Units.	B / The underlying processes that will allow for better communication between police and prosecutors have largely been completed with the draft SOPs awaiting final authorisation and notification to the relevant organisations. The final steps to bring this about should take place in the near future allowing data to be produced to create a baseline on which to assess the application of the new guidelines.
1.9 Number of people engaged in community policing initiatives in three districts of KP.	30 active members of Community policing fora (CPF). / 5000 persons engaged by the CPF (including 10% women).	B / Evidence points to some progress in this component with 23 events recorded as having been staged. This has resulted in 78 police staff and 882 citizens being involved in initiatives so far. The 882 citizens comprised 321 women thus comfortably exceeding the target expectation of 10%. This level of female participation is to be welcomed. It would be interesting to see if such engagement was sustained beyond urban centres. Whilst the milestone target is unmet, it is apparent that it was too ambitious considering the major security risks that arise in bringing together large numbers of citizens under a community policing rationale.
1.10 Number of police investigative / forensic officers, prosecutors and judicial officers (formal security and justice actors) who successfully completed the incremental skills development programme.	327	A / It is reported that 332 persons have been trained thus meeting the milestone. It is important to consider both what training has been delivered and the impact of the training on the operation of the respective organisations of the participants. Aitebaar has recently established a new integrated skills development plan that should contribute to this quality assurance. It is suggested that DFID may wish to look at the impact of training over the next months before the next AR.
1.11 Functional operational systems, procedures and guidelines in place in model units and replicated in other police stations.	19 policies / guidelines / rules / / SOPs re-drafted / developed in consultation with concerned stakeholders and presented for implementation in model units.	C / This indicator is another example of where despite there having been considerable effort expended by Aitebaar, the dependence on others to e.g. approve and formally sign off documents resulted in the milestone being unmet. Out of the 19 papers, two are not expected to be continued on procedural grounds leaving 17. Of these, a minority have been completed with the remainder at various points in the drafting / working group / approval process. Further progress against completion is expected by the end of 2014. In a number of instances, it was mentioned that there were difficulties in getting papers considered by the appropriate level of officials. As this issue applies to a number of indicators, Aitebaar management should ensure that this is actively monitored and that representations are made to relevant authorities when necessary to resolve any issues with the potential to slow delivery of the programme, including asking DFID for support where appropriate. The programme has under-estimated the depth and breadth of consultation and engagement needed beyond the police to ensure these policies translate into institutional reform.

Key Points

The Rule of law output covers six projects (police investigations, prosecutions, community policing, gender responsive policing, correctional services and Alternative Dispute Resolution (ADR). It is clear that there has been significant work done by Aitebaar staff over the past year and the Annual Review (AR) team were impressed by the professional approach and enthusiasm displayed by all those they met. What also became clear is that actual delivery across the output is not as advanced as could be hoped and that in a number of instances, progress had only occurred within recent months. Given that this is Aitebaar’s second AR, it raises the question of why delivery has been slower than expected.

There are a number of factors which collectively contribute to explaining why output milestones have not yet been achieved. DFID’s administrative system requires an AR to be completed by a certain time in the programme’s life cycle. In the case of Aitebaar the AR was undertaken over two weeks before a number of output milestones were due with the result that some data was not available. This lack of alignment is frustrating to all concerned and it is recommended that in future every effort should be made to schedule ARs to coincide wherever possible with logframe milestone dates. On speaking with Aitebaar staff, it was possible to get a clear sense of purpose in their work. However in a number of cases, staff were placing considerably more reliance on their individual work plans to guide activity than the programme log frame. Whilst it is recognised that a logframe can only reflect some of a programme’s impact, it would be helpful to reinforce the importance of achieving log frame milestones given that this is the means of offering external reassurance to DFID about delivery progress.

During the AR, reviewers met a number of new staff who had joined since last year. Whilst it is encouraging to see vacancies filled, it offers a challenge to Aitebaar managers as to how such staff can be assisted to take on responsibility for delivering on work plans that have been inherited thus limiting the ownership of the contents. Aitebaar may wish to examine its staff induction process to ensure that the greatest possible effort is made to improve delivery through better ownership of the objectives and how they are to be achieved. With Aitebaar having many projects, staff turnover is expected, and this issue should not be allowed to become an impediment to delivery. It is also important to note that a number of key posts remained unfilled at the point of the AR e.g. the Investigations lead. The programme has continued to suffer from lack of senior police advisory capacity that can be consistently deployed to strengthen stakeholder engagement, particularly with the Inspector General of KP police, although this post was in the final stages of recruitment at the time of writing the AR. The quality of the log frame was also raised by many Aitebaar staff. Although there have been discussions with DFID over the past year, the log frame as currently constructed is not as central or as useful to the programme as it has the potential to be. The AR team share many of the concerns raised and recommend that Coffey as a matter of urgency engage with DFID as to how the log frame can be revised so as to make the significant changes necessary.

The final factor that needs to be considered from a delivery perspective is the opportunity cost arising of Aitebaar attending to the 2013 AR recommendations, especially the one relating to strengthening the programme’s leadership and management. Coffey have demonstrated both a willingness to act coupled with a determination to move the programme to a better place that would improve the prospects of successful delivery. There is a clear impression that this effort has resulted in a lesser degree of attention being paid to the logframe milestones with the consequence of a number of them not being achieved at this point. There is evidence however of ongoing work that should see a number, if not all, of the milestones achieved within the next three months. For all these reasons, DFID may wish to consider making achievement of these logframe milestones a payment milestone along with the achievement of a revised log frame that is fit for purpose for Aitebaar as it goes into its third year.

Summary of responses to issues raised in previous annual reviews (where relevant)

Programme leadership and management: This issue was a major factor that affected delivery in 2013. Although referred to elsewhere, it is notable that Coffey took the concerns on board and strengthened the management team. This has taken considerable effort and we assume that the structures now in place will result in an increased pace of achievement.

District expansion: The previous AR recommended that the “feasibility of engaging in a second, more permissive district of KP” be considered. To that end, a District Expansion Plan has been drawn up and discussions held with the GoKP resulting in a district (Nowshera) being selected. This has the potential to develop further learning for the programme and we hope that the experience to date will heavily influence how expansion takes place. It may also be useful to make a significant push in the remainder of 2014 on the three existing MPUs before beginning the expansion process to the next district. There will also be a need to consider the appropriateness of the MPU model outside urban, higher income environments. The consensus amongst those consulted was that the model was better suited to communities with higher levels of education and income. In rural districts, there are likely to be new opportunities for the programme to support improved service delivery / functional specialisation as currently being demonstrated by the MPUs. The RIU will need to support appropriate programme adaptation over the next few months.

Political engagement: During the time of the 2014 AR, an Aitebaar Steering Committee Meeting was held with the Additional Chief Secretary, Home Secretary, & other government officials. It is understood that a year had elapsed from the previous meeting although a briefing with the Chief Minister was held in February 2014. For the Aitebaar programme to succeed and be sustained, it remains critical to maintain the support of and access to the GoKP. DFID and Aitebaar management should reconsider current arrangements to ensure that the appropriate level of engagement is being maintained in a way that meets the requirements of all sides. Over the past year, DFID has significantly increased the frequency of its visits to Peshawar in support of Aitebaar, this needs to remain a priority for the office given most police counterparts do not travel to Islamabad and to build on the now established relationship with the KP Inspector General of Police. Given the acutely conflict-affected context of KP, DFID should leverage wider UK assets to respond to strong stakeholder demand for support that strengthens the criminal justice system as not only a development, but counter-terrorism tool.

Aitebaar support to Model Police Stations: It had been recommended that a human resourcing plan be developed for how the model units will be supported by Aitebaar and staffed by the GoKP. The newly developed District Expansion Plan recognises the need to adjust team positions so as to be in a position to manage both the existing support to the Peshawar MPUs and the establishment of the new district. The MPU briefing note from May 2014 also has a section on activities and resourcing. These documents suggest that Aitebaar will refocus resources away from Islamabad to supporting field activity. From a delivery perspective, this subject should continue to be an agenda item in meetings between DFID and Aitebaar management.

Quality assurance of training: Over the past year Aitebaar has introduced both an Incremental Skills Development Plan and a training policy that aims to address the assessment of impact. The operational implementation of these documents should provide a greater degree of clarity than what existed previously. Given the importance of training to much of what Aitebaar seeks to achieve, from a reassurance perspective, DFID and Aitebaar management may wish to consider how the quality of training can be examined in six months and before the next AR.

Co-ordination with other programmes in KP: The previous AR indicated that there was a need for stronger co-ordination and collaboration with other DFID programmes especially around citizen engagement where there may be opportunities to get participants to encourage e.g. female recruitment and community policing. It is noted that there has been some collaboration with e.g. DFID’s AWAAZ programme on legal rights awareness that involved over six hundred participants. DFID and Aitebaar should keep this topic on the agenda to monitor progress on exploiting potential opportunities.

Overall, there is evidence of significant progress having been made although, this is not reflected in the logframe with a number of milestones being unmet. There appears to be an upward trajectory in achievement over the last few months.

Recommendations

DFID and Aitebaar should reflect on whether the current arrangements for political engagement with the GoKP are adequate to meet the requirements of all sides. It is especially important that the Aitebaar programme is aligned with and is seen to be supporting the GoKP.

The log frame must, as a matter of urgency be revised to ensure it becomes fit for purpose for the programme’s final two years. There are suggestions on how this can be achieved elsewhere in this AR.

DFID and Aitebaar should consider what additional steps are needed by Aitebaar management to ensure that the pace of delivery is maintained / increased whilst a) District expansion takes place, and b) the 2014 AR recommendations are followed up.

Consideration should be given to expanding the work on Corrections where there may be opportunities to demonstrate impact through working with Dost, a relatively recent addition to the Consortium.

DFID may wish to consider independent assessment of training impact given the extent of this activity in Aitebaar’s approach.

The subject of achieving more effective co-ordination with other DFID programmes, such as AAWAZ, wider HMG programmes such as EDACE and CAPRI and with other donor activity should be a regular agenda item between Aitebaar and DFID. Even where there is limited geographical overlap, there may be lessons and best practice that can be shared between programme implementers.

Aitebaar management may wish to consider how its induction process for new staff can be improved to create greater ownership of the log frame milestones and how the log frame can be used more effectively to focus on achieving delivery.

In the interests of efficiency, every effort should be made to align the next AR with logframe milestone dates.

Output Title	Increased and effective engagement and communication between citizens and the state
Output number per LF		2	Output Score	B
Risk:		High	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s) Milestones Progress	Milestone(s) Progress	Progress Progress
2.1 Improvement in Knowledge, Attitudes and Practices (KAP) score among citizens in programme areas of KP	3% improvement over baseline (disaggregated by KAP)	B / The initial KAP was deemed insufficiently robust to provide a reliable baseline for the project’s activity, so an increase in KAP scores cannot be shown. A new KAP study, designed and implemented by the newly formed RIU, is in the field and is due to report initial findings by the end of the month. The greater focus on quality research, brought about by the establishment of the RIU, is encouraging and welcome. Safeguards will have to be introduced to demonstrate that the baseline and future studies, now no longer provided by an independent third party, provide data that are free of any conflict of interest.
2.2 Number of news reports and articles published on conflict issues and conflict prevention in local / national newspapers through Aitebaar support	55 (50 news report and 5 articles)	A / With 57 news reports and articles, this milestone has been met. The project’s media training was a useful link with local journalists, improving their skills and then encouraging them to cover press events related to other project activities. The majority of the articles were written from events organised by the project or based on press releases sent out by them. The team’s recognition of the need to add a quality criterion into this output indicator is a welcome acknowledgement of the need to ensure that the news reports published need to demonstrate the added value brought about through Aitebaar training. The embedded Strategic Communications Adviser in the Home Department offers the project great scope to broaden out the range of news reports and articles that can in the future be included in this output indicator. The team discussed the need to train senior editors in media organisations to enact more comprehensive change in the coverage of conflict issues and prevention.
2.3 Number of functional citizen engagement fora (GRM and SPs) established for more effective, transparent and accountable public services in select areas of KPK	2 foras established (1 GRM at KP level and 1 SP at district level in Peshawar)	B / The project has agreement to support two already existing GRMs (at the Public Safety Commission covering the whole of KP and the GCF titled ‘Working Group on Law and Order’ covering Peshawar) but neither are currently functioning and so the milestone is unmet. The project team usefully surveyed all the apparently current GRMs operating in the S&J sector GoKP. This revealed a large number of already established mechanisms, many statute-based, questioning the need to establish additional systems that may over-complicate the bureaucracy and prove counter-productive. Improving what is already there (Public Safety Commission) and what has political support (Working Group on Law and Order) is a pragmatic response to advancing this output indicator. Injecting additional momentum into already existing structures suggests that this milestone is en route to be met in the coming months.
2.4 Number of complaints referred in three districts of KPK (sex disaggregated data)	100 complaints (90 through GRM at KP level and 10 through Social Partnership in Peshawar)	C / The GRM aren’t currently functional and so the number of complaints referred is zero.
2.5 Number of trained government officials in strategic communications, media management, use of social media and improved reporting on S&J issues (disaggregated by sex)	24	A+ / The project has made significant progress in training government officials from across the S&J sector (including prosecutors, police officials and law department civil servants), exceeding the milestone target (24) by training 65 officials. By focussing on the recently implemented Right to Information (RTI) Act passed by the GoKP, Aitebaar training will have sensitised key officials working in the S&J sector to becoming more responsive to the public in relation to this key piece of legislation. The officials trained were those who have responsibility for responding to RTI requests, but as people in positions are rotated, the training will need to continue in the medium-term at least until the principles of RTI are fully embedded in the different bureaucracies. The embedded strategic communications adviser in the Home Department has the opportunity to enact more strategic and sustainable change in the system. Gaining political capital through relatively small amounts of effort which result in high profile changes could create the space to introduce larger, perhaps less ‘flashy’ more systemic changes also.
2.6 Number of policy dialogues, dissemination workshops, held on security and justice sector issues	8	A / Whilst the majority of the policy dialogues and dissemination workshops are due to be held over the next three weeks we are confident having reviewed the material that this target will be met within the milestone date.

Key Points:

HMG coherence: The review team noted Aitebaar’s efforts to engage with AAWAZ and their disappointment at the challenges experienced in doing so to date. The need to link up with other HMG funded programming as much as possible remains. The same holds for wider development sector coherence. The social mobilisation workshop the review team attended was promising but it involved no external parties other than project partners working on Aitebaar. Although there was some awareness of the work of other actors in the S&J and wider development sector in KP (UNDP, PCNA/MDTF, World Bank etc), little evidence was presented that demonstrated coordination, collective working or systematic information sharing. This is something that should be considered as part of the Aitebaar Communications Strategy.

Risk: Following some negative press coverage this year, Aitebaar mentioned a revised process for handling such an issue in the future in one of their quarterly reports. The communications team were not aware of any prepared press lines / Q&A document to be drawn upon should there be any additional press enquiries. It is advisable to have such a document drafted and agreed with stakeholders so press lines can be amended and deployed quickly in case of hostile media questions. This would be an appropriate mitigation for this reputational risk to the programme.

Communications Strategy: The drafting of a ‘communications strategy’ is a welcome development. It is recommended that the strategy is revised and made a communications strategy for the whole project and not just Output 2 (or indeed 3 as per the title of the document). Although communications is fundamental to the second output, the need for effective internal and external communication is crucial for both outputs and thus the entire project. For example, unless the success of the output indicators in Output 1 is persuasively communicated to relevant stakeholders inside and outside of GoKP, then the work of the ‘model’ police stations won’t be replicated across the province as intended. The Aitebaar team were rightly encouraged by the amplification of their messages by the influential PTI social media team. This opportunity should be examined so that its risks can be identified and its benefits maximised.

The strategy should also consider and set out the intended plan for the external branding of the project. The communications team recognised that the branding could not remain static but a plan should be devised as to how that can be developed over time to reflect and encourage greater political buy-in from GoKP, as well as link the project’s activities in the minds of the public with the authorities. Such a strategy would also provide a framework against which to assess any additional communication activity. For example, the team’s intended expansion of their awareness-raising sessions into TV dramas will need to directly contribute towards defined objectives and represent value for money.

As well as recognising the wider strategic level importance of communications, the strategy should also be developed to scrutinise the communications implications for each level of activity. A communications workplan attached to the strategy should link up with the wider project’s workplan and logframe. This will help focus the minds of the communications team on the relative importance of different communication activity. The review team was unconvinced about the need for a Aitebaar Facebook page and twitter feed. The project’s website could arguably have greater usefulness but this still has to be set out and justified. It is clear that the project has a nascent SMS capability but the potential influential use of this tool is not explored in detail in the current strategy.

This level of planning will also have the important consequence of ensuring that Output 2 ‘demand-side’ communication activity is appropriately linked with Output 1 ‘supply side’ activity. Without this consideration of sequencing there is the risk of ‘demand’ and ‘supply’ not matching each other, leading to counter-productive results in terms of community trust. Widening the scope of the strategy would also help ensure that the communication activity is understood and internalised across the whole project.

Sustainability and Scalability: If the establishment of Beat Level Organisations (BLOs) are to be included as a separate output indicator, then greater thought should be given to the sustainability and scalability of this policy. At the social mobilisation working group, one Aitebaar team member said that the “BLOs are at the foundation of the programme”. It is unclear whether the BLOs as currently constituted would continue to function without the support of the implementer SRSP. Any request for additional resources to support these groups should be considered against the viability of these organisations. Aitebaar should also consider the scalability of this approach of community awareness / trust building so they can assess its relevance to the GoKP. Can the current model be adopted by GoKP and replicated across the province or is it just Output 1 activity that is intended to be a model for wider reform? If the current model is adapted and formalised in some sense by GoKP this may also answer questions about the sustainability of these organisations. Ambitions for this element of the project should be clarified at this stage so any, potentially lengthy, necessary political lobbying and reforms can start as soon as possible.

Output Specific Recommendations:

2.1 Recommendation: Once the KAP study is complete, early agreement should be reached with DFID about specifically which elements of the KAP study will the target of “3%” improvement be based upon, to be reflected in revised logframe if appropriate.

2.2 Recommendation: In addition to the development of evaluation criteria for quality measurement, Aitebaar and DFID should also agree categories of news reports and articles based upon the nature of the ‘support’ offered by Aitebaar e.g. press release based upon other project activity, Aitebaar-trained journalist writing about conflict issues, news reports better reflecting GoKP security policy resulting from embedded strategic communications adviser etc. If training is expanded to include senior media editors, then it will be more difficult to assess and judge causality of more systemic change in the way the media covers conflict issues and prevention. The number of senior editors trained could be considered as a separate MOV.

2.3 Recommendation: The two GRM that Aitebaar are set to support are closely linked and will require careful handling to ensure their remits do not overlap. Aitebaar should work to finalise the ToR of the GCF to ensure that it is sufficiently distinct from the Public Safety Commission. There is a need to engage politically to ensure that the GCF is institutionalised and becomes a sustainable and supported feature of the S&J infrastructure in KP. Aitebaar should also continue their efforts to engage with other donors (World Bank, UNDP) who are working on establishing similar GRMs to avoid duplication and share best practice. When the logframe is revised, consideration should be given to MOVs that recognise the inherent challenges faced in operationalising these GRMs (e.g. minutes of meetings that have taken place).

2.4 Recommendation: When the logframe is revised, DFID and Aitebaar need to agree the terminology used to define the milestone indicators. Are only complaints addressed in GCFs? Should the project be measuring complaints referred to a GRM or complaints processed?

2.5 Recommendation: When the logframe is revised, this output indicator should be reworded to better reflect its contribution towards responsiveness. The RTI legislation, not passed when the logframe was initially drafted, is a form of Government-citizen responsiveness not encompassed in the field of strategic communications and yet the majority of the training hitherto has been based on this. An amended output indicator could include an MOV relating to the number of RTI requests received and responded to. Milestones / MOVs will also have to be included to capture the improvements put in place by the embedded strategic communications adviser.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Summary:

Assessing value for money of this programme proved challenging for a number of reasons: the initial business case assumptions were over-ambitious; changes in programme’s focus make them no longer fully appropriate; and the milestone based contract model has made initial VFM criteria less relevant. However, this does not imply that the programme lacks a focus on VFM, and significant evidence is provided below. What is now required is a more contextually relevant VFM strategy to be produced alongside the revised logframe which will allow VFM to be more rigorously assessed as the programme moves forward.

At total cost of £8.1m (or £38 per person), Aitebaar has improved access to policing for 213,000 people[1] in Peshawar - one of the most insecure major cities in Pakistan. 133,478 women can now visit female-friendly facilities at three police stations– resulting in a 67% increase in complaints registered. The programme also has an alternative dispute resolution element, which has trained mediators who, within the first few weeks, have mediated 25 disputes. By the end of the programme it is expected that 1500 disputes will have been mediated at a cost of £31 per dispute[2]. This initiative has reduced pressure on the formal judicial system by mediating disputes through alternate forums which have the potential to resolve them within few weeks, at least 2000 days quicker than the average time taken to resolve disputes through the formal judicial system[3].
[1] Rough estimates of people in the catchment area of three model police stations
[2] £31 covers only the training cost per mediator, while the actual cost which includes travel costs, time spent in mediation, etc will be higher.
[3] World Bank’s Doing Business Report (Sub-National) for Pakistan 2010, suggests that on average these alternate dispute resolution forums deliver results in less than 90 days compared to 2190 days average processing time of the formal judicial system.

DFID has also benefited from a significant investment by Coffey International in improving programme performance following the 2013 AR. This has not been passed on to DFID due to the milestone-based contracting method being applied to Aitebaar.

Key cost drivers and performance

The contract for this programme is a milestone based contract model. This means that payment is linked to the delivery of particular outputs and information is not provided on input costs. Analysis of the cost drivers for a contract of this nature cannot be done. However, Coffey do provide analysis of the share of their budget spent in different areas through their annual operations report. Personnel costs form the largest cost driver followed by operating costs such as security and accommodation. As a technical assistance programme operating in a high security risk location these are expected and reasonable key cost drivers.

Within personnel costs, logframe output two carries the highest costs with a 36% share of personnel spend followed closely by the core team costs (35%) and then output three (16%) and Research and Monitoring & Evaluation (RME) (13%). Output two is the largest and highest risk aspect of the logframe and therefore necessitates significant investment. Core team costs are high, reflecting the increased management oversight that Coffey has invested in the programme to drive performance improvements over the last year. As DFID pays according to a pre-agreed milestone payment plan, the cost passed to DFID does not directly relate to the inputs Coffey is investing – these increased management costs have not been passed through to the programme budget.

VFM performance compared to the original VfM proposition in the business case

The business case VFM propositions use both quantitative and qualitative methods to estimate benefits and effectiveness of different interventions. However, some of the assumptions in these estimations are too strong[4] and not supported by evidence from the literature. The original business case estimated an Internal Rate of Return (IRR[5]) of 21% - very high for a peace building / conflict reduction programme. However, the background calculations are not available to verify this estimate. The information is not available to allow a comparison between what was in the business case and what the programme has subsequently delivered. In addition to these issues, the programme’s FATA component was removed from the contract following inception phase with remaining activities to be carried out in KP alone – leaving the initial assessment partially out of context.
[4] For example, suggesting that 50% of the cases mediated under ADR will entail a payment of £100 is based on anticipation and not accepted literature.
[5] A measure of profitability of investment; comparing benefits and costs of interventions.

In our view, the approach outlined in the business case was the best way forward initially, but is not comparable to what has happened since programme implementation started. This does not imply that programme lacks a focus on VFM. The programme has demonstrated economy and efficiency by actively evaluating inputs and consulting with the government of KPK to pool resources, which has led to reduced costs while ensuring that interventions are efficient and sustainable post DFID funding.

Assessment of whether the programme continues to represent value for money

The £24.78m PSP programme (2012 – 2016) aims to improve security and justice services for 250,000 people in 3 districts of KP by piloting new approaches to policing, prosecutions and corrections with a focus on community engagement and gender. The programme is being implemented in Peshawar, but will subsequently be expanded to two other districts of KP by the end of 2014. To date the programme has spent £8.1 million, but without an overall VFM monitoring mechanism and lack of information available (for wide ranging interventions) it is difficult to quantitatively assess VFM. However, illustrations of VFM are possible.

As a result of the programme, three Model Police Units (MPUs)with improved management systems, gender responsive policing and better trained staff are now available to be accessed by 213,000 people[6]. Furthermore, the establishment of Lady Complaint Units (LCUs) which are available to 133,478 women and has led to increase in women complaints by 67% during May-Aug 2014. Similarly, the alternate dispute resolution programme with 125 trained individuals has been able to mediate 25 disputes within first few weeks of hitting the ground. This approach resolves disputes in an average of 90 days. By contrast, courts in Peshawar take on average 2,190 days to settle disputes. The programme also focused on achieving economy and efficiency of inputs through improved procurement of inputs and personnel and ensuring government buy-in, leading to sustained use of programme interventions.
[6] Rough estimates of people in the catchment area of three model police stations

The Aitebaar team have a good understanding of VFM management. Examples shared in the annual report illustrate potential positive overall VFM. However, since the programme lacked a strategy and a mechanism to continuously monitor VFM, it is difficult to make a fair overarching assessment at this point in time.

The programme originally followed an input / output based delivery contract, but was changed to a milestone based contract post inception phase. This shift led to no requirement to report detailed input-related financial information (which is appropriate for a milestone based contract). This makes it difficult to provide a unit cost assessment and comment if the programme is achieving VFM at output level.

As noted in the previous annual review, covering the inception phase[7], Aitebaar had devised a VFM strategy and way to monitor VFM through a weighted average based index around the four pillars of VFM i.e. economy, efficiency, effectiveness and equity. However, due to the nature of the index design and shift to a milestone based contract the team was unable to utilise the model while moving into the implementation phase. The logframe was designed for input / output based contract and carried unrealistic expectations for delivery, which compounded the problem.
[7] According to implementing partners value for money model (assessed as technically robust) an overall rating of 3 or ‘A’ was accomplished for the inception phase.

Though the programme lacked an overall workable strategy for monitoring VFM, there is anecdotal evidence that the programme is achieving VFM. Some illustrations are shared below:

In terms of achieving economy the team has demonstrated a fair understanding of the need to strike a balance between the quality and cost of interventions:

- Procurement of inputs and personnel
  - The cost sharing[8] of training with KP police reduced the costs significantly (50% reduction claimed by Aitebaar).
    [8] Cost sharing was not cash but in kind, including providing venue, equipment needed for the training, engaging a training facilitator, etc
  - Lady complaint units (LCU) were established within the existing 3 model police stations, saving roughly £24,000 of government investment in providing new infrastructure. Furthermore, the training venue, equipment and trainer to train female officers was funded by the Government, leading to cost savings of £19,000.
  - During the procurement of Management Information System (MIS) for the model police stations the team renegotiated the costs with the supplier leading to a saving of roughly £11,270 or 48% of the original contract.
  - A quantitative value is not available, but a shift from consultant to employment based contract for programme staff (which was driven by a recommendation in an annual audit) is expected to lead to a greater sense of security and higher retention rate in the Aitebaar team.
  - However, since the last annual review, an increased amount of DFID man hours have been needed to help the Aitebaar team get on track in terms of delivery, which has increased overall operational cost to DFID Pakistan.

In terms of achieving efficiency, a fair portion of background work in terms of establishing sound internal programme management systems, policies and procedures is complete. Selective illustrations around efficiency are as follows:

  - Research and Innovation Unit (RIU) The revised methodology for the Knowledge Attitudes and Practices Survey can be undertaken faster and will absorb less time and have a lesser impact on respondents than the original design, whilst generating more usable data. However, it is a bit early to comment on the outcome of this process.

  - Management Information System (MIS) Aitebaar and KP police jointly decided that rather than outsourcing the MIS and training, it would be best to work on strengthening the existing capability of the KP Police. This not only cost less but also provide a long term asset to the KP Police, while allowing them to retain institutional knowledge. Furthermore, to ensure that the MIS will not become useless post DFID funding, KP Police agreed that it will continue providing maintenance of MIS through its own budget and will earmark funds for it[9].
    [9] Remains unconfirmed if the funds were earmarked in KP Budget 2014/15.

The programme is wide ranging but some key effectiveness examples are illustrated below:

Lady Complaint Units
There are only 700 female police officers out of a force of 66,500 (1.1%). Women are reluctant to report crimes in a male dominated police environment, and the only female police station in the province was inaccessible to most women, and failed to register any cases. Aitebaar has helped improve women’s access to police services by establishing pilot Model Police Units (MPUs), which include LCUs, in 3 police stations in Peshawar at a cost of £12,000[10] in infrastructure and refurbishment. There are approximately 133,478 women in the catchment areas of stations where MPUs and LCUs have been established. Lady Complaint Units are enabling women to come forward to ask for police support:
[10] Approximately £4,000 per LCU based on estimates of infrastructure and refurbishment of the MPUs. This figure does not include softer investment.

Number of Women Complainants

Model Police Station	Before LCUs / (Jan to April 2014)	After LCUs / (May to Aug 2014)	Change (%)
University Town	0	11	-
Gulbahar	15	22	46.6%
Faqirabad	31	44	41.9%
TOTAL	46	77	67.4%

Alternative Dispute Resolution provision of justice is crucial to strengthening the state-citizen relationship. The formal court system is very slow and expensive. £46,000 was used to train 125 community mediators who will mediate at least 1500 disputes during the life of the programme at a cost of £31.00 per dispute[11]. To date, 25 disputes are under mediation within the first few weeks of hitting the ground. This approach will resolve disputes in an average of 90 days compared with courts in Peshawar where disputes take on average 2,190 days to be settled. Claimants generally pay 22.3% of the total amount which the Claimant is intending to recover from the Defendant in legal and court fees, and other costs[12] - with ADR, the costs to claimants are negligible.
[11] £31 covers only the training cost per mediator, while the actual cost which includes travel costs, opportunity cost of time spent in mediation, etc will be higher.
[12] World Bank’s Doing Business Report (Sub-National) for Pakistan (2010)

Recommendation:

In light of the revised theory of change and logframe, a revised and functional VFM strategy needs to be devised and implemented to allow assessment of VFM including at outcome level.

Quality of financial management

The Aitebaar Operations Manual sets out strong programme financial management procedures including internal controls such as separation of duties and a fraud prevention plan including steps to take in the instance a fraud is suspected. Finance/IT systems are used to provide the finance team with information needed to track funds and interrogate spending. The procedures outlined look good and the finance team explained that they regularly train staff in financial management including recently at an all staff workshop on 8th August. It is important that Coffey continue to ensure that the Operations Manual is embedded in staff practice, including through induction for new staff and refresher training for the existing team.

Coffey report on finances quarterly (although without providing input cost detail which is not required under a milestone contract) and invoice DFID for pre-agreed amounts as and when milestone deliverables are met. Due in part to slow progress of delivery and in part to confusing milestone deliverables the timing of payment milestones has not matched the original plan as can be seen from the graph below. Communication between Coffey and DFID on milestone slippage has improved over the course of the year. Coffey should continue to alert DFID to slippage in payment schedule at the earliest to ensure that financial forecasts remain accurate.

Fig 1. Spend vs original contract forecast by month for PSP programme

Audit:

The contract provisions for a special report on programme financial information to be conducted by an audit company. Last year this report checked the mathematical accuracy of the invoices presented to DFID and checked time charged above a £3000 threshold and expenses charged above a £1000 threshold against supporting documentation. This style of report provided a useful check on costs during inception phase when the contract was inputs based. This same style of report will be less useful this year as the contract has moved to milestone based and therefore input costs are not visible to DFID. Coffey and DFID need to agree a new form of audit of the programme to take place this year. The review team recommends either a risk based, a VFM or an operational audit.

Recommendation: Coffey and DFID to agree to a sensible approach to this year’s audit - a risk based, a VFM or an operational audit are suggested.

Date of last narrative financial report	18th Sept 2014
Date of last audited annual statement	20th March 2014

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk

Last year’s annual review recommended an increase in the overall programme risk level from medium to high. That remains an appropriate reflection of risk level for a programme working in a difficult security context with limited access and significant Government of Pakistan political interest in rule of law in KPK. Programme risks remain high and challenging to mitigate. There have not been significant changes to this overall risk context in the course of the year.

Key risks that affect the programme are as follows:

Relationships between the programme, DFID and Government remain critical to delivery. The limited access for the DFID team to Peshawar has resulted in an unusual balance between Government stakeholders, DFID staff, and the programme which has created challenges for such a politically sensitive set of activities. There has been one programme Steering Committee this year (13th October 2014) which demonstrates some degree of shared commitment to the programme but that needs to be further built on. This mechanism for shared oversight should continue to be invested in to build and maintain effective relationships in support of programme objectives. During the logframe revision process DFID and Coffey should think through the critical outputs that are further from the direct control of the programme team due to a dependence on Government of Pakistan and DFID / BHC should invest additional, targeted facilitation support in these areas. The AR team saw evidence that this was improving now that the DFID team was more stable, and better relationships with Government partners are developing. However this will need to continue to be prioritised for the programme to achieve full effect.

The high risk security context and implications for access to MPUs remains challenging. This affects not only the programme team but also DFID’s ability to assess programme delivery through project visits. Coffey appear to be managing security well and have not reported any incidents directly affecting programme staff over the course of this year. In areas that the DFID team are unable to visit a third party monitoring contract should be put in place to provide oversight without unnecessary risk to DFID staff.

The reputational risk to HMG of human rights abuses being committed and associated with the programme. Working closely with the police remains high risk, given the prevalence of the ‘thana culture’ of human rights abuses being committed within police stations to extract confessions. However the programme has a robust OSJA and associated risk mitigation process which appears to have been effective to date.

Limited availability of appropriate staff and failure of implementation partners to deliver are risks that materialised early in the programme and that Coffey have invested significantly in resolving over the course of this year. Coffey now have a better team and structure in place that appears to be motivated and well placed to deliver over the course of next year. While these changes have not yet sufficiently materialised in programme delivery against the logframe we anticipate that they will do going forward. Managing and maintaining an effective team will be an ongoing challenge for the programme but Coffey have embedded improved recruitment processes and a better structure that should help them manage these risks better in future.

Risk to UK funds

DFID manage this programme through a milestone based contract. This means that funding is 100% linked to deliverables and Coffey do not provide information on the cost of inputs. Coffey’s own ability to identify fraud and corruption is therefore more significant but it also means that DFID won’t provide additional funding in the event that money is lost due to fraud / corruption. In this regard Coffey carries the risk of fraud and is also best placed to detect it.

As noted above the Aitebaar Operations Manual includes a fraud prevention plan setting out financial management processes to reduce the risk of fraud, red flags to assist in fraud detection and steps to take in the instance a fraud is suspected. These written procedures are good. The key is to ensure that the processes set out in the Operations Manual are embedded in practice.

Recommendations:
- DFID / BHC should invest additional, targeted facilitation support to the relationship with Government in critical logframe outputs that are further from the direct control of the Coffey team.
- In areas that the DFID team are unable to visit a third party monitoring contract should be put in place. Whilst this will be challenging in terms of access to some of the sites involved - due to the need for Government endorsement of monitors and the political nature of some activities, it will be important to explore given the clear need for reassurance that the programme is delivering the intended impact.

Outstanding actions from risk assessment

There are no specific outstanding actions relevant to this programme other than the ongoing management of live risks by the programme team underpinned by the risk matrix and discussed regularly within the programme team and with DFID.

There will be a need to continually monitor the OSJA assessment and the mitigation measures in the event of an OSJA related incident taking place. Presently the AR team are confident that the existing system in place is fit for purpose.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe N

As noted against output assessments and in Fig.1 delivery is behind schedule. As a result of the slow start to the programme noted in last year’s annual review, DFID initiated a Performance Improvement Plan (PIP) for the programme and subsequently an ongoing Performance Improvement Arrangement (PIA). Coffey has responded well to these measures, investing significant management time to assess problems in the programme and find solutions. Improvements have been made to governance structures, consortia management, staff performance management and recruitment for vacant posts. Due to the milestone nature of this programme DFID has not had to fund additional costs for remedial measures.

The programme team now seem better placed and motivated to deliver going forward. The pace of delivery has already notably accelerated over the last quarter and we can expect that trajectory to continue. Given this progress, we expect the programme to deliver against agreed timeframes for the year ahead.

Performance of partnership(s)

Performance of milestone contract

A milestone based contract was agreed at the end of inception to cover the first year of implementation up to December 2014. Payment milestones were mostly drawn from output indicator milestones in the logframe. In the interest of rationalising the total number of milestones, individual payment milestones combined a number of different logframe milestones. The payment milestones range between some closer to the control of the supplier to some further from their direct control.

Recent guidance suggests that this type of challenging, institutional reform programme is not best suited to milestone based contracting due to: difficulties in identifying performance measures that are closely linked to underlying objectives; the need for flexibility to be able to be responsive to Government partners; difficulties in verifying milestone delivery; and the fact that many of the targets are not in the direct control of the contracted supplier. This has posed challenges for DFID and Coffey in managing this contract over the course of the year. While some milestones were delayed due to inadequate supplier planning, others were delayed because of changes in programme priorities or because they were more dependent on other actors such as Government.

Other problems have been that composite milestones with no clear approach to partially met payments have led to confusion; in some cases verification that milestones were met has been difficult; lack of access to input costs has made analysis of VFM challenging for this programme and all this has led to high transaction costs by both Coffey and DFID. There is also a risk that the milestone contract has distracted attention away from the logframe as the primary programme management tool.

However, this approach has meant that the supplier has had the freedom to decide on the inputs they have used to deliver the programme, allowing the programme to be quicker and more responsive to delivery on the ground. It has also meant that DFID has not paid more to fund significant remedial actions following the PIP and PIA. Coffey have invested additional management and oversight to resolve problems on the programme in the last year at no additional cost to DFID.

The question of whether this type of contract has incentivised supplier performance is complicated but our overall conclusion is that it has not provided the strongest performance incentive. Stronger incentives for programme improvement came from last year’s annual review and subsequent performance management processes, underpinned by the total value of the contract. The contract did however, ensure that DFID did not carry the cost of the remedial activities required to improve the programme when problems were identified. For this reason it is worth continuing the milestone style contract into next year. In addition both the supplier and the DFID team have expressed a preference to continue with this style of contract.

Getting the milestone payment plan right for next year will be challenging and will require effective partnership between Coffey and DFID and the willingness to trial something and change if it doesn’t work.

Recommendations:
- The next milestone plan needs to be designed carefully to respond to the refreshed logframe. In order to allow sufficient time to get this right, the review team suggests a contract amendment setting a first milestone due 31st January to revise the logframe and future milestone payment plan.
- The milestone plan needs to clearly refocus efforts on the logframe – either by basing milestones on logframe outputs or by using logframe progress reviews as milestones.
- Outputs translated into milestone payments should be based on the more credible / delivery confident aspects of the logframe. A careful balance needs to be found between outputs that are so directly in the supplier’s control as to only measure process vs tying the supplier to milestones they have no control over delivering.
- Composite milestones should be avoided, unless the different items are directly linked to each other – i.e. to achieve one the supplier must have previously achieved the other.
- Third party monitoring should be established for the contract and logframe, providing an independent view on milestone delivery in locations the DFID team are not able to visit and ideally reducing the number of paper based MoVs.
- Given the challenging nature of this contract, there should be an agreement with DFID procurement or the new DFID Pakistan commercial adviser to provide additional support to this contract so that contract amendments that are genuinely needed can be processed efficiently. As DFID Pakistan’s most innovative private sector contract, this is a sensible investment of procurement time. Alternatively, given the highly political nature of this programme, consideration should be given to including language within the contract that enables milestones to be amended by mutual agreement (exchange of letters etc) rather than an intensive formal contractual amendment process. This would reduce the burden on both DFID and Coffey and enable greater collective focus on delivery.

Consortia Management

The review team met with Coffey, two members of the consortia plus two additional organisations referred to as delivery partners but not consortia members. Coffey provided the Consortia Guidelines, a document specifying aspects of the relationship, which has recently been revised.

Coffey’s contract with DFID lists ten different consortia partners, some of whom have become less relevant as the programme moved to implementation. The original model was to use the consortia to source individuals to fill specific slots within the Aitebaar team rather than outsourcing packages of work to consortia partners to deliver in full.

There have been a number of challenges in implementing this model; it doesn’t appear to provide the best incentive framework for consortia members to engage effectively with the programme. There have also historically been problems with advertising positions early enough and with getting sufficient applicants for posts. The consortia partners we met with expressed challenges of working within the consortia however they both felt that there had been a marked improvement recently in the management of the consortia and were positive about the future. The recently finalised consortia guidelines have been welcomed as has a recently established regular pattern of consortia meetings, the first of which took place last month. There also appears to be a shift by Coffey to outsourcing packages of work to the consortia. This is likely to be a better model for the programme going forward.

Coffey currently has a number of different relationships with organisations within the Aitebaar programme: service providers with a subcontractor relationship who are not considered consortia members; consortia members some of whom are also subcontractors; consortia members who provide occasional individuals to the Aitebaar team but aren’t delivering work packages; and partners who have a steering role for the programme by sitting on the ‘Thematic Panel of Experts’, some of whom are consortia members. This presents quite a confusing picture. Organisations appear to be in different categories for historical reasons rather than where they can have most benefit to the programme. For example, some service providers, due to their length of time operating in the sector, appear to have potential to inform programme strategy but don’t currently have a mechanism to do that as they aren’t considered consortia members or sit on the Thematic Panel.

It is clear that Coffey have recently made improvements to their management of the consortia. The partners we spoke to are positive about the future. Moving forward Coffey should look to rationalise their partner organisations further to ensure that the consortia of organisations they are working with in the broadest sense is the most relevant to the programme and is being used most effectively. Coffey should work towards having a clearer set of partners that are either thematic advisers to the programme or subcontracted delivery partners, and that there are a clear set of partners within both categories that inform programme strategy, and are limited to the organisations best able to play this role.

Recommendation:

Coffey to continue to improve consortia management by rationalising the shape of their current consortia / delivery / steering partner set up to ensure relevant organisations are being used in ways that best meets programme needs.

Asset Management

DFID conducted a spot check of programme assets held at the Islamabad office on the 16th October 2014. The spot check concluded that Coffey are managing assets in line with DFID expectations.

Procurement Processes

The annual review process is not a procurement audit and therefore these conclusions are limited but it did provide an opportunity to assess a sample of the procurement processes that Coffey have delivered over the course of the last year. Documentation for three large (over Rs 3.5m) procurement processes was inspected and a list of all procurements conducted between August 2013 and August 2014 setting out the procurement methods for each was provided.

Coffey have sound procurement guidelines as set out in their Operational Manual with a sensibly differentiated process depending on the size of procurement. Procurement records are well maintained and our assessment, while not an audit opinion, is that Coffey are operating broadly in compliance with their own guidelines as intended.

The Operational Manual sets out that in most cases an open tender procedure should be used for procurements over Rs 3.5m. On two of the larger procurement processes that were assessed, Coffey had decided to waive an open tender procedure in the interest of speed. This is not against their guidelines, which reference ‘most cases’ rather than ‘all cases’ therefore provisioning for a potential waiver. It does however risk reducing Coffey’s ability to seek VFM through procurement. Waiving open tender on large procurements should be used only as a last resort. It’s worth noting that Coffey attempted to mitigate VFM risk by seeking quotations from a large number of potential suppliers.

Both instances noted relate to procurements before Feb 2014 and there is evidence that in more recent procurement processes open tender is being used preferentially. This seems to be as a result of better planning allowing sufficient time for procurement to take place. Coffey should continue their recently demonstrated focus on forward planning allowing them to implement their procurement guidelines as written.

Recommendation:
Procurement team and output leads to maintain good communication on upcoming procurement plans. A procurement tracker may be a useful tool.

G: CONDITIONALITY (½ page)

Not applicable.

H: MONITORING & EVALUATION (½ page)

This annual review was led by Mark White, the Deputy Head of the UK Government’s Stabilisation Unit. He was supported by an integrated and multi-disciplinary UK Country team including:

1. Senior Rule of Law Adviser, Stabilisation Unit
2. Economist, DFID Pakistan
3. Social Development Adviser, DFID Pakistan
4. Senior Programme Manager / Deputy Head Governance Group, DFID Pakistan
5. Statistics Adviser, DFID Pakistan
6. Strategic Communications Adviser, BHC
7. FCO Policing Adviser / Head of CT

The terms of reference for the review are attached at Annex A. The team undertook interviews with programme stakeholders in Islamabad over the course of a week (12-18th October 2014). The team was unable to visit Peshawar for the review due to security constraints, though a parallel HMG visit which included the FCO Policing Adviser, who was a member of the review team, was able to feed in key findings to the review.

Government stakeholders interviewed included members and Chairs of Aitebaar programme governance structures namely Secretary Home and Tribal Affairs, Additional Secretary Home, Secretary Information, Secretary Planning & Development, IG Prisons, Director Prosecutions, and Director Corrections. Beneficiaries and other stakeholders consulted included Community Police Officers, members of Community Policing Forums, Beat Level Organisations, Lady Complaint Unit personnel, Community activists, Prosecutors, Consortium Members and Delivery Partners. The team also met with other major donors and agencies active in KP, as well as rule of law experts. The team also met with related HMG funded programmes such as EDACE, CAPRI and AAWAZ.

AR recommendations have been developed in consultation with DFID, BHC and the Aitebaar programme team.

A summary of this review will be presented to GoKP and other donors active in the rule of law sector upon completion. It will also be shared with Consortium partners, and widely across DFID and other UK government departments.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process