Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Development Research Uptake Sub Saharan Africa (DRUSSA)
Programme Value: £4,973,903		Review Date: 18-19 August 2015
Programme Code: 202004	Start Date: 30th Sept 2011	End Date: 30th Sept 2016

# Summary of Programme Performance
Year	2015	2014	2013	2012
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium

# Summary of progress and lessons learnt since last review
The DRUSSA programme continued to make steady progress during the past year, putting itself in a strong position to achieve lasting, sustainable outcomes in the final year of implementation. This will be in part dependent on the success and pace of activities that take place during the next twelve months, which includes comprehensive sharing of evaluative programme learning with immediate partners and the broader sector.

DRUSSA is supporting 22 universities across twelve countries in Sub Saharan Africa to improve their research uptake capacity, in order to maximise the chances that the research they produce will used by stakeholders. The programme implements a range of activities at multiple levels, including training at the individual level (from short courses to PhDs), the strengthening of organisations through support to strategy formulation and the development of appropriate operational structures. A limited amount of resources have been reserved to influence the environment universities are working in, through activities such as high-level symposia on Higher Education with relevant government ministries in DRUSSA countries, which appear to have been successful.

The progress that universities across the programme have made varies considerably, which is largely to be expected given the range of different contextual and environmental challenges that they face. It is inevitable that all of the universities will still have some capacity weaknesses by the time the programme is completed next year. Therefore it is important that DRUSSA helps to diagnose areas which require further strengthening following programme completion, so that universities can implement research uptake reforms independently. However, the programme’s support to university change programmes to embed practices that improve research accessibility, and its interactions with regional Research and Innovation and Management Associations (RIMAs), is improving the sustainability of work and strengthening longer term institutional links.

The DRUSSA extension project, which commenced in 2013, is working with three ministries in Ghana and three ministries in Uganda to increase demand for research evidence from policy making institutions. It is facilitating high level symposia on relevant policy issues, providing training to civil servants on use of evidence and seconding researchers into the ministries as policy fellows. Whilst this work has inevitably been subject to delays related to political issues, good progress has been made this year and there is the potential for activities to become embedded beyond the life of the programme, with a high level of interest from ministries to expand links with the research sector.

The previous annual review recommended that improvements were made to programme management practices by; ensuring more cohesive planning across output strands; reducing the transaction costs of collaborative working; and working more closely on an ongoing basis. Feedback gained from the review suggests that partners are working more closely and joint planning has become stronger, improving the effectiveness of programme management.

The previous review also recommended further development of Value for Money (VfM) measures and construction of a Terms of Reference for the planned independent evaluation that will take place next year. The programme was initially very slow to act on this and although more progress has been demonstrated recently in the form of a draft set of VfM indicators, these are yet to be populated with performance data.

A. Introduction and Context

DevTracker Link to Business Case:	3717199
DevTracker Link to Log frame:	5066598

# Outline of the programme
The dynamics at many SSA universities can prevent research being effectively disseminated outside the academic domain, let alone being taken up by individuals and organisations that require evidence to tackle development challenges.

DRUSSA works with a set of 22 universities across sub-Saharan Africa to improve the accessibility, availability and use of the research that they produce. The programme builds the capacity of universities at strategic and operational levels to embed sustainable links with groups that use research. Through these linkages with policy makers, practitioners, businesses and communities, it is hoped that pro-poor policy, practices and behaviours can become better formulated.

As well as realising the potential of African Universities to supply research evidence, the programme is working with one set of users to improve the demand and use of research evidence. The programme is working with policy makers in three ministries in Ghana and three in Uganda to help develop their capacity to demand, find, use and apply research evidence.

The key outputs from this programme are:
1. A collection of universities with embedded approach to research uptake. Work with the management of 22 universities to embed research uptake in organisational and institutional practices through leadership engagement, training and benchmarking.
2. A core of specially trained staff from 22 universities that can provide the strategic and operational leadership and expertise for Research Uptake Management (RUM) in their university. This includes 40 staff a year attending short courses in subjects from research management to science communication and 16 M.Phil graduates and PhDs with a specialisation in evaluation and impact assessment (REI), with the particular focus on undertaking evaluation and assessment of development research portfolios.
3. A networked of active and engaged researchers and research uptake specialists committed to making research evidence accessible and useable.
4. Provide new contributions to the evidence base about Research Uptake and Impact Assessment in Africa and globally. Literature is systematically documented, shared within the consortium and externally where appropriate.
5. Capacity building to use research evidence. Political leaders and civil servants within 6 development oriented government ministries in Ghana and Uganda have improved capacity and incentives to use research evidence within the formulation and implementation of development policy.
The programme is aware that under the Gender Equality Act, DFID must have regard to the contribution its assistance is likely to make to reducing gender inequality (development). This is reflected in the number of female participants that have taken part in programme activities, particularly online learning. There are certain areas where it has been more difficult to influence change, particularly at senior leadership levels within Universities, which is inhibited by a lack of female Vice Chancellors. However, where possible DRUSSA has raised the prominence of existing female leaders through programme activities.

## B: PERFORMANCE AND CONCLUSIONS

# Annual outcome assessment
Outcome Indicator 1: Research uptake management is established as an organisational management practice.
The milestone has been met and the programme is heading in the right direction with 18 universities having achieved 40% of their Institutional Change targets so far, with five universities significantly exceeding their targets (70% or more). This includes 12 universities establishing university-wide policies or strategies that govern research uptake, providing evidence that sustainable research uptake management practices are being put in place.

Outcome Indicator 2: Universities are recognised by policymakers and practitioners as sources and contributors of development research evidence.
The universities are establishing pathways for research uptake, with progress most evident where the programme is working with Government ministries in Ghana and Uganda. Policy Symposia involving six ministries and four universities in the two countries have been held and Policy Fellows (from the universities) are in place in five of these ministries (with a sixth impending in the September cohort). All Fellows have designed comprehensive workplans with each Ministry, reflecting tasks and objectives of common interest.

# Overall output score and description
A – Outputs have met expectations.

# Key lessons
The strategic Vice Chancellor’s workshop was valuable in increasing credibility and commitment from senior leadership to the aims of the programme and the work of more junior staff.

# Summary of recommendations for the next year
The recommendations for next year are focused on maximising the sustainability of the programme as it enters its final year, and improving measurement of its impacts and value for money.

- Develop a Terms of Reference for planned independent evaluation activities by the end of September 2015 and agree with DFID before the end of October 2015
- Refine the proposed Value for Money indicators by the end of September 2015 and start collecting data immediately where it is not already available
- Ensure that activities are implemented at pace in the final year, particularly those aspects that have been in the planning stage for a long period of time, such as training under output two
- Ensure that fraud and anti-corruption policies are aligned with DFID’s guidelines by the end of September 2015

# Specific output recommendations
Output 1:
Association of Commonwealth Universities (ACU) to work with Centre for Research on Evaluation, Science and Technology (CREST) to agree on a higher final programme target for the number of second cohort online course participants by October 2015.
Output 2:
- On an ongoing basis training developed should be well adapted to what is most useful for the universities and most likely to be rolled out – and where possible embedded in existing processes.
- During the next year the digital knowledge platform should only be integrated to university systems where they have sufficient capacity and are genuinely likely to use it.
Output 3:
- As discussed with CREST resources should be made available from the programme budget to ensure any journal publications comply with DFID’s open access policy.
- As CREST have noted, case studies developed during the next year should be brief and practical advisory documents that will have appeal for the DRUSSA programme and the broader sector. Studies should be made available before publication of papers if this is going to delay the process significantly.
Output 4:
- In discussions with other partners the programme should finalise plans for how the Drussa.net resources will be made available following the programme by May 2015.
- The programme should consider how the resources Organisation Systems Design (OSD) helped produce for the consolidated course at CREST can be made available to others in the programme by November 2015.
Output 5:
- ACU should consult with the DFID Country Offices about the possibility of providing technical progress updates during upcoming visits to Ghana and Uganda during the next quarterly period.
- Fellows workplans should be analysed by ACU in order to assess workloads, objectives and sustainability before the end of October 2015
- ACU should be proactive about encouraging equal gender representation at the symposia, with a particular focus in Ghana over the next year.

# Has the logframe been updated since the last review?
Yes – the logframe was revised to take account of recommendations of the last Annual Review and reflect additional work the programme was doing. The changes were mainly minor changes to wording of milestones.
## C: DETAILED OUTPUT SCORING

Output Title	A core of specially trained and qualified university staff who can provide the strategic and operational leadership and expertise for research uptake management in their university
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of Masters and PhD / awarded in STS / Programme	Breakdown: / Estimated 6 Masters candidates from Cohort 1 (entry in 2013) on track to complete research assignment in 2015. / Doctoral candidates from cohort 1 have successfully submitted first four chapters of thesis for review. / 6 Masters candidates of cohort 2 / (entry in 2014) on track to / complete course work by end of / 2015 and proceed with research / assignments for completion in / 2016. / The 2 Doctoral students have / proposals accepted by the / university and are on track to / complete the 4 compulsory / modules	Milestone narrowly missed: / 6 Masters students from Cohort 1 (entry in 2013) are on track to complete research assignment in 2015 and expected to graduate in 2016. / 2 Doctoral candidates from cohort 1 have submitted their literature review chapters of their theses for review. / 6 Masters candidates from cohort 2 (entry in 2014) are on track to complete course work by end of 2015 and proceed with research assignments for completion in 2016 (graduation is expected in 2017). / Only 1 Doctoral student of cohort 2 (intake in 2014) has had a proposal accepted by the university, but is on track to complete the 4 compulsory modules. / Due to discontinuation of 2 PhD students in 2014, 2 new Masters students were allowed on the programme in 2015 (cohort 3). Both expected to complete their course work in 2015.
1.2 / Number of DRUSSA / participants / completing short / courses	Breakdown: / Minimum of 40 delegates / (annually) from DRUSSA / partner universities have / completed 4 day short / course that consolidates / learning outcomes of the / previous 6 short courses in / Research Uptake Management.	Milestone narrowly missed: / 39 individuals from 21 universities attended a 3 day short course in June, which focused on consolidating learning of the previous 6 short courses in RUM.
1.3 / Number of non- / DRUSSA participants / completing short / course in science / communication	Breakdown: / Minimum of 20 / participants (annually) / complete online short / course in science / communication	Milestone significantly exceeded: / 85 students (including 23 DRUSSA participants) completed the 6-week online short course, which finished in March 2015. / The course is accredited, leading to a Certificate of Competence from Stellenbosch University.

# Key Points
1.1 Overall the milestones for this output have been narrowly missed, although the programme is firmly on track to meet the final target for this output (a minimum of 16 Masters and Doctoral candidates graduate from the programme). There is 1 less PhD student in cohort 2 against the milestone this year because 2 students have been deregistered due to a lack of progress and inability to dedicate the time required. However 2 new Master students have now been accepted.

It is likely that a few of the PhD students may not complete their courses until the year after programme funding stops. These students are balancing full-time jobs in senior positions in Universities with part-time study. CREST is committed to supporting students beyond the end of the programme if they require it.

1.2 The number of participants taking part in the short course was 1 less than the target, due to some participants not being able to attend. It was decided that the course should last 3 rather than 4 days because participants have busy full time jobs and find it difficult to take time out.

1.3 The online science communication course has been very successful. The cost of participating in the 6 week course was $400 – with this subsidised for participants from DRUSSA universities. The cost was paid for by individuals and participant’s employing institutions. It was an interactive course with continuous assessment by the tutor and practical assignments. During the course a lively network developed; this transferred to Facebook from the university online system at the end of the course and has since grown to almost 400 people (including those who did not have the academic qualifications needed to be eligible for the course). The emergence of a self-sustaining community of practice is very encouraging.

The gender balance of participants on all courses is reasonably good – but best where CREST has some control (i.e. selection for academic courses rather than nominations from DRUSSA universities). For the online science comms course 72 were female and 15 male.

CREST has also been designated a centre of excellence on Science Technology and Innovation (STI) policy, resulting in significant funding from the South African government. It expects to be able to offer a range of opportunities to the DRUSSA universities it has developed good relationships with after the programme finishes.

# Summary of responses to issues raised in previous annual reviews
- CREST discussed the consolidated course with other partners to maximises the opportunity for building on different elements of the programme as recommended.
- The accredited online science communication course was offered at a discounted rate for DRUSSA universities to participate in.

# Recommendations
Given work implemented exceeded against the milestone target 1.3 by almost fourfold, ACU will work with CREST to agree on a more realistic programme target for the number of second cohort online course participants by October 2015.

Output Title	Strengthened strategic leadership and organisational capacity within DRUSSA partner universities to achieve greater uptake of their research by external users.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 / Strengthened / strategic leadership: / University leaders are / better informed and / develop collaborative / models and principles / to improve research / being taken up at / strategic and policy / level within and / across participating / universities.	Breakdown: / At least 16 senior leaders (vice / chancellors) have reviewed and / engaged in sharing of good / practice to improve strategic / leadership in research uptake. / Senior academic / representatives at 2 universities / in two countries have engaged / with policy makers at symposia / to strengthen ways research / evidence is used by policy / makers. / At least 8 universities / have strategies or policies / accepted by senior university / management that increase / accessibility of research outputs / to external users.	Milestone met: / 16 DRUSSA Vice Chancellors have reviewed and shared good practice. 11 face-to-face at the Vice Chancellors’ Leadership Seminar and 5 of the universities unable to attend have responded in writing. / 2 symposia took place in Uganda (48 participants and Ghana (25 vice chancellors). / 12 universities have developed a policy and strategy provision for Research Uptake Management which has been accepted by senior management
2.2 / Organisational systems, / processes and / approaches within / participating universities / are improved to enable / research being more / accessible to policy / makers and practitioners. / Workshops, working / groups, communities of / practice and training / materials are carefully planned and put in place / to support this.	Breakdown: / At least 18 universities have met 40% of targets in their university change programme, reporting positive change that is enabling research to be made more accessible to external users. / Integrating with the Research Uptake Campaign coaching and learning activities, the Communicators Network is / in place and members are / offered opportunities for further / training in research uptake and / science communication	Milestone met: / The Critical Success Indicator framework identifies 23 indicators of institutional change. At the time of reporting, 18 universities have met at least 40% of Critical Success Indicators. / Formally launched at the DRUSSA Progress and Training Conference in December 2014, the DRUSSA Communicators Network comprises: / At least 2 staff members from each university, nominated on the basis that they have/need to have Research Uptake Communication Skills; / Graduates of WP1 Communications Short Courses (almost exclusively Leaders and Champions). / Participants in the RUC2013, RUC2014 and RUC2015 activities raduates of CREST (WP1) online Science Communication course / A meeting with an element of training was held in Kigali. A Train the trainer course for delivery to the Network is being developed with the help of members for early 2016. Content and structure is to be finalised in September, with a trial scheduled for late 2015.
2.3 / Number of DRUSSA partner universities who have compiled and made publicly accessible a comprehensive record of their policies, literature and learning on Research Uptake Management for the benefit of others.	Breakdown: / At least 12 universities have compiled and made publicly accessible a comprehensive database of their policies, literature and learning on Research Uptake Management for the benefit of others.	Milestone exceeded: / The Research Uptake Management eLibrary (RUMeL) comprises 148 research uptake / policy and strategy documents, guidelines, presentations and links to institutional research repositories, authored and / designed by universities and research bodies worldwide, including from 16 DRUSSA universities.

# Key Points
2.1 Higher Education symposium are being planned for a further 2 countries in the next year.

2.2 Training materials are being developed based on the workshops and training previously given to nominated leaders and champions within DRUSSA universities. This will be complemented by content identified in a wider audit of training material available. The programme team are aware of demand
for training the universities can offer to new staff/ early career academics, however to ensure that this training is well adapted to university-expressed demand and joins up with existing training mechanisms in place at institutions, a scoping questionnaire has been disseminated to Leaders and Champions (August 2015)

2.3 The continuation of the RUMeL as a resource is currently being considered and universities are being consulted (alongside the training survey) as to whether they wish to host it on institutional sites or on internal digital platforms, and have the capacity to do so. Third-party website hosting of this digital material post-programme has been posited as an alternative means of maintaining access to this material.

# Summary of responses to issues raised in previous annual reviews
The training courses ACU are developing are aligned with CREST’s courses as recommended.

# Recommendations
It is crucial that the training developed is well adapted to ensure content is useful for the universities and most likely to be rolled out – and where possible embedded in existing processes, even if this means working with a smaller number of universities. Training materials that are just handed to the universities at the end of programme would not be satisfactory. There is plenty of information available, but this needs to be made useable. This should be implemented soon after the results from the survey of universities are available, given it was a year ago and initial audit of relevant training was undertaken.

RUMeL should only be integrated to university systems where they have sufficient capacity and will and are genuinely likely to use it. If it is going to require significant resource or capacity then the option of maintaining access through a third party site or archiving DRUSSA. net should be explored. The programme should consider whether the USB of resources compiled for the CREST consolidated courses provide sufficient information.

DFID and ACU should review the language used in indicator 2.1 by November 2015. Some of the existing milestones are problematic for objective measurement of progress as they refer to impacts which are difficult to measure at the output level. For example events may have taken place but it is difficult to establish if they fed through to improvements in strategic leadership.

Output Title	New contributions to the evidence base about Research Uptake and Impact Assessment in Africa and globally.
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 / Research undertaken and publication of documents and reports- specifically Review Report of scholarship on Research Uptake and Impact Assessment	Breakdown: / Scholarly research paper / published in peer-reviewed / journal (print/ online).	Milestone missed: / 2 papers have been submitted but not yet published.
3.2 / 10 in-depth case study reports on RU in development research projects at Group of 24 universities	Breakdown: / 6 case studies from Masters student thesis are to be disseminated upon completion of academic assessment. Dissemination will cater for multiple audiences on DRUSSA.net and special interest platforms and site, through seminars and RUM conferences.	Milestone narrowly missed: / Milestone will not be met until December 2015.
3.3 / Development of an operational DRUSSA M&E Framework to inform regular M&E reports	Breakdown: / Synthesis study of / quarterly progress / reports integrated in / annual report and / disseminated to DRUSSA / internal audience.	Milestone met / Annual report has been produced by partners.

# Key Points
  1. On the two papers that have been submitted, CREST have received feedback and will be resubmitting shortly. A third article is in preparation. The work is also being disseminated in other ways (including a recent presentation to decision makers at Fort Hare University).

  1. The SA academic year runs until January. It is expected that 6 case studies will be completed by Masters Students in the 2015 academic year, which will bring the total to 8 case studies by the end of 2015. Non-academic case studies that extract key learnings and messages from students’ dissertations will be published on DRUSSA.net and beyond.

# Summary of responses to issues raised in previous annual reviews (where relevant)
A communications plan for the literature review and case studies has yet to developed, however there has been a delay in producing the case studies.

# Recommendations
As discussed with CREST money should be made available from the programme budget to make any journal publications open access where possible.

As CREST have noted, the case studies should brief and practical advisory documents that will have practical appeal for the DRUSSA programme and beyond and made available before publication of papers if this is going to delay things significantly.

Output Title	The DRUSSA network is well informed about all elements of the programme, peer learning is encouraged, and relationships in the region are strengthened to sustain universities' capacity for research uptake.
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 / Number of universities that are providing examples of research uptake communication outputs that can potentially influence, inform and affect decision-making of their identified internal and external stakeholders.	Breakdown: / Communications network nominees from at least 18 universities, take part in user centred coaching activities and events, report improvement in skills/understanding, with 50% demonstrating those skills in the workplace and produce examples of research uptake communications for their identified audiences/users.	This milestone has been met: / 35 network members from 16 universities participated in the communications network event in Kigali, with 85 members from 19 universities participating in the broader RUC2015 campaign. / Pre and post participant survey results conclude that 100% of event participants demonstrated skills/understanding improvements. / More than 50% of participating Universities have published a Research Uptake Communications article on their University website following the course, with more in the pipeline.
4.2 / Audience size and usage for DRUSSA.net and Digest	Breakdown: / Public use of DRUSSA.net is maintained (43500 unique visitors annually). / Network of 900+ registered professionals working or interested in research uptake receiving the DRUSSA eDigest and e-Alerts. / At least 18 universities have contributed an additional 1 or more articles in the year sharing learning and progress; published on DRUSSA.net, the eDigest and delivered at regional workshops or symposia.	This milestone has been exceeded: / DRUSSA.net had 167,000 unique visitors during the past year, exceeding the target by 285%. / The network has 1246 registered users who receive quarterly eDigest and e-Alerts. / 22 of the 22 universities have contributed 1 or more articles (blogs, presentations regional workshops and/or documents for publication.)
4.3 / Regional network relationships, particularly RIMAs, are strengthened to support continuation of the universities' capacity for research uptake management	Breakdown / Regional networks, particularly RIMAs hold awareness/training workshops. DRUSSA university RIMA members share progress and lessons learned at 4 SSA regional conferences, seminars, workshops or meetings	Milestone met / University representatives and programme team members have presented at 4 regional conferences (WARIMA 2014, CARIMA 2015, SARIMA 2015 & EARIMA 2015).

# Key Points
4.1 Participant surveys conducted pre- and –post RUC2015 campaign participation indicated that all who participated in the workshop reported a significant improvement in their skills and understanding. It also indicated that many event participators have subsequently held dissemination sessions at their own Universities to share their RUC2015 insights and learning, and have shared RUC2015 materials with colleagues and within their University’s digital systems.

4.2 Of the 22 universities that have produced at least one article, 12 universities have produced between 2 and 10 articles, with a further 8 universities producing between 11 and 18 articles.

4.3 19 of the 22 DRUSSA universities have been present at Research and Innovation Management Associations (RIMA) conference held during the past year. A ½ day course on Basics of Research Uptake Management delivered at East Africa RIMA (EARIMA), which contained 56 participants, with pre and post assessments reporting positive changes. In addition, 4 non-DRUSSA universities requested follow-up provision of the course for their researchers. South Africa (RIMA) has also confirmed that Research Uptake training will be incorporated into their own training curriculum from 2016 and a broader SSA wide curriculum structure that is currently under development.

# Summary of responses to issues raised in previous annual reviews (where relevant)
OSD have been exploring how the resource on drussa.net and in the repository can be retained for use after the programme. As well as exploring whether universities wish to integrate the RUMeL database into any existing activities or repositories, the team have found that they could secure the site for archiving for up to 10 years. It should be secure and searchable, but not interactive in any way,,

# Recommendations
In discussions with other partners the programme should outline plans by December 2015 to detail how the Drussa.net resources, including RUMeL and short course learning resources, will be made available to DRUSSA universities and other interested actors in SSA before completion of the programme.

1. Consider how the resources USB OSD helped produce for the consolidated course at CREST can be made available to others in the programme.

Output Title	Political leaders and civil servants within 6 development oriented government ministries in Ghana and Uganda have improved capacity and incentives to use research evidence within the formulation and implementation of development policy.
Output number per LF		5	Output Score	A+
Risk:		High	Impact weighting (%):	10
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 / Ministers and senior civil servants in 6 ministries actively engage with policy focused research during and following attendance at policy symposia.	Breakdown: / Senior representatives from each Ministry have engaged with debates in 2 symposia in their policy area and can demonstrate a more active interest in research evidence.	This milestone has been met. / Senior representatives from each Ministry have engaged in 2 symposia, and a total of 13 symposia have been held across the two countries.
5.2 / Existence of evidence to indicate changes in both the formal an informal working cultures in the selected Ministries to encourage the use of research evidence in policy formulation and policy implementation.	Breakdown: / Fellows report indications of / positive change in the informal / working culture when compared / against baseline in 2 out of 6 / ministries	Milestone exceeded / Of the 5 existing fellow placements that have commenced, all have reported positive changes in informal working practices in 5 separate ministries.
5.3 / Number of civil servants within selected Ministries possessing and applying skills to seek out and use research evidence within their policy related work.	Breakdown: / 40/60 participants / demonstrate / improvement in / skills/understanding in / post-course assessment	Milestone exceeded / 64 participants completed training during the past year as part of three courses. 58 participants reported skills and understanding improvements, which were observed from pre and post-assessment results.

# Key Points
5.1 Fellows began placements in Ghana in March 2015 and in Uganda in January 2015. A further cohort of fellows will be selected over the next few months. Policy symposia held during the past year have engaged senior representatives from each Ministry, with the following characteristics being displayed:
All the topics discussed were chosen by the ministries and they reflect pressing policy issues facing the respective ministries today, such as “The Energy (Power) Crises in Ghana and its impact on Economic Activities” or “Quality Education: Some insights for Evidence Based Policy” in Ghana
Presenters for each symposium were chosen from local researchers by the in country partners for the purpose of promoting high quality local research and debate.
Attendance has been healthy across the ministries and a broad spectrum of stakeholders has been represented at the symposia (ministries, national agencies, civil society and commercial bodies).
Unless specified by the Ministry, local media (print, TV and radio), have been present at all the symposia so far.
After each symposium, a policy brief is prepared and circulated throughout the Ministry in question for consideration in upcoming decision making.

5.2 Fellow placements have reported successful changes in informal working practices within ministries, although these findings are self-reported so should therefore be treated with caution due to the risk of optimism bias and lack of independent verification.

5.3 The topics selected for short courses included Research Methods & Accessing Research. In Uganda, the Ministry of Public Service is committed to adopting DRUSSA training modules for inclusion in cross government civil service training following programme closure.

# Summary of responses to issues raised in previous annual reviews (where relevant)
This strand of work should continue to feed into discussions around other DFID funded capacity building work on evidence informed policy making, including the BCURE programme and the Africa Evidence Network.
# Recommendations
ACU should consult with the DFID Country Offices about the possibility of providing technical progress updates during upcoming visits to Ghana and Uganda

Fellows workplans should be analysed by ACU in order to assess workloads, objectives and sustainability before the end of October 2015

ACU should be proactive about encouraging more equal gender representation at the symposia, with a particular focus in Ghana over the next year.

ACU and DFID should agree on a mechanism to ensure that indicator 5.2 does not just rely on self-reported data to demonstrate progress against the end of the programme target.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

# Key cost drivers and performance
A number of activities have driven costs over the past year, all of which are closely linked to overall programme performance:

Universities lesson sharing - the original model of the programme management team visiting each university individually in previous years has been succeeded by a more coordinated network approach, which has broken down the total number of universities into smaller groups. This has encouraged a culture of lesson sharing and more efficient working practices whereby universities can share specific work, such as communication strategies with one another.

Preparation of training materials - developing and agreeing on training content to be delivered - both in government ministries and workshop plans represents a substantial cost of staff time. For example, a short course in science communications, developed last year cost just over £17,000. This was an accredited 6 week online course, completed by 85 students. Resources will feed into a second course to be run next year.

Programme events - the nature of the programme is based around forming partnerships within a network and building new institutional links between the research sector and government bodies. This requires expenditure on events such as policy dialogues and learning symposia, for which the average cost in the last year was £3,000 and £1,200 respectively. Topics generate evidence informed debates on pressing policy issues and help to strengthen sustainable working relationships.

Supporting specific institutions – DRUSSA provides capacity building support to 22 universities across SSA and 6 ministries from Ghana and Uganda. A high level calculation of total institutional support costs per university is estimated at £35k per financial year, whilst support under output five, which works with Ministries, is calculated at around £40k per institution, per financial year. These input costs are low in comparison to other programmes which are achieving similar outcomes, implying that this work represents good economy.

Masters and PhD students - each student carries an associated cost which CREST monitor in relation to how actionable and applicable learning is in practice.

# VfM performance compared to the original VfM proposition in the business case
The original business case contained a weak amount of information on VfM, which presents a difficulty in providing a comparison. However, following a recommendation in 2013 the programme has made efforts to restructure activities and cut those strands that were not providing good VfM. This flexible approach has continued, with plans amended to ensure focus on more effective interventions.

The last annual review specifically recommended that DRUSSA “Develop stronger Value for Money measures, with information on these collected over the next year.” Although measures have been developed into a framework, the team has not yet managed to populate this framework with data. It is recommended that DRUSSA prioritise data collection as this will help to provide DFID with valuable information in relation to the economy (unit costs) of interventions and some limited data on comparative delivery modes.

# Assessment of whether the programme continues to represent value for money
In relation to the costs of specific activities and the outputs delivered over the past year, it can be said that the programme represents good VfM. However, further work is needed to finalise a programme level VfM framework, which will provide a more robust comparative mechanism to look across workstreams. It is disappointing that as it enters its final year a formal assessment of the value for money of the programme remains outstanding.

# Quality of financial management
The quality of financial management has improved. DRUSSA has experienced difficulties with forecasting due to the high number of partners and changeable activities. However, significant improvements in accuracy have been made, which we hope continues next year.

Date of last narrative financial report	May 2015
Date of last audited annual statement	31 July 2014

E: RISK

# Overall risk rating:
This project continues to be rated as medium risk overall.

# Overview of programme risk
The most pertinent risks to programme delivery remain similar to last year same as last year:
- High university staff turnover – Key personnel within DRUSSA universities have left their posts during the delivery of the programme. Work has been carried out to ensure better horizon scanning and reporting to ensure that new staff become part of the existing network when they take up posts.
- Ministry engagement – Output 5 requires the programme to work closely with government ministries in Ghana and Uganda. Although there has been high demand from most organisations to date, the work of programme is subject to sudden political changes – particularly when it comes to timetabling events. Elections are planned in Uganda in early 2016.
- Academic completion and timescales – The PhD look likely to overrun as they are senior people with busy full-time roles – but CREST are confident they will be completed and CREST will support them beyond the end of the programme.

The programme also recognises that there are many things to implement in the final year to help increase the likelihood that progress made will be sustainable and change will continue in the right direction. This requires them to staying alert to risks that may delay or derail their plans given they will have little time to rectify things.

#### Fraud, bribery and anti-corruption
The ACU have separate but comprehensive anti-bribery and anti-money laundering policies. Anti-fraud processes are not covered through a single policy, but instead implemented in accordance with the ACU’s financial procedures manual and staff handbook. This ensures that financial controls are in place with regards to scrutiny of expense claims, verification of timesheets, procedures regarding procurement, handling of cash, collective decision making above certain financial thresholds, sanctions against staff and other implications related to instances of gross misconduct.

As part of the review the ACU were reminded that they should discuss any concerns relating to fraud and corruption with DFID. They currently have no concerns.

The nature of the programme means that the Universities involved do not receive direct funding or grants, but support, training and travel expenses which are either provided for them or refunded when receipts are provided. Per Diems or sitting allowances are not paid.

In relation to downstream partners, funding from the DFID grant is given to implementation partners in South Africa (OSD and CREST), Ghana (the Council for Scientific and Industrial Research (CSIR) and the Institute for Social, Statistical and Economic Research (ISSER) and Uganda (the Uganda National Council for Science and Technology (UNCST) and the Economic Policy Research Centre (EPRC)). The South African partners have recently been visited by the head of finance at ACU to check compliance with financial standards. The newer Ghanaian and Ugandan partners have had to be encouraged to submit their expenses claims, which are for relatively small amounts.

It is recommended that existing fraud, bribery and anti-corruption policies are collated into a single document by the ACU.

# Outstanding actions from risk assessment
The project risk matrix was reviewed as part of the annual review. The matrix is rigorous but would benefit from having the highest impact and highest probability risks highlighted. The review recommends that the matrix is reviewed on a more regular basis, with updates provided to DFID quarterly.

F: COMMERCIAL CONSIDERATIONS

# Delivery against planned timeframe
Overall delivery is on track, although there have been some minor delays across the programme. It is anticipated that further delays will occur in relation to Output 1 and Output 5 over the next year.

There are a number of activities that have been at planning stage for some time and need to be actioned quickly if they are to have the desired outcome, such as the train the trainer course for universities. Delivery against plans needs to be carefully monitored over the next year and delays mitigated where possible.

# Performance of partnership (s)
We recognise that DRUSSA have had a number of DFID programme managers over the course of the programme and a particularly high number of financial contacts. Some members have left at very short notice to provide surge capacity in emergency situations and planned transitions have taken place due to maternity leave. ACU have managed to maintain a close working relationship with DFID over the course of the programme, which should continue over the course of the final year.

As mentioned above, planning and working across the DRUSSA implementing partners has improved, which is critical for internal programme efficiency but also more broadly in relation to achieving strong outcomes. This should continue during the final year.

# Asset monitoring and control
The ACU maintains a project asset register. The nature of the programme means that there are currently no assets over £1000.

G: CONDITIONALITY

# Update on partnership principles (if relevant)
Delivery through the partnership principles with government systems is not deemed relevant for this programme. DRUSSA is a regional programme, which principally applies capacity building support to 22 private and government funded universities, 6 government ministries and a number of individuals. However, no funding is delivered through government systems. Therefore the partnership principles have not been included in the monitoring process.

H: MONITORING & EVALUATION
# Evidence and evaluation
The DRUSSA programme budget allocated £25k for an independent evaluation. The 2014 annual review recommended that the team “prepare the Terms of Reference for the independent evaluation by early 2015 so that evaluators can be appointed in sufficient time to evaluate the impact of the programme so far and report before the end of the programme.”

Unfortunately the programme has yet to develop a finalised evaluative case study ToR. Although a first draft was prepared in May, this was considered too broad and unrealistic given the limited budget. The programme partners are meeting in September to finalise a redrafted ToR, with the aim that evaluators will be appointed soon after.

It is important that the evaluative case study meets the following criteria:
- It is achievable, realistic and focussed. Acknowledging budgetary constraints, a single country case study could be appropriate.
- Work carried out should build on existing programme data and planned M&E activities that will be conducted by the programme during the final year.
- It should provide some robust evidence of outcomes; recognising it is too soon to evaluate impact.
- Provide some independent lessons for the sector on how to run capacity building programmes
- Throughout the process the evaluation must utilise CREST’s expertise in evaluation.
- The timing of this work should be aligned to report before the DFID Programme Completion Review is carried out in Autumn of 2016.
DFID will continue to provide guidance where possible and would wish to agree the final ToR with the programme.
# Monitoring progress throughout the review period
The programme manager at ACU is in regular contact with the DFID programme manager. There are formal quarterly meetings in addition to quarterly reports. Although an acting programme manager has recently been put in place at ACU due to illness, the transition has been managed very well.

During the past year a small, random selection of individuals from DRUSSA Universities involved in the programme were contacted to provide feedback. This was broadly positive, with individuals stating that they have used skills gained from short courses in practice and that they have amended their organisation’s research units thinking, planning and activities to incorporate research uptake, which was largely non-existent before DRUSSA.

Programme beneficiaries noted that some institutions have undertaken “a formal and deliberate drive in research uptake management and has made strides in institutional engagement” because of their involvement in DRUSSA. However, a number also mentioned the constraints they face in relation to staff time and concerns over how to continue to implement progress without the support of DRUSSA.
# Annual Review Process
This Annual Review was conducted by DFID staff in the UK:
- Kate O’Shea, Evidence into Action, Research and Evidence Division
- Ed Barney Evidence into Action, Research and Evidence Division

# Documents consulted:
1. 2015 Annual Report
2. Benchmarking Summary
3. Business Case
4. Risk Analysis
5. Logframe
6. DRUSSA site (www.drussa.net)
7. Quarterly Reports

2014 Annual Review