CHILD PROTECTION FUND II BUSINESS CASE ADDENDUM

SUMMARY INFORMATION
Project Name	Child Protection Fund II
Country or region targeted	Zimbabwe
Type of cost extension (if applicable)	Cost and time extension
Original project budget	£ 20,900,000
Original project start and end dates	July 2016 to June 2021
Cost extension value (if applicable)	£ 12,000,000
Total programme value	£ 32,900,000
New project end date (if applicable)	June 2022
Business Case link	http://iati.dfid.gov.uk/iati_documents/5488618.odt

INFORMATION
What is the project’s purpose?
The Child Protection Fund II is central to delivering on the fourth objective of the UK Aid Strategy in Zimbabwe, addressing extreme poverty, vulnerability and the rights of women and girls. It underpins DFID Zimbabwe’s contribution to ‘Leaving No One Behind’ (the Sustainable Development Goals) and to DFID’s Youth agenda. / The Child Protection Fund’s goal is to realize the basic rights of the most vulnerable children in Zimbabwe through provision of critical child protection interventions within a child and HIV-sensitive social protection framework. It builds on the CPF Phase I (2011-2016), adopting a multi-dimensional approach to child vulnerability which simultaneously addresses household poverty, gender disparities, disability, HIV and risk of violence, exploitation and abuse. Through a theory of change developed for CPF II, the programme aims to ensure that “children, families and communities access improved preventive and responsive child protection services reinforced by household and community economic resilience in targeted areas.” The CPF II outcomes are: / increased availability and accessibility of age/gender-appropriate, affordable, and well-coordinated Child Protection services in targeted areas (18 districts). / families and communities in targeted areas have information, knowledge and skills on violence against children and how to protect children / improved evidence-based policies and legislative instruments to address violence against children implemented and reinforced by institutional capacity / Harmonised Social Cash Transfer (HSCT) beneficiary households have improved economic capacity to protect children from practices that expose them to violence, abuse and exploitation / Taking lessons from CPF I, CPF II has a stronger focus on violence reduction through prevention, information management and governance structures and capacity. An increasing body of evidence about violence against children in Zimbabwe shows that violence is widespread and cuts across age, gender, and socio-economic status. There are many interlinked causes that include: family dislocation and an absence of positive parenting due to temporary migration; a high caseload of single and double orphans which is a legacy of the HIV pandemic; a propensity for resolving disputes violently that stems from generally high levels of trauma and stress in the country; overcrowded living conditions and high dependency ratios due to poverty and jobless-ness; children witnessing sexual relations from a very young age; and widespread unhealthy adolescent relationships in which negative coping strategies such as transactional sex are common, and in which regressive gender norms mixed with substance abuse generate high levels of intimate partner violence. / Weak institutional systems continue to negatively affect quality and adequacy of service provision, with remote, rural areas mostly affected. The CPF II focuses on building and strengthening integrated child protection response and prevention systems, by modelling a joined-up, quality approach in 18 targeted districts while supporting the further development and sustainable resourcing of the wider, national case management system. / The programme’s sustainability strategy rests on the twin-track approach of focusing on effective prevention strategies whilst also strengthening response systems to meet the child protection needs of vulnerable children and end the impunity of violent offenders. Whilst NGOs continue to play a vital role in the prevention and response systems and will likely always have a role in specialist service provision, the intention is to support Government to increase its own financial allocations to the sector year-on-year to make the hybrid public-private system fully effective and as well joined up as it can be. / Sweden (Sida) and the Swiss Development Cooperation (SDC) co-fund the CPF with DFID. Switzerland will continue into 2020 and Sweden will continue for the duration of this extension. / Achievements to date: / The programme has achieved an increase in statutory (acute) child protection case resolution rates from 23% (2017/18) to 43% (2018/19) against a background of staff attrition, lower case allocations, lack of transport and communications and lack of basic supplies. This is a good achievement and is largely attributable to the healthy Government-CSO-UNICEF partnerships built up, structured and gradually better coordinated since year one of CPF II (2016/7). NGO/CSO partners with UNICEF have promptly and constructively engaged with the Department of Social Welfare (DSW) to: / bridge staffing gaps by strengthening the social workforce, reaching agreement with the MoPSLSW to increase the responsibilities of Case Management Officers (CMOs) and increase the numbers of graduate interns under the Government’s social work graduate intern scheme. / directly manage the transport voucher system so that it keeps working for children and their adult carers to travel to referral appointments or to court (World Education International) / help District Social Workers get around for case follow-ups and overcome their communications constraints (all NGO/CSO partners) / support district child protection committee meetings for sustained case conferencing between the different responsible departments (health, education, home affairs, justice and social welfare) (all NGO/CSO partners) / Since 2016 the Government of Zimbabwe’s national case management system has served a total of 178,839 children in the 18 CPF supported districts. This is above the total reach target of 164,000 set at Business Case stage which is a clear reflection of the level of need. The system connects an informal community-based workforce (over 10,000 Child Care Workers) with Government District Social Workers and specialised civil society service providers through the process of case identification, referral, service delivery and after-care. / In 2018/19, the programme tested two good innovations aimed at increasing the early identification of children at risk of abuse: / schools-based early warning systems conducted by teachers in collaboration with Community Childcare Workers (CCWs) and District Social Welfare officers / house-to-house active screening for Violence against Children (VAC) conducted by CCWs with support from World Education International (WEI). / The national case management system demonstrated the strengths of its structure and partnerships in flexibly and rapidly responding to a succession of emergencies. Over 80,000 children in total benefitted from emergency child protection services and information provision closely linked to water, sanitation and health responses during and after the cholera outbreak (in October 2018), counselling and child justice services following civil unrest (in January 2019) and a variety of emergency child protection services following Cyclone Idai (in March 2019). / The functionality of the child protection management information system (MIS) improved with the introduction of an offline version that automatically updates when connectivity is restored meaning that internet downtime no longer prevents district offices from entering all cases. The system also helps with performance management by sending reminders of next steps in referral pathways and was complemented by increased support and supervision of social workers and a structured, modular training curriculum delivered for Child Care Workers which included aspects of maintaining personal resilience. Save the Children is exploring how to make the nine modules of CCW training content available digitally and in vernacular languages. In 2018 lead CCWs were issued with smart phones and now record new case details and case follow-ups digitally whilst at work in communities. Partners Childline and Africaid have developed Apps through which adolescents access advice and Anti-Retroviral Treatment (ART) treatment reminders. / UNICEF has made significant contributions to the language and advancement of the Children’s Bill, Child Justice Bill, the Harmonised Marriages Bill and the Cybercrime Bill. For the former three, adoption by Parliament is expected by the last quarter of 2019 which is a positive result. Going forward, it is important that UNICEF keeps the relationships built with the relevant officers and Centre for Applied Legal Research, where a lot of Zimbabwean legislation for realignment with the Constitution is born. The priority focus should remain on the afore-mentioned new legislation plus revisions to the existing Forensics Act, Disabled Person’s Act, Marriages Act, and Criminal Procedure and Evidence Act.
What is the objective of the cost extension or other changes?
Justification for an extension, referencing performance and further potential to achieve results: / In 2016 UK Ministers approved a five-year Child Protection Fund (CPF) II Business Case (2016-2021). However, the funding committed was initially for three years (£20.9 million) on the basis that outcomes for children needed to be better monitored and evidenced. Monitoring and evaluation efforts thus far had focused on numbers of children reached by case type. / Between 2016 and 2019 the child protection Management Information System (MIS) was designed and rolled out in the 18 Districts funded by the CPF and UNICEF and the implementing partners, with the Ministry of Public Service, Labour and Social Welfare (MoPSLSW), have focused on ensuring that more and more cases are successfully resolved. This means that the child’s protection needs have been satisfactorily met, even though the case may require further monitoring before the file can be closed. / The 2019 CPF Annual Review noted that statutory (acute) case resolution rates had risen from 23% in 2018 to 43% in 2019 which is a good achievement in an increasingly resource-constrained environment. It is based on these clear improvements that the UK proposes to extend our commitment to the programme for another two years under the existing Business Case. / The six Districts visited by the 2019 review team all commented on increased volumes of child welfare cases (such as neglect, basic needs not met, or not attending school) as a direct result of the deteriorating economic and food security situation. The programme will therefore need to renew its focus on improving the case resolution rates for these children in a similar way to the achievement on statutory cases. / The Purpose of the extension is to continue to increase the coverage, quality and inclusivity of child protection services, refining the effectiveness of the National Case Management System and enhancing its capacity to respond to the needs of the hardest to reach groups: children living with disabilities; children on the move; adolescent young offender; and young mothers. / Specifically, there is potential to achieve further results in the following areas: inclusive case management performance; cross-sectoral collaboration in preventing and handling sexual abuse cases; justice for children; and birth registration. / CPF will increasingly deliver improvements to the handling of sexual abuse cases in collaboration with SAFE (Stopping Female Abuse and Exploitation), a new DFID/Sida programme starting in 2020 that will focus on testing and evaluating the most cost-effective methods of preventing all forms of GBV and with Spotlight, a new EU/UN initiative that will increase access to services for GBV survivors. Spotlight aims to emulate the child protection case management model for adult survivors of GBV, initially in a few pilot districts. / There is also scope to a) complete the policy and legislative agenda that was slowed down by an election and other national legislative priorities and b) fully evaluate the effectiveness of the preventative child protection work undertaken by PLAN International and Childline that has focused on both positive parenting / caregiving and empowering girls and boys. / Summary of the changes and improvements to be made: / Harmonised Social Cash Transfer (HSCT) – see ‘Changes to the Business Case’ section on p. 11 / Access to Justice for Children / UNICEF will strengthen the Management Information System (MIS) business processes to reinforce its linkages with the child justice system. / The programme will increase the effectiveness of child and survivor-friendly justice services. This will include supporting the national Pre-Trial Diversion (PTD) programme that diverts child offenders of petty crimes from the criminal justice system, expanding it to additional districts and providing mental health support to young first offenders in remand centres. / The programme will also improve the operation of Victim Friendly Courts. Part of this will be to strengthen the capacity of health workers and the police on quality capture, analysis and use of forensic evidence for child survivors as per the Clinical Management of Rape Guidelines, and in closer adherence to the Multi-Sectoral Protocol on handling child sexual abuse. / Multi-sectoral coordination / UNICEF will collaborate closely with the Ministry of Primary and Secondary Education’s learner welfare department. Schools are important locations for the early identification of concerns around child mental health, violence and disability. Often the education system keeps the information within, but for the child and its family pro-active links with service providers outside the school environment are key. Violence prevention and response and child mental health will be built into teaching and learners’ tools, while education staff and social workers will be trained together on recognizing childhood trauma and service referral pathways. / UNICEF will work with the MoPSLSW to expand the membership of the Working Party of Officials (national child protection committee) to include the coordinator of the Zimbabwe Republic Police’s Victim Friendly Unit, the Judicial Services Commission’s Victim Friendly System, the Registrar General’s Office, the national coordinator on PTD, the policy department of the Ministry of Justice, Legislation and Parliamentary Affairs, and relevant departments in the Ministries of Health and Education. This will better reflect and encourage the responsibilities of multiple Ministries and Departments to deliver results under the NAP for OVC. / Birth Registration / Over the next three years, UNICEF will work with the Registrar General’s Office, the Ministry of Health and Child Welfare (MoHCW) and CSO partners (including those active on this agenda under the DFID funded TRACE civil society and governance programme) to: / Complete a national Civil Registration and Vital Statistics assessment to guide policy and system reform – this was finally agreed with the Registrar General’s Office in May 2019 / Build community awareness on timely birth registration through CSO partners / Support mobile registration in hard to reach and emergency-affected locations / Expand hospital-based birth registration services / Develop and implement an integrated digital birth notification and registration system that digitises the currently manual birth notification system by MoHCW and connects to the National Civil Registry System that captures registration of birth, through a partnership with the Registrar General’s Office and MoHCW. / Children on the Move / The CPF-II extension will more purposefully target children on the move. This group consists of children migrating within Zimbabwe and across borders, including refugee children, in search for work, to visit family or to escape lack of protection at home. On the move, these children are at increased risk of sexual exploitation and trafficking. This work will build on a recent sub-regional study completed by UNICEF, the existing work by CPF partner Save the Children who are already active on this agenda, and the upcoming research that will be commissioned by the SAFE programme. / The emphasis will be on the establishment of alternatives to detention, and access to places of safety and family care for children on the move. UNICEF will work the government to strengthen identification, documentation, tracing and reunification. UNICEF and partners work towards the following results: / Resuscitation of the national taskforce and development of a workplan / Strengthen participation of CSOs in the Trafficking in Persons Inter-Ministerial Committee / Expand the mandate of the Best Interests Determination panel to include all migrant children in need of the service. / Establish and strengthen cross-border migration forums between Zimbabwe and its neighbouring countries. / Support regular joint prison monitoring for children in detention / Provide technical support for establishment/upgrading of alternative detention facilities including regular joint monitoring of such facilities / Married girls / Child mothers / The programme will more actively include girls who are married and/or mothers. Currently these girls fall between the cracks of early marriage prevention programmes and child protection services that mostly concentrate on unmarried children. Even though they are children, married and/or young mothers are considered to fall under the mandate of the Ministry of Women’s Affairs (WA), which is dedicated to women’s empowerment. Unassisted, these are girls who will grow up vulnerable and disempowered, with few tools to break the cycle of vulnerability for the next generation. These girls are children with an adult jacket on, and need support with a child and family lens, that combines catch-up education, livelihood skills including financial literacy, and assisted access to child protection and family welfare services. UNICEF will work with the Ministries of PSLSW and WA and specialised CSO service providers to develop and test a new set of interventions targeting this group of girls in one rural and one urban district. / Disability inclusion / Children living with disabilities will be more structurally included and targeted. UNICEF will build capacity of the MoPSLSW’s Disability Department and the Disability Board, provide training on disability-sensitive child protection to CSO and Government partners, and disability-sensitive sexual and gender-based violence training to social welfare and justice stakeholders. This will strengthen case management and justice processes, supporting special procedures to ensure due process can be followed for children with disabilities. This includes special considerations for PTD decisions, as well as supporting age estimation procedures for children with intellectual disability. / While continuing to work with the CSO partners dedicated to supporting children with disabilities, the programme will also support mainstreaming of inclusion and targeting in prevention and response services implemented through CSO partners and Government partners, including services being offered by Victim Friendly Units and Courts. Community Child Care Workers will be trained on early identification and referral of disability. Lastly, UNICEF plans to support Zimbabwe to complete the country progress report on the Convention on the Rights of People Living with Disability and accelerate legal reform for enhanced protection for people living with disability. / Mental Health / One of the lessons learned under the current CPF II is the great need on the ground for accessible and ongoing mental health support for vulnerable children and adolescents. The impact of trauma is often ignored. Children are particularly vulnerable to trauma because of their rapidly developing brains. Over time, traumatic experiences in the lives of children can have a significant impact on a child's future behaviour, emotional development, mental and physical health. / Some of the innovative programmes providing low-cost community-based approaches to healing, trauma response and peacebuilding that have been piloted in Zimbabwe merit being taken to scale. CPF will partner with civil society organisations that take such community resilience building approaches. Examples include the REPPSI and Miracle Missions/Shamwari projects, Tree of Life, and the Friendship Bench model which could be a particularly powerful methodology for engaging the CCWs in community mental health approaches. Training District Social Workers and CCWs in psycho-social support principles and methods will assist with the appropriate identification of mental health needs during case intake and at case conferencing. This will be coupled with adding mental health awareness to the programme’s existing violence prevention work to increase both help-seeking behaviours and peer-support by children and caregivers.
What is the additional and total support the UK will provide?
The UK will provide a further £12 million for 2019-2022 to complete the programme of work laid out in the 2016-2021 Business Case and incorporate the performance improvements and refinements summarised in the previous section. The proposed annual budget outline is: / CPF II 2019/20 2020/21 2021/22 £ Total (3 yrs) / Output 1: Child Protection Services 1,883,000 1,725,000 1,708,000 5,316,000 / Output 2: Prevention knowledge and skills 645,000 715,000 720,000 2,080,000 / Output 3: Govt data, policy and legislation 595,542 658,165 643,519 1,897,226 / Staff and operations (15%) 580,162 605,539 632,185 1,817,886 / Sub-total 3,703,704 3,703,704 3,703,704 11,111,111 / HQ Cost-recovery (8%) 296,296 296,296 296,296 888,889 / Grand Total 4,000,000 4,000,000 4,000,000 12,000,000 / Budget notes on changes and improvements / Output 1 includes (i) support for protecting children on the move and (ii) children in humanitarian situations (total contingency for the latter of £1.2 million over three years). / Output 3 includes (i) continued improvements to the case management MIS and linking it to the Victim Friendly System, ii) technical support to the Programme Management Unit (PMU) in the MoPSLSW, (iii) technical support to the Registrar General’s Office to assess and build the national birth registration system, (iv) in service training of magistrates, prosecutors, police officers and forensic nurses for judicial system strengthening.
What are the expected results?
Results: / Age- and gender-appropriate, disability-inclusive, well-coordinated and high-quality child protection services provided in 23 districts (expanding from 18, an additional 5). / Communities and families have the appropriate knowledge and skills to protect children and prevent abuse from early childhood through adolescence / Government has improved evidence-based and integrated policies and legislative instruments to address child protection / Humanitarian and social protection programme beneficiaries benefit from complementary social care and protection services (up to 100,000 people) / New Log-frame Indicators: / CPF donors, UNICEF and programme partners will hold a log-frame workshop in September 2019 to analyse the available district data on demography and key vulnerable groups to establish the maximum potential caseloads and - from there - set reasonable yet stretching annual targets for the next three years: / Output indicator 1.3 No. children per year supported through the Integrated Justice System (by age, sex, disability type, HIV sensitive, statutory/non-statutory (national Victim Friendly System, Pre-Trial Diversion, Legal Aid Directorate) – annual targets to be agreed and will increase year on year / Output indicator 1.5 % of cases per year resolved by the Victim Friendly Courts – annual targets to be agreed with incremental improvements / Output indicator 1.7 Functional National Victim Friendly System which provides multi-sectoral oversight on justice service provision / Output 1.2 sub-indicators % of children reached with mental health and psychosocial support – target to be set as a proportion of the maximum estimated case load / Number of migrant unaccompanied minors and separated children identified and linked to comprehensive services – target to be agreed based on hotspot data produced by UNICEF / Number of vulnerable boys, girls and adolescents in humanitarian situations provided with critical child protection services (contingency budget line) / Output 3.3 sub-indicator % of all cases referred to the Department of Social Welfare that are entered into the Management Information System (MIS) – target should be 100% / Output 4 indicators MoPSLSW sets social protection policy direction and delivery priorities that reflect increased Government ownership, accountability and inclusivity. / HSCT beneficiaries are registered on humanitarian assistance lists / Approximately 100,000 people registered to receive humanitarian assistance in rural and urban areas received protection services
What is the approach to implementation?
Management arrangements: / The CPF II extension will retain the same programme management structure which integrates government and NGO efforts under the broader National Action Plan for Orphans and Vulnerable Children III (NAP III) and common CPF objectives. / The MoPSLSW remains the institution with the mandate to oversee the implementation of the NAP III, in coordination with other line and sectoral Ministries. A Programme Management Unit will be re-established to provide technical and secretariat support, institutionalised within the MoPSLSW and staffed by existing civil servants. To ensure adequate capacity to effectively deliver, UNICEF will facilitate the necessary technical support, including to the Case Management Technical Core Team and on results-based management. / The CPF pooled funding mechanism to finance NAP I-III will be retained as the main vehicle for mobilizing donor resources for the NAP in line with Paris Declaration of Principles of Aid Effectiveness. The pooled funding mechanism enables harmonization of donor support for the NAP, including technical reporting and financial accountability. It will continue to be managed by UNICEF, which will use its own systems of financial management and procurement. / UNICEF will continue to contract competent NGOs and private sector companies to deliver specific components of NAP III funded by the CPF. Contract management has proven time intensive, leaving limited time for UNICEF’s technical assistance role, one of UNICEF’s comparative strengths, and necessary for achieving a good balance between upstream policy and downstream community-level work. Therefore UNICEF will introduce a consortium approach by output, where one CSO takes a lead role in contract management of a small consortium of 2-4 CSO partners working towards the implementation of that result. / UNICEF will further develop the shock-responsiveness of CPF II by setting up a register of pre-selected, experienced partners by thematic emergency response area: justice for children; psychosocial support; trauma counselling; prevention of sexual exploitation and abuse; identification, documentation, tracing and reunification; and alternative care for separated and unaccompanied children. / Value for Money: / The programme continues to present good value for money. Case resolution rates (positive outcomes for children) improved by 20% since last year, despite an unconducive environment, and in large part due to effective public-private partnerships and continuous learning. The national case management system continues to adopt a pragmatic approach to a resource-constrained environment by relying on a trained cadre of para-professional volunteers. This means that the total cost of running the case management system per district per year is just $200,000 on average (UNICEF’s calculations submitted to the National Budget sub-committees to advocate scale up in late 2018). Having said this, it remains vitally important that this volunteer cadre continue to be robustly supported and that their future remuneration remains on the table for discussion with Government as part of a National Volunteer Policy. / Economy / The cost of a package to make a community childcare worker (CCW) functional (material, supplies and training): baseline in 2017 was USD $ 287.00. The total cost of supporting a CCW in 2018 was US$ 332.89. The increase is attributed to the replenishment of tools of trade for CCWs (who are volunteers) that was a key recommendation of the 2017/18 review in part to assist with motivation. Their equipment was worn out as it had not been replaced since the start of the first phase of CPF in 2011. They are routinely supplied with hats, bags, t-shirts, stationary and airtime. / Efficiency / Social workers’ workload (ratio of workforce to cases) has decreased. During 2017 the ratio of professional social worker to statutory cases was 1:339. In 2018 the ratio was 1:316. For non-statutory cases, the ratio is 1:219. The decrease is attributed to the 28 Graduate Interns who were seconded to the programme and the effect of the early warning system enabling earlier identification and pre-emptive management of cases. UNICEF will continue to monitor this as it affects case resolution and provision of quality child protection services. / Effectiveness / Case resolution of statutory cases improved in the 18 CPF districts from 23% (2017/18) to 43% (2018/19). This is attributed to the investment made in building the social welfare workforce, provision of technical assistance through mentorship and coaching of both provincial and district social welfare officers and secondment of additional workforce to support case work. / The percentage of statutory cases [sexual abuse] handled in accordance with established timeframe per annum: In 2017 only 19% of survivors of sexual abuse cases recorded by the Family Support Trust (FST) sought professional medical assistance within the requisite 72 hours whereas in 2018 28% of children sought assistance within 72 hours, UNICEF has supported FST to launch a campaign called ’Every Hour Matters’ as part of ensuring that girls report and receive assistance in time to obtain Post-Exposure Prophylaxis (PEP) and emergency contraception. / Equity / The programme continues to strengthen the leave no one behind agenda with an increased number of children with disabilities (3,350 cases in 2018/19) supported through the NCMS. Most of the cases involving children with disabilities were identified and reported through CCWs who received disability inclusive-child protection training and mentorship support from JF Kapnek Trust. The CPF also trained 41 District Social Welfare Officers in sign language. / The successful Early Warning in schools and VAC screening in communities introduced in 2018 will, taken to scale, improve early identification and reach in remote and hotspot areas. / UNICEF will continue to track the following Value for Money (VfM) indicators: / Economy Total annual cost of a package to make a community childcare worker (CCW) functional (material, supplies and training) / Cost per case handled and cost of technical assistance per case (includes staff supervision, mentoring, and case conferencing) / Efficiency Social workers’ workload (ratio of workforce to cases) / Average number of days taken by Victim Friendly Courts to conclude cases of child sexual abuse, taking volume of cases into account / Effectiveness Case resolution rates (annual average percentages per case category) / Percentage of sexual abuse cases handled within the stipulated timeframe (national, legal standards) / Equity Number of children from harder to reach groups identified and assisted through the NCMS / Due regard to Gender Equality: / The intervention is designed to prevent and respond to violations of children’s rights. National data points to gender differences in exposure to different forms of violence at a young age (physical, emotional, sexual). The programme has developed gender-specific strategies that will address the vulnerabilities of both boys and girls in different situations. These situations include (but are not limited to): girls at risk in intimate-partner relationships; boys at risk when they are in conflict with the law; both boys and girls at risk when living with carers who are not their biological parents. / The power of individual learned values versus social and peer pressures is acknowledged. Consequently, prevention work focuses on changing drivers of violence that include dominant ideas about men and masculinity and traditional gender roles. This will involve working with groups of both boys and girls as well as with their respective adult role models, leaders and ‘circles of influence’. Boys, girls, men and women are all expected to benefit because national research shows a strong link between experience of violence at a young age and perpetration of violence as adults. A new DFID funded programme (SAFE, beginning in 2020) will robustly test and evaluate a number of different contextually-tailored methods of preventing gender-based violence and shifting the underlying social norms. / The programme’s previous phase identified the potential for doing harm when statutory (acute) child protection cases are brought into the justice system and experience delays. As a result, the programme is taking a systems approach - in fewer districts initially - to build stronger and more responsive joined-up services. / Results measurement tracks child protection and welfare cases resolved by type and gender. Prevention work is monitored and evaluated according to impact on girls and boys. The cash transfers impact evaluation has explored effects on early sexual debut, safe sex, and incidences of violence in addition to welfare benefits such as retention in school and meeting of basic needs, all disaggregated by gender. / Safeguarding: / In 2018 UNICEF trained all CPF partners in the UN principles and standards on Preventing Sexual Abuse and Exploitation and conducts spot checks on reporting systems that are in place at partner and community level. However, the challenge is more complex when considering the number of Government employees who are in daily contact with children and vulnerable adults across the social welfare, education, health and justice Ministries and Departments. Vetting and accountability systems need strengthening across Government. UNICEF’s social policy unit will support the development of a cross-Government safeguarding policy and implementation plan during this extension phase with the aim of reducing risk in areas that are beyond the programme’s immediate control. / Fund-flow: / The CPF co-funders (Sweden and Switzerland) allow an annual maximum of £200,000 to be spent on supporting the field monitoring and supervisory operations costs of the Government of Zimbabwe’s Department of Social Welfare. UK funds are not used for this purpose.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The major shift relates to Output 4: the Harmonised Social Cash Transfer (HSCT). This will not be funded by the CPF going forward because of low Government budget utilisation (output indicator 4.4 which scored a ‘C’ in the 2019 Annual Review), reflecting low levels of commitment and affordability. However, there are opportunities to link the caseload of children at risk to other programmes of social assistance through operationalising cash plus social care. There are also opportunities to provide technical support to the GoZ / MoPSLSW to help them achieve the policy coherence and sense of policy direction that further external funding support will likely be contingent on. These opportunities are reflected in changes to Output 4 for the remaining period: / Technical advice to the MoPSLSW to shape Social Protection policy direction, deploying technical assistance for system strengthening (DFID, UNICEF, WFP, World Bank, by December 2019) / Link the HSCT and child protection caseload to short-term and externally financed humanitarian assistance programmes such as the WFP Lean Assistance Programme which is also funded by DFID for 2019/20 (UNICEF, WFP MoPSLSW by August 2019) / Provide protection services to recipients of social assistance in both rural and urban settings, linking the DSW and CPF specialist service providers to the Lean Season and Urban assistance caseload (UNICEF, WFP, MoPSLSW by October 2019) / UNICEF has revised the Theory of Change (ToC) to reflect this shift (see Annex 2)
[note] This indicator will measure utilization and efficiency of the system so will have two component targets: A retrospective indicator: of all the cases managed in previous year, 100% of cases entered in the system A current indicator: of all the cases managed in current year, at least 50% of the cases entered in the system

Annex 1 - Delivery Chain Map and Risk Matrix

CPF Risk Description	Action	Mitigating Actions

Disruption of programme activities due to heightened civil unrest (violent demonstrations and heavy-handed response from the state)	Treat and Tolerate	Working with Government and NGO partners, UNICEF will track possible disruptions to programming due to civil unrest and constantly review strategies to ensure ongoing protection of children and access to services by children and families. UNICEF will ensure ongoing political economy monitoring and documentation to ensure availability of data and information for appropriate programme adjustments.
Potential child protection violations during unrests and demonstrations	Treat	UNICEF will strengthen child protection surveillance mechanisms, including informal networks and mechanisms for regular updates by implementing partners. Partnerships between justice and welfare sectors facilitate seamless justice sector, welfare and protection prevention and response mechanisms.
Unstable economic environment characterized by inflation, shortages of fuel and other basic goods and a multi pricing system. / Macro-economic conditions curtail attainment of programme results.	Treat and Tolerate	UNICEF will regularly track financial resources and disbursements made to partners. Regular meetings with partners are conducted as part of broader partnership management. New and emerging bottlenecks as well as financial and market intelligence informs resource planning and financial decision making given the uncertainties in the macro-economic environment.
Possible abuse of children and vulnerable adults in contact with the CPF system	Treat	UNICEF shared the Prevention of Sexual Exploitation and Abuse (PSEA) guidelines with all partners. PCAs include clauses on PSEA and UNICEF staff and partners have been trained on PSEA. In 2019, safeguarding will be integrated into the CCWC training to be implemented by SCI.
Possible policy shifts and slow-down of planned activities due to leadership changes within the Ministry of labour and Social Welfare	Treat	UNICEF will explore opportunities for joint high-level interaction with the Minister, PS and Donors to facilitate increased understanding of programme dynamics by the new Ministry management. UNICEF conducts Management meetings with Ministry leadership so that they are actively involved in the programme.
MoPLSW Staff attrition	Treat	Working with the Ministry, UNICEF will advocate for the appointment of CMOs as Probation Officers in line with Statutory Instrument 125 of 2013.
Weak connections of the Child Protection MIS with other relevant actors like Justice	Treat	UNICEF will provide technical support to the MoPSLSW in MIS development, maintaining the team of MIS personnel. UNICEF has supported the MIS to be linked to the Childline systems as part of ensuring that cases are followed up. UNICEF has facilitated discussion with a possibility of ensuring that Justice and Social Welfare cooperate Multi-sectoral training on handling child sexual abuse under CPF addendum will also be an opportunity to strengthen the response linkages between the social welfare and justice sectors.
Poor HSCT exit Communication	Treat	An HSCT workshop was convened in Masvingo and an exit communication, whose implementation has already commenced in the last quarter of 2018, was developed. UNICEF will continue to closely monitor and engage on the exit communication especially in CPF supported districts. In addition, given 6 out of the 10 most drought-affected districts as identified in ZIMVAC, are CPF districts, discussions will be held on LSA and HSCT targeting with WFP, MoPSLSW and the DFID resilience team with the aim to ensure integration of HSCT households into the LSA beneficiaries list.
Limited internet connectivity to support CM MIS	Treat	UNICEF funded the use of mobile phone-based tethering as this proved to be the best contextual solution. Use of a blanket service provider was expensive and impossible to apply given absence of a universal provider. PS has committed to engage with Internet service providers to ensure better connectivity
Possible demoralization of the CCWs in supporting the CPF community-based activities	Treat	UNICEF finalized the procurement of CCWs working tools- airtime, ID cards, T-shirts, Hats and bags. Bicycle procurement is nearly complete.
Compromised “cash and care” due to discontinued CPF funding for the HSCT	Treat	UNICEF will support the integration of child protection with other existing social; protection programmes like the LSA. From the 10 highest food insecure districts identified from the LSA, six are CPF (Binga, Mudzi, Mwenezi, Buhera, Bulilima and Mangwe). Further UNICEF will fund the government and NGO’s partners activities towards provision of child protection to social protection beneficiaries. UNICEF will also lobby for the inclusion of additional services beyond child protection to the cash and care approach.
Lack of traction in the Child protection legislative reform.	Treat	UNICEF will continue to support the Justice sector with the view of alignment of laws with the Constitution. UNICEF will continue to lobby critical partners to ensure that child justice laws remain key on the parliamentary agenda.
Possible hijacking of CPF interventions for political mileage	Treat	The delivery of all the NAP activities will continue to be apolitical on the basis of need with the designated officers only allowed to administer the programme. NAP gatherings will solely called for the purposes of social service delivery and the provision of child protection complimentary services only without meddling from any political parties.