Annual Review - Summary Sheet
Title: Support to the Public Procurement System in Mozambique
Programme Value: £3.9m		Review Date: September 2015
Programme Code: 202463	Start Date: November 2012	End Date: November 2016

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	B	A	A
Risk Rating	High	High	Medium

Summary of progress and lessons learnt since last review
2015 has been a year of change for the Government of Mozambique – with implications for this project specifically (and others). A new government administration – under the leadership of a new President, though of the same party – was elected in October 2014 and took office in January 2015. The former Ministry of Planning and Development and Ministry of Finance were merged into a single Ministry of Economy and Finance (MEF). There were substantial delays in the approval of the budget for 2015. Finally, the new Ministerial team in MEF requested that the Procurement Oversight Unit (UFSA) review the procurement regulation, with a view to updating and improving it.
This context had a significant impact on the project and its deliverables over the past year. The merging of the former Ministry of Planning and Development and Ministry of Finance into a single Ministry of Economy and Finance (MEF), within which UFSA sits, created a period of uncertainty whereby a new organic structure was developed to reflect the new mandates. Delays in the approval of the budget for 2015 affected UFSA’s ability to use both its own resources and DFID Financial Aid to implement activities in the first half of the year. Finally, the requested to review the procurement regulation, with a view to updating and improving it; this has been a priority of UFSA since June and has diverted staff time and resources away from other activities. Although this represents an opportunity for the project over the longer term it has also hampered progress in some areas over the past 6 months; and has required the Crown Agents team to be flexible in working with UFSA on a changing list of priorities – which they have done effectively. Donor comments to the review of the regulations (coordinated by DFID) have welcomed the opportunity to introduce some changes to the law, but also emphasised the fact that the most important improvements to public procurement in Mozambique will come from effective implementation of the law (new or old).
Despite an uncertain operating environment for much of 2015, the project is overall making good progress towards its overall objective. There is a good basis on which to build going forward: procurement units in all government departments have been created separate to the admin and finance departments, a new procurement regulation will be approved before year end, and revised manuals, compliance tools etc. should all contribute to an improved system for public procurement. A ‘big bang’ push on capacity building to help procurement units across government effectively apply the new procurement regulation, in line with their updated mandates and job profiles will be important in 2016 – and Crown Agents are well placed to support UFSA to do this.
However, in addition to the budget delays, execution of the Financial Aid component of the project remains low given complicated internal government procedures that make UFSA’s access to the funds difficult. For the period to date, this has not been a fundamental obstacle to project progress – since UFSA have prioritized receiving Crown Agents advice and using this to develop tools, guidelines, an online portal etc. The ‘big push’ envisaged for 2016 will require access to resources to support training, workshops etc. UFSA has confirmed it would be happy to consider alternatives to Financial Aid for making the necessary resources more easily available to support this push; including through adjusting the CA contract if feasible.
Summary of recommendations for the next year
UFSA, CA and DFID to use annual planning and budgeting process over next few months to ensure full alignment between UFSA and Crown Agents work plans and that they are well designed and sequenced to support effective implementation of the roll out of the revised procurement legislation – including following up on the key recommended action areas highlighted for each output.
DFID Mozambique to explore with Commercial and Procurement Department, and then with Crown
Agents, what options there may be for reducing the Financial Aid component and reallocating some of those funds to an alternative delivery mechanism to support the complementary activities that will be needed to really ensure a concerted roll out of the new legislation and complementary documents.
DFID to check that ARIES information for project is fully aligned with contract commitments regarding end dates.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3743498.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4586030.xlsx

Outline of the programme
The UK is providing Financial Aid and Technical Assistance to the Government of Mozambique’s Procurement Oversight Body (UFSA) to strengthen public procurement operations and oversight in Mozambique over the period 2013-16. Total support is expected to amount to £3.9 million; of this £2.6m is financial aid to the GoM and £1.6m is for a Technical Assistance (TA) package managed directly by DFID and delivered by Crown Agents (CA). TA is provided through a long term resident adviser and a budget for short term TA missions coordinated by Crown Agents in collaboration with UFSA.
The legal and institutional framework for public procurement in Mozambique was relatively robust, with the establishment of a Procurement Oversight and Regulatory Agency (UFSA in its Portuguese acronym) in 2005 and the approval of modern regulations in 2010. However, in terms of implementation, procurement reforms have been lagging behind relative to other core areas of PFM, as evidenced by: lagging procurement-related PEFA sub-indicators; analysis contained in the 2008 update to the Country Procurement Assessment Report (CPAR); and procurement-related recommendations emerging from annual Auditor General reports on State Accounts and external audits commissioned for donor-funded programmes (e.g. large basket-funds in health and education).
Key functions of UFSA include: overseeing effective implementation, by spending departments, of government procurement law and policies; recommending updates to those laws and policies as required; managing a procurement information system for monitoring overall trends and implementing evidence-based policies, and providing guidance and capacity building to procurement practitioners.
Weaknesses have been identified both at the operational level i.e. capacity and practices of decentralised procurement units (UGEAs) especially at the provincial and district layers of administration, and at the supervisory level. UFSA currently has limited capability to adequately perform its core functions. Donor funding targeted at procurement strengthening and reform has, in recent years, been scarce. It has focused more at the operational/UGEA level (especially in the context of support to particular sectors and/or selected provinces and districts), rather than at strengthening overall policies, processes and oversight of the national public procurement system as a whole.
This comprehensive DFID programme of support to UFSA was designed to fill an important gap in support to key aspects of the procurement function in Mozambique’s public sector. It initially included a pilot component in the education sector aimed at facilitating dialogue and interactions with the Education sector, and to help ensure that reforms are not tackled and supported only by central institutions (e.g. Ministry of Finance) and from the top downwards (by national level ministries) but also from a sectoral level and at deconcentrated operational levels.
This multi-pronged approach for supporting coordinated reforms at a national and sectoral level was expected to increase the pace of reform by generating ownership outside of the central ministry responsible for regulations and policy setting. However, it became clear quickly that the sector pilot component was not working: the long term adviser placed in MINED was not operating at the right level and playing the envisaged role, MINED counterparts were less committed to the project, and mechanism by which the sector could access financial aid was too complicated, and coordination between UFSA and MINED in relation to the management of the project was insufficient. Following the AR 2014, the programme (and CA contract) was restructured to remove the long term adviser from MINED, and reallocate the budget to that for the short term TA missions, whilst making it clear that MINED could still benefit from support if they requested particular assistance from UFSA and could still serve as a pilot e.g. for rolling out of trainings etc.
2015 has been a year of change for the Government of Mozambique – with implications for this project specifically (and others). A new government administration – under the leadership of a new President, though of the same party – was elected in October 2014 and took office in January 2015. The former Ministry of Planning and Development and Ministry of Finance were merged into a single Ministry of Economy and Finance (MEF) which created a period of uncertainty whereby a new organic structure was developed to reflect the new mandates. It also led to substantial delays in the approval of the budget for 2015. Finally, the new Ministerial team in MEF requested that UFSA review the procurement regulation, with a view to updating and improving it.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Despite an uncertain operating environment for much of 2015, the project is overall making good progress towards its overall objective. That said 2016 will be a critical year for rolling out much of the work that has been completed to date and which has been centred on developing new policies, guidelines, tools for supervision and eProcurement etc. During the next year the focus will be on with a focus on making sure that personnel in procurement units across government receive the necessary knowledge, skills and support to ensure that they can make effective use of these new tools to improve the quality of public procurement.
Outcome Statement:	Public institutions at the national and provincial levels run transparent and open procurement competitions
Indicator(s)	Milestones for this review	Progress at Sept 2015
a. Number and share of public sector contracts not related to personnel that are granted prior approval by the Administrative Court (SAI)	Decrease in share of contracts that are not rejected for resubmission by the Supreme Audit Institution	Data not yet available. To be followed up.
b. Extent of follow-up to procurement recommendations left by internal and external audit institutions	Baseline defined on procurement recommendations left by audits and extent of follow-up by UGEAs.	In 2014, 282 supervision visits were completed to follow up on the use of Direct Award and in particular the recommendations of the IGF and TA related to the application of the procurement regulation. This figure will serve as a baseline.
[newly added] / c. % government expenditure contracted through Direct Award	[establishing baseline] / 49%	2014 is the first full year for which data exists on government spending on procurement of goods and services according to different procurement modalities.

Progress towards the outcome indicators is reported (where data is available) in the table above. In relation to SAI review of contracts, data is not yet available. Though it is also unclear to what extent this remains a good indicator for the project; given that the SAI prior review threshold is very low and its own backlogs prevent it from doing an effective job in processing them. As milestones in the logframe for the following period should be reviewed, this indicator should be revisited.
Regarding supervision and follow up on procurement related audit recommendations, there is now a baseline for 2014. Data for 2015 will be available in early 2016: that said with the constraints faced by UFSA in accessing budget resources in the first half of the year, and the energies diverted to restructuring of the Ministry of Economy and Finance and revising the procurement law in the second half of 2015, it is unlikely that supervision and follow up will have increased this year.
Importantly, in this review we have added a new indicator, based on data which is also available (for the full year) for the first time for 2014 and can now serve as a baseline going forward. That this data – showing the percentage of procurement by different modalities - is now available is a first sign of progress; going forward we would like to see the % of procurement completed by Direct Award reduced.
Output	Score	Weight
1	A	20%
2	A	20%
3	B	20%
4	B	20%
5	A	20%
Overall Score		A

Overall output score and description
Overall, the project scores an A; though two outputs are scoring a B.

Key lessons
As predicted, the broader government context had a significant impact on the project and its deliverables over the past year. The merging of the former Ministry of Planning and Development and Ministry of Finance into a single Ministry of Economy and Finance (MEF), within which UFSA sits, created a period of uncertainty whereby a new organic structure was developed to reflect the new mandates. Delays in the approval of the budget for 2015 affected UFSA’s ability to use both its own resources and DFID Financial Aid to implement activities in the first half of the year. Finally, the requested to review the procurement regulation, with a view to updating and improving it; this has been a priority of UFSA since June and has diverted staff time and resources away from other activities. Although this represents an opportunity for the project over the longer term it has also hampered progress in some areas over the past 6 months; and has required the Crown Agents team to be flexible in working with UFSA on a changing list of priorities – which they have done effectively. Donor comments to the review of the regulations (coordinated by DFID) have welcomed the opportunity to introduce some changes to the law, but also emphasised the fact that the most important improvements to public procurement in Mozambique will come from effective implementation of the law (new or old).
There is a good basis on which to build going forward: procurement units in all government departments have been created separate to the admin and finance departments, a new procurement regulation will be approved before year end, and revised manuals, compliance tools etc. should all contribute to an improved system for public procurement. A ‘big bang’ push on capacity building to help procurement units across government effectively apply the new procurement regulation, in line with their updated mandates and job profiles will be important in 2016 – and Crown Agents are well placed to support UFSA to do this.
However, in addition, to the budget delays, execution of the Financial Aid component of the project remains low given complicated internal government procedures that make UFSA’s access to the funds difficult. For the period to date, this has not been a fundamental obstacle to project progress – since UFSA have prioritized receiving Crown Agents advice and using this to develop tools, guidelines, an online portal etc. The ‘big push’ envisaged for 2016 will require access to resources to support training, workshops etc. UFSA has confirmed it would be happy to consider alternatives to Financial Aid for making the necessary resources more easily available to support this push; including through adjusting the CA contract if feasible.
Key actions
DFID Mozambique to explore with Commercial and Procurement Department, and then with Crown Agents, what options there may be for reducing the Financial Aid component and reallocating some of those funds to an alternative delivery mechanism to support the complementary activities that will be needed to really ensure a concerted roll out of the new legislation and complementary documents.
UFSA, CA and DFID to use annual planning and budgeting process over next few months to ensure full alignment between UFSA and Crown Agents work plans and that they are well designed and sequenced to support effective implementation of the roll out of the revised procurement legislation – including following up on the key recommended action areas highlighted for each output.
Has the logframe been updated since the last review?
No. But the logframe should be revisited as part of the annual planning process for 2016, to ensure it is well aligned to changing priorities and time frames for key activities within the work plans to be developed. This should include revisiting the appropriateness of the outcome level indicators.

## C: DETAILED OUTPUT SCORING

Output Title	UFSA's performance strengthened through the provision of high quality strategic support
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones for this review	Progress at Sept 2015
1.1 Planning and management of UFSA's operations reflect strategic priorities	Operational plans aligned to strategic objectives / Strategy mainstreamed and used to enhance UFSA's profile and visibility	Met. / The new UFSA strategic plan is being used as basis for UFSA’s annual operational plans – and as the basis for activities planned for both the FA and TA components of the project.
1.2 Targeted TA outputs delivered to strengthen UFSA operational and organisational performance	Plan for short-term TA agreed / At least one short-term TA output delivered	Met. / A plan for the provision of short term TA was agreed between Crown Agents, DFID and UFSA in early 2015. Over the year this has needed to be flexible to enable CA to effectively respond to the evolving context. CA have successfully managed this flexibility to deliver a number of STTA products and make good progress on others.

Key Points
UFSA had finalised its new Strategic Plan 2015-2019 by September 2014. It had decided to await the formation of a new government before seeking approval; since then and with the attention that the new government has placed on the structural reorganisation following the merger of the Ministries of Planning and Development and Finance into a new Ministry of Economy and Finance, it was decided that Ministerial approval was not a priority at this stage. Rather approval of the annual operational plans should be the priority.
UFSA’s operational plan for 2016 has been approved. Initially drafted at the end of 2015, coordination meetings between DFID, CA and UFSA were used to ensure that the operational plan was indeed well aligned to the priorities set out in the strategic plan and that the CA work plan for technical assistance was also well aligned to UFSAs priorities for the year. Coordination meetings throughout the year have then been used to check progress and help reprioritise in response to emerging issues – in particular the decision by the new Vice Minister of Finance to review the procurement law.
The revision of the law has impacted on CA’s own work and plans for short term TA missions. In response to requests from UFSA they have provided their inputs to the procurement legislation review (including a paper drawing comparisons with peer countries in the region and with the UNCITRAL model procurement law to inform recommendations on best appropriate practice for Mozambique) and to thinking around the status of UFSA, with a proposal that it should be given more autonomy.
In addition to the above papers, CA have made good progress in delivering short term TA to support plans for eProcurement (see output 2). However, some other activities (e.g. finalising a review of the procurement manuals, or the plans to support implementation of new job profiles) have necessarily been deprioritised and delayed as a result of the review of the law, since it will have implications for them.
DFID led a coordinated development partner input to the consultation of the revision of the procurement law: whilst a number of CA recommendations had already been taken on board, DFID used the comments process to emphasise a number of those that had not, or where there remained some ambiguity, including that it would be worth further considering increasing UFSA’s autonomy through a change in its status.
Summary of responses to issues raised in previous annual reviews (where relevant)
n/a – covered above.
Recommendations
Once the review of the legislation is completed, the following activities will be prioritised, not least since they will be an important part of the activities needed to support roll out and implementation of the new law:
- Plan for roll out of new procurement job profiles (UGEAs)
- Revision of procurement manuals – and training associated with roll out of manuals and new job profiles
- Plans for mentoring of procurement staff

Output Title	UFSA's strategies plans and operations are informed by relevant procurement information
Output number per LF		2	Output Score	A
Risk:		M	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones for this review	Progress at Sept 2015
2.1 A reliable and user-friendly MIS is introduced to generate relevant, accurate and timely information on procurement operations	ToRs for integrated PMIS feasibility study (inc. e-readiness assessment) agreed and activities initiated	Met. / An e-readiness report completed in March 2015; STTA mission and workshop. / Following on from this a draft e-procurement roadmap has been prepared and presented to UFSA in August 2015.

Key Points
Crown Agents have been making good progress in their support to help UFSA set out plans towards introducing eProcurement as an important part of developing a Procurement Management Information System (PMIS). As recommended in the last Annual Review, CA have worked with UFSA to deliver a feasibility study, and roadmap towards eProcurement, which will inform government’s plans in this area – and activities to be supported under this project in future years.
In September 2014, UFSA and CEDSIF (the government unit responsible for implementation of Mozambique’s Financial Information Management Information System, eSISTAFE) agreed to a series of actions including the undertaking of a Feasibility Study, including an eReadiness Assessment. A draft study was delivered in May 2015 – drawing on results of a questionnaire completed by government entities and from workshops conducted in February and March (the latter with the presence of an eProcurement specialist hired as short term TA by CA).
The lack of an e‐Procurement system is a major barrier to improving the efficiency, effectiveness and transparency of public procurement in Mozambique. Currently, key procurement data cannot be retrieved from SISTAFE as it only holds basic payment data related to contracts and the lack of such data is a major barrier to improving the procurement system in Mozambique. That said, the current SISTAFE functionality (developed in 2013) is still an improvement over the previous complete lack of information. It disaggregates public expenditure on goods, services and investments executed through e-SISTAFE into different procurement modalities. 2014 is the first year for which the data exists for a full year for government spend on procurement of goods and services and establishes a baseline against which the use of different procurement modalities – and particularly the use of Direct Award – can be monitored. In 2014, Direct Award accounted for 49% of all spending. However, this data continues to have many limitations (e.g. only covers contracts awarded that year, and not spend against previously awarded contracts, and only covers the “internal” component of the budget despite the fact that government oversees procurement of a large number of goods and services using “external” funds that are often fully under its control e.g. through sector common funds, or loan funding).
The procurement system in Mozambique is experiencing the usual challenges associated with the standard decentralised public procurement model but the lack of spend visibility and procurement data makes it almost impossible to quantify the true extent of the issues and challenges. Nevertheless, based on the experience of many other countries adopting e‐Procurement, it is likely that in the long run the financial savings of implementing e‐Procurement in Mozambique could equate to a minimum of 5‐10% of total annual public procurement spend per annum (US$50 –US$100m). These significant savings compare to an estimated investment cost of US$ 4 ‐5 million for the acquisition and maintenance of an e‐Procurement system over 5 years would give a very attractive, high return on investment. Further work to make this case, and secure Government Investment into this, will be required.
However, this investment is not warranted right now. Mozambique is currently at a low level of readiness for the adoption of e‐Procurement (53%) and is not ready to adopt many of the more beneficial e‐Procurement features. Reasons for this include the lack of appropriate legislation permitting the publication of procurement notices online or online tendering: the current development of a new UFSA procurement website and application will provide some quick wins in terms of transparency and the collection of basic data from UGEA’s (see also output 5).
Mozambique would benefit from a progressive introduction of e‐Procurement based initially on using the data recording and reporting features of an e‐Procurement system. At a later date, when the level of readiness has been raised and the necessary changes in the legislation introduced, selective adoption of e‐Procurement for the high spend UGEAs would generate significant financial and nonfinancial benefits such as reduced procurement timescales, increased participation of Small to Medium Enterprises (SMEs), improved procurement planning and financial management. Implementation of an ‘end to end’ fully functioning e‐Procurement system which covers the full procurement cycle from planning to payment should be considered at a later date once the areas identified in the e‐readiness assessment have been addressed.
Based on the Feasibility Study, Crown Agents have now developed an eProcurement Roadmap and submitted this to UFSA at the end of July 2015. This provides recommendations on areas of focus for the short term (next 6-12 months) as well as medium to longer term (1-2 years). Short term recommendations involve: ensuring that eProcurement is addressed in the ongoing review of the procurement decree, launching of the new UFSA website and portal; piloting selective use of eAuctions and digitising the catalogues for goods and services developed last year; continuing to work with the newly developed module for eSISTAFE that captures payment by procurement modality to also implement a unified business register and enable sharing of information between eSISTAFE and the procurement portal; and adopting a unified enterprise email system for UGEAs. The roadmap also sets out options for further developing eProcurement capability over the longer term to help optimise procurement business across government, reducing duplication of data entry, improving collaboration and information sharing across UGEAS, document storage and records management and electronic notification of procurement opportunities using email and mobile.
In leading the preparation of donor comments on the draft revision to the Procurement Decree, DFID emphasised the importance of the law creating the space for increased online procurement methodologies (in addition to improved functioning of the current manual system).
Summary of responses to issues raised in previous annual reviews (where relevant)
n/a – covered above
Recommendations
The key next steps will be for UFSA to formally review and approve the eProcurement roadmap. CA has not yet received formal feedback given that UFSA has been prioritising the review of the legislation. DFID will use upcoming coordination meetings to encourage UFSA to provide feedback and set out the process of approval and adoption of the roadmap as soon as possible. This will inform activities in the CA and UFSA workplans for the coming year.

Output Title	An effective monitoring and compliance framework in place and operational to support UFSA's oversight function
Output number per LF		3	Output Score	B
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones for this review	Progress at Sept 2015
3.1 Effective tools and methodologies for monitoring UGEAs compliance in a systematic way are developed, tested and mainstreamed	Monitoring and compliance tools and methodologies piloted in a sample of UGEAS / Plans for supervisions adhered to	Not fully met. / Progress in this area has been slower than planned though there has been progress since the last Annual Review. Slow progress is in part due to the fact that activities have been deprioritised given work to revise the procurement law and the fact that the revision will have implications for the tools as they are finalised and rolled out.
3.2 Evidence of improved coordination, data sharing and strategic collaboration with the internal and external audit institutions (Inspector General of Finance and Administrative Tribunal)	Plans for joint audits and information-sharing adhered to / Set-up of system for tracking audit recommendations on procurement and extent of follow-up in a systematic way	Met. / UFSA, the finance inspectorate, and supreme audit institution have a joint work plan for 2015 to ensure better aligned work and information sharing in support of improved internal controls, especially those related to public procurement. This will be monitored and reported against.

Key Points
An initial monitoring and compliance (M&C) framework was presented to UFSA by CA in November 2014; UFSA took longer than planned in providing comments but did provide constructive inputs in January 2015. CA also presented to UFSA an M&C Tool to support supervision, started work on preparing Supervision Guidelines, and agreed with UFSA a proposal for updating the procurement manual (and making its use mandatory - which UFSA has agreed to). These new tools are aligned with the M&C framework and the current procurement legislation. Follow up activities were delayed, though with hindsight this was fortunate, as the new Vice Minister’s decision (in June 2015) to review the procurement legislation will have implications for the M&C framework and the accompanying tools, guidelines, manuals etc.
Since June, whilst in parallel providing inputs to the revision of the law, CA has continued to work on: (i) preparing the supervision guidelines though at a slower pace as resources are reallocated to the revision; and (ii) on developing the M&C tool, including presenting this to UFSA in August 2015.
In 2014, UFSA completed 205 supervision visits, at central and provincial level. In the first half of 2015, UFSA has completed 108 supervision missions of state institutions. However, there are concerns that the full year performance for 2015 will be below that of 2014 given the energies and resources that have been diverted away from core activities into the work on reviewing the procurement law.
In order to support improved monitoring and compliance, UFSA has been collaborating with the Inspector General of Finances (IGF, which essentially plays a cross-government internal audit function) and the Tribunal Administrativo (Supreme Audit Institution, SAI). The three control and oversight institutions have prepared a harmonised work plan to be implemented in 2015, which will see UFSA working with: the IGF to improve internal controls around public procurement; and with the SAI for improved follow up of recommendations made in the context of the SAI’s audit and report on the state accounts, for better information sharing around the Single Cadastre which registers eligible suppliers to the state, and to monitor the SAI prior and post-review process for procurements.
Summary of responses to issues raised in previous annual reviews (where relevant)
n/a - covered in above.
Recommendations
Priority activities will now include:
- Completing the Supervision guidelines
- Piloting the Monitoring and Compliance tool by UFSA with selected UGEAs
- Support the revision of the procurement manual – focussing on ‘how’ to apply the new procurement legislation and making it mandatory
- Developing a training programme for UFSA based on the supervision guidelines and manual
- Continuing to implement the joint UFSA, IGF, SAI work plan and ensuring it can be monitored and reported against.

Output Title	Enhanced capability of UGEAs to undertake more effective, efficient and transparent procurement
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones for this review	Progress at Sept 2015
4.1 Evidence of strengthened UGEA capacity	TNA tested in a sample of UGEAs with results informing UFSA's training operations (strategy, contents, methodologies of delivery and targeting of UGEAs) / UFSA training plans are adhered to / Directive on UGEA composition drafted, approved and disseminated	Not fully met. / The milestone related to the Training Needs Assessment was deprioritised following discussion with Crown Agents. Training has been delivered to a number of agents (though the pace has dropped in 2015) and MEF has clarified the role of UGEAs – making them a standalone department in all ministries, and through more clearly defining their role in the proposal of the updated procurement legislation. Although not all of the specific milestones have been met – or at the envisaged scale/pace - there has been concrete progress related to this output during the year and it can be expected that this output will be a priority over the next 6-12 months, not least linked to roll-out of the new procurement regulation.

Key Points
A pilot Training Needs Assessment was conducted in the previous review period for the Ministry of Education – the then pilot ministry. However, Crown Agents concluded that this was not effective and that the result was poor information and analysis. Following discussions it was agreed to deprioritise the completion of Training Needs Assessments given that CA and UFSA have – from their direct work with UGEAs – a good understanding of the reality of their situation. Instead, it was agreed to prioritise the finalisation and approval of job profiles for UGEA staff.
Using short term TA, CA has supported UFSA to develop job profiles for UGEA staff. These were submitted to UFSA by February 2015 and though informally approved by UFSA, were not submitted to the Superior Council of the Ministry of Finance for its approval. Subsequent to the revision of the procurement law, UFSA has confirmed that the job profiles may now need some fine tuning, but it plans to include them in the package of “complementary documents” that will be approved by the Government as integral to effective implementation of the procurement law (along with a revised and now obligatory procurement manual, standard bidding and contract documents etc.) CA has already started working with UFSA to develop a plan to support the roll out and implementation of the job profiles – this will be part of the package of TA that CA will provide to support the implementation of the new regulation.
Positively, and in a move that will support the roll out of the job profiles and ‘professionalization’ of a procurement career within Government, as part of the reorganisation of government ministries following the installation of the new government, a Government directive was issued that requires that the UGEA in each spending department has now been designated as a standalone department (rather than part of the administration and finance department as was previously the case). This has been confirmed in the new organograms that have been approved and circulated for various departments. The draft revised procurement legislation also includes expanded detail on the role of the UGEAs in implementing the law. [Donor comments on the draft ask that this be further clarified to explain how this should work at decentralised and deconcentrated levels of government.]
Notwithstanding the changes ongoing, UFSA has continued to provide training on the implementation of the procurement law in the first half of 2015; 326 government officials and a further 264 economic agents received training. However, there has clearly been a reduction in pace; by the end of 2014, 2,326 government officials from procurement units had been trained in the application of the procurement regulations, the SISTAFE functionality, and in the application of the current procurement manual. This slowdown is unlikely to be corrected for over the second half of 2015, since with the revision of the legislation ongoing it will be more important to adjust the various tools to align with the new law and then focus on a wholesale rollout, focused on training of UGEAS, in 2016.
There is a good basis on which to build: the new status of the UGEAs, new procurement regulation, revised manuals, compliance tools, SISTAFE functionality and portal (see output 5) should all contribute to an improved system for public procurement. A ‘big bang’ push to support training in all of these things (including through new and innovative means e.g. online training modules) will be important in 2016 – and Crown Agents are well placed to support UFSA to do this.
One particular concern however is that this output should be a particular user of the DFID Financial Aid component. As discussed in section 5, expenditure against this component has been relatively slow – largely due to complicated internal government procedures that make UFSA’s access to the funds difficult. For the period to date, this has not been a fundamental obstacle to project progress – since UFSA have prioritized receiving Crown Agents advice and using this to develop tools, guidelines, an online portal etc. However, for 2016, a big push on capacity building to help UGEAs effectively apply the new procurement regulation, in line with their updated mandates and job profiles, should be the priority. This has been discussed with UFSA who would be happy to consider alternative options for making resources available to support this push; including through adjusting the CA contract if feasible.
DFID and UFSA have also discussed how to monitor implementation of this through the budget support Performance Assessment Framework (as part of the PFM pillar) to ensure high level buy-in and support from the Ministry of Economy and Finance.
Summary of responses to issues raised in previous annual reviews (where relevant)
n/a – covered above.
Recommendations
Complete revision of procurement law, and then updates to the full package of “complementary documents”. Develop ToRs for an implementation plan to support role out of the Job Profiles, including training needs, performance evaluation guidelines etc.
DFID Mozambique to explore with CPD, and then with Crown Agents, what options there may be for reducing the Financial Aid component and reallocating some of those funds to an alternative delivery mechanism to support the complementary activities that will be needed to really ensure a concerted roll out of the new legislation and complementary documents.

Output Title	Improved public access to public procurement information
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones for this review	Progress at Sept 2015
5.1 Evidence of gradually improving UFSA internet portal (in terms of publishing relevant and timely procurement information to bidders and the public)	Phase I of Portal project successfully implemented; UGEAs made aware and trained on usage / Baselines on Portal statistics established / Public forum on public procurement established and operational	Met. / Phase I and II of the portal project have now been completed, with phase III now beginning. The portal is live, and though some information is still to be uploaded for the period from Jan 2015, it is now being used to e.g. advertise open government tenders. The forum is informally operational e.g. inputting into the consultation process on the revision of the procurement law.

Key Points
Good progress has been made by UFSA, with Crown Agents’ support, in revamping UFSAs website to become a functioning procurement portal, which is now live at http://www.ufsa.gov.mz/ and though it is not fully operational it is now being used as a tool for public procurement (see screen shot below which shows a number of currently open tenders).

By February 2015, UFSA had acquired new servers, IT infrastructure had been relocated and upgraded, and the portal application was subject to testing in advance of making it available to UGEAs and the public.
By May 2015, the second development of the application and interface had been uploaded to UFSA’s IT infrastructure, the portal database was populated with initial data collected by IT staff, the old portal was deactivated, and a proposal to launch the portal (publicity plus training) was developed.
By August 2015, phase II of the implementation of the portal was concluded and the site was made available to the public. There is already some historical data on the portal, but efforts are still needed to complete the data entry to cover the full financial year 2015. The official launch has been delayed (due to the revision of the law). Though not formally operating (will be launched with the portal), the public procurement forum has become informally operational with all relevant stakeholders identified during last year’s mapping process (e.g. private sector, public companies, spending department UGEAs, the Procurement Professionals Association) invited to the public consultation on the draft revised law, for which turnout was high and interaction and inputs of good quality. This has been followed up with individual meetings e.g. with the private sector business association (CTA) and with development partners.
Summary of responses to issues raised in previous annual reviews (where relevant)
The last review raised the importance of broader stakeholder consultation (covered above) and DFID’s role in keeping the broader donor group informed of progress in the procurement area. As lead donor for procurement, DFID has been keeping the broader development partner group informed about updates – and supporting UFSA to fulfil its reporting requirements against the budget support Performance Assessment Framework indicator, and to provide inputs to development of a new PAF indicator in this area, which could usefully focus on following up implementation of these priorities and the new procurement law.
In addition, given the range of activities that have been undertaken in the past year, DFID has asked the Crown Agents long term adviser to present an overview of progress and key issues to the donor group in early October.
Recommendations
A number of actions are now required to effectively launch, raise awareness and provide training on the portal (e.g. implementing training plans, and disseminating the procedures) as well as completing the data upload for the period Jan to July 2015.
Attention will then turn to the third phase of development of the procurement portal and should focus on:
- Developing and implementing a ‘workflow’ for authorisation to procure
- Further development of the area restricted to UGEAs
- Developing a functionality for companies to request registration as state suppliers
- Specifying and contracting back-up infrastructure to guarantee and safeguard “24-7” access and operation
Organise CA presentation to interested donors for early October 2015.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The project has 2 components – financial aid and technical assistance. An overview of spending and updated forecasts against the budget is included in the Table below, broken down by UK Financial year.

Within the Technical Assistance component the key cost driver are costs associated with the technical advice being provided to UFSA – the costs of the long term TA (including living costs etc.) and the costs of short term TA missions (consultants fees, travel costs etc.). As this part is managed under a milestone based contract we do not have detailed information on exactly how the resources are broken down across categories.
Within the Financial Aid component, expenditure is broken down using Government of Mozambique expenditure classifications. For example, in the first half of 2015, expenditure is broken down as shown in the chart. Costs related to staff participation in seminars and training within Mozambique (27%), plus the procurement of goods (8%) and services (61%) have accounted for the largest use of funds to date.

At this point, there are some concerns that the Government will continue to be unable to execute the financial aid component at the level foreseen in the project. Certainly, execution against the financial aid component has been lower than planned to date. On current revised forecasts (which assume the project continues into 2017 since the Crown Agents contract does, giving the full three years since the project started late – ARIES action is required to align timeframes on the system to the contract) the financial aid component is still set to underspend by approximately £860,000. To date, the low level of execution of this component has not been compromised progress towards project objectives – since the TA support provided by CA has been the focus. However, as discussed above, 2016 will be a big year for the project and will require that UFSA can mobilise the financial aid resources to support project activities – training, seminars, workshops, dissemination etc. If it cannot, then project success will be compromised. UFSA has confirmed that complicated government procedures do hamper its ability to efficiently and effectively access resources; and that it is happy for DFID to explore (including with CA) alternative means of making these resources available to support key project activities over the next year. This may involve a reduced financial aid component, and some management by CA of funds to support events related to their TA. As discussed above, this will need to be further discussed with CPD and with CA.
VfM performance compared to the original VfM proposition in the business case
A series of qualitative VfM measures were established as the basis for assessing VfM of the programme. An update is provided in the table below. On the whole, progress reflects that discussed for the outputs above. There has been progress made on important aspects that will improve the VfM of the public procurement system in Mozambique; therefore delivering longer term VfM for UK investment. Although in some areas progress has been slower than envisaged, these reforms are complex and subject to the broader government operating context. Plans for 2016 will accelerate progress in areas that are so far a bit behind (e.g. the supervision model). The outcome indicator measuring the (hopefully declining) use of Direct Award is also a measure of VfM – with more competitive procurement delivering better VfM for the Government of Mozambique.
Proposed measures of VfM
Indicator / VfM element	Rationale	Progress
Progress against PMIS Strategy (also see logframe output 2) / economy, efficiency, effectiveness, cost-effectiveness	Reliable procurement system baselines would only be available with the introduction and mainstreaming of a PMIS that can enable recording data on transactions across all stages of the procurement cycle (such as procurement plans, notices, tenders, contracts and payments). This will enable the establishment of reliable baselines for tracking performance of the procurement system by UFSA (e.g. to spot bottlenecks in the cycle and large variations in unit-costs)	Some progress now being made towards an improved PMIS: the SISTAFE functionality is working (a first step), the portal is operational, the e-Readiness assessment is complete and a draft eProcurement Roadmap submitted.
Improvements in UFSA model for procurement supervision (also see logframe output 3) / efficiency, effectiveness	Current model is overly centralised and inefficient (as base on field missions by centrally-based staff and not sufficiently analytical and strategic).	Monitoring and compliance tool has been developed and supervision guidelines are being finalised. Once approved – and used in complement to the new regulation – these tools are expected to improve USA supervision.
Improvements in UFSA model for training UGEA staff / (also see logframe output 4) / effectiveness, cost-effectiveness	Current model means UFSA staff-undertake all procurement training of thousands of UGEA staff. Recommendations have been provided to encourage outsourcing at least basic training to a service provider, so as to improve quality and free-up UFSA staff for more analytical and strategic oversight roles	The plan for rolling out training and UGEA job profiles will include options for different delivery mechanisms that will be more sustainable over the longer term.
Cost savings by UGEAs from the online publication of bidding announcements and contract awards rather than in newspapers (at least 500USD per procurement-related insertion per day) / Economy	The procurement portal upgrade offers an opportunity to consider mainstreaming the availability of bids/awards notices online	The portal is now operational and UGEAs are beginning to use. No estimates of cost savings yet available, but these are believed to be substantial.

Assessment of whether the programme continues to represent value for money
Yes, the project continues to represent Value for Money. Both the Technical Assistance and Financial aid are supporting UFSA to deliver important reforms to the public procurement system which will yield cost savings, and efficiencies, for the GoM over the longer term – and at a level much bigger than the UK investment.
Crown Agents are proving themselves to be a flexible and responsive implementing partner in providing the Technical Assistance. The small team in UFSA is working hard to deliver a large workload – on the one hand this offers VfM, on the other there are concerns that they won’t be able to effectively administer the FA at the pace needed through 2016. As mentioned above, DFID will explore alternative options.
Quality of financial management
Financial Management and Reporting is of fair quality. The CA contract does not offer us detailed information on the TA component. The UFSA Reporting usually requires some follow up to get all the information we need but that is linked to their lack of familiarity in administering financial aid ( a ministries department for admin and finance would normally do that, but in this case UFSA is responsible for reporting). As noted above, there are concerns about absorptive capacity and that this could compromise project results.

Date of last narrative financial report	September 2015
Date of last audited annual statement	January 2015 (covering FY 2013). / Report for FY 2014 is under preparation.

The audit report for 2014 is to be completed under UFSA supervision; they have contracted Ernst and Young and the final report will be available in November.

E: RISK

Overall risk rating: Medium.
The risk rating has been downgraded to medium – although there is financial aid provided, and the area is contentious, the overall size and impact of this programme relative to others in the portfolio suggests that a Medium rating is warranted.

Overview of programme risk
An updated risk assessment is provided in the table below.

Table 2: Reviewed Risk Matrix – stick in Annex
Risk description / type	Impact / Probability	Update / mitigation
New administration shows little appetite for procurement reform / [country risk]	M / L	Risk rating adjusted – low probability / On the contrary, the new administration has shown a large interest in procurement reform, requesting a revision of the law. This can be an opportunity, though in fact implementation of (new or old) law remains the key issue. For the current period though, the revision is diverting staff time and energy from other activities. Mitigated through use of CA TA to support activities and preparation to support UFSA with roll out of new law next year.
Senior staff reshuffle following appointment of new administration / [partnership risk]	M / L	Risk rating adjusted – low probability / Has not happened yet and head of UFSA has been confirmed in her post. However, GoM continues to move people so this could still be a risk. Mitigate through active engagement and quick establishment of personal and institutional relationships (involving HoO as required)
Insufficient commitment to, and ownership of reforms from MF/UFSA / [programme risk]	H / L	Risk rating adjusted – low probability / UFSA commitment remains high and has been energised further by the task of revising the law. Take advantage of this to support them in roll out next year.
Lack of coherence between DFID programme and other interventions limits potential for overall impact / [programme risk]	M / L	Risk rating unchanged / DFID remains the only donor with significant engagement in central/strategic level procurement reform. We will continue regular communication and coordination in the context of the procurement WG and feeding into the budget support dialogue (including to develop new PAF 2016-2018)
Weak coordination and collaboration between the many project stakeholders undermine programme coherence and impact / [programme risk]	H / M	Risk Rating unchanged / Coordination and communication between DFID, CA and UFSA are good. Now that MINED has been removed as a key project partner the weak collaboration there has been addressed. DFID capacity to engage has been stretched over past year but will be strengthened with arrival of new PFM lead in January 2016.
Weak technical/managerial capacity and motivation to implement reforms effectively (exacerbated by high staff rotation) / [programme risk]	H / H	Risk rating unchanged / Gaps in capacity are evident both at central and decentralised/UGEA level, and will widen with the trend towards increasing deconcentration of procurement operations to provincial/district levels. However, programme is explicitly designed to help address this. See discussion under outputs 1, 3 and 4 for analysis of issues (the implementation of actions under output 4 will help mitigate).
Weak financial management and reporting capacity increases fiduciary risk / [financial risk]	M / M	Risk Rating unchanged / Mitigate through close engagement during planning and reporting periods. Ensure audit findings are acted upon. Consider additional TA to build FM capacity.
Low levels of absorptive capacity in UFSA, complicated by complicated government procedures followed by the Financial Aid component, hamper use of FA and so implementation of TA related products.	H/H	New risk. / DFID to explore with UFSA, CA, CPD and others what alternative mechanisms could be employed to ensure that project resources are available to support key delivery activities in 2016.

Outstanding actions from risk assessment
None from last year.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme started slow, with the Crown Agents contract only signed in early 2014. As a result, the overall project is behind the original schedule set out in the business case. However, the project is broadly on track against the revised schedule agreed following the contract’s inception phase.

Performance of partnership (s)
Crown Agents is performing very well. The long term advisor has built excellent relationships within UFSA and is demonstrably a trusted part of the team. He – and the wider CA team – have shown themselves to be able to be flexible and responsive to changing needs and demands of government, whilst also maintaining a focus on programme delivery and keeping things moving. The UK based team provide financial and narrative reporting one schedule, are responsive to DFID requests for information, and also use the relationship with DFID to flag things we should be aware of or that they feel we can help raise with UFSA to push forward.

Asset monitoring and control
n/a.

G: CONDITIONALITY

Update on partnership principles (if relevant)
This programme does provide a small amount of Financial Aid to government. As such the partnership principles are relevant to overall programme monitoring, though we would not expect to use this programme to respond to deteriorations in the partnership principle assessment unless the deteriorations were directly related to this project.

DFID assesses the GoM commitment to the UK Partnership Principles on a regular basis in line with the UK Conditionality Policy. The box below provides a summary of the latest assessment, which was cleared by the Secretary of State in June 2015.

Summary of Latest Assessment of GoM commitment to UK Partnership Principles
Overall, it is assessed that the GoM is broadly committed to the four UK Partnership Principles. Commitment to poverty reduction and to improving public financial management are strongest (though there is of course room to improve the efficiency and effectiveness of strategies deployed to deliver on this) and these come out clearly in the new administrations five year strategic plan. Concessions made by FRELIMO in the run up (electoral law, peace agreement) suggested commitment to a peaceful process which has been followed through since then. President Nyusi has offered a number of signs that he intends to run a more transparent, inclusive and accountable government. But he has still to provide substantial evidence of this – the last few months have focussed on reorganising his government, the next few months must focus on delivery. The Government is exploring options – including in consultation with the UK – for models to support improved public sector delivery that may work in the Mozambican context, looking to examples in Tanzania, Malaysia and elsewhere. Within this, one of the biggest challenges will lie in demonstrating a step-change in efforts to implement the anti-corruption laws and so increase the pace of efforts to fight corruption.

H: MONITORING &

Evidence and evaluation
No evaluation is planned for this project.

Monitoring progress throughout the review period
Crown Agents provides quarterly performance reports. UFSA provides six-monthly reports. These are used – along with regular dialogue (monthly coordination meetings) – to discuss progress, performance and any emerging bottlenecks.