Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	September 2015

Title: Private Sector Energy Efficiency Programme
Programme Code: 202555	Start Date: July 2013	End Date: November 2015

Summary of Programme Performance

Year	2014	2015
Programme Score	B	B
Risk Rating	Medium	Medium

Financial Position

Original Programme Value	£8.62 million
Extensions/ amendments
Log-frame revisions (with dates)
Total programme spend	£8.62 million

Follow up actions required following closure
- Collect final results
- Allocation of project assets
- Note whether additional funding has been raised by the NBI to enable programme to continue
- One year from closure – meet with NBI to gauge programme impact

A. Introduction and Context (1 page)

Quest Link to Business Case:	3972311
Quest Link to Log frame:	4519141

Outline of programme and what it has achieved
This intervention has supported the private sector in South Africa to improve its energy efficiency. The scope for and impact of energy efficiency measures in South Africa was originally assessed to be high. South Africa ranks 4th and 7th as the most carbon and energy intensive countries out of the top 50 economies in the world. DFID analysis showed that industry lacked awareness of energy efficiency and the capability to take action. Whilst in many ways the context is supportive of action on energy efficiency (rising electricity prices, pending carbon tax, available finance) comprehensive support on energy efficiency compared with other countries who have made significant improvements was not present. Lack of adequate progress on energy efficiency coupled with rising electricity prices directly threatens the economic growth rate in South Africa, and has a negative impact on job and income security, therefore also poverty reduction in the country.

The Government of South Africa has a revised energy efficiency strategy. It reaffirms commitment to an ambitious 2015 energy efficiency target, and sets a framework for future targets. The strategy has several initiatives which are aligned to this programme, but lack adequate support measures.

The programme was designed to tackle identified barriers including:
- lack of awareness of energy efficiency;
- lack of a capability within industry to identify opportunities for energy efficiency;
- lack of capacity within companies to access available finance, and develop a business case for energy efficiency projects that would get board level support.

It should be noted that this review is a combined Annual/Project Completion Review and that at the time of writing does not reflect the final results. It will only be possible to guage the final results once the programme comes to an end. However due to the imminent closing of the programme and wind-down of activities, it can be fairly accurately estimated if the programme will exceed or fall short of targets. This has been kept in mind during Output scoring.

Although overall the programme was scored as a B, the results were close to an A grade. The programme did not meet the original logframe objectives, however this was likely to be the case at a very early stage as (i) the programme took longer to start up than planned and more importantly, (ii) the programme was closed early due to the end of bilateral funding to South Africa. Logframe targets were not revised down, but the programme has gone a long way to meeting the original targets in a considerably shorter timeframe, and should be commended for this.

DFID funding to the programme will end in November as the UK wil no longer be funding bilateral aid to South Africa.

Programme achievements
A summary of the output measures, current results and Annual Scoring of the programme are contained in the table below:

Output indicator	Actual results – March 2015[1]	Actual results – August 2015	Target -August 2015	Final target	AR/PCR score
Output 1: Number of companies in direct contact with the programme
Output indicator 1.1: No. of companies that are registered on the PSEE website and number of companies that received awareness raising call or advice over the phone.		2018	1823	2000	A+
Output indicator 1.2: Number of participants at workshops, reported by gender and race.		1535	820	933	A++
Output 2: Number of basic medium company services completed
Output indicator 2.1: No. of on-site surveys implemented at sites of medium sized firms. Surveys are deemed “received” on authorisation of final payment by the relevant account manager to the consultant tasked with implementing the site survey.	312	542	615	1000	B
Output indicator 2.2: Number of sites of medium sized firms that have benefitted from follow-up services	0	62	115	500	C
Output 3: Large companies benefitting from strategic management intervention
Output indicator 3.1: Number of large companies (annual energy spend in excess of R45 million) engaged in strategic energy management interventions (measured as no. companies who have signed strategic energy management contracts)	29	37	35	63	C
Output indicator 3.2: Number of large companies having received new or updated energy management plans	2	12	15	30	B
[1] The most recent milestone, as set out in the logframe

Overall Output Score and Description:
Delays during the set-up phase of the programme have resulted in poorer than expected results at this juncture. Despite these delays once the programme was set up, the scale up in the condensed time period has been significant even though a number of the logframe targets have not been reached.
Direct feedback from beneficiaries
This review has involved interviews with a wide range of stakeholders including recipients or beneficiaries in Cape Town, Port Elizabeth and Johannesburg. Stakeholders interviewed were:
Cape Town
- Woolworths – large nationwide retail corporation (500 employees in the distribution facility under consideration)
- Grey Green - Resource efficiency consultancy
- Cape Olive Farms – medium sized agricultural company. Integrated olive producing and processing concern.
- Sappi Cape Kraft – Paper recycling plant, part of large paper producing corporation.
- Ceres Fruit Processors – medium sized fruit juice processing plant
Johannesburg
- ERM – environmental consultancy (160 employees)
- Omnia Chemicals – large chemical manufacturer
- Transnet – large transport, port, pipeline and property management state owned enterprise
- Department of Energy – government department responsible for energy policy and partner of the PSEE programme
- Vodacom – large mobile phone and telecommunications corporation
East London
- Rhino Plastics – medium sized manufacturing and turnkey project concern
- Airports Company – regional office of large company responsible for airport management
- Marina Salt Works – medium sized salt manufacturing plant
- Sherwood Spar – medium sized retail concern
- Western Gruppe – regional office of the Spar group of franchises representing 88 stores.
All stakeholders are enthusiastic about the programme and expect it to contribute substantially to the creation of an energy efficiency market in South Africa. All beneficiaries interviewed expressed a positive engagement with the National Business Initiative (NBI), the implementing agency, describing their interactions as professional and efficient. Beneficiaries also recognised the currently untapped need that is being addressed by the programme and commented on its good timing in relation to the evolution of the energy efficiency sector. The need is being driven by rapidly increasing electricity prices, regular grid based load shedding, growing environmental awareness, the prospect of a future carbon tax, the increasing number of environmental targets and increasing demand side management.
Consultants were generally happy with the interactions with the PSEE and grateful to be part of an emerging sector. Many commented on how the programme has catalysed the sector and has assisted companies to act on energy issues. Consultants would like to see the programme continue, irrespective of where funding comes from. A number were of the opinion that the programme had not yet gained sufficient momentum in the market for it to be self-sustaining. This point might be reached in two to three years time. All expressed a concern about the possibility of the programme closing down as momentum would be lost and the skills and knowledge acquired would dissipate. Consultants acknowledged that the programme had in many instances opened new business opportunities for them.
While there has been a lack of engagement in the programme by the Department of Energy (DoE), it acknowledges that the PSEE programme has opened up a big opportunity for the country by identifying energy savings of nearly 8GWh. These opportunities are identifiable and are held in a searchable database that can be segmented by sector, suggesting the potential for sector based strategies and incentives, where similar conditions exist and technologies used. The database and the skills and experience that have been gained have great value which should not be lost. If secured, additional funding for the programme will come at a low transactional cost and low risk. Greater communication between the programme and the DoE could have resulted in amendments to regulations which could have supported the programme. Should the programme continue, the DoE will seek to have it mainstreamed, acknowledging that it is a ”perfect fit” with the aims and objectives of the energy efficiency plans the department has developed.
All of the large companies interviewed were complementary of the professional nature of their interactions with the PSEE programme and for the focus on making the business case and prioritising the actions recommended. Across the board, large companies are cognisant of the threat to the businesses that insecure energy provision poses and are single minded about mitigating this risk. Large companies have used the opportunity provided by the programme to drive wider energy and climate related plans within their companies. For example, Vodacom indicated that it has been able to utilise the wide engineering expertise in their companies to conduct R&D and to develop solutions, both specific to their industry and more widely, that they have showcased publicly. Transnet has used the opportunity provided by the programme to embed energy efficiency into their long-term planning and procurement processes and integrated energy management into their systems across divisions. Woolworths, on the other hand, have taken the opportunity provided by the programme to take energy efficiencies into their supply chain by providing PSEE with a list of its key suppliers to work with. Omnia have used the PSEE engagement to develop a comprehensive climate change policy. Actions with short pay back period tended to be implemented immediately and were regarded as “no brainers”. A number were keen to be seen as leaders within their sectors and in the country more broadly. All of the large businesses interviewed were seeking ways of sharing their experiences across their organisations.
Medium sized companies were more constrained in what they were willing to implement, primarily due to cost and the need to raise the capital required for the more costly interventions. They have had to plan the timing of implementations to ensure they are not over exposed. Acting to create energy efficiencies has in some cases been an issue of survival because energy was rapidly becoming their biggest expense. In difficult economic conditions, with static or falling sales, cutting costs ensures profitability.
All recipients were conscious of the behavioural changes required to make the energy efficiency measures more effective. A number have introduced training programmes to educate staff, while others are seeking financial incentives to effect change amongst employees.
A number of stakeholders drew attention to the fact that there were a large number of fly-by-night consultants that had given poor advice to clients in the past and consequently had affected the ability of reputable consultants to access the market.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment
While a clear need was identified justifying a DFID intervention to address the South Africa energy efficiency market failures, a very tight timeframe was set with very ambitious targets. Most of the orginal targets will not have been met by the end of the programme in December. To assess the reasons for the anticipated shortfall requires a consideration of the programme ambition vs the ability of the implementing partner to deliver the envisaged results. Were the target too ambitious or unrealistic? At what point did or will the NBI have the appropriate level of capacity to deliver the programme? Was it realistic to expect the programme to be up and running and delivering ambitious results in the given timeframe? Did the UK’s decision to end bilateral aid to South Africa impact on the timeframe for its delivery?

The initial delays in the programme occurred because the time taken to set up was longer than envisaged. This does raise the question of what set-up time could reasonably be expected. This can best be done by reference to the set up of a similar organisation. For this reason, the reviewer interviewed the CEO of the Carbon Trust in the UK which was also set up from scratch to perform similar work. While the two organisations have been set up in somewhat different circumstances, there is some basis of comparison. The Carbon Trust was established by the UK government with great fanfare and initially was well funded. It immediately inherited energy efficiency programmes that were already up and running. The Carbon Trust inherited a large resource base which was not well managed and not focussed. It required an approach that was flexible and could respond to changing conditions and this was supported by the Board. Even with a running start it took some 2 – 3 years to develop a Carbon Mangement Programme that fitted the needs of British business. Demand was driven by a comprehensive advertising compaign and through working with trade and business associations which helped build the project pipeline. In the UK, awareness raising was done in parallel with pipeline development, while in South Africa these two activities happened consecutively. It is also important to note that the energy efficiency drive in the UK is still not self-sustaining and continues to require a subsidy.

The PSEE programme set-up period was as follows:

Date	Event	Comment
June 2013	Agreement with DFID signed	Decision to end bilateral aid to SA taken before signing. Programme shortened to 2 years from original 3 years as proposed.
June to December 2013	Set-up period	Skeleton staff employed
October 2013	Expressions of interest sent to consultants	Only a few well qualified consultants available.
December 2013	First group of consultants on board	Well qualified consultants were part of the ecosystem that needed to be created to drive the market.
December 2013	Official launch	Not a good time of year to launch such a programme. Jus t prior to the X-mas break.
February 2014	First companies sign-up	Slow response initially
February - June 2014	Full staff compliment recruited	A shortage of suitably qualified staff in South Africa available.
June 2014	Advertsing campaign kicks in	Higher numbers of companies sign up.

It can be seen that in effect it took approximately a year to become fully operational, with appropriately skilled staff, well-qualified consultants and a developing pipeline of projects.

Another energy efficiency related programme in South Africa, the National Cleaner Production Centre (NCPC), which is managed by UNIDO and jointly funded by DFID can also be used for comparison. This programme took a year to set-up.

Throughout the project’s lifetime, the NBI has been advised by the Carbon Trust, which has primarily brought its technical experience in the UK to bear. It needs to be recognised that conditions in the UK are different to those in South Africa. In the UK a pool of highly skilled practitioners exists, while in South Africa, many consultants needed to be trained to meet the needs of the programme.

It is perhaps fair to state that a set-up period of 9 months would probably have been more realistic, given that an energy efficiency ecosystem needed to be built. It is clear that the envisaged 6 month set-up period was over ambitious and also that some key activities could have taken place earlier than they did.

Figure 1 below shows the history of the programme and a projection of when it might be expected to meet its overall targets. It also shows some of the key events in the life of the programme. With the exeption of Indicator 2.2, it indicates that most of the targets could probably have been met had the set-up period been in effect three months shorter.

Figure 1: PSEE programme and results timeline

Programme and results timeline showing projected performance
% of final target reached

SET UP AND RECRUITMENT PERIOD
LAUNCH
No interim results available
Programme end (Dec 15)
Programme life

The programme was originally conceived of as a three year programme, but was condensed into two years after the decision of the Secretary of State to end bilateral aid to South Africa. Clearly a three year timeframe for the programme would have likely enabled all the targets to have been met.

Feedback from recipients interviewed is that the programme came at the right time and met an emerging need in the light of the high increases in electricity tariffs and nationwide load shedding. The programme has developed a significant pipeline of projects (7,790 GWh in electricity savings) that still need to be serviced (340 GWh have been verified as implemented). It is clear that the programme has been instrumental in creating the energy efficiency market in South Africa. It is also clear that the programme has been gathering significant momentum and ought to continue.

As DFID funding comes to an end (November 2015) there is a question mark over whether the programme will be able to raise additional funding to enable it to continue. At this point, no new commitment has been forthcoming and there is a risk that the expertise and knowledge that have been built up during the life of the programme will dissipate and be lost, This would be a waste of DFID’s investment. While DFID is unable to provide any additional funding, as much effort as possible should be made to assist the NBI to raise additional funding.

Output Score and Description
The overall output score for the programme is expected to be a B at the time that DFID’s funding to the programmes comes to an end. Output 1 has exceeded expections, while Outputs 2 and 3 are not expected to meet the final target. For a summary of the scoring see Section A.

Lessons and how these have been shared

Longer set up times for these types of programme are required. Similar programmes in other countries have taken longer to set up[2].
[2] Interview with Tom Delay, CEO of the Carbon Trust, where he mentioned that both in the UK and in Mexico a longer time was taken to set-up than in South Africa.

Experience from the UK is not directly transferable to countries like South Africa where different conditions prevail. Initial asumptions were that the Carbon Trust model could easily be replicated in South Africa. This has proved incorrect, as conditions in South Africa are different. In particular, skills levels are lower and wider knowledge of energy efficiency is not as well developed.

Some key set-up tasks could have happened in parallel with others to shorten the set-up time. The marketing campaign could have started earlier and run in parallel with the recruitment of programme staff.

The market was distrustful of a free service. It took much time and persistence to get the market to accept that the programme wasn’t a scam.

Prior market research would have been helpful. This would have enabled a more targeted marketing campaign.

Closer collaboration between DFID and the Department of Energy would have been beneficial. Despite much effort by DFID, there was little close working collaboration with the Department of Energy, which could have supported the programme through the promulgation of complementary regulations.

There is a clear need in South Africa for an energy efficiency programme of this nature. Comments from recipients, the identified pipeline and the rapidly increasing costs of electricity all indicate that there is a clear need for energy efficiency measures to be taken across the spectrum of users.

The model that has been used has worked to create an energy efficiency market in South Africa. Recipients have been complementary of the quality of the services received from consultants and have mostly acted upon the recommendations.

Energy efficiency measures are needed in South Africa to reduce demand on an overloaded electricity grid. Electricity demand currently exceeds supply in South Africa. Energy efficiency measures are a cost effective way of reducing demand and meeting climate objectives.

These lessons have not yet been shared either within DFID or elsewhere. The lessons need to be disseminated to a targeted group of people both within DFID and elsewhere. Other developmental organisations contemplating energy efficiency programmes could clearly benefit from this experience. Organsitions to disseminate this review to include:

- The World Bank Group including the International Finance Corporation
- The Energy Sector Management Assistance Programme, a World Bank administered multi- donor trust fund.
- The European Union Energy Initiative
- The Asian Development Bank
- The African Development Bank

C: DETAILED OUTPUT SCORING (1 page per output)

Overall Output score: B

Output Title	Number of companies in direct contact with the programme
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (August 2015)	End of programme target	Progress
Output indicator 1.1: No. of companies that are registered on the PSEE website and number of companies that received awareness raising call or advice over the phone	1823	2000	2018
Output indicator 1.2: Number of participants at workshops, reported by gender and race.	820	933	1535

Key Points

Output 1.1

- Performance is about 10% above the August 2015 target and by the end of the programme is likely to significantly exceed the target.
- Meeting this target has been a challenge given the low level of awareness of energy efficiency issues within the business community.
- This indicator was originally anticipated to measure the levels of advice disseminated over the telephone to organisations. Unfortunately the programme has not received the levels of inbound calling that it anticipated. The indicator is rather showing high levels of outbound calls made to organisations to raise awareness of the programme
- This indicator is therefore unlikely to have generated any energy or carbon savings in the way that was anticipated
- The lack of response is largely from medium sized companies.
- With the inclusion of out-bound calls, performance exceeds target levels.
- 1823 contacts with companies are targeted by August 2015. These include in-bound, out-bound and website registrations.
- By the end of May, in-bound and out-bound calls stood at 433 while the number of registered users on the project website stood at 51, making a combined total of 484 companies reached by the programme[3]. See tabs “Registered Users” and “April May Call Logs” in the NBI supplied spreadsheet accompanied.
  [3] See tabs “Registered Users” and “April May Call Logs” in the NBI supplied spreadsheet.

Output 1.2
820 attendees to workshops and conferences has been targeted for the end of August and 933 for the end of the programme.
- Programme reports indicate that 1535 attendees, have come to events arranged by the NBI.
- The programme has run a large number of awareness raising events in an effort to draw participants. This included the launch events in Johannesburg, Durban and Cape Town and included partners.
- The programme has also run a number of small business workshops which provided tailored energy efficiency advice for small businesses
- This has proved particularly successful, and will be continued to the end of the programme.
- Results only include NBI specifically arranged events. If including events at which the NBI has been part of (where they have presented or held a stand, but not themselves organised), the figure is significantly higher.
- While the targets were revised downwards, the result already exceeds the original target.

Summary of responses to issues raised in previous annual reviews (where relevant)
- The marketing effort was scaled up and included a range of media as well as face-to-face meetings.
- Additional NBI events were created to attract potential beneficiaries.

Recommendations for future programmes

- If the PSEE is to continue, this indicator and activity should be revued, with weighting reduced
- For future programmes, there are two proposed considerations:
  - Revue the appropriateness of this kind of activity for the South African market – remote advice in South Africa has proved almost fruitless
  - Create greater targeted market awareness prior to launch of the programme to ‘pre-generate’ demand following focussed market research.
- A key learning is the need to advertise both the programme and these events more aggressively, allowing participants more time to plan to attend, and have more engaging, and reactive routes to market e.g. websites, social media etc.

Output Title	Number of basic medium company services completed
Output number per LF		2	Output Score	C
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (August 2015)	End of programme target	Progress
Output indicator 2.1: No. of on-site surveys implemented at sites of medium sized firms. Surveys are deemed “received”on authorisation of the final payment by the relevant account manager to the consultant tasked with implementing the site survey	615	1000	542
Output indicator 2.2: Number of sites of medium sized firms that have benefitted from follow-up services	115	500	62

Key Points

Output 2.1
- 615 on-site surveys are targeted for August 2015, and 1,000 by the end of the programme.
- To date only 542 site surveys have been delivered. Evidence gained from interviews with recipients who have both completed and are part way through the process suggests that surveys have been of a high quality. It is worth noting that only 3 surveys had been completed this time last year. It is likely that the programme will have conducted circa 850 on-site surveys by the closure date (indicated by number of contracts signed).
- The under performance is attributable to the following:
  - The programme took longer to set up that had been originally anticipated.
  - The programme has underestimated the level of awareness about energy efficiency in the market place and recognises that more time and effort needs to go into developing the engagement pipeline.
  - The programme has insufficient in-house marketing expertise and resources.
  - The programme has prioritised effort on output 2 since large company engagements take longer to complete and the programme was under such tight timelines.
Output 2.2
This facet of the programme has not yet scaled up as energy audits are currently being undertaken, so only a few follow-up services have been implemented.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Experienced marketing staff need to be recruited. A new marketing director was appointed.
- An external marketing agency needs to be contracted to help drive the mass marketing campaign which has just been designed.
- The programme should allow consultants to refer their clients to the programme, on the understanding that the work that flows from such referral will be put to tender.

Recommendations for future programmes
- The considerable progress that was made since last year was possible due to the quality of the staff recruited. It is important that well qualified, capable staff are employed for programmes with tight deadlines.
- The strong uptake of survey recommendations is due to the high quality of the reports, which in turn a reflection of the quality of the consultants that are performing the site surveys. Without a strong business case for the implementation of the recommendations, it is unlikely that action to tackle energy efficiency would have been so forthcoming. Success of such programmes rests with the quality of the people engaged to deliver it. Future programmes need to ensure that high quality experienced consultants are employed to deliver them.

Output Title	Large companies benefitting from strategic management intervention
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	45%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (August 2015)	End of programme target	Progress
Output indicator 3.1: Number of large companies (annual energy spend in excess of R45 million) engaged in strategic energy management interventions (measured as no. companies who have signed strategic energy management contracts).	35	63	37
Output indicator 3.2: Number of large companies having received new or updated energy management plans	15	30	12

Key Points

Output 3.1
Performance is moderately above the milestone (end of August 2015) target level. 37 companies have been engaged in strategic energy management interventions with a target of 35 (63 by end of programme).

- The target is the signature of the large company engagements.
- Some companies have been enthusiastic about the programme, while others have taken longer to convince and decision-making processes are slow.
- The length of the contracting time was also under-estimated, with corporations acknowledging that their legal departments have generally been responsible for delays.
- The programme is currently engaging with 37 large companies; due to the timeframe taken to engage with large companies and the imminent closure of the programme, no new large companies will be added to the pipeline. At the time of the review, the audit process had been completed on 17 of these, with a further 20 due before programme closure.
Output 3.2
- 12 energy management plans have received by large companies against a target for August 2015 of 15.
- This facet of the programme is just taking off as the energy audits are acted upon.

Summary of responses to issues raised in previous annual reviews (where relevant)
- The NBI should look at ways of simplifying the contracting process.
- The programme’s marketing and engagement strategy should make use of good case studies and champions within large corporations to demonstrate how significant savings have been made by embarking on an energy efficiency drive.

Recommendations for future programmes
- The contracting process needs to be simplified to speed up engagement with larger companies.
- Future marketing and engagement strategies should make use of good case studies and champions within large corporations to demonstrate how significant savings have been made by embarking on an energy efficiency drive.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers here have been on NBI staff and professional fees for consultants providing Technical Assistance. Other cost drivers for the programme are on marketing activities, office equipment and essential travel and subsistence costs. All costs have been rigorously scrutinised by DFID to ensure rates are within norms for this type of programme.

VfM performance compared to the original VfM proposition in the business case

The original Value for Money proposition included the following two indicators. The NBI, as the chosen partner, was expected to perform as follows, based on offering the least risk approach, being replicable while offering a clear pathway for transformation, and having most local support:

Value for Money (£/MWh)	VFM (£/tonne CO2)
2.2	2.4

Current Value for Money calculation

It is not possible to make a determination of the current Value for Money using current disbursement figures because there is roughly a 6 month timelag following the presentation of an energy efficiency report and a reasonable set of measures that have been acted upon. It would be reasonable to do these calculations 6 months after the completion of the programme to gauge the overall value for money of the programme. To get an indication of the value for money achieved so far requires using the funds disbursed as at the end of June 2015 and energy saved and CO2 avoided as projected at the end of the programme.

Funds disbursed to PSEE (£) – up to end June 2015	4,032,063[4]
Energy savings achieved (MWh) – projected at programme end	1,798,000
CO2 emissions avoided (Tonnes CO2) - projected at programme end	1,300,000
£/MWh - projected at programme end	2.2
£/tonne CO2 - projected at programme end	3.1
[4] Figure provided by the NBI Finance Director

This shows energy savings appear as expected while CO2 avoided has been somewhat lower than expected.

Assessment of whether the programme represented value for money

The programme appears roughly on track to meet value for money expectations, using at least one of the indicators.

Quality of financial management during programme
Following DFID’s Due Diligence appraisal of the NBI, tighter financial controls were adopted. This ensured that these met with DFID’s requirements.

The NBI has strictly ensured that there have been no expenses that were not originally budgeted and has been at pains to ensure that reporting is accurate.

The financial audit that was conducted in 2014 identified a number of controls that could be improved. These were immediately implemented.

NBI’s Finance Director conducts a monthly analysis to compare actual expenditure with financial forecasts in an attempt to ensure accurate forecasting and also financial statements are reviewed by the CEO every quarter.

One of the key risks identified by DFID at the outset of the PSEE programme as part of its Due Diligence assessment of NBI was the potential fiduciary risk attributed to perceived weaknesses in the NBI procurement processes and policies. As a consequence of this programme risk, DFID supported the appointment of Turner & Townsend to work alongside NBI to implement a new Procurement Framework. Whilst there are longer term benefits to NBI of the implementation of the Framework, DFID specifically needs to verify that the Framework is being adopted in the selection of consultants and partners in the implementation of this programme.
Concurrent with the implementation of the new framework, DFID specifically wished to establish that the selection of consultants for the delivery of the PSEE programme has been undertaken in a transparent way, following an effective procurement process, delivering value for money for the programme. A Procuement Audit was undertaken in June 2015 and the following conclusion was reached:

The primary purposes of the procurement audit were to assess if there is still any fiduciary risk through the NBI and specifically PSEE team’s procurement processes and to assess whether the procurement processes are achieving the required transparency and value for money.

The conclusion is that there is a very limited fiduciary risk with PSEE procurement given that the PSEE programmes has fully adopted and embraced the new Procurement Framework implemented by Turner and Townsend with NBI input and support.

Date of last narrative financial report	June 2015
Date of last audited annual statement	September 2014

E: RISK (½ page)

Quality of risk management over the life of the programme

The business case assessed the output risks as medium to low with no high risks identified.

Due to the high level of DFID involvement over the course of the programme, risks have been managed timeously and have been appraised as they have become evident.

The 2014 Annual Review identified high risks against delivery of expected results outputs 2 and 3, which were to some extent mitigated by the extension of the project completion date. It was also recognised in the 2014 Annual Review that expectations related to the original time-frame were unrealistic.

The risk of insufficient interest in the programme due to an ineffective marketing programme was mitigated by the adoption of a comprehensive marketing plan that was executed by a public relations company and which was closely monitored by the DFID programme team.

The risk of funds not being used as intended was considered to be low and no misappropriation of funds evident. The DFID project team rigorously scrutinised all project progress and financial reports, work-plans and budgets. In addition, DFID-SA engaged a procurement specialist to support NBI to develop a procurement framework to strengthen NBIs’ procurement systems thus mitigating this risk further.

The Climate and Environment Assurance Note assessed this programme as low risk because its purpose is to mitigate the risks of climate change in South Africa. Climate change is unlikely to impact on the success of the programme given its timeframe; rather the programme is designed to tackle longer term climate risk including through reducing South Africa’s energy dependencies.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Programme and results timeline showing projected performance
% of final target reached

SET UP AND RECRUITMENT PERIOD
LAUNCH
No interim results available
Programme end (Dec 15)
Programme life

As the chart above indicates, after a set-up period of about a year, the programme has taken off significantly during the course of the last year.

Performance of partnership (s)

On the whole the partnership with the NBI has worked well, although there were a number of issues related to the working relationship that needed to be ironed out as the implementation of the project progressed. DFID was perhaps more involved in the programme than the NBI had anticipated, requiring a formal agreement be reached which set out which decisions DFID wanted to be consulted about. Once this was agreed, regular consultation around key decisions took place. Consultation with DFID was required when significant expenditure was taken or when a key strategic decision needed to be made. Perhaps DFID modus operandi could have been set out and communicated earlier on.

From the NBI perspective, DFID’s involvement in the management of the programme left it with a conflict of interest as it was involved in management decisions but then took on the role of a donor when performance was not to its liking. The NBI would have preferred to have made the management decisions and been accountable to DFID for them.

The decision to condence a three year programme into two years while still aiming to achieve the same results placed a strain on the NBI. Initially there was no accounting for the very real differences that exist between the UK and South Africa, particularly in terms of being able to find suitably qualified programme staff.

The question of who owned the relationship with government also required discussion and clarification. DFID agreed to consult with the NBI when any significant communication with the Department of Energy took place.

The programme drew heavily on the technical experience of the Carbon Trust and could perhaps have also drawn on it programme management expertise. Competent programme management skills were only brought on board over the last year. Doing so earlier may have resulted in the programme gaining traction earlier.

DFID’s decision to end the funding of bilateral programmes in South Africa also coloured the relationship as far as the NBI was concerned, in that the programme was often affected by the politics of the pull-out rather than the needs of the programme itself.

DFID’s withdrawal of funding from the NCPC also left a legacy in that the NBI was viewed with some suspicion by some of its stakeholders.

While it had originally been intended that there would be a close working relationship with the Department of Energy, in reality this did not substantively materialise beyond the regularly scheduled PSEE Steering Committee meetings. Greater engagement by the DoE could have led to regulation changes that could have complemented the work of the programme.

Asset disposal and value obtained by DFID

An asset disposal plan and motivation has been submitted to DFID, although this is yet to be finalised. Their suggestion included two options. One is to retain the assets pending the outcome of obtaining either bridge funding or future funding for the programme. The other is for NBI to donate the assets to a charity organisation in line with DFID policies and SMART RULES should they not be able to secure funding.
1. The The Smart Rules also state ‘if this is not possible or good value for money (e.g. if the cost of selling the assets or using them elsewhere exceeds their value), then assets can be transferred to the existing delivery partner.’ Due to the age of the assets it is recommended that assets be transferred to NBI, as the cost of selling the assets or using them elsewhere exceeds their value.
2. Electronic assets such as computers and servers will have all the data wiped off by the BSD Regional Manager. After this process IT equipment that has been written off will either be donated to NBI who would sign an agreement taking full responsibility of the assets. Decommissioned electronic equipment will be donated to a WEEE (Waste Electrical and Electronic Equipment) accredited organisation for disposal or recycling.
3. If the recommendations are approved partners will state the following in writing as per the Smart Rules Guidance:
- the asset will be put to a good developmental purpose
- the recipient has adequate resources to maintain and operate the asset, including purchase of any consumables
- the item will not be sold or disposed of, or diverted for another purpose, within a reasonable time period
- the recipient has adequate controls in place to ensure that the assets are used as intended
- any local requirements, regarding duties and taxes, or any other formalities, on transfer will be met.
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The NBI contracted consultants to develop a monitoring framework. Through this process some assumptions and indicators were revised. The main change was the emissions factor in energy savings. As a result the logframe was revised and updated during 2014.
Evidence of energy savings and CO2 avoided, has been gathered from companies involved in the programme and by the consultants assisting with the implementations . But it will also be important to assess levels implementation of specific recommendations of consultants which will have a bearing on the overall results the programme achieves.
No evaluation was planned for this programme because of other evaluations being undertaken by the DFID office in South Africa, its current resource constraints and because the programme is under considerable time pressure. An internal evaluation will, however, form part of the monitoring and evaluation strategy undertaken by the NBI with respect to this programme. DFID will be engaged in this process.

Monitoring progress throughout the programme

DFID’s relatively high level of engagement with the programme ensured that progress was regularly monitored and performance related issues picked up before they escalated. Performance has also been monitored by programme managers as the programme has progressed and have gathered the required indicator data.

Stakeholders interviewed have all been positive about their experience of the programme and are of the opinion that it was a significant catalyst in opening up the energy efficiency market in South Africa.

An Annual Review was conducted in 2014 at a point when the programme was beginning to take off.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process