Annual Review

Title: Better Jobs in Bangladesh (205275)
Programme Value £ (full life): £ 6.6 million		Review Date: 08 August 2019
Programme Code: 205275-101	Start Date: 01 July 2017	End Date: 31 December 2023

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023
Programme Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/9085375.odt
DevTracker Link to Log frame:	(latest one will be published in September 2019)

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)
Better Jobs in Bangladesh is a £6.6 million six-and-a-half-year programme to improve the working conditions and safety standards in the Ready-Made Garments (RMG) sector of Bangladesh. This programme provides technical assistance (TA) to the Government of Bangladesh (GoB) to improve the industry inspection capacity and governance; and to mainstream occupational safety and health (OSH). The UK contribution is part of a wider programme worth $24.5 million implemented by the International Labour Organisation (ILO), also supported by the Netherlands and Canada.

Better Jobs in Bangladesh contributes to achieving Sustainable Development Goal target 8.8 of a safe and secure working environment for all workers by 2030 and target 5.5 of women’s economic empowerment. The programme is supporting GoB to set up systems and processes and develop its capacity to inspect factories; enforce laws in terms of safety and labour standards; and mainstream occupational health and safety. This will provide assurance to brands and buyers sourcing from Bangladesh on workplace safety and will support Bangladesh to improve international competitiveness and secure jobs. Bangladesh exported USD 30.61 billion (approximately £25 billion) of RMG during 2017-18, more than 80% of the country’s total exports[1]. The RMG sector employs 4 million workers, the majority of them women, in 4,000 factories. Following the Rana Plaza factory collapse in 2013[2], two international initiatives called Accord and Alliance were set up, in collaboration with international clothing brands and international labour unions. Their objective was to ensure structurally unfit factories are being remediated meaning they are retrofitted with fire and building safety measures. The factories supplying to international brands fell under either Accord or Alliance but the smaller and often more risky ones were left out. To ensure workplace safety for all factories in the RMG sector, GoB set up the ‘National Initiative (NI)’ and took the responsibility of remediation of the 1,549 smaller factories. Assessing the NI factories and putting Corrective Action Plans (CAPs) in place fell under the remit of this programme.
[1] https://www.bgmea.com.bd/home/pages/tradeinformation
[2] https://en.wikipedia.org/wiki/2013_Savar_building_collapse

The four strategic areas of the programme are:
1. Ensuring factory safety through remediation - focused on remediation follow-up of all NI factories by the Remediation Coordination Cell (RCC)
2. Governance - focused on ensuring GoB has the right capacity to effectively regulate industrial safety
3. OSH - focused on mainstreaming OSH to make it both a government and an industry priority
4. Supporting Better Work Bangladesh (BWB) - focused on improving compliance standards in factories to reduce multiple audit requirements by buyers

The principal achievements of the year were:
- A compliance and escalation protocol was agreed, approved and adopted by GoB which will help expedite decisions to close risky factories.
- 697 active NI factories were visited at least once by labour inspectors during the year.
- 54% of NI factories received information on access to remediation finance.
- First draft of a Gender Roadmap for the inspection authority was developed.
- Monitoring safety committees are in the process of being incorporated into the labour inspection checklist

Other than funding this programme through ILO, the UK is also part of a platform called the 3+5+1 where three GoB Secretaries (Labour, Commerce and Foreign Affairs) and five Ambassadors (UK, USA, Canada, EU, and one on rotating basis) along with ILO, meets at regular intervals to discuss safety standards and labour rights issues within the RMG sector. The UK also plays a strong role in the EU’s Sustainability Compact that works on labour rights, workplace safety, and responsible business conduct.

Summary supporting narrative for the overall score in this review (1/2 page)
This annual review (AR) scores an ‘A’. The programme met many of its expectations in a changing context. The programme logframe uses the January to December calendar year for reporting results. In this review the output indicators are scored based on whether the programme is on track or showing early indication to deliver the targets by December 2019. This is the same approach used previously. We recognise, however, that this is not ideal and therefore propose bringing forward the next annual review to April 2020 and basing it on the actual achievements to December 2019.

A central pillar of the programme is to develop the capacity of the RCC so that it becomes an independent government inspection agency that will be both credible to the brands and buyers and will enforce the remediation of all NI factories. In the last year there were multiple unexpected changes in the remediation and inspection governance space of the RMG sector and a new entity called the RMG Sustainability Council (RSC) emerged. Continuous attention is required to transform the RCC into an Industrial Safety Unit (ISU) and ensuring appropriate governance. During the last year the number and quality of factory inspections have gone up, so the output related to it scores an ‘A’, but progress towards setting up a one-stop-shop (OSS) is still at a very early stage, so the component related to that scores a ‘B’.

OSH is an increasing priority for GoB, and the programme can take some credit for this, so it continues to score an ‘A’ in this AR, but further work is needed to ensure that GoB develops and adopts the National Plan of Action for OSH and mainstreams it.

In the BWB component, challenges remain in making it a stand-alone sustainable component that the industry will continue to pay for and get benefit from. Although the majority of the output indicators are met or are on track to deliver results by December 2019, concern remains as the number of factories registered with BWB is not yet adequate to create the intended end of programme impact. In this annual review it scores an ‘A’, but the next steps will depend on a planned impact assessment of BWB.

Recommendations for the year ahead (1/2 page)
Based on this review the recommendations for each section have been outlined in Section B, but overall the programme needs to prioritise the following:

- Work closely with the Department of Inspection for Factories and Establishments (DIFE) and set up the right governance architecture that recognises the newly set up RSC, especially ensuring that RCC evolves into an ISU with legislative oversight on RSC. (before the next annual review)
- The challenge related to access to finance for NI factories remains. So, the programme will need to find the right incentive model that encourages the financial sector to provide and the RMG sector to take advantage of financing for remediation at low cost. (before the next annual review)
- ILO will need to fast track the process of setting up the OSS for industrial safety and develop partnerships with other relevant GoB departments. Before the next annual review, the relevant ministries will be identified, and the OSS conceptualised based on a common understanding among all relevant regulatory bodies.
- A priority for next year will be to develop the National OSH Profile that will provide the baseline standards for OSH and also to develop a standard monitoring tool for OSH across all industries.
- In the next year BWB will need to prioritise the scale and revenue of BWB for it to continue as a stand-alone service for factories.
- This review encourages BWB to report on any improvement in factory facilities for people with disabilities and the number of factories that have reduced negative (or reported positive) impacts on the environment.
- The logframe of the programme needs to be revised for the BWB component, to track the number of factories active with BWB at the output level.
- DFID will bring forward the next annual review by four months from 8 August to 8 April and review the programme for one full year of achieved results from January to December.

GLOSSARY

BGMEA	Bangladesh Garment Manufacturers and Exporters Association
BLA	Bangladesh Labour Act
BW	Better Work
BWB	Better Work Bangladesh
CAP	Corrective Action Plans
DDA	Due Diligence Assessment
DEA	Detailed Engineering Assessment
DIFE	Department of Inspection of Factories and Establishments
FSCD	Fire Service and Civil Department
GoB	Government of Bangladesh
IFC	International Finance Corporation
ILO	International Labour Organisation
ISU	Industrial Safety Unit
LIMA	Labour Inspection Management System
M&E	Monitoring and Evaluation
MoLE	Ministry of Labour and Employment
MoU	Memorandum of Understanding
NI	National Initiative
OSH	Occupational Safety and Health
OSS	One-Stop-Shop
RAJUK	Rajdhani Unnayan Kartripakkha (Dhaka/Capital Development Authority)
RCC	Remediation Coordination Cell
RMG	Ready-made Garments
RSC	RMG Sustainability Council
TA	Technical Assistance
ToC	Theory of Change
ToR	Terms of Reference

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	A Remediation Coordination Cell (RCC) is established / Employers, workers and buyers are better equipped to support and sustain remediation efforts
Output number per LF		1	Output Score	A
Impact weighting (%):		35%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1.1. A compliance and escalation protocol in place	Baseline (June 2017): Compliance Protocol introduced. / Milestone (Dec 2019): No more target for this indicator.	Met expectation in December 2018. No additional target in 2019. / Compliance protocol is agreed, approved and adopted by GoB. / This now has been converted into an escalation protocol.
1.1.2. Proportion of relevant cases examined by the Review Panel for immediate action	Baseline (June 2017): / 0 (the Review Panel was set up in 2018) / Milestone (Dec 2019): 100% of the relevant cases examined by the Review Panel for immediate action	Met Expectation / Three cases were escalated through the protocol and all three were examined by the Review Panel of DIFE for immediate action.
1.1.3. Frequency of visits to factories by RCC representatives	Baseline (June 2017): 0 (NI factories were not even visited once in a year by DIFE inspectors) / Milestone (Dec 2019): / a) 100% of the NI factories that are under remediation visited at least once by RCC engineers; / (b) 35% of them will be visited ‘at least’ three times.	Met Expectation / a) All 697 active NI factories were visited once by the RCC engineers until June 2019. / b) 81% of NI factories (567) were visited three times by the RCC engineers until June 2019.
1.2.1. Percentage of NI factories who receive information on remediation and access to finance by the RCC (per factory, based on priority)	Baseline (June 2017): 0 / Milestone (Dec 2019): 60% of the active NI factories	On track to deliver 2019 target / 54% (380 factories) of the active NI factories received information on remediation financing from the programme until March 2019.

Provide supporting narrative for the score
This output scores an ‘A’ in this annual review.

The objective of the indicator is to set up a functional Remediation Coordination Cell (RCC) that has the capacity to do inspection and enforce remediation at all NI factories by the end of 2020. GoB is committed to transforming the RCC into an Industrial Safety Unit (ISU) that will be responsible for workplace safety for all types of industries. The ISU will also work as an interlocutor between the brands, buyers, manufacturers, international labour unions, and GoB. The Better Jobs in Bangladesh programme is supporting capacity development of the RCC staff, with matching investments from GoB. During 2018, GoB insisted on wrapping up the initiatives of Accord and Alliance and handing over the factories for which they were responsible to the RCC (although it was premature for the RCC to take on these responsibilities, as it did not yet have the necessary capacity). The Alliance closed its operations in December 2018 and the Accord went into multiple rounds of negotiations with GoB. On May 2019, after 19 months of negotiations, a new private sector entity was set up called the RMG Sustainability Council (RSC) backed by the Bangladesh Garments Manufacturers and Exporters Association (BGMEA), clothing brands, and international labour unions. This will work as a local version of Accord and take over Accord factories and its Dhaka operations by mid-2020.

RCC will continue to be responsible for all active NI factories and this programme will prioritise improving RCC’s capacity so that it can gradually merge into ISU. And with RSC now in place, ILO will also work with GoB to ensure either RCC or ISU has a legislative oversight on RSC. The following activities have been completed since the last annual review:
- RCC governance and the future of ISU were prioritised through a review of business processes, existing partnerships, and knowledge transfer capacity of RCC. Six key performance indicators (KPIs) were identified through this process that will guide the readiness of RCC to take over all remediation work of NI, Accord and Alliance.
- The programme provided skills training to enhance the technical knowledge of the RCC engineers. By March 2019, 109 engineers and inspectors had received training on understanding preliminary assessment reports, Corrective Action Plan (CAP) formulation, and orientation on Detailed Engineering Assessment (DEA) Guidance Manuals of fire, electrical, and structural safety. This contributed to the capacity development of RCC engineers with the right skills to assess factories.
- The Department of Inspection of Factories and Establishments (DIFE), which works with RCC, reported that in 104 factories (out of 697 NI factories) remediation works were completed above 80%. In 99 factories it was between 50% to 80%. In 494 NI factories’ remediation of CAP remains below 50%.
- Labour Inspection Management System (LIMA) was officially launched in March 2018 and until March 2019, 76 RCC engineers (48% of the RCC staff) were trained on Remediation Tracking Module of LIMA and 80 staff (50% of RCC staff) were trained on overall use of LIMA. DIFE has mandated all its inspectors to use LIMA while inspecting factories. This will help DIFE, which is under the Labour Ministry, to provide real time information on labour and working conditions of all NI factories and will hasten the decision-making process of closing risky factories.

The programme worked very closely with Ministry of Labour and Employment (MoLE) in developing the capacity of RCC and is on track to deliver the results for December 2019. The challenge is to ensure RCC gets absorbed into ISU through a gradual process and its legislative oversight on RSC gets established quickly.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lesson learnt:
- This component is working in an environment that is mostly out of the programme’s direct control, so its influence is limited. Stakeholders such as garment manufacturers, international labour unions, and clothing brands play a much stronger role than GoB in shaping the major decisions concerning the sector. GoB also assumes that simply having an adequate number of inspectors will be enough to take forward the inspection of factories and enforce labour law. It is important for both the programme and GoB to understand how the stakeholders are shifting decisions about the sector, at the same time being nimble in accommodating the shifts in decisions that impact the programme targets.
- The government inspectors are guided by Bangladesh Labour Act (BLA) and can only look into issues that are listed under this Act. The BLA was amended in November 2018, after a lot of persuasion by the 3+5+1 platform, Sustainability Compact and international labour unions. Yet, the version remains far from what has been recommended by ILO through its Committee of Experts[3]. The BLA needs to be further improved to ensure the workplace safety and labour rights of workers. However, while the BLA impacts the quality of inspection, the improvement of the BLA is not under the remit of this programme.
  [3] https://www.ilo.org/dyn/normlex/en/f?p=NORMLEXPUB:11110:0::NO::P11110_COUNTRY_ID:103500

Recommendation for the year ahead:
- ILO will need to continue to improve the capacity of RCC and follow the agreed work-plan with DIFE during the rest of 2019. At the same time, ILO needs to be nimble in negotiating with GoB on the organisational structure of RCC and ISU by providing space for RSC and ensuring GoB has oversight of the activities of RSC (before the next annual review).
- Access to finance for remediation is still a challenge for the bottom tier NI factories, primarily due to the weak financial performance of the companies. The programme needs to work on developing an incentive model that attracts both the financial institutions to provide and the factories to take up remediation financing (before the next annual review).
- DFID and ILO will need to continue to pursue GoB to improve BLA through the 3+5+1 platform.

Output Title	Framework for one-stop-shop for industrial safety and compliance conceptualised / Labour inspection capacity of DIFE is developed, which is fair, effective and gender sensitive
Output number per LF		2	Output Score	B
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1.1 One-stop-shop (Single Window Service) proposal and business processes recognised and agreed by all relevant ministries	Baseline (June 2017): Single Window Service concept agreed in principle by stakeholders / Milestone (Dec 2019): Development of the one-stop-shop initiated through advocacy with various regulatory bodies	Did not meet expectation / A window was introduced under LIMA that will allow for factories to get e-licensing for fire[4] (a certificate that confirms that fire safety measures are in place). Discussion needs to start to bring DIFE, RAJUK, FSCD under one common platform.
2.2.1 Proportion of labour inspectors who report increased knowledge and skills acquired through practical training (disaggregated by sex)	Baseline (June 2017): 72% / Milestone (Dec 2019): / No target for 2019	No target for 2019 / Progress will be reported from 2020.
2.2.2 Proportion of trained staff within DIFE who report increased knowledge on gender issues (disaggregated by sex)	Baseline (Jun 2017): / Nil / Milestone (Dec 2019): / 10% percentage point increase from the previous year	Did not meet expectation / The process of training material development has started; and the training will start from Q3 2019. Training in Q3 is less likely to improve knowledge and report it by the end of the year.
2.2.3 DIFE’s information and knowledge management capacity strengthened	Baseline (Jun 2017): DIFE's Information and Knowledge Management System LIMA developed in June 2017. / Milestone (Dec 2019): All 24 Offices use LIMA	Met expectation / As of June 2019, all 24 DIFE offices are using LIMA but not 100% staff of these offices. LIMA is now integrated into the revised standard operating procedure of DIFE.
2.2.4 DIFE gender roadmap developed and implemented	Baseline (Jun 2017): 'No gender roadmap available at the beginning of the project / Milestone (Dec 2019): Final draft of the Gender roadmap discussed	On track to deliver 2019 target / First draft of DIFE gender roadmap developed and a validation workshop with GoB counterparts took place in June 2019. The final draft is expected to be adopted by DIFE by the end of this year.
2.2.5 Labour Inspection Reform Roadmap reviewed and progress reported annually	Baseline (Jun 2017): Nil / Milestone (Dec 2019): Labour Inspection Reform Roadmap reviewed and revised	On track to deliver 2019 target / Inspection reform roadmap was reviewed by DIFE with the programme’s input. Revision has to be endorsed by the MoLE.
2.2.6 DIFE Labour Inspection report published annually	Baseline (Jun 2017): Last report published for 2016-17 / Milestone (Dec 2019): Report published by July 2019	On track to deliver 2019 target / DIFE will publish a report in 2019 on labour inspection for the period of 2014-2018. This target corresponds to ILO Convention 81.
2.2.7 All labour inspectors are trained systematically following the comprehensive training plan of DIFE	Baseline (Jun 2017): Nil / Milestone (Dec 2019): Comprehensive training plan developed for DIFE	On track to deliver 2019 target / A comprehensive training plan for DIFE will be developed in Q3 of 2019
[4] http://efirelicense.gov.bd/

Provide supporting narrative for the score

This indicator scores a ‘B’ in this annual review.

The objective of this indicator is to ensure that GoB has the right capacity and governance structure to effectively regulate industrial safety (not only in the garments sector) with staff that are credible and accountable. To do that the programme is supporting the set-up of a one-stop-shop (OSS) for industrial safety and developing a robust and accountable labour inspection system. Developing a one-stop-shop requires buy-in from other ministries and government wings who are going to be part of the same platform. Industrial safety requires buy in from Bangladesh Fire Service and Civil Defence (FSCD) and RAJUK (the government entity responsible for land and building plan in Dhaka). The programme is initiating discussions to bring these two entities together with DIFE under LIMA, but that will require long-term engagement.

The following was done during the year:

- The programme did a desk review of Bangladesh One-Stop Services Act, 2018 to understand the pre-conditions of operationalising an OSS. This helped DIFE to understand the steps to establish one and the need of long-term engagement. Based on the review, the programme is in the process of developing relationship with Bangladesh Investment and Development Authority (BIDA), Bangladesh Hi-Tech Park Authority (BHTPA) and Bangladesh Economic Zones Authority (BEZA).
- Application for fire licence (both new and renewal) is now online and integrated into LIMA. The other services that need to be integrated are - licensing for opening factories, planning for building, electrical and layout.
- By the end of 2018, all 24 DIFE offices were using LIMA for labour inspection. DIFE issued an office order to use LIMA at all its offices in January 2019, which provides the official mandate to use this platform. The implementation of it is yet to be completed.
- The programme arranged a workshop on Labour Administration and Inspection Strategic Review to identify priorities for the next five years and revise the DIFE Inspection Roadmap. This will help to identify priority areas and deploy resources accordingly. DIFE’s capacity has been doubled over the past three years, so the roadmap will help the department to maximise the use of these resources.
- The first draft of a Gender Roadmap was prepared in March 2019. A validation exercise was done in June 2019. This roadmap, which outlines short, medium and long-term measures, will provide direction to DIFE on how to be more gender inclusive in its own policies (recruitments and deployment of staffs in regional offices) and help the inspectors to assess factories based on gender inclusivity (as per BLA).

Making DIFE an umbrella organisation for industrial safety that monitors all factories across Bangladesh will require a long-term strategy and sustained engagement. The OSS (once operational) and the strategies will help DIFE to achieve that.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons:
- Though setting up an OSS is a priority for GoB, not all departments have the capacity to conceptualise and implement one. On top of that, BIDA is mandated by GoB to lead these processes and has Memoranda of Understanding (MoUs) with multiple ministries. Neither ILO nor DIFE is at the centre of these discussions. So, it is important to build those relationships and set realistic targets for DIFE to set up the OSS for industrial safety. This OSS will help DIFE to track which factories are compliant in terms of all types of licences and which are not.
- Increasing the number of inspectors does not necessarily translate into improvement in the quality of factory inspections. That is why it is important for the programme to concentrate on the quality of training and setting strategies for DIFE, so that the work can be taken forward after the programme ends.

Recommendation for the year ahead:
ILO will need to finalise the process of setting up the industrial safety OSS, identify all other government counterparts, and develop MoUs to bring those services under one umbrella before the next annual review.
Output Title	Framework for national OSH programme initiated in line with national OSH policies of the government / Stakeholders' capacity and awareness on OSH built in a gender inclusive manner
Output number per LF		3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1.1 National OSH profile is ready for adoption by the government	Baseline (Jun 2017): Existing OSH policy and profile / Milestone (Dec 2019): National OSH profile drafted and submitted to the government for adoption	On track to deliver 2019 target / MoLE formed a drafting committee for National OSH Profile with technical support from ILO. Expected to deliver the draft document by end of 2019 and submit to government.
3.2.1 DIFE's capacity to monitor the operations of the Safety Committees is strengthened	Baseline (Jun 2017): Nil / Milestone (Dec 2019): Mechanism to monitor functioning of safety committees by DIFE OSH unit established and office order issued	On track to deliver 2019 target / DIFE agreed to develop a checklist for the inspectors to monitor the functions of safety committees. This will help DIFE inspectors to monitor whether the safety committees are functioning.
3.2.2 Number of Trade Union member and Safety Committee members equipped to support OSH management, Risk Identification and correction (disaggregated by sex)	Baseline (Jun 2017): Nil / Milestone (Dec 2018): 900	Unlikely to meet expectation / The training will start in Q3 2019. A training course starting in Q3 is unlikely to deliver the intended results by the end of 2019.

Provide supporting narrative for the score
This indicator scores an ‘A’ in this annual review.

The objective of this indicator is to improve OSH both in policy and in practice and also to assess whether OSH committees are working in accordance with BLA. The target is to develop and implement National Action Plan on OSH.

The following was achieved during the year:
- The National OSH Council was set up by GoB in October 2018 where MoLE and DIFE are members. The council agreed to review National OSH Profile which will provide guidance on mainstreaming OSH both in policy and practice, identify priorities over time and set up tools to monitor progress.
- DIFE agreed to develop a checklist to monitor the effectiveness of safety committees in factories. BLA mandates DIFE inspectors to check whether a safety committee has been set up in factories but that does not include the effectiveness of these committees. The new checklist will help DIFE inspectors to check whether the committees are well-equipped to serve their mandate and raise concerns to appropriate authorities in case of any imminent hazard.

The programme is on track to deliver the output targets by December 2019 and continues its effort to mainstream OSH in the RMG sector. Bangladesh celebrated National OSH day this year for the third time with the theme of ‘Healthy Workers, Safe Life- Ensure Sustainable Development’.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lessons
Continuous engagement and commitment from senior people such as Ministers and Secretaries are required to mainstream OSH in policy and practice.

Recommendation for the year ahead:
Fast track the process of developing the National OSH Profile before the next annual review that will provide a guideline to MoLE in identifying priorities and help set up monitoring tools.
Output Title	Core service delivery model applied / Engaging stakeholders to contribute to responsible business practices
Output number per LF		4	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1.1 Number of compliance assessment reports completed in the reporting period	Baseline (Jun 2017): Nil / Milestone (Dec 2019): 450	On track to deliver 2019 target / 409 Compliance assessment reports have been completed to end March 2019.
4.1.2 Percentage of PC worker representatives that are women	Baseline (Dec 2018): 35% / Milestone (Dec 2019): 40%	Met expectation / As of March 2019- 42% of the Participatory Committee (PC) members are women.
4.1.3 Percentage of supervisory training participants that are women	Baseline (Dec 2018): 15% / Milestone (Dec 2019): 65%	Did not meet expectation / No progress has been made as of yet.
4.2.1 Number of assessment reports produced that are being accessed via subscription by Brand partners	Baseline (Jun 2017): Nil / Milestone (Dec 2019): 300	Met expectation / 398 assessment reports were used by brand partners.
4.2 .2 Number of buyer partners affiliated with BWB	Baseline (Jun 2017): 17 / Milestone (Dec 2019): 25	Unlikely to meet expectation / 22 buyer partners affiliated with BWB.
4.2.3 Percentage of cost recovery viz. total expenditures	Baseline (Jun 2017): Nil / Milestone (Dec 2019): 37%	Met expectation / 41% of the cost of the programme was recovered.

Provide supporting narrative for the score
This indicator scores an ‘A’ in this annual review.

This indicator focuses on improving compliance standards in factories in line with BLA and contributes by reducing the number of social/compliance audits required by brands and buyers. International brands usually audit factories on the basis of their compensation, contracts, occupational safety and health and working time. This component, Better Work Bangladesh (BWB), works with factories to improve performance in these areas thus will reduce the number of social/compliance audit brands need to undertake. BWB is the Bangladesh chapter of an ILO and International Finance Corporation (IFC) programme called Better Work (BW).

The following was achieved during the year:

- As of March 2019, 210 factories were enrolled with BWB generating revenue of £563,000. The number of factories went down, since the last annual review, but the revenue went up by 37%. Manufacturers increase/decrease factory registration with BWB according to their compliance need. The number of factories is expected to go up again within the end of the year.
- Brand partners went up from 18 to 22 since the last annual review.

BWB seeks to demonstrate the industry that there is a link between improved working conditions and increased competitiveness. It is not aimed at working with the whole industry, but rather to become a model of compliance for the garment sector. As a result, the factories enrolled with BWB are mostly the top tier ones and suppliers of big brands. Most of these factories were part of either Accord or Alliance too. So, it is difficult for these factories to distinguish between the benefits of the various initiatives and identify reduced compliance cost contributed by BWB.

On the other hand, BW operates in eight other countries besides Bangladesh and all of these are largely funded by donors from the UK, USA, Canada, USA, Switzerland, Australia, Denmark, Germany and Netherlands. There are government partners from Jordan and Cambodia and brands like Levi Strauss, Li & Fung, Walt Disney, and Gap. The challenge with BW is that while both the brands and factories are benefitting from the services, the cost recovery has been slow in most of its operations. Three of the nine countries in which BW operates (Bangladesh, Vietnam and Cambodia) are large garment-producing countries, the rest are at the nascent stage of their operations. If the operations in these three countries are not yet sustainable, it does not create a strong business case/demonstration effect for the other countries to continue with this service.

That is why it is important for BWB to increase its effectiveness in Bangladesh and set it up as a standalone service that supports factories to reduce compliance costs and improve competitiveness while also benefitting the lives of workers and improving efficiency.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lessons:
The value addition of BWB remains challenging to demonstrate. While workers benefitted from issues like skills training and maternity benefits, the factories need to benefit from reduced audit duplication by the brands and the brands need to benefit from increased compliance - unless this happens, the business model of BWB is not going be sustainable or replicable.

Recommendations for the year ahead:
- DFID, donor partners and ILO will revise the logframe indicators for this to reflect BWB’s position in the industry as a standalone compliance cost reducing programme. This needs to be done before the next annual review.
- As stated in the last annual review, skills development that contributes towards higher paid jobs, needs to be a market driven approach rather a donor subsidised one. BWB has developed partnership with DFID’s Sudokkho programme and now needs to improve its training modules that can sustain beyond donor intervention.
- The programme will need to continue to prioritise scale, sustainability and revenue of BWB.
- BWB to report on any improvement in factory facilities for people with disabilities and number of factories that have reduced negative impact on environment significantly, where possible.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)
The theory of change (ToC) did not change over the past year and it is based on the fundamental logic that enabling policies and organisational capacity are required to drive reform. When labour inspection reform takes place, when RMG factories are remediated, and when OSH is improved in policy and practice - these will all lead to decent, safer working conditions. This in turn will contribute to safeguarding the competitiveness of the sector and contribute to improving the quality of jobs. Outcomes will translate into impacts if:
- Bangladesh’s garment sector continues to stay competitive and the global trade regime remains favourable.
- The government continues to prioritise reforms related to the garment sector and puts in place the required financial and human resources.
- International stakeholders continue to stay engaged and pursue improvements.

None of the underlying assumptions changed over the last year, so the ToC was not revised.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)
The operating environment of the programme is highly influenced by the political scenario in the country. As more than 80% of Bangladesh’s export earning is dependent on this industry, the RMG sector is prioritised by government. There is no similar platform to the 3+5+1 or Accord/ Alliance or Sustainability Compact in other garment producing countries. However, despite being prioritised by government, the need to engage with multiple stakeholders with different incentives makes it a difficult environment in which to bring about lasting change.

Outcome 1: The target is to remediate factories and address all corrective action plans (CAP) of all NI factories. By end 2018, 60%, and by end 2019, 80% of factories were due to be remediated. Remediation progress until March 2019 was just 38%, which is far off the target. NI works with factories that are from the bottom tier of the industry and often do not have the right incentives and financing to complete the remediation. The programme will need to continue to work on the incentive model and access to appropriate finance so that the pace of CAP remediation can improve quickly.

Outcome 2: The target is to set up an OSS for licensing of factories and bring all industrial safety and compliance licences under one platform. There was no target for 2019. The progress towards achievement is slow, but the programme is on the right track and still has three years to complete this task.

Outcome 3: The target is to increase the number of safety committees that work in accordance with BLA and incentivise GoB to adopt the National Plan of Action for OSH. The target for 2019 was a 10% increase in the number of safety committees that are compliant with the priority indicators set by DIFE. DIFE agreed to set up a monitoring process which is moving in the right direction.

Outcome 4: The target is to develop BW factories as role model of compliance by increasing the number of factories and reducing non-compliance. It is too early to comment on the progress of these indicators.

It is too early to expect to see significant progress against most of the outcome targets, which will take time to show results. However, there are some early signs of impact against some indicators. The business case states that, ‘the benchmark for poor performance/VfM will be if two or more Outcome level indicators fall short of targets by more than 30%. In this case, DFID will reserve the right to drastically modify the programme course, strategies and partnerships or stop funding to the programme’. The next annual review, just after the mid-point of the programme, will assess whether the programme is on track to deliver the outcome targets and based on that will decide on next steps.

Explain major changes to the logframe in the past year (1/2 page)
The logframe indicators were revised as follows during last year:
- Effective labour inspection is an underlying condition for both the first and the second pillar to deliver the expected results, so it has been taken out from the Occupational Safety pillar in this revision. The output indicators related to the effective labour inspection have been brought under the overall Governance pillar.
- OSH pillar now solely concentrates on mainstreaming OSH by embedding it as an important responsibility under factory inspection. This also concentrates on capacity improvement of workers’ participation committees and trade unions in risk identification and OSH management.

In terms of results and deliverables, the timelines or milestones have not changed. These revisions were done to make the indicators more specific and measurable. The timeline of the logframe remains a challenge as the programme measures results using the calendar year January to December and the annual review is done for the period of April-March. That makes the results assessment more complex. As per the last annual review recommendation, the programme team worked on several models of timeline, but it did not make the results measurement easier. So, the next annual review due date will be brought forward by four months to April 2020 so that it can be assessed based on the full year results of January-December 2019.

Describe any planned changes to the logframe as a result of this review (1/2 page)
This annual review recommends fine-tuning the logframe further in the 4th pillar (BWB) as recommended in the output section.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
The ‘Better Jobs in Bangladesh’ Business Case (BC) had targets to assess economy, efficiency and effectiveness of the programme using a set of parameters. DFID introduced Equity as an Indicator in March 2017, so it was introduced into the programme accordingly.

Economy: using best practice in procurement and buying quality input at the right price
In the last year ILO worked with a downstream partner Bureau Veritas (BV) and negotiated down two of its contract values for £25,000 (20% of the contract value) and £220,000 (4% of the contract value). BV is the partner for providing capacity development to RCC and DIFE engineers where the majority of the intervention cost is spent.

Efficiency: inputs generating quality outputs at low cost
The BC states efficiency will come through selecting the most appropriate private technical service providers for RCC, balancing costs and quality, developing capacity of DIFE through private sector engineers and increasing efficiency of BWB.

The review has found that both the quality and number of inspections by DIFE engineers have gone up by three times in 81% of the NI factories during April 2018- March 2019. The inspectors now understand how the information collected through LIMA is being used by MoLE. This suggests that the efficiency of the engineers is improving.

Effectiveness: outputs achieve outcomes
The BC states that the effectiveness of the programme will come through GoB’s improved capacity in ensuring industry safety. The effectiveness will be measured based on DIFE improving its own capacity, increased number of safety committees being set up by trade unions/ workers’ representatives, and improved safety and working conditions in non-RMG industries.

The second year of the programme is too early to comment on the effectiveness. But improving the inspection capacity and labour standards are two GoB priorities which resulted in BLA amendment in late 2018. The transformation of Accord into RSC is also a commitment of the sector to improve safety standards as per the requirement of the brands and international unions. The intervention area of the programme continues to be a priority for GoB and the RMG sector. So, the spending is expected to achieve its output and therefore prove to be an effective investment.

Equity: equal opportunities for all gender, ethnicity, religion
ILO ensures ‘equal opportunity for all’ both in its own recruitments and the procurements it undertakes throughout the year. The programme works for a sector that provides about 70% jobs to women. Improving the skills of the women workers, recruiting female inspectors, and embedding a gender lens in factory inspections have been priorities throughout the year.

Among the 20 master trainers of LIMA, two are women; and the gender inspection roadmap has been disseminated in June 2019 which is expected to improve the quality of inspection that has an improved approach to gender sensitivity. The programme did not have any specific target to improve conditions for people with disabilities, but this review recommended that the BWB component report on the improvement in facilities for people with disabilities.

DFID needs to work with the programme to develop VfM indicators in the four areas set out above which will improve the information collection and assessment; and provide strong evidence of VfM. Overall, the programme is ensuring that factory safety and labour inspection remain as priority agenda items for GoB, and also delivering progress across all output areas. The programme funding is going towards government capacity development which can be assessed to have improved when the government is able to efficiently avert another disaster in the industry. Continuous effort is needed from all stakeholders to achieve that. The emergence of RSC emphasises the need of a credible inspection authority that the brands and unions can rely on. So, the programme and ILO continue to provide VfM by ensuring a strong factory safety regime is created that keeps the biggest job-providing sector safe for workers and also by transmitting UK’s message and values to GoB on labour rights issues.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)
The total programme value is £19.8 million for six and half years. DFID is providing one third of it (£6.6million) with equal contribution from Netherlands and Canada. This funding reinforces UK’s position on the 3+5+1 platform and influences GoB to reform its labour rights standards, directly benefitting UK brands and their supply chain. DFID receives questions from British citizens on why UK or UK brands are not doing enough to improve the wage of the workers and labour rights in Bangladesh. DFID’s intervention through this programme and UK’s influence through these platforms help to respond to these concerns. It is likely that the programme will be able to deliver its business case results if it continues to push the reform agenda. RMG will remain a priority sector for Bangladesh in the medium to long term

Recommendation
A VfM strategy with revised VfM indicators that are targeted in the revised logframe (including equity indicators) to be agreed with ILO and co-donors by September 2019 and used for the next annual review.

E: RISK (½ to 1 page)
Overview of programme risk
The programme risk remains at Moderate level in this review. The programme operates in a politically challenging environment. The risks are monitored throughout the year and mitigating actions have been put in place to reduce their potential impact. For example, delivery, political or safeguarding risks are discussed with ILO at regular monthly donor meetings where actions to mitigate these risks are agreed according to the current economic and political context. Additionally, ILO has good communication channels with the major stakeholders in the RMG industry, including factory owners, associations (BGMEA), labour unions and MoLE. This helps ILO to collect information on any shift in the sector and address that at the right level; either by taking up discussions with the sector or by adjusting the programme expectation. The four pillars of the programme depend on this information to assess the risk of each of the activities and plan their actions accordingly. For example, BWB faced challenges from November 2018 to February 2019, due to pre-election tensions, BLA amendment, and minimum wage revision. All of these affected the factory-facing interventions of BWB and reduced the engagement. As a mitigation strategy, since March 2019, BWB engaged with factories with new interventions that will have higher buy-in from the manufacturers, like supporting mothers at work along union training programmes. This helped BWB to again gain access to factories and continue their work. All of these are reported to the donors through the quarterly meetings and reports. The risk register at the programme level is monitored and updated on a quarterly basis.

A safeguarding due diligence assessment of ILO’s country office’s approach to safeguarding its employees and beneficiaries was conducted as part of this annual review. The assessment was carried out based on the central enhanced safeguarding assessment guidance and no major risks were identified. ILO has an Ethics Officer who is in charge of counselling staff on ethical standards, protecting whistle blowers, and encouraging a safe harassment free work environment and a culture of mutual respect. There are policies and procedures in place within ILO to prevent and address any sexual exploitation, abuse and harassment issues, even before they arise. These policies relate to recruitment, anti-corruption, and the ethical standards of employees. The programme works directly with workers at factory level, and with a strong and dedicated safeguarding policy and monitoring mechanism in place. The standards and policies are refreshed annually and communicated to ILO employees through refresher training. As of now the safeguarding risk is considered as minor. A follow-up on Due Diligence Assessment (DDA) recommendations will be carried out bi-annually throughout the programme life to check that all recommendations are being addressed.

ILO has a strong financial management system in place to monitor financial transactions within the programme. ILO uses its central procurement guidance which provides protection from any bias and fraud in selection of partners. The expenditure is reported from the Bangladesh office to the central system of ILO and a finalised report is sent back to the country offices. The programme has a separate finance team which reports to the country office. The country office of ILO is responsible for the checks and balances and reporting to the central office in Thailand. Robust fraud policies are in place and adequate reporting is provided to DFID. ILO assesses the risks, its likelihood and anticipated impact on the programme and records these in the Quarterly Risk Management Framework.

Update on partnership principles (1/2 page)
Better Jobs in Bangladesh does not provide funding to the government directly and hence the Partnership Principles Assessment (PPA) framework does not apply to this programme. Nonetheless, by improving factory standards and working conditions, the programme should ideally contribute to an improvement in workers’ rights in Bangladesh, and to increased job quality and wages, which may lead to reduced poverty.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)
The total budget of this programme is £19.8 million with UK, Netherland and Canada contributing 33.33% each. As of 31 March 2019:
- Total disbursement from the donors to ILO was £8.6 million from July 2017 to June 2019, the programme has spent £3.5 million and a further £3.2 million has been committed.
- Of the total commitment by all the donors of the programme, 41% has already been disbursed. And of this 75% is committed for spend.
- The expenditure is now at 18% of the total agreed budget of the programme and it is expected to go up as GoB recruits more engineers under RCC and as BWB adds more factories in the programme.
Table 1: Budget Allocation, Utilisation (2018-2019)
Component	Total (As per Agreement with Donor)	Current Allocation /ILO Received from Donor	Encumbers/Commitment up to March 2019	Expenditure up to March 2019	Utilisation and encumbers as of March 2019
					Based on total committed by the donor		Based on received amount
					% of Encumbers	% of Expenditure	% of Encumbers	% of Expenditure
By the end of 2020, all 1,500 National Initiative (NI) factories are remediated	$ 6,171,500	$ 2,220,434	$ 1,624,213	$ 623,669	26%	10%	73%	28%
Government effectively regulates industrial safety	$ 585,000	$ 350,753	$ 89,580	$ 40,861	15%	7%	26%	12%
Effective labour inspection system in place based on robust performance management and accountability	$ 1,074,750	$ 687,743	$ 546,074	$ 220,159	51%	20%	79%	32%
OSH improved in policy and practice	$ 432,000	$ 494,147	$ 227,241	$ 4,647	53%	1%	46%	1%
Better Work factories serve as model for compliance	$ 3,189,501	$ 1,357,518	$ 1,074,506	$ 701,143	34%	22%	79%	52%
Program Management & Co-ordination	$ 9,207,709	$ 3,697,789	$ 3,001,179	$ 2,172,098	33%	24%	81%	59%
Programme & Admin Support, Monitoring & Evaluation	$ 3,877,972	$ 1,273,472	$ 1,021,319	$ 658,753	26%	17%	80%	52%
Total	$ 24,538,432	$10,081,857	$ 7,584,112	$ 4,421,330	31%	18%	75%	44%

The main cost elements of the programme were service contracts/implementation agreements with partners, the purchase of equipment, communications, human resources (15%), operational expenses and programme support costs (13% operational/technical/monitoring and evaluation (M&E)) . As per the contract with the donors, ILO will provide a Technical Progress Report and a Certified Financial Statement by the end of September each year. The first report due in September 2018 was received on time and was of acceptable quality.

Quality of financial management
DFID has disbursed £3.5 million in two annual tranches and the third payment of £1.6 million is scheduled for August 2019. A Due Diligence Assessment (DDA) was done in August 2017 before the funding commitment was signed. ILO sends written requests to DFID to release funds for programme implementation. Flexible payment schedules have been adopted to prevent payments being made in advance of need. At the end of each financial year, ILO also submits audited financial statements that provide the breakdown of the expenditure.

ILO has regular contact with the DFID Bangladesh team, including monthly donor meetings and quarterly progress debriefings. ILO was receptive to information requests on risk and compliance; and responses to requests on transparency issues. The ILO programme team attended the risk workshop conducted by DFID and the safeguarding workshop held in DFID Bangladesh in March 2019. No fraud was reported during the reporting period.

Recommendation
ILO and DFID will work together to assess the finance need of the programme to build accurate forecasts. This will be based on other donors’ disbursements and the needs of the programme.

Date of last narrative financial report(s)	n/a
Date of last audited annual statement (s)	30 June 2019 (expected to receive by September 2019)

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
The programme is primarily monitored through monthly meetings and quarterly reports. Besides these, DFID and the other two donors have issue specific meetings as well. For example, logframe revision and gender roadmap discussions were two issues where DFID and ILO had several meetings over the past year. ILO presents programme progress by pillar as well as by cross-cutting themes and provides written reports for each meeting.

As per the (M&E) strategy of the programme, ILO applies its own procedure for assessing progress and reporting results. Quality is assured at the level of information collection and results produced. The programme then reports to all its donors according to agreed quarterly reports that record progress. The programme meets with the donors on a regular basis to report progress.

As part of the monitoring process, DFID carried out two factory visits inside Dhaka and had meetings with MoLE, DIFE, RCC, labour unions, Accord and RMG Local Consultative Group (LCG) to assess the qualitative impact of the programme interventions. Two factories were visited, and GoB stakeholder meetings were carried out which indicated the programme is on track to reach the logframe targets. The two factories visited were Anika Apparels (partially remediated) and MbM Garments (fully remediated) in Mirpur Dhaka. One was an NI factory and the other an Alliance one. The partially remediated factory is not a supplier of any major brand and slowly progressing in improving safety measures. The labour inspector stated that, though there is no imminent risk in the factory structure, the factory is facing challenges in terms of access to finance to complete the unfinished remediation. In the other factory the labour inspector explained how the pillars of the factory building were strengthened to improve safety and how the effluent treatment plant is working to reduce the environmental impact of dye in water. DFID met the Joint Inspector General of DIFE and the Project Director of RCC to understand the progress and challenges of operations which have been reported under the output sections.

Evaluation (1/2 page)
- The first round of evaluation of the programme is scheduled in 2020.
- In addition, BWB aims to have a midline impact assessment (only for the BWB component) by the end of July 2019 (rescheduled from 2018).

Learning (1/2 page)
The programme works in a strongly politically driven sector. The principal influencers of the sector are the large manufacturers, brands and international labour unions. GoB acts as both a stakeholder and an interlocutor between all parties and this programme supports GoB inthese roles. For example, the emergence of RSC was neither in GoB’s plans nor the programme’s. It emerged from the negotiation between Accord and the manufacturers and now the programme has to redirect its strategies to ensure industry safety and that the governance of the RSC is impartial and effective. The emergence of the RSC, and the programme’s response in starting discussion with RCC and DIFE on the governance architecture, is a good example of where being nimble when working in such a politicised sector is necessary and can reap benefits.

Progress on recommendations from previous reviews (1/2 page)

Remediation:
- The last annual review recommended finding the right incentive for the NI factories to continue their effort in completing the CAPs (progress: underway). The programme continues to work with BGMEA to ensure the factory that remediates is celebrated/incentivised and the ones that do not complete are disincentivised through withdrawal of the Utilisation Declaration, that will prevent the factories from importing fabric for their production. There is not yet a perfect model and with the emergence of RSC, the programme will need to rethink the incentive model and embed it within the GoB industry safety processes.
- The last annual review identified that having three authorities controlling the safety regime in factories makes the situation more complex than it needs to be (progress: underway). The programme had the same view and worked on setting up an OSS that will provide one platform for all industrial safety authorities and their services.
Governance:
The last annual review recommended finalising the business process of RCC and its transformation into an ISU (progress: underway). In 2019 ILO conducted a technical review of RCC operations and based on that a technical note was prepared on an ISU. This might require anywhere between 18-24 months to agree the ISU model with GoB. But this technical review outcome will drive the discussion with GoB to finalise the business process.
Skills Training:
The last annual review recommended to avoid duplication of effort in skills training and take a more coordinated approach (progress: underway). BWB has developed a partnership with Sudokkho and started discussion on coordination process. But ILO, DFID and Sudokkho will need to continue to improve understanding of DFID’s approach in skills training to make it sustainable without donor subsidy.
Gender based violence:
The last annual review recommended to improve workers’ understanding of gender-based violence through the workers’ participatory committees (progress: completed). Based on that, BWB incorporated the High Court verdict on sexual harassment prevention into the training modules to improve the understanding of the workers.
BWB and sustainability:
The last annual review recommended to address the slow progress of factory recruitment under BWB and the sustainability of the programme (progress: underway). The concern remains in this review as well. The programme will conduct an impact assessment of BWB and will provide information to make decision on the future of this component.

This annual review was conducted during July 2019 by the SRO and Programme Officer of Better Jobs in Bangladesh. The review team assessed reports and inputs provided by the programme team and cross checked it with the information provided by MoLE in its presentations. The team also interviewed representatives of RCC and DIFE and visited the office of RCC and two garments factories in Dhaka.