Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Enhancing Resilience in Karamoja Programme
Programme Value: £43m		Review Date: 10 October 2015
Programme Code: 203603	Start Date: 10 October 2013	End Date: 31 March 2017

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A
Risk Rating	L	L

Summary of progress and lessons learnt since last review

This is the second annual review of the Enhancing Resilience in Karamoja (ERKP) programme. The implementation of the programme is led by four agencies: UN Children’s Fund (UNICEF), World Food Programme (WFP), the Food and Agriculture Organisation (FAO) and Deutsche Gesellschaft Für Internationale Zusammenarbeit (GIZ).

Achievements
1. 272,852 people were supported to cope with the effects of climate change and levels of acute malnutrition were stabilised. Over 9,600 children have received treatment for severe acute malnutrition (approx. 60% of the annual caseload) and over 66,876 children and pregnant and lactating women have received treatment for moderate acute malnutrition (approx. 49% of the annual caseload).
2. Over 180,000 people are being supported with seasonal food transfers and to create community assets by the WFP public works programme.
3. The campaign to vaccinate 1,500,000 head of livestock started in September 2015 and was launched by the Hon. Minister of State for Animal Industry, representing the Hon. Minister for Karamoja Affairs (the First Lady Janet Museveni). To date (September 25th) the programme has covered approximately 135,000 cattle and 97,000 sheep and goats.
4. The Agro-pastoral field schools are now established and providing a platform for 11,122 people to learn about improved agriculture technologies and practice.
5. The Karamoja Nutrition Strategy has been released by UNICEF and this is now being used as a platform for discussions with USAID and Government around long term planning for nutrition and food security in Karamoja.
6. DFID is currently working with UN partners to assess and design a response to the pockets of food security crisis that are being experienced in Karamoja.
7. UN Partners work on early warning systems and contingency planning has been contributing to the national level contingency planning for El Nino.
8. In December 2014 following a meeting with the First Lady, DFID presented its portfolio of investments in Karamoja (beyond this programme) to a forum of district government officials and have used this as a basis to start the process of a stronger cross team coordination in DFID Uganda.
9. The DFID SRO and UN programme partners have been requested by the OPM Disaster Risk Reduction group to facilitate the consolidation of early warning systems in Karamoja and to support the design of a new National Early Warning System. This emerging system is currently receiving interest from a range of donors including the World Bank and Africa Risk Capacity initiative.
10. Under the evidence and learning component (output 5) DFID is working with USAID around the development of a common research platform for Karamoja. This will support joint (between Development Partners and Government) learning and monitoring and evaluation. This is an important step towards improving the evidence base and aid effectiveness in Karamoja.
11. Work has begun with FAO and GIZ to implement integrated water resource management in Karamoja.
12. DFID have led the Karamoja Development Partners Group and used this as an opportunity to both influence the design of the Karamoja Integrated Development Plan and build a strong relationship with the Government. As a part of the programme learning agenda, DFID is currently discussing the options for supporting the OPM and Ministry of Karamoja Affairs in the development of the revised Karamoja Food Security Action Plan.

Challenges
1. The evidence base around what works in Karamoja is very weak. Research is difficult and expensive and the current process for generating, sharing and using research are disjointed and poorly coordinated across the development partners.
2. The population, environment and society in Karamoja is undergoing radical change, driven by a range of factors. The aspirations of the people are changing and while some will benefit many will struggle. Conventional perceptions of peoples livelihoods are rapidly becoming redundant and further investments are needed to ensure that development programmes are sensitive and reactive to the opportunities and threats that arise.
3. Many donors are redesigning programmes in Karamoja (including USAID, Irish Aid, BMZ, EU and World Bank). This presents an opportunity for improving aid effectiveness and relationships with Government. The Karamoja Development Partners Group is playing a key role in this process. Beyond this group it will also be important to bring the World Bank into this discussion.
4. While the UN Monitoring and Evaluation systems are well set up for process monitoring, they are less focused on impact monitoring and evaluation of programme success.
5. Karamoja is an operating environment where corruption is endemic. However, building a relationship with UN agencies where corruption management can be openly discussed, reported and properly budgeted for is a challenge. DFID Uganda are currently exploring ways to do this.
6. The incentives for accessing nutrition services are complicated and change as peoples livelihoods strategies change. Understanding these incentives and building the health system to respond will important in the next phase of work.
7. Making services work for mobile people in Karamoja is difficult and requires a fundamental mind shift away from the humanitarian approaches. This will require a much more detailed analysis and discussion with Government about what can be best achieved.
8. Supporting the development of social protection systems which can stimulate and strengthen the development of better markets in Karamoja is a key challenge. This is an area where the evidence is weak and where there are complex and competing political and institutional objectives. Understanding and supporting the transition for some, while continuing to support the livelihoods of others, requires a diverse and nuanced approach.
9. Developing and delivering early warning messages to communities is challenging in the face of highly uncertain weather forecasts and changing livelihood patterns. Where the wrong messages are delivered this will undermine community confidence in these systems.
10. Building coherence across the different early warning systems in a way that will yield clear messages based on risk rather than current state requires strong government leadership and development partner buy-in.

Lessons
1. In providing support to OPM Disaster Risk Reduction around the development of early warning systems it is important to recognise that while Karamoja is a key concern to development partners it cannot be seen to dominate the government focus. Therefore, where development partners push for a Karamoja focus this must be balanced with and presented in the context of national development priorities.
2. Centrally funded programmes can be great opportunity to support locally funded development efforts. However, where funds are channelled through UN agencies from HQ they are not always visible to staff in country offices and can cause confusion in crowded spaces. DFID Uganda is now looking to be more proactive in its identification of and work with centrally funded programmes.
3. Working to build the capacity of district governments will take time as the incentive structures for working in Karamoja are complicated. In addition, the challenge of building capacity across development agencies to work effectively and coherently with district governments in Karamoja and with central government is also significant.
4. Early warning systems, which focus mainly on levels of harvest, risk missing the many people who often depend more on informal wage employment, artisanal mining or petty trading. Studies that improve our understanding of livelihood aspirations and strategies (e.g. the Household Economy Analysis) need to be much better integrated into the planning and design of our contingency plans.
5. Where districts and communities are encouraged to develop and respond to early warning systems links should be clearly made with ongoing development initiatives (such as BRACED, Nutrition programmes, agro-pastoral field schools and public works programmes).

Recommendations: Key recommendations for 2015 are summarised in Annex 1. Follow up on recommendations from 2014 is reported in Annex 2.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	4074955
DevTracker Link to Log frame:	4626559

Outline of the programme
The 1.2 million population of Karamoja is the most food insecure and amongst the most vulnerable in Uganda. The traditional pastoralist livelihood, which has provided a natural adaptive approach to climate change, is becoming marginalised and the natural resources on which the population depends are increasingly degraded. In October 2013 the UK allocated £33,500,000 programme funds for three years (2013/4 – 2015/6), to increase the resilience of the population of Karamoja to climate extremes and weather events. An additional £5,000,000 was made available to the programme as an Internal Risk Facility designed to be accessed in response to crises as they arise in Karamoja. The programme is delivered by three UN agencies (UNICEF, FAO and WFP). In May 2015 a further £4,345,744 of ICF funds was approved to support the implementation of integrated water resource management in Karamoja, delivered by FAO and GIZ. This has extended the deadline of the programme to March 2017 and takes the total value to £42,970,744 - including contingency and £125,000 used in programme design.

The purpose of the programme is “to increase the resilience of targeted communities to climate extremes and weather events”. The programme will support 870,000 people to cope with the effects of climate change, this includes: 200,000 people with improved food security through participation in public works programmes; 6,000 agro-pastoralists and pastoralists with access to improved animal nutrition; and 175,000 children under five and pregnant and lactating women treated for malnutrition.

The entry point for this programme is the challenge of building resilient people, communities and services in the Karamoja. The focus on resilience provides a framework for DFID to work with development partners and the GoU to support a substantive shift away from emergency food relief, towards interventions that improve livelihoods in the medium to long-term while protecting the most vulnerable in the short to medium-term. The programme is doing this through a focus on five components:

1. Access to high impact nutrition services – Scaling-up nutrition programmes targeting malnourished children under five, pregnant and lactating women.
2. Food and livelihoods security – Supporting food security and livelihoods for vulnerable households through: public works, livelihood development programmes, livestock services and water resource planning.
3. Early warning systems – Building and improving early warning and response systems for nutrition, drought and animal disease.
4. Development coordination – Strengthening cross UN planning and delivery, developing contingency plans with local governments and strengthening staff capacity to understand and respond to emergencies.
5. Evidence and learning – Understanding what works best in the challenge of building resilience.

The programme started in October 2013 and by December 2013 all partners had started to implement their work-plans. The programme scored an A in its first annual review (October 2014).

High level results in this year included reaching over 180,000 people through public works schemes and providing over 9,600 children with access to treatment for Severe Acute Malnutrition. Accompanying the beneficiary coverage of the programme has been the progress by the three UN partner agencies to bring coordination to their streams of work, and building a common resilience strategy. This second year of the programme has also seen the early warning systems contributing too much improved response planning to localised food insecurity in Karamoja. Institutional work around these systems is contributing to the Government of Uganda and UN contingency planning in respect to both the current food insecurity in Karamoja and the 2015 El Nino event. The FAO is now well underway in working towards the target of vaccinating 1,500,000 head of livestock and together with this they are achieving strong results in building the systems of disease control and surveillance. The work to implement Integrated Water Resource Management in Karamoja began on September 1st and the GIZ and FAO team are both on track to deliver their inception reports on time.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment: A –There are two indicators at the outcome level. The first indicator on the total number of people supported will be moderately exceeded once we receive final numbers from FAO on their vaccination programme (and is 90% achieved even without these numbers). The second indicator on Global and Severe Malnutrition Levels is very slightly under the target, but within the confidence interval. As such the programme scored an A at the outcome level – indicating that the programme had ‘met expectations’. We anticipate that progress will continue in year 3 and that this will provide a strong base for the programme to exceed expectations by the programme end.

The programme outcome is “increased resilience of targeted communities to climate extreme and weather events”. The indicators for this are:

Number of People supported to cope with the effects of climate change (disaggregated by programme and gender): (March 2015 Milestone - 300,000)
The estimate for this indicator is based on the sum of the key output metrics that measure the levels of participation in the services provided by this programme. This sum includes: household beneficiaries from the public works programme; beneficiaries of livestock vaccinations; participants at the agro-pastoralist field schools; and patients engaged in the supplementary feeding programmes.

In this year of the programme 272,582 people (as reported against the March 2015 target) were supported to cope with the effects of climate change. The target is below the milestone as it does not include the impact of the livestock vaccination programme where the data is yet to be validated.

The livestock vaccination programme got underway in August 2015 and as of September 24th 2015 FAO reported that 232,000 head of livestock[1] have been covered, reaching approximately 50,000 beneficiaries[2]. These results will be included in the log-frame once validated by the FAO in their October 2015 progress report. Following a delayed start this programme is on schedule to meet its target of 1,500,000 head of livestock by the end of the programme.
[1] This is an estimation based on real time updates from the vaccination sites as reported by FAO on 24th September 2015. These figures will be validated in the FAO October 2015 progress report.
[2] This beneficiary estimate is based on the livestock ownership patterns in Karamoja which show approximately 4.6 head of livestock per person.

Stabilisation in prevalence of Global Acute Malnutrition (GAM) and Severe Acute Malnutrition (SAM) in children aged 5-59 months in Karamoja (Milestone for March 2015 GAM <11-12% & SAM <2-2.5%)
The targets for this indicator were derived from the UNICEF project proposal and developed based on the findings of the Project Completion Review (PCR) of the DFID Sustaining Nutritional Assistance in Karamoja programme (November 2011 - November 2013). The outcome for the later programme was not achieved, and was based on a reduction in the levels of severe and moderate malnutrition. The PCR noted that outcome targets were not realistic given that GAM/SAM rates are influenced by several factors and underlying causes outside the scope of the programme. Sustainable improvements to nutrition status will require a much longer-term transformation. More realistic targets were therefore developed for ERKP, which focus on stabilizing rates and preventing the development of a critical situation (defined by the World Health Organisation (WHO) as GAM > 15%).

The WFP & UNICEF Food and Security and Nutrition Assessment (FSNA) conducted in December 2014. Indicated an overall prevalence of GAM among children 6-59 months in Karamoja region of 12.8%, (95% CI (11.7 – 14.0). The same survey reported SAM rates at 3.2% (95% CI(2.7-3.9).

Specific to acute malnutrition (wasting), Figure 1 below indicates an overall improvement in the proportion of children that are acutely malnourished between 2000 and 2014. Global Acute malnutrition (GAM) has ranged from as high as 25% in 2000 to 13.4% in 2014. The chart shows a clear reduction between 2004 and 2011 thereafter, an increment was observed in 2012. Similarly, SAM levels have reduced over this 14 year period.

The overall decline in malnutrition rates highlights significant effort by all stakeholders involved in preventing critical emergency levels in the region and to some extent, these have “stabilised” the situation. However, the median GAM rate remains above 10% (WHO emergency cut off for an emergency) and thus, the situation in Karamoja remains unacceptable.

This emphasises the need to strengthen and scale up a range of strategies targeting the systemic and underlying causes of malnutrition and hence, a strengthening of the current multi-sectoral approach of the UN agencies, and other donor and GoU funded programmes is critical.

Overall output score and description
Outputs	Weight	Score	Progress
Output 1 - Increased access to high impact nutrition interventions	25%	A	Agencies have delivered strong performance and have met or nearly met targets for nutrition interventions. Agencies have also demonstrated improvements in systems, process and in learning. They are developing new strategies which inform the future development of these programmes, and have a greater impact on malnutrition and mortality rates.
Output 2 - Increased food and livelihoods security	25%	A+	WFP are delivering public works programme at scale and reaching the beneficiary targets. FAO are working towards reaching the targets for vaccination of livestock and are building stronger systems around this.
Output 3 - Strengthened early warning and response systems	20%	A	All of the systems are up and running and work is underway to link these into a national early warning system.
Output 4 - Improved development coordination	15%	B	Programme indicators were not achieved though the activities are now all underway to ensure that the end of programme targets are met. / However, beyond the specific indicators, significant advances have been made with coordination both within the programme and across the Karamoja development partners.
Output 5 - Increased evidence and learning	15%	A+	An increasing body of knowledge is being generated by the programme and is informing and influencing efforts to improve ongoing work and future plans.

The overall programme has been scored at A – Outputs are meeting expectations. This overall score is derived from weighted average of the individual output scores which were A+ for 40% of the programme outputs and A for 45% and B for 15%. The programme is in a strong position to reach an A+ by completion given the accelerating delivery of outputs and the momentum that is building behind them. This includes increasing levels of influence across the donor community and a much stronger relationship with the government of Uganda. In addition, the discussions around planning are increasingly focused on quality of delivery and value for money over and above just delivery.

Has the log-frame been updated since the last review?
Yes. In line with recommendations from the 2014 Annual Review, the logframe was reviewed in December 2014 by the programme M&E consultants (DELTA) and again as a result of the FAO change in their delivery plan (qn. 4951583). Following this a new business case addendum on integrated water resource management (see qn. 5092249) was agreed in May 2015 and the log-frame was amended to reflect this in August 2015. The main changes agreed were:
Outcome Level
An increase in 173,807 to be supported to cope with the effects of climate change, in 2016-2017, through the interventions under the integrated water resource management work.
Output level
- 2.3 - Livestock vaccination numbers has moved from an overall target of 1.8 million head of livestock by programme end to 1.5 million head of livestock. However, the reduction in numbers is made up for by the increased investments in livestock disease surveillance systems and that the livestock will be given multiple vaccinations.
- 4.4 - New Indicator added to reflect the work that will be done to develop catchment management plans for the Lokok and Lokere catchments.

A further review of the log-frame milestones is recommended within 3 months to focus on the ongoing discussions around the nutrition targets in the light of the cross UN discussions around improvements to nutrition service delivery.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased access to high impact nutrition
Output number per LF		1	Output Score	A
Risk:		Low/medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s) (lead agency)	Milestones (Mar 2015)	Progress
(UNICEF) Number of VHT members actively engaged in nutrition screening, referral and follow up of children with SAM . Numbers are cumulative	1,000	Over Achieved - 1,908
(UNICEF) Number of severely malnourished (SAM) children enrolled in therapeutic feeding programme (gender disaggregated)	11,635 / >70% (12,530 ; of the total SAM burden)	Achieved / 9692 (Apr 2014 - Mar 2015) / (60% of the estimated SAM caseload))
(WFP) Number of moderately malnourished children (GAM), pregnant & lactating women enrolled in the programme. (women, children, gender & age disaggregated )	100,000	Achieved / 85,216 people enrolled / 66,876: children between 5 - 59 months & pregnant and lactating women
(UNICEF) Dietary diversity: % of children 6-23 months who received foods from 3 or 4 food groups (Cumulative %)	Minimum Meal Frequency (target ranger 30% – 50%) / 42% (June 2014) / (FNSA, May 2012) (baseline) / Dietary Diversity Score / Target 5% increase on 1.4% (June 2014)	Minimum Meal Frequency – 36.5% (Dec 2014) / Minimum Dietary Diversity – 3.1% (Dec 2014)[3]
[3] These figures were not reported in in the June 2015 FSNA and so the figures here show the December 2014 figures. There is an issue with comparing these with the June figures as the population’s food consumption changes through the seasons of the year. DFID are currently working with WFP and UNICEF to address this data issue.

The score for this output is A. For each of the indicators WFP and UNICEF have either achieved, or are within an acceptable level of the target. The milestones are based on the estimated prevalence and incidence of malnutrition in the population as whole, and a number of assumptions related to coverage, and hence inclusion, are beyond the programmes control (see section 1.2). In addition the WFP and UNICEF are on course to achieve the end of programme reach targets for both the SAM and GAM treatment programmes.

Improvement in the quality and the coordination of nutrition services is moving forward, and systems and structures are developing. The development of two reports by UNICEF (Karamoja Nutrition Programme Review Report, March 2015 & Karamoja Multi-Sectoral Nutrition Implementation Strategy (2015-2020)) have assisted in developing a clear vison for the sector around which the Government / Office of the Prime Minister (OPM), implementing agencies and development partners can develop a way forward. The joint WFP/UNICEF Food Security and Nutrition Assessments, and the use of tools to enable effective programme performance monitoring have enabled more effective review of programme performance and more effective programme development and planning.

Key Points
  1. Village Health Team (VHT) Screening and Referrals.
The programme indicator, which focuses on the screening and referral levels of the VHTs, has been designed to demonstrate the effectiveness of both the VHTs and the strength of the system within which they are working. Circa 1,908 or 64% of the total VHTs (3,181) in the region were actively referring and following up children with SAM, the programme is exceeding the milestone figure of 1000.

VHTs have been a feature of health service delivery across Uganda and their efficiency and effectiveness is a source of debate. The Ministry of Health has recently completed a review of the VHT system, and key lessons will be applied to the programme.

Operationalization of VHT activities runs within the framework of Integrated Community Case Management (ICCM), which is supported by CUAMM (Collegio Universitario Aspiranti Medici Missionari / Doctors in Africa) and the IRC (International Rescue Committee). Support to on-job training and mentorship of health workers and VHTs is an on ongoing process. Within the programme, nutrition Technical Assistants from CUAMM provide support to district health offices to monitor and supervise nutrition activities including: Integrated Management of Acute Malnutrition (IMAM); Infant and Young Child Feeding; Family Health Days; and Surveillance. The CUAMM technical assistants also support quarterly referral meetings where the VHTs are brought together with other health workers to review the activities and trends in their areas. All of the VHTs in Karamoja received a fresher training on the VHT/ ICCM module and a total of 326 health workers were trained on IMAM during the reporting period. Work with VHTs and health centre staff to ensure effective referrals to the Therapeutic Feeding Programme and from the Therapeutic Programme to the Community Based Supplementary Feeding Programme (CB-SFP) is ongoing. Indicators are also being developed to track VHT/Community referral functionality by monitoring the number of SAM / GAM cases enrolled into the programmes referred by the VHTs.

Other partners work through the VHT structure such as WFP CB-SFP Implementing Partners, and USAID programme partners (Concern and World Vision). These agencies implement varying models of VHT engagement, which are based on Ministry of Health Guidelines and Village Health Team Strategy. Agencies have reviewed VHT allowances and incentives during the year, and an agreement has been reached between WFP, UNICEF, and the USAID supported NGOs to maintain allowances within the Government recommended rates. Work around harmonisation of incentives in ongoing. Further work is required to increase the effectiveness of VHTs and how best to coordinate their activities given the demands placed on them by the different donor programmes.

  1. Delivery of Therapeutic Feeding
The treatment of severe acute malnutrition (SAM) began with support from UNICEF circa 2004-05 at a time when only one facility, Matany Mission Hospital supported by CUAMM, was providing a locally prepared recipe (skimmed dry milk, sugar and oil) for treating severely malnourished children. UNICEF is currently supporting 116 treatment sites (Outpatient and Inpatient Therapeutic centres (OTC/ITC)) at all hospitals, health centre 4s, Health centre 3s and within a limited number of Health Centre 2s[4].
[4] The Health Centres are classified with numbers based on their size and range of services.

Under the programme the treatment of SAM has developed from an intense International NGO (MSF Spain, ACF and CONCERN) presence in 2007 to the current health systems strengthening model, supported through the UNICEF partnership with CUAMM, who provide technical assistance to the districts and health facilities directly.

In terms of the programme coverage of ITC and OTC services, 9,692 children were enrolled into the therapeutic feeding programmes representing 60% of the anticipated caseload. This is above the 50% Sphere[5] standard for coverage of OTC programmes in rural settings, although slightly short of the recommended 70% for combined ITC-OTC programmes. Key programme performance indicators (cured, death and defaulter rates) were within the minimum acceptable Sphere standards. However, the default rate still continues as a key challenge cutting across all districts.
[5] The Sphere Handbook is a widely recognised set of common principles and universal minimum standards for the delivery of quality humanitarian response.

Simplified Lot Quality Assurance Evaluation of Access and Coverage (SLEAC) and Semi Quantitative Evaluation of Access and Coverage (SQUEAC) assessments were implemented by Action Against Hunger in February/March 2015 with support from UNICEF. These have provided accurate estimates of programme coverage. The Coverage Assessment report highlighted an overall % Point coverage of the OTC programme based on SLEAC of 49% (95% CI: 47% - 52%) indicating moderate coverage. However, the report also highlights important differences on coverage rates between the districts and that overall coverage estimates for the region must be taken with caution due to this variation.

The SLEAC and SQUEAC findings indicate that the most commonly reported barriers to accessing these OTC treatment services include: low awareness of the programme (35%), lack of awareness of malnutrition (27%) and being too busy to attend (33%). For Moroto which has the lowest coverage and formed the basis for the SQUEAC coverage estimation, it was found that opportunity costs such as stone quarrying, mining, burning charcoal or collecting firewood were some of the main barriers to access. Overall, for the region, the findings indicate that more needs to be done to increase coverage of the OTC programme with a focus both on strengthening community mobilisation and making the services more accessible to the population.

As noted, UNICEF are working with CUAMM to provide technical support to the district health teams on a day to day basis, this including: supervision of IMAM activities, support to the District Nutrition Focal Points; support to the improvement of supply chain management, support to improve IMAM reporting, and support in the implementation of Family Health Days (an outreach platform aimed at reaching the un-reached during routine service delivery). Family Health Days were originally scheduled to occur four times per year, and have been associated with improvements in vitamin A supplementation, deworming and immunization with coverage of > 90%. However, during the reporting period, the October 2014 and January 2015 Family Health Days rounds were not conducted following recommendations from MoH to hold the campaigns twice in a year April and October.

The programme marked a key change with regard to the treatment of SAM, moving from a programme supported by international NGOs, to a health systems strengthening model, supported through the partnership with CUAMM. In addition to the planned supply chain review, which will capture the work undertaken by CUAMM and UNICEF in this area, there is a need to also undertake a full review of the effectiveness of this model of support prior to the end of the current programme.

  1. Support for Children and Pregnant and Lactating Women
A total of 85,216 people were admitted onto the feeding programme, compared to a target for this indicator of 100,000. Of these 64,199 were children between 5 - 59 months and 2,677 were pregnant and lactating women.

Screening of children for acute malnutrition is undertaken at village level by village health teams (VHTs) once a month, supervised by WFP’s cooperating partners. Admission criteria are based on the national guidelines. Children with Mid Upper Arm Circumference (MUAC) readings in yellow (between >11, 5 cm and <12, 5 cm) are referred to Community Based Supplementary Feeding Programme (CBSFP) sites. Those with MUAC in red (<11, 5 cm) are referred to outpatients therapeutic centres (OTCs). The supplementary feeding sites also receive referrals from UNICEF supported OTCs.

WFP currently operates 163 sites (May 2015) in all districts providing Corn Soya Blend plus plus (CSB++). The consistently high acute malnutrition rate, above emergency thresholds, continues to justify this support. The services are delivered through either Health Centres or community outposts. Implementation of the programme is currently through Andre Food Consult (AFC) and Community Action for Health (CAFH). All Health Centres in the region now either run the CBSFP or have outposts connected to them.

Percentage coverage data (Moderate Acute Malnutrition (MAM) admissions as a proportion of estimated caseload) has remained consistently above 80% since 2009, and above the 50% Sphere standard for % coverage of MAM programmes in rural areas. MAM programme coverage compares well with the SLEAC findings in that the majority of districts are in the high coverage category (>50%) except Nakapiripirit, Kotido and Moroto (low coverage). However, the weighted regional data was lower than would be expected at 49%, and significantly lower than the estimates based on MAM admissions and case load (>80% since 2010). Regional data masks the reality of programmatic coverage and more needs to be done to address persistent low coverage in Moroto both for MAM and SAM programmes. The main barriers to access identified by the SLEAC study include: lack of awareness of the programme or of malnutrition, being too busy due to opportunistic activities (such as mining etc.) and the child being rejected by the programme.

Programme performance is good and within the Sphere Standards at a mean of 82% cured rate and 8% defaulter rate since 2010. A nutrition programme review meeting report (WFP, 2013) highlighted an average non-response rate of 10% over a 12 month period and a mean length of stay of 73.5 days, which is within the 90 day limit used to calculate non-response. However, this data needs to be interpreted cautiously due to factors associated with data accuracy and quality.

Prior to each distribution of supplementary food WFP deliver nutrition and health education on topics such as infant and young child feeding practices, exclusive breastfeeding, and the timely introduction of complementary foods alongside breastfeeding. Messages have been designed and are played out on local radio stations in the north of Karamoja – giving both nutrition advice and details of local nutrition services. Mothers Groups are also being used to convey nutrition messages and to support VHTs in their follow up work. Andre Food Consult is also training lead mothers in some areas on how to prepare balanced meals using locally available foods. While the results of the nutrition outreach programmes are promising (anecdotally) they are not being rigorously evaluated. This continues to create uncertainty around this component of the programme, and presents a challenge for the continuous development of this work. It is also not clear how these communications fit with broader nutrition messages across Karamoja.

Social and Behaviour Change Communication on improved nutrition of mothers is being supported by USAID, WFP and UNICEF programmes. As noted above, for WFP and UNICEF, this is taking place mainly as nutrition and health education sessions attached to the treatment and food support programmes. However, there is currently limited coordination in regards to formative research, information, education and communication. The various partners and agencies have until recently been conducting studies and developing materials in parallel to one another. For example, WFP is currently supporting Ministry of Health to develop outreach material on infant and young child feeding for Karamoja. There is a clear need for harmonisation between USAID programmes, WFP and UNICEF on the tools being applied for formative research and outreach materials. These should build on existing National Nutrition Advocacy, Social Mobilisation and Communications strategies.

This component of the programme is due to finish in 2015, and WFP is in the process of developing a strategy for a future programme. The UNICEF nutrition review recommended a continuation of a revised form of the CBSFP given the high levels of malnutrition in Karamoja. The new WFP Country Programme (approval November 2015) will have a focus on prevention, health system strengthening and the integration of nutrition activities into the health system. Under this programme, WFP intending to integrate the CBSFP with its Maternal Child Health and Nutrition programme. WFP will undertake an external evaluation of the current CBSFP this year, and DFID will need to work closely with WFP through this process.

  1. Dietary Diversity
The achievement of this indicator is based on a combination of Minimum Meal Frequency (MMF) and Minimum Dietary Diversity (MDD). The target for the programme is to show a 5% improvement in the results. In the case of MDD the results show a 1.5% point increase, while the MMF score shows a fall but the score remains in the 30-50% range.

The December 2014 Food Security and Nutrition Assessment reported that among children 6-23 months who had received complementary food, meals provided to them were inadequate, failing to meet the Minimum Meal Frequency (MMF) requirement in 63.5% of cases. Minimum Dietary Diversity (MDD) was even worse. Only 3.1% of the children 6-23 months received minimum dietary diversity. In summary, only 2.2% of the children in Karamoja did receive the Minimum Acceptable Diet (MAD) the day before the survey.

MAD is a composite indicator combining both MMF and MDD and thus provides a useful way to track progress at simultaneously improving the key quality and quantity dimensions of children’s diets. UNICEF have recommended a review and update of the current dietary diversity milestones and targets based on this indicator.

Karamoja region has quite impressive breastfeeding indicators; exclusive breastfeeding is above 80% (FSNA June 2014), early initiation within the 1st hour is >70% (FSNA June 2014) and continued breastfeeding up to 2 years is also high. The main challenge is ensuring a safe, affordable and diversified diet for complementary feeding due to poor access and availability of foods, hygiene and sanitation practices in addition to caring practices.

The particularly high proportion of mothers not able to meet the MAD in the region makes clear the uphill challenge faced by development partners. The maternal and child dietary supplementation programmes implemented by both WFP and USAID supported programmes are the most direct intervention to address or supplement children’s complementary feeding diets. However, these are supplementary feeding programmes and therefore do not cater for the total individual or household needs of the population. This is an area that needs further review, and points to the need to link mothers with livelihood programmes, perhaps adopting a similar model to that supported by the USAID funded programmes.

Summary of responses to issues raised in previous annual reviews (where relevant)
See annex 2.

Recommendations
1. In addition to the planned supply chain review, which will capture the work undertaken by CUAMM and UNICEF in this area, there is a need to also undertake a full review of the effectiveness of the health systems model of support prior to the end of the current programme.
2. The log-frame should be amended to reflect the growing understanding of the challenges to supporting nutrition outcomes in Karamoja.
3. WFP will undertake an external evaluation of the current CBSFP programme this year, and DFID will need to work closely with WFP, both through the programme evaluation and via additional consultancy support, to review the programme and to consider alternative programme strategies and options.
4. Supplementation programmes need to have much stronger link to those programmes that are targeting the systemic and underlying causes of malnutrition and hence, a strengthening of the current multi-sectoral approach of the UN agencies, and other donor and Government of Uganda funded programmes is critical.
5. Social and Behaviour Change Communication on improved nutrition of mothers is being supported by USAID, WFP and UNICEF supported programmes. UNICEF and WFP need to work with USAID funded programmes to develop evidence based guidance that provides a common framework for action.
Output Title	Increased food and livelihoods security
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones (to March 2015)	Progress
(WFP) Household (HAS) and community asset scores (CAS) - WFP Public Works Programme (PWP)	HAS increased in at least 80% of the targeted households. / (no CAS baseline collected)	Achieved / The overall HAS score moved from 3.1 to 3.7. Improvements in this score were seen in 80% of the communities. / The Community Asset score was 3.6(set against an ideal score of 17),
(WFP) Number of women & men participating in Public Works Programmes (PWPs)	20,000 (representing extra beneficiaries on top of the target for year 1 – 160,000)	Achieved / First phase (reach was 198,642 – based on numbers reached in the December 2014 works) / The second phase of works initiated in June 2015 is designed to reach 198,504 beneficiaries.
(FAO) Number of cattle, sheep and goats vaccinated against epidemic diseases	40,000 (foot and mouth disease vaccines)	Achieved / 40,000 FMD vaccines were delivered in April and May 2015. / As of September 2015 the vaccination campaign has covered 232,300 animals and is on course to reach 1,500,000 by November 2015.
(FAO) Number of agro-pastoralists and pastoralists with improved access to improved animal nutrition (sex disaggregated).	4,000	The platform for both indicators is the agro-pastoral field schools. 11,122 people are engaged. The beneficiaries relating to these two indicators will be verified by the FAO in their October 2015 report.
(FAO) Number of women and men agro-pastoralists trained animal husbandry techniques.	3,500

This output has score an A+ reaching more beneficiaries (with overall reach now at 198,504) than expected in the public works programme and achieving the targets of improving household’s access to assets (with an 80% increase across the communities). Likewise the livestock vaccination programme, following a delay, has got off to a strong start and is on course to reach its target of 1,500,000 head of livestock by December 2015. The Agro pastoral farmer field schools are now established and engage 11,122 participants. The field schools are delivering the training around animal husbandry and have started the work on improved animal nutrition. The numbers for each indicator (2.4 & 2.5) will be verified by the FAO in their October 2015 report.

2.1	Household Community Asset Scores
The Household Asset Scores (HAS) and Community Asset Scores (CAS) gives an indication of the strengthened livelihoods of the beneficiaries of the programme. The progress against these scores is measured on an annual basis in November. This indicator is directly linked to the impacts of the public works programme (described in 2.2).

The November 2014 WFP annual monitoring and evaluation report did show that from those communities supported by public works, 80% had seen a rise in the Household Asset Score.

Overall, community asset scores were very low in all the areas, with the maximum value of the CAS found at 6 (compared to an ideal of 17). The most commonly mentioned assets were the presence of a road (75%), woodlots (46%), water catchment (32%), latrine (31%), Dams (23%) and irrigation ponds (19%). On the other hand, assets such as fishponds, contour terraces, water harvesting and irrigation canals were completely absent in all communities. There were some notable differences in community assets at district level: Kotido had the highest number of irrigation ponds (47%), while Kaabong had none; community latrines mostly mentioned in Napak (58%) but less in Kaabong and Kotido (<15%); and community storage was only mentioned as present in Kotido.

The most popular public works projects are woodlots (n=155 – 32%), followed by water infrastructure (ponds, dams, wells) (n=104– 21%). While further and more extensive research will be undertaken (as part of the programme evaluation) into the quality of the individual projects the observations from the annual review around the two most popular project types include:

Woodlots seen during the annual review were all at an early stage of establishment and required around two hours a day to water. It was positive to see people’s attitudes to tree planting (particularly in a context where charcoal production is leading to deforestation), great to see individuals taking responsibility and showing enthusiasm for learning new skills and encouraging to see communities recognising the role of trees in reducing wind and dust. Concerns remain around the suitability of exotic trees (teak and orange); the location of woodlots in respect to water sources; the organisation of groups; and the rules for benefiting from the trees once they mature.

Water infrastructure. Hand dug ponds are the second most popular asset selected by communities. They can provide a valuable water source in the dry season. However, ongoing maintenance is required and there is a challenge to ensure livestock are watered in a separate trough to avoid contamination of the ponds and damage to the bund (walls of the pond).

Overall, the quality of the public works projects seen during the annual review was acceptable and has shown improvement in planning and construction since the first rounds of public works funded under the ERKP. The public works programme consists of small efforts scattered over a wide area. Soil and water conservation is sorely needed, but is not best approached through a myriad of small projects that cannot achieve landscape or watershed level impact. In addition, fixed assets constructed by communities do require long-term maintenance. While the implementing partners are improving their community engagement strategies around planning for the works it is not yet clear if these approaches will create institutions that are strong enough to organise and lead this maintenance.

The income generating projects tend to focus on production - of vegetables, tree seedlings, honey etc. Vegetables are of course useful for home use, although most participants said they would like to sell their produce. Further work is required to understand the degree to which income generating activities contribute to household income and represent a value for money intervention that accompanies the public works. This type of evidence requires complicated research that can deliver longitudinal information that captures the sustainability of impacts.

2.2	Public Works Programme (PWP)
The first phase of public works covered four activity and distribution periods, which are designed to coincide with the times of year when the population is under most stress.

September 2014	A contingency response to 2014 lean season – covered 31,864 participants
November 2014	32,669 participants
December 2014	33,107 participants (198,642 beneficiaries)
March 2015	31,742 participants

In the second phase of public works (June 2015 to 31 May 2016), programme activities are being implemented in four districts of Karamoja covering 17 sub counties, 81 parishes and 315 clusters. The programme is implementing 488 Public Works Projects. The projects are identified in consultation with communities who choose from an approved list of activities (see above for examples). A food commodity transfer of 150kg maize is provided to a maximum 33,084 participants (or 198,504 beneficiaries in households) for participation in PWP activities distributed through three cycles of 50kg/ per cycle to direct participants in the programme. This ration is intended to support a household with six people. In addition to the food for work activities WFP will support 326 Household Income Support Projects (HISP) projects in targeted locations. These activities are designed to help people to capitalise on the newly created public works assets. Examples include vegetable gardening using water captured in ponds and tree nursery (to supply other works programmes).

Beneficiaries - Most of the people working on the projects are women. It was explained during the annual review that men often had several wives. Often the wives live in different villages or even different sub counties, so given the mobility of the men it follows that it is the wives who most commonly register. A requirement for selection to work is that the person has to be able to work, and be food insecure. The selection of who works is done by the community. This does not always go to plan, as WFP report that their implementing partners sometimes remove people selected to work from the list (if they are not deemed to be food insecure) which can cause village elders to stop all participation in the programme.

As observed during the annual review, the reality of participation in public works is that who actually works on a project is not confined to the named participant. While one person may be registered to receive the payment, in effect various members of the household take turns to work on the project, substituting for the person actually registered. The project currently counts the number of men and women registered for the public works scheme. However, it is unlikely that these numbers bear much relation as to who does the work and how the food is used in the community.

The people involved in the projects consistently said that they were learning from the projects and they appreciated the knowledge gained “we have not until now gone to school – this is our school”. It will be important to follow up the projects once they are completed to see the degree to which the communities will be able to maintain them, and use the knowledge gained.

While beneficiaries tend to prefer food, noting that cash can be frittered away or “just used for drinking” it will be important to discuss with communities as to whether a mix of cash and food might be preferable. It is recognised that this will be a key step in the development of markets and longer term growth in Karamoja.

Appropriateness of the transfer - The people who are chosen to work on the projects are relatively few, circa 3% of the population. According to the FAO produced Household Economy Baselines (2014) about 30% of households are classed as ‘very poor’. Therefore, given the limited coverage of this programme (compared to overall need) this should not be considered, as a standalone programme, to be a strong social protection base. It is therefore important to understand how this programme can fit in the context of other social protection and rural development programmes[6].
[6] DFID along with the Karamoja Development Partner Group is supporting donor mapping exercise in Karamoja, which will provide base for understanding the relative contributions of different programmes to development outcomes in Karamoja.

The amount transferred under the public works programme amounts to about 43 days of food for a family of six (at 2100 kcal/cap/day). The degree to which this is significant is hard to tell, especially as it is likely that the work on projects displaces other activities. It also does not take into account any wider sharing of the food, or its ability to create and repay debts that can be important in lean times. The timing of the transfer one at the beginning of the hungry season (March), one at the beginning of harvest time (August) and one during the time of peak crop sales (November) may not also extract maximum value from the transfer for participants by making sure they get grain at times of peak grain prices.

Project location - In 2014/15 55% of total program beneficiaries were located in the district of Kotido. Planned implementation under the current cycle of works will reduce Kotido beneficiaries by 46% and support more equitable targeting in vulnerable hot spots, consistent with FSNA data. This shows good flexibility in adapting the programme to meet areas where the most pressing needs are. However, a key element of impact from social protection relates to the long-term certainty that people get from knowing the safety net is there should they need it. Moving the programmes and thus changing beneficiaries will undermine this social protection impact.

WFP are currently drawing on their experiences under this programme to work with the World Bank and the Expanding Social Protection Secretariat to develop national guidelines for public works[7]. This initiative is also tied into the new World Bank Plans for NUSAF[8] III. The NUSAF III programme will include a substantial investment in public works in Karamoja. This presents an opportunity for DFID funded public works to link with the NUSAF public works to achieve the scale required for both an effective social protection programme and landscape level improvements in natural resources.
[7] The first version of this guidance was shared for consultation at a workshop in September 2015.
[8] Northern Uganda Social Action Fund (NUSAF)

The annual review team concluded that the project has laid some solid groundwork that can be the basis for an effective scaling up that could have a significant impact on food and livelihood security in Karamoja.

  1. Livestock Vaccination
Following a reallocation of funds in year one (see Annual Review 2014) the main activities for this indicator area were rescheduled to be delivered in 2015/2016. As a result, in year one, the programme did not achieve the performance levels as specified in the log frame and this output scored a B.
Between January 2014 and December 2014 Karamoja experienced multiple outbreaks of foot and mouth disease[9] and quarantine was placed over the movement of animals across Karamoja. Both the disease and this response had significant impacts on Karamoja which were analysed by the FAO[10] in February 2015.
[9] Foot and mouth disease impacts the productivity (growth and milk yield) of cows and affects trade.
[10] FAO 2015 - Socio-economic Impact Study of Foot and Mouth Disease in Karamoja.
FAO used both the pause in funding and the wider discussions and analysis around Foot and Mouth to access technical expertise and work with the Ministry of Agriculture, Animal Industries and Fisheries (MAAIF) to develop a new strategy for livestock disease control and surveillance[11]. This strategy, which focuses firstly on foot and mouth disease, also includes the steps to strengthen the wider livestock disease control and surveillance system.
[11] Submitted with the FAO December 2014 progress report.
There have been no significant incidences of epizootic manifestations in the whole of the region since the beginning of 2015. However, cases of Foot and Mouth Disease outbreak were reported in the neighbouring district of Kween in the Sebei region, which border Nakapiripirit and Amudat Districts. This outbreak posed a considerable risk to the Karamoja herd and the smart foot and mouth disease vaccination, conducted between April and May 2015, was intended to create a buffer to prevent any spillage of the epidemic in the region. This intervention covered 40,000 head of cattle. As of August 2015 this strategy appears to have been effective and no new foot and mouth cases have been detected in Karamoja.
The process of vaccination of 1,500,000[12] livestock (cattle, goats and sheep) against a number of common diseases[13] was started in August 2015. The programme was opened in the first week of September 2015 by the Hon. Minister of State for Animal Industry, representing the Hon. Minister for Karamoja Affairs (the First Lady). To date (September 25th) the programme has covered 135,700 cattle and 96,600 sheep and goats. This vaccination campaign is due to be completed by November 2015. The vaccinations are being delivered by the FAO team with support from the Community Animal Health Workers. The annual review team visited two vaccination sites and observed very well organised teams working through large numbers of cows, goats and sheep. This programme of work is very popular with the District Governments and it was referenced by them in each of the four district government meetings (attended by the annual review teams).
[12] 54% of the total animal population as estimated by FAO April 2015.
[13] Foot and Mouth Disease (FMD); Contagious Bovine Pleuropneumonia (CBPP); Contagious Caprine Pleuropneumonia (CCPP); Peste des Petits Ruminants (PPR)/Sheep/Goat Pox.
A vaccination programme alone will achieve short-term impacts but its’ long term value will be defined by the system that is built around it to monitor and control disease. FAO have undertaken a range of activities to strengthen the livestock disease control and surveillance system. These have included:
1. Karamoja Foot and Mouth Disease Technical Coordination Committee (KFTCC) - The committee has met six times between December 2014 and September 2015 and is providing a key platform for coordination, engagement and leadership for the Government.
2. In September 2015 FAO appeared on a TV talk show depicting the supportive vital role of MAAIF, DFID and FAO in the vaccination programme. FAO are currently exploring the possibility of a radio talk / advice show for Karamoja which will address livestock health issues.
3. FAO are working with Mercy Corps to map and test new approaches to private sector supply of veterinary drugs in Karamoja.
4. Training for disease surveillance and biosecurity – FAO worked with MAAIF on a five day training course in May 2015 that covered: Sample collection, packaging, analysis, post mortem, biosecurity and reporting. The 52 participants included District Veterinary Officers, Community Animal Health Workers, and NGOs. Beyond the training programme, FAO is now working with the Community Animal Health Workers to play a much more proactive role in the disease surveillance system.
5. Equipment for disease surveillance – FAO also procured motorcycles to support the area District Veterinary Officers in undertaking routine livestock disease surveillance and monitoring. Furthermore, the process of procurement of cold chain facilities was completed and this support is expected to increase capacity of the Districts to manage vaccines and ensure effective surveillance and control of animal diseases in the region. This equipment is currently being used to support the ongoing vaccination campaign.

2.4 and 2.5	Agro-pastoral Field Schools – improved animal nutrition and techniques
The agro-pastoralist field schools are a platform for delivering a range of services to support livelihood development. They follow a standard participatory engagement process based on sensitisation, group formation, visioning and planning. Once the groups are formed they will undertake action learning around a wide range of processes that are linked back to the group visions. The scope of core activities includes: forage conservation; soil and water conservation; tree conservation; livestock rearing; small scale production and trading; village saving and loans; and rangeland management.

The initiation of the field schools was delayed (see Annual Review 2014) and they finally started following the signing of Letters of Agreement (December 2014) and training for new field school facilitators in February 2015. The programme is supporting FAO to implement field schools in 380 communities. The field school groups include 11,122 participants (4,431 men and 6,734 women) distributed across the seven districts of Karamoja. These represent the core groups who will be engaged in indicators 2.4 and 2.5.

The Annual Review team visited a range of field schools and spoke with both the participants and the facilitators. The observations around these schools included that the platform of field schools can be a good (but not necessarily cost effective) way to get technology to poor farmers in the absence of functioning markets. The team also noted the role that this type of engagement can play in influencing the aspirations of the people in Karamoja, which are still very closely tied to the ownership of cattle. Some people really benefit from these interventions, but it is important to understand who these people are, why they benefit and by how much. It is also important for the role of field schools to be clearly defined and understood. In discussions with the District Governments, the role of field schools in building rural institutions that can be used as platforms for engagement with government seems confused with their role as a platform for learning and sharing new skills.

The field school participants are those direct beneficiaries who will be assessed under the indicator 2.4 (improved access to animal nutrition) and 2.5 (improved access to pasture). The engagement of the field school participants in these activities will be reported on by FAO in their October 2015 report.

For indicator 2.4, FAO are working primarily with NaLIRRI[14] to work through the agro pastoral field schools with the participants to establish of five learning sites for conservation and utilization of hay and crop residues and mineral blocks with a view to introduce hay production. These learning sites will be open to all people and not just restricted to field school participants. Five hay barns of 1500 bales capacity shall be constructed and will be equipped with necessary equipment and materials including hay balers, motorised sickle bar mower, chaff cutters, molasses and other facilities. There will be training on feed compounding and forage conservations. Hay production also offers a potential alternative source of income for rural communities through commercialization. The programme of works began in August and is scheduled to be finished by December 2015.
[14] National Livestock Research Institute

For indicator 2.5, FAO are also working with NaLIRRI to provide the training through the field school annual learning cycle. The training began in July 2015 and will run up to December 2015.

In addition to the activities being delivered through the field schools FAO are also working with Cooperation and Development[15] (C&D) to construct 43 facilities (21 valley tanks, 15 sub-surface dams and seven solar powered irrigation systems. This work began in August and a formal update will be provided in the FAO October 2015 progress report.
[15] A Karamoja based NGO

Summary of responses to issues raised in previous annual reviews (where relevant)
See annex 2

Recommendations
1. Further research is required to understand the wide spread potential of the public works food transfer in terms of securing food security along the annual cycle. This research is required in terms of targeting, quantity, timing and use of the food ration.
2. Assess the market links and value for money of the community livelihood development programmes (household income support programmes and livelihood impacts of the Agro-pastoral Field Schools).
3. Assess the coverage of the current investment on social protection in conjunction with other social protection programmes (DFID and others) compared to the overall need. To have a significant impact on social protection, the environment and production the DFID programme either needs to be scaled up significantly or planned together with other investments in social protection or public works. Opportunities for more joined up programming should be explored.
4. Develop a plan to strengthen and planning and delivery linkages with the ongoing BRACED programme in Karamoja under any future programme.
5. Undertake research to better understand the nature of the benefits from field schools and the linkages between the field schools and the wider communities.
6. Agriculture extension is shown to be a high cost tool. Further work to understand the value for money based on the overheads per farmer / per result should be incorporated into the programme evaluation.
7. DFID has significant investments into crop science. What opportunities are there for introducing bio-fortified and climate resilient crops into Karamoja? How could this be done in the context of poor private sector and infrastructure? And are there opportunities to apply a results based financing model in a context as complicated as Karamoja.

Output Title	Strengthened early warning and response systems
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones (March 2015)	Progress
(FAO) % of Communities, GoU and development partners reporting use of early warning information in their planning of development and/or emergency response activities.	40% of partners and 70% communities reported having implemented early action according to Drought Early Warning Bulletin recommendations	Achieved at community level / "From Dec 2014 Prog. Rep. / Agronomic responses: 52%; / Food stocking / economy: 39%; / Livelihood diversification: 64%; Livestock husbandry responses: 67%; / Physical measures: 32%; / Public health responses: 59%; / Soil & water cons.: 47%; / Overall average: 49% / Not formally measured at Partner / Government Level (see below)
(FAO) Chronic and acute Integrated Phase Classification (IPC) food security analyses conducted.	3 (2 Acute & 1 Chronic)	Achieved / Chronic - Feb 2015 / Acute - November 2014 & June 2015
(FAO) Community Animal Health Workers trained in participatory surveillance.	220	Not met (but actions underway to get back on track) / 84

The score for this output is A. For the first indicator the team has demonstrated the impacts of their work in the target communities and the data that is collected under this programme is used to inform a wide range of decision making tools and government processes. The FAO have met their targets for the release of IPC reports and are working to improve the communication and impact of this tool. The work to support the community animal health workers (CAHWS) is underway and on track to meet the end of programme targets.

Key Points

Early Warning Systems (indicator 3.1 and 3.2)
Indicator 3.1 is measured by the annual survey conducted in December each year by ACTED and reflects the numbers of people who are reporting a response to early warning information. According to this survey (results shown above) it shows a healthy response at the community level to this information. Although the weakness in this survey is that it captures the response only from those directly exposed to the drought bulletin information. It is not a measure of the overall influence across Karamoja. This will be addressed as part of the programme evaluation.

At the government and development partner level this impact has not been formally measured by ACTED as a result of the ongoing negotiations with the OPM National Emergency Coordination and Operations Centre around the national level release of the bulletin (see response to 2014 recommendations). However, the data that is collected by the DEWS system is used to inform both District Governments and a range of other early warning systems, including (Integrated Phase Classification; Food Security and Nutrition Assessment and Famine Early Warning Systems Network (FEWSNET). It is through these systems that the DEWS data does reach a wide range of government and development partners.

In the past year interest amongst the donors has significantly increased around the need for strong early warning systems, particularly for Karamoja but also for Uganda as a whole. There is not yet a clear system that can bring coherence across the range of efforts to collect, share and use information. DFID is currently engaged with FAO and the OPM to review the current early warning systems and support the development of the structure of a national early warning system that can be a basis for more joined up efforts.

The progress in early warning systems supported under the programme is summarised below:

Drought Early Warning Systems – The system (setup in 2008) has now established itself across Karamoja and is accepted by local government assisted by ACTED. It provides a mix of meteorological forecast and livelihoods data to give status and predictions around food security and agriculture practice. This system has remained active at a community and district level but has not yet been released at a national level (see annual review 2014). In March 2015 FAO designed a new approach to supporting the uptake and use of the DEWS system by the OPM National Emergency Coordination and Operations Centre (NECOC). A technical consultant is now working with NECOC to support the release of the ACTED bulletin. He is currently working with the National Early Warning committee on the August 2015 bulletin to test a process for technical assurance and public release. The experience from this will inform the ongoing plans for a new national early warning system.

Food Security and Nutrition Assessments (FSNAs) - Two FSNAs (December 2014 and June 2015) have been conducted as a joint initiative between WFP and UNICEF. For each cycle of assessment UNICEF and WFP are taking the opportunity to further increase the capacity to collect analyse and use data within the region. DFID are currently working with WFP and UNICEF to review the effectiveness of the FSNA as a tool for nutrition surveillance in Karamoja.

Pictorial Evaluation Tools (PET) – PET is a method for undertaking rapid estimates of future crop yield and current livestock condition. FAO have now developed the PET manuals for Livestock Assessment and Crop Assessment and have also trained government officers to use this tool.

Integrated Phase Classification (IPC) - In this year of the programme (up to March 2015) three bulletins were produced (August, November and February) with a further acute analysis undertaken in June 2015 (indicator 3.2). The IPC does remain the prominent source of reference / influence with respect to the government willingness to respond to food security situations. In meetings with the OPM Commissioner for Disaster Risk Reduction the IPC was recognised as the platform that is currently most likely to influence cabinet decisions around drought emergency response. Following the June 2015 IPC report a response analysis meeting was held in Moroto with the District Governments. This was a positive step to strengthen government focus on the way to respond to early warning, but this was largely unconnected to the wider programme work related to the other early warning systems and contingency planning (see output 4 below).

The investments in early warning systems are all individually working but have a significant scope for improving their overall effectiveness through better coordination. Significant observations from the annual review included:

- Any early warning system needs to provide information in time to assess future needs in time to enable a response to be planned. This year most of the reports were gathered during the hungry season which doesn’t hold validity beyond the next harvest (i.e. if you don’t know what the level of harvest is it is difficult to know if there will be a gap between food supply and demand). In addition, only one of the reports (Household Economy Analysis) indicates the gap in food supply and demand, but this is not well linked into the other systems.
- Each of the systems collected data independently, which is good in terms of cross checking data, but there is little evidence that this is done in any systematic way. In particular the difference in results between the FSNA and the Household Economy Analysis update seems not to have been addressed, and the Household Economy update is mentioned in passing in one place in the IPC synthesis report.
The DEWS activities importantly contain a mechanism for providing feedback to communities. Travelling Drama groups, community meetings and radio programmes are all used. The information provided includes the seasonal weather forecast as well as advice and extension information on what crops to grow. Unfortunately, the seasonal forecast was wrong this year and this will significantly undermine community confidence in this type of messaging. Further work is needed to understand how best to communicate with communities given the increasing uncertainty around weather patterns.

3.3	Community Animal Health Workers Trained
Training for the community animal health workers was scheduled for this year. In the first year of the programme (June 2014) PENU (Participatory Epidemiology Network in Uganda) trained 70 Community Animal Health Workers (CAHWs) on participatory livestock disease surveillance. Participants were selected based on necessary literacy and skills level to use the surveillance gear and note/communicate related information. In addition, 14 CAHWs participated in the five day training course led by MAAIF in May 2015 which covered: sample collection, packaging, analysis, post mortem, biosecurity and reporting.

The main component of this activity, covering 470 CAHWs, was scheduled to be delivered in this reporting period. However, the FAO plan to work with the Karamoja Livestock Development Forum was changed following a due diligence assessment of their technical and operational capacity. Subsequently, PENU was selected for this intervention and will begin by October 2015.

Summary of responses to issues raised in previous annual reviews (where relevant)
See Annex 2.

Recommendations

1. The UN delivery partners will need to work with OPM NECOC to inform, influence and then respond to the national early warning system.
2. Investments in early warning should be made in recognition of the structure that is established. Careful VFM analysis should be applied to the introduction / continuation of any primary information generation systems.
3. Further investments in understanding the impacts of early warning messaging on communities is required.

Output Title	Improved development co-ordination
Output number per LF		4	Output Score	B
Risk:		Low	Impact weighting (%):	15
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
(FAO) - Number of local government district development team members trained in DRR & climate awareness (ICF Indicator 13)	Capacity Needs Assessment Conducted and 140 people trained	Not achieved – work is ongoing / Training is scheduled to start in October 2015.
(UNICEF) Number of district teams trained on contingency planning, preparedness and response for nutrition. Numbers are cumulative.	4	Not Achieved – work ongoing / Training is scheduled to begin in October 2015
(FAO) Number of updated district level contingency plans with response options (ICF Indicator 13)	Updates of District Plans in Progress	Not Achieved – work ongoing / Revised District Plans are currently with the OPM awaiting clearance. On release this indicator will be verified.
(GIZ) Two catchment management plans developed and being implemented.	-	On target (work started in September 2015)

The work linked to the first three indicators was delayed and the immediate advancements reported in the 2014 review did not happen in the time frames that were predicted. For example, UNICEF reported that their contract with the International Institute of Rural Reconstruction (IIRR) would be signed in October 2014 and this actually started in June 2015. While FAO reported contract negotiations with the International Union for Conservation of Nature (IUCN) and IIRR being in an advanced state in September 2014 the contracts were not signed until December 2014. As a result this Output will score a B.

Despite these delays the agencies are reporting that all the activities are up and running and the delay in the start has given UNICEF and FAO an opportunity to discuss how they can interact to ensure best value for money.

Key Points

4.1 and 4.3	District Capacity Assessments and Contingency Planning
IUCN and IIRR have now completed (as of September 2015) their capacity needs assessments and reviews of the district level capacity and contingency plans. These are currently being reviewed by the FAO. The content of the support training will be based on the gaps identified through this capacity need assessment. This training and the subsequent updating of the District contingency plans is scheduled to begin in October 2015.

There is a very complicated mix of initiatives that currently are or will be purporting to support contingency planning in Karamoja and across Uganda. This level of attention presents a great opportunity for the promotion and true integration of contingency planning into District Development Plans. However, without coordination and coherence between efforts, there is a risk that the impacts will be confused and diluted.

One such initiative is the £38,000,000 DFID global programme for “Strengthening Humanitarian Preparedness in High Risk Countries”. This programme supports WFP and UNICEF in Uganda to work on a range of early warning and preparedness activities. These activities could complement the DFID Uganda investments in these areas but have only recently (August 2015) been followed up by the programme team. Further work will be required to ensure that future activities under this programme contribute to DFID Uganda programme priorities.

4.2	Nutrition Contingency Planning
UNICEF is in the process of finalising a contract with IIRR to support the review of district emergency, preparedness and response plans with a view to integrate nutrition. This activity will be undertaken jointly with FAO whose focus will be on food security. The main output from this assignment will be a comprehensive nutrition contingency and response plan for Karamoja.

In July 2015 UNICEF signed a contract with IIRR to support the review of district emergency, preparedness and response plans with a view to integrate nutrition. This activity will be undertaken in collaboration with FAO whose key focus will be food security while UNICEF will be nutrition. The same partner (IIRR) has been engaged to ensure harmonization of the approaches used and also to ensure that both reviews complement each other. The key output from this assignment will be a comprehensive nutrition contingency and response plan for Karamoja. There is an opportunity for this work to directly feed into the Karamoja Food Security Action Plan – which is a component of the Karamoja Integrated Development Plan. OPM have requested DFID to support them in the revision of this plan between October and December 2015.

4.4	Integrated Water Resource Management
The FAO and GIZ began their work on these activities in September 2015 (see programme management note (qn. 5162086). Both agencies are on track to meet their scheduled inception targets and will be presenting their programme plans at an inception workshop, held jointly with the Ministry for Water and Environment, on October 2nd 2015.

Other Significant Improvements in Coordination

Karamoja Development Partners Group (KDPG)
DFID held the chair of the Karamoja Development Partners Group for 2015. Key successes over the year have included: strengthened relationship with OPM around the redesign for the Karamoja Integrated Development Plan; discussions with USAID, EU, Irish Aid and BMZ around cooperation in new programmes for Karamoja; representation at the Karamoja Policy Forum; and negotiations with USAID over a new research platform that will support the KDPG and the OPM.

Strengthened Relationships with Government
DFID met with the First Lady to discuss our plans in Karamoja in November 2014 (see qn. 4783701). Following this meeting, the DFID Head of Office and representatives from across DFID Uganda teams visited Karamoja, where the DFID portfolio of investments was discussed with officials from the seven districts (see qn. 4782691 for the trip report). In January 2015, Joy Hutcheon visited Karamoja and reviewed the resilience programme work, the SAGE work and efforts to combat violence against women and girls. Joy also met with the First Lady.

Cross Agency Collaboration
The three UN agencies have made progress in the way they plan, work and report together under the resilience programme. Strong examples of this include:

- UN Joint Resilience Framework – The final version of this framework has not been signed off by the agencies, however the process has involved a significant amount of negotiations between the agencies.
- FAO and WFP - Assessment of light livestock restraint facilities was conducted in all the districts across the region. The suitable locations for construction of cattle crushes in different districts were identified based on a combination of technical criteria and local consultations. FAO produced a map of sites that has been used as a base for discussions around direction the WFP public works programme. FAO are also working with WFP around the provision of WFP public works labour to construct FAO water for production assets.
- WFP and UNICEF – Worked closely together on the SQUEAC survey and the nutrition review. Both of these exercises are being used to direct discussions around how to improve the strength and connectedness of the programmes operating under the ERKP and with nutrition interventions that are funded by USAID.
- Geographical Information System data sharing – All three agencies are currently collaborating to produce maps of the DFID funded resilience activities in Karamoja. These can firstly serve as a platform for discussions around strengthened coordination, but will also open up opportunities for more rigorous impact assessments.

Summary of responses to issues raised in previous annual reviews (where relevant)
See Annex 2

Recommendations
1. When district contingency plans are cleared, FAO and UNICEF should assess their connections and coherence with the many different early warning, contingency support and DRR plans currently being promoted in Karamoja.
2. UNICEF and FAO should report on the process undertaken to provide coherent support to the district governments following their joint activities around contingency planning.
3. DFID Uganda will work with DFID CHASE to identify the scope of current investments of DRR and agree reporting lines that ensure coordination and coherence between initiatives.
Output Title	Increased evidence and learning
Output number per LF		5	Output Score	A+
Risk		Low	Impact weighting (%)	15
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
(DFID) Number of evidence / knowledge (ICF Indicator 14) areas identified, defined, researched and analysed. Numbers are cumulative.	4	Achieved and moderately exceeded / Three evidence / knowledge products have been led by DFID while a further four have been developed by the UN partners. / Score: A+
(FAO) Watershed Management feasibility study developed	Initial feasibility study conducted & results disseminated	A feasibility study on water for production was completed in April 2015. The results informed FAO plans around the construction of water for production assets and will feed into the wider work on integrated water resource management. / In addition, a business case addendum for integrated water resource management was cleared in April 2015. / Further work has now been commissioned to support integrated watershed management (see output 4) / Score: A

Key Points
The body of research that is being generated by the programme is supporting discussions about improving the programme and starting to inform future thinking. The programme has exceeded targets on evidence products but improvements are needed in terms of research rigour and the UN agency focus on communication and research update.

  1. Evidence / Knowledge Products
The following products have been identified and researched under this year of the programme:

Climate Development and Knowledge Network (CDKN) 2015: Economic Assessment of the Impacts of Climate Change in Uganda; Case-study on agricultural production in the Karamoja region; produced together with the Ministry of Water and Environment.

World Agro Forestry Centre 2014: Trees and Livelihoods - A rapid review of evidence relating to the role of trees and livelihoods in Karamoja (November 2014).

World Agro Forestry Centre 2014: Trees and Water Resource Management - A rapid review of the evidence relating to the role of trees in water resource management in Karamoja (November 2014).

Three further streams of research are in the process of being commissioned by DFID to inform both the ERKP and the other DFID interventions in Karamoja. These are:

Gender Assessment – describing the current context for promoting development and resilience in Karamoja with respect to the empowerment of women and girls; and men and boys. The research will feed into a new Theory of Change around gender based empowerment in Karamoja and a strategy for DFID.

Political Economy - providing an understanding of the political economy factors and conflict risks that may impact on the viability and success of programme interventions, and to ensure that our programming “does no harm”.

Note: Both pieces of research were scheduled to start in July 2015. However, in both cases a tendering process run by DFID Uganda did not lead to proposals of an acceptable standard. As a result DFID is working with PEAKS to procure a team to undertake the Gender Assessment. For the political economy assessment DFID are negotiating with a team of suitable experts around their availability to do this work. In both cases the final products are expected by February 2015.

Nutrition Interventions in Karamoja – Research and analysis around the political context, delivery, role and impact of the ERKP nutrition and food security programmes. This will inform the discussions around DFIDs focus on nutrition in the future.

The significant research conducted by the UN partners has included:

FAO 2014: Milk and Vegetables Market Assessment, October – November 2014

FAO 2015: Socio-economic Impact Study of FMD in Karamoja, Dec 2014 – Feb 2015.

UNICEF & Action Against Hunger 2015: Semi Simplified Lot Quality Assurance Evaluation of Access and Coverage (SLEAC) and Semi Quantitative Evaluation of Access and Coverage (SQUEAC)
Note: These assessments give rigorous estimates of the size of the malnutrition caseload in Karamoja and the extent of coverage of the services in each of the districts.

UNICEF & Team Initiatives Limited 2015: Barriers to appropriate infant and young child feeding.
Note: This study was useful for barrier identification, however UNICEF reported that the work did not adequately outline or consider key areas such as people’s perceptions and acceptance of recommendations. The work is undergoing further revision by UNICEF.

Two further streams of research are in advance stages of design. These are:

Review of the Nutrition Surveillance Systems – research to analyse the information systems that are required to further develop our understanding of how to support nutrition security of households, improve the quality and impact of existing interventions, and increase their understanding of seasonal and shock-related changes in individual and household food and nutrition insecurity.

Nutrition Supply Chain Review – research to understand the systems that support the demand for and management of TOR has been developed and is pending final review and clearance.

In addition to the research studies UNICEF worked with WFP on two significant analysis and strategy pieces:

UNICEF & Centre for Humanitarian Change 2015: Karamoja Nutrition Programme Review
Note: this report provided the analysis of evidence and trends to inform the new Karamoja Nutrition strategy.

UNICEF & Centre 2015: Karamoja Multi-sectoral Nutrition Strategy
Note: This strategy outlines a range of nutrition specific and nutrition sensitive actions that are needed in Karamoja.

Other Progress - DFID is currently working with USAID to develop the scope of a new research platform for Karamoja. The inception work for this platform (initially funded by USAID) will begin in October 2015. Beyond providing a mechanism for commissioning new research this platform will provide a clearing house mechanism for existing research. Using tools such as DFID’s guide for assessing the strength of research evidence, the platform will provide evidence appraisal and synthesis. It is hoped that this will help to drive up the quality and breadth of evidence in Karamoja.

  1. Water Management Feasibility Study
A feasibility study on water for production was led by FAO and completed in April 2015. The feasibility study on Water for Production was commissioned to support the identification of appropriate technology and placement of water resource harvesting structures. This study has now informed the types of production interventions and

This study has informed the FAO work to strengthen water for production assets which includes water harvesting tanks (valley tanks) for surface runoff catchment, sub-surface dam for riverine catchment system, and solar powered micro irrigation system using boreholes.

In May 2015 a business case addendum was cleared. The addendum, based on the FAO assessment of need for improved water management, will set the base for integrated water resource management in Karamoja. As this work progresses, it will be reported on against output 4.

Summary of responses to issues raised in previous annual reviews (where relevant)
See annex 2.

Recommendations
1. DFID to maintain a focus on research quality and research uptake and use across the programme delivery partners.
2. DFID to work with DELTA partnerships around two learning events that will focus around the role of the programme in supporting transformational changes in Karamoja.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

A number of key costs have been selected based either on size or that they are indicative of the types of activities that are undertaken. These are set out in the table below:
Key costs	Cost drivers	Measures to control cost drivers	Outcome
UNICEF - Procurement of Ready to Use Therapeutic Food (RUTF) / (27% of original budget)	Global price changes	External factors at play / UNICEF procures RUTFs and trains VHTs.	There has been a reduction in therapeutic commodity prices on the global market due to new suppliers coming up hence the reduction in the unit cost of RUTF from $60 per carton to $47 per carton resulting in a 22% reduction in estimated cost of RUTF.
Delivery of Ready to Use Therapeutic food (RUTF) / (8% of original budget)	Cost of RUTF supplies and management and delivery of the programme		Business case prop.	Comparator		Actual 2015
		Cost of food and delivery of the services (Per child treated for SAM)	US$56	$88		$53
		Management of SAM in OTP, excluding supplies (Per child treated for SAM)	$115	$142		$77
UNICEF- research and survey costs (Food Security and Nutrition Assessment) / (3% of original budget)	Academic and consultancy fees. Costs of operating in Karamoja.	UNICEF has achieved cost savings from contract negotiations with the research suppliers,	UNICEF reported that through their negotiations with partners they have negotiated and made a saving of close to GBP 10,000. / The FSNA itself has been instrumental in focused distribution to those areas only affected by the dry spell.
WFP – public works asset creation (cash and food transfers) / (approx. 70% of overall budget)	Development workers travel within Karamoja without armed escorts. / Telephone communications and poor bank services in the Karamoja region.	Continuous reduction of the project support cost rate per beneficiary and increase in the Resource Envelope rate per beneficiary, ensuring that larger portions of the resources are channelled directly to beneficiaries	Year	Project support cost per Beneficiary	Resource envelope per beneficiary
			13/14	$49	$53
			14/15	$39	$26
			15/16	$15	$46
WFP – supplementary programme / Commodities cost approx. 58% of budget	Market prices / Inflation	Availability of corn and cereal in Karamoja and neighbouring areas	Last year, the commodity unit prices reduced due to favourable market prices at the time of purchase. WFP utilised the savings to procure additional commodities like sugar. The cost per beneficiary is £34.15
FAO – Procurement and delivery of Animal vaccines 2.14m doses / Approx. 13% of overall budget. £1,005,801	Inflation / UgX		Currently working with FAO to document the VFM of the Vaccination programme.
General Operating Costs / UNICEF 8% / FAO 10%	Remoteness of beneficiaries and areas. / Management and support of weak implementing partners / Management of corruption	Negotiated UN admin costs last year.	UN has maintained the cost of doing business in Karamoja this year even in the light of the current inflation and poor exchange rates.
	Inflation / UgX currency	Annual review of contracts with Implementing partners

VfM performance compared to the original VfM proposition in the business case
Across the programme partners are maintaining their focus on value for money and are including VfM descriptions and data in their six monthly reports. Some of the VfM highlights and key influences (as summarised in the table above) are described below:

1. Ugandan Shilling (UgX) Devaluation - Since March 2014, there has been a devaluation of the UgX against the USD at 38%. Across the programme, the fixed contract rates have not changed significantly but this has reduced the cost of operations for costs paid in UgX for UN and their partners.
2. Procurement and delivery of RUTF - UNICEF reports that due to changes in global prices, the cost of RUTFs has gone down. Out of the planned £2m for RUTFs needed for the entire project, £1.93m has been spent, thus a cost saving of £0.07m. The savings will go to purchasing more stocks that can be used to both extend the programme to June 2016 and respond to increased demands of the October 2015 lean season. Out of this total, the cost of delivering and managing RUTFs is £0.16m. Due to the devaluation of the UgX against the USD, there have been exchange gains on local contracts. UNICEF will undertake further work to report on the impacts of this currency movement in their October 2015 report.
3. Resources for Public Works Participants - WFP reports that the resource envelope per beneficiary stands at $46.6 in 2015 and the project support cost per beneficiary stands at $15. Compared to 2014, the resource envelope per beneficiary was $26 and the project support costs per beneficiary were $39. This movement in costs has been partly supported by the devaluation of the UgX but also through an improved process of cost benchmarking and negotiation with the implementing partners. Further details of this will be shared in the WFP October 2015 progress report.
4. FAO Vaccination Programme - FAO reported that instead of engaging an implementing partner to deliver the mass livestock vaccination, they have directly implemented this activity. This has had the benefit of strengthening the district local governments/ministry of Agriculture capacity for animal disease control in Karamoja. Similarly, the FAO reallocated funds (approximately £270,000) between programme activities on finding a proposed new World Bank programme and the DFID funded Braced programme had plans for providing livestock disease surveillance laboratory equipment to facilities in Karamoja. This focus of activities moved to cold chain equipment, disease surveillance (Tsetse Fly) and capacity building for the government staff. Further work in required to document and assess the VfM of the vaccination programme.

Assessment of whether the programme continues to represent value for money
The programme still presents good VfM. Our UN partners are doing a good job in the field with implementing partners and are demonstrating a continued commitment to secure VfM

The indirect returns on the investments will come most with the influence that this programme is having over both the Government and other development partners. For example, the team who developed the Nutrition Strategy are currently working with USAID to see how their programmes can contribute to this. The investments in the structures and systems for early warning are both supporting a more focused response to the current food crisis in Karamoja and will be further supported by new initiatives funded by the World Bank. The work to demonstrate the level of transformative impact (see section H) will demonstrate the wide range of impacts that the programme is having.

Quality of financial management
Overall the three UN agencies continue to provide DFID with the relevant reports every six months (prior to disbursement of funds) in an improved form. At the field level, UNICEF and WFP field staff undertake spot checks on activities, assets and finances every quarter. FAO carries out spot checks twice every year and as and when is required.

The UN implementing partners adhere to UN policies on financial reporting. Implementing partners report to UN monthly and where there are adherence issues, the UN has worked with IPs for corrective action and there is evidence to show this. The UN have done a good job of rigorously managing implementing partners e.g. UNICEF relies on Local governments staff at health centres for RUTF supplies management and works with GoU on training VHTs. GoU opened a separate UNICEF account purely for UNICEF activities. Where previous funds are not fully accounted for, this account is automatically blocked.

On the other hand, WFP partners carry out the agreed activities as per the work plan and budget, and then seek reimbursement from WFP, on presentation of activity reports and on inspection and verification by WFP staff that work has been done to quality standards. Lastly, FAO advances cash to implementing partners in smaller components in the ratio 30 (upfront): 50 (inception): 20 (completion) and sign short term contracts depending on the activities to be carried out.

On testing the due diligence that DFID Uganda carried out on the three UN agencies. UNICEF’s HACT is effective and works well for implementing partners to help them to quickly deliver as expected. Spot checks are scheduled quarterly, and are drawn from the HACT overall plan that is approved by Kampala office by the Chief of Operations and endorsed by the Head of the UNICEF field office in Moroto. An example is Abim district. Prior to working with Abim, UNICEF, through HACT, rated Abim as high risk and monitored their work closely. A few months down the road, Abim was reviewed again and UNICEF found that the risk was still high. At this stage UNICEF engaged Deloitte and Touche to audit their activities and the initial report agrees with the HACT report that the risk is still high. There is evidence to show that the Chief Administrative Officer has written to officers concerned to recover the funds that they have failed to account for. If the report is certified, UNICEF will change the mode of delivery to outsource this function to an NGO to manage activities instead of the district.

In implementing the programme the UN agencies are building up strong experiences in the management of corruption risks in the very challenging environment of Karamoja. However, the relationship between DFID and the UN agencies needs to be strengthened in terms of reporting against these corruption risks and on cases as they arise.

Date of last narrative financial report	UNICEF: 03 September / FAO: 13 August 2015. / WFP: 30 April 2015
Date of last audited annual statement	31 December 2014

E: RISK (½ page)

Overall risk rating: Medium (Outputs: 1 – Medium; 2 – Medium; 3 – Medium; 4 – Low; and 5 – Low)

The risk rating across outputs one, two, four and five has not been changed as a result of this review. The risk rating for output 4 has remained low despite the movement from an A to a B in this year’s assessment. This movement was related to delayed procurement processes of the two UN agencies but DFID are confident that the end of programme targets will be met.

The following risks were identified as being the highest risk factors for the programme performance in the development of the business case:

Risk 1: Deterioration in Security Situation - The security situation in Karamoja has remained stable. Partners are implementing the appropriate security guidelines, with advice from UN Department of Safety and Security and other inter-agency coordination mechanisms.

Risk 2: Programme negatively affected by floods, droughts of weather event – In September 2015 the Government reported an emerging food security situation in Karamoja, following poor rains. The DFID funded early warning systems are indicating pockets of high risk in three of the Districts. WFP and UNICEF are currently undertaking further analysis around a targeted response. DFID is also supporting the Government and UN partners around contingency planning for the 2015 El Nino event.

Risk 3: Agency technical capacity and leadership fails to meet expectations, leading to badly measured, poor quality results – DFID is working closely with partners to ensure that they maintain focused on achieving the results set out in the ERKP. DFID has funded a number of core posts across the ERKP to enable effective implementation. UNICEF and WFP now have full teams working on the programme and these are helping to improve the quality of planning and delivery. However, this remains an area of concern for DFID and further work is required to improve the quality assurance systems and incentives.

Risk 4: Lack of political support from central Government Institutions (– Relationships with government are now stronger than in September 2014. However, the new World Bank funded Northern Uganda Social Action Fund (NUSAF) Intervention and the new EU interventions (both of which will be located within OPM) will impact on the relationships between Government and other Donors. DFID as the lead of the KDPG is currently working with development partners to ensure that we work together in building a strong and productive relationship with government.

Risk 5: The pressure to meet the demands of immediate crisis in Karamoja places a threat against long term viability (new risk) – Karamoja has chronically high levels of malnutrition and very often there are calls to assist people in crisis. Poorly planned short-term responses to address vulnerability can undermine the viability of people, markets and government. DFID’s focus on resilience and research is helping to challenge the assumptions behind the delivery of aid into Karamoja. However, with many donors looking to redesign their programmes of support to Karamoja this is an area that DFID will need to focus on both for its own planning and in cross-donor discussions.

Outstanding actions from risk assessment: There is an ongoing need for active management of the political risks and risk concerning the GoU commitments to the DFID programmes in Karamoja. In addition, Karamoja remains a challenging place to work with very high levels of corruption. DFID will continue to work with the UN partners around their due diligence and systems for managing and reporting corruption.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The project budget has been revised from £38.5m to £42.4m following an approved addendum to the business case for an extra cost of £4.3million towards water management under GIZ and FAO. This extended the project end date from 31 March 2016 to 31 March 2017. On core programming, all agencies have requested for a three months’ extension to conclude activities and reporting.

For the first six months (October 13 – April 14) the programme was allocated £9.3million from ICF and approximately £9million was spent. In 2014/15 the overall country office budget was revised taking account of likely spend by programme partners. The budget was set at £12m against a forecasted expenditure of £12m and £11.7 million was actually spent.

Over the course of 2014/15 FAO spending has been delayed on two occasions following delays in the submission of progress and finance reports to DFID. On the first occasion (December 2014) the delayed payment of £0.4 million was moved out to April 2015 to give FAO a chance to adjust to staff changes and revisit the activity schedule (see qn. 4955456). The July 2015 disbursement was delayed until September 2015 following an FAO challenge to the requirements in the DFID financial reporting template (qn.5141704).

In 2015/16 we forecast to spend £16.7m. This does include an estimated spending on a contingency response to severe drought in Karamoja, which will be approximately £1m and £1m for a response to the threats of El Nino.
Key Actions for 2015	Status
Procurement of contracts	A number of consultancies are ongoing or planned for the next quarter. These include: M&E – transformational indicators, Gender and political economy assessment. / In addition DFID is working to start a Review of the nutrition supply chain (UNICEF); and a review of nutrition information systems.
Payments against forecast	The payments for each of the UN partners are scheduled for October and November 2015. These are due to be the last payments made under this programme for the core activities. DFID expects that these will be made in line with the forecast. FAO and GIZ payments for the integrated water management activities are also expected to proceed on schedule. / We are currently working with the programme partners to finalise their response plans for the prolonged dry-spell in Karamoja and the preparedness work for El Nino. Response plans and budgets will be completed by the end of October 2015 and the forecast updated accordingly.

Asset monitoring and control
Asset monitoring for the programme is coordinated by DFID Uganda programme management staff with support from the UN DFID liaison office. UN hold registers for programme assets which are regularly updated. Assets procured by downstream partners are monitored by Implementing Partners and the strength of monitoring systems is reviewed through the quarterly quality assurance reports. Contracts with Implementing Partners are reviewed every six - twelve months prior to signing another contract.

On this programme, UN-FAO has procured assets and a spot check on the assets confirms their existence in the asset register. Computers and printers are being engraved, motorcycles procured are currently at the registration process and the asset register will be updated to reflect these. Community animal health workers and Veterinary officers use the motor cycles to aid movement during sero-disease surveillance.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The delivery mechanism used by this programme does not directly use Government of Uganda systems. However, the programme is delivered by UN partner agencies who each work with both government (district and national) and NGOs to deliver the services required under this programme. The programme activities have been developed to be consistent with the Government’s Karamoja Integrated Development Plan (KIDP).

DFID is a leader in the Karamoja Development Partners Group and this forum is used to identify the progress towards the KIDP and to note any significant changes in government policy, which may run contrary to DFID’s Partnership Principles. In this year, DFID has worked closely with OPM to support their revision of the KIDP and are now working with USAID on the design of a research platform that will further support both donor coordination and government relationships. Following concerns expressed and the Karamoja Policy Forum DFID is now working to support a more evidence informed discussion around the state of mineral prospecting and mining in Karamoja.

H: MONITORING & EVALUATION (½ page)

Over the course of the reporting period the DFID programme team have visited the Karamoja region six times. This has enabled them to maintain a more evidence/reality based conversation with the UN partners. This knowledge is critical in the ongoing process of building confidence and a strong relationship between DFID and the UN that is based around VFM and results.

In addition, in February 2015, a team from the Independent Commission on Aid Impact visited Karamoja and spoke with UN partners as part of the review of “how we work with multi-laterals to achieve impact”. One of the observations from this report was that “the convergence and co-ordination of these agencies (UN) is helping to increase effectiveness, value for money and impact”.

Under the project each of the partners have budget that is dedicated to robust monitoring and evaluation. In all cases the systems are well established and contributing to the ongoing reporting around the programme. As part of the quality assurance for this work DFID contracted Delta partnerships to document the monitoring and evaluation systems that were being used by each of the agencies. Following this exercise Delta have developed a framework for measuring progress against the impact level transformative indicator (an ICF requirement). Delta are currently completing a retrospective baseline together with a review of progress from the programme over the first two years. This information is scheduled to be completed by November 2015. Delta will then use this framework to conduct an end of programme review.

DFID is currently working with the agencies to support their end of programme evaluation plans and to identify the evaluation gaps that will be filled with direct funds from DFID.

Gender - Across the programme the UN partners monitor and report on coverage in a gender disaggregated form. The nutrition services delivered by UNICEF are targeted to women and children, while those delivered by WFP are provided to all who meet the required level of need (with majority of recipients being children). In the PWP 57% of the participants are women. The terms of reference for the FAO farmer field schools include specifications on undertaking resilience activities that promote gender equality and reduce marginalization.

DFID are working with the PEAKS to undertake an assessment in Karamoja of the impacts of current DFID programmes on the empowerment of women and girls and men and boys. The study will also identify opportunities for strengthening work in this area.
As part of the new stream of work on integrated water resource management, FAO and GIZ are undertaking a full gender appraisal for watershed interventions at the inception stage. This is a broad reaching appraisal including issues around vulnerable groups, youth, HIV/AIDS. It will focus on generating a gender and youth baseline in terms of access to water and other watershed resources, participation in decision-making and participation in institutions.

Annual Review Process
The following activities fed into the review process:
1. DFID visit to Karamoja (September 14-18th). The team for this included: Ben Cattermoul (DFID Uganda); Alan Tollervey (DFID RED); Malcolm Ridout (DFID C&E); Howard Standen (DFID Uganda); Lydia Nandawula (DFID Uganda); and Maria Kwesiga (Delta) (see the trip plan at qn. 5159088).
2. Detailed interviews with key implementing partners (UNICEF, WFP, FAO and ACTED);
3. Review of narrative reports from UN agencies and GIZ;
4. As a follow up to this review, a meeting with government stakeholders will be arranged to present the overview of progress and to discuss the recommendations for the next year.

Annex 1: 2015 Annual Review Recommendations

What	Who	When
Undertake a full review of the effectiveness of the health systems model of support prior to the end of the current programme.	DFID, UNICEF, WFP	By March 2016
Amend the log-frame to reflect the growing understanding of the challenges to support nutrition outcomes in Karamoja.	DFID	December 2015
WFP to undertake an external evaluation of the current CBSFP programme this year, and DFID will need to work closely with WFP, both through the programme evaluation and via additional consultancy support, to review the programme and to consider alternative programme strategies and options.	DFID and WFP	June 2016
Supplementation programmes need to have much stronger link to those programmes that are targeting the systemic and underlying causes of malnutrition and hence, a strengthening of the current multi-sectoral approach of the UN agencies, and other donor and Government of Uganda funded programmes is critical.	DFID , UNICEF and WFP	March 2016
Develop evidence based guidance and processes that provides a common framework for action around nutrition behaviour change in Karamoja.	UNICEF, WFP, GoU and USAID NGOs	March 2016
Undertake research to better understand the role of the public works food transfer in terms of securing food security along the annual cycle. This research is required in terms of targeting, quantity, timing and use of the food ration.	WFP	March 2016
Assess the market links and value for money of the community livelihood development programmes (household income support programmes and livelihood impacts of the Agro-pastoral Field Schools).	WFP and FAO	March 2016
Assess the coverage of the current investment on social protection in conjunction with other social protection programmes (DFID and others) compared to the overall need. To have a significant impact on social protection, the environment and production, the programme either needs to be scaled up significantly or planned together with other investments in social protection or public works. Opportunities for more joined up programming should be explored.	DFID, World Bank, EU, WFP and GoU	March 2016
Develop a plan to strengthen and planning and delivery linkages with the ongoing BRACED programme in Karamoja under any future programme.	DFID	June 216
Undertake research to better understand the nature of the benefits from field schools and the linkages between the field schools and the wider communities.	FAO	March 2016
Agriculture extension is shown to be a high cost tool. Further work to understand the value for money based on the overheads per farmer / per result should be incorporated into the programme evaluation.	DFID and FAO	March 2016
DFID has significant investments into crop science. What opportunities are there for introducing bio-fortified and climate resilient crops into Karamoja? How could this be done in the context of poor private sector and infrastructure? And are there opportunities to apply a results based financing model in a context as complicated as Karamoja.	DFID Uganda and DFID RED	March 2016
The UN delivery partners to work with OPM NECOC to inform, influence and then respond to the development of the national early warning system.	FAO, WFP and UNICEF	March 2016
Investments in early warning should be made in recognition of the structure that is established. Careful VFM analysis should be applied to the introduction / continuation of any primary information generation systems.	FAO, UNICEF and WFP	March 2016
Undertake further rigorous assessments on the impacts of early warning messaging on behaviour in communities is required.	FAO and ACTED	March 2016
When district contingency plans are cleared, FAO and UNICEF should assess their connections and coherence with the many different early warning, contingency support and DRR plans currently being promoted in Karamoja.	FAO and UNICEF	March 2016
DFID Uganda will work with DFID CHASE to identify the scope of current investments of DRR and agree reporting lines that ensure coordination and coherence between initiatives.	DFID	November 2015
UNICEF and FAO should report on the process undertaken to provide coherent support to the district governments following their joint activities around contingency planning.	FAO and UNICEF	March 2016
DFID to maintain a focus on research quality and research uptake and use across the programme delivery partners.	DFID	March 2016
DFID to work with DELTA partnerships around two learning events that will focus around the role of the programme in supporting transformational changes in Karamoja.	DFID and DELTA	March 2016
DFID to fund external consultant to review VFM across the programme.	DFID	March 2016
DFID to negotiate with the World Bank with a view to strengthening communication and coordination across the development portfolio	DFID	November 2015
DFID Uganda to work with DFID HQ and the UN to strengthen our understanding of and approach to corruption management.	DFID & UN agencies	December 2015

Annex 2: Update on 2014 AR Recommendations

NB: Timelines for deliverables varied from what was set but progress is reported against the recommended actions overall.
Action	Resp.	Progress achieved	RAG
Identify strategy for meeting short-term staffing needs to ensure programme deliverables are met in full.	WFP and UNICEF	WFP and UNICEF have filled their vacant staffing positions. / UNICEF used funds save to contribute to the consultancy costs on the Karamoja Nutrition review
Update the ERKP log-frame.	DFID / UN Partners / Delta (M&E Consultants)	The ERKP log-frame review was undertaken and reported on in December 2015. / Following further changes to the programme, including a new stream of activities around water resource management the log-frame update was finalised in August2015.
Further define and then support both the individual and collective learning agendas	DFID / UN partners / DFID	DFID have developed a research and learning framework for the programme. / Each of the agencies now report on their research and communications as part of their six monthly reporting. / As part of the work on the transformational indicator DELTA will organise two evidence and learning events for the programme partners and other key stakeholders. / DFID are also working with USAID to develop a common research platform for Karamoja. / A significant amount of research and analysis has been produced over the past year of the programme. Work on knowledge management will need to remain as a priority to ensure this informs and influences both ongoing and future actions.
Support knowledge management across the programmes to ensure that learning is institutionalised.			ONGOING
Complete the remaining Due Diligence actions and to support their mainstreaming into the UN systems.	DFID and UN Partners	UNICEF, FAO and WFP have all responded to the Due Diligence requirements. / All agencies now report against VFM considerations as part of their 6 monthly reporting but further work is required by all agencies on their framework for quantitative monitoring of VFM.
WFP should be more active in facilitating continuous and shared learning across the implementing partners. And between this programme and others (such as the Karamoja Livelihoods Programme (KALIP) funded by the EU).	WFP	WFP have built in a stronger process around learning and development as part of their implementation of the fourth cycle of public works. Areas of coverage will include thought leadership, WFP value addition under ERKP, accountability and transparency, technical leadership, adaptive management, joint learning and coordination at scale. / With regards to Labour Intensive Public Works, WFP will document and support practical changes which are small and workable towards improved distribution process, asset quality, coordination and predictability of transfer. / DFID will work closely with WFP to follow how this learning and development process is implemented.	To follow up.
Review the role of supplementary feeding programmes in post emergency operational contexts.	DFID, WFP	The UNICEF nutrition review recommended a continuation of a revised form of the CBSFP given the high levels of malnutrition. / The proposed WFP country strategy focuses on bringing the supplementary feeding programme into the health system linked to a much greater focus on prevention. / The role and impact of the programme will be evaluated as part of the ERKP evaluation programme and DFID will work closely with WFP through this process.
WFP and the M&E team to work together to understanding and improve the impacts of nutrition messaging and education. This challenge should be informed by the behavioural research that is planned by UNICEF.	WFP	The UNICEF led research on Infant and Young Child Feeding practices was completed in August 2015. However the report is yet to be cleared by UNICEF and it is evident that further work will be required to strengthen to quality and applicability to the nutrition challenges in Karamoja. / In addition the ongoing work by WFP with the Ministry of Health is not clearly linked to either the UNICEF research or other donor funded programmes.
Identify the work required to better understand the effectiveness of Village Health Teams (VHTs) and how best to use them and coordinate donor practice. This should be done with the DFID Millennium Development Goals (MDG) team who can address this at a national level.	WFP and UNICEF	UNICEF and WFP have been engaged in discussions around improving the use of VHTs in nutrition programmes. The Karamoja Nutrition Strategy outlined a range of interventions that could strengthen this. / Further work is required with the DFID MDG team as part of a cross-office review of work in Karamoja.	ongoing
FAO should redevelop the strategy and work-plan for the use of these funds by December 2014. This will ensure that activities can begin without delay in April 2015.	FAO	FAO redesigned their work plan to show the delivery of activities over the remaining time for the programme. This was agreed as part of the process to release funds in April 2015 (see qn….)
DFID to work with UN partners to ensure the development of effective programming relationships between the ERKP and Office of the Prime Minister (OPM) / UNDP Disaster Risk Reduction Unit.	DFID, OPM, UNDP, UNICEF, WFP, FAO	DFID have been working with both OPM and UN partners to strengthen the working relationship. An indicator of the progress was a meeting held on September 1st where DFID and UN partners presented and discussed the range of early warning activities currently ongoing in Karamoja. The discussions focused on the potential that these have for providing basis for an improved national early warning system. / In meetings with the Commissioner for Disaster Risk Reduction DFID have been asked to support negotiations across all development partners around the formation of a new national early warning system.
DFID to review the status of the DEWS bulletin in October and develop contingency plan for the work.	FAO, DFID	DFID have worked with FAO to address the uptake and use of the DEWS bulletin. This has included changing the programme focus to enable technical assistance to be allocated to OMP NECOC to support the integration and learning from the DEWS system. / NECOC are currently working through an assurance process to formally release the August 2015 DEWS bulletin. / If the DEWS bulletin is release this will represent a key milestone in the uptake and use of the DFID investments into early warning systems. However, it should also be acknowledged that the systems and processes that ACTED have set up at community and district levels are now acknowledged by OPM as a necessary element of a long term early warning system for Karamoja.	Review further in the context of the new national early warning system
DFID to work with FAO and their implementing partner (the Agency for Technical Cooperation and Development (ACTED)) to improve the communications plans for the DEWS bulletins and IPC reports.	DFID, ACTED and FAO	DFID have encouraged FAO to improve the communications plan for the IPC report and DEWS bulletin. While the DEWS bulletin has remained strong at the community and district levels in Karamoja its dissemination beyond that has been restricted by institutional confusion at a national level. However, the same cannot be said for the IPC and it is clear that further work to understand the role of the IPC and the channels for supporting its uptake and use is required.
FAO to develop a strategy for the development of the IPC, including details of funding sources; data sources and communications.	FAO	DFID held a meeting with FAO in June 2015 to review the overall support to early warning systems in July 2015. This included a focus on the financial base and communications plans for the systems. / FAO have provided DFID with an overview of the current state and future potential of the IPC which includes the funding base and institutional framework. This does provide a clear vision for how the IPC may be developed. However, this does not address the improvements around the current programme that have been requested by DFID (see qn…) or the links with the ongoing work to build a national early warning system. / Further work is required in this area to both improve the current quality of communication and coherence between systems.	Review further in context of new national early warning system
DFID to work with UN partners to share programme activity maps and continue to support better coordination: within the project; across the region; and nationally.	DFID, FAO, WFP and UNICEF	Following meeting of the partner data management teams all partners are working together to map their activities. / WFP, UNICEF and FAO have all done this and are now working to develop combined maps to demonstrate the programme activities and to inform planning and evaluation work.	ongoing
Describe and communicate the process that is underway to strengthen DFID and UN working relationships around the common theme of resilience.	DFID and UN partners	UN partners have worked together to create a common Resilience Framework. A meeting was held in April 2015 to present the basis of this framework, but since this time the agencies have failed to reach agreement on a final version. / Agencies report that they now have plans to release this framework in October 2015.	Ongoing