Type of Review: Annual Review
Project Title: Education Programme, Burma
Date started : July 2011	Date review undertaken: November 2013
Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## List of Acronyms
APE	Alternative Parenting Education
CBOs	Community Based Organisations
CCA	Child Centred Approach
CESR	Comprehensive Education Sector Review
CFS	Child Friendly School
CILE	Creating an Improved Learning Environment
CMSS	Community Managed Support System
CMSS	Community-managed Support System
CSP	Costed Sector Planning
DEPT	Department of Educational Planning and Training
DP	Development Partner
DPRE	Disaster Preparedness and Response in Education
DSW	Department for Social Welfare
ECCD	Early Childhood Care and Development
ECWG	Education Communication Working Group
ELPs	Essential Learning Packages
EMIS	Education Management Information System
ETWG	Education Thematic Working Group
EXCEL	Extended and Continuous Education and Learning
FESR	Government's interim Framework for Economic and Social Reform
GoUM	Government of the Union of Myanmar
JESWG	Joint Education Sector Working Group
KBC	Kachin Baptist Convention
LEIP	Learning Environment Improvement Plan
LEP	Language Enrichment Programme
MDEF	Multi-Donor Education Fund
MEC	Myanmar Education Consortium
MEDG	Monastic Education Development Group
MERL	Monitoring, Evaluation, Reports and Learning
MNEC	Mon National Education Committee
MoE	Ministry of Education
MoSW	Ministry of Social Welfare
MOSWRR	Ministry of Social Welfare, Relief and Rehabilitation
MPC	Myanmar Peace Center
NE	New Generation
NFE	Non-Formal Education
NFPE	Non-Formal Primary Education
NNER	National Network for Education Reform
PEF	Parenting Education Facilitators
QBEP	Quality Basic Education Programme
SSA/SIP	School Self-Assessment/School Improvement Plan
SWG	Sector Working Groups
TEIPs	Township Education Improvement Plans
TEMIS	Township Education Management Information System

## Introduction and Context
What support is the UK providing?
DFID is providing £10.5 million over four years to increase educational access, improve systems efficiency and raise learning levels at basic education level. The programme runs from October 2011 to December 2015 and consists of 4 components: / Quality Basic Education Programme (QBEP) - UNICEF: Quality Basic Education Programme (QBEP) (2012-2015) was launched in January 2012. It builds from the achievements and lessons learnt from MDEF I. QBEP will support over three million girls and boys in Burma to go to government schools and benefit from improved quality of education through support to some 37 townships (11% of total townships in Burma)[1]. MDEF donors will provide USD 86 million over the four-year cycle. Between February 2012 to December 2015 it is expected DFID will provide (GBP 3 million, 6%), AusAID ( AUD 30 million, 37%), EU (EUR 22 million, 33%), Denmark (DKK 25 million, 5%), Norway (NOK 8.5 million, 2%) and UNICEF ($14 million,17%) / Myanmar Education Consortium (MEC): MEC support the building of capacity of complimentary (non-government) education systems and structures including community and school based early childhood development, non-formal education programmes for vulnerable children and young people who cannot attend government schools. The education providers are the State, the Monastic School System, Ethnic Education Departments and civil society/ non state organisations. Three founding members are Save the Children Myanmar, World Vision and Burnet Institute. Save the Children is the prime recipient of donor funds and hold contracts and sub-grant agreements with World Vision and Burnett Institute. World Vision and Burnett Institute provide sub-grants to their partners as required. Current funding comes jointly from DFID and AusAID with a joint commitment to date of $ 20 million. Total DFID contribution is £ 3.7 million (approximately $ 6 million) - 30% of current total fund from January 2013 to December 2015. / Save the Children – New Generation Programme: This programme had a focus on early learning and transition to primary school. The aim was to increase the number of children, particularly from the poorest communities in Burma, who access and complete their primary education, bringing new opportunities for children in Burma. The programme covered 10 Townships in North Shan and, Kayin States, Sagaing, Magway, Mandalay and the Ayeyarwaddy Divisions. DFID’s contribution is up to £2.7 million from May 2011 to June 2013. This programme was rolled into Myanmar Education Consortium from July 2013. / Creating an Improved Learning Environment (CILE) Programme - Shalom Foundation: This programme is trying to improve access to quality primary education in community based schools and schools under cease-fire administrated areas in Kachin and Mon States by creating a conducive learning environment for children on community based self-reliance support. DFID’s contribution is up to £1.1 million from November 2011 to October 2013.
[1] Please see Annex 1 – Map of UNICEF Implementing Townships in Myanmar

What are the expected results?
The intended impact of the programme is to increase the number and proportion of children (age 5-9 years old) in Burma accessing and completing a quality basic education. / The intended outcome is 200,000 (4 % of estimated eligible school age population[2]) children supported to remain in school with an increase in completion rates[3] during early years of primary school and to Grade 5 (9 years age). / The expected Outputs for the programme as a whole (including other donor contributions to the Quality Basic Education Programme (QBEP) and the Myanmar Education Consortium (MEC) are: / 125,000 children will benefit from improved Early Childhood and Development services, particularly in poorer, rural areas nationally. / 1.1 million primary school children (22% of estimated eligible school age population) will have improved access[4] to quality teaching and learning in schools nationally / 81,000 children will have improved access to quality non-formal, alternative and life skills education / Schools from 25 townships will have improved management and accountability to local communities. (please see annex 1 for geographic information)
[2] http://data.worldbank.org/country/myanmar 2010 no. of pupils on primary education
[3] The survival rate was not set in Education Programme, Burma Approved Business Case. The targets need to set if UNICEF QBEP complete Mid-Term Review in mid-2014 and agree targets on survival rate.
[4] Improved access referred children has an opportunity to engage early childhood development activities at school or community and boosting their readiness for school and long-term chances of academic success and increase access to quality learning materials and higher quality teaching provided through the programme.

What is the context in which UK support is provided?
Educational statistics in Burma are in the early stages of development. The current primary source of information on education in Burma is Myanmar Multiple Indicator Cluster Survey (MICS) 2009 - 2010[5], other sources include UNESCO Institute for Statistics[6], World Bank Data on Education, Myanmar[7]and Comprehensive Education Sector Review report. The statistics that are available should be treated as indicative and prone to large margins of error. / From available evidence it is accepted that Burma is off-track to meet MDG2 - ensuring that all children complete a full course of primary school. Overall 22.9% of Burma children aged 36-59 months attend early childhood education. Pre-school attendance in urban areas is more than double that of rural area.[8]According to CESR report, the primary school enrolment rate of 5-9 year olds is 84.6% for 2010-11 school year. The average primary school dropout rate is 11.1% between the school year 2006-07 and 2010-11. Dropout rate is highest in Grade 1 (14%) and Grade 5 (21.7%) according to CESR report, Completion rate based on National Data in CESR report is 68.6% but Multiple Indicator Cluster Survey (MICS) completion rate is 54.2%. Dropout rate for urban is 1.9% and rural is 13.9%. No data is available for conflict affected areas. Standards of literacy, numeracy and overall attainment are low. An even smaller proportion of children, usually from richer families, have access to secondary and higher education. / More positively, available evidence suggests Burma is close to meeting MDG3 - ensuring gender equality. At the primary level the ratio of boys to girls is broadly equal[9] with no overt discrimination against girls in teaching practice. However, there are variations across different regions and there is some evidence that more boys drop out in the later years of primary school in order to work. Government figures suggest that women outnumber men significantly in higher education. Burma's newly formed Parliament has a total of 659 elected members. Of these, 20 are women. / The root cause of these problems is the chronic underinvestment in education by the Burmese government over the course of decades and the failure to reform. Relative to other countries in the region a disproportionate amount of Government expenditure is devoted to the military with low levels of support to social services such as health and education. A key assessment of the real relative priority of education can be done by examining the amount allocated, as a percentage of total budgetary expenditure, and as a percentage of GDP.[10] / As a percentage of total budgetary expenditures / Education spending (as measured by allocation to the Ministry of Education) in the 2012/13 budget amounted to MMK 752,066 million, which is 11% of total spending on ministries and departments (MMK 6,833,362 million). In the Myanmar context, total budgetary expenditures exclude expenditures by State Economic Enterprises (SEEs) because these are in general more than covered by SEE Receipts. The following table shows education spending by type in 2012/13: / Expenditure Type Amount (MMK Million) / Current 543,016 / Capital 209,050 / Financial (interest) 0 / Total 752,066 / As a percentage of GDP / From Annex 2 we can see that education represents 15.2% of current expenditures on ministries and departments, and 6.7% of corresponding capital expenditures. Budgeted GDP for 2012/13 is MMK 51.38 trillion as indicated earlier. Accordingly, education spending as a percentage of GDP is 1.46%. / For a regional perspective, the figure shows government spending on education both as a percentage of GDP and as a percentage of total government expenditure. Unfortunately the latest comparative information is for 2008, at which time Myanmar spending on education was at 0.7% of GDP and 3.5% of total government expenditures. However, budgeted spending for 2012-13 has been added, which still compares poorly with Myanmar’s neighbours, even if fully implemented. There is clearly some distance to travel and this could hinder Burma’s economic development if its workforce remains poorly educated compared to those of neighbouring countries. / There are high nominal increases in spending in the budget for FY 2012-13, but these may be less significant than they at first appear because of substantial salary increases and increases in the price of imported goods. Neither of these represents an increase in real resources for the education sector. Education spending is dominated by salaries (current) and construction (capital), which is positive, but the concern remains that salary pressures crowd out spending on goods and services. / Education in Burma is traditionally highly valued and many parents are prepared to make great sacrifices for their children’s education. Both current quasi-civilian government and opposition set education as a high priority. The 30 Year Long Term Basic Education Development Plan 2001-2031 sets out a range of strategies under ten broad Goal Programmes to achieve Universal Basic Education by 2016 and Universal Secondary Education by 2031 – however costing, resourcing and implementation all present significant challenges. It remained to be seen whether the transition to a nominally civilian government will make any difference. / A significant number of children who cannot access public schools rely on education services provided by monasteries and other religious organisations, community groups, and ethnic minority state administrations operating outside the control of the Burmese government. Monastic schools have operated in Burma since the 11th century. They are strongly community-focused, often offering a range of services. These schools receive little or no financial or management support from the central government or local authorities but provide services to some of the poorest and most vulnerable children in Burma as the cost of attending them is relatively low. However, there are strong differences between individual monastic schools, with some maintaining similar hierarchical and authoritarian relationships with communities and children that are typical of government schools. / DFID Burma’s education programme is designed to address these issues by expanding existing programmes and partners with a stronger focus on access, quality and inclusion of the poorest and most marginalised children. There will be an increasing focus on demand-side approaches, including increased community participation and mechanisms to increase accountability and responsiveness of the education system to meet the needs of communities and their children. Improved educational standards should contribute to higher growth and productivity as could contribute to stability and peace.
[5] Myanmar Multiple Indicator Cluster Survey (MICS) 2009 – 2010 : http://www.unicef.org/myanmar/resources_1375.html http://www.unicef.org/myanmar/resources_1375.html
[6] UNESCO Institute for Statistics : http://www.uis.unesco.org/template/pdf/EducGeneral/Factsheet07_No6_EN.pdf http://stats.uis.unesco.org/unesco/TableViewer/document.aspx?ReportId=121&IF_Language=eng&BR_Country=1040&BR_Region=40515
[7] http://data.worldbank.org/country/myanmar
[8] Myanmar Multiple Indicator Cluster Survey (MICS) 2009 – 2010 : http://www.unicef.org/myanmar/resources_1375.html http://www.unicef.org/myanmar/resources_1375.html
[9] Myanmar Multiple Indicator Cluster Survey (MICS) 2009 – 2010 : http://www.unicef.org/myanmar/resources_1375.html http://www.unicef.org/myanmar/resources_1375.html
[10] Snapshot of Social Sector Public Budget Allocations and Spending in Myanmar http://www.unicef.org/myanmar/resources_1375.html

## Section A: Detailed Output Scoring
Output 1: Improved ECCD service delivery and coverage, particularly in poorer, rural areas
Output 1 score and performance description: B / Overall Assessment: This output on the provision and coverage of early childhood development services is scored at B because although indicators on policy and the quality of ECCD Centres are on track, the indicator on children reached by these services is still lagging. / Progress against expected results: / Source of Data: UNICEF 2012 Annual Report, UNICEF 2013 Mid-Year Report on Quality Basic Education Programme, MEC Six-Monthly Report 2013 and Save New Generation – Final Technical Report 2013 / Output Indicator 1.1 Baseline Milestone 1 (2012) Milestone 2 (2013) / No. of children who have benefited from ECCD services Planned Awaiting baseline data from UNICEF QBEP. MEC : 2700 (From Current Save Programme) 28,841 / UNICEF: 20,000 Save: 8,841 MEC: 74,298 / UNICEF: 40,000 Save: 19,582 MEC: 14,716 / Achieved 20,656 / UNICEF: 20,416 MEC: not started in 2012 Save: 2, 740 (1,347 boys and 1,343 girls) 42,071 / UNICEF : 28,000+5,000 MEC : 242 children (122 boys and 120 girls) Save : 13,829 (6,955 boys and 6,874 girls) / Output Indicator 1.2 Baseline Milestone 1 (2012) Milestone 2 (2013) / % of ECCD centres that meet minimum quality standards (School and Community Based) Planned 5% for school based No target set 10% for school based 30% for community based / Achieved Baseline on quality of school-based preschools conducted in 15 townships and 181 schools were monitored by UNICEF. UNICEF : 17% for school based / 31% for community based / Save : 175 community operated centres with agreed minimum quality standards for ECCD / Output Indicator 1.3 Baseline Milestone 1 (2012) Milestone 2 (2013) / Multisector ECCD national action plan/policy in place Planned 0 Policy Framework designed Policy Drafted / Achieved National Steering Committee and Task Force established. Policy outline has been developed. Policy Finalised and submit for approval. / Draft 5-year strategic plan in place for review / Key Progress / Drafting of a holistic multi-sectoral Early Childhood Development Policy was completed through an inclusive, participatory process. The five year ECCD strategic plan (2014-2018) was drafted and it highlights key strategies and related activities, responsible agencies and costed-plan. / QBEP programme The programme provided technical support to Ministry of Education to revitalize a Kindergarten curriculum as part of the “quick win” in the Basic Education System. It facilitated the visit of multi-sectoral delegation from Government of the Union of Myanmar (GoUM) to Cambodia to study the country’s experience in policy development and implementation of ECCD programme. / The QBEP programme also supported expanding quality ECCD and building an effective system. An overall orientation and planning workshop for pre-school expansion involved 193 representatives of Departments of Basic Education, State/Regional Education Offices, District Education Offices and Township Education Offices, who provided important inputs to the planning process and strengthening of systems building. A participatory learning and action assessment process on community needs and readiness for implementation of pre-schools in academic year 2013-14 was carried out and 639 communities were involved. Out of 639 communities, 199 had initiated to open pre-schools with the support provided by the programme. / MEC Programme: Initial delays in the sub-grants contract signing have had an impact on the ability to schedule activities as intended during the school year. Under the component of ECCD, World Vision and Save the Children had implemented the community engagement activities such as situation analysis on early childhood development opportunities, community engagement in the establishment of ECCD community centres and management committees. Both partners of MEC were confident that the planned targets will be achieved within the first twelve months of the project period. / Evidence and Research / A baseline study of 181 school-based ECCD facilities in 15 targeted townships was undertaken in 2012 to report on the proportion of such facilities that meet minimum quality standards. The results indicated the scale of the challenges still to be faced, showing that only 2 per cent currently meet all 15 core quality indicators, and that 54 per cent need urgent attention.
Recommendations: / QBEP and MEC to work to identify ways to accelerate improvements in the quality of ECCD centres. / QBEP and MEC to promote integrated early childhood support – nutrition, health, education and parenting in line with latest research evidence / Development partners promote strengthened and integrated data management and use – including use of Geographic information systems (GIS). / DFID to encourage cross-learning between QBEP, MEC, the Livelihoods and Food Security Trust Fund (LIFT, which works in the livelihoods sector), and the 3 Millennium Development Goal Fund (3MDG, which works in the health sector). / Impact Weighting (%) : 25% / Revised since last Annual Review? No / Risk : Medium / Revised since last Annual Review? No

Output 2: Improved access to quality teaching and learning in schools
Output 2 score and performance description: A+ / Overall Assessment: / This output is scored as A+ since milestones on numbers of students provided with essential supplies and teachers trained have been exceeded. Although there is some evidence of a change in teaching practises, quantitative information on this indicator is not available. / Steady progress has been made on improving the quality of teaching. The programme contributed to the development of a national teacher education policy and draft national teacher education strategy. As downstream interventions, a training manual is being developed with the MoE team to strengthen the capacities of primary head teachers in instructional leadership. At the same time, the capacities of primary teachers in targeted townships were strengthened using a revised Child Friendly School (CFS) in-service teacher training manual. / Progress against expected results / Source of Data: UNICEF 2012 Annual Report, UNICEF 2013 Mid-Year Report on Quality Basic Education Programme, MEC Six-Monthly Report 2013 and Shalom CILE Programme – Annual Narrative Report 2013 / Output Indicator 2.1 Baseline Milestone 1 (2012) Milestone 2 (2013) / No. of students in targeted townships provided with essential supplies for basic learning materials and textbooks, including humanitarian support Planned 0 658,051 / UNICEF: 620,000 Shalom: 38,051 678,218 / UNICEF: 632,000 Shalom: 46,218 / Achieved 684,003 / UNICEF: 654,120 Shalom: 29,883 (15,312 in KIO + 14,571 in Mon) 853,204 / UNICEF : 758,054 Shalom : 50,152 / Output Indicator 2.2 Baseline Milestone 1 (2012) Milestone 2 (2013) / % of primary teachers applying improved teaching methods as defined by classroom observation criteria Planned Awaiting baseline data from UNICEF QBEP. UNICEF: 20% / MEC: 15% / Achieved Baseline report on teacher practices in classroom has been finalized. (UNICEF) UNICEF : Field observation indicates changes in certain teaching practices / MEC : 0 / Output Indicator 2.3 Baseline Milestone 1 (2012) Milestone 2 (2013) / No. of Primary teachers receiving training Planned 3900 UNICEF: 3,900 MEC: 0 10,256 / UNICEF: 9,250 MEC: Shalom: 1,006 10,979 / UNICEF: 9,250 MEC: 400 Shalom: 1,329 / Achieved 9,452 / UNICEF: 9,080 Face-to-Face+ 1,125 INSET Shalom: 149 13,034 / UNICEF : 10,933 (Second batch will start in August 2013) MEC : 0 Shalom : 1,191 / Key Progress / QBEP programme - Key highlights include: / Comprehensive Assessment / Strengthening of teachers’ education included comprehensive assessments in education colleges by a joint project team from Chiang Mai University of Thailand and Kobe University of Japan with initiative and leadership from the Ministry of Education. The study covered 4 Education Colleges out of 20 which trained pre-service primary school teachers. The study is expected to be completed by late 2013 and the findings will also inform the CESR process. / Pre- and In-service Teacher Training / QBEP is engaging in continuous advocacy for a broader scope for teacher education in Basic Education, Technical and Vocational education and Non-formal Education. QBEP contributed to the development of a national teacher education policy and draft national teacher education strategy and both incorporates pre- and in-service teacher education as well as the elements of continuing professional development. / 10,933(6% of national data[11]) primary teachers were trained on effective teaching and learning practices in 37 townships nationally / 6,799 teachers (including teachers from non-state providers in Mon State) from 37 townships nationally were trained to deliver a Language Enrichment Programme / Evidence and Research / QBEP undertook analysis of a baseline study on learning achievement conducted in early 2012, as well as a comparison between the baseline and a follow-up study on teaching and learning practices. Together, these analyses are providing important insights into the impact of the QBEP programme in both critical areas of education quality. / Analysing Key Changes in Teaching Behaviour: A Shift towards more Child-Centred Approaches / Study results indicated that the following teaching-learning behaviours are occurring more frequently among teachers in 200 QBEP-supported schools in academic 2012-2013 than in the previous school year: / Checking the prior knowledge of students / Using a positive tone / Using equal participation / Using group work and peer tutoring, although it was still only used by teachers with higher abilities / Using a class layout for group work / Moving around to interact / Summarising findings / Asking open questions / Interacting with individual students / Allowing students to demonstrate something to the entire class / Working with students with special education needs / Evaluating student answers, probing, commenting and building new questions based on students’ answers. / Closed questioning and cued elicitation techniques – behaviours frequently observed during academic 2011-2012 – were observed less frequently and gave way to more child-centred forms of interaction. / Analysis of Student Learning Achievements: Major Challenges Remain / Analysis of the data from a baseline study on learning achievement among Grade 3 and 5 students in the Myanmar language and mathematics provided results related to quality of education. While students performed well on the Myanmar language exams in both grades, the exam papers in mathematics for both grades were found to be too difficult. / Only 17 per cent of students in Grade 3 were found to pass an arbitrary minimum requirement of having a 50 per cent probability of correctly answering a mathematics question with an average level of difficulty[12]. Similarly, only 22 per cent of Grade 5 students passed a minimum requirement of attaining a 50 per cent probability of correctly answering a question of average difficulty (see second graph below). / Scaling Up of Secondary Life Skills / To scale up the national Secondary Life Skills (SLS) education, QBEP provided systematic and continuous capacity development support to MoE in 2012-2013. This has been achieved through the provision of technical support for review and revision of the national curriculum, and through capacity building of national trainers and 11,200 secondary teachers on implementing the new curriculum in 93 townships. As a result, 916,000 lower secondary students were benefiting from a learner-centred Life Skills programme that equips them with both knowledge and psycho-social competencies. / 12 school health staff and 138 monastic school teachers also were trained; in turn, nearly 4,000 students had the opportunity to deepen their knowledge regarding reproductive health and HIV prevention through health talks and lessons. / Provision of School Supplies / Over 758,000 (15% of students in primary education nationally at 2010[13]) primary school children were provided with essential learning materials (stationaries, text books, exercise books, back pack, etc.) including children in conflict affected areas. Overall enrolment data for 2012 showed 464,217 children attending primary schools in the 25 townships. The data also showed that in many targeted townships, enrolment had increased by 2 to 8 per cent between the 2011-12 and 2012-13 school years (see Figure Below). / Figure: Enrolment Difference Between Academic 2011-12 and 2012-13 / MEC Programme: Only Burnet and its partner organization contribute to this output in the reporting period. A national baseline of 127 monastic schools in 8 states and regions has begun and will finish in November 2013. Design and data collection tools were developed with the support of an external consultant from Melbourne. / Monastic Education Development Group (MEDG) established three hubs in three divisions (Mandalay, Sagaing and Ayeyarwaddy). The MEDG is headed by senior monks elected by all states and divisions to represent Monastic Education to donors and to set minimum standards for Monastic Education around the country. The hubs will coordinate teacher training activities, assist in monitoring and evaluation, and provide resources for teachers. MEDG is mentored by Burnet Institute and regular quarterly meetings set up for strategic planning. / CILE Programme - Shalom: 50,152 primary students received basic schooling materials in Kachin and Mon states.
Recommendations: / MDEF donors should support the development of research and impact evaluation capacity as well as a hub for knowledge sharing. / UNICEF to clarify how Output Indicator 2.2 will be measured. / Impact Weighting (%) : 35% / Revised since last Annual Review? No / Risk : Medium / Revised since last Annual Review? No
[11] http://data.worldbank.org/country/myanmar
[12] In Myanmar language, if we set the minimum requirement in the same manner, we find that 55% of Grade 3 students and 77% of Grade 5 students passed this requirement.
[13] http://data.worldbank.org/country/myanmar

Output 3: Improved access to quality non-formal, alternative and life skills education
Output 3 score and performance description: A+ / Overall Assessment: The outputs achieved moderately exceed the milestone targets. For out-of-school-children, downstream work focused on increasing their access to two innovative Non-Formal Education (NFE) programmes. The programme reached 40,000 out-of-school children, mostly working children, and equipped them with life skills while promoting literacy. With regard to upstream work, capacity development support was provided to standardise the national examination for primary equivalency, under the Non-Formal Primary Education (NFPE) programme. A national task force to facilitate the strategic priority of expanding NFPE in Burma was set up with the leadership from Ministry of Education and participation from different actors: UNICEF, INGOs, LNGOs and private donors. / Progress against expected results / Source: UNICEF 2012 Annual Report, UNICEF 2013 Mid-Year Report on Quality Basic Education Programme, MEC Six-Monthly Report 2013 / Output Indicator 3.1 Baseline Milestone 1 (2012) Milestone 2 (2013) / No. of children who have accessed non-formal, alternative or life skills education Planned 19,000 / UNICEF: 11,000+8,000 MEC:0 20,000 / UNICEF: 14,000+6,000 MEC: 20,570 / UNICEF: 14,000+6,000 / MEC: 570 / Achieved 41,577 / UNICEF : 24,000 EXCEL + 17,577 NFE 20,000 / UNICEF : 10,800 EXCEL + 9,200 NFPE MEC : NFE study completed. Report to be finalized for dissemination. / Output Indicator 3.2 Baseline Milestone 1 (2012) Milestone 2 (2013) / Percentage of reached out of school adolescents completing EXCEL in targeted townships Planned UNICEF: 85% of total reached complete full course UNICEF: 85% UNICEF: 85% / Achieved 96% for EXCEL (2011-12) 2012-2013 completion data will be collected later in the school year. (UNICEF) 97.1% of total reached learners completed 3-phase EXCEL course / Key Progress / QBEP programme - UNICEF : / Bolstering opportunities for out-of-school children and expanding NFPE / To increase access of out-of school children (OSC) to alternative learning opportunities, QBEP Programme and the private sector supported MoE in expanding access of 16,426 OSC aged 10-14 years to the Government’s two-year accelerated NFPE programme. This strategic partnership has resulted in expansion of the programme to 483 centres in 73 townships (UNICEF 38, MoE/private sector 45). / Meanwhile, both the NFPE and EXCEL programmes have been expanded for academic year 2013-2014 to 80 townships and 22 townships respectively, thereby increasing the access of out–of-school children and adolescents to education. A total of 20,000 out-of-school children were enrolled in either NFPE or EXCEL for the year (9,200 NFPE, 10,800 EXCEL); this is close to the 2013 targets of 10,000 and 14,000 respectively. Some 627 new NFPE facilitators attended a 7-day training of trainers in 3 zones (Yangon, Bago, Magwe), while 327 new EXCEL facilitators received Phase 1 EXCEL training of trainers. The latter includes how to teach basic reading and writing and provides learning materials. / Lastly, in January 2013 a third workshop on adolescent storybooks was conducted to increase access to adolescent reading materials. Involving 16 post-EXCEL learners from geographically diverse backgrounds, the workshop resulted in the production of 28 storybooks on peacebuilding, environmental conservation, reproductive health, prevention of HIV, prevention of tuberculosis and malaria, prevention of sexually transmitted infections, prevention of trafficking, and landmine awareness. All have been finalised and are ready to print. / Fostering a national equivalency framework / Development of a national framework for Non-Formal Education equivalency and certification has particularly been prioritised. As part of this initiative, UNICEF advocacy for institutionalising a standardised NFPE equivalency test has been a key strategy to allow other actors to implement the Government-led programme, while MoE retains quality assurance control. Such advocacy resulted in MoE agreeing to allow the Myanmar Literacy Resource Centre (MLRC) to be the first NGO to support implementation of NFPE. A task force representing key education stakeholders has begun work on the standardised test. / In addition, UNICEF facilitated South-South cooperation whereby a team of Government officials was sent to Indonesia to observe that country’s accelerated equivalency programme, as well as its relevant policies, structure and system, and to learn how to continue to expand coverage. Another team, consisting of NGO staff and Government officials, was enabled to attend a regional workshop in Bangkok on alternative learning equivalency programmes with the aim to further advocate to policymakers. Both teams have shared their findings and recommendations, including setting up of a specific Department of NFE, with the Deputy Minister of Education and the CESR team. / Evidence and Research / A study on the subjects of NFPE level 2 (Myanmar language, mathematics, English, general studies) by using standardised tests and covering 2,000 NFPE students and 800 formal school students from 13 randomly selected townships was carried out in early 2013. Results of the study showed that achievements in English, Myanmar language and mathematics are all better for formal students than for NFPE students, although differences in mean values generally were small. In general studies, achievements of NFPE students were at the same level as that of formal students. These results indicate that in order to achieve the expected level of learning competencies, closer monitoring and mentoring of NFPE facilitators will be required. / Meanwhile, the completion rates for NFPE learners in academic 2012-2013 stood at 65.14 per cent of 4,664 level 1 learners and 77.03 per cent of 4,045 level 2 learners, illustrating the continuing challenges of dropout and low attendance. Out of 3,116 successful candidates for secondary school, 720 (23.11 per cent) are currently enrolled at secondary level. For both levels, the average pass rate was quite high, at 85.06 per cent for level 1 and 94.80 per cent for level 2. Determination of a learner’s completion of each level was made by taking into account their performance in level-end tests, attendance, achievement of expected learning outcomes, and performance of activities in the integrative workbook. / Increasing EXCEL coverage / Through partnerships with 6 NGOs in 21 townships, the QBEP also continues to support life skills and literacy enhancement for older adolescents under the EXCEL programme as part of second-chance education. A total of 9,235 out of 9,505 out-of-school children enrolled in EXCEL training in academic 2012-2013 (97.1 per cent), including 14 children with disabilities, completed Phase 3 of the programme in March 2013, significantly surpassing the 2013 target of 85 per cent. In addition to these out-of-school children, 4,664 parents and other community members (60 per cent females) also received EXCEL lessons to improve their knowledge and promote awareness of the prevention of communicable diseases. / MEC Programme: A qualitative study on the situation of non-formal education was carried out by World Vision Team in 8 townships in 4 States and Divisions and the analysis showed that in 90% of targeted townships, educational services are not currently available for out of school children. One of the leading reasons for drop-out is economic hardship; with most of the out-of-school children working as vendors or scavengers, during the school day. Disability was found to be another reason for not accessing education services.
Recommendations: / QBEP and MEC to investigate: / The prevalence and reasons for non-school attendance – by age, gender, special need, location etc / ‘Pathways’ through education – specifically the potential for students in NFE to re-enter the formal education system and how best to incentivise this. / The cost effectiveness of existing NFE offers to ascertain and disseminate best practice / Impact Weighting (%) : 20% / Revised since last Annual Review? No / Recommendations / Risk : Medium / Revised since last Annual Review? No

Output 4: Improved management of schools and accountability to local communities
Output 4 score and performance description: A / Overall Assessment : Output 4 should score A as QBEP support to development of Township Education Management Information System (TEMIS) has expanded to 15 townships from the baseline of 3 partially operational townships, exceeding the milestone for this year. / Progress against expected results: / Output Indicator 4.1 Baseline Milestone 1 (2012) Milestone 2 (2013) / Proportion of schools with operationalized SSAs/SIPs in targeted townships Planned 0% 20% / Achieved 1000 schools received training on SSA/SIP process, 5000 PTAs members trained on school improvement plan 1,300 schools from 24 townships have developed SIPs / Output Indicator 4.2 Baseline Milestone 1 (2012) Milestone 2 (2013) / # of townships with TEMIS fully operational Planned 2011 TEMIS partially operationalised in 3 townships TEMIS partially operational in 5 townships TEMIS partially operational in 8 townships / Achieved In the selected 25 townships for TEMIS programme, school data is being collected with revised TEMIS forms and data entry on computer database for collected TEMIS data is in the progress. The TEMIS database is now partially operational in 15 townships / Key Progress / Enhancing education planning and management / A module for the training of head teachers in instructional leadership has been developed (linked with Output 2) and 30 core (master) trainers have been trained. This module will be used to train all head teachers in the core 25 townships in the future. / To strengthen the capacity of schools and school cluster personnel in education planning, management and mentoring, the programme has trained 1,300 head teachers in these townships on effective school management, community mobilisation and facilitation for improved participation in schools. / Bolstering Education Planning at Township and School Levels, Through TEIPs/SIPs, School Grants and TEMIS / QBEP programme provided technical support in terms of planning, budgeting and monitoring of educational delivery at sub-national level. A rapid review of state-, district-, township- and school-level planning, budgeting, monitoring and financing issues was conducted in April 2013 in 4 townships of Mon State. The manual is considered a dynamic document that has gone through continual adaptation and delivery, with pilot trainings to be held throughout all of Mon State before delivery of TEIPs to 25 QBEP townships in academic 2014-2015. / Out of some 1,300 schools in 24 townships that developed School Improvement Plans (SIPs) in 2012 following self-assessments, about 400 schools from 16 townships have been selected in 2013 as priority recipients for school grants to support implementation of their SIPs. / QBEP support to development of the Township Education Management Information System (TEMIS) continues to expand; thereby underscoring the programme’s deepened commitment to ensuring reliable education data collection and analysis. The TEMIS database is now partially operational in 15 townships.
Recommendations: / UNICEF to coordinate and ensure compatibility of Education Management Information Systems (EMIS) and geographic information systems (GIS) among the multiple parties engaging in this area. Strong EMIS / GIS underpin rational, cost effective education expansion and are a starting point for accountability and performance management. / In promoting better data use Development Partners encourage the integration of map based digitisation of data fields from the outset – e.g. in health, education and livelihoods, etc. / DFID to explore opportunities to strengthen educational outcomes that may be created by a major increase in mobile telecommunications penetration over the next 2 years. / Impact Weighting (%) : 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N / Advancing Support to Overall Education Reform / Comprehensive Education Sector Review (CESR) is the first review being undertaken in the education sector since 1993, and represents a breakthrough towards greater aid effectiveness and an intensely collaborative effort under the new government with a broad range of development partners. / With extensive QBEP support and the coordinated technical assistance of a coalition of development partners, the CESR was formally launched in Nay Pyi Taw on 23 October 2012. The landmark event sent a strong signal of shared commitment to support evidence-based policy and planning, improve equity, and strengthen education results throughout the system. / The overarching objectives of the CESR are: / Develop a knowledge-base on the strengths and challenges in the Myanmar education system and identify areas for reform; / Support and contribute to the development of evidence-based policies, legislation and education sector improvements; and / Develop costed education sector plans (based on the findings of the review). / The CESR will be conducted through a coherent three phase process, which aims to strike a balance between completeness, quality and timeliness. / QBEP has strategically supported capacity development of the CESR team and conducted several analytical studies during the CESR’s first phase, which have informed the findings and recommendations of the Ministry of Education’s Rapid Assessment Report, and will also contribute to further in-depth analysis, policy development and planning during the education reform process. These studies include reviews of Basic Education policy, education law and legislation; a study on textbook policy; and analysis to support development of a national strategic framework for teacher education, thereby addressing a key policy gap. / In all, the CESR has been a catalyst for fundamentally changing the way the Ministry of Education and development partners work together, forming a closer, more collaborative partnership. This has built trust, positive relations, shared ownership, and joint commitment to results. It has also helped develop a more focused, shared vision, and built Ministry confidence in its capacity to lead. As a result, this process has positioned the education sector at the forefront of good development cooperation practices at a critical time in Myanmar’s evolution toward broad reform. QBEP support has played a strategic role in delivering these results so far. Through its continuing support to the coming phases of the CESR, QBEP is well-positioned to leverage influence on sector reform and promote more equitable, sustainable education outcomes for children in Burma. / Education Support for Conflict affected Area / In the overall context of persistent conflict in parts of Burma, which continues to affect education opportunities for thousands of children, the Education programme is enhancing attention to peace building issues through QBEP and Shalom Education programme. QBEP and Shalom developed a strategy on education for conflict prevention and peace building, incorporating both early peace building and adolescent capacity development, using ECCD and Life Skills-Based Education as entry points. As part of the “whole state approach” in Mon State, UNICEF also has managed to bring Government and non-Government education actors together. / QBEP programme developed children’s storybooks for peace building to celebrate diversity and foster appreciation of different cultures and languages. These books will be printed in both the Myanmar language as well as six ethnic-minority languages. Supplementary reading materials on conflict resolution and peace building also have been produced as part of the literacy component of the EXCEL programme. / QBEP also responded the hard to reach and emergency affected areas in consultation with MoE based on assessments of education situation in camps and series of conflict analysis work carried out by the UN and other agencies in both the Rakhine and Kachin States, take into account measures of both conflict sensitivity and peace building and also based on the response plans developed under UNOCHA with all clusters and key actors.

## Section B: Results and Value for Money.
1. Progress and results
1.1 Has the logframe been updated since last review? No / The logframe has not been updated since the logframe in the Business Case approved in July 2011. / 1.2 Overall Output Score and Description: / The following table summarises the scoring by output provided in section A. / Output Number Output Description Impact Weight (%) Output Performance Risk / Output 1 Improved ECCD service delivery and coverage, particularly in poorer, rural areas 25% B Medium / Output 2 Improved access to quality teaching and learning in schools 35% A+ Medium / Output 3 Improved access to quality non-formal, alternative and life skills education 20% A+ Medium / Output 4 Improved management of schools and accountability to local communities 20% A Medium / The cumulative output score is A (Outputs met expectation) / 1.3 Direct feedback from beneficiaries / Beneficiaries’ feedback on Save – New Generation Programme / Participants’ feedback in the Participatory Programme Review held in June 2013 reported that parents and Parenting Education Facilitators (PEFs) are more coordinated and actively involved in ECCD provision as their level of understanding on child development and the value of ECCD have increased. As a result of parenting education session, children are benefitting from improved care and parenting practice by their parents. Parents display positively changed attitudes and opinions of children and have become more interested to be involved in the ECCD services as they have seen their children’s behaviour and social communication and language development improving. Furthermore, the interest in ECCD has been seen to widen to neighbouring villages. Participants noted that they saw children with disabilities show progress and development which has been challenging stigma and attitudes towards disability in the communities. Caregivers were consistently reported to be capable, dedicated and efficient. Participants also reported significant impact of Community-managed Support System (CMSS) for vulnerable children who have needed support to enable them to come to ECCD centres and Primary School. Management Committee members reported that their capacity has increased and the Management Committees are performing well. / Beneficiaries’ feedback on UNICEF QBEP programme / "I have to confess sadly that I violated child rights a lot. I treated [children with disabilities] badly and did not care much about them. In this training, I learned about child rights and came to know how to treat them with respect. At first, I was very afraid of children with disabilities. I did not want to touch them, and avoided them as much as possible. But now I am not afraid of them anymore. I came to understand that they needed our touch, our warm heart, and special care. I have decided to practice what I learned from this training and share my knowledge with community leaders, church leaders, parents and teachers in my village.” One of the ECCD caregivers confessed at the review session in ECCD caregiver refresher training.
1.4 Summary of overall progress / Overall the Education Programme has made good progress, mainly driven by the largest element QBEP as MEC started half way through the reporting period and the small Shalom and SCF components were coming to an end. More children are in school, with better educational materials and better-trained teachers. And school management systems have been strengthened. Milestones on getting more children into education, and supporting them with better educational materials were exceeded. The milestone on getting more children into ECCD was missed, though substantial progress was made and the milestone for the quality of ECCD was met. Milestones for out of school children and adolescents attending non formal or alternative education were met. Milestones for the improved management of schools in targeted areas were also met. Milestones for training teachers in Child Centred Approaches to learning were met but more data is needed on the impact of this training in classrooms. / Quality Basic Education Programme (QBEP) – UNICEF / At policy level, the multi-sectoral ECCD policy is nearly finalised and a draft Five Year ECCD Strategic Plan with QBEP support, highlighting 10 key strategies and incorporating investment and coordination plans, is undergoing review. The achievement indicates the continuing great scope for ECCD expansion as community and family interest in ECCD accelerates in Burma. / Critically, the CESR process has continued to make progress during the first half of 2013 and is increasingly referred to by MoE as a comprehensive education reform process rather than a “review,” which suggests a recognition that the initial two-year period marks the beginning of what will be a much broader undertaking. / Overall, it is becoming apparent that the QBEP has high potential to make a lasting impact in the quality of and access to education for the state’s children. / Myanmar Education Consortium (MEC) – MEC / Although it was due to start in late 2012, it actually started in April 2013. All the three partners (Save the Children, Burnet Institute and World Vision) had initial delays in the contract signing, which had an impact on the ability to schedule activities in keeping with the school year. This meant rearranging some activities and affected the achievement of targets. However, MEC is confident that the planned targets will be achieved within the first twelve months of the project period. / Early Learning and Transition to Primary School Programme: New Generation – Save the Children / The project has been implemented over a period of unprecedented and unexpected change across Burma both in the wider political, social and economic context, but significantly in the education sector. This has presented opportunities but also unexpected challenges which have impacted on the project. The programme ended in June 2013 and was incorporated into MEC in July 2013. The DFID Burma Education programme team plans to do a study on the evidence about Early Childhood Development which has been developed under this programme and how this can be applied in future Education Programme in Burma. / Creating an Improved Learning Environment (CILE) in Kachin and Mon States – Shalom Foundation / It had a significant delay due to active conflict in Kachin since mid-2011. Due to the significant challenges encountered in Kachin as well as the organization capacity in the programme management, the programme is not likely to meet their targets at output and outcome level. The current grant finished by end of October 2013.
1.5 Key challenges / Political ethno-linguistic tensions / Language is at the heart of nation building in Burma. The potential of education as a unifying force for social mobility and driver of growth and social development (or conversely as a centripetal force) was greatly determined by issues associated with language of instruction. / The country continues to struggle with communal conflict in Rakhine State and other parts of the country, as well as the armed conflict in Kachin and Shan States. The results were delayed implementation of the education activities in some targeted townships in Kachin, Shan and Rakhine States. / In many states parallel systems of education delivery are in place – state education (in Burmese) and local language non state education. Education was put at the heart of peace negotiations but this has not yet led to improved education links between the state and non-state providers. / Governing Environment / Education in Burma is the responsibility of 13 line Ministries. The two most important after the Ministry of Education are the Ministry of Religious Affairs (faith based schools) and Ministry of Science and Technology (vocational high schools). Establishing links within these Ministries was challenging within an institutional structure that does not readily support inter-Ministerial communication and coordination. / Decentralisation is occurring much faster than anticipated. The government is increasing its staff at state, district and township levels but roles and responsibilities, decision making and budgeting remain unclear. / Donor coordination / The education scene is dynamic – there is a unique window of opportunity for donor partners to shape the development of an education system. This will however be dependent on DFID and/or other development partners strengthening their in country technical expertise on education. / Lack of and Use of Data / Evidence generation and information sharing is weakly developed. There is a need to strengthen ‘research’ and knowledge management. / The Ministry of Education remains cautious about wider dissemination of data to the general public and the CESR does not yet have an internet platform on which it posts its documentation.
1.6 Annual Outcome Assessment / The rapidly changing overall governance landscape in Burma has offered unprecedented opportunities to build on the Burma Education Programme. Education plays an important role in nation building, social development and economic growth. There are strong correlations between education level and maternal and family health. Education was the first sector to embark on a comprehensive sector analysis and reform. The government has proven evidence of increased commitment in education sector by doubling the budget from 2011-12 to 2012-13, albeit from a low base. / The programme has supported improved access and quality of basic education for children in many disadvantaged townships. Through different programmes (QBEP, MEC, Save and Shalom), DFID Burma Education Programme has supported education reform, system building and capacity development (national, state and regional and townships) and education support in emergencies (Kachin and Rakhine). / Over 20,000 children are now accessing quality services to promote early childhood development, boosting their readiness for school and long-term chances of academic success / Over 850,000 primary school girls and boys, including children in hard-to-reach areas affected by conflict, are also able to learn more effectively through learning materials and higher quality teaching provided through the programme / The programme also reaches out to children who are unable to attend formal school due to poverty and other barriers, with over 42,000 school-aged children benefiting from non-formal learning programmes. / The national figures for primary school net enrolment rate are 84%[14] in 2012 which is an important increase even though it remains low compared to the regional average of 94%.
[14] UNICEF Mid Term Review Report (Draft) Annex 1 : Map of QBEP Targeted Townships

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / Components Budget planned (£) 2011-15 Actual Spent (£) 2011-15 Budget vs Actual (%) 2011-15 Budget planned (£) 2013-14 Actual Spent (£) 2013-14 Budget vs Actual (%) 2013-14 Remarks / Design for Burma Education Programme 31,000 29,445 95% 31,000 29,445 95% Completed / Save the Children : Early Learning and Transition to Primary School, New Generation Programme 2,638,096 2,556,471 97% 665,014 255,176 38% Programme ended on June 2013. 3% underspent at the end of programme. / UNICEF : Myanmar Quality Basic Education Programme 3,000,000 3,000,000 100% 0 0 0% On-going Programme. A full disbursement of committed budget from DFID to the programme. No budget planned/Actual spent in year 2013-14. / Shalom : Creating an Improved Learning Environment 1,304,223 896,184 69% 541,494 133,455 25% Programme ended on October 2013. Programme absorption is 69% of the budget because of unstable situation in some Programme areas. / MEC : Myanmar Education Consortium 3,528,574 2,200,000 62% 1,073,811 1,000,000 93% Programme implementation has been five months period and it is in inception phase. / Total 10,501,893 8,366,282 80% 2,311,319 1,418,077 61%* / *Due largely to underspends by Shalom and SCF, both of which have now come to an end. The unspent funds will be channelled into MEC. / 2.2 Key cost drivers / Following is the cost drivers of the projects base on up to date actual expenditure or final expenditure report. According to the analysis, the lack of M&E data is alarming although both UNICEF and MEC programme put a great emphasis on generation of evidence. The programme budget will need to review factoring the available resources for independent evaluation. / UNICEF QBEP Programme (Jan 2012 - Jun 2013) / Early Childhood Development 16.8% / Quality Basic Education 47.5% / Education Planning and Management 2.9% / Second Chance and Alternative Education 8.8% / Emergencies 0.0% / Technical support 11.2% / Cost of local office 2.6% / Other cost and services 6.3% / Support to special targets townships 0.4% / Monitoring & Evaluation 3.6% / Note : Excluding 7% Indirect Cost Recovery MEC Programme (Feb - Jul 2013) / ECCE work utilise 47% / Access to quality basic education 28% / Policy Dialogue 0% / NFE alternatives for out of school children 3% / Capacity building 5% / Monitoring and Evaluation 2% / MEC Program Management Unit (Admin/Management) 15% / Note : Excluding 11% Indirect Cost Recovery / New Generation Programme - Save the Children (May 2011 – Jun 2013) / Staff 46% / Running Costs 9% / Training 19% / Construction ECCD Centres & Refurbishment of Schools 11% / Matching Funds and micro projects 10% / Learning Materials 4% / Consultants and Evaluation (not including staff costs and staff related travel costs for M&E staff) 1% / Note : Excluding 7% Indirect Cost Recovery CILE programme - Shalom (Nov 2011 – Jul 2013) / Project Inception Phase and Core Master Plan Development 2% / Organizational Development and Technical Resource Sustainability for Education department 2% / Capacity Building of Teachers, Education Officers & Central Education Committee (CEC) 14% / Strengthening Monitoring Support Mechanism and Evaluation 7% / Materials supports 61% / Establishing Mini – Library 1% / Fundraising for long - term Educational Support 1% / Regular M & E visits 1% / Project team regular Management/admin Costs 11% / Note : Excluding 7% Indirect Cost Recovery / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The QBEP programme had a crucial focus on building a firm, evidence-based foundation to provide comparative data with which to measure improvements in education quality by 2015. Numerous baseline surveys have been conducted, including: / Survey of the number of school-based Early Childhood Development (ECD) facilities meeting minimum quality standards; / Study on classroom teaching and practices to assess teachers’ methods and effectiveness; / Study on learning achievements in maths and Myanmar language for Grades 3 and 5. / Significant efforts have also been made to strengthen other aspects of M&E, including through capacity building and improved field data collection/supply monitoring. Detailed findings are shared in the Detailed Output Scoring Section. / The Save the Children – New Generation Programme carried out two studies to evaluate the effectiveness of the programme / Alternative parenting education approach / School Readiness Assessment / The findings from both studies showed that parents acquire systematic parenting knowledge on how to give care and support according to the nature of child development in the implemented villages. Concern with child care practice and development grows, parents become aware of their inaccurate knowledge and they also acquire skills to give positive discipline and listen attentively to children after attending PE sessions. Perceptions changed on children with disabilities, understanding the need to give more love, attention and support. Understanding of the importance of playing for children learning increased and the need to support children to learn in a healthy environment. Some habits or beliefs did not change like giving priority to younger children, though this is good for younger children who need more support and attention from adults. / 3.2 Where an evaluation is planned what progress has been made? / QBEP and MEC programme have a crucial focus on building a firm, evidence-based foundation to provide comparative data with which to measure improvements in education quality by 2015. / A mid-term review of QBEP was planned to be conducted jointly by the MoE and the UNICEF/MDEF partnership focus on Quality and Effectiveness and Governance and Management. Due to the delay in recruiting the MTR consultants, the schedule for mid-term review shifted from November 2013 to January 2014. The Steering Committee is finalising the selection of consultants for the QBEP mid-term review. / MEC began implementation in April 2013 so it is too early for an evaluation.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / Political Risk / Both the government and opposition see education as a priority – Education is the first sector to embark on a comprehensive sector analysis and reforms, which were endorsed by the President. Expenditure on education has doubled over the last year. / With regards to education policy, the Constitution of 2008 states that citizens (a) have the right to education; and (b) shall be given basic education which the Union prescribes by law as compulsory. Again, education policy in the 30 Year Plan of 2001 stressed the importance of education and transformation of Burma into a knowledge-dominated, learning society in which education attains international standards. However, there are still challenges in the actual implementation. / Limited exposure and contact with high level officials at the MoE and National Education Committee tends to limit progress on key policy changes. / Human Capacity Risk / The human resource capacity gap in the MoE is due mainly to the lack of adequate budget and lack of ability to hire the required number of professionals to support the implementation and expansion of quality basic education in Burma. Rapid expansion of the teacher workforce and appropriate training to develop this work force is going to be a major challenge. There is a big role for development partners to strengthen teacher education and human capacity building in the Ministry of Education, incorporating the best evidence based practices from situations in which resources are limited. / Contextual Risk / Historically UNICEF and JICA are the bodies holding MoUs with the Ministry of Education. UNICEF in particular has been the key player in education over the last decade with donors engaging with government through them. Alongside this, donors have held bilateral agreements with a number of small NGOs, delivering education in conflict affected areas and the monastic sector. There needs to be a more carefully thought out division of labour in support of central government planning and financing of the Education sector in Burma. / At field level a plethora of new NGOs are offering alternative delivery modalities. There is a need to develop a firm coordination structure in the education sector for formal / non formal division of labour. MEC could play an important role in helping orchestrate geographically targeted, coordinated, quality assured interventions as well as playing a role in research, knowledge management and as a conduit for NGO voice, especially in the Comprehensive Education Sector Review (CESR). / Fiduciary Risk / DFID payments to partners were payments in arrears. Partners’ cash flow situations were regularly monitored and analysed before disbursement. Agreed payment schedules were amended with MoU amendments following the cash flow analysis. Funds were withheld where insufficient evidence of expenditure was provided. External annual audits were conducted on the partners and management responses to the audit recommendations were regularly monitored. / Conflict Risk / There is a risk that work in conflict-affected areas exacerbates conflict and/or does not contribute positively to peace building objectives. Conversely, inter-communal conflict and continuous violence in Rakhine State and other parts of the country may cause disruption to programme implementation. Emergency preparedness should be mainstreamed in the programme with effective training and standby agreements for assessment and response, factoring in the principle of “do no harm”. / Regionally focused education work should not be conceived as neutral – areas such as language and history are inherently political – development partners need to be fully aware of this and keep this in mind when channelling support to NGOs.
Risk of funds not being used as intended / With regard to field monitoring, an investigation into UNICEF-branded supplies found in markets in Yangon and Dawei (8 sets of exercise books, 3 textbooks) found that none were from the UNICEF-/MDEF-supported QBEP programme that started in 2012. The textbooks were all identified as fake copies misusing the UNICEF brand name. The MoE supply management team was informed, and the Director General of DEPT issued a letter to all programme townships reminding all MoE staff to prevent any leakage of UNICEF-branded supplies to market sellers. UNICEF will disseminate a public corporate message on the ban on using the UNICEF brand but also will continue awareness raising among targeted communities and markets regarding UNICEF supplies. / In terms of supply monitoring, supply receipt forms were revised and the tracking system was improved. / 4.4 Climate and Environment Risk / Climate and Environmental risks are minimal. Transport to and from and around the implementation site and monitoring was one impact but the estimated value achieved by supporting quality education was thought to outweigh this impact.

5. Value for Money
5.1 Performance on VfM measures / Measures to be used to assess value for money were set out clearly in the Business Case. However, all the implementing partners’ reports do not specify clearly how they performed on value for money. This is one area Education Programme Management team needs to request greater emphasis on in future progress reports from partners. Anecdotal evidence on VFM includes: / Economy / QBEP and Save – New Generation Programme: Resources of ECCD toys are made with inexpensive local materials, which are affordable for communities to replace. Practical ECCD workshops for communities include how to make educational toys and resources using inexpensive local materials. / Indirect costs negotiated with UNICEF in 2011 - an overall ceiling of 7% of the total fund may be allocated to indirect costs. / Technical expertise procurement for the survey and reviews were through competitive tendering. / The equipment used in Save – New Generation Programme will be redeployed to MEC Save the Children Programme at the project closure. / Efficiency / MEC support to leaders within the Monastic Education System to collaborate and share information. / The programme supported minimum standards for efficiency and performance (e.g. minimum quality standards for community-managed and school-based ECCD centres, competency of ECCD caregivers, ECCD network groups, school administrators in the monastic school system, competency and teaching and learning techniques of teachers in alternative education systems, NFE centres); / The programme made significant efforts to strengthen other aspects of M&E, including through capacity building and improved field data collection/supply monitoring as well as establishing community feedback mechanisms. / Save – New Generation Programme performed strongly on delivering efficiently – it achieved its targets whilst remaining under budget. / Effectiveness / QBEP facilitated eight members of a multi-sectoral delegation from Burma to visit Cambodia in early 2013 to learn about the country’s experience of policy development and implementation of an ECCD programme. / The QBEP Programme has forged a working partnership with state education service providers at local and national levels to deliver quality basic education services and strengthen the education system in Burma through evidence based research and the CESR process. / In addition to the results detailed above, the benefits of the program have been significant and include: / Integrated approach to service delivery (ECCD, Primary Education, NFPE, Life Skill Education) / More effective coordination between NGOs, UN and Development Partners through various coordination mechanism (ETWG, JESWG, etc) / Enhanced policy dialogue between partners and the Ministry of Education / Equity / Exact rates of disability and developmental delay among young children in Burma remain unknown, but such children are receiving increasing attention as understanding of relevant issues increases. Training on developmentally appropriate practices is given to preschool teachers by the Government and NGO partners. / The Rapid Assessment Report recommends scaling up implementation of the NFPE programme. It would not only increase the programme reach but also provide new education opportunities for a greater number of the nearly 1 million children currently out of school. This has long been a key advocacy message from QBEP. / 5.2 Commercial Improvement and Value for Money / QBEP called for bids to conduct the comprehensive survey of the Education College system according to UNICEF’s procedures, with a joint project team from Chiang Mai University of Thailand and Kobe University of Japan winning the process. This was in line with the Government’s goal of receiving priority technical assistance from a team led by representatives of a country from the Association of South East Asian Nations (ASEAN). / MEC is in inception phase. MEC implementing partners have their own procurement policies and practices in place with common standards addressing, for example, value for money, child protection, environmental impact, untied procurement and fair and open competition and asset inventory. Procurement for the MEC program is guided and managed by Save the Children Myanmar’s procurement policy. / Unit Cost Analysis / Costs of ECCD programmes across the world vary significantly caused by differences in programme characteristics, delivery mode (e.g. parental education, home-based care models, community-managed or school-based ECCD services), focus of the intervention, age range of children, staff requirements, and duration. / There are a range of unit costs in the Business Case to support assessments of value for money: / Per year unit cost / Unit cost per child for teaching and learning materials (full learning package) $10 (UNICEF) / Unit cost per child per year at the outset of Save the Children’s first programme £60.09 / Estimated unit cost per child for the new programme £36.05 / The following unit cost analysis is based on activities carried out by Burnet Institute, Save the Children and World Vision in the first two stages of MEC’s development. These costs were relatively high as it includes the set-up costs – ECCD construction and network group funding. These costs will fall over time as the programme expands and more children enrol in ECCD centres. / Two years unit cost per child ($) Save the Children World Vision / (MEC) (NG) / ECCD Centre 437.28 240.06 562.32 / Parenting Education 123.40 99.14 / Alternative Parenting Education 191.79 137.40 / Transitions Curriculum 33.40 20.15 / 5.3 Role of project partners / UNICEF and Save the Children Fund Myanmar are the fund managers for QBEP and MEC programmes. Both partners ensured programme results were delivered on time, as anticipated and to a high standard. All the decision making for the QBEP and MEC programmes is through quarterly Steering Committee meetings. Discussions in Steering Committee meetings include procurement, risk, programme updates, engagement opportunities with the CESR process, sector coordination, and programme reviews. / Both MEC and QBEP have dedicated resources to set up M&E, manage information, and analyse and present it for informed decision-making at Steering Committee meetings. But as highlighted in Section 5, both programmes need to put evidence based results on VFM into their regular reports. / 5.4 Does the project still represent Value for Money : YES / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / There are no specific conditions.

7. Conclusions and actions
Overall, the Education Programme has delivered good results, achieving most of its targets and exceeding them in many areas, despite the delay in the implementation of MEC. / Coordination in the education sector (JESWG, ETWG) served as a catalyst for MoE and development partners to form a closer, more collaborative partnership which has built trust, positive relations, shared ownership and joint commitment to results in the education sector. / The key lessons learned from the Education Programme in Burma were the importance of government leadership and the importance of strengthening the capacity of national, sub-national and local level partners (including MoE) for effective implementation and the sustainability of the programme. / The way forward / Though great efforts have been made by Government and Development partners to respond to the emerging opportunities, the need is huge and the importance of education to the peace and stability of Burma cannot be overstated. There is clear pressure on both the current government and the opposition to improve education as one of their key priorities. Investment in education can bring transformative change and DFID Burma can help achieve important results in the sector, including by encouraging lesson learning from other countries. / The opportunities to shape the evolution of education delivery in Burma are immense. The pace of change combined with the level of resourcing currently available will require careful strategic choices and staff time to ensure results are delivered. There needs to be a further analysis on the upcoming resource allocation round in education investment on focus area: geographical and / or technical as well as modality (government and or non-state actor). / The recent visit from Senior Education Adviser (DFID Burma 15%) in June 2013 had laid out 2 possible scenarios: / DFID focuses on support through the non-state sector – current position – to ensure effectiveness this will require strong relationship management and greater technical input. It may be worth considering focus on niche areas and quick wins for DFID support, e.g. promoting a shift to integrated nutrition / cognitive development (with an associated research programme). / DFID focuses on strengthening government processes – In the medium to long term DFID Burma should seek to engage with this space. Ultimately making government national provision more effective and cost efficient is the prize. This would likely have staffing implications – both in CPD of local staff and deployment of targeted technical knowhow and even consideration of a full time adviser. / In the interim the programme needs to remain connected to the rapidly accelerating engagements with government – as is being done through the Public Expenditure Review (with the World Bank) and the close working relationship with Australian AID.

8. Review Process
This review is based on from the UNICEF Quality Basic Education Programme Jan - Jun 2013 midyear report, MEC Feb - Jul 2013 progress report, Save – New Generation Programme May 2011 – Jun 2013 Final report and Shalom Creating an Improved Learning Environment Program Nov 2012 - Apr 2013 progress report. / The review process took place over the period of November 2013 and this has been peer review process. DFID review team comprised Mr Billy Stewart (Senior Health Adviser), Dr Mya Thet Su Maw (Health Programme Manager) and Nan Hom Nwet (Programme Officer). Peer review and quality assurance of the report was done by Chris Hindley (Head of Programme Delivery), Colin Bangay (Senior Education Adviser), Thom Adcock (Economist) and Hoa Ngo Thi Quynh (Result Adviser). / List of Documents in the Review Process are / UNICEF Quality Basic Education Programme Jan - Jun 2013 midyear report (Quest no 3999775) / Draft UNICEF Quality Basic Education Programme Jan - Jun 2013 midyear report (Quest no 4182814) / MEC Feb - Jul 2013 progress report (Quest no 4226396) / Save the Children New Generation May 2011 – Jun 2013 Final report (Quest no 4226388) / Shalom Creating an Improved Learning Environment Program Nov 2012 - Apr 2013 progress report (Quest no 4226382) / MDEF Steering Committee meeting and midterm review on 13th Sept 2013 (Quest no 4226409, 4186704) / UNICEF MDEF II Programme Document (Quest no 3393602) / MEC Description of Action (Quest no 4224984 ) / Shalom Nov 11 – Oct 12 annual report ( Quest no 3767947) / Education Programme in Burma Business Case (Quest no 3160718) / Education Programme Logical Framework (Quest no 3160723) / BTOR Colin Bangay, Senior Education Adviser (DFID Burma) June 2013 (Quest no 4069817)