Business Case and Intervention Summary

Title: Extending DFID Nigeria’s Policy Development Facility into Phase 2 (PDF 2)

What support will the UK provide?
Nigeria Policy Development Facility – Phase 2 (PDF 2) / The UK government will expand its Policy Development Facility to continue to provide targeted assistance to help Nigeria’s ‘champions of change’ implement economic and social policies that lead to poverty reduction. The second major phase will enable the UK to back reform through: / Backing key economic and public sector reformers in Nigeria with technical support. / Conducting research and studies that can be used to influence and shape Nigeria’s economic reform agenda. / Initiating explorative studies for potential complementary DFID programmes. / It will be complemented with HMG lobbying efforts around key policy priorities. / How much funding does the UK expect to provide? / This business case is for an additional £18.5 million to expand the existing £15 million facility. The overall facility size will therefore rise to £33.5 million and will be competitively retendered. / Period of funding? / The funding will cover a five year period (FY 2013/14 – FY 2018/19).

Why is UK support required?
Need to continue supporting Nigeria to be better at reducing poverty. / The Nigerian government faces major challenges in policy making and implementation of its economic and social reform agenda. These challenges include limited evidence-based policy, weak institutions and weak government agencies. Historically, the bonanza from the oil and gas sector has crowded out the effective development of other employment giving sectors of the economy. Ultimately these challenges mean that despite over 10 years of economic growth averaging 7% a year, poverty levels in the country have remained roughly the same at around 100 million poor. / The UK’s role and ability to make a difference. There is a lot at stake for the UK. HMG has a unique position to support Nigeria as a development partner for the following reasons: / the historical bilateral relationship; / not many other development partners in country; / HMG has broad bilateral relationship on trade and security; / DFID works closely with FCO in lobbying and seeking influence – protecting and promoting champions of change, and countering corrupt or poor performance in the public sector. / Effective leverage is critical in Nigeria and has delivered results / Leverage (influencing) successes HMG has achieved in recent years include: / The 2005 Debt Relief Deal, followed by creating sustainable debt management capacity through 3 phases of support to the DMO (now ending), a big institutional and VFM success. / The Petroleum Industry Bill, improved through political work (with Ngozi Okonjo Iweala) and technical support through Nigeria’s oil and gas sector reform programme (FOSTER) and IFIs. / Routine Immunisation policies and systems, addressing a collapse in the last 2 years, through extensive lobbying of federal and international development partners. / Reform of the fertiliser subsidy, harnessing the lessons of DFID’s rural market programme (Propcom), and technical assistance to the Minister’s transformation plans. / Budget and financial management systems, through various work with the Finance Ministry. / The UK Government recognises that it can play an important role in supporting Nigerian ‘champions of change’ toward achieving poverty reducing growth. The current Policy Development Facility commitment space has been exhausted in advance of the expected time-frame for the programme (2010-2015) and the expansion will enable HMG to increase its support of key reformers and leverage poverty reducing change.

What are the expected results?
The Impact of PDF phase 2 is that the Nigerian Government implements policies that lead to poverty reduction. The Outcome is that Nigeria’s ‘champions of change’ make increased use of capacity and evidence to enable them to pursue vital economic and social reform. / The impact and outcome of this programme are fully aligned with DFID Nigeria’s operational plan. It will help leverage better use of Nigeria’s resources for its national development, unleashing its growth potential. Its approach reflects a principle in the operational plan that better governance and growth are inter-dependent. Much of the support will be aimed at addressing constraints to growth but it will also make a small contribution to the number of poor people whose incomes increase by between 15 and 50% (an operational plan result target). 6,300 incomes have already been increased by PDF 1, with this figure likely to double by 2014. / The political and policy challenges of working in Nigeria means many PDF investments may be unsuccessful. PDF is like venture capital. The question is not does everything have to be a success? The question is: are there enough high value successes to justify the overall portfolio? / The existing PDF 1 has produced enough high value success to more than justify its portfolio. Providing embedded advisers and technical support to key ‘champions of change’ across 10 government agencies. Notable high value successes include the establishment of a Sovereign Wealth Fund for Nigeria’s oil savings and successful implementation of a nationwide business plan competition running for its second round. It is on-track to deliver 12,000 new jobs through backing 2,400 young entrepreneurs. It is difficult to predict the results PDF 2 will contribute towards. It is a flexible and responsive portfolio that backs reforms where suitable opportunities emerge. It will ultimately be judged on whether there are enough high-value successes.

Business Case

Strategic Case

A. Context and need for a DFID intervention / President Goodluck Jonathan’s election victory in 2011 led to the appointment of an economic team that included notable reformers. This included renowned Ngozi Okonjo Iweala as his Coordinating Minister for the Economy and Minister of Finance. Other ‘champions of change’ included the Ministers of Power, Trade and Investment, as well as Agriculture. There was already a strong Governor at the Central Bank of Nigeria. The priorities of this team are focused around Nigeria’s ‘economic transformation agenda’. / The economic transformation agenda aims to achieve the following key reforms: / Ensure macroeconomic stability & sustainable growth / Carry-out structural reforms, privatization, liberalisation, and deregulation / Strengthen institutions, support transparency, fight against corruption. / Invest in priority sectors (infrastructure, agriculture, housing and construction, security) / These reforms are vital for economic growth and ultimately poverty reduction. Since 2011, the reform agenda has faced many challenges including: / Capacity Challenges / Limited current capacity of civil service to implement reforms at the pace and quality required. / Political Challenges / Public backlash and protest when the government attempted to remove the country’s petrol subsidy in January 2012. / Public Agency backlash, when the Minister of Finance attempted to reduce the number of agencies in Nigeria’s ports from 16 to 6 in order to reduce processing time of goods. / Privatisation challenges for the power sector including the resignation of the Minister of Power due to an alleged conflict of interest. / Periods of fuel scarcity caused by union action as a result of discontent with stricter processes to verify imports before payments. / A number of high profile reports pointing to corruption and mismanagement in the oil and gas sector. / Conflict Challenges / Increased instability and conflict in Northern Nigeria / The government has had varied success at overcoming these challenges to reform. In particular areas DFID Nigeria has backed reformers and the transformation agenda with technical support. This approach has already delivered results but it has depleted the PDF funds before the natural end of the programme. DFID Nigeria is seeking an additional £18.5 million to continue its technical support for Nigeria’s economic transformation agenda. Two of the highest Value for Money results achieved from PDF 1 portfolio are the establishment of Nigeria’s Sovereign Wealth Fund and 6,300 jobs created from the Youth Innovation and Employment programme ‘You Win’. / Box 1: Backing Nigeria’s Sovereign Wealth Fund / PDF support to the Sovereign Wealth Fund shows how the programme enables DFID to provide highly strategic, flexible funding to help the Federal Government implement a major financial policy reform in the face of significant vested interest. / Need / The Excess Crude Account (ECA) holds revenues from the sale of excess crude oil. Controversy surrounded its legal mandate and it has been subject to non-transparent disbursements. It was mainly used to fund recurrent expenditure at the different levels of government. The ECA fell from US$20 billion in January 2009 to US$0.5 billion at the end of 2010. / Opportunity / The Nigerian Sovereign Wealth Fund (NSWF) was seen as remedying the deficiencies of the ECA: it would be independently managed, have ring-fenced funds, be legally sound, have political buy-in, undertake transparent investments, and would have rigorous guidelines for withdrawal of funds. / Obstacle / In 2008, an inter-ministerial team was established to convert the ECA to a Sovereign Investment Fund. The team’s efforts were promising but unsuccessful. / Intervention / In 2010, time was running out for the then current administration to deliver this important reform. There was no assurance that a future administration would be as willing to safeguard excess oil revenues. DFID intervened: providing two financial and legal placements in the Ministry of Finance, and commissioning international expertise to prepare and lobby for a best-in class international fund within the short remaining term of the last administration. / The NSIA Act was passed by the National Assembly and assented to by the President in May 2011. PDF has been supporting the operational launch of the fund: the NSWF Board and key positions have been appointed and the Fund will make its first investments in 2013. / DFID’s critical role / This result could only have been achieved with DFID’s ability to bring in expertise to advise the Nigerian government. At the critical phase of implementation no Nigerian budgetary provisions were available to finance the significant technical expertise required. Further, no Nigerian emergency funds could be accessed without jeopardising reform: a request for an emergency appropriation would have needed Nigerian National Assembly approval, which would have exposed the project to opposition from key vested interests at a critical, and premature, stage. The 2012 Annual Review concluded that “without DFID support, the SWF would not have proceeded in a timely and rigorous way”. / Impact / The expected benefits of the Sovereign Wealth Fund for the Nigerian economy are significant: The country’s oil savings safeguarded for national development were £620 million in 2012 and will likely rise to much higher levels in the next few years. Part of these oil savings will be used to invest in much needed infrastructure projects, the remaining money will be invested in other assets for future generations with a component that can be used for macro-economic stabilisation. / Box 2: Backing Youth Innovation and Employment in Nigeria / PDF’s flexible and responsive support helped a flagship Presidential programme on Youth Innovation and employment create 6,300 new jobs across the country from the first round of a business plan competition. Another 6,000 are likely to follow by early 2014 bringing total job creation to over 12,000. / Need / Unemployment in Nigeria was estimated by Nigeria’s National Bureau of Statistics to be around 30 million people in 2010 and on the rise. 80% of the unemployed were young people between the ages of 15 to 44. Trends of discontent from this demographic group in North Africa and the Middle East as part of the ‘Arab Spring’ made this a high priority issue for the Nigerian Government, keen to show early impact. / Opportunity / The Presidential flagship project was aimed at having a quick impact on job creation, early in his administration. / Obstacle / The political need in Nigeria to demonstrate results quickly and robustly whilst using a very innovative approach meant that this project would have been challenging for weak government institutions to deliver on. The process of selecting winners through Nigerian Government systems with no checks and balances would undermine credibility of the fairness of the competition. It would also present a high corruption risk. / Intervention / The Nigerian Government ran a fair and merit based business plan competition targeted at young entrepreneurs. Candidates would put together a concept note and if successful were invited for business skills training with the aim of putting together a business model and business plan. Business plans were assessed by a local business school and 1,200 winners were selected. These winners were given seed capital (up to £40,000 from the Nigerian Government), and further training to help make their business a success. / DFID’s critical role / PDF quickly mobilised external expertise and technical support to help with the ‘nuts and bolts’ of running an innovative competition at fast pace and also brought in external partners such as Plymouth Business School and School for Start-ups to help quality assure the process and provide training to the young entrepreneurs. / Impact / From the first round alone 6,300 jobs have been created so far, 2,800 of these are in the conflict affected Northern Nigerian region. Around 1,200 entrepreneurs were given significant seed funding and training, with many more provided with basic business training. A further round targeted at women is currently underway, with a third round under development.
B. Impact and Outcome that we expect to achieve / The results in the table below provide examples of the results the Nigerian Government were able to achieve with support from DFID/ PDF 1. / Table 1. Portfolio of results achieved with support from PDF1 / Example of results achieved by Nigeria’s reformers DFID/HMG influence and technical support from PDF 1 / Recommendations to Nigerian Cabinet on developing a Northern Nigeria Growth strategy, leading to asset mapping exercise and future growth strategy development. / Port Reforms initiated to reduce port clearance time. Cutting number of government agencies present at ports from 16 to 6 and customs reform underway with an intention to move to streamlined approach. / Strengthened Federal Budget process / Review of government regulatory framework recommending areas for streamlining. / New Nigerian Agribusiness and Agro-Industry (NAADI) Policy and a new policy for the Micro, Small and Medium Enterprise (MSME) / Improved methodology for measuring job creation with field work commencing at end of 2012. / Monitoring and evaluation of local government level accountable grants and progress towards MDGs. / Launch and adoption of the Save one million lives programme strategy 36 embedded advisers providing technical assistance support to Nigeria’s ‘champions of change’ across more than 10 Nigerian institutions. / Ministry of Finance and Budget Office / Ministry of Trade and Investment / Ministry of Agriculture / Ministry of Power / National Planning Commission / Office of the Chief Economic Adviser to the President / Sovereign Wealth Fund / Ministry of Health / National Primary Health Care Devt. Agency / MDG office / Securities and Exchange commission / Studies on growth opportunities in three Northern Nigeria conflict affected states used to influence various members of Nigeria’s Economic Reform team. / Political economy of monitoring and evaluation study commissioned and distilled with the National Planning Commission. / Methodologies paper in measuring employment commissioned and provided to Office of the Chief Economic Adviser to the President. / Policy Study on Customs reform. / Women in cross-border trade study. / Political Economy of low cost private education in Lagos. Policy Studies on a range of areas (examples- list not exhaustive) / Sovereign Wealth Fund established and operational. Nigeria can make better use of its oil savings for its national development. $ 1 billion set-aside for its future use with more funds likely to be made available. Some of these funds will be invested in vital infrastructure projects in Nigeria, some in foreign assets (for future generations) and some funds on hand for macro-economic stabilisation. Without the Sovereign Wealth Fund these resources would have likely been used for recurrent expenditure rather than being invested. PDF provided critical technical support to help establish Nigeria’s Sovereign Wealth Fund. Providing financial specialists at a time when the framework and bill for the sovereign wealth fund were developed. Also providing embedded advisers and support to the screening process of high profile candidates. / 6300 jobs already created from 1,200 businesses selected on a fair and merit based basis to receive seed-funding and entrepreneurial training from the Federal Ministry of Finance. Over 2,800 jobs created in the conflict affected Northern Nigeria. / 6000 further jobs on track to be delivered in the next year, taking the total to over 12,000 from the first two rounds. PDF provided critical technical support to safeguard the process, instil confidence in the President’s flagship Youth Innovation and employment programme and help the Nigerian government to deliver. PDF is also committed to support round 2, a women only round which will likely lead to another 6,000 jobs created by the end of 2013. / New trade policy document created at Ministry of Trade and Investment. PDF provided trade specialists to assist in putting Nigeria’s trade policy together and providing evidence on groups such as women involved in cross-border trade. / It is difficult to predict the results PDF 2 will achieve. It is a flexible and responsive portfolio that backs ‘champions of change’ where suitable opportunities emerge. However, using a similar approach to PDF 1, and applying the ‘venture capital’ model, it will be expected to have a portfolio of outcomes where the benefits outweigh the costs of the programme. / The Impact of PDF phase 2 will be that the Nigerian Government implements policies that lead to poverty reduction. The Outcome is that Nigeria’s ‘champions of change’ are empowered with evidence and capacity to pursue economic and social reform.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The PDF model of rapidly providing high quality technical support to key Nigerian reformers has already achieved impact[1]. A theory of change as to why it has worked well (and the conditions of where it works best) is captured in the theory of change in section H of the appraisal case. One of the key elements to success is the flexibility and responsiveness of the programme. The five options developed in this section are based around this common theory of change with the variation in the options around the delivery route of the programme. / PDF programme fully managed in-house / In this option, DFID advisers would screen requests for support from potential clients of PDF using the criteria based around the theory of change. If the request was accepted, DFID project managers would procure and contract manage external expert technical assistance to provide to the client. / Advantages / Strategic decision-making process controlled in-house. DFID advisers have comparative advantage in assessing requests for support against the criteria based around the theory of change above due to analytical skillset, existing diplomatic and intelligence links. / As strategic decision-making is carried out in house, direct diplomatic links between clients (senior Ministers, Perm Secs, Delivery Agencies and key civil society institutions) and DFID/HMG are developed. / In-house strategic decision-making means that flexibility can be retained over the course of the programme with only light-touch oversight. (logframes can be adapted over the course of the project without the onerous and intensive third-party involvement that would be required to avoid conflicts of interest if strategic management of the programme was outsourced). / Contract management of TA, including monitoring and evaluation, would be carried out in-house. Flows of information from TA / Disadvantages: / Highly administratively burdensome. Additional project management resource would be required in-house to run the contracts, would require further expansion of DFID Nigeria staffing levels and procurement of many new smaller projects. / Expanding DFID Nigeria’s role in contract management for smaller interventions would not provide any synergies with UK’s diplomatic and influencing role and would not represent comparative advantage between DFID and a private sector service provider. / Not having sufficient capacity in house will mean slower, less flexible provision of support. Will likely miss many opportunities to back or influence reform. / Strategic decisions taken by DFID, procurement and contract management sub-contracted / In this option, a third party would be contracted to provide procurement and contract management services to the PDF programme. / DFID advisers would screen requests for support from potential clients of PDF using the criteria based around the theory of change. If a request was accepted, DFID advisers would work with PDF to agree terms of reference with the client, and instruct the third party to procure and contract manage external expert technical assistance to provide to the client. / Advantages: / as per a) above. / as per b) above. / as per c) above. / Administrative and procurement aspects of contract managing DFID-funded technical assistance is sub-contracted to a third party. DFID staff resource is focused on the highest-value activities only (in which DFID has some comparative and cost advantage). / This is the approach which has been taken in PDF I, and has provided strong value for money in terms of the cost of technical assistance. / Disadvantages / Monitoring and evaluation of technical assistance is undertaken primarily by third-party contractor with limited political access to Nigerian government. Will still need regular DFID review to make sure balance of support across Nigerian government remains high value. / Entire programme sub-contracted. / In this option, high-level impacts and outcomes would be defined, and delivery of these would be sub-contracted to a third party organisation. Strategic decision making over the inputs and outputs most appropriate to deliver outcomes would rest with the third party organisation, as would responsibility to procure and manage inputs. DFID retains strategic oversight of the programme. / Advantages: / This approach has proved highly successful in other DFID Nigeria programmes which have required intensive strategic management oversight to ensure results, such as DFID’s Nigerian Infrastructure Advisory Facility (NIAF). / This would free up DFID adviser time, which has significant opportunity cost. Increase the capacity of the office. / Disadvantages: / Requests from clients would be dealt with by consultants rather than DFID Advisers. As a result this option would not leverage the political knowledge of HMG and not reinforce and build diplomatic relationships. Third party contractors will as a result have some comparative disadvantage relative to DFID advisers when making strategic support decisions. / Adaptation of log frames over the course of the programme is likely given the fluidity of opportunities for reform and the historic instability of Ministerial positions in FGN. Such adaptation would be more onerous if strategic management functions were contracted to a third party organisation, as any suggested adaption organisation of logframes by the third party would have to be formally quality assured by DFID to ensure no conflict of interests. / This option will be more expensive in financial terms than both Options 1 and 2 as the commercial premiums attached to sub-contracting strategic decision making functions are higher than sub-contracting administrative functions. Making some reasonable assumptions around fee rates and accommodation[2] it could end up costing an additional £2 million over five years (or discounted costs of an additional 1.7 million[3]). / Entire programme provided by HMG civil servants. / In this option, requests for support by clients would be met by DFID staff in-office or by short-term secondments of DFID or HMG staff into Nigerian Ministries. / Advantages: / No premium would be paid for contracting private sector expertise. / Disadvantages: / This would be a slow mechanism through which to provide support. As reported in the PDF Annual Review 2012, one reason why PDF has proved relatively successful in supporting economic reform is that it can respond with speed and flexibility to emerging opportunities. If speed is not possible, the value of the programme to the client & HMG’s opportunity to influence and achieve impact is much lower. / Depending on the type of support requested, it may be difficult or impossible to provide the skill sets required by clients amongst existing DFID or HMG personnel. If they can be found, lessons from ‘what works’ with technical assistance suggests diaspora or local based experts engender more ownership from government which can increase impact. / The core operational capacity of DFID and any other donor departments would be reduced during periods of secondment. / Finance for technical support provided direct to the Nigerian Government / In this option, DFID provides finance rather than technical expertise to back ‘champions of change’ in Nigeria. / Advantages: / Most decentralised option. Reformers can prioritise how they source technical expertise based on their own needs. / Disadvantages: / Nigerian government systems and processes present high fiduciary risk for UK funds. / Capacity to identify the right technical support may be lacking within government. / Nigerian government systems may lead to long delays in bringing in technical support. / Identifying feasible options / Options II and III are feasible options. PDF has acted under option II whilst other successful technical assistance programs such as NIAF have operated under Option III. / Options IV and V are considered unfeasible. Option 1 is considered unfeasible at the scale of this programme. Previous requests from clients have frequently been for provision of highly specialised technical experts, required at short notice to deliver critical results. For example the successful passing of Sovereign Wealth Fund legislation was achieved in part by the rapid procurement of financial and legal expertise unavailable within the UK or Nigerian Governments. / Had support been limited to secondments of UK civil servants, comparable legal and financial expertise could not have been sourced. This would have reduced the likelihood of the legislation being sufficiently legally robust to safeguard several billion dollars of oil revenues for prudent and transparent future investment. / Procuring assistance through civil service secondment would be slower than procuring from private sector providers and there would be frequent miss-match between skills needed and skills available. / The ‘Do Nothing’ counterfactual / In the do-nothing counterfactual, existing support for key economic reformers within the FGN and elsewhere would be withdrawn and not replaced as PDF I commitment space is exhausted. Requests for short term support to help develop and implement evidence-based economic policy would be turned down or redirected to other DFID or donor programmes that may be able to provide resources. / Costs: / The capacities of reformers within FGN and elsewhere to drive through change in policymaking that benefit the poor would be weakened at least in the short term, and progress on economic policy making would likely slow. / DFID and HMG will lose the benefits of improved relationships with key Nigerian reformers. HMG’s capacity to influence Nigerian policymaking will be weakened. / Benefits: / Other resources may become available to key Nigerian reformers in the medium/long term e.g. private sector secondments from oil and gas companies. These may mitigate some of the costs facing FGN in the ‘do nothing’ option but could also bring new risks in terms of conflicts of interest & would only likely be placed where there was a commercial interest. / Other DFID Nigeria programmes may be able to divert resources to support policy development previously supported by PDF. However this would come with an opportunity cost as resources are diverted from productive engagement elsewhere. / Regional or international DFID-funded resources such as the International Growth Centre (IGC) could provide some economic policy development advice and expertise. Currently IGC does not have presence in Nigeria, and would likely only provide a particular type of evidence support. Unlikely to provide support on capacity/implementation issues. / Resources could be redeployed from PDF to other areas of DFID Nigeria’s portfolio
B. Assessing the strength of the evidence base for each feasible option including delivery routes / Emerging literature on ‘complexity theory’ makes the case that in order to respond to ‘complex problems’ such as the implementation of an economic reform agenda in a fragile and politically challenging context, requires crucial elements such as adaptability, flexibility and decentralised decisions[4]. The model of PDF 2 (and PDF 1), is to create a strategic facility that has all the features of being able to address ‘complex problems’ and can also capture lesson learning. / Beyond the growing literature on how best to respond to complex problems, the most relevant evidence of the effectiveness of this approach stems from operational research and evidence of PDF 1 and similar approach programmes operating in DFID Nigeria’s portfolio. / Evidence from DFID Nigeria’s Portfolio / DFID Nigeria has had success understanding the political economy of reform and providing targeted technical support complemented with HMG lobbying efforts. Examples of where this package has leveraged (influenced) poverty reducing success include: / The 2005 Debt Relief Deal, followed by creating sustainable debt management capacity through 3 phases of support to the DMO (now ending), a big institutional and VFM success. / Doubling electricity provision through supporting ‘champions of change’ with HMG lobbying and extensive technical support from the first phase of DFID Nigeria Infrastructure Advisory Facility.[5] / The Petroleum Industry Bill, improved through political work (with Ngozi Okonjo-Iweala) and technical support through Nigeria’s oil and gas sector reform programme (FOSTER) and IFIs. / Routine Immunisation policies and systems, addressing a collapse in the last 2 years, through extensive lobbying of federal and international development partners. / Reform of the fertiliser subsidy, harnessing the lessons of DFID Nigeria’s agricultural markets programme (Propcom), and providing technical assistance to Minister’s transformation plans. / Budget and financial management systems, through various work with the Finance Ministry. / Experience from these examples of what makes technical assistance likely to be more successful include: / Getting the balance right between international and local knowledge. International support and expertise can be important – it lends legitimacy, and can give access to wider knowledge (eg. on Sovereign Wealth Fund). But local problems often need solutions which are clearly local, and legitimate as local (eg. embedded advisers need to be loyal to the Nigerian government, hence diaspora or locally based experts are often used). / Work with the grain but build coalitions. Isolated, externally-driven technical interventions rarely work. Stakeholder analysis is needed for nearly every intervention to understand whether and how the interests and incentives exist to enable a policy to gain consent and how it might work best. Most policy change and implementation needs a collation of interest or support which either allows, or helps push change. / Find and support key ‘champions for change’. They are the main drivers of reforms, and the lynchpin of any coalitions needed to drive change. TA can help, but it is the champions and their coalitions who often determine the legitimacy of the intervention. / DFID has taken these principles on board under PDF 1. The political and policy challenges of working in Nigeria means many PDF investments may be unsuccessful in terms of eventual impact. PDF is like venture capital. The question is not ‘does everything have to be a success?’ The question is: ‘are there enough high value successes to justify the overall portfolio?’ The track record of results achieved by PDF demonstrates this approach is working scoring an ‘A’ in its last independent Annual Review with impressive results. The review identified that one reason for the PDF’s ability to achieve results is that it can respond with speed and flexibility to emerging opportunities. / Other Evidence outside of DFID’s Portfolio / A World Bank evaluation[6] of their policy formulation support and technical assistance to client countries across their whole portfolio over a period of 2000 to 2006 gives some evidence towards the likely impact of this type of support. The majority of their support to policy formulation and technical assistance was rated at least average. Between 65 and 80 percent of users of policy formulation support and Technical Assistance in client countries and between 74 and 87 percent of users within the Bank gave ratings of average and above when asked to what extent these products met their stated objectives.
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / Cross cutting for all options is the issue of local capacity. PDF is in part set-up as a response to absences in local capacity in order to implement policies. In itself PDF will not greatly strengthen capacity in a long-term sustainable manner. Its high focus on providing rapid technical support to enable reform minded Nigerian partners to achieve pro-poor policy reforms, often negates the longer term focus. However, the majority of embedded advisers the programme provides are Nigerians, often brought back from the diaspora in the UK and US. Some of these later go on to take up political positions in Nigerian Government and become political reformers themselves. / One potential criticism of PDF is that the support it provides introduces an element of moral hazard. Providing a relatively effective means for a Minister to ‘get the job done’ rapidly, may reduce the Minister’s incentive to rectify deep-seated problems which render much of the civil service so ineffective. An independent review of PDF in 2012[7] considered the issue of moral hazard and sustainability. It concluded that in an ideal world, such short-term support would not be necessary; but in the real world of Nigeria, the sources of dysfunction in large parts of the civil service are so profound that even determined reforming Ministers could not address them in a time-scale which would also enable key policy objectives to be achieved; this trade-off means that using programmes of support like PDF for priority objectives is warranted; but the long-term goal of strengthening the civil service should in parallel be addressed, notably through larger and longer-term term programmes. / PDF needs to be seen in the context of DFID Nigeria’s wider portfolio of programmes. It is a complementary programme to DFID Nigeria’s Federal Public Administration Reform programme (FEPAR), an existing programme that aims to build long term capacity in the Federal Government. PDF will not attempt to address long-term public service issues, but will be closely joined up with FEPAR to ensure that these issues are being addressed.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / The only marginal difference in the various options’ impact on climate change and the environment is that the different contracting structures might imply different carbon/environmental footprints. Arguably the more people involved (e.g. having a service provider) the higher the footprint, and the more that an intermediary is involved, the less DFID will be able control decisions such as whether to do face-to-face meetings versus more environmentally friendly options such as video or teleconferences, particularly if the experts available are not currently living in Nigeria. This can therefore be seen as an additional cost of Options II and III. However, as noted elsewhere, most of the experts sought for PDF in its first phase were Nigerian residents, so this may minimise this difference. / Cross-cutting for all options is the extent to which there is political appetite in country to seriously address the issue of climate change and damage to the environment as part of any of the policies supported and taken forward through PDF. Historically, the political appetite at the Federal level has been low. Inadequate responses to oil spills in the Niger Delta, unrestricted gas flaring, proliferation of privately owned diesel and petrol run generators in self-generation market, lead poisoning from artisanal mining in Northern Nigeria, are all very powerful examples of where government appetite has been low to address large environmental problems. Nevertheless, DFID Nigeria is helping Nigeria to address some of these big issues. For example, DFID Nigeria’s oil and gas sector reform programme (FOSTER) is working on a framework to map locations of oil spills and work with government agencies to improve their responsiveness. DFID Nigeria’s infrastructure programme is attempting to support the government efforts to make a market for gas feasible- which if successful would limit the extent of wasteful gas flaring. A programme under-development is looking at opportunities to use solar power on public buildings such as schools and health clinics and using this as a way to get a critical mass of investment in Nigeria making solar power more competitive with diesel and fuel generators. / We do not have much evidence about the environmental impact of past policies that PDF has supported, however we expect that they did not exasperate any climate and environment issues beyond what would have taken place in any case. Rather, the issue was whether the right opportunities were identified. For instance in the ‘You Win’ business plan competitions, DFID might have promoted the idea of encouraging “green businesses” within the competition. Although this would need to be weighed up against other policy priorities (such as the gender priority that led to a women-only round of the competition). To consider such opportunities in the future, PDF 2 will, for every policy request from the Nigerian government, look at an early stage whether there are any opportunities for “green growth” and share this with the technical advisors so that they incorporate this into their advice. Where needed and appropriate this might lead to commissioned research studies, the evidence from which could be used to influence the Nigerian Government to consider including the ‘green growth’ element within the policy. / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option(s) Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1,2,3,4 C B
E. If any, what are the likely major impacts on social development? / Much of PDF 2’s impact is likely to be on the enabling environment for growth and poverty reduction. Though much of the impact on the poor will be indirect, PDF 1 did have some elements that had direct causation on improving livelihoods of the poor. The ‘You Win’ programme, whilst providing seed-funding largely to ‘middle-class’, entrepreneurial Nigerians (due to the education bias in the application process), had an employment multiplier that meant on average 5-6 low-income people were employed for every entrepreneur given the seed funding and training. The second round of the competition will have a larger gender impact as purely targeted at women entrepreneurs. An estimated 1,200 young women will be provided with Ministry of Finance seed-funding and PDF 2 provided training to get their business ventures going. This should have a similar multiplier effect on job creation as the first round. / An early initiative that PDF 2 may undertake will be further poverty focused research which may be used to influence the Nigerian Government, the public debate up to the 2015 elections, and the commitments of the new post-2015 administration.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / Each intervention within PDF will have to be considered in terms of the likely impact on fragility and conflict and at a minimum should follow ‘do no harm’ principles. The Federal Government’s Youth Innovation and Employment competition ‘You Win’, backed by PDF 1, featured a minimum number of winners by region to make sure that the conflict affected North could adequately benefit from the competition. This has led to over 2,800 jobs being created in Northern Nigeria, with a similar number on track to be achieved in early 2014 from the second round of the competition. / PDF 1 also commissioned 3 State level studies in the 3 most conflict affected states looking at growth opportunities. This has fed into DFID influencing with the Federal Government. / PDF 2 will need to continue considering its impact on conflict and fragility, and should be strategically deployed to build evidence that is useful in influencing the Nigerian Government to do more on Northern Nigeria economic growth agenda.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / Costs / The total cost for each active option will be £18.5 million over five years. The ‘do nothing’ alternative will cost nothing. There will be variances around the feasible options for how much of the £18.5 million will be as managed funds and how much as programme administration. The main differences will be in responsiveness and flexibility as captured in section A, however, option 3 (entire programme subcontracted out), would likely cost an additional £2 million over five years. This will divert £2 million away from the ‘managed fund’ and essentially divert resources away from front-line delivery. / Options Description Operating cost over 5 years Managed Fund Strategic Opportunities Fund Other Total / Option 2 Contract-out to service provider sourcing and monitoring of Technical Assistance whilst retaining strategic decision making in-house £3.5 million £13.2 million £1 million £0.8 million £18.5 million / Option 3 Fully contract-out programme, including decisions on ‘champions of change’ to back. £5.5 million £11.2 million £ 1 million £0.8 million £18.5 million / Counterfactual Do Nothing £0 million £0 million £0 million £0 million £0 million / Discounting the operating costs of PDF over the 5 year period shows Option 2 with discounted costs of £2.6 million and Option 3 with discounted operating costs of £4.6 million. Option 2 clearly enables more resources to be dedicated to frontline delivery. / Benefits / The exact benefits from PDF II are difficult to predict. The economic benefits can be best seen through some illustrative results based around what the facility has already achieved. These should not be read as attributions to the programme, but rather as critical contributions. / Option 1: Extend PDF by £ 18.5 million over 5 years. (illustrative results based on first phase) / Key Areas Identify Results Quantify Results Monetise Results / Technical advisory support to key economic reformers in Nigerian Government Improved effectiveness of key economic reformers in Nigerian Government N/A N/A / Sovereign Wealth Fund Amount of country’s excess oil savings that are safeguarded for national development £620 million in 2012 / £1.2 billion every year going forward Potential £9 billion (discounted value) safeguarded for Nigeria’s national development over 20 years.[8] / Technical Support to Nigeria’s Trade Policy A trade policy that encourages greater trade for economic growth and job creation. N/A N/A / Federal Government’s Business Plan competition for Young Nigerians ‘You Win’ No. of businesses receiving seed funding and support. / No. of Jobs created from Business Plan competition 1,200 businesses receiving seed-funding and support. / 6,300 jobs created. (this figure will likely double on completion of second round) (No. of Jobs x discounted average income) / £78 million discounted additional income over 20 years[9] / Indeed, these successes were based on £15 million spent over 3 years. £18.5 million spent over 5 years should yield a similar, if not higher level of results, but it should be noted that uncertainty may pose some risks around the results (e.g. 2015 elections, any changes in key government appointments etc). / Whilst the future of the portfolio is difficult to predict it is safe to anticipate some of the areas where we may want to use PDF 2 based on current priorities. For instance: / Growth in the conflict-affected Northern Nigeria is a priority for DFID. We will want to deploy the PDF to back those that are pushing for growth enhancing strategies in Northern Nigeria and enable them to have the capacity to formulate and implement policies. Examples might include providing policy support to the National Security Adviser or the Chief Economic Adviser to the President. / Putting Poverty Reduction on the political landscape. Using evidence and political lobbying to highlight poverty issues. / Capacity support to reforming agencies. 15 years of partnership with Nigeria on Debt Management has led to incredible outcomes, including debt relief, development of a domestic debt market and a return to the international capital markets for Nigeria. Key to this success was political focus from the Nigerian Government and an extensive long-term programme of support. DFID needs to be able to back ‘champions of change’ with capability where these overlap with our objectives. A dedicated programme with Nigeria’s debt management office has now concluded yet we should keep the option to support them (and other agencies with ‘champions of change’) in the future through the Policy Development Facility. / ‘Do nothing’ Alternative / It’s useful to consider the ‘do nothing’ alternative i.e. what would happen without the DFID intervention and the assumed theory of change? What results could be delivered by key reformers in the absence of DFID support? This is a challenging counter-factual and most usefully considered by looking at the illustrative results and DFID’s contribution through the PDF Facility. / You Win -Without the technical support from PDF it would be difficult for the government to have put together a credible selection of candidates for the ‘You Win’ programme. Results would ultimately have suffered. PDF played a vital role in ensuring the integrity of the selection process and its successful completion. It can also play an important role in the implementation of the rest of this programme. The costs of ‘You Win’ would not necessarily decrease because the Ministry would be forced to find alternative ways and spend their own money. This would likely be much less efficient than Options 1& 2. / Sovereign Wealth Fund. The Federal Government would have struggled to find alternative funding for the financial consulting firm to provide the large scale technical assistance required. There might still have been a framework for a Sovereign Wealth Fund but either this would have taken longer to implement, or the safeguards within it may have been weaker, risking future funds. / Trade policy, it’s likely that one would have been produced and even possible that another donor such as UNIDO could have supported the process. However, it is unlikely that other donors such as UNIDO could have provided high quality technical support as quickly as DFID could through PDF. It’s possible that other support might not have been timely enough to influence the quality of the policy and bring in voices of different groups that otherwise would not have made input (e.g. women involved in cross border trade). / All these examples show instances where the overall quality of the outcome would have been significantly lower without DFID support. / Balance between the costs and benefits of each option / It’s difficult to quantify DFID’s overall contribution to the illustrative monetised results to any useful extent but with some break-even analysis we can quickly see that this type of support justifies the cost. For instance of the £78 million additional income from the jobs created from the ‘You Win’ scheme over 20 years- DFID would only need to have contributed less than 20% to these results in order to justify the full £15 million spent by the entire PDF programme. In fact this is justifiable given the critical partnership role DFID has been able to play. This is just one example. Another with the Sovereign Wealth fund potentially safeguarding almost £9 billion for Nigeria’s national development (discounted over 20 years), DFID’s contribution would only have to be 0.2% in order to justify the full £15 million spend by PDF (over phases 1 &2 and not just the Sovereign Wealth Fund). In both cases the PDF support was critical to the success. If PDF 2 has a portfolio that contains a similar level of successful projects it will more than justify its existence. Indeed even a less successful portfolio could be justified. This therefore rules out the ‘do nothing’ alternative. The ‘do nothing option’ will involve leaving key reformers in Nigerian Government without responsive support and will weaken the UK government’s hand to influence policy. This is contrary to DFID Nigeria’s strategic approach in Nigeria. / This means that the better decision is choosing between the two feasible ‘do something’ options / Options Costs Benefits Comments / Option 2 – (existing PDF model) Moderate (small admin/m&e team in place that can bring in expertise and manage programme to respond to opportunities flagged by DFID) / £3.5 million operating costs over 5 years / (present value of £2.9 million) Could achieve a similar portfolio of illustrative results identified from PDF 1. / Strengthens HMG relationship with Nigerian reformers. Leverages HMG political and strategic knowledge and relationships in order to decide which reforms to influence and back, but outsources administration, project management and procurement to a devoted resource. / Option 3 – (heavier use of technical consultants in administrating the managed fund). High / (admin + technical consultants to direct and implement the managed fund) / £5.5 million operating costs over 5 years (present value of £4.6 million) Could achieve a similar portfolio of illustrative results identified from PDF 1, but in practice may not have access to the information on the political economy that HMG has. Uses technical consultants to build relationships with government, would still need HMG guidance on who to back. Possible duplication in function. / On balance, the existing PDF model (option 2), is judged to be the preferred option where the net benefits are likely to be highest. It uses DFID advisers, service providers to their comparative advantage. Whilst the majority of support will be contracted in through a service provider, DFID Nigeria will set-aside £1 million over the five years which can be used as a strategic opportunities fund to contract expertise directly through DFID procurement systems without going through an intermediary service provider (i.e. option 1). The judgement on when to use this would be informed by comparative advantage of the various players, and only when support could not otherwise happen.
[1] PDF Annual Review 2012, Alex Duncan and Dr. Hakeem Baba-Ahmed, Policy Practice.
[2] Assumes 3 additional technical staff engaged at £500 per day. One of which would be international and would require accommodation.
[3] Discount rate at 10% standard for DFID Nigeria programmes.
[4] ODI (June 2011) ‘Taking Responsibility for Complexity’ Harry Jones – Working Paper 330.
[5] NIAF Project Completion Review, 2011
[6] Independent Evaluation Group (IEG) 2008, ‘Using Knowledge to Improve Development Effectiveness: An Evaluation of World Bank Economic and Sector Work and Technical Assistance,2000–2006’, World Bank,
[7] Nigeria PDF Annual Review 2012, Alex Duncan and Dr. Hakeem Baba-Ahmed, Policy Practice.
[8] Assumes $1 billion is set-aside for the Sovereign Wealth Fund every year for 20 years.
[9] Assumes 95% of Businesses survive first year whilst receiving seed funding and training and employ 9 people on average. At least 40% survive second year, and 20% survive after that. Those that survive are assumed to grow at 7% per year (in line with average economic growth). Average wage salary at just under £2,000 per year.

H. Theory of Change for Preferred Option

Providing responsive critical contributions to the Nigerian economic reform process

Is implementation possible?
Can this help meet our objectives?
Can we provide a critical contribution?
Can HMG influence for better outcome?
DFID screens request and assesses politics
Policy initiator requests assistance with…
if yes
technical assistant
support provided
if process successful...
policy implemented
if policy successful...
non-oil economic growth facilitated
if theory correct...
expanded opportunities for the poor

If I

If successful…

DFID/ HMG lobbying for policy change

if yes

I. What measures can be used to monitor Value for Money for the intervention? / At every annual review DFID will consider the economy, efficiency and effectiveness of the programme. The 2012 Annual Review of PDF provides a good example of how this can be done. This review looked at the economy, efficiency and effectiveness of key flagship projects individually (e.g. sovereign wealth fund support, ‘you win’ programme, and trade policy support). It also provided cross cutting assessments on how costs were controlled for key areas such as: / Average cost of embedded advisers (and benchmarked with other DFID programmes) / Average daily cost of expertise brought in for policy studies and research (benchmarks should be used). / The findings of the 2012 annual review economy measures from the managed fund are summarised below and serve as a useful benchmark for PDF 2. / Short-term (mainly studies) Monthly (embedded advisers) / Daily fee rate £ Daily fee rate N[10] Monthly fee rate £ Monthly fee rate N / Number 74 5 28 3 / Mean 497 333 4,778 2,667 / Lowest 150 320 1,477 2,600 / Highest 950 384 6,767 2,800 / Maximum payment ceilings will be set for long-term embedded advisers. The 2012 independent review found no evidence that this ceiling under PDF 1 had prevented needed expertise from coming in. / Case studies around major policies that have been introduced with support from PDF 2 will be carried out (such as in case of Sovereign Wealth Fund and You Win competition), with an attempt to monetise the benefits where possible and credible. Finally, on-going monitoring and evaluation of impact, outcomes, and outputs will be a critical part of the PDF 2 management function. Embedded advisers will report on a quarterly basis with updates on progress and contributions to any outcomes. PDF 2 will flag to DFID via a performance traffic light system any embedded advisers that are ‘off track’ from their original terms of reference. DFID can discuss with relevant beneficiaries of the technical assistance and agree a way forward that addresses any performance issue.
J. Summary Value for Money Statement for the preferred option / Option 2, which follows the model developed in PDF1 is deemed to be the best value for money option. It delivers high expected benefits (as achieved in PDF1), whilst using DFID expertise and service providers to their comparative advantage.
[10] Naira converted to £ sterling at the rate of 250.

Commercial Case

Direct procurement through a contracted supplier

A. Clearly state the procurement/commercial requirements for intervention / The overall objective is to have a facility that flexibly and responsively brings in quality technical expertise to support selected economic reforms at the lowest possible cost to DFID. Although the existing service provider for PDF, HTSPE Ltd, has provided a satisfactory service so far, given the size of the extension, contracting rules and best practice mean DFID wishes to retender this work. The two key elements of PDF will be a programme administration team and a managed fund. / The main procurement requirement is therefore to manage a competitive procurement cycle that will enable us to outreach to a wide potential market, receive good quality tenders, evaluate them appropriately, negotiate a contract that represents very good value for us while incentivising the supplier to deliver to a consistently high standard, and manage the contract relationship throughout the life of PDF II. / Ideally, we should retain the excellent Value for Money benefit that features within the existing arrangement. This is the absence of a service-provider mark-up on elements of the managed fund. The 2012 independent annual review of PDF found that this halved the cost of embedded advisers for comparable services (compared to DFID programmes that have mark-ups on managed funds). We will seek to maintain this, but may find the markets unwilling to offer this benefit. / As PDF 1 will have exhausted commitment space (but not disbursements) before the end of its contract date, we will aim to handle the transition and pass on existing (but undispersed) commitments to PDF II without disruption. / The additional reasons why the contract is to be set up this way are: / DFID Nigeria judged that there would be an acceptable level of market interest in supplying these services from a technical strong market base. / Fiduciary risks preclude funding through Nigerian Government systems. / There is no case for indirect procurement to deliver the whole programme through a multilateral organisation because seeking this would result in lower benefits than direct procurement of a service provider by DFID. / DFID will set-aside £1 million for a Strategic Opportunities fund to be managed by DFID rather than the service provider (as per option 1) to bring in technical expertise directly without going through an intermediary.
B. How do we expect the market place will respond to this opportunity? / As we embark on this competition, we accept that, although the market is not entirely unknown to us, and offers in principle proven management consultancy management and skills in a developing country context, there are two factors that may make PDF II business unattractive for service providers in the market. These are;: / The commercial objective of avoiding service-provider mark-ups within the managed funds risks reducing the profitability of the programme, compared to standard consultancy work for DFID or other clients.. / There is a strong incumbent that has performed well. This may understandably , discourage potential new entrants from investing time in costly proposal writing and bidding for this work. / These two factors will weaken competition. However, this may prove an attractive gate-way programme for a new service provider that is hoping to establish a foothold in Nigeria and position itself for future donor work in Nigeria. / DFID Nigeria will try and promote interest in this work by emphasising the important role it may have for a new service provider getting an in-country presence, as well as encouraging the existing service provider to bid. We will proactively seek interest, by conducting market intelligence gathering of potentially interested contractors. describing the problems the project aimed to address, the purpose of the outputs and what results and performance would look like. We will aim to show that we have a keen appetite to receive tenders, and were not simply going through a competitive exercise because of a legal mandate to do so.
C. How does the intervention design use competition to drive commercial advantage for DFID? / DFID Nigeria expects to source suppliers from one of its frameworks under which pre-qualified suppliers stand ready to supply services. The governance or wealth creation frameworks may be used. The adjudication of bids and proposals will be primarily on the basis of ability to deliver a specified set of services to an adequate standard at an acceptable cost. However, adjudication will not be on the basis of cost alone; additional considerations such as quality, relevant experience, past performance and proposed approaches to delivering the outputs were also considered, in order to ensure that optimal value for money is obtained. VFM reviews of supplier performance will be conducted annually by DFID Nigeria. This Business Case sets out the VFM context for the project and the tests that the suppliers will undertake consistently to ensure that they meet the commitments that they offered before their engagement. The bidders will be made aware of the result-focused nature of this intervention; therefore the emphasis will be on delivering “results” and ensuring Value for Money.) / The contract will be agreed for a period of 5 years with an option for extension. VFM reviews of supplier performance by DFID Nigeria will be conducted annually using criteria that will be elaborated by DFID Nigeria in consultation with the lead service provider. DFID Nigeria’s commercial adviser will aim to ensure close management of contractor performance, including quality in delivery of outputs, cost control, innovative solutions to problems, understanding where ownership rests, etc. / When PDF management procure services they will be expected to use the best procurement practice possible given the time available to influence reforms. How well they do at this will be vital to ensure good value for money for DFID. A lot will rest on the service provider’s ability to quickly tap into a broad network of consultants with the right skills and experience to be mobilised in Nigeria. / As part of the competitive tender for this work, service providers will be expected to demonstrate how they will ensure good value for money for DFID.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The key underlying cost drivers in this intervention will be the cost of management services. By this we mean the consultancy fee rates of the international specialist skills required for the delivery of the various aspects in the project. We will ensure that we are able to negotiate consultancy fee rates and endeavour to get VFM. Living costs are high in Nigeria, and this will be a major driver of consultancy costs, as is the perception of Nigeria as a difficult environment to operate in. Our ability to influence these factors is, and remains, quite limited. / There are a number of elements that affect the price. Unless we are able to negotiate a further arrangement whereby the contract price excludes mark ups (which is most unlikely), we will have to apply directly or our share of a number of standard charges. These are management costs spread between salaries, direct overhead costs relating to the provision of staff and brought-in consultancy (e.g. medical insurance, visas, etc.), indirect overhead costs to contribute to the costs of being in business, such as corporate operations, managed costs, recruitment, back office administration, headquarters, etc., and the profit margin. The details of this are: / Direct salary costs (including income tax), / non-salary benefits for expatriate staff for items, where required (such as school fees), / payment for annual leave taken by staff which is not invoiced to DFID (25 days per year), / pension contributions for full-time staff in Nigeria (statutory requirement), / direct overheads such as life assurance costs (a legal requirement in Nigeria for local staff), / “Workmen’s Compensation” insurance (a legal requirement in Nigeria), / other insurance costs (including medical insurance), / the costs incurred in recruiting team members, / Indirect costs / corporate overheads, such as: / administration costs associated with staff contracting and mobilisation, / risk management, safety and security costs / -recruitment, and a range of corporate functions / Profit / We aim to negotiate a contract in which the profit element is in single figures. / Broadly, there are two aspects of this programme that will drive costs and influence the price. The smaller and more predictable costs from the management structure (i.e. the daily rates of those managing the facilities), and the less predictable costs of the support they contract in to influence economic policy reform. / The key value-added from the first aspect will be the extent that expertise brought in from the managed fund is good value for money, and the competency in managing these technical inputs through-out the life-time of the contract. We can measure how well this is done as part of the normal annual review cycle being conscious that appropriate benchmarking in unit costs is used. / The value-added from the technical expertise brought in as part of the managed fund is based on the influence they have on policy processes and implementation. We will measure this as part of annual reviews, and on-going interactions with relevant DFID advisers.
E. How will the contract be structured and how will contract & supplier performance be managed through the life of the intervention? / The contract will be structured with two key elements. / Programme management; / Managed-funds / The management contract and supplier performance will be closely managed through the life of the intervention. DFID Nigeria will complete an annual review of contractor performance using the performance indicators agreed at the outset of the programme. Quarterly financial and physical progress will be monitored against work plans and financial forecasts. / Payments will be authorised against satisfactory performance against the work plan; and specific objectives. Tenderers will be evaluated on their proposed payment processes, and negotiations will be held with the chosen supplier to maximise the amount of the contract price that is pegged to acceptable delivery. Objectives will be defined at each annual review. / The supplier will be strongly encouraged to maximise value for money throughout the life of the project, actively benchmarking and testing how to reduce the cost per beneficiary or widen the number of beneficiaries for the contract value. / Non-fee expenditures will be realistically set, notably hotel and subsistence costs, and reviewed regularly. The contract will reflect the levels of insecurity, and enable the supplier to enhance security if it considers this necessary. / The contract terms enable DFID at its discretion to reduce funding if we feel that the programme is not delivering the anticipated results, whether this is due to poor performance or to factors external to the programme. The log frame will be used to measure the performance of the suppliers through external annual reviews. / The contract will contain specific clauses designed to prevent and detect corruption. The details are set out in the Financial Case below.

Financial Case

A. Who are the recipients of all proposed payments? / The main recipients of proposed payment will be to the Service Provider who is yet to be identified; the organisation would be responsible for implementing the programme and providing the technical expertise to the identified ‘champions of change’. However other potential recipient would be Independent Audit Firms engaged by DFID Nigeria, Independent Review teams for annual assessment of progress against logical framework and minimal procurement activities to Crown Agent Nigeria Limited (CANL) – DFID Nigeria’s Procurement Agent under the core country agreement. There is also £1 million Strategic Opportunities Fund that would be used in circumstances when it made sense for DFID to procure through its own systems rather than via a service provider.
B. What are the costs to be incurred directly by DFID? / DFID directly funds the cost of Annual Reviews, Procurement of goods & equipment and Audits. Although DFID directly funds these project activities, the funding is within the overall project budget. / Managed Fund / The largest cost component of the programme is the managed fund. This would be paid in arrears to the service provider based on monthly invoices, and they would use this to draw on appropriate technical support for the given area. It would fund a mixture of technical support including (but not limited to) embedded advisers, short term technical assistance and research studies. / Embedded Advisers / Under PDF 1, the total cost of embedded advisers averaged around £820,000 per year which funded 36 embedded advisers across government. PDF2 would maintain those that are currently performing well and still strategically relevant, and scale up in new areas where there are ‘champions of change’. PDF 2 would allocate around £5 million to fund embedded advisers over the five years. / Research and Evidence / Under PDF 1, just under £1.8 million was spent on a total of 27 evidence studies over the life-span of the programme. As PDF 2 is a five year programme keeping the same pace of studies would mean around £3.5 million could be spent on studies over the five year period. / Technical support / The ability to provide technical support to help innovative Nigerian Government projects such as ‘You Win’ or fledgling institutions such as the Sovereign Wealth Funds take-off is crucial. Under PDF 1, £3.6 million will have been spent supporting 3 rounds of the You Win competition. £1 million was spent bringing in specialist financial expertise to advise on the establishment of the Sovereign Wealth Fund. PDF 2 would have £4.5 million available to provide technical support to these types of initiatives where there is strong alignment of objectives with DFID Nigeria’s Operational Plan.
C. What are the costs to be incurred by third party organisations? / Nil
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / N/A
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / This fund will be sourced from the DFID Nigeria Programme resource allocation.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / The profile of estimated costs is: / Component 2013/14 / (million) 2014/15 / (million) 2015/16 / (millions) 2016/17 / (million) 2017/18 / (million) 2018/19 / (million) Total / (million) / PDF II – Procurement of Services (running costs of programme) £0.116 £0.700 £0.700 £0.700 £0.700 £0.584 £3.500 / Managed Fund £0.500 £2.600 £3.084 £3.000 £2.200 £1.816 £13.200 / Procurement of goods & equipment £0.100 £0.100 £0.100 £0.150 £0.000 £0.000 £0.450 / M&E £0.000 £0.050 £0.050 £0.050 £0.100 £0.100 £0.350 / Strategic Opportunities Fund £0.000 £0.500 £0.200 £0.100 £0.100 £0.100 £1.000 / TOTAL £0.716 £3.950 £4.134 £4.000 £3.100 £2.600 £18.500 / The above allocations are indicative only, and should be considered as flexible within the overall budget framework. The line for project M&E is the budget allocated for independent Annual Review and the cost of independent audit reviews / The procurement line is the budget allocated for purchase of goods and equipment’s for the service providers such as vehicles and office setup. / We will ensure accurate forecasting through a detailed discussion with identified supplier on work plans & budget and monthly monitoring of project activities and expenditure. An illustrative forecast based on past financial performance of PDF is provided below for FY 2013/14. It is assumed that the service provider is engaged and starts work by the end of January 2014. / FY 2013/14 / Component Feb / (million) Mar / (million) Total / (million) / Procured Services 0.058 0.058 0.120 / Managed fund 0.200 0.300 0.500 / Goods and Equipment 0.050 0.050 0.100 / M&E 0.000 0.000 0.000 / Strategic Opportunities Fund 0.000 0.000 0.000 / TOTAL 0.308 0.408 0.716 / An indicative quarterly forecast of the programme over the life-span of the programme is provided in annex 2. The component codes that the programme would contribute to are: / 15110 - Economic and Development Policy/Planning / 80010 - Economic Research
G. What is the assessment of financial risk and fraud? / The assessment of financial risk and fraud is low for DFID’s funds. The service provider to be identified, would go through DFID’s procurement procedure to reduce any case of fraud. We expect that the supplier identified from the procurement process would have proven to have in place robust accounting and management systems to minimise fraud. DFID Nigeria will approve all sub-projects identified to be funded, which will be consistent with the work plans and proposed budget approved by the Programme Officer and Lead Adviser. The programme is subjected to a periodic independent audit during the life time of the programme, to ensure that funds are used for the purpose intended. These checks reduce the risk of fraud.
H. How will expenditure be monitored, reported and accounted for? / The service provider is expected to invoice DFID on a monthly basis, in arrears, covering all the expenses related to the project activities delivered during the month. The invoice will be subjected to scrutiny for accuracy by the Project Officer and Deputy programme manager. The Project lead adviser will also need to confirm his satisfaction of the deliverables before an invoice is approved for payment. / On an annual basis, PDF II will be required to provide all financial information for the Value for Money (VfM) framework. The independent assessment will review the VfM claim of PDF II as part of their assignment and recommend any necessary adjustments in the succeeding year. / In addition, the project will submit an annual audited account and the report will be shared with DFID. Independent auditors will be contracted by DFID when required to audit PDF II. The cost of auditing and reviewing audited accounts has been incorporated within the overall project monitoring and evaluation expenditure. / Programme performance will be monitored through annual reviews and by financial audits to determine the accounting standards and practices put in place are adequate. Appropriate recommendations for changes will be made after such reviews and audits.
I. Are there any accounting considerations arising from the project? / None identified.

Management Case

A. What are the Management Arrangements for implementing the intervention? / A PDF Administrator (service provider) will assist DFID (represented by the economic adviser and programme officer) with the management of PDF with specific responsibility for the procurement of inputs, contract administration, monitoring and reporting of physical and financial progress and providing quality assurance of the technical work proposed and/or completed. In addition the service provider is responsible for ensuring that the mechanisms for monitoring and evaluating the project at output, purpose and goal levels are in place and are adequate for measuring the indicators included in the logical framework. / Beneficiaries, mainly Federal Government of Nigeria Ministries, Departments and Agencies, are responsible for approving TOR for the technical work proposed, day-to-day technical supervision of contractors, and approval of contractors’ technical reports.
B. What are the risks and how these will be managed? / The project is medium risk; the risk of corruption to DFID’s own funds is low given that none of PDF funds will go through Nigerian government systems, although there is a reputational risk for DFID if corruption is identified in any linked activities by the Nigerian Government. / The main risks for delivering results relate to the nature and extent of the political commitment, and subsequent leadership, to take forward policy reform. / Following the elections in 2011, the new government has a stated commitment to the President’s Transformation Agenda which is in turn linked to the federal government’s Vision 2020. Interventions have been initiated by DFID through discussions with key reformers in the President’s cabinet, including but not limited to the head of the National Economic Management Team/Minister of Finance, Minister of Power, Minister of Trade and Investment and Minister of Agriculture. The residual risk is the opposition to policy reforms both from within and outside the agencies concerned. The generation and communication of evidence to support policy reform, should serve to reduce such opposition.
C. What conditions apply (for financial aid only)? / Not applicable.
D. How will progress and results be monitored, measured and evaluated? / There will be an independent project completion report of PDF 1 which will evaluate the progress towards outcomes and impact of the programme. This will also form a basis for monitoring the progress of PDF 2. This will be commissioned before the start of PDF 2. / The performance of short term interventions is normally monitored through an inception report, draft and final technical reports. Organisational support may include an inception report, but is normally monitored through regular (monthly or quarterly) reports and a final administrative report, plus any relevant technical reports. Whereas all technical documents are reviewed by the relevant DFID adviser, quarterly reports may be summarised by the programme on a six-monthly basis sent with the full report for DFID review. Final administrative reports will likewise be summarised for DFID review. / Output 1: Relevant and high quality PDF policy research and consultation products delivered to beneficiaries. Indicator 1: Proportion of projects assessed as executed satisfactorily or better during implementation. Source: Ratings for project execution as assigned by beneficiaries in Project Monitoring and Completion Reports. A sample of these ratings will be validated by the service provider as part of the annual review. Indicator 2: Beneficiary, user and DFID perceptions of relevance, quality and use of PDF-supported policy studies and events. Source: Study undertaken by service provider as part of annual review. Study to include web survey and follow-up focus group discussions with a sample of survey correspondents. / Output 2: Relevant and high quality PDF organisational support delivered to beneficiaries. Indicators and Source as for Output 1. / The Outcome is that Nigeria’s ‘champions of change’ make increased use of evidence and capacity to pursue economic and social reform. Indicator 1: Number of instances where beneficiary can demonstrate that PDF-supported policy studies, policy consultation events and organisational support have directly influenced changes in policy formulation or implementation. Source: Annual tracer study to follow up a sample of instances where beneficiary and/or DFID Nigeria and PDF consultants claim PDF influence over policy formulation or implementation. Evidence will be sought to demonstrate when and how influence has occurred; findings will be analysed and discussed with relevant stakeholders. / Indicator 2: Citation of PDF-supported data and analysis in policy dialogue, budget submissions, performance reports within targeted MDAs, National Assembly and targeted Civil Society Organisations CSOs/networks. / Source: Annual tracer study to follow up a sample of instances where beneficiary and/or DFID Nigeria and PDF consultants cite PDF-supported data and analysis in policy dialogue, budget submissions, performance reports. Evidence will be sought to demonstrate when and how influence has occurred; findings will be analysed and discussed with relevant stakeholders. / Impact: the Nigerian Government implements policies that lead to poverty reduction (Aggregate impact of wider DFID Nigeria programme portfolio). / Indicator 1: Proportion and amount of Federal Government of Nigeria (FGN) budget allocations in selected sectors classified as poor. Source: FGN annual budget allocations / Indicator 2: Proportion and amount of FGN budget performance (expenditure) in selected sectors classified as pro-poor. Source: FGN Budget execution reports.
Lograme / Quest No of logframe for this intervention: 4030907