Business Case

Summary Sheet

Title: Ethiopia Productive Safety Net Programme Phase 4 (PSNP 4)
Project Purpose: / Support poverty reduction and food security in Ethiopia through the development of national social protection and disaster risk management systems.
Programme Value: / UK support of £276m over the 2015-20 phase (comprised of £176.2m from the UK International Climate Fund (ICF) and £99.7m from the country programme budget). / This would be combined with increasing domestic finance from the Government (c. £312m) and funding from another ten donors (totalling c. £1,558m).			Country: Ethiopia
Project Code: 204290	Start Date: 1st September 2015		End Date: 31st December 2020
Overall programme risk rating:	medium
Quest Number:

Contents

Intervention Summary

Under the proposed intervention, DFID will provide £276m over five years to support the development of national systems for social protection and disaster risk management in Ethiopia. £266m will be provided towards the £2.35 bn costs of the next phase of the Productive Safety Net Programme (PSNP 4). This will deliver (i) targeted assistance to the poorest rural Ethiopians, resulting in gains in food security, livelihood diversification and poverty reduction, and reductions in the need for costly humanitarian food aid; and (ii) investments in core administrative sub-systems (e.g. targeting, case management, crisis preparedness and early warning) required for the evolution of effective, integrated national social protection and climate resilience. Remaining funds will be used for technical assistance (£5m allocated to the PSNP Donor Coordination Team to manage analytical work and provide effective coordination to the 11 donors who support the PSNP; £2.5m for a Capacity Development Facility; and £2.2 m for DFID-managed research and technical assistance). A break point after three years will allow DFID to evaluate progress and the case for continued support. Overall we judge the risk to be medium, with the greatest residual risk (after mitigation) being with regard to implementation capacity constraints. Given the nature of this risk, and the expected high reward from this programme, this is within DFID Ethiopia’s risk appetite.

What is the problem to be addressed?

Despite rapid gains, Ethiopia remains one of the poorest countries in the world. In 2011, 34% lived below the food poverty line and 44% of children were stunted. Poverty makes people vulnerable to shocks. For the majority who rely on rain-fed agriculture, poor rains threaten their ability to feed themselves. Without savings, assets or insurance, a shock forces the poor to adopt short-term survival strategies (e.g. selling animals) which undermine their long-term opportunities. Vulnerability perpetuates poverty even if a shock does not happen. With no buffer to protect them from destitution if a crisis occurs, the poor adopt risk-minimising strategies (keeping children home to work in order to maximise income; planting resilient staple crops rather than risky but profitable cash crops; keeping savings in cash rather than high-return assets). These make it harder for them to take up opportunities and so work their way out of poverty in the long term.

These household-level processes have significant long-term effects on individuals and households, and aggregate consequences for economic and social development. Effects are particularly pronounced for young children, for whom inadequate food intake results in irreversible effects on physical and mental development, with costs for future labour productivity and economic growth (estimated at £1.85bn or 16.5% of GDP each year). Structural food insecurity, environmental degradation and a highly variable climate (made more unpredictable by climate change) also makes Ethiopia vulnerable to humanitarian crises such as the 1984-5 famine, in which up to a million died.

The Government has formulated innovative and successful policies to reduce hunger and avoid famine. In 2003, Government and donors concluded that a decade of annual humanitarian appeals had not reduced high levels of chronic hunger; and worked together to design a better approach. In 2005 the Productive Safety Net Programme was introduced to respond to a predictable caseload of food insecurity with predictable targeted transfers. This has lifted 1.4m people out of poverty; and enabled Ethiopia to avoid famine during the severe 2010/11 drought.

What will the DFID programme do?

The Government and the donors have reviewed lessons learned to date and reflected these in PSNP re-design. The PSNP will continue to address poverty, hunger and climate vulnerability both immediately and directly (through transfers that help the poorest households to meet consumption needs during the lean season, and which can be expanded in coverage to respond to drought); and over the long term (through livelihoods support which expands economic opportunities for the poor and public works projects which address the root causes of food insecurity).

The Government started to put in place a framework of national policies into which the PSNP can fit, and to which it will contribute. Policies for Disaster Risk Management, approved in 2013, and Social Protection, in late 2014, both assign the PSNP a central place in ex ante prevention and mitigation and ex post response to shocks. PSNP is also a key element in the Climate-Resilient Green Economy strategy, which aims to take Ethiopia to middle-income country status with no increase in per capita CO2 emissions; and the National Nutrition Plan.

DFID will support this evolution, building outwards from PSNP programme systems and downwards from the national policy frameworks. The support will help to build effective, integrated national systems for social protection and disaster risk management, using and improving PSNP systems for targeting, enrolment, transfer payments, planning, and monitoring, support to create the underpinning of administrative subsystems which can be used for all poverty-targeted services. Investment in district-level disaster risk profiles and contingency plans and improvements in the early warning system will serve the broader set of programmes that comprise the Government’s disaster risk management strategy.

The next phase of the PSNP builds on successes to date, while addressing areas of shortfall and expanding in scale. The programme will expand from 319 to 411 districts to provide 10 m people each year (roughly 10% of the population or one third of those under the poverty line) with cash and / or food transfers in return for labour on community-selected public work projects. From year 3 onwards, the composition of this 10m caseload will stabilise with 8.3m chronically food insecure people, who will receive regular, multi-year transfers; and an annual selection of 1.7m who are in short term (seasonal) food insecurity. Humanitarian food aid will be reduced, coming in to top-up PSNP coverage as needed. The shift from food to cash transfers will be accelerated and pilots of electronic cash transfers expanded. Transfer values will increase to achieve greater impact and cost-effectiveness; the very poorest (those with disabilities, the elderly living alone) will receive transfers for 12 rather than just six months a year; and for the remainder, it will be possible to substitute attendance at training in good nutrition practices for part of their public works labour requirement. Other measures will also link PSNP beneficiaries to child health and nutrition services (and bring households with acutely malnourished children into the programme).

Domestic GoE financing for the PSNP will increase dramatically to £323.5 m ($498 m) for the next five years[1]. However, this will be a long-term effort: with per capita GNI a third of the sub-Saharan African average, and limited scope for reallocation from other sectors (Ethiopia already has one of the highest rates of pro-poor spending), it does not yet have the fiscal space to cover the whole PSNP budget, and will require continued donor support to the next phase of the programme. The ramping up of domestic financing (from 8% in the first year to 22% in the fifth year) will help establish a trajectory for increases in absolute spending and share beyond 2020.
[1] Key source documents for this Business Case (e.g. the PSNP 4 Design Document and World Bank PAD, and the Social Protection Public Expenditure Review) present historical and planned expenditures in either Ethiopian birr or US dollars. When converting these values to sterling, this Business Case will use the appropriate annual average exchange rate for past expenditures; and currently prevailing exchange rates for planned future expenditures. These current rates (taken from www.oanda.com) are £1 = 33 birr; and £1 = $1.53984.

What results do we expect?

There are two broad sets of expected results. The proposed intervention will generate both final-level developmental outcomes (impact on poverty, nutrition, and inclusive economic growth); and the evolution of national institutional capacity and effective systems for social protection and disaster risk management. Final outcome results will include:

- 3 million people reporting new economic activities and sources of income
- Increased dietary diversity and reduction in child malnutrition
- Improved rural infrastructure (roads, schoolrooms, health posts, small-scale irrigation schemes) resulting in community-wide improvements in productivity and incomes
- Sequestration of between 2.4 and 4.1 million tonnes of CO2
- A 70% increase in living standards for PSNP beneficiaries
- 4.3 million people lifted out of poverty

How does this fit with DFID’s wider priorities?

The proposed intervention will support the realisation of core DFID priorities and commitments. Over the last five years, results attributable to DFID’s support to PSNP 3 have contributed a significant share to DFID-wide public commitments to food security and cash transfer coverage, and have helped Ethiopia to meet national and MDG targets. The results that are expected from PSNP 4 – in terms of poverty reduction, food security, climate change mitigation and adaptation and improved outcomes for women and girls – remain central to DFID’s international and domestic commitments.
Strategic Case

Context: what is the problem to be addressed?

Despite rapid economic growth and gains in human development over the last decade, Ethiopia remains one of the poorest countries in the world. Extreme poverty is manifested first and foremost as high levels of hunger and malnutrition, with 34% of Ethiopians living below the food poverty line in 2011. Factors explaining food insecurity include complex topography and unpredictable rainfall (now complicated by climate change); high population density and pressure on land and environmental resources; limited access to agricultural inputs; weak market integration; and few off-farm opportunities. 80% of the population rely on rain-fed agriculture characterised by small holdings and low productivity. For many, poor rains or adverse price movements threaten their ability to grow enough to feed themselves or earn income to buy food (Dorosh and Rashid 2012; Rahmato et al 2013)[2].
[2] The recent World Bank Poverty Assessment finds that while the poverty rate fell by a quarter between 2005 and 2010/11 (from just under 40% to just under 30%), the welfare of the bottom 15% fell in real terms, mainly due to a rapid increase in food prices towards the end of the period (World Bank 2015).

Food insecurity in Ethiopia has both chronic and transitory components. Large numbers live with chronic hunger: in successive years they are unable to secure enough food for a significant part of the year, eating smaller and fewer meals in the months preceding the harvest. Others are food secure in ‘normal’ years, but vulnerable to shocks (either a widespread production shock such as crop failure or livestock death following failed rains; or a household-specific shock, such as the outlay of money to deal with a medical emergency) which may force them to sell productive assets (e.g. livestock) to obtain money with which to buy the food they need. These crisis coping strategies increase the risk of falling into a poverty trap and long-term, chronic food insecurity (Carter et al 2008).

Food insecurity has long-term effects on individuals and households, and aggregate consequences for national economic and social development. Inadequate food intake during early childhood results in irreversible effects on physical and mental development, with implications for future labour productivity and economic growth. Estimates suggest that those who were three or younger during the 1984 famine (and survived) have experienced income losses of 3-8% per year over their lifetime (Dercon and Porter 2010)[3]. While child malnutrition has fallen since 2000, the incidence of stunting (due to chronic food insecurity) remains extremely high at 44% (2011). Economic studies estimate the annual costs of under-nutrition at £1.85bn, or 16.5% of GDP (UNICEF 2013).
[3] Twenty years later, children who were below three years or in utero during the 1984 famine were on average 3cm shorter than their siblings; less likely to have completed primary school; and more likely to have experienced recent illness.

Structural food insecurity also makes Ethiopia vulnerable to periodic humanitarian crises. Endemic chronic food insecurity plus a certain level of transitory food insecurity (households ‘churning’ in and out of due to shocks) is normal in Ethiopia. However, a shock that affects millions of households simultaneously – e.g. a widespread failure of rains – has the potential to trigger a famine. Famines have been a recurrent feature of Ethiopian history, most recently in 1973-4 (which killed an estimated 250,000) and 1984-5 (when up to a million died).

By 2003 both the Government and donors were dissatisfied with reliance on humanitarian relief as a long-term strategy. Ten years of expensive annual ‘emergency’ food aid appeals had not addressed the underlying causes of food shortage or built resilience to shocks: it often arrived too late to protect households from the need to undertake crisis measures (notably, selling livestock), making it harder for them to work their way out of poverty. Seeking a better approach, the Government launched the Food Security Programme, with the PSNP at its core.

Designed with support from DFID and other donors, the PSNP responds to a predictable caseload of food shortage with predictable, timely transfers to help targeted households to get through the hungry season. Since 2010, the third phase of PSNP (PSNP 3) has addressed poverty, hunger and climate vulnerability both:

immediately and directly, through (i) regular transfers (cash and/or food) that help extremely poor households to meet consumption needs during the lean season without the need to resort to harmful crisis coping mechanisms; and (ii) the ability to expand coverage in response to a large-scale drought, using pre-positioned contingency funds (the Risk Financing Mechanism or RFM);
and
over the long-term, through (iii) public works projects (which are selected by the community and address root causes of food insecurity by reducing soil erosion, linking communities to markets through roads, and building or rehabilitating schools and clinics); and (iv) support to help households improve and diversify their incomes through advice and credit provided through the Household Asset Building Programme (HABP).
The policy context for PSNP has changed in recent years as the Ethiopian Government has formulated new policies to reduce hunger and avoid famine. In addition to the revised (2013) Disaster Risk Management strategy, in 2014 a national Social Protection Policy was approved by the Council of Ministers (MoLSA, 2014). With a Social Protection Strategy in draft to provide operational detail, this paves the way for a more coherent policy system and approach to budgeting. A new Public Expenditure Review describes spending on social protection as dominated by social assistance (safety net or transfer programmes) and general subsidies (Figure 1). Other sub-sectors (social insurance and labour market interventions) remain relatively small in both coverage and expenditure. While safety net spending has averaged 55% of annual social protection spend over the last five years, and subsidies 32%, the latter have been expanding over time, while safety net spend has come down. Support to PSNP 4 and related policy dialogue offer an opportunity to reverse this trend, redirecting spending from distorting and regressive subsidies to effective and pro-poor safety nets.
Figure 1: Patterns of social protection expenditure ($m), 2009-2013

Source: World Bank (2015, forthcoming) pp. 13-14

What will DFID support do?

### Support the next five years of Productive Safety Net Programme (PSNP) delivery and systems-building

Despite significant gains under PSNP to date, food insecurity remains widespread and severe in Ethiopia. The Ministry of Agriculture (MoA) has asked donors to continue support to the new (2015-20) phase of the programme (PSNP 4). Over the last year, donors have worked with the Government to re-design the programme. DFID engaged actively and has given notional commitment, subject to Ministerial approval, to maintain support to the new phase.

PSNP 4 will remain at its core a large-scale public works programme, paying extremely poor households transfers (of cash or food) in return for labour on local development projects. Community-based targeting identifies those households which are chronically food insecure: most (92%) will receive transfers for six months of the year to get them through the pre-harvest hungry season (a ‘predictable response to a predictable need’) as wages for public works labour. Public works projects are selected by the community, with technical input from local government staff. Many of these projects are soil and water conservation measures which reverse long-term environmental decline and restore agricultural productivity; others build infrastructure for economic development (rural roads and small-scale irrigation) and basic service delivery (school rooms and health posts). The remaining 8% of the caseload who cannot work (the elderly, chronically ill and disabled) will now receive transfers for all 12 months of the year.

The design of the new phase retains core features of the current phase, while introducing some significant changes. (See Box 1.) Design innovations reflect (i) a response to lessons learned from implementation; (ii) policy and programme initiatives at national level that change the strategic context for transfer programming; and (iii) experience from successful safety net programmes in other countries. Based on these lessons, the new phase aims to both broaden and deepen the impact of the programme.

PSNP 4 will broaden coverage (from 319 to 411 woreda) and caseload (from 5 million to 10 million, or roughly a third of the population below the poverty line). Processes for beneficiary identification and entry to the programme (targeting) will build on the good performance seen to date in PSNP 3; while the management of programme exit (graduation) will be significantly improved (see Annex 1). Most beneficiaries (73% in the first year, rising to 84% from the third year) will be in chronically food insecure households, and receive multi-annual assistance; the balance (27% declining to 16%) will be people falling into short-term hunger and brought onto the programme for a year at a time in response to annual humanitarian needs assessments.

Box 1: Summary of key design changes from PSNP 3 to PSNP 4

Strategic: policy, political economy and scale
- Evolution from a stand-alone, time-bound food security programme to an effective and efficient permanent social safety net to address extreme poverty, build climate resilience and promote inclusive economic growth
- Embedding the programme within a number of new Government policies and strategies (social protection, disaster risk management, climate resilient economic growth, nutrition) recognises its contribution (much already achieved, some in potential) to a much broader range of economic and social outcomes than ‘just’ food security
- Building links to other Ministries should broaden support and help realise potential to contribute to other policy goals
- Significant increase in domestic financing, with a trajectory which should lead to the programme moving fully on-budget
- Expansion of geographic coverage and caseload to address previous exclusion errors based on resource constraints
Programme entry and exit
- A proxy means test (poverty / food security index) to be developed and rolled out to complement existing targeting
- Lowlands to be encouraged and supported to pilot and monitor adaptations to the targeting process
- Stable 10m annual caseload reduces potential for graduation ambitions to translate into counter-productive quotas
- Graduation prediction system helps set local planning figures which are realistic and reflect spatial variations in graduation potential (high in some places and years, lower in others)
Transfer size
- Higher monthly per person transfer value will generate greater impact in reducing hunger and malnutrition and supporting sustainable exit from poverty with fewer households just ‘treading water’
- Permanent direct support clients will now receive 12 months not just 6 months of transfers each year
New focus on nutrition
- Households with a child under treatment for acute malnutrition to receive PSNP transfers (to ensure that therapeutic rations assigned to the child are not divided among other members of the family)
- PSNP households with a child treated for acute malnutrition can move one adult from public works to temporary direct support, to enable sustained parental care for the child
- Direct support beneficiaries to attend training in nutrition and childcare practices and attend clinic-based check-ups
- Public works beneficiaries have the option to attend 3 training sessions in place of one day of public works labour
Public works
- Incorporation of findings from the Climate Smart Initiative pilots to further strengthen the contribution to climate change adaptation and mitigation, and avoid any risks of maladaptation
- A geo-coded database of watersheds and completed public works to better track implementation and aggregate impact
- Identification of public works types and worksite management practices better adapted to lowlands needs
- Improvements to the technical guidelines for roads and water projects
Livelihoods support: compared to HABP, both greater realism and greater ambition
- Clarity that PSNP will help to link beneficiaries to livelihood support services provided through other Government agencies and programmes, but cannot deliver these services itself;
- PSNP will support development of non-agricultural microenterprises and jobsearch as well as agricultural extension
- Recognition that extreme poverty and vulnerability makes the poor rationally credit averse; credit to be supplemented by support to savings and (for female headed households) a lump-sum transfer for investment in productive assets
Strengthened provisions for women and girls
- Standardisation around more generous allowance for pregnancy and early childcare (women to be transferred from public works to direct support from fourth month of pregnancy through to one year after birth)
- Use of public works to construct daycare centres
- Minimum standards for female participation in programme committees
Disaster risk management and integration with annual humanitarian response
- Regional contingency removed; trigger / no trigger Risk Financing Mechanism replaced by pre-programmed annual Federal Contingency, which should guarantee timely response and smoother joint planning with humanitarian actors
- Increased PSNP transfer value much closer to parity with humanitarian food transfers
- PSNP supports production of woreda risk profiles and response plans
Programme management
- Transition from a paper-based management information system to a fully computerised, modular MIS to improve oversight and accountability and speak to information systems in other Ministries (in health, transport, water etc.)
- Environmental and social safeguards to track and respond to strategic issues (possible association with other GoE programmes) as well as public works sub-project issues.

Deepening the impact of the programme will be achieved through design improvements and institutional and systems development. The value of PSNP transfers will increase (to £4.4 per person per month, or enough for 15 kg of cereals and 4 kg of pulses) to improve the impact on poverty. Households identified as ready for graduation will receive a lump-sum payment to enable them to buy productive, income-generating assets. Livelihood support services will be strengthened, providing beneficiaries with training, advice and access to credit to improve agricultural production and income, develop off-farm household enterprises, and / or find waged employment.

PSNP4 will evolve from a stand-alone programme to a core element within integrated Government strategies for social protection and disaster risk management (DRM). The Government has begun to put in place an overall framework of national policies, strategies and investment plans into which the PSNP can fit, and to which it can contribute. Policies for DRM, approved in 2013, and Social Protection (SP), approved in late 2014, both assign the PSNP a central place in disaster prevention, mitigation and response. PSNP is also an important element within the Climate-Resilient Green Economy (CRGE) strategy, which aims to achieve economic growth that will take Ethiopia to middle-income country status with no net increase in per capita emissions; and the National Nutrition Plan (NNP). PSNP 4 will build a platform of administrative tools and capacities on which other social protection and poverty-targeted programmes can build. Shared data systems and greater coherence between different programmes are expected to result in cost savings and greater effectiveness.

In addition to the majority (£266m) that will be spent as PSNP 4 implementation, a small sum (£9.6m or 3.2% of the total) will be allocated for support to analytical and advisory activities supporting design and implementation of social protection systems. Some of this would be allocated to the Bank-executed partnership trust fund that supports the PSNP Donor Coordination Team (DCT), which serves as a public good for all the donors to the programme. The remainder would be managed directly by DFID Ethiopia, providing the option of financing research which relates to social protection elements external to the PSNP and the DCT; and / or that is related to PSNP, but of interest primarily to DFID[4].
[4] We would try to minimise using DFID-managed funds for PSNP-related analysis. PSNP has built up a strong record for donor coordination and harmonisation, and one of the principles of good donor behaviour within the PSNP donor working group (DWG) is that wherever possible analytical work relating to the programme should be agreed on and commissioned and managed collectively.

What are the expected results?
The results, indicators and targets proposed here are taken primarily from the logframe for the 2015-2020 phase of the PSNP. While this logframe is a consensus product, DFID has been actively engaged in shaping it (particularly with regard to goal, outcomes and outputs 1 and 4). In addition to the results identified in the programme logframe, the Business Case attempts to quantify some additional expected results with estimates for key impact indicators (including poverty reduction and carbon sequestration).
The impact and outcomes of the proposed DFID support fall under two themes. The first set relate to final, household- and individual-level outcomes in terms of poverty reduction, food security and human development. The second set relate to improvements in institutional capacity and the long-term evolution of national systems for social protection and disaster risk management.
The impact of the programme is as follows:
- PSNP contributes to the evolution of Government strategies and programmes in social protection, disaster risk management, climate-resilient green growth, and nutrition.
- Livelihoods and resilience to shocks are enhanced, and food security and nutrition improved, for rural households vulnerable to food insecurity.
The outcome of the programme is:
Enhanced participation in improved rural safety net, livelihood and nutrition services by food insecure male- and female-headed households.
The following table summarises some of the key expected results at the outcome / impact level:

Table 1: Selected key results

Household-level results
Reduction in hunger	Reduction in the average food gap (by 20% for newly-enrolled clients, by 33% for existing clients)
Improvement in living standards	70% increase in p.c. consumption expenditure (from 212 birr pc / month in 2012 to 360 birr pc / month in 2020)
Reduction in the national poverty headcount	4.3 m lifted out of poverty in 2020
Livelihood diversification	30% of transfer households report one or more new income sources by 2020
Local / community level results
Environmental rehabilitation / climate change adaptation	500,000 hectares of degraded land enclosed for regeneration by 2020
Improved rural incomes and livelihood diversification	Expanded economic opportunities through PSNP public works (small-scale irrigation, feeder roads, land reclamation) and livelihood services
Economic growth in PSNP woredas	Local economic multipliers generate £1.725 bn in additional rural incomes
National-level results
Evolution of a national social protection system	System integration enabled with development of critical common administrative systems (targeting; management information system; etc.)
Strengthened national system for disaster risk management	Need for annual humanitarian food aid reduced as regular PSNP caseload increases to 8.3 million; with additional 1.7m p.a. provided with short-term assistance through the Federal Contingency budget. / PSNP supports development of woreda disaster management plans.
Global level results
Climate change mitigation	1.381m tonnes CO2e sequestered by 2021; 3.246 m MT CO2e by 2025

Gender consideration in the proposed intervention

The next phase incorporates changes to increase the impact of the programme on women and girls, summarised in a Gender Action Plan (World Bank 2014 PAD). These include more specific guidelines on transferring pregnant and lactating women to direct support; active promotion of women to site supervisor roles for public works; and the introduction of soft conditions to encourage knowledge and utilisation of social services. For pregnant and lactating women (transferred on a temporary basis from public works to direct support beneficiary lists), conditions focus on ante-natal and post-partum clinic visits and participation in the Community-Based Nutrition programme. Other women (and men) will now be able to count participation in health, nutrition, family planning and financial literacy training as a contribution towards their public works obligations - a change which will benefit women in particular (World Bank 2014 pp. 47-8). The livelihood component will give particular emphasis to the needs of women: two people in each household can now receive livelihood support (in contrast to previous practice, which targeted the household head, who was generally the man) and the provision of advice and grants to individuals within the household will be customised to their needs, interests and capabilities. Other improvements will provide greater breadth and depth of sex-disaggregated data on programme activities and outputs, and are likely to be particularly important for understanding and improving the impact of the programme on women and girls.

Preliminary results from the last round of PSNP 3 impact evaluation suggest that transfers may have important effects on household behaviour and gender outcomes. Transfer receipt seems to have a significant impact on girls’ enrolment and progression through school; and increase the age at which they marry. Further research will look into these findings in more detail and seek to identify ways to modify PSNP 4 design to maximise these effects.

Strategic fit with UK and Ethiopian priorities
The PSNP addresses the need for a programmatic response from DFID to issues of vulnerability and extreme poverty; and the need for an inclusive approach to the scale up of DFID investments in economic development. Within the DFID Ethiopia Country Poverty Reduction Diagnostic (DFID Ethiopia 2014), the PSNP (along with the humanitarian and nutrition programmes) addresses the needs of the poorest and most vulnerable within Ethiopia – that segment of society which the recent Ethiopia Poverty Assessment suggests did not share in rising living standards and falling total poverty over the last decade. The proposed intervention helps to strengthen the foundation on which other aspects of DFID Ethiopia’s strategy (supporting economic growth and transformation, expanding basic services and human development, and improvements in governance and security) can be built.
PSNP has provided an important contribution to DFID and broader HMG objectives. PSNP achievements constitute a significant share of DFID’s global commitments on food security and cash transfer coverage results. In the Country Office Operational Plan, PSNP is responsible for delivery of one of the eight headline results (that 495,000 people will achieve food security). More broadly, PSNP has made a significant contribution to Ethiopia’s progress towards Millennium Development Goal (MDG) targets for reducing poverty and hunger, as well as increasing primary enrolment and gender parity outcomes (which were not anticipated in the original design).
While the primary focus of the proposed programme is on direct, targeted poverty reduction, it also contributes to the shift towards greater DFID investments in economic development. The DFID Ethiopia economic development portfolio encompasses programmes pitched at different levels, from high-level macroeconomic policy making, through the Infrastructure Advisory Facility, to private enterprise development and household land registration. In this spectrum, PSNP 4 helps to build the economic potential of the poorest segments of society. Transfers themselves play a significant role, in stabilising income so that households can retain and accumulate assets and in creating local economic multiplier effects through demand for local goods and services. Other components of PNSP 4 spending – notably the livelihoods support services and the capital investments in rural infrastructure such as roads and irrigation – directly contribute to economic development. Taking a narrow definition restricted to only these budget lines, some £24m of the PSNP budget over the first three years would count as economic development (around 10% of the projected economic development total). Design innovations introduced under PSNP 4 will strengthen the role of the programme (and the portfolio of Livelihood and Humanitarian Team more broadly) in building economic resilience (reducing and mitigating the risks that might derail Ethiopia’s development model) and ensuring that economic development is sustainable and inclusive. Finally, PSNP 4 will provide a major contribution to the realisation of UK Government commitments to support climate change adaptation and mitigation in developing countries.

Political economy and partner positions
The political economy of PSNP is broadly favourable to success, although there are some recognised issues which will require close attention. The programme is implemented through and owned by the Government. However, the Government has tended to see the programme as a time-bound intervention which is expected to eradicate food insecurity within a relatively short period. Written into the targets of the 2010-2015 Growth and Transformation Plan (GTP), this has driven Government efforts to ‘graduate’ households out of the programme at a rate which donors believe is not sustainable and which moves people off the programme before they are self-sufficient. The danger is that large-scale premature graduation results in many graduates falling back into poverty and food insecurity. The need to make graduation policy based on evidence rather than political targets has been a focus of joint reviews of the current programme and a central issue in the design of PSNP 4. Mitigation efforts focus at both the technical level (building into the next phase tools which will make District-based planning figures more realistic, and individual household readiness assessments more consistent and rigorous) and political level (encouraging the Government not to include graduation targets in the second GTP, now under preparation).
The PSNP works within a broader Government agricultural policy which has delivered agricultural growth, but which will need to evolve over time. Land policy and state control over the supply of inputs such as fertiliser have both advantages and disadvantages for long-term food security. The expansion of geographical coverage and redesign of livelihoods support under PSNP 4 will bring the programme into closer working contact with other Government agricultural programmes, and create potential openings to influence these policy debates.
In the past, the Government’s tendency to see PSNP as a time-bound programme addressing food insecurity as a residual rather than structural problem has also underpinned difficulties in ensuring domestic financing. To date, while the Government has been happy to spend on other pro-poor sectors and programmes (and has one of the highest ratios of poverty-focussed spending in Africa), it has been willing to regard PSNP as a variant on humanitarian assistance, and so rely primarily on donor funding.
New Government strategies and policy frameworks for social protection, disaster risk management and a climate-resilient green economy are supportive of a shift in Government thinking. The PSNP is assigned a key role in all three strategies, which should help encourage the Government to see the need for a standing social safety net to deal with structural issues of extreme poverty and hunger, build resilience against climate and price shocks, and support inclusive economic growth. Over the last two years DFID and other donors have funded Government officials to attend conferences on graduation policies and to learn from successful high-growth middle income countries (e.g. Brazil) which have greatly expanded cash transfer programming as part of a successful strategy of inclusive economic development. Government thinking is moving towards accepting the need for standing social safety nets as part of the permanent machinery of social and economic policy (as outlined in the Social Protection Policy): in addition to PSNP 4, the Government is now starting to develop an urban social safety net.
This shift is reflected in Government commitments to dramatically increase (albeit from a low base) the share of programme costs that are funded from domestic revenues. Current programme accounting probably substantially underestimates the GoE contribution to date through staffing and facilities; but during the design process donors, drawing on a commissioned PFM / fiscal space study, have requested that the Government commits more funds from domestic resources over the next phase.
Figure 2: Government financing will rise significantly over the next five years

Source: World Bank 2014 p. 183
The Government has committed to double its funding from £190m over the last five years to £323m over the next five. This will be tapered, rising from £37m ($57 m, or 7.6% of annual costs) in the first year to $149m (£97m or 21.5% of costs) in the fifth year (Figure 2): hopefully, the trajectory of incremental annual increases established over the coming five years will allow the Government to become comfortable with the idea of on-budget financing, and will be continued in the future until the programme is largely or entirely domestically financed. It is worth noting that Ethiopia has made greater progress in this direction than any other low income country in sub-Saharan Africa: but with per capita GNI (£266) still well below the average for developing sub-Saharan Africa (£1,009) or low income countries as a whole (£403), this is a long-term process which can justify external support for some years to come.

DFID comparative advantage, capacity and partnership

As a significant partner to the PSNP from the start, DFID has technical competencies in social protection policy and programming which is recognised by both the Government and other donors. DFID is also recognised as having specific relevant institutional expertise (in-country and available for draw-down from headquarters and other country offices through cadre 10% contributions) in cash transfer value-for-money analysis and in relating social protection issues to climate change, livelihoods support and nutrition.

Under the preferred option, DFID’s support to PSNP would be as non-budget support financial aid to the Government, and as such will be provided in the context of DFID’s country-level assessment of GoE commitment to the Partnership Principles and a programme-level Partnership Principle Assessment. The lead advisor for PSNP contributes to the regular office-wide review of the Partnership Principles; the team has also conducted a review of programme-level risks and mitigation measures that relate PSNP concerns to the overall UK-Ethiopia partnership.

Appraisal Case

What are the feasible options that address the need set out in the Strategic Case?

Two feasible options have been identified for comparison against a counterfactual 'do nothing' option:

- Option 1: End DFID support to social protection in Ethiopia (do nothing)
- Option 2: Support PSNP through non-budget financial aid provided directly to the government
- Option 3: Support PSNP through non-budget financial aid channelled via a World Bank Multi-Donor Trust fund

Option 2 and 3 are both designed to deliver the desired outcome through continued support to PNSP, but delivered through different modalities. Option 2 is would provide funds directly to the Ministry of Finance and Economic Development (MoFED). Option 3 would follow the same basic structure, but channel PSNP programme funds via the World bank Multi-Donor Trust Fund (MDTF) for the programme, and from the Trust Fund to MoFED, in return for paying the World Bank a £11m management fee.

Under both Options 2 and 3, approximately £230m will go directly to households as transfers, or to communities as capital investments in public works[5]. £32m will be spent on system development through the PSNP budget, and a further £2.2m will be retained by DFID for small but strategic non-PSNP interventions in support to the social protection sector. These may include (for example) the provision of technical assistance to the Ministry of Labour and Social Affairs (MoLSA) in developing their systems and capacities in both strategic planning (the overall social protection system) and operational delivery (assuming responsibility for delivering transfers to the permanent direct support beneficiaries).
[5] For the purposes of matching spend to outcomes, the £210 m that will go towards final outcomes (rather than longer-term institutional development) is comprised of the transfer costs (£179 m) and public works capital expenditures (£21m) under Outputs 2 and 3; plus the livelihood transfers (just under £10 m).

Two additional options for DFID support for the development of the social protection sector were considered at an early stage of design. However, changes in the policy context over the last year have since ruled them out.

Further piloting of the Social Cash Transfer approach. This has been piloted over the last three years in Tigray Region with the support of UNICEF. During the PSNP re-design process, UNICEF joined the PSNP Donor Working Group, and it was agreed that lessons from the the Tigray pilot will be incorporated into PSNP 4. As the social cash transfer approach no longer exists as a separate programme, this option has now been discounted.

Supporting the development of a new, urban social safety net. This is at an extremely early stage of development and the Government is not looking for engagement from donors other than the World Bank. While opportunities for DFID support may open up in a few years, it did not seem possible to build them into this business case, given the current degree of uncertainty. This option was discounted; but may be reassessed at the three-year mid-point of DFID funding.

### Option 1: End DFID support to social protection in Ethiopia

Under option 1, DFID would cease providing funding to the sector on the expiry of the current PSNP in 2015. This option would free up DFID financing for other programme priorities. In the absence of substitute funding from other actors, this option will reduce the size of the PSNP4 programme; and reduce the impact of the programme on poverty. A conservative projection suggests that without DFID support to PSNP 4, there would be an extra 373,000 people in poverty in 2020. DFID withdrawal could lead other donors to reconsider their support to PSNP 4 and this might result in a large-scale drop in financing for the programme.

### Option 2 and Option 3: Support social protection and disaster risk management through PSNP 4

There is a high degree of consensus within DFID Ethiopia around the case for support to continued evolution of social protection in Ethiopia. This reflects the DFID Country Poverty Reduction Diagnostic analysis and the strategic case for intervention; the evidence base for what works; and the opportunity to maximise DFID Ethiopia financing for climate-resilient poverty reduction by mobilising additional money (and impact) from the ICF.

As outlined in the Strategic Case, there is a need for an instrument that provides a direct but developmental (rather than emergency) response to high levels of extreme poverty, vulnerability and food insecurity. The DFID Ethiopia portfolio covers a spectrum from pressing emergency humanitarian operations, through medium-term investments in development outcomes (human development and economic opportunities), to promoting ‘upstream’, long-term improvements in the enabling environment for development (macroeconomic policy and good governance). On this spectrum, social protection bridges the gap between humanitarian operations and developmental programmes. Poverty-targeted, direct-to-the-poor cash transfers help very poor households to smooth consumption, avoid adverse coping strategies, and overcome barriers that prevent them from benefiting from human development and livelihoods programmes; and help to build resilience to climate shocks at household, community and national levels. There are relatively few alternatives which would deliver the same objectives, against which the proposed support to PSNP and social protection system building might readily be compared.

The proposed focus of DFID’s proposed support to social protection would be the fourth (2015-2020) phase of the Productive Safety Net Programme (PSNP 4). There are a number of reasons for proposing this mechanism.

The PSNP has an established record of delivering results at scale and with good value for money. PSNP is by far the largest transfer programme in Ethiopia and the one for which there is most evidence of impact on food security, poverty, dietary diversity and education. This provides a solid foundation for introducing innovations to enhance impact on both long-standing and new objectives.

Secondly, and centrally for this business case, this next phase of the PSNP’s evolution will not only deliver impact on final outcomes through effective operations but also investments that contribute to the development of an integrated national social protection system over the longer term. Two of the five PSNP 4 outputs focus on building tools and capacities which support effective implementation of PSNP but also the consolidation of a broader social protection system. Management tools to be developed for PSNP 4 will be designed to be used not just by PSNP but also by other poverty-focussed Government programmes. Spending on system tools and capacities accounts for £295m (13% of the PSNP 4 budget) over five years (£36m of DFID’s proposed £276m spend). PSNP 4 thus aims to build on programme-specific capacities to put in place the foundations of a broader system that will provide coherence to different social protection programmes.

Finally, there is an existing commitment of £182m of ICF financing for PSNP, contingent upon approval of the Business Case and commitment of £94m in Country Office funds. Funding for PSNP thus helps to leverage additional funds, enabling DFID to achieve more with the available DFID Ethiopia Country Office budget.

We considered a range of levels of potential funding in support to PSNP. Considerations have included (1) the level of need (reflected in the increased scale and ambition of the Programme, as described in the Design Document); (2) the evidence that PSNP constitutes an effective and efficient use of funds to achieve these objectives; (3) the issue of incentives and the need to encourage the Government to increase the level of domestic, tax financing for PSNP; (4) the proportion of total external, donor funding for the programme that is covered by DFID (i.e. what is considered fair and prudent ‘burden share’); and (5) competing potential uses for DFID funds within the DFID Ethiopia budget envelope. Based on this assessment, we judge £266m over 5 years as non-budget support financial aid to PSNP, targeting against a clear annual workplan and complemented by £10m in other spending, to be the right DFID contribution. At 11% of the total financial need for the programme, this is a reasonable burden share for DFID.

The key choice remaining – and the difference between Options 2 and 3 - is the financing instrument by which to support PSNP 4. To date, DFID has supported the PSNP through disbursements directly to the Ethiopian Ministry of Finance and Economic Development. Under Option 2, we would continue with this mechanism. Alternatively, under Option 3, we would channel our support through a World Bank-administered multi-donor trust fund (as do many of the other donors to the programme). The Appraisal Case assesses the case for support to social protection against the ‘do nothing’ counterfactual (option 1). It then compares the advantages and disadvantages of two possible variants on financing and partnership (options 2 and 3).
Assessing the evidence base: lessons from PSNP 3 and other programmes

The overall evidence for the impact of safety net cash transfers on final outcomes is rated as ‘very strong’. The case for supporting safety net transfer programming is supported by a large volume of robust research and evaluation, both from Ethiopia and other countries (see for example Grosh et al 2008; Fiszbein et al 2009; Arnold, Conway and Greenslade 2011; Bastagli et al 2015 forthcoming). This allows us a high degree of confidence in the results that can be expected for the proposed intervention. These following pages summarise the key points with regard to the known impact of the PSNP; more detail on each point can be found in Annexes 2 and 3.
High quality impact evaluations suggest that the PSNP is now implemented well and results in large and widespread gains in household welfare and rural development. Impact assessments demonstrate that transfer programmes are generally very well targeted (the highlands PSNP and the Tigray Social Cash Transfers); but less well targeted in the lowlands, where PSNP was introduced five years later. Participation in the programme:
adds significantly to pre-transfer income and consumption;
- has a significant impact on food security. Between 2010 and 2012, PSNP transfers reduced the average annual food gap of PNP beneficiaries – the number of months in which households struggle to feed themselves – by half (1.5 months); and resulted in a significant improvement in dietary diversity. The percentage of PSNP beneficiaries achieving full (12 months) food security rose from 17% in 2006 to 32% in 2012. Impact on food security has been particularly large for female-headed households.
- increases household spending on not only food but also non-food items (Kumar and Hoddinott 2013 pp, 27-9);
- has improved educational attainment (grade progression and completion), particularly for girls.
- appears to help to reduce the age at which girls marry and leave their parents household; and as such, contributes to tackling the serious problem of early and child marriage in Ethiopia;
- has been one of the three drivers of poverty reduction between 2005 and 2011 (World Bank 2015). The direct impact of PSNP transfers reduced the national poverty headcount rate by 1.6 percentage points in 2011, lifting more than 1.4 million people out of poverty. Indirect effects via higher agricultural productivity increase this impact further[6].
  [6] In the same year (2011), humanitarian transfers reduced the poverty headcount by 0.4 percentage points, or c. 353,000 people.
- has helped extremely poor households to invest in inputs and farm-level improvements which will improve agricultural productivity and allow them to manage their land more profitably, particularly when combined with livelihood support services.
The PSNP incorporates gender equity provisions relating to who in the household can claim transfers; consideration of the needs of girls and women in the selection of public works, setting of work norms and provision of childcare at public works sites (Coope 2014 pp. 8-10); and female participation in programme governance (Evers et al 2008; Jones et al 2010; SNSF 2014; Coope 2014). The broad findings are of improving and in some cases good performance (e.g. the programme’s impact on schooling in Tigray has been even better for girls than boys), but with considerable variation between provisions and regions (with the lowlands generally lagging).

PSNP has also made aggregate, area-level contributions to rural development and disaster risk management. Public works completed under PSNP constitute a massive investment in rural development: in 2013/14, over 48,000 sub-projects were planned, requiring 104 million person days (Campbell 2015 p. 11). Bio-physical studies and cost-benefit evaluations have shown that PSNP public works have contributed to reversing soil erosion and environmental degradation and expanding the area served by small-scale irrigation and improving access to markets and schools. The injection of cash transfers into poor communities generates significant multiplier effects (estimated at 1.84) as recipient households spend their additional income on local goods and services, providing a significant boost to incomes and growth in the locality.

At a national level, the PSNP has contributed to policy goals for disaster risk management and climate resilience. The PSNP’s Risk Financing Mechanism (RFM) helped Ethiopia to manage the 2011 Horn of Africa drought crisis without the famine that occurred in neighbouring Somalia and the significant spike in acute hunger and malnutrition seen in northern Kenya – or, for that matter, the kind of famine that such droughts have induced in Ethiopia in the recent past (ICAI 2012; Sida et al 2012). Economic analysis suggests that in Ethiopia over a span of 20 years, investment in building resilience to crises (in which PSNP plays a major role, and one which will increase under PSNP 4) will save some £2.1bn ($3.3bn) compared to reliance on humanitarian response (Venton et al 2012).

Finally, PSNP also contributes to climate change mitigation. Successive PSNP public works impact evaluations have found that PSNP soil and water conservation activities, and the resulting enclosure of protected areas leading to the regrowth of vegetation and carbon capture in the soil, have resulted in the sequestration of atmospheric carbon on a large scale, with 1.45 m tonnes of CO2e sequestered in just two sample watersheds.
The technical assessment of PSNP impact is broadly in line with beneficiary feedback. Perspectives from those living in PSNP districts (both transfer beneficiaries and non-beneficiaries) have been collected through the qualitative research in the two-yearly impact assessments; through DFID field visits and Annual Reviews; and through longitudinal research on rural socio-economic change under the Well-being and Ill-being in Developing Ethiopia (WIDE) studies.
There are also objectives which the PSNP has not achieved to date (but it is hoped will be achieved with design changes in PSNP 4); and others which have not been part of the PSNP logframe before now, but are now incorporated in PSNP 4. There are four main areas in which evidence has guided significant design changes:
- Ambitious goals set by the Government for HABP have not been matched with adequate financing or official attention, and have accordingly fallen short.
- Compared to the highlands, PSNP has had much less impact in the pastoral and agro-pastoral lowlands (where capacity is lower, environmental change more rapid, and the programme was introduced five years later).
- The Risk Financing Mechanism (RFM) played a critical role in preventing famine in 2011, but could have been much more effective if implemented as planned. Since 2011, the Government has not managed to combine regular PSNP transfers, RFM and humanitarian resources in the way that agreed processes (and logic) require, and the effectiveness and transparency of RFM utilisation has fallen well short of what is desired and needed.
- Significant gains in food security have not yet resulted in better child nutrition. It seems that improved food intake is a necessary but not sufficient condition for improved nutrition: access to clean water and sanitation, knowledge of breastfeeding and weaning practices, and quality of public health services are also needed.
- Finally, the evidence for what works in building institutional capacity at the programme level, and building functioning, integrated systems for social protection and disaster risk management that piggy-back on safety net administrative processes and capacities, is thinner and on this basis must be assessed as ‘medium’.

Criteria for appraisal
Box 2: Criteria for DFID intervention

1. Household-level outcomes: reduced poverty and food security.
2. Local level outcomes: rural social and economic development.
3. National level outcomes: inclusive and climate-resilient development
4. Global-level outcomes: contribution to climate change mitigation.
5. Value for money

Based on this summary of the evidence, the assessment below summarises the arguments in favour of either of the proposed social protection interventions – either option 2 or option 3 - relative to the ‘do nothing’ counter-factual (option 1). The case for DFID support (Options 2 and 3) will be assessed against five criteria (see Box 3). Each of the first four describes a category of desired outcomes, from household level through to global public goods; the fifth is the criterion that the proposed intervention must represent good value for money. The choice between Options 2 and 3 is then discussed with reference to issues of feasibility and risk management.

Theory of change
The theory of change for the proposed support rests upon a number of assumptions about how inputs will give rise to outputs, outputs to outcomes, and outcomes to impact and policy-level objectives (DFID 2012; Browne 2013). Assumptions informing the design of the programme are summarised in Annex 4. The diagram on the following page provides more detail on this intervention logic by making explicit the assumed causal relationships and assessing the strength of the evidence underlying each assumption.

Figure 3: Theory of change for PSNP 4

Using the definitions and indicators from the results framework and logframe included in the PSNP 4 Design Document, Figure 4 maps the cause-effect relationships by which outputs (on the left) are assumed to contribute to achieving the indicators that define the Programme’s outcomes and impact (on the right). The width of a given arrow linking one step in the results chain to the next provides an indication of the strength of evidence for this given link: a thin arrow indicates sound theory but limited Ethiopia-specific evidence to date, whereas a thick arrow indicates a high degree of confidence that A will indeed lead to B, based upon the evidence base that now exists.
The theory of change also attempts to highlight how results at a higher level are often dependent upon a combination of processes and achievements at a lower level. Improvements in livelihoods, for example, will require a combination of household-focussed activities (regular and lump-sum transfers, advice on income-generating activities, and access to credit) and locality-level improvements to the natural resource base and market integration through public works.

Estimated costs and benefits of each option

### Option 1: Stop DFID support to social protection

This option would release £94m for alternative uses within the DFID Ethiopia country programme (the remainder being leveraged funding from the ICF). This could be used to increase the size of existing or planned programmes; and/or support the development of new programmes.

The costs would be quantified in the form of slower progress against the development outcomes to which PSNP contributes; and possible need for compensatory spending in other parts of the DFID Ethiopia programme. The DFID funding proposed under options 2 and 3 would constitute 16% of total current indicative commitments of Government and donor finance to the PSNP; and 11% of the total five year PSNP costs. Given the current financing gap (i.e. the difference between indicative commitments and total costs), it is unlikely that other sources would be able to substitute for the lack of DFID financing. In this case, the PSNP would be significantly smaller than planned.

It is hard to predict how PSNP implementation would be adjusted to compensate for the lack of DFID financing. Options for the Government and the remaining donors would include one or more of the following:
- Reduced coverage. The programme would stay largely within its current boundaries, rather than, as planned, expand to encompass 92 new woredas, most of which are within the Somali Region. Reducing activity in this region runs contrary to DFID commitments to focus increasing attention on the developing regional states (such as Somali) in the interests of conflict reduction, national integration and regional (Horn of Africa) stability.
- Reduce transfer generosity. PSNP transfers are set to increase (in line with recommendations from NAO and PAC reviews, which noted that – given the very low current value of most DFID-supported transfer programmes, and within limits - increasing transfer values are generally more effective in generating sustainable exits from poverty, and as such generally represent better value for money). In the absence of a contribution from DFID, one option would be to keep to the current (lower) transfer value; and maybe to freeze the value over the lifetime of the programme (i.e., drop the provision for inflation-related annual adjustments). This would reduce the impact of transfers on programme beneficiaries.
- Remove the Federal contingency. The Federal contingency will provide transfers to 2.86m people in 2015/16, 2.98m in 2016/17, and 1.73m in each of the remaining three years. This would be a relatively simple component to cut if DFID did not finance the programme.

In the absence of substitute funding, these options will reduce the size of the programme; and reduce the impact of the programme on poverty. A conservative projection suggests that without DFID support to PSNP 4, there would be an extra 373,000 people in poverty in 2020. This forecast is however extremely crude, both in its own right and in ignoring second order, knock-on effects of DFID withdrawal[7]. The DCT has expressed concerns that DFID withdrawal would lead other donors to reconsider their support to PSNP 4; and that this herd effect might result in a large-scale drop in financing for the programme.
[7] This estimate (373,000 extra people in poverty in 2020/21 if DFID does not fund PSNP 4) is based on the impact of the programme on poverty in 2010/11 (1.4m); scaled up to reflect the larger planned caseload in 2020 (10m as opposed to 7.6m in 2010/11) and the higher transfer value (an additional 4kg pulses on top of the previous 15kg grains) in 2020 compared to 2010/11; and then multiplied by 0.16 (DFID’s share of planned funding, and thus projected impact). It is crude on three counts. Firstly, it simply attempts to relate impact in one phase to impact in another through a comparison of their relative coverage and generosity: a more sophisticated method would attempt to project the level and distribution of per capita consumption in 2020/21; make assumptions about the targeting accuracy of the programme; and then on this basis model the impact of PSNP transfers on the consumption distribution, and see how many it raised above the poverty line. This would be possible (e.g. using the Social Protection module of the World Bank’s ADePT software): but unfortunately it has not been possible to obtain the HICES 2010/11 microdata from the Ethiopia Central Statistical Agency (CSA). Secondly, the modelled impact is purely mechanical and mathematical (an income / distribution effect): it does not account for second-order impact on poverty through the use of transfer income for productivity-enhancing household investments, or the role of transfers in improving household credit-worthiness and access to finance, or in protecting against asset depletion in the event of a shock. Nor does this number account for the poverty-reducing effects of the environmental rehabilitation and economic infrastructure created through PSNP public works. Finally, it does not attempt to account for the poverty-reducing effect of the technical advice, job search assistance and lump-sum transfers through the livelihoods component. For all these reasons, it is likely that the estimated 373,000 additional poor in the absence of DFID funding is conservative, under-estimating the likely increase.

A smaller PSNP is likely to result in increased humanitarian caseload; which DFID may need to help meet through additional humanitarian programming. The introduction of the PSNP in 2005 reduced the average size of the annual humanitarian food needs requirement; this call on humanitarian resources (to which DFID has been a major contributor) has fallen further over the second phase (2010-2015), despite a drought of unusually large proportions in 2010/11 (Table 2; Figure 4).
Table 2: PSNP and humanitarian caseloads since 2000

	Caseloads (million people p.a.)
	humanitarian food	PSNP
average, 2000-2004	7.54
average, 2005-2009	4.03	6.76
average, 2010-2014	3.81	7.18

Sources: Wiseman et al 2009 p. 39; 2008 and 2009 HRDs from http://reliefweb.int/report/ethiopia/; Rahmato 2013 p. 116 in Rahmato, Pankhurst and van Uffeln 2013

Figure 4: Since 2005, PSNP has reduced the need for humanitarian assistance to Ethiopia

responding to food insecurity, 2000-2014:
humanitarian and PSNP caseloads (millions of people supported)
sources: Wiseman et al 2009 p. 39; 2008 and 2009 HRDs from http://reliefweb.int/report/ethiopia/ ;
Rahmato 2013 p. 116 in Rhmato, Pankhurst and van Uffeln 2013

### Options 2 and 3: Support the development of the social protection system

#### Expected costs

The costs of Option 2 and 3 are similar. In both cases, DFID will providing £266.3 m over the five years in funds to PSNP programme activities; £5.5 m to the DCT; £2.5 m to the new capacity building facility; and retain £2.2 m for DFID-managed analytical and advisory work (see the Financial Case below). DFID spending will be front-loaded, tapering from £80 m in 2015/16 to £47.2 m in 2019/20. This reflects the higher costs in the first few years of PSNP 4 implementation due to initial investments in systems and capacity development activities.
In the case of Option 3, there is a fee to be paid to the World Bank for managing DFID’s funds as a contribution to the multi-donor trust fund[8]. This will somewhat reduce the amount of funds passed on to the government for PSNP 4 implementation. Table 3 summarises the relatively minor cost differences between options 2 and 3.
[8] The new (mid-2015) cost recovery rates for World Bank trust funds are 5% on the first $50 million and 4% on the next $450 million.

Table 3: PSNP 4: Cost structures of alternative DFID options

budget component		Option 2		Option 3
		PSNP funds direct to GoE		PSNP funds through MDTF
		£m	%	£m	%
1	PSNP	266.3		266.3	96.5%
	- transferred to GoE	266.3	96.5%	255.3	92.5%
	- administration fee to WB (5%)			11.0	4.0%
3	DCT	5.0	1.8%	5.0	1.8%
4	Capacity-building facility	2.5	0.9%	2.5	0.9%
4	DFID-managed research and TA	2.2	0.8%	2.2	0.8%
total		276	100.0%	276	100.0%

The total cost of PSNP 4 for five years is £2.35bn ($3.625 billion), up from c. £1.49 billion for the previous five years. Table 3 presents these total costs. The increase is mainly driven by (i) the increase in coverage (from less than 6 million beneficiaries in 2014/15 to a stable 10 million for the next five years); and (ii) higher transfer values. Based on current revenue projections, total PSNP expenditure will be equivalent to 3.5% of total GoE expenditure and 1.1% of GDP (in but at the lower end of the 1-2% of GDP that most developing countries spend on safety nets).

Table 4: Total five-year PSNP 4 programme budget (£m)

Source: World Bank 2014 p. 183; MoA 2014 p. 92. Converted at £1 = $1.5398.
† soil and water conservation, small-scale irrigation and water supply (c. 69% of total PW spend) count as 90% ICF eligible. Other public works (e.g. rural roads, social infrastructure - c. 31% of total PW spend) count as 25% ICF eligible.

To date, Government and donors have provided indicative commitments of $2.627 bn, leaving a financing gap of $1bn (£648 m) for the outer years of the programme (see Annex 9 for sources of committed financing). As the programme absorbs significant parts of the current humanitarian caseload, resources from donor humanitarian budgets are expected to shift to the PSNP over the medium term. Based on this, and the fact that many donors are only able to commit resources for shorter periods than the programme’s five years, it is expected that the financing gap will be closed during project implementation. (This was the case during the current phase, which also began implementation with a large financing gap.)

The next five years will see a significant increase in GoE domestic financing of PSNP. Under PSNP 3 (2010-2015), the Government contribution was largely as substantial but unmonetized operational spending (the salaries of staff working primarily on PSNP implementation) estimated at £130-160m; the GoE financial contribution was only a token £6.5m. In the next phase, however, the Government will contribute £185m ($284m) towards financial costs, in addition to operational expenditure (valued at £138.6m ($213m) over five years). In year 5, the Government will be financing 28.6% of the total annual PSNP budget, and 21.5% of total programme costs (see Table 5).

Table 5: Government contribution and sustainability (£m)

	year 1	year 2	year 3	year 4	year 5	Total
	2015/16	2016/17	2017/18	2018/19	2019/20
estimated value GoE operational expenditure	27.7	27.7	27.7	27.7	27.7	138.6
proposed additional GoE cash contribution	9.6	21.1	35.2	50.2	68.9	185.0
total GoE contribution	37.3	48.8	62.9	77.9	96.6	323.5
as share of total PSNP programme costs	7.6%	10.2%	13.1%	17.1%	21.5%	13.7%
as share of estimated total GoE expenditure	0.2%	0.4%	0.6%	0.8%	1.0%

Source: World Bank (2014) p. 183. Dollar values converted to pounds sterling at £1 = $1.53984.

Forecasts for GoE revenue suggest adequate fiscal space for the proposed PSNP 4 expenditures. Government contributions are based on recommendations from the World Bank’s fiscal space study and should be sustainable. Donors will also engage in a policy dialogue which aims to contain and reverse GoE spending on general subsidies, which are regarded as a sub-optimal tool for social protection (relatively costly, regressive and resulting in distorted markets and incentives). There is a strong case, in Ethiopia as in other countries, to re-direct public expenditure from subsidy reform into transfer programmes which are better targeted and proven to be effective.

In summary, keeping other factors equal, the costs of Option 1 would be higher levels of food insecurity and extreme poverty, and lower levels of climate resilience, than under Options 2 or 3. Based on recent trends in Ethiopia, headcount rates of poverty and hunger are likely to continue falling even without the PSNP; but they will fall at a slower rate, and in five years’ time will remain considerably higher, than would be the case with DFID support to the PSNP. This higher level of deprivation could be partially offset by allocating the £94m of DFID Ethiopia country funds wholly or in part to other programmes (probably humanitarian food aid) that address these needs. However, there is a broad consensus (in Ethiopia and globally) that humanitarian assistance is most effective in, and best reserved for, addressing acute and unpredictable need. Given that much poverty and hunger in Ethiopia is chronic, structural and predictable in nature, there is a strong rationale (in terms of both efficiency and effectiveness) for DFID to adopt a mixed response, which combines a developmental, PSNP response to the predictable base level of chronic need, complemented by a humanitarian response to the unpredictable inter-annual variation in the level and spatial distribution of short-term, crisis-induced food needs.

#### Expected benefits
The following pages summarise and justify the expected benefits of Options 2 and 3, framed under each of the assessment criteria listed previously[9]. Expected benefits are quantified and monetized wherever possible. The detail behind these results – the formal theory of change that underpins the expected relationship between inputs, outputs and outcomes, and the basis by which each estimated result is calculated – is provided in Annex 4. Most of the expected results have been extracted from the targets in the programme logframe in the PSNP 4 Design Document, which reflect some 18 months of discussion between the Government and donors[10]. In a few cases, the Business Case also attempts to extend on these documents with additional efforts to quantify expected benefits.
[9] For simplicity, the discussion of estimated benefits from PSNP 4 implementation use the total benefits estimated from the whole programme. In the summary cost-benefit table, however, these benefits are scaled down to 16% of the total (reflecting DFID’s share of programme funding) to provide a fair basis for comparison with DFID costs.
[10] Only selected logframe indicators are reproduced in the Business Case under ‘expected benefits’. The full programme logframe is very long consensus document: while considerable effort has gone into it, and it is on balance a much more useful framework than the PSNP 3 logframe, there are still questions about some of the indicators and targets. Some of the newly-introduced indicators are useful additions, and can credibly be measured: but without baseline data (which should be obtained from the late 2015 impact evaluation survey), have not yet set target values, and so are not included in the Business Case. For some of the other new indicators, the complex construction of the indicator definition or questions over the data collection instruments that will provide the source for these indicators: and so are not included in the Business Case.
Broadly speaking, we have considerable confidence regarding the results that are expected from transfers and public works. The evidence base for these cause-effect relationships is derived from rigorous impact evaluations of PSNP (and similar programmes in other developing countries). The basis for projecting expected results is more speculative with regard to the more innovative design elements introduced in this phase. These include the linkages to nutrition programming and livelihoods support; the development of effective coordination mechanisms; and the capacity building activities which should strengthen delivery at programme and system levels.

#### 1. Household level benefits
PSNP 4 incorporates a number of changes which are expected to increase the impact of the programme on household outcomes, beyond that which was obtained under PSNP 3. Those designated as permanent direct support clients (the elderly, those with disabilities, the chronically ill) will receive transfers for 12 rather than just six months each year. Secondly, monthly transfer values will increase for all recipients: the value will be based on the cost of 15kg of grains plus 4kg of pulses (costed at a cash value of £4.4 / $6.8), rather than just, as under PSNP 3, just 15kg of grains. This will bring the nutritional value of PSNP food transfers much closer to that of the humanitarian food basket, which is designed to provide a full 2,100 kcal / person / day (as well as higher protein and fat contents); the equivalent PSNP cash transfers will allow for more effective consumption smoothing and livelihood impacts than in the past (MoA 2014a; World Bank 2014 p. 110). This increase in transfer values from the very low levels employed to date is in line with the recommendations in the NAO and PAC studies on value for money in DFID-supported transfer programmes.

In addition to these changes, which will increase the impact per beneficiary, the expansion of the programme will bring these benefits to more beneficiaries. 41 woredas will be brought into the programme in 2016/17 and 51 in 2017/18. The caseload will rise from current levels (5.2m in 2014/15) to reach and remain at 10m for the next five years (equivalent to roughly a third of the population in poverty). With more generous benefits reaching a greater number of people, the impact of PSNP 4 on aggregate national welfare indicators (mean p.c. consumption and food gap, poverty rates and utilisation of services amongst the poorest) is expected to increase significantly.

Transfers will improve the food security of beneficiary households, building on progress seen between 2010 and 2014. The key measure of food security will be a reduction in the average food gap – the number of months in a year that a household struggles to feed itself, and is forced to reduce the number of meals per day and/or the size of portions. The food gap is expected to fall by a third for current beneficiaries, but only a fifth for newly-enrolled beneficiaries; living standards for beneficiaries are expected to rise by on average 20%.

PSNP 4 also introduces arrangements to improve nutritional outcomes for PSNP recipients, and so contribute to the realisation of the targets in Ethiopia’s National Nutrition Programme (NNP). The increased transfer value described above should contribute to gains in both the quantity and quality of food consumed by recipient households. In addition, PSNP 4 incorporates a focus on nutrition under revised eligibility and targeting rules (households with an acutely malnourished child will be automatically enrolled for one year; existing client households with a child who falls into acute malnutrition will be shifted temporarily from public works to direct support status); the promotion of livelihood activities and public works that contribute to local improvements in nutrition; and, critically, using ‘soft conditions’ to link PSNP beneficiaries to training and health services which should improve nutrition outcomes (Bossuyt 2015a, 2015b; PSNP 2015; World Bank 2014 p. 11).

The programme will expand access to improved economic opportunities for the poorest rural households, helping them to increase and diversify incomes to work their way out of food insecurity and, eventually, ‘graduate’ from the need for PSNP transfers. In the next phase, PSNP livelihoods support activities will incorporate significant changes, drawing on learning from HABP and other livelihoods support programmes. At an institutional and managerial level, livelihood support will be fully integrated as a component of PSNP 4 programme design and logframe (in contrast to the semi-autonomous status of HABP over the last five years). The new livelihoods component will support a broader range of livelihoods opportunities, including diversification into off-farm livelihoods (self-employment) and access to waged jobs, in addition to the improvements in smallholder agricultural productivity that were in practice the focus of HABP advice over the last five years. Support will add new elements – mentoring, financial literacy training, the promotion and facilitation of savings, and the provision of a one-off transfers to enable households to meet the ‘lumpy’ costs of investments in productive assets, inputs or jobsearch – to the previous, somewhat minimal HABP package of business advice and credit.

The PSNP 4 Design Document incorporates a strengthened focus on gender (elaborated in the PSNP 4 Gender Analysis and Action Plan). In part, this entails a closer focus on the implementation of provisions that existed in PSNP 3, but were implemented unevenly between different localities. Other design features are new to PSNP 4. Key provisions include the definition of physically less-demanding tasks for women engaged in the public works programme; a 50% reduced workload for women; transition of pregnant women from public works to temporary direct support from the fourth month of pregnancy (or earlier, on receipt of a medical certificate) through the end of the first year postpartum; the use of public works labour to construct day care centres; and minimum standards for representation by women on a variety of safety net committees. The Gender Action Plan includes capacity building and awareness raising targeted to women; increased institutional engagement of the Ministry of Women, Children and Youth Affairs and the Women, Children and Youth Directorate of the MoA; and ensuring the posting of Social Development Experts at woreda level.

These changes should help to lift – at a minimum - between 3.2 and 5.4 million people out of poverty by 2020. These estimates reflect merely the direct, distributional impact of PSNP transfers (the income effect); in addition to this effect (transfer income lifting households up over the poverty line), PSNP 4 will help to reduce poverty by helping transfer-recipient households to afford productive investments (which shift them to a long-term trajectory of higher private incomes) and avoid the need for negative survival strategies and downward movements in the face of weather-induced production shocks. These second-order effects are likely to increase the impact on the poverty headcount significantly above five million.

Table 6: Selected key benefits: household level

Form of impact	Measure	Projected impact of PSNP
Living standards	Average non-food consumption spending for PSNP beneficiaries (per capita per month, 2012 prices)	70% increase (from 212 birr (£7) per capita per month in 2012 to 360 birr (£12) in 2020
Food security	Food gap (average number of months in a year that PSNP households report needing to reduce the number or size of meals)	One-third reduction for prior (PSNP 3) beneficiaries / 20% reduction for new beneficiaries
Nutrition	dietary diversity (average number of food groups (out of 7) consumed the previous day)	30% gain (from 3.4 in 2012 to 4.4 in 2020)
Livelihoods	Average value of asset holdings (constant prices)	30% gain
	Percentage of PSNP beneficiaries reporting new income sources	30%
Poverty reduction	National poverty headcount (number of people living below the national poverty line of 3,781 birr / £146 per capita per annum, 2011 prices)	4.3 million fewer people in poverty (base case – low case 3.2 million, high case 5.4 million)

#### 2. Local / community level benefits
As under PSNP 3, PSNP 4 can be expected to contribute significantly to rural economic development through the construction of infrastructure which restores soil fertility, enables water management, and improves access to markets. While the exact mix of public works activities (which are selected annually by communities) is hard to predict, on the basis of PSNP 3 outputs it is likely to contribute more than 3,500 km of rural roads, 40,000 km of hillside terraces and 450 schoolrooms each year.

PSNP 4 public works will build on the significant achievements under PSNP 3, while incorporating changes where needed to improve suitability or quality of works. These changes include modifications to further increase the contribution to climate change adaptation; closer attention to identifying public works suitable for lowlands landscapes and livelihoods; making the works programme more gender sensitive; improving the quality and sustainability of roads and water projects; and enhancing the potential contribution of public works to nutrition, health and livelihood outcomes. In highland woredas where the PSNP has been implemented since 2010, the focus is likely to shift from soil and water conservation to projects more directly focused upon livelihoods. Once the natural resource base in a watershed has been regenerated, new livelihoods become possible as irrigation and expansion in the area under cultivation create new economic opportunities (e.g. the sale of cash-crops and a shift to commercial- rather than subsistence-oriented livestock practices).

The evidence suggests that PSNP public works have already made a significant contribution to climate adaptation. PSNP 4 will strengthen these effects by incorporating considerations of climate change on an explicit and systematic basis. Drawing on the findings of the DFID-supported Climate Smart Initiative (CSI) pilots, PSNP 4 will influence both the choice of works and the ways in which works are designed and implemented. Supported by woreda-level facilitators, local people are identifying ‘best-bet’ activities for building food security in the context of uncertainty about future climatic conditions. PSNP4 will significantly increase the land covered by improved watershed and rangeland management structures and practices.

The £1.725 bn ($2.657 bn) provided in PSNP transfers over the next five years should generate an additional £1.449 bn in local economic multiplier effects. Based upon analysis of the impact of transfers on economic activity in Tigray region, it is estimated that every 1 birr of transfers can be expected to generate an additional 0.84 birrs in local economy income. This additional income is equivalent to 41% of total PSNP 4 programme costs.

Table 7: Selected key benefits: community level

Form of impact	Measure	Projected impact of PSNP
Environmental rehabilitation	Total closed area subject to enhanced management for climate adaptation (hectares)	500,000 ha by 2020
Stimulation of rural incomes	Gain in private incomes (m birr) due to increase in local demand for goods and services (multiplier effect of PSNP transfers in PSNP localities)	£1.449 bn by 2020

#### 3. National level benefits
Over the next five years, PSNP 4 will support the evolution of coherent, effective and efficient national systems for social protection and disaster risk management. The PSNP will evolve from a relatively autonomous, time-bound programme to become a central part of broader, permanent structures that contribute to a variety of national policy objectives. This shift to a systems approach implies the development and implementation of common administrative mechanisms to tackle policy, institutional and budgetary fragmentation. The tools and instruments central to the delivery of the PSNP 4 will be designed not only to support the implementation of the next phase of the PSNP but also as operational underpinnings for the overall social protection and DRM systems. Ultimately, different Ministries and programmes serving the same clients (the extreme poor and those vulnerable to extreme poverty) should use a common set of PSNP-built tools, instruments and approaches to ensure maximum impact and cost effectiveness (MoA 2014 pp. 11-13).

The expected results of these PSNP 4 investments in systems building will focus on six priority areas. These are (i) targeting (the principles and processes for programme entry and exit, with a particular focus on pastoral areas); (ii) information management and programme monitoring (the design and implementation of an integrated, electronic Management Information System (MIS) which can share data with other information systems); (iii) development of local DRM capacities (harmonised early warning systems and pre-planning for scaling up transfer and livelihood activities in response to shocks); (iv) improving arrangements for planning, coordination and governance; (v) strengthening social accountability and grievance redress mechanisms and gender provisions; and (vi) systematic and sustainable investments in capacity development (MoA 2014; World Bank 2014).
The PSNP is assigned a significant role in the Government’s 2013 Disaster Risk Management (DRM) policy and investment plans. This reflects the important potential of the PSNP – some of which has been realised to date, some of which has not – to contribute to both the prevention or mitigation of impact before a shock occurs (e.g. through public works which restore soil moisture and water tables and so help to prevent a failure of rains from turning into a drought) and a timely and effective response to a shock that has broken (using pre-positioned contingency funds and PSNP delivery channels to extend timely relief transfers to shock-affected households).

Since the PSNP was written into the DRM policy, design changes have been incorporated in PSNP 4 which should significantly improve the potential contribution to DRM objectives. Firstly, the core PSNP transfer programme will expand to absorb part of the caseload of need that has to date fallen to the humanitarian system to serve. Recognising that many of those served by humanitarian food aid in recent years have been in need of such assistance in successive years (i.e., are in fact chronically food insecure, and therefore would be better served by a developmental safety net programme rather than emergency assistance), the PSNP will seek to ‘right size’ its core caseload, expanding to reach 7.1 m people in the first year, rising further to stabilise at 8.3m from year three.

Secondly, to address the shortcomings of the PSNP 3 Risk Financing Mechanism (RFM), the relationship and sequencing between the PSNP and humanitarian food aid – the ‘continuum of response’ – has been fundamentally redesigned. PSNP 4 will now budget and plan for a significant response to remaining transitory need every year. The woreda contingency fund (equivalent to 5% of the base program cost) will be retained, but is likely to make only a modest contribution to scaling up in the event of a shock. The Regional contingency (which was frequently under-utilised, which in turn impeded triggering the RFM) will be abolished. The RFM will be replaced with a Federal Contingency budget. Unlike the RFM, this Federal contingency is to be utilised every year, avoiding the incentives that might prevent the triggering of a scaled-up response, and the dependency upon imperfect and sometimes contradictory early warning assessments that created scope for disagreements between stakeholders about whether or not the humanitarian situation justified triggering the RFM.

The size of the Federal contingency will decline slowly as the size of the regular programme expands and then stabilises. On the principle that for the next five years the PSNP will provide transfers to a total of 10 m people each year, the balance between this total allowance of 10m p.a. and the regular transfer caseload will be available as the Federal contingency, to respond to transitory (i.e. seasonal) need. The Federal Contingency budget will thus provide one-year transfers to 2.861 m of the transitory caseload in the first year of the next phase; falling to 2.297 m in the second year; and 1.733m each year from the third year onwards (Table 8). Humanitarian food aid will then be sought to meet the residual transitory needs of those who are not reached by the Federal contingency in a given year. This revised continuum is premised upon bringing together processes that have to date been poorly harmonised. A single assessment (the HRD) will involve both PSNP and humanitarian actors, and give rise to a single response plan and budget, which is then implemented with a shared monitoring and accountability system.

Table 8: The PSNP 4 caseload will include a budgeted annual sum for responding to transitory needs
	year 1	year 2	year 3	year 4	year 5
	2015/16	2016/17	2017/18	2018/19	2019/20
chronic caseload	7,139,000	7,703,000	8,267,000	8,267,000	8,267,000
transitory caseload	2,861,000	2,297,000	1,733,000	1,733,000	1,733,000
total PSNP caseload	10,000,000	10,000,000	10,000,000	10,000,000	10,000,000

PSNP 4 will build resilience to climate shocks not only through targeted transfers, environmental rehabilitation and climate-proofed local infrastructure, and provisions to respond to 1.7m people in transitory, seasonal food shortage; but also by building institutional capacity and plans which improve the Government’s capacity to anticipate, plan for and then respond quickly to shocks such as natural disasters or food price hikes. The programme will contribute to the production of woreda-level risk profiles and contingency plans; strengthening early warning and needs assessment and streamlining the process for triggering a response; and integrating PSNP transitory transfers and humanitarian transfers (with each other and with targeted supplementary feeding (TSF) and Community Management of Acute Malnutrition - CMAM).

The benefits obtained through DRM system-building activity is hard to monetise, but likely to be large. A more effective DRM system will deliver economic benefits both as losses averted through timely and effective early warning; and through long term risk reduction (the development of risk reduction plans to inform public works).

Finally, welfare gains through PSNP will result in aggregate gains in health and life expectancy through a variety of channels. The first is the effect of transfer receipt on more and better food and increased spending on health care (Kumar and Hoddinott 2013 p. 29). Additional benefits accrue to all those living in PSNP woredas through infrastructure created through PSNP public works which provides access to clean water, new health posts and roads that improve timely access to emergency health care (Berhane et al 2013 pp. 192-3). In addition to these income (transfer) and access (public works) benefits, PSNP 4 will link transfer beneficiaries to health and nutrition training and services, and acutely malnourished children to PSNP benefits. An accepted way of estimating and monetizing these aggregate effects is as disability-adjusted life years (DALYs), which represent years lived with ill-health and years lost through premature mortality, relative to a global standard (WHO 2014).

Table 9: Selected key benefits: national level

Form of impact	Measure	Projected impact of PSNP
Disaster risk management	Estimated savings from losses averted through (i) more timely and accurate early warning and (ii) risk reduction through public works	£39 m by 2020
Health	Reduction in Disability-Adjusted Life Years	10% reduction (£46.1 m) by 2020

#### 4. Global-level outcomes: climate change mitigation

Crude estimates suggest that PSNP 4 will sequester between 0.726 and 2.036 million tonnes of CO2e by 2021 (mid-point estimate of 1.381 m tonnes CO2e); and (assuming that no new enclosure occurs) between 2.42 and 4.07 m tonnes CO2e by 2025. In monetary terms, this sequestration can be valued at between $2.2 m and $6.1 m by 2020; and $7.3 and $12.2 m by 2025 (with a mid-point estimate of ($4.1m by 2020, at least $9.7 m by 2025).
#### 5. Value for money

Cost efficiency: administrative overhead and cost-to-transfer ratios

The value for money of PSNP 3 has compared well to international benchmarks. The most basic measure of cost-efficiency for a safety net programme is total cost-to-transfer ratio (TCTR). In PSNP, the TCTR in 2014/15 stood at 1.30 (i.e. it cost a total of 1.30 birr - 0.30 birr in non-transfer costs - to deliver one birr of transfers to a beneficiary household). An alternative way of expressing this is to say that in 2014/15, 77% of total programme costs were accounted for by money transferred to beneficiaries, and 23% by non-transfer costs (administrative, management, capital and capacity-building expenditures).

As an indicator of overall cost-efficiency, however, TCTR is an imperfect measure for a public works programme, and will underestimate the cost-efficiency of PSNP relative to a more simple transfer programme. In a straightforward transfer programme, all non-transfer expenditures are essentially overheads and can be classified as costs and compared to the transfer sums (the benefits). In a public works programme, however, the capital costs of public works are not simply administrative overhead: they generate separate outputs or benefits (e.g. environmental rehabilitation and new infrastructure), additional to the benefits generated by transfers to households. Similarly, the livelihood-enhancing expenditures of the HABP have generated additional outputs (gains in household income-generating capacity) which are more properly recorded on the benefit side of the ledger.

Removing the costs of public works and livelihoods from the calculation makes PSNP more directly comparable with other transfer programmes. By this measure, total costs to deliver one birr of cash transfer to a household have averaged 1.09 birr over the last five years: transfers to beneficiaries have accounted for between 89% and 94% of total safety net costs. This is in line with the 10% overhead figure regarded as the benchmark for cost-efficiency in a mature transfer programme; and compares well to other DFID-supported transfer programmes (see Annex 5). It was also the most efficient out of six public works programmes reviewed in White, Hodges and Greenslade (2013).

Total cost to transfer ratios will be slightly higher during PSNP 4 in comparison to PSNP 3. This is because PSNP 4 will invest heavily in capacity- and systems-building (areas in which PSNP 3 under-invested): these investments will increase the non-transfer share of total costs. Depending on which costs are considered as overhead, cost-to-transfer ratios over the next five years are likely to range between 1.16 and 1.36 (see Annex 5 for details of the calculations). These compare well to other programmes, including those funded by DFID.

Cost effectiveness and the net present value of public works investments

There are high rates of return associated with public works projects under PSNP 3. The three Public Works Impact Assessments have derived net present value (NPV) and economic benefit-cost ratios (BCRs) which were positive in all cases[11]. Based on these findings, we have estimated an overall average BCR of 4.42 over 25 years for public works that will be created under PSNP 4. On this basis, the 2020 net present value of public works created through PSNP 4 will be £292m, based on an investment of £195m invested over the next years (£39m each year). Annex 5 provides more detail on these calculations.
[11] M.A. Consulting (2009) found BCRs (using a 10% discount rate over a 25 year span) ranging from 1.5–6.5; GoE (2011) found BCRs ranging from 1.14–2.50 (both 10% and 15% discount rates were tested, both over 25 years); and Metafaria Consult (2013) found household-level BCRs ranging from just over 1 to just over 36 (using a discount rate of 15% over 25 years).

Value for money in choice of transfer modality: costs and benefits of cash, food and electronic transfers
While there are strong reasons to assume that cash transfers are under most circumstances more cost-efficient and effective than food transfers, it is unfortunately not possible to construct a direct comparison. The 2012 VfM assessment of PSNP concluded that while it is certain that cash transfers are cheaper to implement, the lack of transparency over food management costs (Government, donor and NGO) makes it is possible to say by how much (White and Ellis 2012); similarly, a more recent study on the VfM of food, cash and vouchers in humanitarian programmes in Ethiopia (Cabot-Venton, Bailey and Pongracz 2014). However, the 2014 study found that cash in most scenarios in Ethiopia is more cost efficient to deliver than in kind food transfers. In WFP pilot programming, cash was 25-30% less expensive than food aid. The World Bank estimates that the planned move to cash for 70% of clients (the equivalent of all highland areas) could lead to $22m in cumulative savings during PSNP 4 implementation. The Government’s cash first principle now looks even closer to being implemented with USAID having committed to move to $20m cash out of $100m per year from year 2 of the PSNP 4.
The study on the VfM of cash in emergencies also suggests that additional efficiency gains in cash could be made through the use of innovative transfer mechanisms and consolidated transfer platforms. Mechanisms that transfer direct to beneficiaries through electronic payments involving mobile phones or smartcards and which can be used by several programmes could improve the system greatly, but it is not clear what is feasible, or how much it would cost. Two pilots have been adopted to examine the potential for electronic payment of PSNP transfers, one with microfinance institutions and the other using mobile phone services. The benefits of using electronic payment systems can be even wider than within the social protection system by enabling financial services to be brought to previously ‘unbanked’ recipients.
Balancing cost efficiency and cost effectiveness: accounting for investments in capacity and systems

A key question for the future of support to social protection development and delivery is whether a singular focus on efficiency may undermine effectiveness. The National Audit Office (NAO) and Public Accounts Committee (PAC) reviews of DFID support to cash transfer programming identified the risk that minimising costs (which provides good measures of efficiency, in terms of ratios of inputs to outputs) may compromise the results that can be achieved (cost-effectiveness). This has been a concern in the implementation of PSNP. The recent (November 2014) Joint Review and Implementation Support (JRIS) mission noted multiple pressures on PSNP performance as a result of inadequate non-transfer budget allocations (DCT 2014)[12].
[12] These include an acute shortage of woreda administrative budget; low per diems which create disincentives for monitoring through field visits; discrepancies between allocations for woredas with the same caseloads due to the wage rate formula; high levels of staff turnover (and thus difficulties building and retaining capacity) due to low levels of wages and benefits for both permanent MoA staff (in comparison to staff in other sectors) and contract staff (DCT 2014).
Recognition of this dilemma underpins the significant investment that PSNP 4 will make in building institutional capacity and system integration. The ICT-based management information system, for example, will cost a relatively significant amount ($160m or 4.4% of total programme costs) but the benefits are expected to be significant, in terms of enhanced timeliness for transfer delivery, more accurate planning and budgeting, and greater control over expenditure and reduction in opportunities for mis-spending or corruption.
These benefits are expected to accrue to the wider national social protection system, and not just PSNP 4. For example, the Urban Social Safety Net Programme currently under design will consciously exclude a budget line on systems development, as it is planned to make use of PSNP systems. Other complementary programmes under the DRM, CRGE and National Nutrition Programme will also benefit from investments in PSNP systems, improving the level of service coherence and synergy for recipients. These programmes should be able to deliver a greater value in combination, as systems, than the sum of their parts. However, there appear to be few precedents or models with which to quantify these benefits and any cost-benefit analysis would face inevitable challenges in monetising benefits (White, Hodges, Greenslade (2013). DFID Ethiopia has volunteered PSNP 4 as a case study country for upcoming (2015) Policy Division research on how to measure and maximise the value for money of systems-building investments for social safety nets.
Similarly, higher budgeted costs associated with linking PSNP transfer recipients to other services should result in greater impact across a broader range of outcomes. Investment in linking the receipt of PSNP transfers to nutrition services, for example should have significant economic benefits. These are hard to estimate with accuracy: but the 2012 Copenhagen Consensus estimated that every $1 spent on reducing malnutrition has a least a $30 return. Similarly, estimates suggest that economic gains from increased productivity as a result of improved nutrition could exceed $5bn in Ethiopia by 2025 (MoH and USAID 2013).
Over the first year of implementation, DFID will commission a full VfM review of PSNP 4. This will seek to identify a small set of key VfM measures that can be incorporated in the DFID logframe and provide strategic oversight of trends and patterns on cost-efficiency and effectiveness, and allow us to identify areas in which we can pursue economies in costs and efficiencies in translating costs into results.

### Feasibility and risk management: comparison of Options 2 and 3

The differences between Options 2 and 3 are primarily to do with the relative advantages and disadvantages of the different partnerships and delivery channels that each Option involves, and in particular the implications for our ability to manage certain risks. Most of the risks to the DFID programme (described in full in the Management Case below) are not affected by the choice between Options 2 (PSNP funds channelled directly to MoFED) and 3 (PSNP funds channelled to MoFED via the multi-donor trust fund). The following list (and more detailed table in Annex 6) summarises the team’s assessment of that subset of risks which may be affected by the choice between Options 2 and 3.

Access to PSNP benefits is influenced by factors other than need (poverty / food insecurity) to include or exclude on the basis of perceived party loyalty. Annual disbursements to MoFED (Option 2) may provide marginally better flexibility for DFID to scale back or cancel in the case of borderline evidence of political manipulation. Acting unilaterally in the absence of a common donor position would however be a serious step: in practice, it is far more likely that if we felt the need to freeze disbursement, the other donors (including MDTF donors) would too.

Risk that PSNP implementation becomes linked to evidence of negative outcomes from GoE programmes such as resettlement. As above: Option 2 seems to offer marginally greater flexibility in the (unlikely) case that we felt the need to postpone or cancel releases but other donors wished to proceed.

Coordination failures amongst GoE entities constrain PSNP performance and outcomes; and retard the evolution of a functional, integrated national social protection system. The direct-to-MoFED channel (Option 2) would provide us with slightly more opportunity to re-allocate funds to MoLSA (or another institution), should we decide that this is necessary to compensate for particular capacity shortfalls beyond the MoA.

DFID (or the PSNP donors more widely) fail to allocate sufficient staff capacity to ensure adequate oversight of an increasingly large programme of work. Under Option 3, supporting the World Bank PSNP team (through the administration fee levied on DFID’s contribution to the MDTF) would strengthen the analytical and supervisory capacity available to the donor group, which would be helpful when restrictions on DFID’s total operating costs (TOC) make it hard for us to allocate staff time to the programme. However, increasing the funding we give directly to the Donor Coordination Team to boost DCT capacity would be a simpler and probably better solution.

Reforms to the continuum of response fail; the PSNP Federal contingency does not work as planned and / or coordination with the humanitarian system fails. Option 2 would seem to offer significantly greater flexibility. The need to make the continuum of response work (and so improve on the RFM experience under PSNP 3) is at present the one concern that is sufficiently important that we consider making it a programme-specific condition for continued full disbursement (to be reviewed in 2017/18). Retaining flexibility to scale back our later contributions (by 15%, proportionate to the Federal Contingency Budget share in the total PSNP budget) and re-allocate these sums to humanitarian channels makes Option 2 more attractive.

PSNP supports actions (livelihoods activities or public works) which result in environmental degradation or increase vulnerability to climate change. As above, there is perhaps some marginal advantage to Option 3: channelling resources through the MDTF, and paying £11 m to the Bank in overhead management fees, would expand the Bank’s resourcing for staff and analytical and advisory work on safeguards and maximising the PSNP contribution to climate change adaptation and mitigation (specialisms which they are technically well suited to perform). However, it seems that simply increasing the funding for DCT staffing (which can be achieved under either Option 2 or 3) is a more straightforward way to achieve the same ends.

There appears to be only minor, if any, difference between the options with regard to fiduciary risk. Initial consideration favoured Option 3 on the grounds that chanelling DFID funds through the World Bank trust fund might improve financial management and controls on fiduciary risk. In practice, however, the Bank provides financial supervision for all the donor funds to PSNP – both those that pass through the Trust Fund and those that are provided direct - that enter the pooled programme account in MoFED.

On the basis of this assessment, Option 2 appears to offer on balance a slightly better capacity for managing the range of risks facing the DFID programme. The most important difference is the increased flexibility that Option 2 provides for (carefully) setting conditions – particularly regarding the implementation of the Federal contingency - that would be essential to ensuring programme effectiveness (and justification for continued full DFID funding).

Identification of the preferred option

Option 1 (do nothing) is rejected on the grounds that it will entail higher levels of poverty, food insecurity and climate vulnerability in 2020 than under Options 2 or 3. The funds (£94 m over five years) that would be freed up for DFID Ethiopia to do other things by stopping DFID’s support to social protection and disaster risk management would be only a third of the funds that would be available to DFID under Options 2 and 3 (as the ICF commitment of £182 m for PSNP 4 would no longer be available); and to balance the country office portfolio and respond to higher levels of humanitarian need, DFID Ethiopia would need to find another instrument for poverty-targeted development assistance. At present, we do not see a credible alternative instrument that offers the kind of proven potential for large-scale impact that is available through PSNP 4 and associated systems building investments (Options 2 and 3).

In choosing between Options 2 and 3, there are only marginal differences (in favour of Option 2) with regard to developmental impact and VfM (criteria 1 through 5). The slight advantage in favour of Option 2 is that it involves no MDTF management fee (£11 m) and as a result there are slightly greater resources for PSNP implementation and correspondingly slightly larger benefits. Option 2 would also seem to provide greater flexibility for DFID to manage risks and adapt during programme implementation.

On the basis of the assessment above, it is recommended that DFID choose Option 2.

Summary comparison of costs and benefits

The table below summarises the expected PSNP4 benefits that could be monetised. To provide a direct comparison between costs and benefits explicitly attributable to DFID funding, the calculations of monetised benefits summarised in the previous pages are scaled down in this table to reflect DFID’s share of total funding.

Table 11: Overview of expected monetised benefits and costs (£m)

	£m
Summary of costs
1. PSNP programme costs - costs to DFID
Key instruments (lumpsum)	4.7
Capacity building	8.8
Transfers - Permanent Direct Support	27.5
Transfers - Public works and Temporary DS	123.8
Capital budget for public works	23.3
Contingency budgets	44.9
Livelihood capacity building	5.8
Livelihoods transfer	10.6
Evaluation and audit	0.4
Woreda Admin Budget	9.5
Regional and Federal management	6.9
2. Support to Donor Coordination Team	5.0
3. Support to PSNP capacity building	2.5
4. Support to other social protection / DRM systems-building	2.2
5. Costs to beneficiaries (birr)
enrolment-associated costs	7.8
collection costs	0.1
total costs	283.9

Summary of benefits
1. Household-level benefits
increase in household consumption	121.4
increase in household assets	58.3
increase in health and life expectancy (valued as DALYs)	46.1
2. Community-level benefits
public works investments (NPV over 5 years)	34.2
local economic multiplier effect	112.9
3. National-level benefits
DRM systems	4.6
4. Global benefits
carbon sequestration	0.5
total benefits	377.9

Assumptions:
a PSNP costs to beneficiaries and all PSNP benefits attributable to DFID support are calculated at 11% of programme totals (reflecting DFID funds as share of total five-year PSNP budget)
b Transfers average 1,070 birr pc pa; 80% of transfers go to the poor; 75% of transfer is consumed (and 25% invested)
c Net present value of five years of public works estimated at $449 in 2020.
d Local economic multiplier of 1.84 (rural Tigray estimate, adjusting for credit, capital and other market constraints)
e DRM benefits estimated conservatively at $20 m p.a. (combined effect of losses averted through early warning and long-term risk reduction through woreda risk profiles and risk reduction planning)
f Base case scenario of 726,605 tonnes CO2e sequestered by 2020; valued at $3 / tonne.

Based on the relatively crude monetisation of expected benefits, the expected benefits of the proposed DFID support to social protection and DRM significantly outweigh programme costs.

Commercial Case

The theory of change for the preferred option aims to achieve large-scale impact through a mixed approach which involves (i) sustaining successful elements and introducing systems-building innovations within a large, Government-implemented programme (PSNP 4); and (ii) complementing this with strategic analysis, advice and capacity building activities to develop key elements of the social protection system beyond the PSNP. This implies that DFID support will involve both indirect procurement (the majority of total spending, related to the implementation of PSNP 4, managed by the Government of Ethiopia or the World Bank); and a small quantity of direct procurement, primarily of consultancy services for research or technical assistance, managed by DFID.

Indirect procurement

For PSNP implementation, DFID funds transferred to the MoFED are passed on to the MoA and the Regions. (See ‘Financial case’ below for the flow of funds.) Procedures governing procurement of goods and services for the programme are laid out in the PSNP Procurement Manual and World Bank PAD; and summarised in chapter 14 of the Programme Implementation Manual (PIM)[13]. Referencing the IDA Articles of Agreement and World Bank guidelines (which apply to all programmes funds, including those from DFID), these documents lay out the principles of good procurement: that funds should only be used for the intended purposes, are only made available when needed, and need to be managed so as to maximise economy, efficiency, effectiveness, transparency and fair competition[14].
[13] The PIM lists what may be procured under the programme. This includes: (i) goods (e.g. food grains and pulses, vehicles, office furniture and equipment, generators, IT equipment, construction materials for public works, agricultural inputs); (ii) small works (e.g. semi-skilled labour for the construction of farmer training centres, school rooms, road crossings, rural water supply facilities, etc.); (iii) non-consulting services (e.g. transport); (iv) consulting services (e.g. technical assistance, studies, reviews, project audits, impact evaluations, public work reviews); and (v) training and workshops at different levels (MoA 2014 chapter 14). See also World Bank (2014) pp. 74-86 for the PAD provisions regarding procurement.
[14] In addition to the Articles, the PIM references World Bank (2011) Guidelines: procurement under IBRD loans and IDA credits. (January 2011); World Bank (2011) Guidelines: selection and employment of consultants by World Bank borrowers. (January 2011); World Bank (2011) Guidelines on preventing and combatting fraud and corruption in projects financed by IBRD loans and IDA credits and grants. (October 15 2006, revised January 2011); and the provisions of the PSNP Legal Agreement (World Bank 2014 p. 14-2).
### Rationale for the use of Government and World Bank procurement and delivery systems

Government procurement capacity is under-developed, but improving. The World Bank Country Procurement Assessment Review (CPAR) at Federal level found procurement systems to be acceptable overall when benchmarked against international good practice. The legal framework for public procurement has improved considerably in the last few years: however, capacity remains a significant challenge at all levels. The Federal Public Procurement Agency (FPPA) seeks to improve procurement by strengthening the capacity of staff and oversight functions. The CPAR did however identify a gap in procurement audit capacity as the Auditor General function is not equipped to focus specifically on procurement. PSNP 4 design documents lay out how the programme will contribute to the broader agenda of building FM and procurement capacity in Ethiopia, particularly through the capacity- and systems-building components (outputs 1 and 5 respectively).

The use of GoE and World Bank systems to manage the bulk of programme funds is seen as offering the optimal balance between costs, benefits and risk. The overall fiduciary risk of using GoE procurement systems has been assessed as moderate, with a positive trajectory of change and a credible programme of financial management reform currently in place (see Financial Case, below). Financial aid to Government and use of indirect procurement incurs lower transaction and overhead costs than alternatives. In these circumstances, it is desirable to use and in the process strengthen GoE systems and existing joint governance structure (an approach that is in line with the corporate DFID commitment to use country FM and procurement systems wherever possible in the interest of aid effectiveness). The proposed approach to delivery through GoE channels helps to consolidate the development of sub-national implementation capacity and accountability.

### PSNP procurement processes and thresholds

Under PSNP 4, the thresholds for different procurement processes have been revised upwards, to reflect the effect of inflation since these thresholds were set out for PSNP 3. The methods to be used for procurement of different types of inputs – including consultancies - and contract values are summarised in Annex 7. There are also a number of special cases. The main ones are as follows.
- For the procurement of food grains, alternative procurement methods (e.g. the use of framework contracts or pre-qualified suppliers for a defined period) will be explored: the Government will identify the best strategy and obtain the Bank’s agreement.
- Improved seeds and fertiliser will be procured locally through direct contracting from cooperatives or producers unions. (The structure of agricultural input markets in Ethiopia – in which Government-owned enterprises and farmers’ unions and co-operatives are often the only suppliers – often makes it impossible to follow a competitive process at the local level.)

Other changes from PSNP3 to PSNP 4 include improvements in capacity and clarification (extension) of procurement responsibilities. Dedicated PSNP procurement staff are to be introduced within the Woreda Agricultural Offices; and procurement responsibilities revised to (i) incorporate the roles and responsibilities of new implementing agencies and (ii) reflect the integration of procurement related to the livelihood component, which now falls under the overall PSNP procurement plan.

PSNP procurement plans are agreed between the World Bank and each GoE implementing agency (Federal, Regional and woreda) and updated at least annually. These plans are legal documents intended to guide the timely initiation, monitoring and reporting of procurement activities, and cover the methods that are to be used for procurement or consultant selection; the need for pre-qualification and prior review; estimated costs; and timeframes. Funds for procurement activities will be released at the start of each programme / Government fiscal year. At the centre, FSCD will prepare and submit to the World Bank a quarterly procurement performance report covering Federal and Regional procurement activity. The Government will select and appoint a procurement auditor for the Programme, acceptable to the World Bank, who will produce an annual independent procurement audit, to be submitted within 60 days of the end of the fiscal year. The World Bank will carry out at least one post review of procurement actions each year.

Incremental operating costs will be procured using GoE administrative procedures, acceptable to the World Bank and verified by Task Team Leaders and FM Specialists.

Within the programme, the scope for transformative gains in efficiency and value for money through better commercial practice is relatively modest as a share of total programme costs, but large in absolute terms. The bulk of programme spending (£1,725m or 72%) is passed directly to beneficiaries as transfers. Some of this cost is for food transfers, with the potential to make savings through more competitive or better-timed procurement; most however is simply cash passed down from Federal to Regional to woreda level, to be passed on to beneficiaries. If better commercial practice is to lead to cost savings it will be in relationship to the procurement of goods and services relating to the design and implementation of key administrative instruments such as the management information system, public works database, or proxy means test (total cost £$40m or 2% of total operational budget); capacity building (£64m or 3%); the capital inputs for public works activities ($195m or 8%); livelihood capacity building (£49m or 2%); or management and operations work (£142m or 20%). DFID will discuss with the Government and other donors the possibility of contracting (through the DCT or through the DFID-managed funds) a Commercial Advisor to work with the two DCT Procurement Officers to assess supply chains within the programme and advice the Government on how these could be managed to improve value for money.

In addition to funds disbursed to and then managed by the Government, some DFID funds (proposed £4m) will be provided to support the work of the DCT. These funds will be managed in accordance with the same World Bank procurement rules described above. DFID Ethiopia with support from a UK-based Commercial Advisor is working with FM specialists in the World Bank Ethiopia Country Office to raise the commercial focus of the Bank’s procurement work over time.

Direct procurement

DFID will retain a budget line of £2.2m for goods and services to be contracted and managed directly. This will provide us with flexibility to support (i) PSNP-related analytical and technical assistance / advisory services which are additional to those managed by the DCT and / or (ii) similar inputs related to non-PSNP elements of social protection system development

These services will be contracted through competitive bidding mechanisms following DFID procurement guidelines, and managed in close consultation with the Commercial Advisor. Bids will be assessed on both cost and value for money and quality).

Competition and value for money will be maximised, in individual contracts and in shaping the market over time, through early engagement with a broad range of suppliers. The PSNP DFID team already have a good knowledge of the national and international markets for many of the technical services that are likely to be required; and will draw on the networks available to us– to ensure that we obtain access to the full range of potential suppliers, and are informed as to their relative capabilities and delivery record.

We anticipate that most direct procurement managed by DFID will be for relatively small, discrete pieces of work completed over a year or less. Where DFID does procure services which are large, complex and / or delivered over a long timeframe, we will build in performance criteria, formal reviews and break-points to ensure a focus on delivery and provide options for contract termination if necessary. Wherever possible, contracts will be structured around output-based payments to ensure timely delivery of high-quality work.

The team will consider the potential for contracting partnerships between international and Ethiopian-based suppliers. For individual contracts, this approach often provides the optimal (and cost-effective) combination of (i) high-level technical skills and relevant knowledge of current international practice with (ii) detailed knowledge of the programme and Ethiopian contextual factors.

Key cost drivers under PSNP 4

As under PSNP3, the main cost element in PSNP 4 is the total sum paid to beneficiaries as transfers. The determinants of this sum are the programme size and transfer levels – that is, (i) the number of recipients (caseload); (ii) the size of the transfers provided to households each month; and (iii) the number of transfers paid per year. All three will rise under PSNP 4: the programme will reach more people, in more woredas, with a higher monthly transfer value and (for the permanent direct support clients) 12 rather than six months of transfers p.a.. PSNP 4 also introduces a one-off lumpsum livelihood transfer for the very poorest households. This increase in transfer costs is the main driver of the increase in total programme cost.

However, the PSNP 4 also includes an increased share for non-transfer costs, reflecting activities and investments that have not been included in previous phases of the PSNP. Many of these fall under Output 1. The costs of these new systems- and capacity-building activities are budgeted at $161 m over five years (4.4% of the total budget). While these are large costs in absolute terms - building and running a MIS and single registry is not cheap (Barcar and Chirchir 2014) and, as with all ICT projects, are at risk of time and cost over-runs (see Annex 8) – they are relatively small in relation to the size of the PSNP, and should lead to economies of scale and efficiency gains as the programme moves from manual data entry to computerised entry[15]. Table 12 outlines the costs for ‘key instruments’ under Output 1, which DFID is proposing to support with £4.7m.
[15] The World Bank reviewed data collection costs involved in the production of national beneficiary registries, and concluded that compared to many other African countries (e.g. Lesotho), Ethiopia is likely to have significantly lower costs. This is because (i) the data collection will be carried out by current Government employees (and so will not entail additional salary costs); and (ii) these enumerators and community mobilisers are resident in the community in which they work, and so incur much lower subsistence and accommodation.

Table 12: PSNP 4 investments in key instruments for system- and capacity-building (£m)

instrument	year 1	year 2	year 3	year 4	year 5	total
	2015/16	2016/17	2017/18	2018/19	2019/20
National registry	1.3	2.6	4.5	4.5	0.0	13.0
Mapped database of public works	0.8	-	-	-	-	0.8
Public works watershed tracking system	-	1.6	1.6	-	-	3.1
Support for early warning system improvements	1.3	6.5	3.2	1.3	0.6	13.0
Support for woreda risk profiling and contingency planning	1.3	1.9	1.3	1.3	-	5.8
DRM awareness	0.4	0.4	0.4	0.4	0.4	1.9
Other (FM and management information systems)	0.6	0.6	0.6	0.6	-	2.6
total	5.7	13.6	11.7	8.2	1.0	40.3

Source: World Bank 2014 p. 183. Dollar values converted to pounds sterling at £1 = $1.53984.

Financial Case

Estimated costs, recipients and sources of financing

PSNP will cost £276m over five years (2015 to 2020). The majority of this expenditure will be on the costs for the design and implementation of PSNP-4, including the systems-building activities included in the PSNP workplan. DFID funds transferred to the Government will be deposited in the pooled account, and as such the allocation to different PSNP programme activities will follow the shares planned out in the five-year budget for the programme that is captured in the Design Document and the World Bank PAD.

Table 13: Profile and composition of DFID funding (£m)

Budget Heading	year 1	year 2	year 3	year 4	year 5	Total
	2015/16	2016/17	2017/18	2018/19	2019/20
Output 1: Priority instruments and tools are in place to support an effective system for social protection and disaster risk management
Key instruments (lumpsum)	0.9	1.5	1.3	0.9	0.1	4.7
Capacity building	5.4	0.8	0.8	0.8	0.8	8.8
Output 2 Appropriate, timely and accessible transfers are received by male and female clients & Output 3 Sustainable community assets are built up and access to social services is enhanced
Transfers - Permanent Direct Support	6.8	4.9	5.3	5.3	5.3	27.5
Transfers - Public works and Temporary DS	30.4	22.1	23.8	23.8	23.8	123.8
Capital budget for public works	6.3	4.3	4.3	4.3	4.3	23.3
Contingency budgets	16.2	8.8	6.6	6.6	6.6	44.9
Output 4: Clients’ livelihood opportunities are facilitated through three pathways: crop and livestock, off-farm income generation, and employment
Livelihood capacity building	1.6	1.1	1.1	1.1	1.1	5.8
Livelihoods transfer	3.1	2.8	3.0	0.9	0.9	10.6
Output 5: Effective management and operational processes are in place to manage the programme
Evaluation and audit	0.2	0.0	0.1	0.0	0.1	0.4
Woreda Admin Budget	2.2	1.7	1.9	1.9	1.9	9.5
Regional and Federal management	1.9	1.3	1.3	1.3	1.3	6.9
total PSNP programme costs	74.9	49.3	49.3	46.8	46.1	266.3
Third party: transferred to World Bank multi-donor partnership trust fund
DCT	3.0	0.5	0.5	0.5	0.5	5.0
capacity-building	1.5	0.25	0.25	0.25	0.25	2.5
Managed by DFID directly
DFID	0.6	0.4	0.4	0.4	0.4	2.2
total	80.0	50.4	50.5	47.9	47.2	276.0

Reflecting the allocation of the majority of the proposed DFID funds to PSNP programme costs, the main recipient of DFID funding will be the GoE (Ministries and agencies at the Federal level and their corresponding line structures at Regional, zonal (where zones exist) and woreda levels). The recipient of the largest sums will be MoA; smaller sums will be allocated to MoLSA, the Federal Cooperative Agency (FCA) and the Federal Micro and Small Enterprise Development Agency (FEMSEDA).

Compared to our support to the previous five years of PSNP, the proposed DFID contribution to PSNP 4 will increase slightly (by 4%) in absolute terms, but fall slightly as a share of total current financing commitments (see Annex 9 for a summary of financing sources for PSNP 4). It will fall more as a share of the total five-year budget, not all of which is currently covered by Government or donor commitments). At currently prevailing dollar-sterling exchange rates, DFID’s budgeted support to PSNP 4 (£266.3 m) would amount to 11% of total programme costs (cash plus GoE operational budget). However, the programme has yet to be fully funded: the indicative financial contributions summarised in Table 33 leave a financing gap in the outer years of just over $1bn.

A sum of £7.5m will be allocated to and managed by the World Bank. Of this, £5 m will be provided to the trust fund that supports the operation of the DCT, contributing 20% annually to DCT operating costs. Referred to as the ‘partnership trust fund’ and managed by the World Bank, this will support the operating costs of DCT staff (salary and non-salary payroll costs, travel, etc.), non-salary operating costs, and research and consultancies in support of PSNP. This sum is justified, given the need to reconcile the increased complexity of the programme with stable or declining DFID staff time available for monitoring and managing the programme. Another £2.5m will support a new capacity-building technical assistance facility.

Finally, DFID will retain some funds (£2.2m) to support DFID-managed contracted activities in support of social protection system development. This will give us the flexibility to support any analytical, research, advisory or technical assistance consultancies that cannot be supported through the DCT.

Following agreement reached in 2014, two-thirds (£176.2m) of DFID’s total funding for PSNP 4 and related social protection systems building will be financed by the UK International Climate Facility (ICF). The bulk of this ICF finance will be used to support regular and contingency transfers and the capital costs of public works. The remaining third of the total budget (£99.7m) will be financed from the DFID Ethiopia Country Office budget. Table 14 summarises the allocation of total costs over the five year period by (i) recipient and financing instrument and (ii) source of DFID funding (Country Office or ICF). Table 15 presents the expected profile of DFID spend, and the estimated annual allocation of ICF and Country Office funds.

Table 14: Total 2015-2020 DFID spend by recipient and funding source (Country Office budget or ICF)

Table 15 Profile of spend of DFID finance, 2015/16 through 2019/20 (£m)

Budget Heading	EFY 08	EFY 09	EFY 10	EFY 11	EFY 12	Total
	2015/16	2016/17	2017/18	2018/19	2019/20
CO	30.9	18.0	18.5	16.5	15.9	99.7
ICF	49.1	32.4	32.0	31.4	31.3	176.2
total DFID	80.0	50.4	50.5	47.9	47.2	276.0

Depending on how inclusive a deinfition is used, between 10% and 47% of total DFID spend could be classified as capital spending (CDEL). These calculations, and the ARIES sector codes under which spending will be reported in DFID, are summarised in Annex 9.

DFID will release funds according to the profile presented in Table 35 in annual disbursements. The timing of these disbursements will be discussed and agreed with the Government, the World Bank and the DCT; but are likely to fall in September of each year, beginning in September 2015.

Flow of funds

Under the preferred design option (option 2), DFID funds for PSNP are transferred directly to MoFED (Figure 5). As with other DFID financial aid programmes, the money will be disbursed to a segregated designated foreign currency account at the National Bank of Ethiopia. From here, funds are transferred to the pooled programme birr account under the Channel One Programme Coordination Unit (COPCU). The pooled account combines DFID funds with those from other PSNP donors and the Government. Donors can only make transfers into the MoFED account once they have received satisfactory Interim Financial Reports (IFR) from MoFED. The full process of flow of funds (in nine steps) and financial reporting (five steps) is described in detail in the PIM (pp. 12-14 through 12-17).

World Bank
IDA funds
DFID
Irish
Aid
PSNP 4 MDTF
Separate foreign currency bank accounts
in the National Bank of Ethiopia
GoE domestic finance
Pooled birr account in MoFED
Federal MoA
(including Federal contingency)
MoLSA
Other donors
UNICEF
Danidash
Aid
Sida
RNE
Aid
DFATD
USAID
EC
WFP

regioasMoA
Woreda WAO
Transfers to beneficiaries and capital costs of public works
WoLSA
public works and temporary direct support
Local suppliers
permanent direct
support
Woreda contingency
Livelihood
transfer

BoFEDs
Federal
MoLSA
Regional
BoLSA
Woreda
WoLSA
WoFEDs

Figure 5: Flow of funds in PSNP 4

Light arrows represent flow of funds.
Dark arrows represent reporting.

Source: MoA (2014) PIM p. 12-14; sizing of funds based on DFID staff calculations.
MoLSA
Financial management and fiduciary risk

### Assessment of national Financial Management systems

Fiduciary risk in general, and corruption risk in particular, is considered lower in Ethiopia than in other countries at a similar stage of development. The 2010 Public Expenditure and Financial Accountability (PEFA) review concluded that the public financial management (PFM) systems and processes were functioning well by international standards, and rated Ethiopia’s performance as third best in Africa. Several weaknesses were identified, but the conclusion was that these areas are being addressed adequately by the Government’s Expenditure Management and Control Programme.

Similarly, the DFID 2010 Fiduciary Risk Assessment (FRA) assessed the overall fiduciary risk as moderate. This was based on substantial risks arising from weaknesses in timeliness of annual financial statements and legislative scrutiny of external audit reports, balanced with a strong internal control framework. A range of accountability systems are in place in the sectors, which are particularly strong on the supply side (e.g. internal audit systems and vertical accountability to the various levels of the administration). The assessment concluded that “there is a reasonable confidence that DFID’s money would be used by the Government of Ethiopia for the intended programmes and projects.” This assessment is currently being updated with a new FRA now available in draft (Cant and Belew 2015).

### Programme-level financial management systems in PSNP

PSNP financial management has improved considerably over time; but significant weaknesses still remain (World Bank 2014 p. 24). Financial reports are now largely on time and of good quality and the Annual Audits for 2012/13 and 2013/14 were both unqualified, for the first time in the nine years of implementation. However, both the Audits and the quarterly Interim Financial Reports (IFR) continue to note recurrent problems (in particular, excessive cash-on-hand balances and long-outstanding advances and payables). These problems are rooted in serious difficulties in building and retaining FM capacity, due in particular to the difficulty of recruiting and retaining accountants for posting in remote woredas.

Arrangements for PSNP financial management have been assessed recently in both a DCT-managed FM assessment (unnamed 2014); and in a DFID-commissioned programme-level FRA, currently in draft (Martin and Mussa 2015). Budget utilisation has improved, but is still poor, with significant overspend and (more often) underspend against the annual budget (Figure 6). This reflects on weaknesses in the process for plan and budget formulation and delays in budget transfer between regions (which also results in low levels of expenditure in the first quarter of each year, and high expenditure in the last quarter). Accounting codes used in preparation of the programme budget are not used to record expenditures, making it hard to report on spending below summary levels; and there is a need for MoA to assume greater responsibility for effective financial management (which will make it easier to integrate PSNP more fully into Ministry-wide policy-based budgeting). The fact that the annual PSNP budget has only been ‘proclaimed’ at the Federal level arguably weakens the control, accountability and oversight mechanisms which the Regional governments can exert over programme spending.

The draft DFID FRA (which combines a backward look at PSNP 3 and a forward look at PSNP 4) rates both fiduciary risk and corruption risk as ‘moderate’ (Martin and Mussa 2015 pp. 5). This is similar to the World Bank PAD for PSNP 4, which rates capacity risk as 'high' and fiduciary risk as ‘substantial’ (although adequate to meet IDA requirements for Bank financing under OP/BP 1.0: World Bank 2014b pp. 24, 98-9). Both the FRA and PAD identify structural and capacity issues (including inadequate regional supervisory powers over PSNP spending; high turnover of woreda level accountants and cashiers; high levels of between-year and between-region variations in levels of budget utilisation; poor follow up on recurrent audit findings), especially in remote lowland woredas. Audits report ineligible expenditures and long-outstanding payments, which have resulted in reimbursements to the programme account. Food management remains a concern: inadequate transparency and accountability create potential for mismanagement and abuse (although the World Bank notes that such reports ‘tend to be isolated and have involved only a tiny fraction of programme resources’: World Bank 2015c p. 7).
Figure 6: Budget utilisation improved to 2012/13, but deteriorated again in 2013/14
Deviation of actual expenditure from budget, by component (negative = underspend, positive = overspend)

Source: budget and spend data from IFRs; compiled for DFID by DCT

However, financial management and control of fiduciary risk has improved over time. The programme has moved from Excel to IBEX accounting software; and the timeliness and quality of IFRs has improved. The Food Management Improvement Programme has identified and begun to address weakness in commodity management. The FRA notes that 'steady progress has been made in strengthening financial management of PSNP III' and 'there appears to be a credible programme of financial management reforms planned for PSNP IV'. These include significant improvement in PSNP financial management since 2009 (in terms of budget discipline; the timeliness of fund transfers; the timeliness and fullness of quarterly IFRs and Annual Audits) and the return of unqualified audits for the last two years. PSNP 4 design documents commit the Government to a number of changes (and commit significant resources to capacity-building) to ensure further improvements in financial and commodity management.

PSNP 4 introduces a number of changes intended to improve financial management practices and outcomes. While the budget will still only be proclaimed at the Federal level, this proclamation will now include a detailed breakdown by Region and sub-component (to facilitate monitoring of expenditures against the budget); and an MoU signed between MoFED and the Regional Governments will improve the scope for scrutiny by the Regions’ legislative oversight bodies. IBEX accountancy software will be rolled out to those areas where it has not been used to date, replacing Excel-based reporting. Internal control and supervisory roles at each level will be strengthened with the recruitment of additional staff and tailored capacity development for COPCU (World Bank 2014 p. 24).

The PSNP budget will become more detailed, with the introduction of a new code in the chart of accounts for transfers financed through the contingency budgets. New formulae for calculating the administrative, capital and contingency budgets at woreda level and management budgets at Regional and Federal level should better match budgets to needs, and avoid cases where implementation has been constrained because of inadequate provision for administrative and management costs (MoA 2014d p. 12-1). The PIM lays out the allowable expenditures and spending ceilings for different budget items at each level; the basis for cashflow forecasting; the process by which budgets are prepared and consolidated; and the various forms of financial report required, with the timeframes allowed for submission of each of these. As with procurement processes, the World Bank’s financial management rules and procedures apply to all programme funds, not just those of the Bank itself (IDA) or those other donors’ funds managed by the Bank through the programme Multi-Donor Trust Fund (MDTF).
Under PSNP 3, the Government has shown its commitment to refund to the donors’ accounts ineligible expenditures identified in the Audits. However, this has often occurred with a considerable delay, as Regions attempt to find and submit supporting documentation in response to Audit findings of inadequately-documented expenditures[16].
[16] Thus, for example, ineligible expenditures identified by the 2011 audit were refunded to the donors in 2013.

### Management of food resources

While there has been considerable progress in the financial management of PSNP over recent years, the management of commodity (food) resources remains a more serious problem. The timeliness of delivery of PSNP food transfers has improved, but continues to be slower than that of cash transfers and is generally not achieving the agreed performance standards; and food losses (particularly in the lowland regions) concern both Government and donors. The food management system – which is also used for the distribution of humanitarian food aid - has made some progress but as of 2015, particularly in recent years with the DFID-funded Food Management Improvement Programme (FMIP), but is still not yet well integrated. Information on dispatches, receipts and stocks is hard to match, making monitoring and accountability weak. While the contracting of food transport has improved, the PSNP supply chain continues to suffer from a lack of storage facilities. It is hard to track the movement of food once it is dispatched from the main warehouses; and internal control mechanisms at the level of the woreda and Food Distribution Points (FDP) level are weak (MoA 2014a p. 57; MoA 2014 c p. 73).

Some of the delays in food delivery are due to poor communication between FSCD and EWRD. FSCD has only limited understanding of operational aspects of food delivery and management (in particular, the lead times required for delivery of food); while the EWRD is unfamiliar with key aspects of the PSNP (and so fails to anticipate PSNP requirements, despite their predictable nature). The creation of intermediate regional hubs in recent years has improved accountability but capacity is weak with unclear responsibility for food management, procedures which are not fully understood or followed, and an absence of a capacity building budget for food management.

Continued improvement in the food management system is thus a major focus for PSNP 4. Building on the diagnosis and recommendations of the FMIP, PSNP 4 will strengthen the MoA’s ability to account for food resources by establishing clear ownership, accountability and reporting mechanisms. This will entail building the capacity of the logistics case team within DRMFSS to manage humanitarian as well as safety net food resources (with spillover benefits for the DRM system more broadly). Accountability will be strengthened through creation of a Food Management Unit within DRMFSS and appointment of Food Management Focal Points within the Regions. Communications on disbursements and receipts will be improved, along with the system for addressing food losses, which will be designed to ensure firstly that beneficiaries receive their full entitlements on time, and secondly that MoA will reimburse the Programme account for food losses[17]. The Programme will adopt the tools developed by FMIP, mainstreaming the use of the Commodity Allocation and Tracking System (CATS) for timely quarterly reporting and ensuring that the new Commodity (and Food Management) Procedure Manuals are available, understood, and properly followed (MoA 2014c pp. 76-7; MoA 2014d Chapter 13).
[17] Losses due to moisture and infestations will be borne by the programme; losses due to misappropriation and mismanagement will be covered by the Government, by claiming from the defaulters (MoA 2014c p. 77).

### Asset management

The value of assets purchased under PSNP, while small as a share of the overall programme budget, is nevertheless large in absolute terms. Programme operations necessitate a large fleet of vehicles and considerable amounts of investment in office equipment, including ICT equipment. To date, the management of these programme assets has not been very systematic, which has contributed to broader problems in developing and retaining implementation capacity.

Drawing on the physical asset management guidelines developed by the Safety Net Support Facility (SNSF) and linking responsibility for PSNP assets to existing GoE policies[18], PSNP 4 now dedicates a chapter in the PIM to physical asset management. This establishes the responsibilities of each implementing unit for the assets under their control, including planning for needs, procurement, effective operations and maintenance, periodic assessment and revaluation of assets, and disposal. Offices are responsible for ensuring that ownership certificates are up to date; there is a register of fixed assets and an annual physical inventory; vehicles are used effectively (including through pooling) and driven and maintained to ensure their longevity; and assets are disposed of through the fixed asset management system (MoA 2014d Chapter 15).
[18] The administrative regulations covering the responsible management of PSNP programme assets include the Government-Owned Fixed Asset Management Manual (GOFAMM), the MoFED Vehicle Utilisation and Management Directive, the Ethiopian Transport Authority and the PSNP PIM (World Bank 2014d p. 15-1).

Management Case

Management arrangements

To a significant degree, the management arrangements for PSNP are a continuation of those that have been used for PSNP 3. After ten years of implementation, these arrangements work reasonably well; and DFID, the Government and other donor partners now have a good sense of what is needed to address areas of weakness.
### DFID management

Within DFID Ethiopia, PSNP 4 will be managed by the Livelihoods and Humanitarian Team (LHT). A senior advisor (currently a social development advisor) will serve as the Senior Responsible Owner (SRO) for the programme. The SRO will be supported by a second advisor (currently a livelihoods advisor) and Programme Officer (who will monitor and manage financial and contractual issues under the SRO’s direction). The team will draw on other DFID staff (within the Ethiopia office and beyond) as and when necessary to meet particular needs. If necessary, the team will use some of the £2.2m DFID-managed budget to recruit a programme-funded advisor, possibly to sit within MOLSA and support the elaboration of a costed social protection strategy and capacity development plan.

The SRO will report to the LHT Team Leader and work with team members responsible for DFID humanitarian and nutrition programmes to these linkages within the PSNP. Any concerns that cannot be resolved at a team level will be escalated to the Deputy Head or Head of Office. DFID Annual Reviews, to be finalised in September each year, and revisions to the Programme Delivery Plan (conducted at a minimum in March and September each year) will provide opportunities to review the partnership and DFID’s continued engagement. A formal review of progress and decision point on continued support will be scheduled for mid-2018, following the Mid-Term Review of PSNP 4. In keeping with the DWG code of conduct and global principles of donor harmonisation and alignment, DFID will seek to resolve concerns firstly by raising them within the DWG and securing consensus on a joint approach, which will then be taken to Government by the Donor Chair.

DFID is scheduled to take the DWG Chair in January 2016, six months into the period of PSNP 4 implementation. As such, DFID will engage in meetings with Government on a regular basis as either the Donor Chair or Deputy Chair from October 2015 through to September 2016.

### Government structures

There will be some significant changes as well as continuity. Reflecting the expanded size and ambition of the next phase, the management structures for PSNP 4 will be more complex than for PSNP 3. The shift from a programme to a systems approach and the framing of PSNP 4 in relation to national policies (for social protection, DRM, CRGE and nutrition) entails significant investment in effective coordination structures. Figure 7 summarises management structures at the Federal level; Annex 10 spells out the institutional roles and relationships in more detail[19].
[19] Annex 10 spells these out GoE institutional responsibilities in more detail.

To achieve success, implementation support structures will need to be strengthened. The relatively ‘light’ structures employed by PSNP 3 were not always enough to provide oversight and direction to different components and specialisms. While the Disaster Risk Management and Food Security Sector (DRMFSS) had overall responsibility for programme management, technical experts who were tasked to support PSNP (by providing strategic direction to public works and HABP) but who sat in other MoA Directorates (NRMD and AED, respectively) often faced competing demands on their time from their parent Directorates. PSNP 4 attempts to address this fragmentation by appointing Public Works and Livelihoods Focal Points within DRMFSS (specifically, within FSCD) to coordinate with, respectively, the Public Works Implementation Unit in NRMD, and the Livelihoods Implementation Unit within AED. FSCD’s oversight and coordination role will also be strengthened with the addition of a Programme Management Advisor and Food Management Specialist (and other technical specialists as needed). Within the MoA, the incorporation of livelihood support activities within the overall PSNP and the effort to ensure complementarity between public works and household livelihoods strategies will need to be reflected in much closer integration between Food Security, Agricultural Extension and Natural Resource Management Directorates.
Figure 7: PSNP 4 coordination and management arrangements – Federal level

Minister of Agriculture
MoA

PSNP Joint Strategic Oversight Committee
Chair: MoA State Minister for DRMFSS
Co-Chair: State Minister for MoLSA
Members: Directors from MoA (FSCD, EWRD, NRMD, AED), MoFED (COPCU), FEMSEDA, MoLSA, FCA, MoWCYA; Heads of Regional BoA; donor representatives

Food Security Coordination Directorate (FSCD)

Rural Economic Development and Food Security (RED&FS) committees

Coordination and Management Committee
Chair: Director of FSCD
Co-chair: DWG donor chair
Members: Directors (MoA, MoFED, MoLSA, MoH); donors; DCT

Joint Technical Committees (JTC)

Systems Development JTC
Chairs: MoLSA and FSCD
Secretary: DCT
Transfers and Resource Management JTC
Chairs: COPCU, FSCD and EWRD
Secretary: DCT
Public Works JTC
Chairs: NRMD
Secretary: DCT
Livelihoods JTC
Chairs: AED, Livestock Development Directorate, FSCD
Secretary: DCT

Pastoral Task Force
Joint Food Management Task Force
Joint Financial Management Task Force
Joint Social Development Task Force

Nutrition Task Force

Source: MoA (2014) p. 18-6

New Ministries will need to become actively engaged in PSNP planning, management and reporting. In particular, capacity will be need to be built in MoLSA and its Regional and woreda line structures so that over the next five years MoLSA can assume responsibility for the permanent Direct Support beneficiaries.

Regional PSNP annual plans and budgets are approved by Regional Cabinets. Implementation of the programme is supervised by the Regional Food Security Steering Committee, chaired by the Regional President or his delegate; while the Head of Regional Bureau of Agriculture (BOA) is responsible for the management of PSNP and chairs the Regional Food Security Task Force (RFSTF). Three Technical Committees (Transfers and Resource Management, Public Works and Livelihoods) report to the RFSTF. Regional Food Security is responsible for day-to-day coordination of the programme, including the timely delivery of resources to clients. At a sub-national level, pastoral areas will require particular attention. The Design Document and PIM recognise the case for flexibility, allowing and supporting these regions to adapt institutional structures to suit their context[20].
[20] Thus in Somali Region, where there is a large number of programmes focussing on pastoral, agro-pastoral and ex-pastoral livelihoods but also limited government capacity to coordinate, there is a case for a single steering committee structure to manage PSNP and other programmes in a coordinated way.

Programme planning will remain, as under PSNP 3, strongly bottom-up in nature. The Community Food Security Task Force is responsible for targeting, while clients have a set of rights and responsibilities related to programme implementation and accountability, as outlined in the PSNP charter. At kebele level, the PSNP is managed by the Kebele Food Security Task Force (KFSTF), with oversight from the Kebele Cabinet and Kebele Council; while the Kebele Development Committee oversees development activities in the kebele more broadly and supports coordination between the PSNP and other interventions. A Kebele Appeals Committee (KAC) ensures local-level accountability, particularly around appeals regarding targeting.

The woreda is the key level in determining needs, preparing plans and implementing activities. The Woreda Food Security Task Force (WFSF) and Food Security Desk will manage and coordinate implementation, under the oversight of the Woreda Council through the Woreda Food Security Steering Committee; while the Woreda Office for Finance and Economic Development (WOFED) supports procurement and financial management[21].
[21] At kebele level, programme implementation is primarily the responsibility of agricultural development agents (DAs), who implement livelihoods activities and oversee public works; with some support from health extension workers (HEWs) for the provision of BCC activities and monitoring of compliance with co-responsibilities. Woreda-level responsibilities will evolve over the course of the programme: until social workers are present at the kebele level, DAs and HEWs will support the management of the permanent direct support activities (i.e. the co-responsibilities). Even when this transition has been made, transfers to all other clients (i.e. public works and temporary direct support clients) will continue be managed through WoFED and the Food Security for cash and food respectively (MoA 2014 pp. 18-2 to 18-4).

### Donor harmonisation and alignment

PSNP donors have developed comprehensive arrangements to support Government implementation with coordinated external support. A recent review of PSNP donor governance has re-affirmed the broad principles for balancing individual and collective roles, while recommending some improvements (Anderson 2015). The programme is now supported by 11 donors, who constitute the PSNP Donor Working Group (DWG)[22]. The DWG meets every two weeks, with a different donor chairing the Group and hosting the meetings for a six month period. The incumbent Chair is supported by a Deputy Chair: in the first three months of the Chair’s term, the Deputy will be the previous Chair, whereas in the last three months the Deputy will be the upcoming new Chair. This helps to provide continuity and reduce disruption in handover[23].
[22] The current donor partners to PSNP 4 are as follows: the World Bank, USAID, DFID, the EU, Canadian DFATD, WFP, IrishAid, the Netherlands, Danida, Sida and UNICEF.

A Donor Coordination Team (DCT) serves as the secretariat for the DWG, supporting the Group and the donor chair in particular. The DCT helps to coordinate individual donor requirements and views to arrive at common position for dialogue with the Government; provides logistical support to programme management and a common pool of technical expertise on aspects of PSNP implementation (e.g. the engineering aspects of public works, or IT skills for developing the Management Information System) that individual donors would be unable to staff themselves; commissions and manages studies that the DWG requires; and provides institutional memory for the donor community in the face of staff turnover. In agreeing and maintaining a collective dialogue between donors and Government, the DCT reduces transaction costs on both sides and enables donors to achieve more, at lower cost, than if all 11 donors routinely engaged with Government on a bilateral basis.

The DCT is set to grow to support the expanded size and complexity of the next phase of the programme[24]. The DCT is financed through a World Bank Partnership Trust Fund, with contributions from PSNP donors (including, it is proposed, £5.5 million from DFID); and is hosted in the World Bank Ethiopia Country Office.
[24] Plans call for eight full-time staff positions (Coordinator, Deputy Coordinator, Public Works Specialist, Livelihoods Specialist, Information Officer, Operations / Procurement Officer, Junior Programme Officer (to evolve into a Financial Management Specialist position) and a Team Assistant); reinforced by seven consultancy positions (Capacity Development Specialist, DRM / Humanitarian Specialist, CSI Focal Point, Nutrition/ Conditionalities Specialist, E-Payments Specialist, FM Consultants and an M&E Specialist (DCT 2015a p. 3)

Risk and risk management

PSNP 4 is a large and complex programme, which promises large-scale benefits but also entails a considerable range of risks. For the purposes of identifying, assessing and mitigating these potential sources of stress or shock to the programme, these risks are classified in line with the DFID typology (DFID 2014a pp. 16-17).

The programme is assessed as overall medium risk; but with a number of lower probability risks that, if they occurred, would have a significant impact upon the programme. Some of these risks are external to the programme but the majority are operational risks related to the ambition of the expansion in scale and scope that is proposed over the next five years. This section provides a comprehensive assessment of risks to PSNP 4; and identifies actions to be taken to manage these risks (Table 17). Annex 11 provides narrative detail. This assessment is that of DFID staff; but draws on assessments by other donors to the programme, notably the World Bank (World Bank 2014 pp. 19-21 and 98-102), which has triggered a number of safeguards policies which impose specific requirements on programme management (Table 16). The risk matrix will be revisited and updated by DFID at regular intervals (at a minimum, twice a year, in March and September).
Table 16: World Bank safeguard policies for PSNP 4

OP/BP 4.01	Environmental Assessment
OP 4.09	Pest management
OP/BP 4.11	Physical cultural resources
OP/BP 4.10	Indigenous Peoples
OP/BP 4.12	Involuntary resettlement
OP/BP 4.37	Safety of dams
OP/BP 7.50	Projects on international waterways

Source: World Bank 2014a p. 6
Table 17: Risk assessment and mitigation

DFID’s 2005 Conditionality Policy sets out the principles on which an aid partnership should be based. DFID Ethiopia carries out regular assessments of the Ethiopian Government’s commitment to the Partnership Principles underpinning UK aid. A country-level Partnership Principles Assessment (PPA) was last conducted in October 2014 and concluded that the Government of Ethiopia remains committed to the underlying principles of our partnership; and that this commitment was sufficient to continue financial aid. However, we noted that we continue to have concerns (particularly in relation to civil and political rights) which prevent us from considering a return to general budget support. Before each disbursement of financial assistance under this programme, DFID will provide written assurance to the approver that there remains credible commitment of GoE across all four Partnership Principles.
The DFID PSNP team will contribute to annual updates of the country-level PPA, and seek to ensure consistency in similar assessments by other PSNP donors. The team will work closely with the World Bank safeguards specialist to ensure that policies are in place to screen, mitigate and monitor environmental and social risk at both the public works sub-project level (the focus of safeguards to date) and at the systemic level (any wider indirect relationship between PSNP implementation and other Government programmes that might have negative local consequences.

DFID Ethiopia has also conducted a programme-level PPA which applies the Partnership Principles to DFID’s support to the PSNP (DFID Ethiopia 2015). This concludes that the Government is strongly committed to poverty reduction, sound financial management and domestic accountability within the design and implementation of the programme. Provisions in the Design Document and PIM and the incorporation of the PSNP within the Social Protection and DRM policies provide reassurance that this commitment will continue. The concerns with civil and political rights expressed in the country-level PPA, however, have implications for DFID support to the PSNP. The Design Document and PIM address these concerns and safeguards provide protection against the distortion of targeting or the misuse of transfers to induce compliance with other programmes. These will need to be further strengthened and backed up by bilateral (DFID-GoE) and collective (DWG and DCT) monitoring and dialogue. The programme-level PPA will be updated in a written assurance prior to any Submission requesting release of funds for PSNP 4. We also propose a formal break point evaluation after three years, prior to the release of funds for 2018/19 and 2019/20. This will provide an opportunity to assess progress, the trajectory of change, any concerns about unintended consequences of PSNP4, and the likely level of achievement by the end of the five-year phase.

Programme risks will be reviewed and updated during implementation as new evidence comes to light. These will be reviewed at each Annual Review (and, between Reviews, in quarterly updates to the Programme Delivery Plan) to consider whether risks have changed, the effectiveness of mitigation actions and any changes in the overall risk/reward as against appetite for risk. Risks will be fed into the team and office level risk registers. Risks which go beyond the tolerances outlined in this Business Case will be raised to the Deputy Head or Head of Office.

Monitoring and evaluation[25]
[25] This section draws heavily on the M&E chapters in the PSNP 4 Design Document (MoA 2014c pp. 83-98) and PIM (MoA 2014d, chapter 17). It also draws on the lessons from PSNP 3 M&E in the ‘review and options’ document (MoA 2014a); and the covering note to the 2013 revision of the DFID logframe (DFID Ethiopia 2013b).

PSNP 4 will retain the high quality of evaluation established to date (see Annex 12); while addressing the weaknesses in the monitoring system. The monitoring and evaluation (M&E) system will encompass a number of broad classes of information and corresponding data collection tools. These include (i) regular and ad hoc programme monitoring, focussing on inputs, activities and outputs; (ii) process assessments (e.g. Public Works Reviews); and (iii) periodic evaluations which assess progress towards outcomes and impact.

### Monitoring and reporting

Box 3: ‘Real time’ monitoring tools
Regional Information Centres (RICs) collect data on transfers and other key indicators from a (large) sample of woredas to provide monthly data on progress against key performance targets (e.g. timeliness of transfer delivery). RICs are established in four regions: getting the RICs functioning in Afar and Somali regions will be a priority in PSNP 4. The Federal Information Centre (FIC) compiles and reports RIC data to provide programme wide analysis (and also supervises and supports the RICs to ensure quality control).
The Rapid Response Mechanism (RRM) was introduced to address critical implementation problems as they occur. Rapid Response Teams (RRT) will be deployed regularly to the Regions (and a sample of woredas and kebeles within each Region) to monitor implementation progress (through focus group discussions with implementers, clients and non-clients and a review of records). They are intended to provide on-the-spot advice on how to address constraints or errors in implementation, as well as providing regional and federal level managers with information on the types of challenges faced at the local level. Source: MoA 2014c p. 96.
Programme monitoring will include both regular and ad hoc elements. Regular monitoring includes monthly and quarterly reporting by kebeles and woredas, quarterly reporting at the Regional and Federal levels, and quarterly Interim Financial Reports (IFR). The PIM describes the reporting obligations of each line unit at each level in detail. This regular reporting will be supplemented by more ad hoc, opportunistic monitoring, described in programme documents under the heading of real time monitoring. The two main sources of real-time data are the Information Centres and the Rapid Response Mechanism (see Box).

PSNP 4 also introduces a new kind of monitoring through tracking of client participation. For some components it is sufficient to track activities (e.g. transfer disbursement or completion of public works). However, for other objectives (e.g. linking client households to nutritional or livelihoods information and services) it is important to take the household as the unit of analysis. As such, PSNP 4 introduces reporting systems and revises data collection templates to enable tracking of client participation (MoA 2014d pp. 171 to 17-2).

Under Outputs 1 and 5, PSNP 4 will make significant investments in improving monitoring and reporting. At the core of this improvement will be the development of a computerised (rather than paper-based) management information system (MIS), including a single registry of beneficiaries (to improve case management and oversight of coverage) and a geo-coded database of completed public works structures. The anticipated costs of each of these investments (totalling $62 m over five years) have been presented in the Appraisal Case above.

### Evaluation

The contract for the next five years of impact evaluations will be tendered in 2015. DFID, along with the other donors and Government, is providing input to the design of the impact evaluation. DFID will sit on the panel for the review of bids; and will seek to ensure that questions, instruments and sampling test the assumptions in the theory of change (with emphasis upon gathering data to test those assumptions for which the evidence base is currently limited). Data collection (qualitative and quantitative) will take place in late 2015, 2017 and 2019, with results from becoming available 10-12 months after data collection. It has been agreed that the highland household panel which has been used since 2006 will not be retained: after ten years, it will be necessary to refresh the sample. As before, the evaluations will be contracted by the DCT, not the Government, and will remain fully independent.

The Programme will retain the six-monthly Joint Review and Implementation Supervision (JRIS) exercise, which provides an opportunity for all stakeholders to review implementation and progress towards programme goals. The JRIS Aide Memoire will be used to guide management actions over the coming six months.
### Monitoring and evaluating gender outcomes

The increased focus on gender within PSNP 4 requires corresponding refinements to the M&E system. Simple reporting tools have been developed for kebele- and woreda-level reporting on the fulfilment of the Programme’s gender provisions, in programme processes as a whole and separately in public works planning and management. Logframe indicators relating to beneficiaries are disaggregated by sex (of the individual beneficiary or the head of household, as appropriate); and both the single registry and the impact evaluation will support more detailed gender analysis. Annex 13 summarises the PIM provisions relating to gender and other social concerns, and notes both the body responsible for implementation and the body responsible for monitoring.

### DFID reporting

DFID’s internal monitoring and evaluation will make use of these common programme arrangements to the maximum extent possible, and minimise the duplication of effort in DFID-specific monitoring. The DFID Annual Review will be timed for submission in September each year: it will draw heavily on the outputs of the May JRIS (in particular the Aide Memoire) and August MoA Annual Report. Over the first year of implementation, the DFID PSNP team will review the programme logframe and identify a subset of critical indicators and targets for inclusion in a DFID logframe which will be more manageable for Annual Review purposes, while retaining the objectives and balance of the common, programme logframe. The DFID Programme Delivery Plan (PDP) will be updated as and when necessary, but at a minimum twice a year (once following the Annual Review, and the second in March, drawing on the November JRIS and the findings of the annual programme audit, which is usually released in January).

Using programme reporting for DFID purposes will entail some challenges: for example, despite considerable efforts during the design process, the logframe is still long and contains a number of indicators for which baseline and target values are not yet defined. However, using common tools and processes is preferable to the alternative (which would involve DFID staff participating in and contributing to common monitoring and management processes, but then also requesting meetings and documentation to complete a DFID annual review against a DFID-specific logframe). Table 18 summarises the schedule of key regular reporting instruments within PSNP 4.

Table 18: schedule for monitoring and oversight of PSNP 4

	planning and implementation	financial management	Evaluation	DFID internal
January		Annual Audit on EFY ended last June IFR for 1st Quarter (July-Sept)
February
March		IFR for 2nd quarter (Oct-Dec)		scheduled PDP review
April			draft impact evaluation (every two years)
May	JRIS
June		IFR for 3rd Quarter (Jan-March)
July	new Ethiopian Financial Year (EFY)		final impact evaluation (every two years)
August	MoA Annual Report on previous EFY
September	MoA Annual Plan and Budget	IFR for 4th Quarter (April-June)		DFID Annual Review
October
November	JRIS
December

The Design Document includes a helpful recognition that the M&E arrangements for the next phase will need to evolve during implementation. There is an agreement that, at the latest, the logframe will be reviewed and revised at the mid-term review in 2018.
Abbreviations, acronyms and Ethiopian terms

AED		Agricultural Extension Directorate (of MoA)
AR		Annual Review
BCR		benefit-cost ratio
belg		March-through-May rains (traditionally the main rains for the southern regions of Ethiopia)
BoFED		(Regional) Bureau of Finance and Economic Development
BoLSA		Bureau of Labour and Social Affairs

CDEL		(DFID / HMG) recurrent programme spending
CFI		chronically food insecure
CGAP		Consultative Group to Assist the Poorest
CMAM		Community Management of Acute Malnutrition
CMC		(PSNP 4) Coordination and Management Committee
COPCU		Channel One Programme Coordination Unit (of MoFED)
CPAR		(World Bank) Country Procurement Assessment Review
CPRD		(DFID) Country Poverty Reduction Diagnostic
CSA		Central Statistical Agency
CSAE		Centre for the Study of African Economies
CSI		Climate-Smart Initiative

DA		Development Agent
DAG		Development Assistance Group
DCT		(PSNP) Donor Coordination Team
DECC		(UK) Department for Environment and Climate Change
DHS		Demographic and Health Survey
DRM		Disaster Risk Management
DRMFSS		Disaster Risk Management and Food Security Sector (of MoA)
DRS		Developing Regional States (of Ethiopia)
DS		Direct Support
DWG		Donor Working Group (of donors supporting the PSNP and HABP)

EFSS		Ethiopian Food Security Survey (2006, 2008, 2010, 2012)
EFY		Ethiopian Financial Year (run July 1 to June 30)
ESMF		Environmental and Social Management Framework
ETB		Ethiopian birr (£1 = c. 30 ETB)
EW		Early Warning
EWRD		Early Warning and Response Directorate (of MoA)

FAO		Food and Agriculture Organisation (of the UN)
FCA		Federal Cooperatives Agency
FDP		Food distribution point
FEMSEDA		Federal Micro and Small Enterprise Development Agency
FGD		focus group discussion
FHH		female-headed household
FIC		Federal Information Centre
FMIP		Food Management Improvement Project
food gap		period (in months) during which a household lacks adequate access to food and needs to skip meals or reduce portion sizes for five or more days
FPPA		Federal Public Procurement Agency
FRA		Fiduciary Risk Assessment
FSCD		Food Security Coordination Directorate (of MoA)
FSP		(Government of Ethiopia) Food Security Programme (introduced 2005)

GNI		Gross National Income
GoE		Government of Ethiopia
GPS		Graduation Prediction System
GTP		(Government of Ethiopia) Growth and Transformation Plan

HABP		Household Asset Building Programme
HEW		health extension worker
HFA		height-for-age (a measure of stunting or chronic malnutrition)
hh		household
HICES		Household Income, Consumption and Expenditure Survey (2000, 2005, 2010/11)
HMG		Her Majesty's Government
HRD		annual (Government of Ethiopia) Humanitarian Requirements Document
HVFB		High-value food basket. In Amhara, districts in which the PSNP is implemented with the support of USAID receive a more generous transfer package.

IBEX		Integrated Budget and Expenditure (GoE accounting software)
IBRD		International Bank for Reconstruction and Development (World Bank)
ICAI		(UK) Independent Commission for Aid Impact
ICF		(UK) International Climate Fund
IDA		International Development Association (World Bank financing)
IDS		(University of Sussex) Institute of Development Studies
IFPRI		International Food Policy Research Institute (Washington, DC)
IFR		Interim Financial Report
IGA		income-generating activity
infotech		technical guidance sheets for the design and construction of public works structures
IPCC		Inter-Governmental Panel on Climate Change

JRIS		Joint Review and Implementation Supervision
JSOC		Joint Strategic Oversight Committee (of PSNP 4)

KAC		Kebele Appeals Committee
KFSTF		Kebele Food Security Task Force
kebele		sub-district

LEWIE		Local Economy-Wide Impact Evaluation

MDG		(UN) Millennium Development Goals
MDTF		Multi-Donor Trust Fund
meher		mid-June to mid-September rains (the main rains for highland agriculturalists)
MFI		Microfinance Institution
MHH		male-headed household
MIS		management information system
MoA		Ministry of Agriculture
MoFED		Ministry of Finance and Economic Development
MoH		Ministry of Health
MOLSA		Ministry of Labour and Social Affairs
MoWCYA		Ministry of Women, Children and Youth Affairs
MT		metric tonnes
MTR		Mid-Term Review

NAO		(UK) National Audit Office
NBE		National Bank of Ethiopia
n.d.		no date
NNP		National Nutrition Programme
NPV		net present value
NRMD		Natural Resources Management Directorate (of MoA)

OCHA		Office for the Coordination of Humanitarian Affairs
ODA		Official Development Assistance
ODI		Overseas Development Institute (London)
OP		(DFID Ethiopia) Operational Plan
OpEx		(DFID Ethiopia) Operational Excellence Team
OPT		Occupied Palestinian Territories

p.a.		per annum
p.c.		per capita
PAC		(UK) Public Accounts Committee
PAD		(World Bank) Project Appraisal Document
PCR		(DFID) Project Completion Report
PDP		(DFID) Programme Delivery Plan
PEFA		Public Expenditure and Financial Accountability Review
PFM		public financial management
PIM		Programme Implementation Manual
PLW		pregnant and lactating women
PLWHA		People Living with HIV/AIDS
PPA		(UK) Partnership Principles Assessment
PSNP		Productive Safety Net Programme
PtoP		from Protection to Production (multi-country research programme led by FAO)
PW		public works
PWIA		Public Works Impact Assessment
PWIU		Public Works Implementation Unit

RDEL		(DFID / HMG) recurrent programme spending
RED&FS		Rural Economic Development and Food Security (sector coordination body)
RFM		(PSNP) Risk Financing Mechanism
RFSTF		Regional Food Security Task Force
RIC		Regional Information Centre
RuSaCCo		Rural Savings and Credit Cooperatives

SCTP		Social Cash Transfers Pilot (UNICEF-supported pilot programme in Tigray Region)
SNNPR		Southern Nations, Nationalities and People’s Region
SNSF		Safety Net Support Facility
SSA		sub-Saharan Africa
SSN		Social safety net
SWC		soil and water conservation

Tabia		District-level administrative unit in Tigray Region; equivalent to a woreda
TCTR		total cost to transfer ratio
TLU		tropical livestock unit: TLU equal one for cattle, horse and mules, 0.15 for sheep and goats, 0.005 for poultry, 0.65 for donkeys and 1.45 for camels (Ramakrishna and Demeke 2002)
TSF		Targeted Supplementary Feeding
TVET		Technical and Vocational Education and Training

UNDESA		United Nations Department of Economic and Social Affairs
UNICEF		United Nations Children's Fund
UNOPS		United Nations Office for Project Services
USAID		United States Agency for International Development

VfM		value for money
VSLA		Village Savings and Loans Association

WB		World Bank
WFP		World Food Programme
WIDE		Well-being and Ill-being Dynamics in Ethiopia (research programme)
WoFED		Woreda Office of Finance and Economic Development
WOLSA		Woreda Office for Labour and Social Affairs
Woreda		District

Annexes

Annex 1: PSNP 4 targeting and graduation

Over the last ten years, the PSNP has developed and refined an approach to targeting (the identification and enrolment of beneficiaries) that is well adapted to the capacity, information and resource constraints of a very low income developing country. Targeting adopts a multi-stage approach, selecting woredas (districts) based upon historical patterns of recurrent humanitarian food aid and then within each woreda selecting beneficiary households using a combination of administrative and participatory methods (a checklist of eligibility criteria is used to produce a provisional list of beneficiaries, which is then displayed and discussed and if necessary amended in a community meeting). Those who feel that they have been wrongly excluded can apply to have their case heard in the Kebele Appeals Committee (KAC).
High quality evaluations built into the PSNP suggest that the programme is now generally targeted and implemented well. Impact assessments (Berhane et al 2013 pp. 47-68) and additional targeting analysis of the household panel data (Coll-Black et al 2012) find that the programme has been:
- well targeted in the highland regions in which PSNP was first introduced in 2005 (Amhara, Oromia, SNNPR and Tigray), and which have accounted for on average 82% of the total PSNP caseload over the period 2010-2015 Coll-Black et al 2011, 2012; .
- poorly targeted in the lowland, pastoralist and agro-pastoralist regions of Afar and Somali, where the programme was introduced only in 2010 and which have accounted for on average 18% of the total caseload (Lind et al 2013 pp. 50-71). Improving targeting outcomes in the lowlands will be a priority for the next phase of the programme.
  Figure A1.1 PSNP targeting at a national level -HICES

  Cumulative proportion of market income and transfers
  Cumulative proportion of the population

  Table A1.1 PSNP targeting at a national level - DHS

  source: HICES 2010/11, analysed in World Bank (2014) p. 75

  DHS wealth quintile	Percentage of group who receive PSNP transfers

  Poorest	24.2
  Second	10.1
  Middle	6.0
  Fourth	3.6
  Richest	1.9
  Total	8.9

  source: CSA (2014), Table 2.8.
The distribution of PSNP transfers is also picked up through national household surveys. Analysis of the 2011 Household Income, Consumption and Expenditure Survey (HICES) in the new Poverty Assessment finds that the PSNP was the most pro-poor of the Government programmes that were studied and more pro-poor than humanitarian food aid. The 2014 Demographic and Health Survey (DHS) finds that 75% of those reporting receipt of PSNP transfers fall in the bottom two quintiles of the wealth distribution (Figure A2.1; Table A2.1).
New woredas (and then within them, new kebeles) are to be selected if they received emergency food assistance in three of the five years preceding 2014. The order in which these woredas will be absorbed into the programme will be based on an assessment of (i) the level of need and (ii) an assessment of their readiness in terms of key capacities. Indicative caseload allowances will be assigned to these woredas based on an average of their annual relief food beneficiaries.

PSNP 4 will largely retain these arrangements while introducing some additional improvements. Within existing woredas, the households remaining in the programme at the end of PSNP 3 (c. 5m) will continue into PSNP 4; any households which have received emergency food distribution in the three years preceding 2014 will also be enrolled. The 92 new woredas (and then within them, new kebeles) are to be selected if they received emergency food assistance in three of the five years preceding 2014. The order in which these woredas will be absorbed into the programme will be based on an assessment of (i) the level of need (indicative woreda caseload, based on average repeat humanitarian caseloads in previous years) and (ii) an assessment of their readiness in terms of key local government capacities.

Box A1: Targeting and classification criteria

Households are eligible for PSNP transfes if they are:
- A member of the community (i.e. not just temporarily resident)
- Chronically food insecure (faced continuous food shortages – a food gap of 3 months or more per year - in the last 3 years)
or
- Have become suddenly food insecure as a result of a severe loss of assets (financial, livestock, means of production, assets), especially if linked to the onset of severe chronic illness, such as AIDS
- Have no adequate family support and other means of social protection and support
Once assigned an indicative caseload allowance, a kebele will then assign this between communities. Chapter 3 of the PIM outlines how the Community Food Security Task Force (CSTF) then selects households based on defined eligibility criteria, and subsequently classifies them as either public works / temporary direct support (if there is adult labour in the household) or permanent direct support beneficiaries (if no adult labour is present) Box A1 summarises the eligibility criteria. The provisional list is then displayed for at least a week; and a meeting of the community called to confirm the assessment and address inclusion or exclusion errors. The confirmed list is then submitted to the Kebele Food Security Task Force (KFSTF).
The process is backed by a grievance process: an excluded household can take their case to the KAC (which meets quarterly).

A full (‘periodic’) retargeting of the programme will be conducted every three to five years. In the interim, annual recertification will confirm that households are still eligible (present in the community and meeting the needs criteria); adjust allowances for any changes in household size and composition; enroll any households who successfully appealed wrongful exclusion; remove those were identified 12 months earlier as ready for graduation; and consider adding to the permanent list any household that was in the previous year enrolled on a temporary basis due to the presence of an acutely malnourished child in the family. Once enrolled into the core caseload, a household will remain in the programme for a minimum of three years before being considered eligible for graduation.

PSNP 4 introduces two significant modifications to the targeting process. Firstly, over the next few years a food insecurity / poverty index – that is, a Proxy Means Test (PMT) which predicts household eligibility based on observable household characteristics proven to correlate with food insecurity - will be developed and piloted as a complement and cross-check to the process of administrative and community-based targeting that is described above. In addition, woredas, kebeles and communities in the lowland regions are encouraged and supported to develop and pilot adaptations to the targeting process (originally developed for stable, stationary highland communities of smallholder farmers) in ways that reflect the very different, clan-based social organisation and norms of lowland pastoral and agro-pastoral groups.

Graduation

If the process and outcomes for programme entry (targeting) are seen as broadly effective and legitimate, there is more concern about the management of programme exit (graduation). The Government has been extremely keen that households ‘graduate’ from PSNP. While donors share the objective of helping households onto an upward path that will allow them to become food secure and resilient to shocks and so no longer require transfer support, we feel that the Government has been extremely unrealistic about the speed at which this can be achieved, given the extreme poverty of PSNP beneficiaries, the level of shocks to which they are exposed, and the relatively modest size of PSNP transfers. There has been significant concern within the Donor Working Group that the Government’s ambition, reflected in the targets included in the five year national development strategy (the 2010-2015 Growth and Transformation Plan), was leading officials to set quotas which resulted in households being removed from the programme before they were ready. The impact evaluations have confirmed that while graduates are marginally better off in terms of asset holdings, they are still significantly food insecure (and on this measure – the measure on which graduation is meant to be based – no different from those who remain on the programme). This raises the danger that households graduated prematurely from the PSNP will soon fall back into acute food insecurity in the face of any shock, and then need to receive either humanitarian food aid or be re-enrolled in the PSNP.

PSNP 4 attempts to address these concerns. A simple, Excel-based Graduation Prediction System (GPS) combines data on underlying local agroecological and market conditions with annual rainfall and crop production measures to generate an indicative estimate of the likely number of graduates in a locality, allowing local officials to plan and budget for the year. CFSTFs then conduct an annual wealth ranking exercise: they identify the typical characteristics of 3-4 different local wealth groups and classify PSNP households into these categories, take the number supplied by the GPS and work downward through the household list from the top, better off group until either they have met the GPS number of the committee considers that the households under consideration are not in fact ready for graduation. The list of proposed graduates is posted publicly for a week and then discussed for verification or correction in a full public meeting of the community. Any disagreements are taken to the KAC for consideration. Once the KAC has completed its determinations on all the appeals, the list is sent up to the KFSTF and onwards to the woreda and region. Once the poverty / food security index is developed and under implementation, it will be used to further cross-check the proposed list, and further reduce the risk of premature graduation.

Summary

To date, both technical assessment and beneficiary feedback suggests that the targeting process is effective and accepted as legitimate. This comes out in the impact assessment (in focus group discussions), in the WIDE qualitative research, and the fieldwork that ICAI conducted in evaluating PSNP impact in late 2014. There has however been much less acceptance of the way graduation has been managed. It is hoped that the changes introduced under PSNP 4 will resolve these problems with graduation. We also hope that the design of the new programme with regard to caseload will reduce the high-level incentives for overly-ambitious enforcement of graduation. With a stable caseload of 10 m per annum for the next five years, any graduates are to be replaced by enrolling other eligible households who have previously been excluded by budget constraints.
Annex 2: The strength of the evidence

Type of evidence			Characteristics of the body of evidence				studies
			quality	size	contextual proximity	consistency
Ethiopian evidence
1.a	Primary and empirical
1.a.i	PSNP evaluations: programme implementation and household-level impact		High / Methodological mix (descriptive statistics; quasi-experimental (NNM, PSM); and qualitative research) and triangulation / Analysis of data at multiple levels (large-scale household panel; survey of regional, woreda and kebele capacities, practices and perceptions; semi-structured and focus group discussions) / Large sample, multiple rounds, consistency in data collection instruments, sizeable in-year differences and between-year changes… / which support identification of statistically-significant effects, including at disaggregated levels (between regions, or between MHH and FHH)	Large for a single programme / 3 key papers for the 2010 round; / 4 key papers for the 2012 round; / plus / additional topic-specific peer-reviewed journal articles / and quality-controlled working papers from credible international bodies (IFPRI, World Bank)	High / All relate directly to PSNP	High / findings change between rounds as programme implementation has improved, but demonstrate high internal consistency – different indicators point to the same conclusion - within each round	Berhane et al 2011a / Berhane et al 2011b / Sabates-Wheeler et al 2011 / Coll-Black et al 2012 / Hoddinott et al 2013 / Berhane et al 2013 / Lind et al 2013 / Kumar and Hoddinott 2013 / Hoddinott 2013
1.a.ii	PSNP public works impact evaluations		High / Based on analysis of primary data (engineering, bio-physical, microeconomic)	Small / Few PWIA conducted to date; each takes only a very small sample of PSNP woredas / watersheds. Best considered strong case studies, indicative but not statistically representative of the universe of PSNP public works.	High / Assessments of PSNP public works using primary data; / however, some estimations (e.g. on m3 soil carbon sequestration through area enclosure) draw on experimental data from non-Ethiopian contexts.	High / Studies point to similar, credible findings	Metaferia Consulting Engineers (2011) / Sutcliffe (2011) / MoA (2013a)
Type of evidence			Characteristics of the body of evidence				studies
			quality	size	contextual proximity	consistency
Ethiopian evidence (continued)
1.a		Primary and empirical (continued)
1.a.iii		PSNP and HABP programme reporting	Medium / Basic descriptive data on programme implementation (evidence of activities and outputs)	Large / Various planning, budgeting, and reporting (activity, financial, physical)	High / All specific to PSNP and HABP.	Inconsistent / Reports are largely but not perfectly consistent.	Annual Plans / Annual Reports / IFRs / Monthly FIC reports / etc.
1.a.iv		PSNP Public Works Reviews	Medium / Weighted sample of 80 projects / Quantified qualitative assessment: a team of technical experts agrees consensus scores for a wide range of performance indicators relating to adequacy of the PW planning process, technical quality and sustainability of PW structures.	Small / Should be two reviews per year (therefore 6 to date): only 4 have been completed	High / All relate exclusively to PSNP public works.	Inconsistent / Sample of 80 projects per year is small in comparison to the overall universe of PSNP public works (c. 30,000 pa), resulting in sometimes large swings in some ratings from one year to the next.	MoA 2011a / MoA 2011b / MoA 2012 / MoA 2013
1.a.v		Socio-economic research which includes findings on PSNP impact	High	Small	High
1.a.vi		evaluations and assessments of the Social Cash Transfers (SCT) pilot in Tigray region	Medium to high / Evaluation of SCT pilot in Tigray follows the same approach as the PSNP impact evaluations, with the strengths described above. / Estimation of local multiplier effects due to SCT conducted by FAO-led team, using established (LEWIE) approaches to modelling.	Small / Two (baseline and midline) rounds of SCT household survey; plus several outputs from the PtoP local economic impact research.	Medium / High / All relate to Ethiopia; however, to date all have been based on findings from the pilot in Tigray region, and may not necessarily be directly transferable to other regions	High / Conclusions are consistent internally (within the small set of findings relating to the SCT) and externally (with findings on PSNP implementation and results within Tigray).	Berhane et al 2012 / Berhane et al 2013 / Kagin et al n.d. / Kagin et al 2014
		Other transfer programmes in Ethiopia / small-scale pilot add-ons / variations to PSNP	Well-designed mixed methods research on CGAP Graduation pilot, PSNP Plus, and MERET.	Small / Less than 10 known to the team.	High / Most relate to small-scale USAID-, WFP- or CGAP-managed variations on PSNP basic implementation model.	- / Tend to look at different specific aspects so not directly comparable: neither consistent nor consistent.	Sengupta 2012 / Burns 2011

Type of evidence		Characteristics of the body of evidence				studies
		quality	size	contextual proximity	consistency
Ethiopian evidence (continued)
1.b	Secondary
1.b.i	Papers for 6-monthly JRIS / MTR reviews	Low / JRIS / MTR regional Aide Memoires and Federal thematic reviews (transfers, PW, resource management, capacity and coordination, HABP) vary in quality (roughly equal quantities of medium and low); Aide Memoire useful record, albeit politically negotiated	Medium / In any given JRIS, c. 10 key short Federal documents and 6 Regional Aide Memoires; over time, amounts to a substantial dataset on evolution of a given aspect of PSNP implementation.	High / All specific to PSNP and HABP.	Inconsistent / Consistency of conclusions between groups and within each thematic group over time is high but not perfect – hence the ‘inconsistent’ rating.	From 2012 MTR (by way of example): / MoA (2012b) / DCT (2012) / Transfer Working Group (2012a, b) / PW MTR Working Group (2012a, b) / Food Management Working Group (2012a, b) Procurement Working Group (2012a, b) / Group 4A (2012a, b) / MTR Output Working Group 4B (2012a, b) / HABP Working Group (2012a, b)
1.b.ii	Thematic studies	Medium / Mixed quality, from national sample surveys to community or regional situation analysis of varying standards		Medium / Some studies specific to PSNP/HABP; / others (e.g. national gender assessments, findings of national surveys such as DHS or HICES, regional or community case studies, socio-economic studies) more contextual		e.g. Van Domelen and Coll-Black (2012) / Envers et al 2008 / MoFED 2012

Type of evidence		Characteristics of the body of evidence				studies
		quality	size	contextual proximity	consistency
International evidence
2.a	Primary and empirical
2.a.i	Impact evaluations	High	Medium	Medium	Variable
2.a.ii	public works impact evaluations	Low / Based on analysis of primary data (engineering, bio-physical, microeconomic)	Small / Most public works programmes have not been subjected to rigorous evaluation (or even output reporting): see McCord (2012) for review and discussion	Medium / Technical aspects of public works in other countries largely transferable to Ethiopian context; management context however often dissimilar (smaller scale, shorter duration)	Inconsistent
2.b	Secondary
2.b.i	Systematic reviews and evidence synthesis / stocktakes	Medium / Across all themes and regions / countries, roughly equal numbers of high, medium and low quality studies.	Large	Medium	Inconsistent / Consistency of conclusions varies between themes and / or regions: therefore rated ‘inconsistent’	Grosh et al (2008) / Fiszbein et al (2009) / Arnold, Conway and Greenslade (2011)
2.b.ii	Thematic studies	Medium / Across all themes and regions / countries, roughly equal numbers of high, medium and low quality studies.		Medium	Inconsistent / Consistency of conclusions varies between themes and / or regions: therefore rated ‘inconsistent’

Annex 3: Evidence of PSNP and SCT performance and impact

### A3.1. Household level benefits

Transfers are well targeted and, since 2010, delivered in a full and timely manner
The first phase of the programme (2005-2010) focussed upon developing programme delivery systems. In the second phase (2010-2015), these systems have bedded down, resulting in significant improvements in the timelines and fullness of transfer payments.
Figure A3.1 Average transfer levels have risen

The PSNP incorporates gender equity provisions relating to who in the household can claim transfers; consideration of the needs of girls and women in the selection of public works, setting of work norms and provision of childcare at public works sites (Coope 2014 pp. 8-10); and female participation in programme governance (Evers et al 2008; Jones et al 2010; SNSF 2014; Coope 2014). The broad findings are of improving and in some cases good performance (e.g. the programme’s impact on schooling in Tigray has been even better for girls than boys), but with considerable variation between provisions and regions (with progress in the lowlands generally lagging, or less clear).

Direct transfer effects: higher income and living standards (p.c. consumption) for very poor households
PSNP transfers provide a significant addition to the pre-transfer income and consumption of the poorest groups (A2-2). The bulk of transfer income is spent on food, resulting in a shorter hungry period and a better, more diverse diet (see below): but PSNP transfers have also increased household spending on non-food as well as food items, including healthcare, education, and consumer goods and services (housing improvements, clothing, and transport) by an average of 44 birr per person per month in 2012 (Kumar and Hoddinott 2013 pp, 27-9).

Improved food security and dietary diversity; but not yet any impact on nutrition outcomes
The PSNP has had a significant impact on food security, reducing the number of months each year that households have to go hungry. The percentage of PSNP beneficiaries reporting full current food security (i.e. a food gap of zero) has doubled since the programme began, from 16.8% in 2006 to 36.2% in 2012 (Hoddinot et al 2013b p. 6)[26]; in the highlands regions, PSNP clients have seen their months of food security rise from an average of 8.4 per year in 2006 to 10.1 in 2012. Table 9 summarises the contribution of PSNP transfers in terms of the average reduction in food gap and improvements in dietary diversity between 2010 and 2012: these figures describe the impact that can be attributed statistically as due to PSNP, rather than other background factors. Between 2010 and 2012, PSNP transfers have improved food security by on average just under 1.5 months for those households receiving public works payments, and by almost 2 months for those receiving direct support transfers. Impact was particularly large in Amhara Region and for the most marginal of beneficiaries (direct support households and female-headed households involved in public works). Reflecting the improvements in programme implementation between 2010 and 2012, the impact on the food gap attributable to PSNP transfers over the two years 2010-2012 is twice that which was achieved between 2006 and 2010.
[26] This confirms that PSNP has met and exceeded its target for contribution to the DFID global headline results commitment to food security.

Table A3.1: PSNP impact on food security and dietary diversity, 2010-12

type of PSNP recipient	Improvement in food security attributable to PSNP
	reduction in food gap (months / year)	gain in number of food groups (1-7)
public works – all households	1.48***	0.462***
public works – female-headed households	2.65***	0.380***
public works – male-headed households	1.34***	0.330***
direct support – all households	1.93***	0.620***

Source: Kumar and Hoddinott 2013 pp. 22; 24; 30; 31; 67.
*** = statistically significant at 1%; ** = statistically significant at 5%.

Operating at scale and over a sustained period, PSNP has been a major driver of an overall decline in food insecurity in the districts in which PSNP operates. Between 2010 and 2012, the size of the average food gap in these districts has fallen by 40% in the highlands, and 45% in the lowlands. Both male- and female-headed households have experienced dramatic gains, although gains for male-headed households (MHH) have been faster, and from a better initial position, than those for female-headed households (FHH).

Figure A3.2: Between 2010 and 2012, the average food gap in PSNP districts has fallen
by 40% in the highlands by 45% in the lowlands

Despite improvements in calorie intake and dietary diversity, PSNP has not yet had any impact on nutritional outcomes. Analysing anthropometric data collected in the panel data from the 2008, 2010 and 2012 rounds of the impact assessment, IFPRI has found no robust, statistically significant relationship between receipt of PSNP transfers and child nutrition at 24 months of age (Berhane, Hoddinott and Kumar 2014)[27]. The conclusion is that more and better food intake is a necessary but not sufficient condition for improving nutritional outcomes – a conclusion that is in line with the international consensus on strategies for reducing malnutrition.
[27] Interestingly, the same study also found no statistically significant impact to date on nutritional outcomes from the nutrition-focussed CMAM programme.

Reduction in national poverty rates
Table A3.2: PSNP impact on poverty in 2011

	before transfers	after / transfers	impact / (% points)
poverty head count ratio	32.5%	30.9%	1.6%
poverty gap	9.4%	8.2%	1.2%
squared poverty gap	4.4%	3.2%	1.2%

Source: World Bank (2015)
In 2010/11, PSNP transfers lifted around 1.4 million people over the poverty line. The recent Ethiopia Poverty Assessment identifies PSNP as one of the three drivers of poverty reduction between 2005 and 2011 (World Bank 2015): the direct impact of PSNP transfers reduced the national poverty headcount rate by 1.6 percentage points (1.4 million) while indirect effects via higher agricultural productivity increase this impact further[28]. For others, PSNP transfers were not enough to lift them over the poverty line, but did get them closer to it: this is captured in the reduction in the poverty gap that is attributable to PSNP transfers.
[28] In the same year (2011), humanitarian transfers reduced the poverty headcount by 0.4 percentage points, or c. 353,000 people.

Improved access to basic services for the poorest rural households

Preliminary analysis suggests that PSNP improves educational attainment and progress for children (and girls in particular) in households receiving PSNP transfers. In Tigray, children in households receiving PSNP public works payments (the poorest and most marginalised households) performed better than the children of other households (which are richer and more food secure) in grade attainment and rate of grade progression between 2010 and 2012 (table A3.3). These results need to be subjected to further statistical tests, and tested in other regions: but the size of the effect is sufficiently large that there is a good level of confidence that the conclusion (that transfer payments improve educational participation) will stand.
Table A3.3: Schooling attainment and progression in Tigray Region

indicator		PSNP public work recipient	non-PSNP
mean grade attainment	girls	4.29	3.99
	boys	4.13	3.58
number of grades completed between 2010 and 2012	girls	1.92	1.75
	boys	1.77	1.56

Source: Hoddinott with Kumar 2013 slide 51

In addition to these household-level income effects (i.e., impact on access to services due to receipt of transfers by poor households), PSNP has improved access to services through infrastructure built through public works. The evidence for the effects of PSNP-built health posts, school rooms and roads are discussed below under community-level impact.

Transfers appear to reduce the incidence of early marriage for girls

Emerging evidence from the 2014 highlands assessment, presented in April 2015, suggests that PSNP is helping to reduce the age at which girls marry and leave their parents’ household. Transfer recipient households are larger than comparable non-recipient households. Analysis of household composition confirms there is no difference in the number of young children (in other words, the difference in household size is not due to higher fertility rates in PSNP households). Similarly, there is no difference in the number of males in the household. Rather, the difference in household size is attributable to the fact that PSNP-recipient households contain on average a significantly larger number of girls aged 7 to 17 years. Since the major reason for girls in this age range to leave their parents’ household is to get married, it seems likely that, by relaxing cash constraints (and keeping girls in school longer), PSNP transfers are helping to delay the age at which girls marry and then move out (Hoddinott 2015).

Inclusive economic development: household-level investments in productivity and livelihood diversification

While the primary role of safety net transfers is to ensure a minimal acceptable level of current consumption, they may also have an effect on household livelihood strategies and longer-term improvements in income-generating capacity. The majority of (modest) transfer income provided to very poor households is consumed (primarily as food) rather than invested, in line with programme objectives of food security and poverty reduction. However, the addition that transfers provide to total household income can also reduce liquidity constraints, improve credit-worthiness and affect household economic behaviour with regard to labour, savings, access to and utilisation of credit, investment in productive assets or productivity-enhancing inputs, and how assets are used.

To begin with, transfers can help very poor households to manage their land more profitably. The 2013 mid-line evaluation of the Tigray Social Cash Transfer Pilot (SCTP) suggests that these transfers helped destitute labour-poor households (analogous to PSNP Direct Support clients) to switch from sharecropping-out to owner-cultivation and renting out (Figure A3.3). There was also a significant increase in the proportion of beneficiary households who have made long-term investments in their land (stone terracing, soil bunds, levelling)[29]. Analysis in the 2015 report (forthcoming) will test whether these associations are causal.
Figure A3.3:	Households receiving transfers have increasingly switched to more profitable use of land

Source: Hoddinott et al 2014.
[29] The proportion of SCT beneficiaries who invested in one or more forms of plot improvement rose from 9.4% in 2012 to 22.6% in 2013. This compares to rates in the control group, which rose from 16.7% to 30.5%.

The impact of PSNP transfers on livelihoods varies depending on the characteristics of both households and the communities in which they live. These nuances emerge from beneficiary accounts collected during the third round of research under the Well-being and Ill-being in Developing Ethiopia (WIDE) programme of longitudinal sentinel site studies (see Box).
 In more recent rounds of the PSNP impact evaluation, when transfer values have been significantly higher than pre-2010 levels, households have on average consumed 75% of the amount they receive as cash transfers, and invested 25% (World Bank 2014 p. 111). The 2014 impact assessment results (to be released in the second quarter of 2015) should update this estimate of household investment rates, and hopefully provide additional information of the impact of transfers on household livelihoods.
Box A3.1:	Household-level economic effects of PSNP - beneficiary accounts from WIDE 3

General:
- PSNP cash/food had enabled households to improve their livelihoods by preventing asset sale, releasing income that could be invested, providing collateral for loans and smoothing consumption.
- After droughts, PSNP helps people re-build assets more quickly.

Landless or near-landless poor households
- can borrow from relatives and friends using PSNP income as guarantee
- and so reduce taking high interest loans from moneylenders
- less dependence on firewood selling

Landed households with a number of dependents but low labour supply
- can reduce distress / survival sale of assets
- are more able to pay debt, tax and contributions
- can stop share-cropping land out and regular daily labour and work on own land
- but there may be opportunity costs (time spent away from their own farm due to public works labour obligations)

Poorer households
can invest in planting crops such as coffee and chat that need more than a year to generate income

Better-off households with land and a good labour supply
- can store crops until prices rise and then sell for a better profit
- can reduce asset sales and invest in new assets
- can take more production / livelihood risks

source: Bevan et al 2013a slides 25-29; 2013b p. 5; WIDE 2012 pp. 3, 15.

To boost the effects of transfers on economic activity, programme managers could either increase the value of transfers (as planned under PSNP 4: see below); and / or complement transfers with services specifically focussed on transforming livelihoods. Taking this second line, the Household Asset Building Programme (HABP) has been rolled out since 2010 as a complement to the PSNP transfers programme (replacing the previous Other Food Security Programme or OFSP[30]. The theory of change is that while PSNP transfers help very poor households to stabilise their income and consumption and avoid costly hand-to-mouth survival strategies, transfers alone will not be enough to for large numbers of them to shift to more productive livelihoods and higher private incomes, and so permanently escape poverty. HABP is intended to help households to get on a path of self-sustaining growth and work their way over a poverty trap threshold (and ultimately out of the need for PSNP transfers). It should be noted that to date the Government has extended HABP only to the original four highland regions which had been in PSNP since 2005: the lowland regions, with lower levels of local government capacity, have not been included in HABP. Through HABP, PSNP beneficiaries should:
[30] Between 2010 and 2015, DFID has funded and managed PSNP and HABP as a single programme.
- Receive support from a Development Agent (DA) – a state agricultural extension agent - to help develop a household business plan for a new or improved income-generating activity (IGA), drawing on market and technical analysis of the local livelihood zones;
- With an approved Business Plan, obtain access to credit (up to 4,000 birr, or c. £120) by linking them to the nearest financial services through a regional micro-finance institute (MFI)[31];
  [31] A block grant is provided from the Federal levels to regional BoFEDs: this is then passed to MFIs as a line of credit, from which MFIs provide loans of up to ETB 4,000 to chronically food insecure, PSNP beneficiary households.
- Which they then use to implement their business plan, with ongoing technical advice from the DA;
- Who can draw on HABP-supported, region-specific capacity development activities (value chain analysis and provision of inputs and farm technology).

However, HABP implementation started late and the impact on livelihoods and incomes has lagged behind the (highly ambitious) targets set by the Government in 2009. Programme reporting data shows considerable progress against basic quantitative measures of output, such as the numbers of households with a business plan and MFI loans[32]. However, there are doubts about the quality as opposed to quantity of business plans; loan disbursement varies considerably between Regions[33]; and average loan size has become steadily smaller, to the point where they may not be useful. The household panel surveys used in PSNP-HABP impact assessment find relatively few households reporting access to HABP services[34].
[32] HABP reporting from 2013/14 indicates that a cumulative total of 816,622 household business plans have been developed, up from 683,256 in 2012/13 (Output Group 5, 2014). Assuming five people per household, this translates to coverage for c. 4 million beneficiaries (60 % of total PSNP beneficiaries).. Similarly, programme reporting shows increasing numbers of households have obtained credit and are receiving advice from DAs.
[33] Loan disbursement in EFY 2006 averaged 40% of the target, with considerable regional variation from 220% in Tigray to 8% in Amhara (MoA 2014a).
[34] HABP monitoring data suggests a much wider reach: according to this reporting data, more than one million households have received technical advice, of whom more than 800,000 have prepared business plans. In practice, it seems that neither the monitoring data nor the impact evaluation are particularly suited to capturing the implementation of HABP. The design of the next five years of impact evaluation will incorporate changes (for example, in sampling and the wording of questions) that are designed to better capture the implementation and outcomes of livelihood support services.

There are a number of reasons for the off-track performance of HABP. The need for significant prior investment in institutional capacity development delayed implementation. When implementation began, ownership and accountability was problematic (HABP requires coordination between different line structures, within and beyond the Ministry of Agriculture). Donors who funded HABP financed only the capacity development and implementation costs, and were dependent upon Government financing the provision of HABP credit. When in 2012 changes to arrangements for Federal-to-Regional fiscal transfers removed earmarked funding for HABP credit, Oromia region opted to spend the money on capital-intensive rural infrastructure, so did not distribute any HABP credit. Transfer of the HABP budget to Regions and subsequent utilisation of that budget has often been slow (PSNP 2014); DAs at kebele level are overstretched, face competing incentives and targets for their work, and often lack the skills needed to help households to develop off-farm and employment-focused business plans, resulting in a bias towards on-farm IGAs[35]; and there is an unresolved problem with old outstanding debts among some HABP households who took out loans under an earlier programme, which have prevented some of the most needy households from obtaining access to HABP loans.
[35] With a wide ranging job description, only roughly one third of DAs time is expected to be available to support households to develop business plans (World Bank – key informant interview). Under the Ministry of Agriculture structure, DA areas of expertise typically cover crop science, animal husbandry, and natural resource management.

Despite shortfalls against targets, HABP has had some success[36]. It has shifted the model of Government credit provision from one in which credit was provided by the extension service (which was ill-suited to the role) to one in which it is provided by financial institutions. In 2013/14, MFIs distributed about 535m birr to nearly 200,000 households. The programme has also helped to mobilise savings (a total 129 m birr in 2013/14) to supplement Government-supplied credit. Some 4,569 new Rural Savings and Credit Cooperatives (RuSACCOs) have been created since the start of HABP[37]. Even using the impact assessment results (which are far more conservative than programme monitoring data), the numbers reached by HABP are, in absolute terms, large. Through HABP, 310,000 people have formulated a business plan, 1.16 million have obtained credit for productive purposes, and 763,000 have both access to credit and ongoing support from a local Development Agent (table A3.4).
Table A3.4: Coverage of HABP livelihood services

Source: DFID staff calculations based on (i) percentages from the EFSS (John Hoddinott, personal communication) and (ii) PSNP beneficiary numbers |(2014/15 MoA annual plan)
[36] In quantifying HABP progress, there are substantial differences between the data derived from programme reporting and what emerges from the population-based data (the household panel sample survey conducted every two years for PSNP impact evaluation), which finds very low percentages of households reporting contact with or benefits from HABP.
[37] DFID (2015) p. 11.

In recent years, variants on the HABP model have been piloted, with encouraging results which have strongly influenced the re-design of the livelihood support component of PSNP 4. These draw in particular on experience from livelihoods programmes in Bangladesh, which have achieved large gains through a more intensive support package. This approach has been analysed by CGAP (the Consultative Group to Assist the Poorest), which has then attempted (with Ford Foundation support) to replicate the Bangladeshi experience through ‘Graduation Project’ pilots in six other countries. One of these is Ethiopia, where a pilot has provided a more complex package of services to PSNP households in Tigray, with promising results. By combining provision of support for immediate needs (i.e. safety net transfers) with longer-term investments in skills training, savings services and asset transfers, this has enabled 75 to 98% of participating households to successfully graduate from transfers in a period of 18 to 36 months.

There is also evidence that to achieve household economic behaviour and gains in income, the best results are achieved by combining transfers with livelihood support services. This evidence is however somewhat complex.
- In the first three years of the programme (2005-2008), PSNP resulted in a surprisingly large increase in household investments in assets (mainly livestock) – even as impact on food security in these first years was very modest, with significant gains coming in only after 2010 (Gilligan et al 2009a, 2009b)[38]. While these investments in livestock have productive value (as draft power and potentially a source of income), their role is primarily as savings and insurance.
  [38] Between 2010 and 2012, however, PSNP appears to have had a significant effect on current consumption (and food security) but little impact on livestock holdings. One possible explanation (with some suggestive evidence to support it) is that since 2010 households have tended to switch from quantity of livestock to quality and from a subsistence focus to a more commercial focus, with investment in improved breeds and a rise in the proportion of households reporting income from the sale of livestock products.
- By contrast, household-level investments in agricultural inputs (fertiliser use) and land improvements (stone terracing of fields or fencing to keep out animals) take time to generate benefits and are much less liquid, so perform less of an insurance function but are potentially more important for long-term productivity and food security (Hoddinott et al 2012 pp. 782-3). In 2010, PSNP transfers on their own resulted in modest investments in fencing fields (row 1 in Table A2.6); but the combination of transfers and participation in OFSP/HABP livelihood support resulted in significant gains in household-level investments and input use, relative to (i) those who received minimal transfers (taken as the proxy for no transfers, i.e. the control group), (ii) those who received transfers but no livelihoods support, and (iii) those who received livelihood support, but no transfers (rows 2 through 4 in the table below, respectively). By 2010, these investments had not yet shown statistically significant impact on yields, with one exception: the addition of PSNP transfers significantly increase yields relative to those who received only the OFSP/HABP livelihood package.

Table A3.5: Gains from the combination of PSNP transfers and OFSP / HABP livelihood support, 2006-2010

Source: adapted from Hoddinott et al (2012) pp. 779-782.
*** = statistically significant at 1%; ** = statistically significant at 5%. Results that are not statistically significant at 10% or more not shown.

### A3.2. Local / community level benefits

PSNP has also made aggregate, area-level contributions to rural development and disaster risk management. Improving access to markets and schools, and expanding the area served by small-scale irrigation. Between 2007 and 2013, PSNP public works have rehabilitated more than 600,000 hectares through area enclosures, constructed more than 600,000 km of stone and soil bunds, developed more than 8,000 springs, built more than 4,000 classrooms and constructed 39,000 km of community roads and maintained a further 83,000 km of community roads.

PSNP public works 1: environmental rehabilitation, productivity and climate adaptation
The public works constructed under PSNP have made a sizeable contribution to reversing widespread environmental degradation. For an overwhelmingly rural society, Ethiopia has a relatively high population density[39]. In the Ethiopian highlands, growth of human and livestock populations has over the last century or more resulted in the loss of most forest cover and intensive cultivation and grazing of often steeply sloping land[40]. In the twentieth century, rapid runoff of heavy rainfall on steep and unprotected soil led to high rates of soil erosion and declining fertility. By the mid-1980s, some 27 m hectares or almost 50% of the highland area was considered to be significantly eroded, of which 14 m ha was seriously eroded and over 2 m ha beyond reclamation, with loss of topsoil running to millions of tonnes per annum (FAO 1986 cited in World Bank 2012 p. 41; Ayalew and Selassie 2015 p. 126). Average household landholdings in the highlands are now less than a hectare and soils are typically thin and over-worked, limiting the potential for agricultural productivity gains.
[39] The national average was 90/km2 in 2015 (projected to rise to 100/km2 by 2020: UNDESA 2012): but this obscures very large variations (much higher densities in the highlands, where the majority live, balanced out by very low densities in the southern and eastern lowlands).
[40] Population growth and land pressure in the northern highlands was also a driver of the territorial expansion by which from the late nineteenth century the northern highland Abyssinian kingdom expanded to absorb both the central plateau and the peripheral lowlands. This process of state formation (empire-building, socialist centralisation and now ethnic federalism) continues to the present, with a legacy of incomplete incorporation and unresolved conflict in many parts of the centre and periphery (Markakis 2011).
In the semi-arid eastern and southern lowlands, environmental change is one of the major challenges to the livelihoods and food security of pastoralists. Increasing livestock numbers has contributed to land degradation, competition for pasture and water, and inter and intra-ethnic conflict. While variable rainfall and episodic drought are part of the natural environment in lowland Ethiopia, and pastoralist communities have an array of traditional coping mechanisms and resiliencies, the increased frequency of extreme weather and droughts threatens to overwhelm these coping mechanisms (Devereux 2006; Stark et al 2011).
These long-term trends towards environmental degradation – in both highlands and lowlands - have in recent decades been exacerbated by climate change. Ethiopia is one of the countries most vulnerable to climate risks in Africa. This is in part because of the projected changes in temperature, precipitation and soil moisture; but also in large measure because of the country’s heavy dependence on rainfed, subsistence agriculture. Mean annual temperatures have increased by 1.3oC between 1960 and 2006: while average national rainfall has not been decreasing on an annual basis, the March-through-May belg rains (which constitute the main rains for the southern regions of Ethiopia) have become increasingly variable and extreme. Southern Ethiopia in particular has experienced extremely low rainfall events in recent decades, with severe droughts in 2006, 2008 and 2010/11. While climate models for the Horn of Africa tend to agree in predicting large magnitude changes, they often disagree on the direction of change. This puts a high premium on measures (in PSNP and other programmes) that will support resilience under a wide range of future climate scenarios[41].
[41] The most likely scenarios suggest higher temperatures and higher annual rainfall; but with rainfall increasingly concentrated in intense events resulting in high rates of runoff and lower levels of infiltration and soil moisture. Temperatures are predicted by the IPCC to continue to rise in the range of 0.9-1.1oC by 2030, 1.6-2.0oC by 2050, and 2.5-3.5oC by 2080 (LTS et al 2013; World Bank 2013; Stark et al 2011).
PSNP public works have helped to reverse this process of long-term environmental degradation; and to build household- and community-level resilience to the effects of climate change. Based on a participatory annual planning process that takes the watershed as the planning unit, the majority of PSNP public works activities to date have focussed upon extensive soil and water conservation (SWC) measures, including soil and stone terracing, percolation trenches, half-moon dams, and gully control structures. Following stabilisation, large areas of hillside have been enclosed to exclude firewood collection and grazing, allowing for the re-growth of vegetation that further helps to reduce runoff and restore the water table, leading to longer periods of seasonal stream flow and open up possibilities for small-scale irrigation (SSI) schemes. As part of the three rounds of Public Works Impact Assessment (PWIA), bio-physical studies have constructed several measures of PSNP environmental impact:
- The reduction in soil loss due to PSNP public works is estimated to average between 12 tonnes per hectare (Metafaria Consulting 2013 p. ix) and 15 tonnes / ha. (MA Consulting 2009 p. 10).
- There are significant, visible increases in wood and herbaceous vegetation cover on degraded communal lands that, prior to stabilisation and enclosure through the PSNP, suffered from over-grazing and soil erosion. Watershed-level increases in biomass ranged from 58% to 82%, providing a resource for the community (cut-and-carry fodder for livestock, forage for bees, and the possibility of the extraction of timber or non-timber forest products in the future).
- By reducing surface runoff and increasing infiltration, SWC activities have raised groundwater levels, enhanced springflow and increased stream base-flow levels. Communities report that springs continue to flow longer into the dry season. The recharging of the water table makes it possible to improve water supply (through shallow hand-dug wells) and begin to introduce small-scale irrigation (SSI) which can reduce harvest losses during a bad year, and enable double-cropping during a good year (MA Consulting 2009a pp. 9-10).

The reduction in runoff and soil erosion and the resulting rehabilitation of local natural resources give rise to significant benefits in terms of local economic development. In the 12 locations studied in the third (second 2011) PSNP public works impact assessment, per-hectare yields increased by 66% for cereals, 22% for pulses, and 8% for perennial crops following SWC activities (Metafaria Consulting 2013 pp. 36-7). Gains in livelihood diversification and income emerge in account from beneficiaries and local officials (see Box); and are experienced by both those who receive PSNP transfers and their better-off neighbors.

Box A3.2: Public works have enabled productivity gains and livelihood diversification

A. Beneficiary perspectives

Young men organized in a group and have started beekeeping using the area closures protected by the Safety Net. Transitioning beneficiary FGD, Sokota woreda, Amhara

Our soil is preserved, our animals are getting enough grass and forests are developed in our locality. Women beneficiary FGD, Saesi Tsaedamba woreda, Tigray

Bunds constructed on hillsides help to regenerate trees and fodder. The youths are now organized and have started to harvest the regenerated grass to sell for animal feed and roofing material. It also reduced flood erosion which in turn helped us to increase land productivity. Transitioning beneficiary FGD, Zeway Dugda Oromia

Grass for animals is growing in the hills. People use the grass for their animals and I know there are people who sell the grass here in the village. DS beneficiary FGD, Erer woreda, Somali

Some households were collecting grass from area enclosures for their animals and there are a few who get a small benefit by selling grass. Women’s beneficiary FGD, Erer woreda, Somali

The farm lands retain water that helps us to increase crop production. A plot that used to produce about six to nine bags of cereals is now producing up to 16 bags as a result of public works. Men’s beneficiary FGD, Sokota woreda, Amhara

B. Perspectives of local officials

In this kebele, irrigation fields grew from 25 hectares to 108 hectares. The farmers have recognized this contributes to the productivity of the land, which has improved from 10 to 30 quintals per hectare. DA, Sayint woreda, Amhara

Yes, soil fertility has improved. There are plots from which harvest was around 10 quintals per hectare, that have reached up to 30 quintals per hectare. DA, Sayint woreda, Amhara

The livelihood of the people has also been changed. Now the water potential has increased due to the PSNP conservation works and the community is busy working on their irrigated plots... Before the PSNP, it was only possible to earn 60-70 quintals per hectare and now it reached 320 quintals per hectare. DA, Ahiferom woreda, Tigray

The constructed soil bunds have helped rangeland rehabilitation in the kebele, and the increased availability of feed has led to improvements in the price of animals. DA, Harshin woreda, Somali

First, those people who do not have cash were able to get money through the public works they have done, and became further involved in business activities by transporting their products by donkey carts on roads that were constructed by the Safety Net. People with livestock like cows and oxen now are able to access grass because of terracing work done and the grasses and trees that were planted. As a result of this, they increased their production and productivity of their animal. DA, Tembaro woreda, SNNPR

We treated and changed gully sites and made it source of cash income for us. We grow animal feed like elephant grass on this treated land. We are also able to produce fruit crops like papaya and avocado and backyard vegetables. We also built three big dams. Look at these mountains. They were nude. We planted trees and rehabilitated them as you see them now. FSTF, Saesi Tsaedamba woreda, Tigray

Sources: Berhane et al 2013 pp. 183-191; Lind et al 2013 pp. 125-127.

However, these gains from natural resource management (NRM) take some time to emerge. This is one explanation for the more limited NRM-related benefits reported from public works in the lowland regions, where PSNP implementation only began from 2010 (as opposed to the highlands, where PSNP started five years earlier). However, there are also other reasons for the more limited impact of public works on NRM-related livelihoods in the lowlands. These include difficulties securing consistently adequate labour inputs, given the mobility of the lowland pastoralist and agro-pastoralist groups and the limitations to the number of hours it is possible to work each day in the lowland heat; combined with shortfalls and delays in the delivery of materials and tools to widely-spread work sites. Recurrent drought during the last five years has meant that the benefits of some public works (e.g. SWC activities designed to allow grass to re-grow; tanks designed to capture and store rainwater) have yet to be felt[42].
[42] In assessing the more limited impact to date of public works in the lowlands, it should also be noted that the mix of public works types in the lowlands is different from that in the highlands: SWC activities are a smaller share of the total, with rural roads dominating and generating significant advantages in the form of access to health services (and maternal health services in particular).

PSNP public works 2: infrastructure improves access to services and markets in poor rural districts

The majority of households in PSNP woredas report that public works have directly benefited them, with roads, health posts and schools benefiting the greatest numbers. The impact assessment (see table A3.6) includes responses from both transfer beneficiaries and non-beneficiaries, confirming that, as intended, these contribute to local economic, social and environmental development for the community as a whole.

Table A3.6: Percentage of all households reporting they benefited from PSNP public works, by type (2012)
	PSNP transfer recipients / 2012/13	roads	water harvesting	SWC (communal land)	SWC / (private land)	wells	schools	health / posts
Amhara	1,819,607	73	43	45	50	59	59	70
Tigray	1,238,677	62	45	46	49	30	39	73
SNNPR	1,264,026	86	72	55	42	63	79	86
Oromia	1,300,003	77	71	51	55	50	59	75
Somali	729,390	76	71	77	65	90	96	100
Afar	472,229	78	68	45	55	78	66	26

Source: Berhane et al October 2011 p. 115; Berhane et al July 15th 2013 p. 191; Lind et al 2013 p. 129

The value of PSNP public works also comes out in the qualitative component of the impact assessment. There is a need for continued attention to address some technical weaknesses (particularly with regard to roads and water supply sub-projects, and in the lowlands in general): however, the general perception emerging from beneficiary feedback is highly positive (see Box A3.3). In the lowlands, rural feeder roads are particularly appreciated: a consistent theme is that these roads improve access to health care, particularly maternal healthcare (Lind et al 2013).

Box A3.3: Beneficiary perspectives on the impact of public works: quotes from the 2012 focus group discussions

- Due to the Safety Net, places where even hyenas cannot pass through are opened to the people to walk easily… Before this road was constructed there was no access to the market, and we used to sell our products cheaply. Now we have access to the market and can sell our produce at good prices. We used to carry sick people to health facilities by ourselves. Now vehicles can enter into our village and take sick people and pregnant women to health posts. FGD, SNNPR.
- We were able to attend this meeting because of that road we constructed. When someone got sick in the past we used four sticks to bring to the road but now the Bajaj [motor-rickshaw] can enter and take sick people. FGD, Somali
- The community now has better access to safe drinking water. Each of the [village] clusters has 2 to 3 safe water supply schemes, most of which are built under the PSNP. Development Agent, Tigray

Sources: Berhane et al 2013 pp. 183-191; Lind et al 2013 pp. 125-127.
Local economic multiplier effects

The injection of cash transfers into poor communities generates local multiplier effect, as beneficiaries spend their additional income on goods and services, most of which (particularly food) are purchased locally. Non-food consumption of PSNP clients in the highlands increased by 19% between 2010 and 2012 (somewhat more than the increase for the survey sample as a whole: Kumar and Hoddinott 2013 pp. 38-41) and traders in all regions report that demand (for food and other goods) increases due to PSNP cash transfers.
These income multiplier effects seem to be sizeable. The Protection to Production Project (PtoP), run by the FAO, has researched these effects in seven sub-Saharan African countries. In Ethiopia, PtoP studied the multipliers generated by the UNICEF-supported Social Cash Transfers Project (SCTP). The SCTP worked in two tabias[43] (one urban and one rural) in Tigray to provide cash transfers of a similar value to those provided by PSNP 3, to labour-poor households equivalent to the Direct Support beneficiaries under PSNP (with design innovations surrounding the development of a social worker profession and creation of community care coalitions (CCC) to link SCTP beneficiaries with other social services). From 2015, the SCTP approach will be incorporated into PSNP 4 arrangements for Permanent Direct Support Beneficiaries. As such, the PtoP findings on multipliers in the SCTP can be taken as a good basis for predicting the multipliers that can be expected from PSNP 4.
[43] A tabia is the Tigrinyan equivalent to a woreda.

Using a local economy-wide impact evaluation (LEWIE) model, the PtoP study estimates that each birr transferred through the SCTP generated between birr 1.26 and 2.52 birr, depending on location and how local supply response is assumed to work. Table A2.8 summarises these results. For the purposes of forecasting PSNP impact, the more conservative estimate from the rural site is chosen (1.84). This implies that every 1 birr that PSNP 4 provides in transfers generates an additional 0.84 birr in local income. The majority of the additional income accrues to local non-PSNP beneficiaries.

Table A3.7: Local income multipliers of cash transfers in Tigray

district		simulation assumptions
		unconstrained supply response	credit, capital and other market constraints modelled
Abi-Adi	urban	1.35	1.26
Hintalo-Wajirat	rural	2.52	1.84

Source: Kagin et al 2014.

### A3.3. National level benefits

PSNP 3 contributions to managing drought shocks

PSNP 3 has helped Ethiopia to mitigate the impact of natural disasters, particularly drought shocks. As described in the Strategic Case, Ethiopia has a long history of drought events which in the past have often precipitated large-scale famine. Reflecting the importance of low input rainfed agriculture to the Ethiopian economy, weather shocks have also in the recent past had a significant impact on GDP and national economic growth rates (Figure A3.4)[44].
[44] The relationship between rainfall and economic growth has become weaker since the early 2000s. There are several possible interpretations to this. One is that new policies and programmes – including PSNP – have increased economic resilience to climate shocks. Another is that the reliability of official estimates of GDP (and agricultural production in particular) have become questionable: a point made by several economists.

PSNP has helped Ethiopia to manage these shocks more effectively, both through (i) ex ante mitigation effects (improving household economic status and building up their buffers in advance of a shock, combined with improvements in soil and water conservation through public works which have replenished water tables) and (ii) strengthening household capacities for ex post coping (as transfers sustain basic consumption in the face of a drop in subsistence food production). ICAI and others credit PSNP (both the regular safety net and the scaling up through the RFM) as making a significant contribution to Ethiopia’s success in managing the 2010/11 Horn of Africa drought crisis: the impact in Ethiopia was much less than in neighbouring Kenya or Somalia, and much less than in Ethiopia in the past (ICAI 2012).
Figure A3.4: Correlation between rainfall and GDP growth

Source: GoE 2011 p.11.

The design of PSNP 3 recognised that shocks (primarily drought) would continue to affect rural Ethiopia, pushing vulnerable households into short-term (transitory) food insecurity. Some of these shock-affected households would find it hard to recover, and so join the chronically poor population who need multi-year assistance.

To prevent this, PSNP 3 included two instruments to enable the PSNP to scale up in response to shocks. The first was a contingency budget (CB) amounting to 20% of the value of the core programme budget (5% held and managed by woredas, and 15% by Regions). These budgets would be used to respond to localised shocks by extending the transfer season for existing client households and / or bringing newly food insecure transitory clients onto the programme for one year. The second instrument was a risk financing mechanism (RFM) consisting of pre-positioned funds managed by the federal Government. If a shock was large, and both woreda and Regional contingency budgets were exhausted, the RFM would be triggered to enable transfers to shock-affected households (whether existing or new beneficiaries). Both contingency budgets and the RFM could only be used in PSNP woredas, where PSNP implementation arrangements were in place. Food aid from the humanitarian system (provided in response to the needs assessment in the annual Humanitarian Requirements Document or HRD) would only be needed to address needs in non-PSNP woredas, or in PSNP woredas when the scale of need was such that all other sources of finance (CB and RFM) were inadequate.

The intention was thus that PSNP regular transfers, contingency budgets, RFM and humanitarian response system would work together in a harmonised way to ensure further erosion of food security. The RFM Guidelines laid out a sequence for responding to progressively larger shocks, in which contingency budget resources are used first; if it is anticipated that these will be inadequate, RFM resources are triggered in time to be available when CB funds run out; before resorting to resources released through a humanitarian appeal, if the RFM is in turn exhausted. The regional contingency budget and Federal RFM would be triggered in response to analysis of monthly early warning reports (produced at woreda level and passed upwards); while use of triggered funds would be informed by PSNP-specific contingency plans.

In practice, woreda CB funds have been used primarily to address exclusion errors in the core programme (i.e. to bring un-served chronically food insecure households into PSNP); while, with the exception of Tigray, regional CB resources have been used to address transitory needs[45]. However, annual contingency budgets were often not fully used[46]: instead, humanitarian resources generated through the HRD appeal have been used to meet needs in PSNP as well as non-PSNP woredas. Unfortunately the HRD has generally assumed that CB resources had, or would be, fully used each year (as in principle it should be), and so deducted from the estimated seasonal needs numbers the number of people who could be addressed through the contingency budget. This has resulted in an under-estimation of the humanitarian food aid required.
[45] In Tigray, the regional contingency budget was used to extend the number of months in which direct support beneficiaries received PSNP regular transfers, in recognition of their more significant needs: a policy which is now reflected under PSNP 4 in the category of Permanent Direct Support clients, who will receive transfers for 12 rather than just six months each year (Girma Tegenu and Mulugeta Eshetu , 2013 and Guush Berhane et al., 2013).
[46] Annual utilisation of the regional CBs averaged between 60% and 82% in the first four years of PSNP 3: Loveless and Palacious (2013).

The decision making process for the release of the Regional contingency budget is not clear. While contingency budgets should be released on the basis of information generated by the monthly early warning system, this data is extensive but often poor quality, and regional analysis limited (Loveless and Palacious 2013). Instead, Regions have drawn on a mix of sources, including needs assessments and hotspot analysis, to inform decisions. It also seems that regions may have under-used their CB to conserve funds in case there are needs later in the year which they cannot be sure will be confident will be addressed through RFM or humanitarian resources.

Under PSNP 3, monitoring and financial management systems have made it hard to track the use of contingency resources. Formats for collecting monitoring data have not required information on additional beneficiaries enrolled using the contingency; the PASS accountancy software has not been used to manage CB payrolls; there has been a mismatch between physical and financial reporting, with Regions often reporting levels of CB utilisation higher than those presented in annual financial reports. The fact that contingency budget use often spans financial years further complicates reporting (Girma Tegenu and Mulugeta Eshetu 2013). Finally, difficulties in using and tracking contingency budget resources are particularly pronounced in Afar and Somali, due to both lower levels of administrative capacity but also the additional logistical challenges of managing the contingency in the form of food rather than cash.

The Risk Financing Mechanism, too, has been used in ways which have diverged significantly from what was planned, and which have reduced the impact that it should have had. The RFM was triggered in 2011 in response to the 2010/11 Horn of Africa crisis, to address transitory food needs for 9.6 million people, 6.5 million of whom were existing clients (who received an additional three months of transfers). A number of reviews (e.g. ICA 2012, Sida et al. 2012) conclude that it brought much-needed additional resources to the response to this extremely severe drought and (together with the regular PSNP programme) complemented the humanitarian response, enabling Ethiopia to avoid the severe impact seen in neighbouring Somalia and northern Kenya (and, indeed, the severe famines seen in Ethiopia itself following earlier droughts).

However, implementation was extremely muddled, significantly reducing the efficiency and effectiveness of the response. There were a number of related problems.
- Sequencing of interventions did not follow the principles laid out in the RFM guidelines. Rather than being triggered by routine early warning data (which indicated a need to respond as early as February 2011) and coming in early to precede and frame the release of an appeal for additional humanitarian resources, the RFM was delayed, such that it was partially informed by this appeal and regional requests made in June/July 2011. Funds were only released in August 2011 and reached woredas between October and December, after humanitarian food aid distribution began in April (Gray and Asmare 2012).
- Contingency budgets remained available and unused (utilisation stood at 88% and 82% respectively for the financial years ending in July 2011 and July 2012) even as the RFM was being brought in[47].
  [47] It should be noted however that the unspent balance of contingency funds is equivalent to only 5% of the RFM that was spent: Gray and Asmare (2012), MOFED (2011) and MOFED (2012).
- Poor coordination between PSNP and humanitarian implementation caused misunderstanding about which populations might be covered by different instruments, contributing to delays and gaps in coverage, with some groups who did not receive assistance until late in the year (Sandford (2012a), OCHA (2012) and Sida et al. (2012).
- Differences between the value of PSNP and humanitarian transfers created confusion and inequities. The value of the PSNP transfer was lower than that of the full food basket which the humanitarian response aims to offer.

Thus, while the PSNP (both the core programme and RFM) helped avert famine in 2011, it was not sufficient to prevent the drought from negatively affecting household food security and livelihoods. There is limited rigorous data, but anecdotal evidence suggests that significant asset depletion occurred as a result of the 2011 crisis. This conclusion is supported by the PSNP impact evaluations, which show that while PSNP beneficiaries suffer less from the effects of a shock, they still experienced asset losses and reduced consumption (Béné et al. 2012).

The RFM was triggered a second time under PSNP 3 in 2014. Once again, RFM funds were used in ways that were poorly harmonised (in terms of timing, targeting and modality) with humanitarian resources, and as a result much less effective than they should have been. Donors and Government agreed to trigger the RFM in March, with a recommendation for immediate release in the form of cash transfers; but four months passed before RFM funds were transferred to the regions and (in part) on to the woredas. At this point, food prices were significantly higher, and as a result the cash resources of the RFM would be much less effective as a tool for helping households obtain food. The Ministry announced a preference to use the RFM to provide food transfers; and in August stopped further transfers of RFM funds from the Federal level to the regions, and from the regions to the woredas, in order to pursue the food procurement option. This was problematic as World Bank procurement rules require time; and the proposed source (WFP stocks) required the Bank to get Vice-Presidential approval for a very large sole-source procurement. While early warning data worked better and decisions were taken more promptly than in 2011, long delays in acting on this decision and a mid-course change of approach reduced the effectiveness of this spending.

### A3.4. Global-level outcomes: climate change mitigation

Public works impact assessments suggest that PSNP has resulted in large-scale carbon sequestration through soil stabilisation and area enclosure resulting in biomass regeneration. Two public works impact assessments have estimated the quantity of carbon sequestered per hectare in areas enclosed and protected through PSNP. Table 17 summarises the most recent estimates; which are in line with those from the earlier PWIA, which estimated total CO2 sequestered after five years in the two sample watersheds at 1.45m tonnes (Sutcliffe 2011 p. 23). Given the number of watersheds improved through PSNP public works each year, it is likely that PSNP has a sizeable impact on carbon capture. This opens up the possibility for the Government of Ethiopia to tap into international carbon markets for much-needed development finance. A number of factors have to date made this difficult, but a DFID-supported Climate Smart Initiative is supporting analysis of PSNP-based climate financing options and advising the Government on strategy.

Table A3.8: Estimated rates of carbon sequestration due to environmental rehabilitation (after 5 years)

soil cover type		estimated carbon sequestration (tons / ha)
before PSNP activities	after PSNP activities
bare soil	grassland	0.99
degraded grassland	open shrubland	4.84
open shrubland	dense shrubland	5.06

Source: Metafaria Consulting Engineers 2013 p. v

Through the ICF-funded Climate High-Level Investment Program (CHIP), the Climate Smart Initiative (CSI) aims to strengthen the PSNP by integrating climate change considerations into PSNP operations on a systematic basis. CSI has supported assessments of the PSNP and HABP and pilots of promising and innovative interventions in 24 districts. Informed by lessons from these pilots, CSI has fed into the design of PSNP4. PSNP4 will significantly increase the land covered by improved watershed and rangeland management structures and practices.

Annex 4: PSNP 4 theory of change and estimation of results
The theory of change for the proposed support rests upon a number of assumptions about how inputs will give rise to outputs, outputs to outcomes, and outcomes to impact and policy-level objectives (DFID 2012; Browne 2013). The key assumptions informing the design of the programme are summarised in Table A4.1. The diagram on the following page provides more detail on this intervention logic by making explicit the assumed causal relationships and assessing the strength of the evidence underlying each assumption. Using the definitions and indicators from the results framework and logframe included in the PSNP 4 Design Document, Figure 4 maps the cause-effect relationships by which outputs (on the left) are assumed to contribute to achieving the indicators that define the Programme’s outcomes and impact (on the right). The width of a given arrow linking one step in the results chain to the next provides an indication of the strength of evidence for this given link: a thin arrow indicates sound theory but limited Ethiopia-specific evidence to date, whereas a thick arrow indicates a high degree of confidence that A will indeed lead to B, based upon the evidence base that now exists.
The theory of change also attempts to highlight how results at a higher level are often dependent upon a combination of processes and achievements at a lower level. Improvements in livelihoods, for example, will require a combination of household-focussed activities (regular and lump-sum transfers, advice on income-generating activities, and access to credit) and locality-level improvements to the natural resource base and market integration through public works.
Broadly speaking, assumptions are least contentious with regard to the results that are expected from transfers and public works. The evidence base for these cause-effect relationship is derived from a large volume of rigorous PSNP impact evaluation and, more broadly, from evaluations of programmes in other developing countries. Assumptions are less robust, and the arrows thinner, with regard to the more innovative design elements introduced in this phase of PSNP. These include the linkages to nutrition programming; the effectiveness of livelihoods support (and in particular the development of off-farm and waged incomes, which lagged under the previous phase of PSNP-HABP); the development of effective coordination mechanisms to link MoA implementation arrangements with contributions from other Ministries; and the time and cost required to commission and implement some large and important pieces of work (including a computerised management information system) which should strengthen programme and system capacity.

Table A4.1: Key assumptions in the theory of change

Context
A significant percentage of the rural poor experience high levels of poverty and vulnerability due to dependence on rainfed agriculture; small plots; a degraded natural resource base; variable rainfall; remoteness and lack of market integration; and limited off-farm income opportunities.
These micro-economic household-level phenomena have negative aggregate macro-economic effects. Malnutrition during childhood limits labour productivity as adults, resulting in a drag on growth; coping strategies employed by households to avoid or survive shocks (planting tough but low-return crops rather than riskier but higher-return cash crops; keeping children home from schools or taking dowry for early marriage of daughters) make it harder to later escape poverty.
The Programme can secure the financing necessary to deliver at the scale and sophistication anticipated in the Design Document. The Government and other donors will deliver on their existing funding commitments; additional funding can be secured to address the financing gap currently existing between the five-year budget and the total commitments to date.
Inputs to outputs
Government and World Bank systems will use funds efficiently and effectively. DFID funding will be used to make the long-term investments (in programme management capacity and systems development) and deliver the services (transfers, livelihoods and nutrition advice to households, construction of public works) outlined in PSNP plans. Effective targeting will ensure that transfers and other assistance reaches the intended beneficiaries.
Outputs to outcomes and impact
Households are fundamentally rational. Extremely poor, cash-constrained households will use the transfers and advice that they receive to improve current consumption (food, healthcare, education); and / or to invest in their future (keeping girls in school rather than marrying them off for a dowry; buying inputs for improved agricultural productivity; diversifying into off-farm microenterprise; or searching for a waged job). Impact evaluations suggest confidence in this.
Public works contribute to local economic and social development. To do so they will need to be adapted to local needs; well-integrated with local Government planning of infrastructure and service delivery; help communities to cope with climate change; and meet technical standards for quality. This is largely achieved in the highlands; but less certain in the lowlands.
Coordination is possible and delivers the hoped-for synergies. Different parts of the Ministry of Agriculture (MoA) work together to deliver the combination of transfers, extension advice and appropriate, technically-sound public works that is needed to improve livelihoods and build climate resilience. The MoA in turn can work together effectively with other Ministries (MoFED, MoLSA, MOH) to link PSNP beneficiaries to nutrition services and off-farm economic opportunities. International experience and pilots such as the Tigray CGAP and SST programmes suggest cross-Government coordination is possible and does deliver additional benefits; but this will need to be achieved at scale and within the programme timeframe.
Capacity is adequate to deliver the proposed services; or can be strengthened over time through the proposed capacity-building activities. Local authorities in the new intake woredas can be brought up to strength in time to take on programme implementation responsibilities.
The economy continues to expand and creates economic opportunities for the rural poor. The PSNP protects poor households against falling back, and provides the first few rungs of a ladder to work their way out of poverty; but markets and other Government programmes need to be in place to provide the next few rungs.
Impact to policy objectives
Over the next five years, PSNP succeeds not only as a programme but as the foundation for achieving cross-Government policy objectives. PSNP capacity development and coordination arrangements will provide a core set of administrative and management systems (for targeting, case management, monitoring, etc.) which can be and are adopted by other poverty-targeted programmes, and which help to coalesce complementary programmes and policies into functioning Government systems for social protection and disaster risk management.

Figure A4.1: Theory of change for PSNP 4

The remainder of this section elaborates on this theory of change, summarising the results that are expected from support to PSNP 4 and the evidence or estimation underpinning these estimates. Most of these expected results have been extracted from the targets contained in the programme logframe in the PSNP 4 Design Document (also incorporated in the Results Framework of the World Bank PAD). These reflect some 18 months of discussion between the Government and donors[48]. In addition, in some few cases, the Business Case has attempted to extend on these documents with additional efforts to quantify expected benefits. These predicted results are based on the evidence of impact observed to date under PSNP 3 and - where relevant – that achieved under the UNICEF Social Cash Transfer Programme pilot (which will be folded into PSNP 4). The details of this evidence have been summarised above, and is described in more detail in Annex 3. In each section, we note how the changes to be introduced in PSNP 4 (taken primarily from the PSNP 4 Design Document, the World Bank PAD and the new Programme Implementation Manual) are likely to increase or decrease future impact, relative to what has been observed to date.
[48] Only selected logframe indicators are reproduced in the Business Case under ‘expected benefits’. The full programme logframe is very long consensus document: while considerable effort has gone into it, and it is on balance a much more useful framework than the PSNP 3 logframe, there are still questions about some of the indicators and targets. Some of the newly-introduced indicators are useful additions, and can credibly be measured: but without baseline data (which should be obtained from the late 2015 impact evaluation survey), have not yet set target values, and so are not included in the Business Case. For some of the other new indicators, the complex construction of the indicator definition or questions over the data collection instruments that will provide the source for these indicators: and so are not included in the Business Case.

Within this overall picture, the level of confidence with which it is possible to predict impact, and the level of precision with which it is possible to predict the magnitude of impact (and so set targets), varies between different outcomes. Thus on the basis of observed trends in PSNP impact in four Ethiopian regions to date, it is possible to predict with a high degree of confidence that cash transfers will have impact on food security and poverty in established programme areas; and to estimate the size of this impact in in advance with a reasonable degree of precision. The evidence for the impact of the programme on schooling, by contrast, is more limited (there is evidence of a strong positive effect from both PSNP and SCT, but to date this has only been explored in one region). Moving towards the lower end of the spectrum, the size of any possible impact on nutrition is much less certain, as to date neither PSNP nor SCT has shown any impact on nutrition, and the innovations that are being introduced in this new phase (to connect transfer-recipient households to nutrition advice and services) have not yet been implemented in Ethiopia. While the logic behind these innovations is sound and there is evidence from other countries, there are no Ethiopia-specific findings from which to extrapolate.

Finally, it is extremely hard to produce credible quantitative or monetized estimates of benefits to be expected from building institutional capacity and achieving integration between different elements of an emerging national social protection system. This is in part because institutional capacity and coherent systems are harder to define and measure than are final outcomes such as food security (the food gap) or living standards (per capita consumption). It is also in part because these objectives are relatively new, within PSNP specifically and within social protection programming globally. While capacity development has been an objective of PSNP for the last five years, it has been a relatively minor focus compared to that of household-level outcomes: less has been done, and less measured.

#### 1. Household level benefits

Consumption and food security: changes to transfer coverage, generosity and modality

PSNP 4 will incorporate a number of changes which on balance are expected to increase the impact of the programme on household outcomes, beyond that which was obtained under PSNP 3. There are two major changes that will increase the generosity of the programme, and the likely direct impact on recipient households.
- Firstly, those designated as permanent direct support clients (the elderly, those with disabilities, the chronically ill) will receive continuous rather than just seasonal support: that is, they will receive transfers for 12 rather than just six months each year, covering 90% of their food gap.
- Secondly, monthly transfer values will increase for all recipients. To date, the transfer value has been pegged to the cost of 15kg of grains per person per month. In the next five years, the value will be based upon the cost of 15kg grains plus 4kg of pulses (costed at a cash value of £4.4 / $6.8). This will bring the nutritional value much closer to that of the humanitarian food basket, which is designed to provide a full 2,100 kcal / person / day[49]. This new transfer value is expected to result in improved levels of household consumption as a result of the increased kilocalorie value and higher protein and fat contents[50], as well as more significant consumption smoothing and livelihood impacts because of the higher value of cash transfers (MoA 2014a).
  [49] The PSNP transfer will remain somewhat short of direct equivalency with the full humanitarian food basket, which is meant to include oils as well as grains and pulses.
  [50] It is worth noting that although the new transfer reflects significant improvement in nutritional value, it does not provide all necessary micronutrients and fat, and therefore linkages to other nutrition interventions, where available, will remain important.
These two changes constitute a significant increase in transfer value. For public works and temporary direct support clients, annual transfer receipt will increase by over 50%; permanent direct support clients will receive three times what they received under PSNP 3 (Table A4.2). It is estimated that PSNP transfers will account for on average 45% or more of the annual food needs of beneficiary households (World Bank 2014 p. 110). This increase in transfer values from the very low levels employed to date is in line with the recommendations in the NAO and PAC studies on value for money in DFID-supported transfer programmes.

Table A4.2: Increase in transfer value (2015 birr per beneficiary per annum), PSNP 3 to PSNP 4

		PSNP 3 (2011)			PSNP 4 (2015)			change, PSNP 4 cf PSNP 3
		PW	DS		PW and temporary DS	permanent DS		PW	DS
caseload		6,483,178	1,158,980		6,425,100	713,900
grains	kg	15	15		15	15
	birr / month	91	91		91	91
	months	6	6		6	12
	p.a.	543	543		543	1,087
pulses	kg				4	4
	birr / month				48	48
	months				6	12
	p.a.				288	576
total p.a.		543	543		831	1,663		153%	306%

Costs (2014 prices): 6 birr / kg grains, 12 birr / kg pulses
Source: DCT and World Bank unit costs; analysis by DFID Ethiopia staff

In addition to the changes described above, which will increase the impact per beneficiary, the expansion of the programme will bring these benefits to more beneficiaries. The geographical coverage of the programme will expand from 319 woredas to 411 (with 41 woredas brought into the programme in 2016/17 and 51 in 2017/18). The programme caseload, which under PSNP 3 has declined from a high of 7.6m in 2011/12 to the current level of under 5.2m in 2014/15, will rise to and stay at 10m for the next five years. (This would mean that PSNP caseload is equivalent to roughly a third of the population in poverty in 2010/11.) With more generous programme benefits reaching a greater number of people, the impact of PSNP 4 on aggregate national welfare indicators (mean p.c. consumption and food gap, poverty rates and utilisation of services amongst the poorest) is expected to increase significantly on that which was achieved under PSNP, as described above.

Trying to estimate the size of the likely impact on programme-wide outcomes is however complicated by the fact that the programme will be expanding to enrol new beneficiaries. This expansion will include right-sizing the programme in the 319 woredas that constitute the current operational area of PSNP 3, where the programme in 2014/15 is not currently reaching all those in need. The expansion will also be geographical, as the programme expands into 92 new woredas. We do not yet have baseline values for beneficiary households’ consumption, food security, educational enrolment or asset values in the 92 new woredas; but they are likely to be lower on average than amongst the clients in the 319 existing woredas, as many of these households have been enrolled in the programme for a number of years already. This is partially captured in the logframe outcome targets, which disaggregate between current and new beneficiaries in terms of the expected results for food security; but not for living standards (see logframe extract in Table A4.3)[51].
[51] There is a seeming anomaly in that the average level of food insecurity amongst PSNP 3 beneficiaries is already at 1.5 months (the finding from the 2012 impact assessment): yet this is set as the target for PSNP beneficiaries for 2017/18, suggesting no progress is required between 2012/13 and 2017/18. However, the population of current PSNP 3 beneficiaries will have been reduced through graduation in 2013 and 22014, and will be further reduced through re-targeting for PSNP 4 in late 2015. At each of these stages, those with zero or minimal food security will have been removed from the programme; pushing upwards again the average level of food insecurity amongst those remaining and continuing on the programme into PSNP 4.

Table A4.3: Expected benefits: food security and living standards

Outcome indicator			baseline	year 1	year 2	year 3	year 4	year 5
				2015/16	2016/17	2017/18	2018/19	2019/20
1	Number of months of self-reported food insecurity (including safety net transfer) for PSNP - disaggregated by PSNP 3 beneficiaries and all beneficiaries	prior (PSNP3) beneficiaries			1.5		1
		all beneficiaries			2.9		2.3
2	Average non-food expenditure of PSNP PW clients (2012 constant birr per adult equivalent per month) - disaggregated by sex		212 / (2012)		300		360

Source: MoA (2014) p. 111.

An integrated approach to nutrition promotion

PSNP 4 introduces arrangements designed to improve nutritional outcomes for PSNP recipients, and so contribute to the realisation of the targets in the National Nutrition Programme (NNP)[52]. Most immediately, the increased transfer value described above should contribute to improvements in both the quantity and quality of food consumed by recipient households. In addition, nutrition-sensitive considerations are incorporated into the new programme under eligibility and targeting rules; the menu of livelihood activities and public works that are available to communities; accountability and reporting requirements; and, critically, linking PSNP beneficiaries to knowledge and services which should improve nutrition outcomes (Bossuyt 2015a, 2015b; PSNP 2015; World Bank 2014 p. 11).
[52] The National Nutrition Programme is overseen by a National Nutrition Coordinating Body, chaired by the Ministry of Health and co-chaired by the Ministries of Agriculture and Education. It aims to achieve large-scale reductions in stunting, wasting and chronic undernutrition, focussing heavily on the critical first 1,000 days from conception to when a child reaches two years of age. The NNP works in conjunction with the Health Extension Programme (HEP), which provides free services for a range of basic health interventions (immunization, impregnated bed nets and treatment for malaria, severe malnutrition and pneumonia in young children) as well as behaviour change communication (BCC) through health extension workers and a volunteer “health development army (HDA)” (MoA 2014 p. 7).

Targeting will aim to enrol in the transfer programme those who are either vulnerable to or already experiencing malnutrition. These measures incorporate a mixture of sensitization ‘nudges’ and explicit rules relating to who receives PSNP transfers, and under what terms.

Targeting will still be based upon community discussion; but designed to be preceded by information and discussion on the nutritional needs of pregnant and lactating women in poor households.

The programme will extend transfers to households affected by a nutritional emergency, to increase the effectiveness of targeted nutritional interventions provided by the health service. A household whose child is identified as malnourished - and therefore selected to receive intensive care through Therapeutic Supplementary Feeding (TSP) or Community Management of Acute Malnutrition (CMAM) – will be enrolled into PSNP on a temporary basis. This is intended to improve the well-being of the household as a whole; and so reduce the likelihood that the supplementary foods allocated for the child are shared out amongst other household members. Over time, such households will be considered for inclusion in the core programme (and so receive multi-year benefits).

In households already receiving PSNP transfers, recipients will be moved from public works to direct support transfer lists as needed to avoid or respond to malnutrition. Pregnant women will be moved to the DS list at four months or on confirmation by a health worker that she has attended her first antenatal check-up (whichever occurs first); and will remain on the DS list until 12 months after delivery[53]. In addition, households with a malnourished child under five years will be allowed to move one adult in the household (usually the mother) temporarily from public works to direct support benefits in order to allow them to take care of the malnourished child.
[53] This provision is not entirely new: under PSNP 3, pregnant and lactating women (PLW) were to be moved to DS transfers. Without detailed guidance, however, there was considerable variation between and within regions in how early in her pregnancy a woman might be entitled to stop public works; and how many months she could remain on direct support. The provisions under PSNP 4 should both standardise practice and (in most locations) result in a better allowance.

Conditions or co-responsibilities will be used to ensure that PSNP clients receive information on household-level practices and care-seeking behaviour that will improve nutrition. Behaviour change communication (BCC) messages will be focussed upon specific groups; but available to all.

For those receiving temporary DS transfers (pregnant and lactating women, those PSNP clients caring for a malnourished child, and anyone moved onto the programme through referencing from the TSF or CMAM programmes), co-responsibilities are ‘soft’ in that clients are informed of their responsibilities and compliance (e.g. attending community BCC training sessions or regular growth-monitoring sessions at their local health clinic) is monitored; but non-compliance will result in closer support, and not the withdrawal of transfers.

Those receiving public works transfers – both women and men - will also have the option to substitute attendance at BCC sessions for some of their public works obligations: attendance at three such sessions will count as one day of public works labour. In this case, however, the obligations are not ‘soft’: failure to attend will reduce the transfer income they receive for that month (just as failure to complete the required number of days of public works labour results in pro rata deductions from transfer pay).

The programme will also promote nutrition through public works and livelihoods support. Nutrition-sensitive public works will include established activities such as construction of water and sanitation (WASH) facilities, and new ones, such as the creation of kitchen gardens for the production of fruit and vegetables. Planning for livelihood support activities will also incorporate guidance to consider local nutritional benefits that can be gained through, for example, milk production and processing. In both cases, achieving greater nutrition-sensitivity is a matter of sensitizing local communities to the possibilities for contributing to better nutrition through certain choices, without compromising the bottom-up principles of community-based PSNP planning.

It is hard to predict the results of this increased focus on nutrition within PSNP 4: because these are new activities and outputs, there is no trend from which to set stretching but feasible targets. This is reflected in the logframe, where there are a number of nutrition-related indicators, for which targets will only be set once there is baseline data (mainly from the 2015 impact assessment)[54]. However, three indicators do have baseline values, and two have targets. At a minimum, PSNP 4 is expected to double the percentage of transfer beneficiaries who receive access to community-based nutrition counselling; and increase from 3.4 to 4.4 the number of food groups (out of 7) that transfer-recipient households consume in a given week (Table A4.4).
[54] These include output indicator 3.10 (percentage of pregnant and lactating women (pregnant or with a child < 2 years) in client households participating in community-based nutrition activities); 3.12 (Percentage of adult household members who attend at least three BCC sessions annually); and 3.13 (Percentage of pregnant women transitioning to temporary DS before four months on the basis of health facility referral).

Table A4.4: PSNP 4 contribution to nutrition: output, impact and policy targets

		Baseline	2015/16	2016/17	2017/18	2018/19	Target 2019/20
Policy objective indicator 5	Improve nutritional status of women and children (NNP impact objective). Percentage of stunting in children under five years in the PSNP operational area	48.8% (2012)					tbc
Impact indicator 1.1	Increase in household dietary diversity (disaggregated by sex of head of hh)	3.4 (2012)		+0.5		+1
Output indicator 3.11	Percentage of clients who receive community-based nutrition counselling services	40%	50%	60%	70%	80%	80%

Sources: MoA (2014) pp. 100-122; Berhane, Hoddinott and Kumar (2014) p. 12.

Livelihoods support

In the next phase, livelihoods support activities will incorporate significant changes drawing on learning from HABP and other livelihoods support programmes. At an institutional and managerial level, livelihood support will be fully integrated as one component of the PSNP 4 programme design and logframe (in contrast to the semi-autonomous status of HABP over the last five years). Key features of the re-design of the livelihoods component include:

Recognition that more productive smallholder agriculture will not be the primary driver of economic transformation and poverty reduction over the long term. The strategy aims to support households in improving their livelihoods through three pathways: (i) increased household-level agricultural and livestock production (which has in practice been the focus of HABP to date); (ii) diversification into off-farm livelihoods (service or manufacturing self-employment); and (iii) access to good waged employment.
- This is done through recognition that sequenced access to services along with close monitoring and skills development will have better impact on poor households’ livelihoods. This draws on and incorporates findings from the Tigray CGAP pilot, which has combined transfers with longer-term investments in training, savings services and asset transfers, with considerable success.
- An appreciation that poor and vulnerable households are often rationally credit averse. The new phase seeks to enhance the potential of very vulnerable households to benefit from livelihood promotion activities, and minimise their risk exposure. This is done through a combination of coaching/mentoring, promotion and gradual build-up of savings, combined with the provision of a lump sum livelihood transfers to these households, enabling them to meet the ‘lumpy’ costs of investments in productive assets, inputs or jobsearch.
- Individuals who have enterprise experience and a better coping strategy will receive financial literacy training, business development skills and savings promotion. These groups will access financial services through the mainstream system - the MFIs and RuSACCOs, with the programme providing a partial loan guarantee to reduce MFIs’ risks in lending to these clients.
- The new phase also seeks a smooth exit / graduation of households from the safety net programme. Households will continue receiving transfer support for an extra one year after being identified as graduates.

Table A4.5: Expected benefits: Livelihoods support services, economic diversification and income

Goal indicator				baseline	year 1	year 2	year 3	year 4	year 5
					2015/16	2016/17	2017/18	2018/19	2019/20
Goal: Resilience to shocks and livelihoods enhanced and food security and nutrition improved / for rural households vulnerable to food insecurity
3		Average value of asset holdings				+15%		+25%	+30%
Outcome: Enhanced participation in improved rural safety net, livelihood and nutrition services / by food insecure female/male headed households
11		Percentage of safety net clients reporting new income sources			5%	10%	20%	30%
12		Percentage of safety net households with business plans reporting that their business plans reflect their priorities, needs and capabilities		46% / (HABP Qualitative survey report)		65%		75%
Output 4: Clients’ livelihood opportunities facilitated through three pathways: crop and livestock, off-farm income generation, and employment
1	Percentage of safety net households who report saving regularly (in development groups/VSLAs, RUSACCOs, MFIs, banks, etc.) - disaggregated by sex of household member who saved				25%	30%	35%	40%	50%
2	Percentage of safety net households who received the complete livelihood training package			0%	30%	55%	75%	85%	90%
3	Percentage of safety net households reporting that the programme has enabled them to access on-farm and/or off-farm livelihood opportunities and/or labour/wage employment opportunities		On-farm:	45%		65%		80%
			Off-farm:	20%		30%		40%
			waged work:	0%		5%		15%
5	Percentage of ultra-poor safety net households receiving livelihoods transfers [after completion of checklist]			0%	30%	60%	75%	85%	90%
9	Percentage of clients receiving employment related skills training - disaggregated by sex)			0%	10%	15%	20%	25%	30%

All results to be disaggregated by sex.

Poverty reduction

The direct, immediate impact of PSNP transfers (the income effect) is projected to reduce the 2020 poverty headcount by between 3.2 and 5.2 million (Table A4.6). These are crude estimates: without access to HICES microdata it has not been possible to model impact using the actual distribution of household per capita consumption. (Even with this data, it would be necessary to make a number of strong assumptions regarding how average p.c. consumption will evolve over the next five years, and the distribution around this average.) To reflect the uncertainties around these projections, the Table estimates low case and high case scenarios at 25% below and above the base case estimates.

Table A4.6: Projected poverty reduction impact of PSNP 4 (2015 and 2020)

	2011	2015	2020
population a	88,220,048	98,942,000	111,521,000
predicted poverty rate b	32.5%	27.6%	23.4%
predicted poor c	28,671,515	27,290,259	26,105,214
PSNP caseload	7,535,000	10,000,000	10,000,000
impact of PSNP (%pt)	1.6%
impact of PSNP - % reduction in poverty rate c	4.9%	4.9%	4.9%
poverty reduction due to PSNP (4.9% reduction in predicted headcount)	1,411,521	1,583,072	1,784,336
scaled up for larger caseload d		2,100,958	2,368,064
scaled up for larger caseload and larger transfers e
- base case		3,302,926	4,311,073
- low case (base – 25%)		2,477,194	3,233,305
- high case (base + 25%)		4,128,657	5,388,842

Sources and assumptions:
DFID staff estimates.
a	population projections from UNDESA 2012.
b	2011 pre-transfer poverty headcount rate estimate from World Bank 2015. 2015 and 2020 estimates projected based on geometric mean of rate of poverty change 2000-2011.
c	Impact of PSNP on poverty headcount rate (4.9% reduction in poverty rate – from 32.5% down to 30.9%) taken from 2011 and applied to 2015 and 2020 estimates of pre-transfer poverty rates.
d	2011 rate of impact scaled up to reflect increase in caseload from 7.5m in 2011 to 10m in 2015 and 2020.
e	Impact scaled up for increase in generosity of PSNP transfers: 2015 weighted average of 157% (153% for 6,425,100 PW and temporary DS beneficiaries and 306% for 713,900 permanent DS) and 2020 weighted average of 182% (7,440,300 PW and temporary DS plus 826,700 permanent DS).

In addition to the poverty-reducing effect of transfers in lifting households up (‘promotion’), PSNP 4 will also help to reduce poverty by helping transfer-recipient households to avoid downward movements in the face of weather-induced production shocks (‘protection’). Using the 2011 HICES data, the World Bank has modelled the impact of a ‘moderate’ drought on the income and consumption of rural households. These simulations suggest that average per capita consumption in PSNP woredas would drop by 8% in the face of such a shock; for the poorest households (which are most dependent upon agriculture and in the absence of the safety net would be most severely affected), PSNP transfers help to reduce the impact to an average of 6% (World Bank 2015).

#### 2. Local / community level benefits
Under PSNP 3, public works have made a major contribution to rural development through environmental, economic and social improvements. Some of these are summarised in in more depth in Campbell 2015. Gains include:
- Improved agricultural productivity at the watershed level through soil and water conservation (SWC) measures and area closure which have reduced erosion and siltation and restored depleted water tables
- Farm-level SWC structures (e.g. soil or earth bunds and more recently bench terracing) which have resulted in significant improvements in rainfed crop yields (Table A4.7).
  Table A4.7 Increased crop yields due PSNP public works

  crop type	yield (quintals / hectare)			increase due to PSNP
  	before	after		quintals / ha.	%
  cereals	3.37	5.60		2.23	66%
  pulses	4.90	6.00		1.10	22%
  perennials	4.01	4.33		0.32	8%

  Source: Metafaria Consult 2013 p. 37.

- Small-scale irrigation schemes that reduces vulnerability to low or unusually-timed rainfall.
- Water supply projects such as spring developments or hand-dug wells (which by 2008 had contributed 20% and 41% respectively to Ethiopia’s Millennium Development Goal targets for 2010).
- Construction or rehabilitation of health posts, school rooms or Farmer Training Centres.
- Construction or maintenance of rural roads that improve communities’ access to markets for purchase of inputs such as fertiliser, and to sell crops.
PSNP 4 public works will build on the significant achievements seen under PSNP 3, while incorporating changes to address those areas where the suitability or quality of works need improvement. These changes include modifications designed to further increase the contribution of public works to climate change adaptation; closer attention to identifying and then implementing public works activities more suitable for the lowlands; making the works programme more gender sensitive; improving the technical quality and sustainability of roads and water projects; and enhancing the potential contribution of public works to nutrition, health and livelihood outcomes.

Predicting the mix of public works activities that will be completed over the next five years is difficult given the bottom-up nature of public works planning. This in turn makes it hard to quantify likely outputs and resulting outcomes (including climate adaptation outcomes). It is however possible to note and extrapolate from some observed trends to provide informed speculation about the direction of change[55].
[55] The following paragraphs benefit from discussions with Mr. Ian Campbell at the World Bank.

In highland woredas in which the PSNP has been implemented to date, there is a gradual shift from SWC sub-projects to sub-projects more directly focused upon livelihoods. Once the natural resource base in a given watershed has been regenerated as a result of SWC activities, new livelihood activities become possible through the introduction of a different public works mix. The stabilization of hill slopes, reduction in up-slope soil erosion and down-slope sedimentation, and rising water table allows communities to introduce small-scale irrigation from the newly replenished streams and springs. More ambitiously (as now seen in Tigray), gully rehabilitation and bench terracing is creating ‘new’ cultivable land which is then allocated to needy community members (often landless youth). Irrigation and expansion in the area under cultivation create new economic opportunities (such as the sale of cash-crops) and discarded crop matter available for zero-grazing livestock feed, enabling the reduction of traditional free-grazing, which in turn makes more land available for crop production.
It is harder to speculate about the likely mix of public works outputs and benefits in the lowland woredas; or in the 92 new woredas which will be brought into the programme from 2016. In the lowland woredas (which only came under PSNP from 2010) there is less of a time-series from which to extrapolate: in addition, the additional attention that PSNP 4 will direct to improving public works implementation and results in these woredas may drive a change in the mix seen to date. In woredas which will be incorporated into PSNP for the first time over the next five years, it is likely that soil and water conservation will be a major focus, as they were for the now-mature PSNP woredas during the early years of PSNP implementation.
Largely because of the difficulty in predicting the public works choices of communities, the PSNP 4 logframe for Output 3 focuses heavily upon results as defined by indicators of good planning processes, technical quality ratings, and beneficiary satisfaction. A selected sub-set of these indicators are shown in Table A4.8. For the same reason, most of these indicators and associated targets are expressed as percentages, rather than absolute values.

Table A4.8: PSNP public works – participatory planning and technical quality

Source: MoA 2014 pp. 111-116

  - Public works and climate-resilient rural economic development
The evidence suggests that PSNP public works have already made a significant contribution to climate adaptation. PSNP 4 will strengthen these effects by incorporating considerations of climate change on an explicit and systematic basis. Drawing on the findings of the Climate Smart Initiative (CSI) pilots, PSNP 4 will influence both the choice of works and the ways in which works are designed and implemented (the technical guidance sheets or infotechs). The CSI emphasises the importance of learning, both by beneficiaries and those managing PSNP implementation, for the evolution of policy and programme systems which can adapt to climate change over time. Supported by woreda-level facilitators, local people are identifying ‘best-bet’ activities for building food security in the context of uncertainty about future climatic conditions. PSNP4 will significantly increase the land covered by improved watershed and rangeland management structures and practices (Table A4.9).
Box A4.1: The PSNP Climate-Smart Initiative (CSI)

CSI is a DFID-financed project managed by the DCT, launched in 2014 to integrate the implications of climate change into the activities and systems of the PSNP and HABP. An inception phase generated a series of studies summarising the state of knowledge on climate change projections, the achievements and risks of PSNP and HABP implementation from a climate adaptation perspective; and provided recommendations for future modifications to maximise the climate resilience benefits from a joined-up approach to transfers, public works, livelihood support activities and management arrangements. The CSI is now supporting a consortium of NGOs to test these ideas in practice in 24 pilot woredas, adopting a new ‘climate smart’ approach to community-level planning and tailoring programme activities to local conditions. New ideas and successful practices are shared through a central hub to promote the sharing and uptake of best practices; which have fed into the design of PSNP4.
Source: World Bank 2013 pp. 47-60.
Table A4.9: PSNP 4 results for climate adaptation through public works

		Baseline	2015/16	2016/17	2017/18	2018/19	Target 2019/20
Policy objective indicator 4	Climate Resilient Green Economy Strategy: Build Ethiopia into a middle-income country by 2025 in a way that is both resilient to the effect of climate change and does not result in a rise in greenhouse emissions
4.1	Percentage of land covered by improved watershed and rangeland management structures and practices
4.2	MT CO2e sequestered in public works-supported watersheds
Output indicator 3.4	Total closed area subject to enhanced management for climate adaptation (ha)		37,500	94,000	172,000	297,000	500,000

  - Protecting and promoting women and girls
The PSNP 4 Design Document incorporates a strengthened focus on gender (elaborated in the PSNP 4 Gender Analysis and Action Plan). In part, this entails a closer focus on the implementation of provisions that existed in PSNP 3, but were implemented unevenly between different localities. Other design features are new to PSNP 4. Key provisions include the definition of physically less-demanding tasks for women engaged in the public works programme; a 50% reduced workload for women; transition of pregnant women from public works to temporary direct support from the fourth month of pregnancy (or earlier, on receipt of a medical certificate) through the end of the first year postpartum; the use of public works labour to construct day care centres; and minimum standards for representation by women on a variety of safety net committees. The Gender Action Plan includes capacity building and awareness raising targeted to women; increased institutional engagement of the Ministry of Women, Children and Youth Affairs and the Women, Children and Youth Directorate of the MoA; and ensuring the posting of Social Development Experts at woreda level.

  - Rural economic development through local multiplier effects
The £1.725 bn ($2.657 bn) provided in PSNP transfers over the next five years should generate an additional £1.449 bn in local economic multiplier effects. Based upon the LEWIE simulations, every 1 birr of transfers can be expected to generate an additional 0.84 birrs in local economy income. This additional income is equivalent to 41% of total PSNP programme costs for the next five years.

#### 3. National level benefits

Development of a national social protection system
Over the next five years, the PSNP will evolve from a relatively autonomous, time-bound programme to become a central part of a broader, permanent system that delivers social protection and other national policy objectives. This shift to a systems approach is at the heart of PSNP 4, and implies the development and implementation of common administrative mechanisms to tackle policy, institutional and budgetary fragmentation.
Under Output 1 of the PSNP 4 logframe, the tools and instruments central to the delivery of the PSNP 4 will be designed, tested and scaled up. These tools will be designed not only to support the implementation of the next phase of the PSNP but as operational underpinnings for the emerging overall social protection and DRM systems. Ultimately, different agencies and programmes serving the same clients (the extreme poor and those vulnerable to extreme poverty) should use a common set of tools, instruments and approaches to ensure maximum impact and cost effectiveness. PSNP will play the leading role in developing most of these tools and instruments, which can then serve other poverty-focussed policies and programmes (for example, health fee waivers). It will help the Government to define and then deliver a minimum set of services for vulnerable households, with clear linkages and roles for different implementing Ministries and line structures operating under unified planning and coordination frameworks (MoA 2014 pp. 11-13).
The expected results of these PSNP 4 investments in systems building will focus on six priority areas. These are (i) targeting (defining the principles and processes for programme entry and exit, with a particular focus on pastoral areas); (ii) information management and programme monitoring (the design and implement an integrated, electronic Management Information System (MIS) which can share data with other information systems, with a unified single registry of beneficiaries and a geo-coded database of completed public works); (iii) the development of local DRM capacities (harmonised early warning systems and pre-planning for scaling up safety net and livelihood activities in response to shocks); (iv) improving arrangements for planning, coordination and governance; (v) strengthening social accountability and grievance redress mechanisms, including for the implementation of gender provisions; and (vi) systematic and sustainable investments in capacity development (MoA 2014; World Bank 2014).

More effective disaster risk management (DRM) through early warning and disaster preparedness

The PSNP is assigned a significant role in the Government’s 2013 Disaster Risk Management policy and the related Strategic Programme Investment Framework (DRM-SPIF). This reflects the important potential of the PSNP – some of which has been realised to date, some of which has not – to contribute to the ex ante prevention or mitigation of impact before a shock occurs (e.g. through public works which restore soil moisture and water tables and so help to prevent a failure of rains from turning into a drought) as well as a timely and effective ex post response to a shock that has broken (by using pre-positioned contingency funds and existing PSNP delivery channels to expand transfer coverage to newly, transitorily food insecure household and / or extend the number of months that transfers are paid).

The PSNP was written into the DRM under the current, third phase of the programme. Since then, the design changes incorporated in PSNP 4 should significantly improve the programme’s potential contribution to DRM objectives. Firstly, the core PSNP transfer programme will expand to absorb part of the caseload of need that has to date fallen to the humanitarian system to serve. Recognising that many of those served by humanitarian food aid in recent years have been in need of such assistance in successive years – that is, they are in fact chronically not merely transitorily food insecure, and therefore would be better served by a developmental safety net programme rather than emergency assistance – the PSNP will seek to ‘right size’ for need in the woredas in which it operates. This will involve expanding to reach 7.139 m people in the first year, rising further to stabilise at 8.267m from year three (2017/18).

Table A4.10: The PSNP 4 caseload will include a budgeted annual sum for responding to transitory needs
	year 1	year 2	year 3	year 4	year 5
	2015/16	2016/17	2017/18	2018/19	2019/20
chronic caseload	7,139,000	7,703,000	8,267,000	8,267,000	8,267,000
transitory caseload	2,861,000	2,297,000	1,733,000	1,733,000	1,733,000
total PSNP caseload	10,000,000	10,000,000	10,000,000	10,000,000	10,000,000

Secondly, to address the shortcomings of the PSNP 3 Risk Financing Mechanism (RFM), the relationship and sequencing between the PSNP and humanitarian food aid – the ‘continuum of response’ – has been fundamentally redesigned under PSNP 4. PSNP 4 will now budget and plan for a significant response to remaining transitory need every year. The woreda contingency fund (equivalent to 5% of the base program cost) will be retained, but is likely to make only a modest contribution to scaling up in the event of a shock. The Regional contingency (which was frequently under-utilised, which in turn impeded triggering the RFM) will be abolished. The RFM will be replaced with a Federal Contingency budget. Unlike the RFM, this Federal contingency is to be utilised every year, avoiding the incentives that might prevent the triggering of a scaled-up response, and the dependency upon imperfect and sometimes contradictory early warning assessments that created scope for subjectivity and disagreements between stakeholders about whether or not the humanitarian situation justified triggering the RFM.

The size of the Federal contingency will decline slowly as the size of the regular programme expands and then stabilises. On the principle that for the next five years the PSNP will provide transfers to a total of 10 m people each year, the balance between this total allowance of 10m p.a. and the regular transfer caseload will be available as the Federal contingency, to respond to transitory (i.e. seasonal) need. The Federal Contingency budget will thus provide one-year transfers to 2.861 m of the transitory caseload in the first year of the next phase; falling to 2.297 m in the second year; and 1.733m each year from the third year onwards (Table A4.10 above). Humanitarian food aid will then be sought to meet the residual transitory needs of those who are not reached by the Federal contingency in a given year. This revised continuum is premised upon bringing together processes that have to date been poorly harmonised. A single assessment (the HRD) will involve both PSNP and humanitarian actors, and give rise to a single response plan and budget, which is then implemented with a shared monitoring and accountability system.

PSNP 4 will build resilience to climate shocks (primarily drought) not only through targeted transfers, environmental rehabilitation and climate-proofed local infrastructure, and provisions to respond to 1.7m people in transitory, seasonal food shortage; but also by building institutional capacity and plans which improve the Government’s capacity to anticipate, plan for and then respond quickly to shocks such as natural disasters or food price hikes. The Programme is now seen as a cornerstone of both the Social Protection (SP) and Disaster Risk Management (DRM) policies. These outcomes derive from the programme’s contribution to the production of woreda-level risk profiles and contingency plans; strengthening the early warning and needs assessment system and streamlining the process for triggering a response; and integration of PSNP transitory transfers and humanitarian transfers (with each other and with targeted supplementary feeding (TSF) and Community Management of Acute Malnutrition - CMAM).
The benefits obtained through DRM system-building activity is hard to quantify and monetise, but likely to be large. Drawing on international evidence, there are two main channels by which a more effective DRM system may benefit a country. The first is through losses averted through timely and effective early warning. As a global benchmark, well-functioning, modern early warning systems in Europe reduce disaster-related asset damage by between 0.003% and 0.017% of GDP (Hallegate 2012, cited in World Bank 2014 p. 115). Based on Ethiopia’s GDP in 2013, this would result in benefits of £1-5.2m ($1.5-8m) p.a.; and may well be considerably larger than the global average, given that 45% of Ethiopia’s GDP is generated by the weather-sensitive agricultural sector (compared to much lower rates in Europe). The World Bank estimates that the economic benefits to Ethiopia may be more in the order of £19.5-32.5m ($30-50m) per year. Secondly, long term risk reduction (through development of risk profiles and risk reduction plans to inform public works) is estimated to lead to additional benefits of £130m-£143m ($200m-$220m) per year.
Assuming that the combined benefits from better early warning and ex ante risk reduction action (totalling £162m p.a.) accrue from the third year of PSNP4 implementation, improvements in DRM achieved through PSNP 4 could save a total of £487m by 2020. Given the difficulties with modelling these effects, however, a relatively conservative estimate of £13m ($20m) p.a., for a total of £39 m over the lifespan of PSNP 4, is used for the purpose of cost-benefit analysis below.
Reduced morbidity and mortality

An accepted way of estimating and monetizing the aggregate effect of the proposed intervention on health and life expectancy is as disability-adjusted life years (DALYs). DALYs represent years lived with ill-health and years lost through premature mortality relative to a global standard. WHO (2014) published country estimates for DALYs attributable to the incidence of major diseases: from these, the impacts of health-enhancing interventions can be assessed as DALYs averted.
In the case of the proposed DFID programme, health effects (measureable in DALYs) can be assumed to accrue from a variety of channels. The first is the effect of transfer receipt on nutrition and health. In 2012, households consumed on average 75% of what they received in PSNP transfers, primarily as increased spending on more and better food, but also as increased spending on health care (estimated from the 2012 impact assessment as averaging an extra 7.5 birr per capita per month: Kumar and Hoddinott 2013 p. 29). Additional benefits accrue to all those living in PSNP woredas (not just transfer recipient households) through infrastructure created through PSNP public works. In the 2012 highland sample, 48% said that they had better access to water due to PSNP public works, quoting health gains and resulting productivity increases; 60% said that they had obtained health benefits form health posts built through public works (Berhane et al 2013 pp. 192-3). Over the next five years, PSNP 4 will build on these income (transfer) and health access (public works) benefits with deliberate efforts to link PSNP beneficiaries to health and nutrition training and services, and acutely malnourished children to PSNP benefits.
Through these various channels, it is estimated that PSNP 4 will save an estimated $606 m in DALYs over the five years of the next phase. This assumes that the WHO disease category most amenable to PSNP 4 influence is that of ‘Communicable, maternal, perinatal and nutritional conditions’; and that the combined influence of increased calories and dietary diversity, improved access to clean water, sanitation and health posts, and linkages to health and nutrition services will reduce the burden of this category of diseases by 10%.
#### 4. Global-level outcomes: climate change mitigation

Crude estimates suggest that PSNP 4 will sequester between 0.726 and 2.036 million tonnes of CO2e by 2021; and (assuming that all new enclosure stopped) between 2.42 and 4.07 m tonnes CO2e by 2025. This is based on two possible scenarios for the areas that might be enclosed over the following five years (the first based on recent performance of PSNP; and the second based on the logframe targets for areas enclosed and subject to enhanced management for climate adaptation); and a range of three possible values for the per-hectare rate of sequestration five years after enclosure, based on the rates reported in the latest (second 2011) PSNP Public Works Impact Assessment. For the purposes of the summary of expected benefits at the end of the Appraisal Case, the mid-point between the two base-case scenarios is used (1.381 m tonnes CO2e in 2020).

Table A4.11: Alternative estimates of total carbon sequestration under PSNP 4

DFID staff calculations based on the following sources and assumptions:
a	Rates of CO2e sequestration after 5 years taken from Metafaria Consulting (2013) pp. v. (Low case (0.99 MT/ha) is the sequestration rate for conversion of bare soil to grassland; base case (4.84 MT / ha) is rate for conversion of degraded grassland to open shrubland; high case (5.06 MT / ha) is the rate for conversion of open shrubland to dense shrubland.)
b	Rates of sequestration over four, three, two and one years calculated as arithmetic fractions of the five-year values.
c	Historic average for area closed taken from PSNP Annual Reports of the last three years (MoA 2012b p. 33; MoA 2013c pp. 71 and 93; MoA 2014a pp. 85 and 93).
d	Cumulative totals of area enclosed is taken from PSNP 4 logframe (output indicator 3.4); annual increments calculated by subtraction.

In monetary terms, this carbon sequestration benefits can be valued at between $2.2 m and $6.1 m by 2020; and $7.3 and $12.2 m by 2025. These estimates are based upon the price ($3 / MT) used in the 2011 Public Works Impact Assessment; updated price estimates might yield higher estimates. For the purposes of the summary of costs and benefits presented below, we take the mid-point between high and low values ($4.1m by 2020, at least $9.7 m by 2025).

Annex 5: Value for money in PSNP and other DFID-supported cash transfer programmes

Figure A5.1: Total-cost-to-transfer ratios in PSNP 3
total costs (birr) to deliver 1 birr of transfers to households
Source: PSNP expenditure data reported in quarterly IFRs and compiled by the DCT; analysed by DFID Ethiopia staff

Table A5.1: PSNP cost efficiency in comparison to other DFID-supported transfer programmes
Non-transfer costs as a percentage of transfer costs

country	Programme	2013/14	2014/15 (forecast)
Bangladesh	Challenging the Frontiers of Poverty Reduction	43%	43%
	Chars Livelihoods Programme	29%	27%
Ethiopia	Productive Safety Net Programme - inc. capital costs	27%	30%
	Productive Safety Net Programme - n.i. capital and HABP costs	10%	11%
Ghana	Livelihood Empowerment Against Poverty	8%	11%
India	Bihar Child Support Programme	27%	21%
Kenya	Hunger Safety Net Programme	33%	16%
	Cash Transfers: Orphans and Vulnerable Children	12%	12%
Mozambique	Cash Transfer Programme	-	-
Nigeria	Child Development Grants Programme	82%	59%
OPTs	Palestinian National Cash Transfer Programme	-	-
	Urban Food Voucher Programme	21%	-
Pakistan	Benazir Income Support Programme	7%	7%
Rwanda	Vision Umurenge Programme	17%	16%
Uganda	Social Assistance Grants for Empowerment	25%	28%
Yemen	Social Fund for Development	7%	12%
Zambia	Social Protection Expansion Programme	36%	30%
Zimbabwe	Child Protection Fund	12%	9%

Source: DFID Policy Division reporting to PAC; using PSNP budget data

### Projected cost-to-transfer ratios
A direct comparison of TCTR between PSNP 3 (using actual spend as reported in quarterly IFRs) and PSNP 4 (using the five-year budget) is also complicated by the fact that IFR and budget categories are not exactly the same. With these caveats in mind, the table below presents uses the programme budget to forecast cost-to-transfer profiles for PSNP 4 under three different constructions of what are included as total costs for delivery of transfers. The costs that are included in each of these three models is summarised below the table.

Table A5.2: Projected TCTR under PSNP 4 – three models

	2015/16 EFY 2008	2016/17 EFY 2009	2017/18 EFY 2010	2018/19 EFY 2011	2019/20 EFY 2012	all five years
Model 1: including all costs	1.41	1.35	1.36	1.36	1.34	1.36
Model 2: n.i. capital costs or key instruments	1.28	1.20	1.21	1.22	1.22	1.23
Model 3: Including only overhead costs	1.15	1.16	1.16	1.17	1.17	1.16

Budget categories included for each of the three models
transfer costs			non-transfer costs
(same for all three models)				model 1	model 2	model 3
Transfers - Permanent Direct Support	√		Evaluation and audit	√	√	√
Transfers - Public works and Temporary DS	√		Woreda Admin Budget	√	√	√
Contingency budgets	√		Regional and Federal management	√	√	√
Livelihoods transfer	√		GoE operational costs	√	√	√
			Livelihood capacity building	√	√
			Capacity building	√	√
			Capital budget for public works	√
			Key instruments (lumpsum)	√

### Projecting an all-PSNP benefit-cost ratio for public works under PSNP 4

There are high rates of return associated with public works projects under PSNP 3. The three Public Works Impact Assessments have derived net present value (NPV) and economic benefit-cost ratios (BCRs) which were positive in all cases (table A5.3). M.A. Consulting (2009) found BCRs (using a 10% discount rate over a 25 year span) ranging from 1.5–6.5; GoE (2011) found BCRs ranging from 1.14–2.50 (both 10% and 15% discount rates were tested, both over 25 years); and Metafaria Consult (2013) found household-level BCRs ranging from just over 1 to just over 36 (using a discount rate of 15% over 25 years).

Table A5.3: Benefit-cost ratios for public works under PSNP 3 (2012)

region	micro-watershed	SWC	Small-scale irrigation	roads	water supply	health facility	school
Tigray	Adi Tsalka	1.12	2.86	4.32	1.61	2.34	5.01
	Keshi Aynalem	1.04	1.48	3.11	1.58	1.25	5.13
Amhara	Molla Geremoch	1.22				1.28	5.04
	Legabero Wekelo	2.57	3.03	1.06	2.17	1.71	5.95
Afar	Halle Ella - Yallo	1.41	1.74	2.90			4.30
Oromia	Gola Gorba	1.55		2.09	32.56
	Garaguracha - Habro	1.11		1.21
Harari	Negadras - Sofi	3.32					4.49
Dire Dawa	Lega Dhugo	1.21		1.35	18.12		6.02
Somali	Bulabora - Bike			1.54	36.12
SNNP	Arbegna Koste	7.25		2.20	9.81	4.51	4.66
	Doyancho	1.01		2.16	18.84	2.13	4.03
minimum		1.01	1.48	1.06	1.58	1.25	4.03
maximum		7.25	3.03	4.32	36.12	4.51	6.02
median		1.22	2.30	2.13	13.97	1.92	5.01
number of micro-watersheds		11	4	10	8	6	9
		p. 77	p. 90	p. 92	p. 94	p. 96	p.98

Source: Metafaria Consult 2013. BCRs based on discount rate of 15% over25 years.

To produce a crude projection of the net value for the totality of public works created by PSNP 4 over the next five years, we assume an average BCR of 4.42 over 25 years. Without being able to estimate the mix of public works types that will be completed under PSNP 4, we have assumed that this will follow the proportions found in the 2012 sample described in the table above. We have multiplied the median BCRs for each the various types of public works outputs presented in the table above by the number of sample watersheds in which projects of that type were found; totalled these values; and divided by the total number of projects studied to obtain the weighted average of 4.42 (Table A5.4).

Table A5.4: Obtaining an estimated all-PSNP BCR

	SWC	Small-scale irrigation	roads	water supply	health facility	school	total
number of projects in PWIA sample	11	4	10	8	6	9	48
median BCR (25 years, 15% discount) for this type of project	1.22	2.3	2.13	13.97	1.92	5.01
weighted total (= number of projects x median BCR )	13.42	9.20	21.30	111.76	11.52	45.09	212.29
weighted average BCR for projects in the PWIA sample							4.42

A BCR of 4.42 after 25 years can be back-projected to give estimates of BCRs after 1, 2, 3, 4 and 5 years. These ratios can then be applied to the investments made in each of the five years of PSNP 4 ($60m / £39m in each year) to provide year-specific estimates of benefits, which can be totalled for 2020/21. The costs of public works are assumed here to include only those costs which are covered under the ‘capital costs’ budget line (materials, transport, and limited inputs of paid-for skilled and semi-skilled labour): in other words, the calculation of benefits is conservative as it does not include as a cost input the labour cost of transfers paid to public works beneficiaries.

Table A5.4: Estimated net present value of public works investments ($60m p.a.) in 2020

	year 1	year 2	year 3	year 4	year 5	Total
	2015/16	2016/17	2017/18	2018/19	2019/20
investment in public works (capital budget) (£m)	39	39	39	39	39	195
BCR in 2020	2.60	2.18	1.60	0.72	0.38
net present value in 2020 (£m)	101	85	62	28	15	292

Annex 6: Potential for different risk management capacities under Options 2 and 3

Annex 7: Procurement thresholds and methods to be used in PSNP 4 (indirect procurement)

Table A7.1: Procurement processes for contracts of varying types and values

Procurement method	Threshold values			Standard bidding documents / to be used
	works	goods	non-consulting services
International Competitive Bidding (ICB)	$10m and above	$1m and above	$1m and above	WB Standard Bidding Document and prequalification document
Prior review threshold required	$7m and above	$1m and above	$1m and above
National Competitive Bidding (NCB)	$0.2m to $10m (with prior review above $7m)	$0.1m to $1m	$0.1m to $1m	Federal Government Standard Bidding Document (with a few exceptions†)
Shopping (comparing quotes from 3+ suppliers)	Below $0.2m	Below $0.1m	Below $0.1m	RFQ document in the Procurement Manual
Limited International Bidding (LIB)	Can be used only on an exceptional basis, when there are a limited number of known suppliers worldwide
Direct Contracting	Under $5,000: written justification and internal Government review (Head of Agency approval) / $5,000 and above: World Bank prior review
Community participation in procurement	Procurement to be effected though participation of communities

Source: MoA (2014) PIM – version 1.0. p. 14-3.
† see PIM pp. 14-5 to 14-6.

Table A7.2: Selection of consultants

Type of consultant	Prior Review Threshold	Maximum value for National Shortlist
Firms	$200,000 and above	Below $200,000
Engineering and works supervision	$300,000 and above	Below $300,000
Individuals	$100,000 and above	n.a.

Note: all consultancies for the provision of legal and procurement services are subject to World Bank prior review, regardless of value. ToRs for all contracts shall be cleared by the World Bank.

The method for procuring the services of consultancies will depend on the value of the contract and the nature of the contracted party.
- For firms, consultancies above $200,000 will be awarded through Quality and Cost-Based Selection (QCBS). Services of a standard or routine nature (e.g. audits) may be procured through Least-Cost Selection (LCS). Small assignments may be procured through Selection Based on Consultants’ Qualifications (CQS). Shortlists for engineering or works supervision contracts below $300,000 in value may be composed entirely of national firms.
- Selection of individual consultants will be based upon a comparison of the CVs of three or more candidates who express interest or are approached directly. These decisions will normally be subject to post review; prior review will only be required in exceptional cases (e.g. when hiring for long-term technical services for the duration of the programme), which will be outlined in the Procurement Plan.
Single source selection (SSS), of either individuals or firms, may be used only in exceptional cases, when it presents a clear advantage and a competitive process is not practical or appropriate. SSS will require a strong justification and the World Bank’s endorsement.
Annex 8: Developing and implementing a computerised Management Information System (MIS)

The DFID programme team recognises that large ICT projects frequently run into significant cost and time over-runs; and that this is a concern for the development of the PSNP MIS. To mitigate and manage these risks, we will ensure that the process receives adequate attention (from us, and from others) to ensure that it remains on track. In doing so, we can draw on experience existing within the PSNP community with regard to the management of ICT projects, and the kind of challenges that are likely to be faced. Over recent years the programme has rolled out payroll management (PASS) and accounting and financial reporting (IBEX) software packages, to replace the paper- and Excel-based practices that were in place previously: this has provided valuable lessons on some of the key risks (the need for a policy on provision and up-dating of anti-virus software on networked systems; the need for investment in continuous retraining to cope with staff turnover).

The initial consultancy on options for the development of the MIS, commissioned by the DCT during the PSNP 4 design process, also attempts to foster realism, resulting in the fairly large cost estimates. Building on this, the Design Document laid out some basic principles (MoA 2014e pp. 20-21); and the broad steps that will need to be followed:

- Integrated programme MIS designed and implemented in stages (single client registry and public works database as priority modules); explicit interface with other information systems (existing and planned) allows programme MIS to draw on and contribute to MIS of other strategies (social protection, DRM) and sectors/programmes (e.g. nutrition, maternal and child health).
- Establish National Registry Secretariat within MoLSA to oversee the setup of the Registry and report regularly on progress to the Social Protection Platform
- Contract design of overall modular MIS architecture
- Design, test, re-design and build consensus for MIS architecture.
- Contract design of Unified Single Registry as part of MIS architecture
- Develop Rollout Plan (schedule, assigned responsibilities, capacity development plan) developed and implemented.
- Reach agreements Memoranda of Understanding between Ministries and with the Central Statistics Agency (CSA) on protocols for data sharing and common use of single registry.
- Strengthen the link between the cycle of six-monthly joint reviews and high-level programme management committees.

Progress against this schedule was reviewed in the recent June JRIS exercise and target dates established for the first milestones (those relating to the finalisation of Terms of Reference and tendering for consultancies to bid for the design of the overall architecture). The DCT is recruiting an ICT systems specialist to manage support to this process, and the donors and Government have agreed to establish a PSNP MIS working group to monitor and guide the process: DFID will be part of this group.

Annex 9: Sources of PSNP 4 financing and classification of DFID financing

Table A9.1: Financing sources for PSNP-4

Source: World Bank 2014 p. 183-4. Sums are in current dollars; currency conversion by World Bank staff.

Depending on how broadly we interpret (i) ‘assets’ and (ii) contribution to the creation of those assets, we could classify anywhere between £27m (10%) and £129m (47%) of projected spend as capital spending (CDEL). The low case, based on a narrow definition, counts only:
- the capital costs of the PSNP public works (the concrete, metal and other materials that go into public works structures, plus the small allowance for hiring in skilled labour for certain tasks); and
- the spending on ‘key instruments’ (the hardware and software investments that will go into creating a computerised management information system). The table below summarises the forecast spending under the key instruments budget line; and the team’s judgements as to which of these investments – totalling to £3.8m - count as CDEL.

Table A9.2: Of the £4.7m that DFID will invest in ‘key instruments’, £3.8m scores as CDEL

Source: World Bank 2014 p. 183. Dollar values converted to pounds sterling at £1 = $1.53984.

In addition to these two lines of spending, the high case counts also counts as CDEL:
- the transfers paid to PSNP beneficiaries as wages for labour on public works (these labour costs are central to the creation of the infrastructure and environmental assets created through public works); and
- the money paid to (some) PSNP beneficiaries as ‘livelihoods transfers’. These livelihoods transfers (one-off and much larger than the regular monthly safety net transfers that are the core of the programme) are intended to help recipients to make the investments in ‘lumpy’, indivisible productive assets such as livestock or tools.

There is a good case for at least some of the spending under each of these two additional budget lines counting as CDEL.

- We assume that 80% of the budget line ‘Transfers – public works and temporary direct support’ is accounted for by public works wages and therefore counts as CDEL. The remaining 20% is assumed to be (i) transfers paid to those on temporary direct support (such as pregnant and lactating women), who do not need to participate in public works and as such do not contribute to the creation of physical assets; and (ii) transfers paid in return for compliance with conditions other than public works labour, such as attendance at training sessions on good household nutrition practices or child growth monitoring.
- We assume conservatively that only 25% of spend under the ‘livelihoods transfer’ budget line is on permanent assets and therefore CDEL-eligible. Although these transfers are intended to support household investments in assets, we do not yet know how successful this will be: it seems likely that a proportion of households will of necessity use some or all of their transfer for subsistence rather than investment purposes; or will use it to invest in inputs (e.g. fertiliser or veterinary care) which is, in accounting terms, better seen as a recurrent spending rather than investment in a new asset.

The following table summarises the amount and profile of DFID spending that would be classified as CDEL under either the conservative low case or the more inclusive high case definitions.

Table A9.3: High and low case forecasts for CDEL spending

Remaining spending is regarded as recurrent programme spending (RDEL).

The ARIES input sector codes under which spending will be reported in DFID are summarised in the following table. For the purposes of these codes, 69% of spend is classified as social protection; 16% as Food aid and food security; 6% as investment in improving agricultural land resources; and 9% as rural development. These last two codes are included in the sub-set of input codes that score as ‘economic development’: by this definition, total DFID spending on economic development under PSNP 4 will be £39.8 m, or 14% of the total.

Table A9.4: Sector codes for DFID spending (£m, 2015/16 to 2019/20)

Annex 10: Government roles and responsibilities relating to PSNP 4 implementation

### Summary of Federal functions

The Ministry of Agriculture (MoA), in close partnership with the Ministry of Labour and Social Affairs (MoLSA), will be responsible for the management and coordination of the programme, with overall coordination vested in the MoA’s Disaster Risk Management and Food Security Sector (DRMFSS).
- The Food Security Coordination Directorate (FSCD) will coordinate the program, appointing focal points for Systems Development, Livelihoods, Public Works, Financial Management and Food Management, and organising monthly management meetings with all key implementing partners, prior to the Coordination and Management Committee (CMC) meetings. It will ensure timely transfer of resources to beneficiaries and prompt release of resources to implementing partners based on their approved annual plans and budgets.
- The Early Warning and Response Directorate (EWRD) will be responsible for the early warning system (including triggering a response that informs use of contingency budgets) and the food management system (storage, handling, dispatch, delivery and monitoring). To strengthen commodity management, EWRD will establish a dedicated Food Management Unit at federal level supported by a network of food management focal points at regional and woreda level.
- The Natural Resource Management Directorate (NRMD) will provide support, technical coordination and oversight of public works through its Public Works Implementation Unit (PWIU). A Public Works Focal Point will be appointed in FSCD to provide overall coordination.
- The Livelihoods Implementation Unit (LIU) in the Agricultural Extension Directorate (AED), working with the Livelihoods Focal Point in FSCD, will coordinate and oversee livelihood support services. The LIU and the Livelihoods Focal Point will work with other actors to provide the services relevant for different livelihood improvement strategies. All these key partners will appoint PSNP Focal Points.
- The Federal Cooperatives Agency (FCA) will oversee and support capacity building for rural savings and credit co-operatives (RuSACCOs) and the creation and strengthening of agricultural cooperatives.

The management of permanent direct support clients will gradually move to MoLSA. Given the current capacity limitation of MoLSA at all levels, and the fact that the structure of MoLSA does not exist at the woreda level in some regions, a gradual roll-out plan will be decided after the completion of the MoLSA capacity assessment. This will be used to determine a minimum capacity requirement at the federal, regional, zonal and woreda levels and to develop a specific capacity building plan. The roll-out plan will first focus on regions where there is an existing structure at the woreda level and some level of permanent MOLSA government staffing. The programme will also provide resources to build capacity including hiring of additional technical contract staff as required.

MOFED will be responsible for financial management and reporting, and for channelling resources to regions.

The following table, reproduced from the Programme Implementation Manual, provides more detail on these and other roles.

Ministry of Agriculture (MoA)
The main role of MoA is to oversee the management and coordination of the PSNP 4 / Provide technical support for planning and implementation / Assist in setting policy direction / Coordinate and create linkages between ministries
1.1 Disaster Risk Management and Food Security Sector (DRMFSS)
The main role of DRMFSS is to coordinate the PSNP 4. DRMFSS is directly answerable to the Minister of Agriculture for the performance of the PSNP 4
Food Security Coordination Directorate (FSCD)	The main role of the FSCD is to facilitate day-to-day management and coordination of PSNP 4
Early Warning & Response Directorate (EWRD)	Support the Continuum of Response: / Provide accurate and timely early warning information with PSNP 4 capacity development support / Develop Early Warning triggers for the Risk Financing Mechanism and work with FSCD to incorporate the Early Warning system into the continuum of response / Work with FSCD to build strong linkages between the PSNP 4 Risk Financing resources/activities and humanitarian response resources/activities / Procure, transport and manage in-kind commodities for the PSNP 4
1.2 Natural Resource Sector
Natural Resource Management Directorate (NRMD)	Oversee the Public Works component of the PSNP 4, including: / Public works design and technical oversight / Public works monitoring and evaluation / Coordinate with providers of BCC and literacy/financial literacy training to ensure that public works clients’ participation in these activities is counted toward their public works requirement / Ensure climate change activities ( carbon sequestration, climate resilience building) are incorporated
13 Agriculture Development Sector
Agricultural Extension Directorate (AED)	Through the Development Agents (DAs) and, where applicable, woreda subject matter specialists: / Support community targeting / Participate in planning, design and implementation of PWs / Provide appropriate technical support to clients who have chosen the on-farm pathway / Provide mentoring support for all livelihood pathways
Technical & Vocational Education & Training (TVET)	Provide appropriate technical and vocational training to clients who have chosen off-farm or employment livelihoods pathways
Federal Cooperatives Agency (FCA)	Provide financial literacy training to safety net clients (in conjunction with MFI agents depending on the area) / Provide technical support and training for off-farm livelihood pathways in conjunction with the Federal Micro and Small Enterprise Development Agency (FeMSEDA) / Provide business skills and marketing training to clients (in conjunction with FeMSEDA and others) / Provide technical support to RuSACCOs to enable them to serve safety net clients
Women’s , Children and Youth Affairs Directorate	Oversee and coordinate implementation of PIM gender provisions
1.4 Livestock Development Sector
	Provide technical support and training for on-farm livelihood pathways related to livestock / Provide overall coordination support for all livelihood pathways in pastoral areas in conjunction with FeMSEDA, FCA, and MOLSA / Through the Development Agents (DAs) and, where applicable, woreda subject matter specialists: / Support community targeting; / Participate in planning, design and implementation of PWs / Provide appropriate technical support to clients who have chosen the on-farm pathway; / Provide mentoring support for all livelihood pathways.
Ministry of Finance and Economic Development (MoFED)
MoFED is accountable for the overall financial management of the PSNP 4, including: / Management of the special and pooled Birr accounts and financial reporting. / Disbursement of cash transfers to clients

Ministry of Labour and Social Affairs (MoLSA)
Social Welfare Development Directorate	Progressively take responsibility for the permanent direct support caseload using common instruments and systems / Ensure that the social cash transfer pilot is implemented in tandem with the PSNP 4 using common instruments and systems / Develop the Unified Single Registry with PSNP 4 and eventually assume full responsibility as capacity is built
Employment Promotion Directorate	Work with FeMSEDA to provide technical support to link clients to employment opportunities for the employment livelihoods pathway

Ministry of Health (MoH)
Maternal and Child Health Directorate	Provide technical assistance to ensure health and nutrition related activities are technically sound / Help ensure PSNP 4 clients have access to existing health and nutrition services in a coordinated manner / Work with MOLSA and MoA to jointly develop key tools and instruments serving the same client (e.g. Unified Single Registry) / Through Health Extension Workers, provide nutrition messaging through Behaviour Change Communication (BCC) as a soft conditionality for temporary direct support clients, and as a public works substitute for public works clients

Federal Micro and Small Enterprise Development Agency (FeMSEDA)
	Provide technical support and training for off-farm livelihood pathways in conjunction with the Federal Cooperatives Agency , Agriculture Development Sector (ADS) and Livestock Development Sector / Work with MOLSA depending on the region to link clients to employment opportunities for the employment livelihoods pathways

Ministry of Women, Children and Youth Affairs (MOWCYA)
	Provide technical assistance to ensure activities targeting women, children and youth are technically sound / Help ensure PSNP 4 clients have access to existing services targeting women, children and youth in a coordinated manner / Help ensure gender issues are adequately addressed, monitored, and adjusted accordingly

Source: MoA 2014 pp. 81-84; MoA (2014) pp. 18-5 to 18-6; 18-20-18-29.

Annex 11: Summary of risks by type

#### External risks

Severe drought might derail progress in reducing food insecurity

A key external risk to PSNP is a drought shock of such magnitude that PSNP and humanitarian protective arrangements are overwhelmed. In this case, PSNP may succeed in reducing impact compared to the no-PSNP counterfactual, but gains in household welfare by 2020 would be below those required to achieve PSNP 4 targets.

The experience of PSNP 3 suggests that this risk is manageable. The 2010-11 Horn of Africa drought was an extreme climatic event (very low frequency, very high magnitude): yet various sources of evidence, including PSNP impact evaluations (which show the average food gap continuing to close between 2010 and 2012) suggest that the combination of the PSNP and a large-scale humanitarian response prevented the drought from de-railing the positive trend towards improving rural welfare. Under PSNP 4, expanded coverage and a revised continuum of response should allow for the effective management of a large-scale drought (albeit at the cost of running down multi-year funds, which would then need to be replenished to enable delivery of the later years of the phase).

A further source of external risk is that local officials might use the denial or promise of PSNP benefits to induce households to behave as desired by local authorities. This could take a number of forms.

Access to PSNP benefits may be influenced by factors other than need

Firstly, local officials might allocate (or say that they are allocating) access to the programme based on political affiliation. Particularly if the targeting process coincides with the run-up to elections, it is possible that local authorities might extend PSNP transfers as a reward to non-poor supporters of the government in power; or deny transfers to poor opposition members[56]. Alternatively, officials might seek to bring as many households as possible into the programme to engender loyalty to the ruling party, diluting resources so that per household transfer levels drop to levels at which they have very limited impact.
[56] In 2010, it was alleged that local officials in SNNPR and Tigray had threatened to deny access to donor-financed, Government-implemented programmes (including PSNP but also PDP, GEQUIP, PSCAP, DIP and humanitarian food aid distribution) to those who belonged to opposition parties (Human Rights Watch 2010).
Studies have found it hard either to prove conclusively or to disprove decisively these allegations of political distortion. The first two rounds of impact evaluation (2006 and 2008) did find evidence of dilution through the rapid rotation of households on and off the programme. However, this appeared to be due to misunderstanding of programme objectives and processes: with improved training, dilution has dropped off significantly, with an increase in the average length of time that households have been on the programme, and a dramatic increase in average household transfer receipts. In the 2005-2010 phase, research by ODI (2006) found limited but inconclusive evidence of politicisation of PSNP targeting (by both ruling and opposition parties). The report concluded that if manipulation did occur it was ‘locally specific rather than pervasive or systematic’ (Sharp, Brown and Teshome 2006). In late 2009, USAID conducted a visit to seven woredas which historically voted for the opposition to investigate the possibility that relief food or PSNP transfers were subject to political distortion. They found no clear evidence of such distortion in the allocation of households to the PSNP; but noted there was potential for distortion in the allocation of PSNP resources from Region to woreda. Finally, in 2010, in response to allegations from HRW and opposition politicians, the Development Assistance Group (DAG) conducted a comprehensive review of accountability systems and safeguards in major donor-supported programmes, including PSNP. It identified a number of mutually-reinforcing safeguards within PSNP, some of which had been present in the first phase, and some of which had been implemented since January 2010 (DAG 2010).
Analysis of PSNP targeting and consultations with beneficiaries and non-beneficiaries in PSNP implementation communities have not revealed any evidence of politicisation. PSNP targeting performance has been evaluated a number of times, in a number of ways. Using the impact evaluation panel survey, researchers have looked at the characteristics of the households selected for inclusion in in PSNP and concluded that the targeting principles were being followed for both public works and direct support beneficiaries: PSNP recipient households average significantly lower incomes, fewer assets and smaller areas of agricultural land than do their neighbours.
This does not prove beyond doubt that there have been no cases of either inclusion error in general or political distortion in particular. It does however suggest that if incidents of distortion have occurred, they have been very rare. PSNP targeting out-performs the international average for social safety net (SSN) programmes; all surveyed African SSN programmes; and more than half of Asian SSN programmes (Coll-Black et al 2011 pp. 14, 16, 22-3). The impression of accurate targeting is reinforced through analysis of nationally-representative sample surveys which contain a question on receipt of PSNP transfers. Both the 2011 Household Income, Consumption and Expenditure Survey (HICES) and the 2014 mini-Demographic and Health Survey found PSNP beneficiaries concentrated in the bottom two quintiles of the wealth distribution; the HICES data also shows that PSNP is more accurately targeted to the poor than is humanitarian food assistance (World Bank 2015a p. 75; CSA 2014 p. 15).
These sources of information, showing that PSNP beneficiaries are, as intended, the poorest, suggest that there is no systematic enrolment of ineligible (non-poor) households on the basis of party affiliation (inclusion error). The possibility that local officials ration PSNP benefits to poor members of the party in power while excluding equally poor households thought to be loyal to other parties is harder to disprove: given that programme coverage has fallen to five million in 2014/15 and there are estimated to be 20-30 million Ethiopians under the poverty line, there are many who should receive PSNP transfers but do not (exclusion error) and the difference in welfare between beneficiaries and non-beneficiaries is likely to be extremely small even with the best-possible targeting system. As such, it is hard to either prove or disprove that political affiliation plays a role in determining who is excluded. However, politics as a basis for inclusion has not been mentioned in the qualitative research for the impact evaluation, or in the independent WIDE longitudinal studies (both of which would be places where if it existed, it would be expected to come up in discussion).

PSNP and other Government development policies

Secondly, transfers could be made conditional on household compliance with other Government programmes and policies. The denial or promise of PSNP transfers might be used to induce households to move to new locations as required by Government development policies for service provision (the effort to resettle scattered, generally lowland populations in commune centres under the Commune Development Programme or CDP) and / or the acquisition of land for large-scale commercial investments. Development Agents might use the offer or withdrawal of PSNP transfers to force people to purchase fertiliser supplied by the Government extension service (and so meet their targets for the distribution of agricultural inputs)[57].
[57] A US-based human rights organisation has alleged that receipts of food transfers for Suri in the South Omo (in SNNPR) have been made contingent upon households registering a house in a settled village (Oakland Institute 2014 Engineering ethnic conflict: the toll of Ethiopia’s plantation development on the Suri people. November 2014). The 2014 PSNP Roving Appeals Audit found a case of a PSNP beneficiary who was threatened with eviction from the programme for refusing to buy Government-supplied fertiliser; and a number of cases where payments for fertiliser had been deducted at source from PSNP transfers (WABEKON Development Consultants PLC (2015) 2014 Roving Appeals Audit of PSNP. Addis Ababa). Both reports are cited in World Bank 2015c pp. 7-8.

To date, geographical overlap between PSNP 3 and the CDP has been limited. However, with PSNP 4 expanding to cover all districts in Somali and Afar Regions (where the CDP and other development-induced relocations have been relatively common) and additional districts in South Omo, the overlap will become more extensive. The World Bank has conducted a study of the potential interface between the CDP and those programmes (including PSNP) that the Bank finances.

Either of the risks described above – the use of PSNP benefits to secure either electoral support or compliance with Government policy – would clearly compromise the programme. Firstly, in terms of a narrow focus on PSNP objectives, the denial of safety net transfers to those entitled to them or the awarding of transfers to those not entitled to them would be a fundamental violation of the needs-based targeting that is central to programme design and impact. More broadly, such abuse would not be in line with international good practice on resettlement, to which the Government has committed.

These risks will be managed using a range of different approaches. Changes in PSNP 4 should help monitor and reinforce programme adherence to human rights and PPA principles. The safeguard and social accountability mechanisms of PSNP 3 are to be strengthened with greater resources and attention. As described in the Enhanced Social Assessment and elsewhere, this will involve:

- A communication strategy and public awareness campaign that actively disseminates information regarding programme principles (targeting, rights and responsibilities, options for appeals and grievance redress, etc.), particularly for those groups (e.g. female-headed households) and areas (e.g. pastoral communities) which have been found to have less knowledge of how the programme is meant to work.
- A robust, community-based targeting process, now to be cross-checked with a proxy means test and with dedicated attention to improving targeting in the lowlands.
- a computerised management information system which incorporates a single beneficiary registry, and which should allow for better monitoring of patterns in programme entry and exit and enable investigation into case management.
- continued regular quantitative assessment of the accuracy of targeting through impact evaluation (using a household panel survey) and analysis of PSNP beneficiary incidence in national surveys.
- strengthened social accountability mechanisms. In the last year of PSNP 3, Government and donors have piloted the incorporation of PSNP into the remit of the second phase of the Ethiopia Social Accountability Project (ESAP 2), which has supported improvements in health, education and agriculture services under the Promotion of Basic Services (PBS) programme. ESAP 2 contracts national civil society organisations (CSOs) to administer Citizen Report Cards (CRCs) and Community Score Cards (CRCs) and then facilitate local feedback meetings between the providers and users of basic services to identify problems and propose solutions. The pilot was a success, adding value to both the PBS (providing a more complete picture of MoA services) and PSNP (complementing the programme-specific social accountability mechanisms). Under PSNP 4 the ESAP 2 overlap pilot will be expanded to cover 10% of PSNP woredas; lessons learned will inform the incorporation of PSNP 4 into the remit of ESAP 3 (World Bank 2015b p. 10).
- The monitoring of social accountability and beneficiary and non-beneficiary perceptions of fairness through improved record-keeping by the Kebele Appeals Committees (KAC); and the spot-checking of these processes through continued periodic roving appeals audits and rapid response missions.
- direct beneficiary feedback and assessment of local perceptions of programme fairness through the impact evaluation, WIDE research, and periodic DFID or multi-donor field visits.

These programme-centred measures will be complemented by other, broader checks. For as long as is considered appropriate, DFID will remain actively engaged in the work of the Development Assistance Group (DAG) to conduct periodic multi-agency visits to monitor the implementation of the CDP (and now development-induced resettlement more broadly); and to use the findings of these consultations to inform policy dialogue with the Government (DAG 2015). These risks will also be incorporated into the cross-HMG Risk Matrix for Ethiopia, with status and trajectory of change to be reviewed jointly by the Embassy and DFID Ethiopia and, if necessary, elevated for the attention of the Head of Office and / or Ambassador in consultations with senior GoE officials.
#### Delivery risk

Delivery risk is taken here to cover both (i) the risk that intended positive outcomes do not occur as planned; and (ii) the risk that unintended negative outcomes occur. As such, it subsumes the category of ‘environmental and social risk’. The incorporation of environmental and social risk under delivery risk for PSNP reflects the fact that PSNP is explicitly intended to benefit the poorest and most vulnerable groups in Ethiopia, including through improving the natural environment: if some of these groups suffer negative consequences due to PSNP implementation, this is not merely a negative side-effect but a shortfall in programme delivery.

The risk that the Programme will have a negative impact on the environment is addressed in both design and implementation. Throughout PSNP 3, the Programme has employed an Environmental and Social Management Framework (ESMF) to screen each proposed public works sub-project for potential negative effects; where risks are identified, mitigating actions need to be proposed. The ESMF is the operational application of the World Bank’s safeguards policies. The ESMF was comprehensively updated as part of the preparation for PSNP 4 (MoA 2014).

In preparation for World Bank support to PSNP 4, an Enhanced Social Assessment was conducted, involving consultations in 20 kebeles in all eight PSNP-implementing Regions (MoA 2014c). Given that PSNP is intended to benefit the extreme poor (chronically food insecure households), the Assessment identified ‘underserved and most vulnerable’ rural groups within the PSNP client population, to assess if the Programme would benefit them, and identify any design changes required to improve the benefits they receive. These groups include women (in male- as well as female-headed households); children; polygamous households; pastoralists; unemployed rural youth; recent migrants who are new residents in their current woreda, and so lack family or social networks; and labour-poor households (those who will receive Direct Support transfers) in which adults are, for example, elderly or chronically ill, including people living with HIV/AIDS (PLWHA).

The Social Assessment concluded that in general the core functions of PSNP serve to reduce risks and improve welfare for the most socially marginal groups; but also identified a number of design modifications which would increase the positive impact, and minimise the chances of negative impact, for these groups (ibid pp. 7-9). Most of these have now been incorporated in the PSNP 4 Design Document and PIM. These include provisions that:
- provide ‘permanent direct support’ households (those with no adult labour due to disability, old age, chronic illness etc.) with transfers all year round (12 rather than just six months each year).
- Clarify and standardise the approach to allocating transfers for polygamous households
- Adapt programme implementation to the livelihoods practices and social organisation of pastoralist and agro-pastoralist groups in the lowlands. This includes adjusting the annual planning, budgeting and reporting cycle; revising the lowland public works guidance; and working with clan leaders to improve targeting outcomes.
- Reduce the possibility that public works requirements have a negative effect on women (through clearer guidance on (i) when pregnant and lactating women should be moved from public works to direct support, and (ii) specification of lighter work (and 50% shorter hours) for women’s participation)
- Relax the provision against implementing public works on private land: with consensus from the community, public works can now be used to improve the lands of the most vulnerable members of the community (female-headed households with severe labour shortages)
- Develop health and safety guidelines and ensure the provision of first aid services at public works sites
- reiterate the prohibition on child labour on PSNP public works and emphasise the importance of schooling
- Strengthen social accountability and grievance redress mechanisms
- Provide livelihood advice and access to financial services to individuals, rather than (as under HABP) to households (when in practice it was almost always the male head of household who would get the support).
- Emphasise savings and one-off livelihoods grants (recognising that for the poorest and most vulnerable households credit is often not the most appropriate form of support, and may in fact increase the risk of destitution); and prioritise women for the roll-out of the one-off lump-sum grants for livelihoods investments

The Enhanced Social Assessment concluded that “overall PSNP 4 will need only minor adjustments [from PSNP 3] to meet the needs of the most vulnerable and the communities were in general happy with the design and accepted proposals for PSNP 4. Regarding involuntary asset loss, no examples were found and no complaints were made in the woredas visited” (MoA 2014c p. 6).

One of the main concerns with regard to PSNP 4 delivery relates to the livelihoods component. The new PIM includes provisions designed to promote coherence, coordination and implementation between the different institutions (within and beyond MoA) involved in the delivery of livelihood services. This will entail significant investments in capacity building and coordination. There are particular concerns about the capacity of the front-line bureaucrats – the Development Agents – who will be required to deliver the livelihood services. Ethiopia has one of the biggest agricultural extension services amongst low income countries (in terms of the ratio between DAs and farmers): but the number of DAs is still low and competing demands on their time very high. High workloads, low salaries and poor housing result in high rates of staff attrition (Brown, Umer and Kinyeki 2015p. 13). While it is relatively easy to fill vacancies left by resignations given the supply of recent university graduates, high turnover results in the loss of accumulated knowledge and skill and retards the development of institutional capacity.

While the pressure on DAs is significant and a concern for programme delivery, capacity has been increasing in recent years. In PSNP impact evaluations, the percentage of households reporting improvement in DA support between 2010 and 2012 ranged from 69% to 84%, depending on Region; this built on impressive improvements between 2008 and 2010, when 53% to 82% of households reported improvement in DA support. This improvement is likely due to a combination of increases in DA staffing and HABP’s focus on extension service provision to PSNP households. The evaluation found that PSNP public works participants and recent graduates were more likely to receive DA support than comparable non-PSNP households; however, direct support beneficiaries are no more likely to receive DA support than comparable non-PSNP households (Berhane et al 2013; cited in MoA 2014a p. 40). PSNP 4 design attempts to build on this progress in improving the numbers and workloads of DAs, with DA numbers, skills and length-in-post a priority for the new PSNP Capacity Development Strategy and facility. The PIM also incorporates improvements to workflow systems (notably a streamlined household Livelihood Checklist) that are designed to enhance efficiency and reduce the administrative burden on DAs.

#### Fiduciary risk

In recent years, Ethiopia has made good progress regarding Public Financial Management (PFM). This can be seen in the Public Expenditure and Financial Accountability (PEFA) reports conducted in 2007, 2010 and 2014. Ethiopia is currently ranked in the top five countries in the Africa region in terms of PEFA scores (World Bank 2014 p.7)[58].  The key findings from the draft PEFA 2014 are (i) significant improvements in budget variances; (ii) the internal control system is comprehensive, widely understood and effective at the Federal Government level; (iii) external audit follows international standards and covered 100% of Federal Government expenditure in 2012/13; and (iv) at the Federal and Regional levels, spending reports are prepared on monthly basis with no more than 4 weeks lag while quarterly reports are available after two weeks of end of the quarter.
[58] World Bank (2014) Project Concept Note (draft) - Ethiopia PFM project. June 2014, p.7. The ranking pertains to the Federal Government of Ethiopia which has received a PEFA score of around ‘3’ for 2014.

However, FM capacity remains underdeveloped, particularly in programmes such as the PSNP which involve millions of small monthly transactions in the remotest areas of the country where staff turnover impedes capacity development. These risks relate primarily to the inappropriate or ineffective use of programme resources for developmental but non-programme purposes. Fraud and corruption risks are seen as less significant than fiduciary risks. The World Bank PAD for PSNP 4 rates capacity risk as 'high' and fiduciary risk as ‘substantial’ (although adequate to meet IDA requirements under OP/BP 1.0: World Bank 2014b pp. 24, 98-9); the draft DFID FRA (which combines a backward look at PSNP 3 and a forward look at PSNP 4) rates fiduciary risk as 'moderate' ( Martin and Mussa 2015 pp. 5). Both the FRA and PAD identify structural and capacity issues (including inadequate regional supervisory powers; high turnover of woreda level accountants and cashiers; high levels of between-year and between-region variations in levels of budget utilisation; poor follow up on recurrent audit findings), especially in remote lowland woredas. Food management remains a concern: inadequate transparency and accountability create potential for mismanagement and abuse (although the World Bank notes that ‘Overall however these reports tend to be isolated and have involved only a tiny fraction of programme resources’: World Bank 2015c p. 7).

Although weak, financial management and control of fiduciary risk in PSNP have improved over time. The last two annual audits have been unqualified, for the first time; the programme has moved from Excel to IBEX accounting software; and the timeliness and quality of Interim Financial Reports (IFRs) has improved. The FRA notes that 'steady progress has been made in strengthening financial management of PSNP III' and 'there appears to be a credible programme of financial management reforms planned for PSNP IV'. The management of food resources lags financial management; but has started to improve with the DFID-financed WFP Food Management Improvement Programme (FMIP). With both financial and food resources, the few instances of misappropriation have resulted in Federal and Regional Governments taking legal action and imposing jail sentences and bans on trucking companies.

The Government’s overall commitment to the control of fiduciary risk in the PSNP is strong. Instances of misappropriation have resulted in Federal and Regional Governments taking legal action and imposing jail sentences, confiscation of assets and bans on trucking companies found guilty of mismanagement of food resources. The new phase does entail new risks with the expansion to a further 92 woredas, which will need to be brought up to capacity; significant budgets have been committed to building capacity throughout the programme but particularly in these new operational areas. PSNP 4 design documents commit the Government to a number of changes (and commit significant resources to capacity-building) to push forward further improvements in financial and commodity management. Realisation of these plans will be followed through in the DCT and the PSNP FM Task Force. The shift from food to cash, and over the longer term form physical cash to electronic payment, should further help minimise the potential for misuse of resources. PSNP 4 will change governance mechanisms in ways that improve Regional oversight of funds: while the annual PSNP budget will still only be ‘proclaimed’ at regional level, MoUs between Federal and Regional Governments will provide Regional budget breakdowns and enhance abilities and obligations of the regions in managing PSNP resources for intended purposes (Martin and Mussa 2015 p. 16). New procedures are incorporated in the updated PSNP Financial Management Manual and summarised in chapters 12 (financial management), 13 (food management) and 14 (procurement) of the PSNP 4 PIM should consolidate and carry forward progress seen over the last few years.

Annex 12: Monitoring and evaluation under PSNP 3

PSNP has benefited from an extremely high standard of impact evaluation. A performance and impact assessment is conducted every two years (2006, 2008, 2010, 2012 and most recently 2014, for which the draft headline results are to be released in April 2015). This evaluation involves:
- a survey – the Ethiopian Food Security Survey (EFSS) - of a sample of households in PSNP woredas (in 2012, 5,092 households in the highlands and 1,619 in the lowlands). In the highlands, the sample is a panel; this has not been possible to reproduce in the lowlands of Afar and Somali due to the mobility of the population, the lower capacity of the local CSA offices, and insecurity in some woredas. The household survey provides the basis for the key outcome / impact level calculations of programme impact on household food security (the food gap and asset holdings).
- the woreda capacity survey, which assesses the staffing, skills and procedures of the woreda-level institutions responsible for implementing the programme
- a community (kebele) and local price questionnaire
- qualitative research through key informant interviews and focus group discussions (FGD)

The evaluations reflect collaboration between a number of actors. Quantitative data (from households, community bodies and woreda officials) are collection by the regional offices of the Central Statistical Agency (CSA) and have been analysed by researchers from the International Food Policy Research Institute (IFPRI); qualitative research is conducted by the Sussex-based Institute of Development Studies (IDS) and the Ethiopian organisation Dadimos.

These two-yearly assessments generate two reports (a programme performance report and a household impact assessment) each for the highland and lowland regions. They generally produce final estimates some 12 months after data collection, reflecting the time required to enter, clean and analyse the data; discuss the draft findings; and incorporate revisions and additions.

Routine monitoring has been less well developed. Basic data includes numbers of beneficiaries; status of the transfer of funds (from Federal to Region, Region to woreda, and woreda disbursement to beneficiaries); and quantities of public works planned and then subsequently completed. Much of it has been paper-based, with hard copy sent from woreda to Region, collated, and the summed data then sent in hard copy from the Region to the Federal level. This has limited the ability of programme managers and policy makers at the Federal level to identify and understand patterns of variation in performance; it also involves considerable lags. This lack of granular detail in the monitoring data is one reason why the two-yearly impact evaluation has also collected a lot of information on basic aspects of programme implementation that would be better collected through routine monitoring.

Between regular reporting on operations and the evaluations is an intermediate category of reviews. A number of these instruments were introduced as stop-gap solutions to provide basic information on programme activities and performance in the absence of timely and comprehensive reporting, and still play an important role: these include tools (e.g. the public works reviews, roving audits and RRT visits) which are based on large samples to compensate for the lack of detailed comprehensive MIS data. These play an important role; but are somewhat erratic in frequency, which limited their value as a source of information for annual monitoring purposes.

Thus, the Public Works Reviews should in principle should be conducted twice a year, with the first review focussing on the quality of the planning process and the second assessing the quality of the works that have been undertaken: but in practice, only four occurred over a three-year period. These reviews are described as ‘quantitatively informed qualitative assessment’ (1st 2011 Public Works Review p. 8): they could better be described as a qualitatively-informed quantitative assessment, in that they rely upon mixed teams of experts reaching a consensus on how to value a given sub-project or function of woreda planning (from ‘very poor’ through ‘poor’, ‘satisfactory’, ‘good’ and ‘very good’); applying numeric weights according to score; calculating total numeric scores for each woreda or project; and in turn aggregating up to derive average scores for regions or types of projects . While the sample is reasonably large (in 2012, 156 sub-projects from 35 woredas in all eight regions in which PSNP operates), this is still a small fraction of the total number of sub-projects (in excess of 30,000) that are implemented by PSNP each year. This, plus the fact that sampling is purposive rather than random (aiming to provide insights into the performance of difference types of projects, even if some of these account for only a small fraction of overall PSNP-supported projects) means that the scores should be taken as indicative rather than statistically representative. It has however provided a reasonably good check of the ‘typical’ performance of PSNP public works, and the variations around this norm; and considerably better than is available for most public works programmes.

There is some way to go in integrating the large number of separate streams of monitoring data. Reflecting the division of departmental responsibilities within MoA (and particular donor interests), there is limited capacity to generate an overview of programme performance that encompasses transfer delivery, public works completion, and HABP outputs.

Partly to compensate for the underdevelopment of routine (monthly or quarterly) monitoring data, and to address the fragmentation of information streams, the Programme has developed a mechanism of comprehensive six-monthly joint reviews to track implementation and progress towards outcomes. These Joint Review and Implementation Supervision (JRIS) events occur in late May and late November and each involves two weeks of consultation (the first in the Regions, the second in Addis Ababa) and some 400 participants. On the final day of the Federal workshop, key findings are presented to the State Minister of Agriculture and head of the PSNP donor agencies, with agreements on actions to be taken written up and circulated in an Aide Memoire.

There have been significant gaps in the collection of data against a number of indicators particularly for the HABP programme. As the related sections of the HABP chapter indicate there appears to have been very limited data collection for Outputs 3, 4 and 6. While some of this may be due to changes in indicators between the original logframe and the final (2012) version, it is likely due primarily to the difficulty in measuring some of the indicators, as they require household-level data, but the impact evaluations (the primary source of household-level data) are unable to isolate HABP interventions from regular extension and credit support. In 2013, a pilot study was conducted on household-level qualitative data, the findings of which may help improve M&E collection and analysis during the next phase. In addition, there has been limited monitoring for the PSNP output 5: coordination, complementary and synergy promoted in Government and with programmes and organizations.

The current set of M&E instruments have been reasonably effective in capturing key trends in programme implementation and results; but will need to evolve further in the next phase. A number of ad hoc ‘quick and dirty’ innovations and a strong evaluation system have enabled the programme to identify problems and communicate success over the first nine years of its life. However, the planned incorporation of the safety net within broader policies and system in the near future will require that M&E becomes more comprehensive, timely and above all integrated; while the improvements in government capacity that have been achieved since 2005, together with falling costs of information and communication technologies (ICT), makes such a shift feasible.

The aspects of M&E that receive the most focus are those which provide information to regional and federal level and there is a tendency to think that all monitoring information (as well as evaluation data) needs to be submitted in this way. In addition there is insufficient attention paid to who needs what information at what frequency in order to assist decision making and a lack of awareness of the needs of front line implementers. As a result too much data is planned to be collected but actual data collection often includes gaps and is poor in quality. Furthermore, data is expected to be collected before the users of such data have been determined or the methods by which the data is to be analysed is agreed.

Annex 13: Monitoring the gender and social development provisions

Gender and Social Development (GSD) Provision	Responsible for implementation	Responsible for monitoring
Transition of pregnant women to temporary direct support after first ANC visit (or in the absence of such a visit the fourth month of pregnancy)	DA	WFSTF
Continuation of women’s participation in temporary direct support through 1 year postpartum
Targeting priority for female-headed households for programme inclusion	CFSTF and KFSTF
Targeting priority PLWHA
Targeting priority for women in polygamous households
Targeting priority for divorced women (during programme implementation)
Targeting priority for disabled people
Targeting priority for female household heads for livelihoods transfer
Permanent direct support for elders	WoLSA
Permanent direct support for physically disabled people
Joint client card entitlement for husband and wife	KFSTF
Labour support for eligible labour-scarce households	PWFU
Careful consideration of the needs of men and women and other vulnerable groups in annual public works planning	KFSTF	DAs monitor during PW planning
PW projects shall reduce women’s regular work burden
Construction of childcare centres at PW sites
Lighter tasks for women	PW Foreman / forewoman, DA, Natural Resources Desk	WFSTF
Protection for children under 16 years from participating in PW
PW team composition should be balanced with men and women; women-only teams for certain projects
Women’s participation in PSNP decision making structure
Women as team leaders in PW
Women’s 50% workload for PW
Women’s late arrival and early departure for public works
Travel distance to PW - PW site should not be far from village
Accessibility of livelihoods interventions – livelihoods activities (financial / literacy training, technical training, and business skills/marketing training) should be at times and in locations accessible to women whenever possible	DA
Resource distribution distance – distribution site should be not more than 3 hours’ walking distance from village	Early Warning Desk

Source: MoA 2014d pp. 17-10 to 17-11.

Annex 14: PSNP 4 Logframe

### Policy Objectives indicators

Hierarchy of Objectives	Objectively Verifiable Indicators	Means of Verification
Policy Objectives
GTP: To contribute to the achievement of GTP objectives through contributions to four key government policies, strategies and programmes	Number of clients raised above poverty line	Government of Ethiopia poverty surveys
	Total poverty-oriented expenditure as % of GDP	Government of Ethiopia poverty surveys
Social protection: To see all Ethiopians enjoy social and economic well-being, security and social justice	Number of safety net clients expressed as a percentage of people living below poverty line	Programme monitoring and core Government of Ethiopia data
	Number of safety net clients benefiting from fee waivers and nutrition-related conditionalities	Programme monitoring
DRM: To reduce risks and impact of disasters	Value of distress sales of assets by safety net clients as compared to previous similar disasters in operational areas	Annual analysis of crop and livestock losses from monthly EW reporting.
	Number of children in operational areas affected by severe malnutrition	Demographic and Health Survey (DHS)
CRGE: To achieve the GTP goal of building Ethiopia into a middle-income country by 2025 in a way that is both resilient to the negative impacts of climate change and does not result in a rise in greenhouse gas emissions	% of land covered by improved watershed and rangeland management structures and practices	Public Works MIS
	Mt CO2e sequestered in public works supported watersheds	Public Works Impact Assessment
Nutrition: Improve nutritional status of women and children	% stunting in children under 5 in operational areas	Biannual Household Survey

### Goal: “Resilience to shocks and livelihoods enhanced and food security and nutrition improved for rural households vulnerable to food insecurity.”

Indicator		Baseline	Target					Means of verification
			2016	2017	2018	2019	2020	Frequency	Source
1	Percentage of children 6-23 months of age who receive a minimum acceptable diet [Nutrition] – disaggregated by sex	No PSNP related data. DHS 2011 is 4% ;		x		x		Every 2 years	Household impact survey
2	Household dietary diversity [Nutrition] – disaggregated by sex	2012: 3.4 food groups (0.46 increase in # of food groups consumed by PW clients and 0.60 increase by DS clients)		+0.5		+1		Every 2 years	Household impact survey
3	Average value of asset holdings [Livelihoods] - disaggregated by sex			+15%		+25%	+30%	Every 2 years	Household impact survey
4	Number of different income sources [Livelihoods/resilience] - disaggregated by sex			x		x		Every 2 years	Household impact survey

### Outcome: “Enhanced participation in improved rural safety net, livelihood and nutrition services by food insecure female/male headed households”.

Indicator		Baseline	Target					Means of verification
			2016	2017	2018	2019	2020	Frequency	Source
1	Number of months of self-reported food insecurity (including safety net transfer) for PSNP - disaggregated by PSNP 3 beneficiaries and all beneficiaries	PSNP3 beneficiaries		1.5		1		Every 2 years	Household impact survey
		All Beneficiaries		2.9		2.3
2	Average non-food expenditure of PSNP PW clients (2012 constant birr per adult equivalent per month) - disaggregated by sex	212 (2012)		300		360		Every 2 years	Household impact survey
3	Percentage of clients reporting that they can provide adequate meals for their family for 12 months a year - disaggregated by sex	0	10	20	30	40	50	Every 2 years	Household impact survey
4	Percentage of households reporting improvements in self-reported well-being - disaggregated by sex			20		40		Every 2 years	Household impact survey
5	Percentage of clients reporting that asset depletion is prevented as a result of transfers - disaggregated by sex	40%?		45%		55%		Every 2 years	Household impact survey
6	Number of clients covered by the programme (chronic caseload)- disaggregated by sex	7.2 m	7.2 m	7.8 m	8.3 m	8.3 m	8.3 m	Annual	Progress reports/MIS
7	Average number of consecutive years that highland client households have received safety net transfers (survey year and preceding year) - disaggregated by sex	none		x		x		Every 2 years	Household impact survey (then MIS)
8	Percentage of safety net clients reporting their livelihood has benefited from public work created assets - disaggregated by sex of respondent and type of PW			30%		50%		Every 2 years	Household impact survey
9	Percentage of safety net clients reporting that they have benefited from public work created social infrastructure - disaggregated by sex and type of PW			70%		80%		Every 2 years	Household impact survey
10	Percentage of client households with adequate Knowledge, Attitude and Practices (KAP) of nutrition-related behaviours - disaggregated by sex	none		x		x		Every 2 years	Household impact survey
11	Percentage of safety net clients reporting new income sources - disaggregated by sex	0	0	5	10	20	30	Every 2 years	Household impact survey
12	Percentage of safety net households with business plans reporting that their business plans reflect their priorities, needs and capabilities (disaggregated by sex of respondent)	46% (HABP CUs Qualitative survey report)		65%		75%		Every 2 years	Household impact survey

*2012 impact assessment; **Public works review; ***Programme monitoring data (IC or other), most recent available
### Output 1: Prioritised instruments and tools in place to support an effective system for Social Protection and Disaster Risk Management

Indicator		Previous Indicator/ Target	Baseline	Target					Means of verification
				2016	2017	2018	2019	2020	Frequency	Source
1	Percentage of safety net woredas where MIS and single registry are operational	N.A.	Single Registry	0% (Core modules ready for data entry in pilot woredas)	0%	25%	50%	75%	Every 6 months	Programme Monitoring /Annual Report
			MIS		0%	25%	50%	75%
2	Percentage of kebeles where poverty index is used to complement community targeting	No equivalent		indices developed	25%	40%	55%	75%		Programme Monitoring
3	Percentage of clients and non-clients in safety net woredas reporting that targeting and graduation processes are fair - disaggregated by sex	Clients: 78% (2012)		50%		75%			Every 2 years	Household impact survey
		Non-clients: 51% (2012)		40%		60%
4	Percentage of households graduating in the previous year who report they were given at least 12 months' notice- disaggregated by sex	20%	20%		75%		85%		Every 2 years
5	Percentage of graduate households that report full (12 month) food security - disaggregated by sex of HH head				80%		90%		Every 2 years	Household impact survey
6	Number of woredas having contingency plan and DRR plan		112	160	210	260	310	360		DRM Coordination Office reporting
7	Percentage of woredas providing regular (12 months / year) EW monitoring data to the regions		c. 40% (50-60% in highlands, 0% in lowlands)	50%	60%	70%	80%	90%		DRM Coordination Office reporting
8	% of woreda annual safety net plans fully incorporated in woreda development plan with a rating of good or above - disaggregate highland and lowland	90% of PSNP plans fully incorporated in woreda development plans by 2011	Highland: 83% have good or above (2012)**	90%	95%	95%	95%	95%	Annual	Public Works Review
			Lowland: 25% have good or above (2012)**	40%	50%	60%	75%	90%
9	Percentage of clients and non-clients who are aware of programme objectives and entitlements (disaggregate by sex, and by permanent DS and other clients)	No equivalent	Overall clients: 62% (2012 impact assessment data)		65%		75%		Every 2 years	Household impact survey
			Clients -- male-headed households: 66%		67%		77%
			Clients -- female-headed households: 55%		63%		73%
			Public works clients: 68%		70%		75%
			Direct support clients: 44%		60%		70%
			Non-clients: 64% (2012)		65%		75%
10	Percentage of grievances registered related to delivery of PSNP that are addressed	No equivalent	70%	70%	75%	80%	80%	80%	Annual (cross-checked every two years)	Programme Monitoring /MIS (cross-checked with Household impact survey)
11	Number of safety net kebeles implementing social accountability tools	No equivalent	4	30	60	90	120	130		Programme Monitoring
12	Capacity development indicators which are expected to be developed after the development of CD strategy			100%	100%	100%	100%	100%	Annual	Progress reports/MIS
13	Number of woredas implementing CSI recommendations		24	24	60	130	250	400	annual	programme monitoring / administrative data
14	Number of woredas covered by the programme		319	340	360	411	411	411	Annual	Progress reports/MIS

### Output 2: Appropriate, timely and accessible transfers received by male and female clients

Indicator		Baseline	Target					Means of verification
			2016	2017	2018	2019	2020	Frequency	Source
1	Percentage of clients paid within the agreed timeframe (20 days for cash and 30 days for food) -	Highlands: 2013 data varied between 44 and 77% with an average for year of 48% of cash woredas -- but for 45 days rather than 20.***	60%	70%	80%	90%	90%	Reported on annually, but data collected monthly	IC/MIS
		Lowlands: No data available for food because of lack of functioning IC
2	Percentage of clients reporting that they receive cash or food transfers at a place less than 3 hours walking from their home - disaggregated by sex	84% in highland area*		90%		90%		Every 2 years	Household impact survey
		Varies between 90% (Somali) and 20% (Oromia) in lowland areas*		70%		90%
3	% transfers received that have a value of at least 15 kg of cereals and 4 kg of pulses per person per month		50%	55%	60%	65%	70%	Annual	Program monitoring and Household impact survey
4	Percentage of households reporting that use of transfers is decided jointly by wives and husbands - disaggregated by sex	No data		x		x		Every 2 years	Household impact survey
5	Percentage of clients receiving woreda contingency resources within 60 days of threshold being reached	No data	65%	70%	75%	75%	75%	collected monthly, reported on annually	IC/MIS
6	Percentage of clients receiving federal contingency budget resources within 60 days of identification of needs	No data	50%	60%	70%	80%	80%	Reported on annually, but data collected monthly	IC/MIS

### Output 3: Sustainable community assets built up and access to social services enhanced

Indicator		Previous Indicator/ Target	Baseline	Target					Means of verification
				2016	2017	2018	2019	2020	Frequency	Source
1	Percentage of public works planned and implemented following the GoE's CBPWD Guidelines or Rangeland Management Guidelines integrated with DRR/Adaptation and mitigation plan – disaggregated by highland and lowland	100% of PW plans developed following community planning guidelines by December 2010	Highland: 72%**	75%	80%	85%	90%	90%	Annual	PW Review
			Lowland: 43%**	50%	60%	65%	70%	70%
2	Percentage of public works projects constructed according to technical standards in info-techs – disaggregated by highland and lowland	90% of public works reaching satisfactory standards and sustainability ratings by December 2010	Highland: 89%**	90%	91%	93%	94%	95%	Annual	PW Review
			Lowland: 81%**	82%	83%	86%	87%	88%	Annual	PW Review
3	Percentage of public works projects screened in accordance with ESMF – disaggregated by highland and lowland	100% of PW projects screened in accordance with ESMF by December 2010	Highland 90%**	90%	100%	100%	100%	100%	Annual	PW Review
			Lowland: mixed results	50%	60%	70%	80%	80%
4	Total closed area subject to enhanced management for climate adaptation		zero	37,500 ha	94,000 ha	172,000 ha	297,000ha	500,000 ha	Annual
5	Percentage of clients that feel PW sub-projects reflect their needs - disaggregated by sex		75	82	84	86	88	90	Annual	Household impact survey/ / Social Accountability tool and PW reviews
6	Percentage of public works projects for which planned mitigating measures have been implemented	None	Voluntary asset very high - but not full range of measures	50%	60%	70%	80%	80%	Annual	PW Review
7	Percentage of public works projects for which arrangements for community engagement and/or operation and maintenance are established – disaggregated by highland/lowland		Highland: 75%	80%	85%	90%	95%	95%	Annual	PW Review/MIS
			Lowland: 64%	70%	75%	80%	85%	90%
8	Percentage of PW plans prepared / following GSD considerations – disaggregated by highland/lowland		Highland: 74%	76%	80%	85%	90%	93%	Annual	PW / review/MIS
			Lowland: 64%	65%	68%	73%	77%	80%	Annual	PW Review/MIS
9	Percentage of female clients who report PW are implemented following GSD considerations – disaggregated by highland/lowland		Highlands: 81%		88%		93%		Every 2 years	Household impact surveys
			lowlands: 59%		65%		72%		Every 2 years	Household impact surveys
10	Percentage of PLWs (pregnant or with children <2) in safety net client households participating in Community Based Nutrition activities (disaggregated by specific services provided to respectively pregnant women and lactating women)	None	PSNP Pregnant women: Nutrition counselling sessions - no baseline		x		x		Every 2 yearly (HH survey) and annually (PW MIS)	Household impact survey/MIS
		None	Lactating women with children under 2 attending Growth Monitoring and promotion (disaggregated by <1 year and 13-23 months) - no baseline		x		x		Every 2 yearly (HH survey) and annually (PW MIS)	Household impact survey/MIS
11	Percentage of clients who receive community-based nutrition counselling services		40	50	60	70	80	80	Annual	MIS/progress reports
12	Percentage of adult household members whose members attend at least three BCC sessions annually (disaggregated by sex of participant and by public works/direct support)	N.A.	Public work Clients (No baseline)		x		x		Every 2 yearly (HH survey) and annually (PW MIS)	Household impact survey/MIS
		N.A.	Direct Support clients (no baseline)		x		x		Every 2 yearly (HH survey) and annually (PW MIS)	Household impact survey/MIS
13	Percentage of pregnant women transitioning to temporary direct support before 4 months on the basis of health facility referral [amongst women who reach the 4th month of pregnancy during the public works period]	None	No baseline		x		x		Every 2 yearly (HH survey) and annually (PW MIS)	Household impact survey/MIS

### Output 4: Clients’ livelihood opportunities facilitated through three pathways: crop and livestock, off-farm income generation, and employment
Indicator		Previous Indicator/ Target	Baseline	Target					Means of verification
				2016	2017	2018	2019	2020	Frequency	Source
1	Percentage of safety net households who report saving regularly (in development groups/VSLAs, RUSACCOs, MFIs, banks, etc.) - disaggregated by sex of household member who saved	No equivalent indicator		25	30	35	40	50	Every 2 years	Household impact survey
2	Percentage of safety net households who received the complete livelihood training package (disaggregated by sex of household head)		0%	30%	55%	75%	85%	90%	Checklist, Reported on annually, but data collected monthly
3	Percentage of safety net households reporting that the programme has enabled them to access on-farm and/or off-farm livelihood opportunities and/or labour/wage employment opportunities (disaggregated by sex )		On-farm: 45%		65%		80%		Every 2 years	Household impact survey
			Off-farm: 20%		30%		40%		Every 2 years	Household impact survey
			Labour/wage employment : 0%		5%		15%		Every 2 years	Household impact survey
4	Percentage of safety net households receiving credit for their business plan after completion of checklist - disaggregated by sex )	90% of HABP clients have access to financial services attributable to HABP by December 2012	45%	50%	55%	60%	65%	70%	Reported on annually, but data collected monthly	Financial institutions
5	Percentage of ultra-poor safety net households receiving livelihoods transfers [after completion of checklist] - disaggregated by sex	No equivalent indicator	0%	30%	60%	75%	85%	90%	Reported on annually, but data collected monthly	Programme reports
6	Percentage of clients with business plans developed - disaggregated by sex		0	40	55	75	85	90	annual	MIS and progress reports
7	Percentage of ultra-poor safety net households who received livelihoods transfers reporting at least every month visits/meetings by DAs - disaggregated by sex	No equivalent indicator	0	30%	60%	75%	85%	90%	Annually (if surveys) or every two years (if IFPRI impact assessment)	Household impact survey
8	Percentage of clients with business plans reporting that the plans reflect their priorities, needs and capabilities - disaggregated by sex		18	60	65	70	75	80	every 2 years	Impact evaluation
9	Percentage of clients receiving employment related skills training - disaggregated by sex)		0	10	15	20	25	30	Annual	Progress reports

### Output 5: Effective management and operational processes in place to manage the programme

Indicator		Baseline	Target					Means of verification
			2016	2017	2018	2019	2020	Frequency	Source
1	Percentage of safety net woredas/regions meeting minimum safety net staffing standards –disaggregated by highland/lowland and new woredas	Highland (80%)	82%	84%	86%	88%	90%	Annual	Progress reports/MIS
		Lowland	x	x	x	x	x	Annual	Progress reports/MIS
		New Woredas	x	x	x	x	x	Annual	Progress reports/MIS
2	Percentage of woredas that adopt and meet key performance standards for planning, implementing and reporting (including finance, procurement, commodity and fixed asset status)- disaggregated by highland/lowland and new woredas	Highland	82%	84%	86%	88%	90%	Annual	Progress reports/MIS
		Lowland	x	x	x	x	x	Annual	Progress reports/MIS
		New Woredas	x	x	x	x	x	Annual	Progress reports/MIS
3	Percentage of agreed Joint Steering and Oversight Committee (JSOC) meetings held as planned		75%	75%	75%	75%	100%	Annual	Progress reports/MIS
4	Incidence of recurrent audit findings (financial, commodity and procurement) on resources at woreda, regional and federal levels	Financial management -- Year 1 audit as baseline	x	x	x	x	x	Annual	Audit reports
		Procurement -- Year 1 audit as baseline	x	x	x	x	x
		Commodity audit -- Year 1 audit as baseline	x	x	x	x	x
5	Percentage of woredas submitting Woreda Monthly Stock & Distribution (Utilisation) Reports to the zone (where active) or regional government (where zones are not active) on a quarterly basis		60%	70%	80%	90%	100%	Annual	Progress reports/MIS
6	Percentage of permanent direct support caseload under MOLSA management			30% in selected highland woredas	50%	70%	100%	Annual	Progress reports/MIS
7	Level of implementation of the gender action plan	NA	x	x	x	x	x	x	Targets for every year: A min of 80% of gender action plan activities, included in the PSNP annual plan, implemented

Annex 15: Bibliography

Ambel, Alemayehu and Beratu Yigeza (2013) A profile of well-being in Ethiopia: evidence from the Ethiopia Rural Socioeconomic Survey. World Bank Poverty Reduction and Economic Management; Washington DC; June 2013.
Anderson, Stephen (2015) PSNP Governance Retreat Outcomes, 26 February 2015 – draft report. Food Economy Group consultancy for the PSNP DWG; March 2015.
Arnold, Catherine, Tim Conway and Matthew Greenslade (2011) Cash transfers: literature review. DFID Policy Division, London, April 2011.
Attanasio, O., L. Pellerano and S.P. Reyes (2009) ‘Building trust? Conditional cash transfer programmes and social capital’. Fiscal Studies Volume 30, No. 2, pp. 139-177, http://onlinelibrary.wiley.com/doi/10.1111/j.1475-5890.2009.00092.x/abstract
Ayalew, Gizachew and Yihenew G. Selassie (2015) “Soil loss estimation for soil conservation planning using Geographic Information System in Guang Watershed, Blue Nile Basin.” Journal of Environment and Earth Science Vol. 5 No. 1 pp. 126-134.
Baird, Sarah et al. (2010) Cash or condition? Evidence from a randomized cash transfer program. World Bank Policy Research Paper No. 5259; March 2010.
Barber, S. and Gertler, J. (2008) The impact of Mexico's conditional cash transfer programme, Oportunidades, on birthweight. University of California, Berkeley, CA, USA.

Barkar, Valentina and Richard Chirchir, (2014) Single registries and integrated MISs: de-mystifying data and information management concepts. Department of Foreign Affairs and Trade, Commonwealth of Australia, May 2014.
Bastagli, Francesca, Jessica Hagen-Zanker, Luke Harman Valentina Barca and Luca Pellerano (2015 forthcoming) Cash transfers rigorous literature review (working title). ODI and OPM for DFID Policy Division.
Berhane, Guush et al (2011a) Evaluation of Ethiopia’s Food Security Programme: documenting progress in the implementation of the Productive Safety Nets Programme and the Household Asset Building Programme, IFPRI, IDS and Dadimos, October 19 2011
Berhane, Guush et al (2011b) The impact of Ethiopia’s Productive Safety Nets and Household Asset Building Programme: 2006-2010; December 30, 2011
Berhane, Guush, Stephen Devereux, John Hoddinott, Fredu Nega Tegebu , Keetie Roelen and Benjamin Schwab (2012) Evaluation of the Social Cash Transfers pilot programme, Tigray Region, Ethiopia: baseline report. IFPRI, IDS and Mekelle University, 5th December 2012.
Berhane, Guush, John Hoddinott and Neha Kumar (2014) The Productive Safety Net Programme and the nutritional status of pre-school children in Ethiopia. IFPRI, 9th April 2014.
Berhane, Guush et al (2013) The implementation of the Productive Safety Net Programme and the Household Asset Building Programme in the Ethiopian highlands, 2012: Program Performance Report. IFPRI, IDS and Dadimos, July 15th 2013.
Berhane, Guush, John Hoddinott, Jessica Hoel, Natasha Ledlie, Freda Nega Tegebu, Benjamin Schwab and Thomas Woldu (2013) Evaluation of the Social Cash Transfer Pilot Programme, Tigray Region, Ethiopia: Midline report. IFPRI and Mekelle University, December 15th 2013.
Bevan, Philippa, Catherine Dom and Alula Pankhurst (2013a) Long-term perspectives on development impacts: WIDE3 Stage 3. Presentation for Consultation Workshop for RED/FS, PBS and PSNP Group; Addis Ababa, 7th March 2013.

Bevan, Philippa, Catherine Dom and Alula Pankhurst (2013b) Stage 2: eight food insecure communities – short summary. Long-term perspectives on development impacts: WIDE3 Stage 2. Mokoro; March 2013.
Bossuyt, Anne (2015a) How nutrition sensitive is the PSNP 4 design? PowerPoint presentation for the DCT; January 2015.
Bossuyt, Anne (2015b) PSNP 4 PIM – nutrition sensitive interventions under output 3: the implementation arrangements. PowerPoint presentation for the Public Works Coordination Unit at NRMD / MoA; February 26th 2015.
Brown, Kevin Mohammed Umar and Charles Kinyeki (2015) Workforce study to better understand the efficiency and effectiveness of DFID’s support to the Promotion of Basic Services (PBS) Programme – Final report. Coffey International Development Ltd., for DFID via Governance, Social Development, Conflict and Humanitarian Professional Evidence and Applied Knowledge Service (PEAKS); Reading, January 2015.
Browne, Evie (2013) Theories of change for cash transfers. GSDRC Helpdesk Research Report; April 2013.
App Burns, John (2011) PSNP Plus: linking poor rural households to microfinance and markets. PSNP Plus longitudinal impact study – summary of findings. Feinstein International Center, Tufts University for USAID and CARE; November 2011.
Cabot-Venton, Courtenay, Bailey and Sophie Pongracz (2014) Value for money of cash transfers in emergencies. DFID.

Caeyers, Bet and Stefan Dercon (2012) “Political connections and social networks in targeted transfer programmes: evidence from rural Ethiopia.” pp. 639-675 in Economic Development and Cultural Change Vol. 60 No. 4 (July 2012); available online in an earlier form as Oxford University CSAE Working Paper 2008-33.
Campbell, Ian (2015) A cost-benefit assessment of the public works program of the Ethiopian Productive Safety Net Program (PSNP) Phase 3 (2010-2015); and estimated projected costs and benefits of public works under PSNP 4. Consultancy for DFID Ethiopia; April 2015.
Cant, Jeremy and Fantahun Belew (2015) Federal Government of Ethiopia Fiduciary Risk Assessment – draft report. March 2015.
Carranza, Eliana and José V. Gallegos (2013) Ethiopia: trends of well-being 2000-2011. World Bank Africa Poverty Reduction and Economic Management; Washington DC; June 2013.
Carter, Michael R., Peter D. Little, Tewodaj Mogues and Workneh Negatu (2008) “Poverty traps and natural disasters in Ethiopia and Honduras.” pp. 85-120 in Armando Barrientos and David Hulme (eds.) (2008) Social protection for the poor and poorest: concepts, policies and politics. Palgrave.

Coady, David, Margaret Grosh and John Hoddinot (2004) Targeting of transfers in developing countries: review of lessons and experience. World Bank and IFPRI; Washington DC.

Combaz, Emily (2013) Social inclusion in productive safety net programmes. GSDRC Helpdesk Research Report; 11th October 2013.

Coll-Black, Sarah, Daniel Gilligan, John Hoddinott, Neha Kumar, Alemayehu Seyoum Taffesse and William Wiseman (2011) Targeting food security interventions when “everyone is poor”: the case of Ethiopia’s Productive Safety Net Programme. ESSP Working Paper No. 24; International Food Policy Research Institute (IFPRI) and Ethiopian Development Research Institute (EDRI); Washington DC; May 2011.
Coll-Black, Sarah, Daniel Gilligan, John Hoddinott, Neha Kumar, Alemayehu Seyoum Taffesse and William Wiseman (2012) “Targeting food security interventions in Ethiopia: the Productive Safety Net Programme.” in Dorosh and Rashid (eds.) 2012.
Conway, Tim and Andy Norton (2002) “Nets, ropes, ladders and trampolines: the place of social protection in current debates on poverty reduction.” pp. 533-540 in Development Policy Review Volume 20 No. 5.
CSA and ICF International (2012) Ethiopia Demographic and Health Survey 2011 Addis Ababa and Calverton, Maryland.

CSA (2014) Ethiopia Mini-Demographic and Health Survey 2014. CSA and MoH; Addis Ababa; July 2014.

Dadimos (2014a) Institutional Capacity Assessment of Afar Regional State Bureau of People Organization, Labour and Social Affairs for Manage Direct Support Beneficiaries of PSNP (Draft Report). Dadimos Development Constultants for MOLSA; November 2014.

Dadimos (2014b) Institutional Capacity Assessment of Amhara Regional State Bureau of Labour and Social Affairs for Manage Direct Support Beneficiaries of PSNP (Draft Report). Dadimos Development Constultants for MOLSA; November 2014.

Dadimos (2014c) Institutional Capacity Assessment of Southern Nation, Nationalities and People’s Regional State (SNNPRS) of Ethiopia, Agency of Labor and Social Affairs (AoLSA) for the Management of Direct Support Beneficiaries of the PSNP Components (first draft). Dadimos Development Constultants for MOLSA; November 2014.

DAG (2010) Aid management and utilisation in Ethiopia: a study in response to allegations of distortion in donor-supported development programmes. Development Assistance Group, Addis Ababa, October 2010.

DAG (2013) Summary of the multi-agency missions to the Commune Development Programme, Ethiopia – Final. Development Assistance Group, Addis Ababa, May 2013.

DAG (2015) Resettlement assessment missions: recommended way forward. DAG Governance Technical Working Group; mimeo; May 2015.
Davis, Benjamin and Justin Kagin (2013) The impact of the Tigray SCTP on economic activities. Meeting of Steering Committee of Tigray Social Cash Transfer Pilot, Tigray Bureau of Labour and Social Affairs, Mekelle; November 12-13th, 2013; from http://www.fao.org/economic/PtoP/en/.
DCT (2012) Main Messages for Development Partners – MTR November 2012. Key messages reference sheet for DP staff attending the Federal MTR; Addis Ababa, November 2012.

DCT (2014) JRIS: Final Wrap-Up Presentation. Addis Ababa, 28 November 2014.
DCT (2015a) PSNP/HABP Donor Coordination Team Annual Plan – 2015. 3rd February 2015. QUEST 4866411.
DCT (2015b) DCT 2015 Annual Plan. PowerPoint presentation to the DWG; 3rd February 2015.
DCT (2015c) PSNP/HABP Donor Coordination Team Annual Report – 2014. 17th February 2015. QUEST 4863535.
DCT (2015) Financial projection for EFY 2008 – PSNP 4. PowerPoint presentation to the DWG; 2nd April 2015.
De Brauw, A. and Hoddinott, John (2008) Must conditional cash transfer programs be conditioned to be effective? The impact of conditioning transfers on school enrolment in Mexico. IFPRI, Washington DC
Dercon, Stefan and Catherine Porter (2010) “Live Aid revisited: long-term impacts of the 1984 famine on Ethiopian children.” CSAE Working Paper Series 2010-39. October 15th 2010.
Dercon, Stefan and Catherine Porter (2011) “A poor life? Chronic poverty and downward mobility in rural Ethiopia, 1996-7 to 2006-7.” in Bob Baulch (ed.) 2011 Why poverty persists: poverty dynamics in Asia and Africa. CPRC and DFID; Edgar Elgar, Cheltenham, UK and Northampton MA, USA.
Devereux, Stephen (2006) Vulnerable livelihoods in Somali region, Ethiopia. IDS Research Report 57; Brighton, April 2006.
DFID (2011) How To Note: Guidance on using the revised logical framework. January 2011.
DFID (2011) Logframes as monitoring tools. InSight page accessed 30th July 2013.
DFID (2012) Theory of change guidance note. Evaluation Department; December 2012.
DFID (2013a) How to Note: Assessing the strength of the evidence. January 2013.
DFID (2013b) Logframes – an introduction. PowerPoint presentation.
DFID (2013c) ICF KPI 1: Number of people supported by DFID programmes to cope with the effects of climate change. Indicator methodology note; last modified March 2013.
DFID (2013d) Social dimensions of transport – a resource for social impact appraisals. August 2013.
DFID (2014a) Smart Rules: better programme delivery.

DFID (2014b) Procurement / commercial guidance. Gerry O’Conner / PCD; December 2014.

DFID Ethiopia (2009) Project Memorandum Ethiopia: Productive Safety Nets Programme 2 (2010 – 2014), January 2009.
DFID Ethiopia (2011) Operational Plan (2011 – 2015), DFID Ethiopia, Addis Ababa.
DFID Ethiopia (2012) Ethiopia: Fiduciary Risk Assessment. DFID Ethiopia, Addis Ababa, April 2013.
DFID Ethiopia (2013) DFID Partnership Principle assessment (draft), DFID Ethiopia, Addis Ababa, June 2013.
DFID Ethiopia (2013b) Revisions to the DFID logframe for support to the Ethiopian Productive Safety Net and Household Asset-Building Programmes (PSNP and HABP): Explanatory notes. Tim Conway and Ayuba Sani; September 2013.
DFID Ethiopia (2014) Ethiopia – Country Poverty Reduction Diagnostic (third draft). PowerPoint slidepack; 18th March 2014.
DFID Ethiopia (2015) Programme Level Assessment of the Partnership Principles to inform financial aid disbursements to the social protection / food security sector. May 2015.
Dissanayake, Ranil, Zoe Stephenson and Matthew Greenslade (2012) Evaluating social transfer programmes: guidance for DFID country offices. DFID; June 2012.
Dorosh, Paul and Shahidur Rashid (eds.) Food and agriculture in Ethiopia: progress and policy challenges. Philadelphia: University of Pennsylvania Press.
Evers, Barbara, Almaz Wondimu, Jean Garsonnin and Alemtsehay Aberra (2008) PSNP gender study: final draft. Contextual Gender Analytical Study of the Ethiopia Productive Safety Nets Programme; Helm Corporation for Government of Ethiopia. 12th May 2008.
FAO (1986) Highlands Reclamation Study: Ethiopia. Final Report. Two volumes. Rome.
Filmer, D. and Schady, N., (2008) “Getting girls into school: evidence from a scholarship program in Cambodia” pp. 581-617 in Economic Development and Cultural Change, Vol. 56 April 2008.
Ariel Fiszbein (Author)
› Visit Amazon's Ariel Fiszbein Page
Find all the books, read about the author, and more.
See search results for this author name
Are you an Author? Learn about Author Central
Fiszbein, Ariel, Norman Schady, Francisco H G Ferreira, Niall Keleher, Pedro Olinto and Emmanuel Skoufias (2009) Conditional cash transfers: reducing present and future poverty. World Bank Research Report, Washington DC.
Food Management Working Group (2012a) Mid-Term Review Progress Report. Addis Ababa, 4th October 2012.
Food Management Working Group (2012b) Mid-Term Review Issues Papoer. Addis Ababa, 25th October 2012.
Garcia, Marita and Charity M.T. Moore (2012) The cash dividend: the rise of cash transfer programs in sub-Saharan Africa. World Bank Human Development Sector; Washington DC.
GoE (2011) CRGE Vision: Ethiopia’s vision for a climate-reilient green economy.

Gilligan, Daniel O., John Hoddinott, Neha Kumar, Alemayehu Seyoum Taffesse (2009) Can social protection work in Africa? Evidence on the impact of Ethiopia’s Productive Safety Net Programme on food security, assets and incentives. Mimeo; Washington, D.C: International Food Policy Research Institute.
Gray, Bill and Eleni Asmare (2012) Report of a learning review of the implementation of the Risk Financing Mechanism of the Productive Safety Net Programme 2011.
Grosh, Margaret, Carlo del Ninno, Emil Tesliuc and Azedine Ouerghi (2008) For protection and promotion: the design and implementation of effective safety nets. World Bank, Washington DC.
Group 4A (2012a) Institutional capacity to manage – Review report of the institutional capacity status and issues. Addis Ababa, October 2012.
Group 4a (2012b) MTR Issue Paper: the effects of human resource management on capacity and performance of PSNP / HABP. Addis Ababa, October 2012.
HABP Working Group (2012a) Household Asset Building Programme (HABP) Mid-Term Review (MTR) Progress report. Addis Ababa.
HABP Working Group (2012b) HABP MTR Issues Paper. Addis Ababa.
Hallegate, S. (2012) A cost-effective solution to reduce disaster losses in developing countries: hydro-meteorological services, early warning and evacuation. World Bank Policy Research Paper #6058, Washington DC.
Hoddinott, John (2013) The implementation of the Productive Safety Net Programme in Afar and Somali Regions, 2012: Lowlands Programme Outcomes Report (DRAFT). IFPRI, July 24th 2013.
Hoddinott, John (2015) PSNP 2014: early read on performance and outcomes, highlands. IFPRI presentation to the PSNP Donor Working Group; 14th April 2015.
Hoddinott, John, Guush Berhane, Daniel O. Gilligan, Neha Kumar and Alemayehu Seyoum Taffesse (2012) “The impact of Ethiopia’s Productive Safety Net Programme and related transfers on agricultural productivity.” pp. 761-786 in Journal of African Economics Vol. 21 No. 5, September 2012.
Hodges, Anthony, Matthew Greenslade and Philip White (2011) Guidance for DFID country offices on measuring and maximising value for money in cash transfer programmes: Toolkit and explanatory text. DFID Policy Division; October 2011.
Holmes, Rebecca and Nicola Jones (2010) Social protection programming: the need for a gender lens. ODI Briefing Paper 63, October 2010.

Human Rights Watch (2010) Development without freedom: how aid underwrites repression in Ethiopia. New York, October 2010.
ICAI (2012) DFID’s humanitarian emergency response in the Horn of Africa. Report 14; London, September 2012.
IFPRI, IDS and Mekelle University (2012) Minutes of steering committee meeting of Government of Tigray Social Cash Transfer Pilot Programme (Draft version 20 nov.) mimeo courtesy of UNICEF Ethiopia.
Jones, Nicola, Yisak Tafere and Tassew Woldehann (2010) Gendered risks, poverty and vulnerability in Ethiopia: to what extent is the Productive Safety Net Programme (PSNP) making a difference? ODI for DFID; October 2011.
Kagin, Justin, Edward Taylor and Karen Thome (n.d.) Local Economy Impacts of social cash transfers: a comapartive look. PtoP; University of California Davis.
Kagin, Justin, Edward Taylor, Frederica Alfani and Benjamin Davis (2014) Local Economy-Wide Impact Evaluation (LEWIE) of Ethiopia’s social cash transfer pilot programme. PtoP; University of California Davis and FAO.
Kumar, Neha and John Hoddinott (2013) The implementation of the Productive Safety Nets Programme: highlands programme outcomes report – Draft. IFPRI, August 18, 2013.
Lagarde, M., Haines, A. and Palmer, N. (2007) ‘Conditional cash transfers for improving uptake of health interventions in low- and middle-income countries: a systematic review’ JAMA, 2007; 298(16):1900-10
Lind, Jeremy et al (2013) The implementation of the Productive Safety Net Programme in the Ethiopian lowlands, 2012: Program Performance Report (DRAFT). IDS, IFPRI and Dadimos, July 24th 2013.
Loveless, Jeremy and D Palacios (2013) Assessing the links between PSNP/HABP and the Disaster Risk Management System. Draft 1.
LTS International Ltd., AEA, Common Futures, and B&M Development Consultants (2013) “Headlines” and draft report: A mapped assessment of the likely impacts of climate change for Ethiopia (Output 8). Productive Safety Net Programme (PSNP) and the Household Asset Building Programme (HABP): Climate Smart Initiative Building Food Security through Climate Resilience.
MA Consulting Group (2009a) Impact Assessment of the PSNP public works programme. Volume I: Executive Summary. MA Consulting Group in association with Prospect Development Consult for the World Bank and Government of Ethiopia; May 2009.
MA Consulting Group (2009b) Impact Assessment of the PSNP public works programme. Volume II: Main report. MA Consulting Group in association with Prospect Development Consult for the World Bank and Government of Ethiopia; May 2009.
Macours, K., Schady, N. and Vakis, R. (2008) Cash transfers, behavioral changes, and the cognitive development of young children: evidence from a randomized experiment. World Bank, Washington, DC.
Maluccio, J. and Flores, R., (2004) Impact evaluation of a conditional cash transfer program: the Nicaraguan Red de Protección Social FCND Discussion Paper 184, Washington DC, International Food Policy Research Institute.
Markakis, John (2011) Ethiopia: the last two frontiers. James Currey.
Martin, Joe and Mohammed Mussa (2015) Fiduciary risk assessment of the PSNP programme, Ethiopia – revised final draft. Consultancy for DFID; July 2015.
McCord, Anna (2012) Public works and social protection in sub-Saharan Africa: do public works work for the poor? United Nations University Press and UCT Press; Toky, New York, Paris and Claremont, South Africa.

Metaferia Consulting Engineeers (2011) 2011 Public works impact Assessment Phase I – Final Report. Addis Ababa, 30th October 2011.

MoARD (2009) Food Security Programme 2010-2014: Productive Safety Net,. Addis Ababa: Ministry of Agriculture and Rural Development: August 2009.
MoA (2011a) First 2011 Public Works Review in Ethiopia: Final Report. MMA Development Consultants for Natural Resources Management Directorate; March 2011; Addis Ababa
MoA (2011b) Public Works Review, Second Federal Report. MMA Development Consultants for Natural Resources Management Directorate; November 2011; Addis Ababa.
MoA (2012a) Second 2011 Public Works Review in Ethiopia: implementation and sustainability performance. Federal Synthesis Report. MMA Development Consultants for Natural Resources Management Directorate; May 2012; Addis Ababa.
MoA (2012b) Strategic assessment of the impact of the implementation of the Productive Safety Net Programme (PSNP) on vulnerable programme beneficiaries. Addis Ababa; 21st August 2012.
MoA (2012c) The PSNP / HABP MTR Progress Report. Addis Ababa, November 2012.
MoA (2013a) Planning performance of public works: First 2012 Review in PSNP-supported regions. MA Development Consultancy for Natural Resources Management Directorate; March 2013; Addis Ababa.
MoA (2013b) Draft impact assessment report – consulting services for conducting Productive Safety Net Program 2nd 2011 Public Works Impact Assessment. Metaferia Consulting Engineers for MoA, Addis Ababa, March 2013.
MoA (2013c) Productive Safety Net and Household Asset Building Programs 2012/13 (2005 EFY) Annual Implementation Performance Report (July 8, 2012 – July 07, 2013). Addis Ababa, August 2013.

MoA (2013d) Terms of reference – Roving Appeals Audit of the Productive Safety Net Programme 2013 Kebele Appeal Committee audit. Mimeo, October 2013.

MoA (2014a) 2013 Review of the Productive Safety Net and Household Asset Building Programmes. Ministry of Agriculture; 19th February 2014.

MoA (2014b) Productive Safety Net Program Phase 4 (PSNP 4): Enhanced Social Assessment and Consultation – final report. DRMFSS, FSCD; Addis Ababa, 9th June 2014.
MoA (2014c) Productive Safety Net Project Phase IV – Environmental and Social Management Framework (ESMF). Natural Resource Directorate (Public Works Coordination Unit) and Agricultural Extension Directorate (Livelihoods Strengthening Coordination Unit); 6th June 2014.
MoA (2014d) PSNP and HABP Annual Report 2013/2014 (EFY 2006).
MoA (2014e) Productive Safety Net Programme 4 Design Document. Disaster Risk Management and Food Security Sector, Food Security Coordination Directorate, Ministry of Agriculture; Addis Ababa; November 18, 2014.
MoA (2014f) Productive Safety Net Programme Phase IV: Programme Implementation Manual – version 1.0. Ministry of Agriculture; Addis Ababa; December 2014.
MoFED (2010) Growth and Transformation Plan, 2010/11-2014/15: Volume 1 (Main Report). November 2010; Addis Ababa; CPIA ratings for ‘equity of public resource use’ and ‘policies for social inclusion / equity’.
MoFED (2010) Growth and Transformation Plan, 2010/11-2014/15: Volume 1 (Main Report). November 2010; Addis Ababa
MoFED (2012) Ethiopia’s progress towards eradicating poverty: an interim report on poverty analysis study (2010/11). Development Planning and Research Department; Ministry of Finance and Economic Development; March 2012.
MoH and USAID (2013) A tool to support nutrition advocacy in Ethiopia: Ethiopia PROFILES 2012 estimates – Final Report. Washington DC; October 2013.
MoLSA (2014) National Social Protection Strategy of Ethiopia. Addis Ababa.
MTR Output Working Group 4B (2012a) Progress report - Coordination, Complementarity and Synergy.
MTR Output Working Group 4B (2012b) MTR Issues Paper for Group 4B - Coordination, Complementarity and Synergy. Addis Ababa, October 2012.
NAO (2011) DFID: transferring cash and assets to the poor. National Audit Office, November 2011
Oakland Institute (2014) Engineering ethnic conflict: the toll of Ethiopia’s plantation development on the Suri people. November 2014.
Output Group 5 (2014) Group work findings - Output Group 5: HABP. PowerPoint presentation; JRIS Federal Workshop 24th–28th November 2014.
no author (2012) Minutes of steering committee meeting of Government of Tigray Social Cash Transfer Pilot Programme (Draft version 20 nov.) mimeo courtesy of UNICEF Ethiopia.
Procurement Working Group (2012a) Productive safety net program (APL-III) Mid-Term Review Progress Report. Addis Ababa, October 2012.
Procurement Working Group (2012b) MTR Issues Paper. Addis Ababa, November 2012.

PSNP (2014) November 2014 PSNP Joint Review and Implementation Supervision (JRIS) - draft Aide Memoire.

PSNP (2015) ToR of the Nutrition Task Force (NTF).

PW MTR Working Group (2012) PSNP Public Works (PSNP Output 3: Quality, new & existing community assets with operational management mechanisms established). Final Draft Report for input to the MTR. Addis Ababa, September 2012.

Sabates-Wheeler, Rachel, Jeremy Lind, Mulugeta Handino, John Hoddinott, Mulugeta Tefera, Girma Bekele and Feyera Simma (2011) The implementation of the Productive Safety Nets Programme in Afar, Somali, and selected lowland woredas in Oromiya. IDS, Dadimos and IFPRI, October 2011.

Sabates-Wheeler, Rachel, Jeremy Lind and John Hoddinott (2011) Implementing social protection in pastoralist areas: how local distribution structures moderate PSNP outcomes in Ethiopia. IDS and IFPRI, December 20th 2011.

Sandford, Judith (2012) Addressing vulnerabilities post-2014: What are the options? A joint Government-Development Partner position paper. World Bank
Schady, N., and Araujo, M. C. (2006) Cash, conditions, school enrolment, and child work: Evidence from a randomized experiment in Ecuador. World Bank, Washington DC.
Schady, N., and Araujo, M. C. (2008) ‘Cash transfers, conditions, and school enrollment in Ecuador’ Economía 8 (2): 43–70.
SCT (2013) Tigray Social Cash Transfer Pilot Programme (SCTPP) Brief.
Sengupta, Anasuya (2012) Pathways out of the Productive Safety Net Programme: lessons from the graduation pilot in Ethiopia. CGAP Working Paper; June 2012.
Sharp, K., Taylor Brown and Amdissa Teshome (2006) Targeting Ethiopia’s Productive Safety Net Programme (PSNP). ODI, IDL Group and A-Z Capacity Building Consult; August 2006.

Sida, Lewis, Bill Gray and Eleni Asmare (2012) IASC Real-time evaluation of the humanitarian response to the Horn of Africa drought crisis: Ethiopia. IASC: Geneva.
Skoufias, Emmanuel (2005) Progresa and its impacts on the welfare of rural households in Mexico. IFPRI Research Report 139, Washington DC.
Soares, F. V., R.P. Ribas and G.I. Hirata (2010) “The impact evaluation of a rural CCT programme on outcomes beyond health and education.” pp. 138–157 in Journal of Development Effectiveness. Vol. 2, No. 1, March 2010.
Stark, Jeffrey, Katsuaki Terasawa, and Mersie Ejigu (2011) Climate change and conflict in pastoralist regions of Ethiopia: mounting challenges, emerging responses. Foundation for Environmental Security and Sustainabilityfor USAID; October 2011.
Subbarao, Kalanidhi, Carlo del Ninno, Colin Andrews and Claudia Rodríguez-Alas (2013) Public works as a safety net: design, evidence and implementation. World Bank Human Development Sector.
Sutcliffe, J.P. (2011) 2011 Public works impact assessment Phase I – Separate Appendix 3 (Economic impacts) 26th October 2011.
Teferra, Sehin and Liyousew Gebremedhin (2010) Gender and social exclusion in Ethiopia. Review for DFID Ethiopia, Addis Ababa, July 2010.

Tegenu, Girma and Mulugeta Eshetu (2013) Assessment of the targeting, utilization and reporting procedures of the PSNP Contingency Budget.
Transfer Working Group (2012) PSNP Mid-Term Review Progress Report on transfers. Addis Ababa, September 2012.
Tribal Helm (2009) Productive Safety Net Programme – Fiduciary Risk Analysis. Final; 12th November 2009.
UNDESA (2012) Ethiopia – UN population profile and projection.
unnamed (2014) Resource management – Working Paper. [Consultancy for] the formulation of the next generation of the PSNP and HABP. November 2014.
Venton, Courtney Cabot, Catherine Fitzgibbon, Tenna Shitarek, Lorraine Coulter and Olivia Dooley (2012) The economics of early response and disaster resilience: lessons from Kenya and Ethiopia. DFID; June 2012.

WABEKON Development Consultants PLC (2013) 2012 Roving Appeals Audit of PSNP. Addis Ababa, April 2013.
WABEKON Development Consultants PLC (2015) 2014 Roving Appeals Audit of PSNP.
White, Philip and Frank Ellis (2012) Ethiopia’s Productive Safety Net Programme, 2010-14: a value-for-money assessment. DFID for PSNP-HABP Donor Working Group.
White, Philip, Anthony Hodges and Matthew Greenslade (2013) Guidance on measuring and maximising value for money in social transfer programmes – second edition. DFID, April 2013. InSight EPE
White, Philip and Anthony Hodges (2014) Measuring and maximising the value for money of social protection systems development – technical proposal. Proposal to DFID Policy Division; 15th December 2014.
WIDE (2012) Rapid Briefing Note on Fieldwork 2 for the WIDE 3 Worknet. WIDE Long-term perspectives on development impacts in rural Ethiopia: stage 2.
Winters, Paul (2013) When and under what conditions should we expect to find evidence of cash transfer programs on household livelihoods? PowerPoint presentation to workshop on the Protection to Production Project, 24-25th September, FAO, Rome.
Wiseman, W., Van Domelen, Julie and Sarah Coll-Black (2012) Designing and implementing a rural safety net in a low income setting: lessons learned from Ethiopia’s Productive Safety Net Program 2005-2009. World Bank, Washington DC, January 2012.
World Bank (2005) Ethiopia – Wellbeing and poverty in Ethiopia: the role of agriculture and agency. PREM AFTP2; Report No. 29468-ET; Washington DC; July 18 2005.
World Bank (2009) Project Appraisal Document on a proposed grant in the amount of SDR 223.5 million (US$ 350.0 million equivalent) and a proposed credit in the amount of SDR 83.1 million (US$ 130.0 million equivalent) to the Federal Democratic Republic of Ethiopia for a Productive Safety Net APL III Project in support of the Third Phase of the Productive Safety Net Program. Social Protection Unit, Country Department AFCE3, Africa Region: September 25, 2009.
World Bank (2012) Options for strengthening land administration – Federal Democratic Republic of Ethiopia. Report No: 61631-ET.
World Bank (2013a) Coping with change: how Ethiopia’s PSNP and HABP are building resilience to climate change. Addis Ababa.

World Bank Ethiopia (2013b) Review of the 2012 Roving Appeals Audit – for DWG information only. 9th May 2013.
World Bank (2014a) Project Appraisal Document on a proposed credit in the amount of SDR 391.9 million (US$ 600 million equivalent) to the Federal Democratic Republic of Ethiopia for a Productive Safety Net Project 4. Social Protection and Labor Global Practice, Eastern Africa 1: September 4, 2014.
World Bank (2014b) Social safety nets and gender: learning from impact evaluations and World Bank projects. IEG, World Bank; Washington DC.
World Bank Group (2015a)  Ethiopia Poverty Assessment 2014. Report No. AUS6744; Poverty Global Practice, Africa Region; Washington, DC; January 2015.
World Bank (2015b) Pilot: strengthening the effectiveness of social accountability in PSNP and PBS overlapping woredas. March 2015.
World Bank (2015c) Briefing note: ensuring fair program delivery in PSNP 3 and PSNP 4. Internal note for Donor Working Group; April 2015.
World Bank (2015, forthcoming) Federal Democratic Republic of Ethiopia – Public Expenditure Review in social protection (2009-2013). Draft; March 2015.
Young Lives (2011) Understanding changes in the lives of poor children. Young Lives Round 3 Survey Executive Summary – Ethiopia, September 2011.

Endnotes