Annual Review – post April 2018

Title: Palestinian Market Development Programme to Strengthen the Private Sector in the Occupied Palestinian Territories
Programme Value: £20.8 million (UK £15m, EU £5.8m)		Review Date: 04/04/2018
Programme Code: 201828	Start Date: 21/10/2013	End Date: 31/11/2019

Summary of Programme Performance
Year	2013	2014	2015	2016	2017
Programme Score	C	A++	A++	A	A+
Risk Rating	Moderate	Major	Major	Major	Major

During the reporting period (January-December 2017), PMDP met its yearly targets overall and scored A+. The below table summarises the 2017 Annual Review scoring.

	Output	Impact weight %	Score
1	Improved private sector skills and innovation	65%	A+
2	Market system failures addressed in specific sectors	15%	A+
3	Strengthened trade and investment linkages with international markets	20%	A
	Overall output score		A+

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5479471.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5368162.xls

A. Summary and Overview

Overview

Israeli imposed restrictions on the movement of labour and goods across the Occupied Palestinian Territories (OPTs) continue to be the primary obstacle to unlocking the Palestinian economy’s full potential. According to the Palestinian Central Bureau of Statistic Gross Domestic Product (GDP) of the Palestinian Economy was $13.4 billion in 2016. Once factoring in the size of the population this is equivalent to GDP per capita of $2,957 ($3,727 in the West Bank and $1,851 in Gaza). Output is increasingly dominated by Services as the Agriculture and Manufacturing sectors suffer most from the constraints imposed by the Israeli occupation. The economies of the West Bank and Gaza are disconnected from one another and are on divergent paths - the West Bank continues to record some growth, albeit below potential and the rate needed to address unemployment, whilst the Gazan economy continues to deteriorate with rising levels of unemployment and deteriorating living standards.

Growth in the OPTs is volatile. This is particularly true for Gaza where growth is highly correlated to outbreaks of violence and flows of donor assistance into the strip. In 2017, the economy showed increasing fragility with growth slowing to 3.1 per cent. This was primarily driven by a significant decrease in Gaza where growth fell from 7.7 per cent in 2016 to 4.5 per cent in 2017. Deteriorating infrastructure and expenditure cuts in Gaza contributed to its decline in economic growth; persistent instability and conflict have eroded the economy’s productive base and stunted growth potential. The West Bank also experienced a decline in 2017 with growth at 2.7 per cent. The IMF forecasts a growth rate of three per cent over the medium-term for the OPTs and deems this too low to remedy economic imbalances and to have a meaningful impact on living standards.

As a result unemployment rates in OPTs continue to remain high at 27.4 per cent; 43.6 per cent in Gaza compared with 18.1 per cent in the West Bank. Youth unemployment is critically high with around two-thirds of young people in Gaza without employment. There continues to be a substantial disparity between the labour force participation rates of males and females in the OPTs with 71.2 per cent for males and only 19 per cent for females. A fundamental challenge is to stimulate growth and generate sufficient jobs for a burgeoning population. Should a political resolution to the conflict be found and restrictions on Palestinians lifted, evidence suggests that the economy would grow at the required levels to reduce unemployment. In the meantime, there is a need to develop a dynamic, productive and competitive private sector to enhance growth and create jobs.

Description of programme

Within the context of the Israeli occupation, the Palestinian Market Development Programme (PMDP) aims to improve market systems and the competitiveness of the Palestinian private sector by working with businesses to increase their productivity and revenue through skills upgrading and innovation, addressing market system failures in specific sectors through sector wide analyses and strengthening trade and investment linkages with international markets.

By October 2019, the UK will have provided up to £15 million for the Palestinian Market Development Programme (PMDP) to achieve these objectives with the aim of creating sustainable employment opportunities. The EU is co-funding the programme with £5.8 million, through a delegated agreement with DFID, bringing the total programme budget to £20.8 million. PMDP has three main components:

1. Provision of matching grants and technical assistance to Palestinian businesses to mitigate risks associated with doing business in a fragile context.
2. Carrying out market analysis to identify and address market failures in key economic sectors.
3. Strengthen inward investment and commercial linkages with Diaspora Palestinians and enhance know-how of Palestinian institutions in the area of trade and investment.

All three components are in line with commitments outlined through our Operational Plan to increase long-term growth and employment by addressing government and market failures.

By 2019, PMDP is expected to:

- Assist 750[1] Palestinian firms (494 through all grants windows and 256 through Gaza Back to Business with 35% of beneficiaries under all grants windows managed or owned by women) through matching grants and technical assistance to develop 470 new/existing products and enter 321 new markets.
  [1] This number was 810 in last year’s report in anticipation of a £1 million scale up for further activity in Gaza. The scale up was not approved, so numbers were adjusted to reflect the programme’s delivery capacity within the original budget.
- Create up to 2,818 direct jobs and 2,800 indirect jobs.
- Leverage a minimum of £155m in additional attributable sales (of which £55m would have come through the Gaza Back to Business component (B2B)[2].
  [2] The Gaza Back to Business (B2B) component was initiated after the 2014 conflict in Gaza with a focus on rehabilitating damaged businesses. It began receiving applications in October 2014 and ended in March 2017.
- Assist 130 companies to increase exports;
- Enable 130 companies to start using their own funds to develop and sustain their businesses.
- Assist 380 companies in improving their annual business performance.
- Assist 256 companies who experienced damage due to the 2014 conflict in Gaza to get back to business (B2B).

Development Alternatives Incorporated Europe (DAI Europe) implements the programme. Galway Development Services International (GDSI) is the evaluation supplier. DFID uses Reuter Thompson’s World Check to carry out online vetting of beneficiaries against international terrorism and sanctions lists. This is done by a DFID staff member running the names of would-be beneficiaries and partners through World Check. The Programme Steering Committee consists of DFID, the EU and the Palestinian Ministry of National Economy (MoNE).

Supporting narrative for the overall score

PMDP continues to be an effective private sector development programme. It performed well against its Output 1 objectives, moderately exceeding its targets. It showed similar performance relative to 2016 against Output 2 milestones, matching and moderately exceeding incumbent indicators with the exception of significantly exceeding one of the new indicators, which assesses improvement in knowledge and skills. PMDP demonstrated progress on Output 3 where it matched and exceeded targets where it had underperformed in the previous year; it showed consistency in 2017 with respect to performance against established indicators. Overall, the programme comfortably met its targets over the year.

In 2017 the programme increased its focus on job creation for women and youth and businesses in marginalised areas under the banner “new direction”. It introduced matching grants with different eligibility criteria for this group of would-be beneficiaries. Early indications are positive with women owned and marginalized companies reporting higher job growth compared to other enterprises. The programme also revamped its approach to receiving and assessing applications, switching to a “batch” system, which had positive results in terms of the amount of applications received.

PMDP’s value for money (VfM) framework is now more robust and comprehensive with the inclusion of effectiveness indicators for both Output 2 and Output 3. There has been some change in the direction of monetised VFM indicators, with some indicators increasing. Nonetheless, this should not be read as an indication that the programme is not delivering VFM but rather as a means of assessing change over time to better understand how costs are changing and why. For example, the amount it costs to improve a product and enter a new market has increased on average but the calculated returns from such support still outweigh the cost. Overall, the assessment is that the programme continues to demonstrate VfM. PMDP also developed indicators associated with indirect jobs, which better reflect the overall economic impact of the programme. In order to be better aligned with the DFID VfM framework, the programme should consider developing indicators that measure the cost of assisting the most detached and disadvantaged (equity).

Recommendations for the year ahead

Output 1

- To consider better streamlining the application process to make it more efficient and productive.
- To make grants more accessible and visible and continue to employ a mapping methodology which disaggregates grants by gender, geographically and by grant type/size.
- To potentially consider diversifying the geography of the market by targeting other cities and regions.

Output 2

- To prioritise and capitalise on the more responsive markets (agriculture and IT services).
- To consider disaggregating results by region to better understand how to penetrate more detached and marginalised markets.

Output 3

- To improve communication links with Commercial Trade Representatives[3] (CTRs) to ensure uniformity and better monitoring.
  [3] Commercial Trade Representatives are hired personnel based in Palestinian diplomatic missions in select countries whose aim is to promote business to business linkages between companies where they are based and Palestinian companies.
- To address the CTR contracts for the sustainability of the programme as they move from a PMDP funded contract to one supported by the Ministry of National Economy through the Palestinian Investment Promotion Agency (PIPA) CTRs Coordination Unit (CCU).
- To consider a more proactive approach to facilitate discussions with diaspora Palestinians in order to increase trade and investment links.
- To consider approaches to increase the visibility of CTRs in the respective countries and to raise awareness among organisations of the CTRs’ function and standing.
- To assess the performance of CTRs in terms of effectiveness and consider alternatives.

Value for money

- PMDP should consider developing indicators that measure equity: how fairly are the benefits distributed and to what extent will we reach marginalised groups.
- To build on indicators and metrics, which better quantify the overall economic impact of the intervention and its sustainability.

## B: DETAILED OUTPUT SCORING

Output Title	Improved private sector competitiveness
Output number per LF		1	Output Score	A+
Impact weighting (%):		65%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Total number of enterprises assisted	701 / Total assisted: 445 / B2B: 256	729 / Total assisted: 465 / B2B: 264
1.2 Number of women owned or managed enterprises assisted	135 / TA: 135 / B2B: No target	143 / TA: 143 / B2B: No target

Provide supporting narrative for the score

This output moderately exceeded its target for the year, assisting a total of 729 companies including 264 firms in Gaza, which continues to recover from the 2014 conflict. It exceeded its milestone despite Indicator 1.1 being revised upwards from 570 to 701 in 2016. Companies receiving support other than through the B2B window contributed to the creation of 326 jobs and added £23 million in additional sales in 2017, bringing the cumulative total to 1,159 jobs and £56 million in additional sales. Enterprises in Gaza receiving support through the B2B Window contributed to an additional £15.9 million worth of sales bringing the cumulative total under B2B to £56.9 million.

1.1: Compared to 2016, the amount of applications received almost doubled, from 228 to 441 in 2017, taking the total number of applicants throughout the programme to 1,113. Of the 441 applications, 24.5 per cent were accepted, which consisted of 131 beneficiaries. Of these 131 beneficiaries, 56.5 per cent were from the manufacturing and service sectors with only 6.1 per cent from the ICT industry.

1.2: PMDP introduced and started implementing its “new direction” in 2017. This included rolling out three new grant mechanisms (Women and Youth Employment-WAYE, Results-based, and Marginalised Areas) and shifting its approach of processing applications from “first-in first-served” to a “batch” approach. This allowed PMDP to process applications in a more efficient manner as well as focus on the applications with the highest potential to yield results.

In 2017, 53.5 per cent of net new beneficiaries have their businesses located in marginalised areas[4]. The additional beneficiaries raised the total number of beneficiaries from marginalised areas to 213, representing 45.8 per cent of all served grantees to date. This is a direct result of the introduction of a ‘marginalised’ window, offering matching grant conditions and extra outreach efforts that better reflect the needs of such businesses. This was in response to earlier difficulties in reaching potential beneficiaries in marginalised areas. Marginalized areas companies delivered 52.6 per cent of the net jobs created in 2017 in 2017. A possible theory for this greater-than-expected performance could be the fact that most employers are city-based which requires employees to migrate from marginalized areas to cities, a costly and often undesirable outcome for job seekers based in marginalized areas. In this instance, companies remained in marginalized areas enabling those who wanted to remain in their area of living to seek employment opportunities through these companies. If proven, this could be an indication of high demand for employment in rural areas.
[4] Marginalised areas are geographic locations where it is harder for Palestinian businesses to set up operations due to numerous factors. Examples of marginalised areas include East Jerusalem, the Seam Zone, Jordan Valley and Area C. Gaza is also considered a marginalised area due to its dire socioeconomic indicators and the difficulty of doing business there.

PMDP moderately exceeded its target of assisting 135 women-owned/managed companies. The programme helped 143 women-owned businesses, which represents 35 per cent of all companies assisted under all grants windows excluding B2B in 2017; an improvement on 2016 figures. The absolute increase of 50 enterprises compared to 2016 can also be attributed to the new Women and Youth Employment component, which was introduced this year.

Success Story2017 –A Breakthrough: Stimulating the production of animal feed alternatives in oPt

PMDP supported Al Yasin Company, a livestock and investment company specializing in small ruminants’ production in Bani Naeim south of Hebron, to enter the commercial production of silage and Total Mixed Ration (TMR). These alternative feeds were first identified through the analysis of the animal feed market, and have the potential to reduce the cost of sheep and goat rearing by up to 36%. PMDP designed and launched a results-based partnership with Al Yasin whereby PMDP contributed £30,500 towards technical expertise, equipment costs, raw material, and marketing activities and Al Yasin invested £97,000 in land development, infrastructure, and equipment, to establish the first TMR production unit in Hebron. Hebron and its environs contain the highest concentration of the sheep and goat population in the West Bank. Much of this population is reared through intensive production, which involves the use of expensive concentrated feed. Silage and TMR will provide herders with an alternative, natural option at a significantly lower price. By July, the company had produced and sold 100 Metric Ton (MT) to about ten herders. The company produced and sold 600 MT, exceeding the annual target of 500 MT, of silage and TMR by the end of December 2017. Through support to Al Yasin Company, PMDP managed to introduce a new methodology for livestock herders to become self-sufficient and rely less on expensive mainstream feeds.

Recommendations

- To consider better streamlining the application process to make it more efficient and productive. With the move to a “batch” approach resulting in a substantive increase in applications received, PMDP could consider reducing the process time of applications.
- To make grants more accessible and visible and continue to employ a mapping methodology which disaggregates grants by gender, geographically and by grant type/size. This system would be very useful for PMDP in the final year of operations. It would allow DFID and the EU to target clients if they have visitors who want to see PMDP.
- To potentially consider diversifying the geography of the market by targeting other cities and regions and partnering with organizations which traditionally work in marginalized areas. With the overall progress in the major West Bank cities, it could prove difficult to further penetrate what could be becoming an over-saturated market.

Output Title	Market system failure in specific sectors addressed
Output number per LF		2	Output Score	A+
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of market system studies completed	15	15
2.2 Number of interventions based on completed market system studies	24	30
2.3 Number of products/services improved/developed to address market failures	19	22
2.4 Number of individuals reporting an increase in knowledge and skills	267	473

Briefly describe the output and provide supporting narrative for the score

2.1: This programme output met its targets for 2017. One new study on labour market for skilled IT professionals in Jerusalem was conducted in 2017 compared to four the previous year. This brought the cumulative total to 15, which is the same as the target for the year. PMDP initiated 11 interventions in 2017, bringing the cumulative total to 30. An intervention is an activity that is meant to resolve a market system failure identified through PMDP’s market system analyses of select sectors (agriculture, IT, and tourism). Six of the interventions in 2017 were carried out in the IT sector. An example of an IT intervention which concluded in 2017 was the ICT/Web-skills Bootcamp whereby PMDP partnered with four IT companies to invest in training and hiring of recent IT graduates as entry level professionals. The intervention led to the permanent hiring of 26 out of 38 trained graduates.

2.2: During 2017, PMDP and the Jerusalem Entrepreneurs Society and Technology Hub (JEST) conducted the Jerusalem Hi-Tech Labour Market Assessment. The assessment identifies the factors required for Jerusalemites to enter the technology industry. The study focused on the labour market for skilled IT professionals in Jerusalem, and to understand why Palestinian IT graduates from Jerusalem are unable to participate in a fast-growing technology sector. In the Israeli market, there is a reported shortage of around 10,000 software development professionals, and specifically in Jerusalem, a shortage of 500-1,000 individuals. This gap is expected to grow at 10 per cent per annum. The market study has investigated the reasons for this, and has suggested six interventions that JEST can implement to boost employment of Palestinians in the Jerusalem technology sector.

2.3 and 2.4: PMDP introduced these two new indicators in 2017 to better assess the effectiveness of interventions put in places to address systemic market failures within the OPTs. It moderately exceeded its target pertaining to the amount of improved products, achieving 22 and substantially exceeded it for the other indicator; 473 people reported an increase in knowledge and skills.

Recommendations

- To devise an approach to prioritise and capitalise on the more responsive markets (agriculture and IT services) as given the majority of the budget is allocated to Output 1, there is a risk of spreading too thinly across the different markets. To help achieve this, PMDP could consider better integration and cohesion with other donors and programmes in this space.
- To consider disaggregating results by region to gain a better understanding of the ability to penetrate more detached and marginalised markets.

Output Title	Strengthened trade and investment linkages with international markets
Output number per LF		3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of activities completed by PMDP within the framework of support provided to the Palestinian Investment Promotion Agency (PIPA) and key market institutions	28	29
3.2 Number of people trained on trade and investment promotion	30	30
3.3 Number of women trained on trade and investment promotion	6	14
3.4 Number of Commercial Trade Representatives (CTRs) placed	6	6
3.5 Number of Diaspora engaging activities conducted	24	25
3.6 Number of gaps and impediments to trade and investment based on the National Export Strategy (NES), Investor Needs Assessment and Output 2 analysis	10	10
3.7 Number of engagements with relevant stakeholders	4	6
3.8 Capacity building activities for relevant stakeholders	2	3
3.9 Number of laws or bylaws facilitated and TA provided to improve the regulatory environment	2	2
3.10 Number of TA activities provided to the Ministry of National Economy (MoNE) and other institutions to tackle issues relating to Doing Business Report	2	4
3.11 Number of Women and Youth (WAY) related gaps and impediments identified	4	4
3.12 Number of engagements with relevant stakeholders on Women and Youth -(WAY) related issues	2	3
3.13 Number of capacity building activities of relevant stakeholders to address Women and Youth (WAY)-related issues	1	1
3.14 Number of policy recommendations for the Palestinian Export Council (PEC) plan implemented/in process	2	3
3.15 Branding strategy developed	Yes	Yes

Provide supporting narrative for the score

3.1: In 2017, this output’s performance significantly improved. During 2017 PIPA facilitated investments with a total capital of $64.5 Million which contributed towards creating 1,862 direct jobs[5]. A total of eight activities were carried out in support of PIPA bringing the total number of activities to 29. PMDP continued to provide technical assistance to PIPA to achieve focus on priority sectors. PIPA also introduced a new incentive package for renewable energy and conducted various outreach activities to promote investments in this sector. PIPA is also focusing on specific sectors, namely the renewable energy and agricultural sectors with articulated value propositions and bankable projects for each.
[5] This number is attributed to PIPA and not PMDP.

3.2 and 3.3: Last year, the programme did not report any progress on these two indicators. However, in 2017, PMDP matched their target of 30 people being trained in trade and investment promotion and more than doubled its target of the amount of women being trained. Fifteen of PIPA staff participated in a two-part training workshop to develop capacity and knowledge on identifying investment opportunities. As a result of the exercise, PIPA has formulated its policy agenda and developed two position papers and two advocacy plans for the agriculture and renewable energy sectors. PIPA staff learned how to understand and analyse the three major financial statements (balance sheet, income statement, statement of cash flow), conduct the statements analysis through ratio analysis, consider central issues when budgeting and planning, understand the financing alternatives between debt and equity and the cost of capital, analyse investments utilising capital market analysis tools such as the Internal Rate of Return (IRR) and the Net Present Value (NPV).

3.4: The Commercial Trade Representatives (CTRs) were deployed in five markets (UK, US, Russia, Germany, and Kuwait) and have been providing information on the regulations, standards and requirements for entering their respective markets, especially for agriculture and food products, tourism, ICT, and stone and marble sectors. So far they have arranged over 80 business-to-business (B2B) meetings, leading to six companies reporting export deals. Four deals for which PMDP has been provided commercial information on equate to over $1 million of agribusiness products. As a direct consequence of PMDP assistance, PIPA is focusing on specific sectors, namely the renewable energy and agricultural sectors with articulated value propositions and bankable projects for each with a newly introduced incentive packages focused on the renewable energy sector.

3.5: PMDP continued to engage with Palestinians in the Diaspora, moderately exceeding its 2017 target. The programme has been working to advance engagements with the diaspora. PMDP developed a new partnership with the Deir Debwan Charity Organisation to identify investment opportunities and contribute to the economic development of their home village. PMDP also continued supporting Invest Palestine efforts, leading to the establishment of a $2.5 Million investment fund and continued to engage with multiple influential diaspora individuals on ideas that are aimed at creating new local job opportunities.

3.6-3.15: PMDP have made steady improvements following the EU’s €2 million add-on in December 2015. PMDP expanded the mandate of Output 3 in mid-2016 to include work on Business Enabling Environment (BEE) and the National Export Strategy (NES). On the BEE, PMDP’s support to MoNE with policy reforms contributed to achieving the highest jump to date in the ranking of the West Bank and Gaza in the World Bank Doing Business Report this year (2018), from 140 to 114. PMDP met and moderately exceeded targets related to legislation and policy reform, which includes the new Companies Law draft and the business licensing reform that were both submitted this year to the Cabinet of Ministers. The new Companies Law is coherent with international best practices of modern company laws which safeguards investor rights and protects investments. This, in turn, contributed to improving the ranking of the OPTs in the World Bank’s Doing Business Report. In addition, the business licensing reform aimed to reduce the bureaucratic steps to license a business in the OPTs, making it easier and cheaper for businesses to register. PMDP has also facilitated the National Export Strategy (NES) implementation, a branding strategic framework has been produced and discussed by the Palestine Export Council (PEC) members. PEC and the Cabinet have also endorsed the one-stop shop (OSS) mechanism for export procedures and the monitoring system for differentiating local handicrafts from imports.

Recommendations

- To improve communication links with CTRs to ensure uniformity and better monitoring.
- To oversee the transfer of CTR contracts, for sustainability purposes, from PMDP to PA through the PIPA CCU.
- To consider a more proactive approach to facilitate discussions with diaspora Palestinians in order to increase trade and investment links.
- To consider approaches to increase the visibility of CTRs in the respective countries and to raise awareness among organisations of the CTRs’ function and standing.
- To assess the performance of CTRs in terms of effectiveness and consider alternatives.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

Inputs  Outputs  Outcomes

Output 1

Inputs in the form of matching grants and technical assistance will be provided to encourage firms to invest in procuring business services to improve their skills and innovation. Matching grants will also encourage business service providers to invest in the quality of their services to compete for high value assignments and to be more responsive to firms’ needs. PMDP will also work more hands-on with disadvantaged women and youth companies to help develop a clearer business outlook and will partner with prominent Civil Society Organisations (CSOs) to facilitate support to such companies through its specially designed grants windows.

As firms improve their skills and innovation capacity they will be able to produce higher quality and/or lower cost products and services which could compete in the domestic market against imported products and even in international markets for higher value products and services. As demand for business services increase, the assumption is that firms, including Business Service Providers (BSPs), will be crowded in to provide high quality services and products to the market. Firms will also be able to use the procured business services to develop their marketing skills which will enhance their overall competitiveness.

Output 2

Conducting analysis of underperforming value chains or potentially high performing sectors will enable the team to identify and address the specific market failures. This could require facilitation and/or systemic interventions to be co-funded through the matching grant scheme.

This will be shared with other donors and market agents, including the Palestinian Authority, to encourage behaviour change. Addressing the systemic issues that are hindering market development will enable specific value chains within certain sectors to reach their full potential and improve productivity and quality.

Output 3

The PMDP project will provide technical assistance and systems to the Palestinian Investment Promotion Agency (PIPA) to develop the necessary skills to map the market and identify existing and potential business investment opportunities and enhance its aftercare services. PMDP will aim to mobilise the Diaspora and other potential investors through various activities. A more effective PIPA, a mobilised Diaspora and skilled commercial representatives will result in strengthening trade and investment linkages with international markets.

Changes

PMDP implemented a “new direction” in 2017, which brought about some additions and alterations to the Theory of Change (ToC). This included a focus on job creation and the quality and sustainability of jobs and increased specificity on women and youth. It also placed emphasis on considering different needs and special requirements for companies operating within challenging marginalised areas. Indicators pertaining to Outputs 2 and 3 were also introduced to better quantify and monitor the effectiveness of the programme.

Describe whether the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Overall, the programme is performing well against outcome and impact objectives. The Palestinian businesses supported by PMDP have overall shown increased competitiveness as demonstrated by the increase in the amount of firms reporting an increase in revenue including additional export sales and new exporters. PMDP has also positively contributed to lowering the unemployment rate as it’s exceeded its job creation target. However, given the size and value of the programme and the various and volatile political and economic factors at play, this has not been reflected in unemployment and poverty figures. Progress has also been made regarding positive behaviour change among firms in specific market systems/sectors.

An area of improvement is the engagement and investment of diaspora Palestinians. This was highlighted by the performance of the CTRs and whether they are as effective as is desired to achieve the required impact. To address this, PMDP could consider a more proactive approach in targeting Palestinian diaspora and making the CTRs more visible and accessible. Alternatively, different approaches to CTRs could also be considered to encourage investment in Palestine.

Explain major changes to the Logical Framework in the past year and this year

PMDP developed an adjusted Logical Framework (Log-Frame) during the year. The updated Log-Frame mainly aimed to strengthen the representation of both Output 2 and 3, and ensuring full compliance and consistency within the different outcome and output levels for different components. These changes were mainly in the form of effectiveness and efficiency indicators to better quantify and monitor the impact of the programme. As a consequence of this review, the Log-Frame should include indicators that monitor equity as part of the VfM framework and indicators, which better measure the effectiveness of CTRs and/or an alternative component to attract Palestinian diaspora to invest in Palestine.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

Key cost drivers and performance

The main cost drivers of the programme are staff costs, running expenses, and matching grants. These cost drivers have been identified in the original business case and are not expected to change. In addition to the implementer’s costs, the programme covers evaluation supplier expenses andvetting expenses.

In 2017, Building on PMDP’s lessons learned and recommendations received from GDSI, DFID and EU, a revision process for both the PMDP logframe and Value for money guidelines took place. The revision process aimed mainly to strengthen both components 2 and 3 representation in the programme logframe and VfM. The adjusted VfM frameworkwas approved in December 2017 with a total of 36 indicators that include effectiveness indicators to assess all programme components.

Economy

PMDP reports six economy indicators covering all the programme’s three components. Overall, the programme continues to demonstrate improved performance for this VfM metric. The original target mentioned in the BC for the share of total costs attributed to management was 25 per cent. As of 2017, this figure was at 10 per cent of total programme costs down from 33 per cent when the programme began and the same as the previous year. It stands at a cumulative share of 14 per cent throughout the duration of the intervention. PMDP has a core staff of 34, 13 of which are considered management while the rest are considered technical staff. PMDP’s technical staff is engaged in programme delivery activities including the provision of technical support to beneficiaries.
Efficiency

PMDP reports two efficiency indicators, the first of which covers all three of the programme’s components and the second of covers only Output I. PMDP is making efficient use of its resources. The programme has trusted systems in place for financial management, tracking of grants, procurement and tracking of implementation. These processes due however add to costs and are high relative to the value of grants provided to beneficiaries but is deemed necessary given the operating context. PMDP is delivering its outputs efficiently and remains on track to achieve end-of-programme targets, which is illustrated by the continued decrease in the share of staff who are not directly involved in the delivery and implementation of services. This is now at 42 per cent, down from 49 per cent in 2016 and 93 per cent in 2014 when measurements began.

Cost Effectiveness

PMDP measures the cost per outputs produced. In previous years, only Output 1 had metrics that measured this. However, in the last year, metrics have been introduced for Output 2 and 3; as this is the first year, comparisons and trends are not applicable. The overall trend remained positive relative to the 2014 baseline. However, an area where VfM has shown a sign of deterioration is the amount of money it costs to improve a product and enter a new market. In November and December 2017, PMDP signed grants with the purpose of support entering new markets with a total of 33 clients. The value of grants for those 33 were counted in the nominator, despite the fact that it is not expected that they report new markets during 2017, this may justify the rise from 2016 to 2017.

Output 1

- Cost per £1 in generated sales fell from £0.09 in 2016 to £0.07 in 2017.
- Cost to create a new fixed-term employment job decreased from £3,150 in 2016 to £3,032 in 2017.
- Cost per new foreign market entered increased relative to 2016; from £22,170 to £24,492.
- Cost per existing product improved showed deterioration. In 2017, it went up from £12,595 to £20,292[6].
  [6] In 2017, a total of 23 companies were contracted at end of calendar year in November and December, having their grants costs included in the cost calculation but without accounting for the economic benefits of improving such products. This will be adjusted in the 2018 report and factored in.

Output 2

This year will be the first year to evaluate effectiveness of this output. A total of eight VfM indicators were added. Both indicators aim to measure the amount needed to create one new job attributed to Output 2.

- Cost per new job created (without grantee share[7]) in 2017 was £2,602.
  [7] PMDP offers matching grants whereby beneficiaries pay a share towards a support activity. Grantee share refers to the amount paid by beneficiaries towards a support activity funded by PMDP.
- Cost per new job created (with grantee share) in 2017 was £5,072.

In order to get a better sense of this number as there is no baseline or previous year’s information to benchmark or compare with, the main reference will be the component 1 results, as both indicators 17 and 18 are similar to these two indicators. Comparing against the highest cost per new job created values from Output 1, when excluding the grantees ‘share, both components value are near with Output 2 slightly higher. However, when including the grantees’ share, Output 2 is relatively higher than Output 1.

- Cost per £1 of additional revenues (without grantee Share)
- Cost per £1 of additional revenues (with grantee share)
- Cost per beneficiary using new/improved service/product (without grantee share)
- Cost per beneficiary using new/improved service/product (with grantee share)
- Cost per service provider adopting new practices/products (without grantee share)
- Cost per service provider adopting new practices/products (with grantee share)

Cost per additional revenue aims to measure the cost incurred to create a £1 of additional revenues, considering both additional sales and reduced costs. In 2017, it costs £0.34 to generate a £1 increase in total revenues without considering grantee share and £0.63 to generate a £1 increase with grantee share.

Both indicators pertaining to cost per beneficiary aim to measure the value needed for beneficiaries to use new or improved services/products under Output 2. It costs £1,613 and £2,745 to have one beneficiary/customer to use the improved/new service/product for the first time.

As of 2017, it costs £17,753 and £33,279 to have one service provider adopting new practices/products.

Output 3

Three new VfM indicators were developed for Output 3. The three indicators reflect main components: PIPA capacity improved, well-functioning CTRs placed, diaspora attitude towards trade, and investment and know-how enhanced.

- Cost per £1 of the value of investments facilitated by PIPA
- Cost per trade and investment deal facilitated by commercial trade representatives (CTR)
- Cost per diaspora initiatives designed and launched by partner organisations as a result of PMDP’s support

PMDP has focused on capacity building activities for PIPA, and as with other capacity building interventions, quantifying the impact is very difficult because such impact may expand to levels that is not easy to reach or refer to a certain intervention. PMDP has supported PIPA with a strategic framework, improved the organizational structure, supported outreach activities to businesses and investors, and conducted a value proposition for two sectors, etc.

The indicator evaluates the CTR programme based on number of deals signed, due to the difficulty and sensitive of accessing information related to the value of deals. During 2017, a total of six trade and investment deals had been signed. PMDP has spent a total of £107,422 on the two CTRs reporting the six trade and investment deals (UK CTR and Germany CTR). Thus for every deal signed, PMDP has invested a total of £17,904. PMDP was able to obtaincommercial information on the value of four out of the six deals signed, the four deals have reported a total value of £769,230 (£653,882 from UK CTR and £115,348 from Germany CTR), thus when looking at the VfM from the value of trade and investment deals aspect, we will find that, in 2017, it costs £0.14 to generate a £1 in a trade an investment deal.

Diaspora support activities have indicated that by the end of 2017, 11 initiatives were designed and launched by partner organizations as a result of PMDP support. The cost spent on diaspora activities has reached a total of £129,084. Thus, for every initiative, PMDP has invested a total of £11,735 on average by the end of 2017.

Recommendations

- In order to be in alignment with DFID’s VfM framework, PMDP should consider developing indicators that measure equity: how fairly are the benefits distributed and to what extent will we reach marginalised groups.
- To build on indicators and metrics which better quantify the overall economic impact of the intervention and its sustainability.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Major

The overall risk rating for the programme remains “Major” based upon continued instability resulting from political deadlock in peace negotiations between Israelis and Palestinians and the blockade on Gaza. This means that occasional flare ups in violence are more likely, which could impact programme operations and deliverability.

Overview of programme risk

The risk register (annexed) is regularly monitored on a quarterly basis. In addition to monitoring risks identified through the programme, the below risks have been identified and are monitored regularly:

The political context, particularly in Gaza, raises the risk that funds may indirectly or unintentionally be diverted for use by illicit and unauthorised organisations. Safeguards employed by the programme for vetting, anti-fraud, anti-corruption, contracting, and procurement were found to be effective, which was also confirmed by the programme’s independent evaluation supplier. Safeguards are monitored regularly.

Outstanding actions from risk assessment

There are no outstanding actions from risk assessments.

Update on partnership principles

The PA Ministry of National Economy is a member of the Steering Committee of the programme. In addition, PMDP works closely with the Ministry on the Commercial Trade Representatives component as well as the Business Enabling Environment (BEE) component. Finally, PMDP supports the Palestinian Investment Promotion Agency (PIPA) to improve its capacity and attract investments.

The Partnership Principles are relevant to the management and monitoring of this programme given it works directly with the PA.  We assess the Palestinian Authority’s commitment to DFID’s Partnership principles on a regular basis, most recently in April 2018. The Partnership Principles are also discussed through a formal meeting with the PA annually. This was last undertaken in June 2016 where we acknowledged progress by the Palestinian Authority against a number of indicators in particularly challenging circumstances.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues
DAI Europe (implementation supplier) and GDSI (evaluation supplier) continue to meet commercial partnership requirements.

Delivery against planned timeframe
The programme has met its targets for the year and remains on track to deliver its end-of-programme targets in 2019. The programme still has a significant amount of spend forecast for the final six months of operations which is a risk given the possibility of staff attrition as the programme comes to an end. This will be monitored closely.

Quality of financial management
DAI provides quarterly financial reporting and expenditure forecasts as well as monthly invoices. DFID carries out random spot checks on expenditure lines in each month’s grants invoice from PMDP. The total amount spent during the reporting period was £4,832,185 with breakdown presented below:
PMDP finances during reporting period January-December 2016
Item	Spend
Implementation Supplier (DAI Europe)
Fees & Expenses[8]	£2,510,868
Grants	£2,235,387
Evaluation Supplier costs	£62,111
Vetting costs	£23,819
Total	£4,832,185
[8] This includes management and technical staff. Technical staff are engaged in programme delivery.

During 2017, the actual invoiced amount related to grants was £2,235,387. This amount was spent under the open and partnership grants mechanisms. The table below provides details on the grants spending and commitments cumulative to date and detailing spending for each grant type and location (Gaza and West Bank) till the end of the reporting period (Dec 31, 2017).

Grant Details Report – 2017 and Cumulative to date / Grants Detailed Commitments and spending by (TYPE) as of Dec 31, 2017
Grant Type	Committed / 2013-2016	Committed 2017	Cumulative Committed 2013-2017	Disbursed 2013-2016	Disbursed 2017	Cumulative Disbursed 2013-2017
Technical Assistance and Grants / West Bank	£2,563,790	£847,440	£3,411,229	£1,438,596	£1,237,383	£2,675,979
Technical Assistance and Grants / Gaza	£276,161	£506,284	£782,445	£228,008	£399,458	£627,466
Subtotal Technical Assistance	£2,839,950	£1,353,724	£4,193,674	£1,666,604	£1,636,841	£3,303,445
Back to Business	£3,782,315	-£18,396	£3,763,919	£3,428,139	£335,779	£3,763,918
Partnership Grants	£669,002	£425,795	£1,094,797	£302,252	£262,768	£262,768
Other (TA) under grants	£3,729	-	£3,729	£3,729	-	£3,729
Total GBP Cost Inclusive of Mark-up	£7,294,996	£1,761,123	£9,056,119	£5,400,723	£2,235,388	£7,636,111

Asset monitoring and control
PMDP keeps an updated track of the programme asset record, which DFID monitors on a quarterly basis. The last two asset checks were conducted in December 2016 and September 2017. Last year’s financial audit found no irregularities.

Date of last narrative financial report(s)	31 January 2018
Date of last audited annual statement (s)	16 August 2017

G: MONITORING, EVIDENCE & LEARNING

Monitoring (1/2 page)

The programme falls under the OPTs Economic Development pillar and is managed by a Project Officer, Senior Programme and Policy Officer, Private Sector Adviser, and the Team Leader who is also the Senior Responsible Owner (SRO). The team monitored progress in 2017 as follows:
- DFID’s Senior Policy and Programme Officer met with PMDP management on a monthly basis, called PMDP management on a weekly basis and corresponded on PMDP-related issues on a daily basis.
- DFID’s programme team also met regularly with the EU Project Manager and Head of the Economic Development Unit separately and together with DAI Europe.
- DAI Europe submitted monthly performance sheets, quarterly progress reports, and quarterly financial reports.
- DFID held occasional meetings with PA Ministry of National Economy at both ministerial and technical levels.
- PMDP organised quarterly Steering Committee meetings.
- GDSI provided regular assessments quarterly and annually and have improved programme efficiency.

A significant achievement from a monitoring and evaluation perspective was the steering committee approval of the adjusted Log frame and Value for money guidelines in December, 2017. The newly updated Log frame and VFM guideline has been used for reporting all achievements for the year ending December 31st, 2017. The updated Log frame mainly aimed to strengthen the representation of both Output II and III, and ensuring full compliance and consistency within the different outcome and output levels for different components.

A push to centralise the data and information via PMDP’s management system – TAMIS – was made during 2017. A specific M&E view was created for both the Open Grants and the Gaza B2B-B2M windows on TAMIS to document all results of surveys conducted throughout the programme. This is important to ensure the documentation of results in the management information system and will allow easy access for results.

Annual Review

The annual reviewdraws on: (i) PMDP’s Fourth Annual Report; (ii) PMDP’s Fourth Annual Financial and Operations Report[9]; (iii) PMDP M&E Evaluation Reports and Annual Survey Results; (iv) PMDP Value for Money Analysis (VfM); (v) interviews with PMDP staff in Ramallah and Gaza; (vi) interviews with DFID and Office of the European Union Representative in Jerusalem; (vii) semi-structured interviews with PIPA, JEST as well as the Everest Group; (viii) meetings with PMDP client businesses in the West Bank and Gaza (29), BSPs (2) and a focus group with the Palestinian Federation of Industries in Gaza; (ix) semi-structured interviews with 4 CTRs; (x) interviews with the USAID Compete programme and Mr Antoine Mansour working for EU on Donor Mapping and identifying the next steps of the EU programme.

Progress on recommendations from previous reviews (1/2 page)

Recommendation	Progress
PMDP and DFID will increase end-of-programme direct job targets from 2450 to 3020 jobs and amend the milestone accordingly by May 2017.	The total amount of jobs created throughout the programme as of 2017 is 2,574. Targets have been exceeded for each year of the programme, including this one.
PMDP will fill vacant programme positions in Ramallah and Gaza, particularly in the area of Monitoring and Evaluation by July 2017	Two evaluation advisers joined PMDP and helped develop an enhanced monitoring and evaluation framework and proposed a series of new indicators for the Logical Framework. The team also devised and put forward a VfM assessment framework.
PMDP to develop a methodology to assess the quality of jobs created through the programme.	PMDP has used the ILO framework as its reference for quality of jobs assessment, from which it was agreed that five out of the seven dimensions of the ILO framework will be used.
PMDP to improve ways of tracking and analysing the impact of interventions under Output 2.	PMDP have devised indicators, which monitor the amount of products improved and/or developed to address market failure and the amount of people reporting an increase in knowledge and skills as a result of market interventions to better assess the impact. The new indicators both exceeded their respective targets for 2017.
PMDP to develop VFM effectiveness indicators for Outputs 2 and 3.	Building on PMDP’s lessons learned and recommendations, a revision process for both the PMDP Logical Framework and VfM guidelines was carried out. It strengthened both Outputs 2 and 3 representation. The adjusted VfM guideline was approved in December 2017 with a total of 36 indicators that include effectiveness indicators to assess all programme components.
PMDP to increase its outreach in marginalised areas and establish realistic targets in 2017.	In 2017, 53.5 per cent of net new beneficiaries have their businesses located in marginalised areas. The additional beneficiaries raised the total number of beneficiaries from marginalised areas to 213, representing 45.8 per cent of all served grantees. This is a direct result of the introduction of special marginalised window.
PMDP to monitor the effectiveness of new grants windows in creating jobs for women and youth in 2017.	PMDP moderately exceeded its target of assisting 135 women-owned/managed companies. The programme helped 143 women-owned businesses, which represents 20 per cent of all companies assisted in 2017; an improvement on 2016 figures.
PMDP to develop a facilitation strategy for the furniture sector by September 2017.
PMDP to devise and initiate interventions for tourism and furniture sectors in 2017 based on the study recommendations, while ensuring interventions are spread out more evenly throughout the year.	Due to constraints within the tourism sector, PMDP have decided to scale back The number and scope of interventions will be reduced; one intervention were completed in 2017. There were no reported interventions within the furniture sector.
PMDP to finalise placements of remaining CTRs and assess performance level, impact, and VfM.	The Commercial Trade Representatives (CTRs) were deployed in six markets (UK, US, Russia, Germany, Kuwait and the Netherlands) and have been fully active providing information on the regulations, standards and requirements for entering their respective markets. / Among the three new VfM indicators were developed for Output 3 was well-functioning CTRs placed.
On quarterly basis, PMDP and DFID to continue to monitor PIPA’s political will to embrace necessary change to implement its objectives.
PMDP will continue to engage with other public and private institutions with the aim of improving investment and trade.	PIPA introduced a new incentive package for renewable energy and conducted outreach activities to promote investments. During 2017 PIPA facilitated investments with a total capital of $64.5 Million creating 1,862 direct jobs. PMDP matched their target of 30 people being trained in trade and investment promotion and more than doubled its target of the amount of women being trained
PMDP to launch a branding initiative in line with National Export Strategy (NES) and Palestinian Export Council (PEC) objectives.	A branding strategic framework has been produced and discussed by the Palestine Export Council (PEC) members. PEC and the Cabinet have also endorsed the one-stop shop (OSS) mechanism for export procedures.
PMDP to continue to help PIPA to increase its effective engagement with other national organisations	PMDP developed a new partnership with the Deir Debwan Charity Organisation to identify investment opportunities and contribute to the economic development of their home village. PMDP also continued supporting Invest Palestine efforts, leading to the establishment of a $2.5 Million investment fund and continued to engage with multiple influential diaspora individuals on ideas that are aimed at creating new local job opportunities.