CSSF Strand document:

Economic stability in Egypt

June 2015

Contents

Topic	Page

Summary.....................................................................................................3
Strategic case..............................................................................................4
Appraisal case..............................................................................................8
Commercial case.......................................................................................14
Financial case............................................................................................15
Management case.................................................................................... 16
Annex A – Summary of log-frame indicators............................................20
Annex B – The scoping mission back to office report................................21
Annex C - References.................................................................................25

Intervention Summary
What support will the UK provide? / The UK will provide £1.75 million (technical assistance) to support better, more accountable economic policies in Egypt. This will be through supporting reform minded policymakers already driving reforms, challenging bad policies through increased public dialogue, and promoting state and non-state models of inclusive growth, which target and help the poorest, most vulnerable Egyptians directly. / Why is UK support required? / Egypt matters to stability in the Middle East, and economic reform is necessary for political stability in Egypt. A number of competent economic ministers are already driving sensible economic reforms, with the backing of the President. Many of these have been overdue for decades. As a result, the old social contract is changing. A state that provided jobs and subsidised goods, is now facing fiscal pressures, and is having to deliver services and embrace market economics. The UK has an important role to play through this transition as practical UK expertise is highly valued. / This economic work is in support of the National Security Council strategy for Egypt, and will operate alongside inclusive governance and security strands. Lessons learnt will inform the next 4 year approach to Egypt (CSSF 2016-20). / What are the expected results? / This programme will support the Government’s existing economic reforms plans, while building the public’s understanding of economic reforms to hold the state to account. This will be done through technical advice, analysis, sharing HMG expertise, and supporting grass root models of excellence. The following are the expected outputs under each of the 3 strands of work: / A: Supporting the state: / 100 civil servants trained on better regulation or economic reform. / 15-20 high level champions trained on better Public Financial Management. / 10 advisory visits take place, with HMG experts sharing expertise in Cairo. / B: Challenging the state / 2,500-3,000 citizens polled on their views and perceptions around corruption. / 6 publicly broadcast TV debates on anti-corruption. / 2 workshops on international best practice on tackling corruption. / C: State and non-state models of inclusive growth / Building capacity of Ministry of Social Solidarity (MoSS) to deliver 500,000 direct and 1.5 million indirect beneficiaries under the cash transfer programmes. / Help 8 aspiring social enterprises develop crowd-funding videos to raise support for critical pieces of new business plans. / Provide financial literacy training for 500 women in poorest districts of Upper Egypt.
2. Strategic Case
2.1 Context and need for intervention / As the Egypt CSSF Operational Plan laid out, economic grievance[1] was one of the main drivers of the Arab Spring and has underpinned much of the subsequent turbulence. While political and security abuses of power have played an important part, the structural problems of Egypt’s economy remains a very real threat to the country’s stability in two ways: 1) economic crisis or stagnation generates unrest and the cycle of protest and repression continues; 2) lack of progress or mismanagement of the reforms needed to avoid 1 will further marginalise an already poor and vulnerable population leading to widespread protests (and violent security response). / Egypt saw strong growth in the 2000s but it remains effectively a rentier economy[2], based heavily on Suez Canal fees, oil and gas and tourism receipts. It is estimated that 60% of workers are employed in informal economy[3], depriving the state of taxes, workers of protection and businesses access to capital. Public expenditure is opaque and wasteful, with almost a third being spent on salaries and wages, a quarter on subsidies and a quarter on debt servicing. Extra investment in health and education has done nothing to stop the steady deterioration of services. The military[4] retains a powerful role in the economy although data remains scarce on actual assets, they own all non-residential or agricultural land, have large military factories and companies making everything from pasta to cars to holiday resorts, and often receive large state contracts without scrutiny or tendering. On top of this, Egypt remains a highly corrupt economy, ranked 97th of 174 countries in TI’s Corruption Perception Index in 2014. / Many of these issues have been aggravated by the turbulence of the last four years. Short term, populist measures have increased the public and military sectors. whereas With the drop-off in traditional rents (tourism, fees from Suez Canal) and foreign direct investment (FDI) and an ever increasing subsidy bill, Egypt has become heavily indebted and dependent on aid from the Gulf. / If not for the approximately $8bn from Qatar in 2013 and the $26bn in Gulf support over the past 18 months, Egypt would already be facing a severe financial crunch, particularly on foreign currency reserves which have fallen from $36bn in 2011 to $14bn today. The collapse of tourism and the diversion of oil and gas from export to the ever-expanding local demand have made Egypt even more reliant on external support especially remittances ($20bn a year), Gulf and other aid flows. Despite the gloss of the March 2015 economic development conference and slick presentations of future plans, the macro-economic fundamentals in Egypt are of grave concern. The budget deficit in 2014 was as high as Greece’s when it turned to the IMF and even in the Government’s ambitious plan to bring the rate down to 10% (FY 14/15) would still be roughly the same as the UK’s peak in 2010 when the austerity programme started. / Egypt’s main financial supporters, Saudi Arabia, the UAE and Kuwait, place a high value on Egypt’s stability as a market and as a force for moderation in the region. Their support is not limitless, however, and increasingly they have focused on project financing rather than grants and loans and encouraged Egypt to seek other sources, whether that be development banks or the IMF. How Egypt’s fiscal deficit is addressed, through subsidy cuts, public sector reforms and tax system changes, will have a tangible impact on the wellbeing of Egyptian citizen’s and their attitude towards the state. This also emphasises the importance of having a strong, competently led and adequately staffed Ministry of Finance to lead the fiscal and associated structural reform process. / It is estimated that 70% of the Egyptian population is under 30 and 700,000 new young workers[5] enter the labour market annually. The successive failure to provide jobs for the young population is considered to be a major source of instability. Underemployment is particularly marked in Egypt. More widely, one in four Egyptians live on less than $2.5 dollars per day[6], while half of the population (of 89 million) earn less than $4 per day. / Women’s labour force participation is 25% nationally[7] (though in some areas it is much less than this). This reflects a number of issues, including discriminatory social norms that limit women’s economic opportunities, educational attainment and confidence, but also issues of safety and security are likely to have an impact on women’s choices and economic opportunities. A recent study by Booz Allen[8] consulting firm found that raising the level of female employment to male levels could boost Egypt’s GDP by as much as 34% percent – a crucial pillar of long-term stability in a country with high levels of unemployment and a fast growing population. Women’s economic empowerment is also likely to be associated with lower population growth, an issue that could have a huge destabilising effect in the future. / The state’s social compact in the 1950s and 1960s was for universal services and subsidies, in exchange for political acquiescence.[9] As the population rose from 22 million in 1952 to 89 million today (and is now growing at 3m a year), the universal subsidies on bread, fuel, utilities and services has become untenable. In 2014, the Government spent $21bn on petroleum products alone. Previous efforts to reform subsidies, particularly food and fuel, have led to major outbreaks of social unrest and have usually been repealed. Basic services have deteriorated as a sclerotic bureaucracy (7 million civil servants and 5 million more workers in public enterprises), corruption and lack of investment have undermined the institutions. Lack of accountability has allowed this trend to continue unchecked. While the state has spent up to a third of its budget on subsidies and various social protection schemes, these have often been poorly or un-targeted and poverty rates have continued to grow. / The combined economic, social and political shocks of 2008-2011 have already left a significant proportion of the population vulnerable. This vulnerability has come at the same time as the state services declining still further and foreign and domestic funded aid projects grinding to a halt due to security and political clampdowns. Attempts to reduce the deficit will increase the strain on Egyptians. / The Arab Spring of 2011-12 highlighted the need for social inclusion and a new social contract in the countries affected, including Egypt. Redistribution through universal subsidies is no longer affordable and leads to significant inclusion errors in the provision of social welfare. In 2014, Egypt spent $21bn on various energy subsidies and only $4.3bn on pensions, grants and cash transfers. With the lack of effective tools, successive Governments have sought to buy off dissent and provide some form of social protection by a compound mass of allowances, extra payments and bonuses for the huge state bureaucracy. The state wage bill alone has increased by 110% since 2011. With the breaking down of the social compact and an increasingly stark divide between the cosseted state sector and the vast, poorly paid informal sector, state legitimacy is being eroded. / Avoiding the elite capture of growth: Public transport, education, health and other pro-poor areas of public investment have been neglected for decades. The boom of the 2000s, exacerbated the inequality in opportunity between the rich and well-connected and the rest. Further tough decisions need to be taken to reform ineffective and untargeted subsidies, (World Bank analysis found that the wealthiest quintile receives fully 28 percent of the resources spent on subsidies[10]), but these decisions will cause further pressure on the poor and middle classes who have come to depend on a wide range of heavily subsidised goods and services including food, fuel, electricity, water, transport and fertiliser. If done properly, replacing these with social protection measures that protect and empower the poorest and economic policies and regulations that promote inclusive economic development, e.g. better infrastructure planning, improving the business climate, and social entrepreneurship, reducing barriers for business and job creation will not only strengthen the Government’s resolve to continue reform but also mitigate the very real risks of socio-economic unrest caused by such reforms. / 2.2 Government reform actions taken to date / To date the Government has started enacting a number of policies under an ambitious plan in pursuit of better economic governance and economic stability. For example, in the past 12 months, the Government has: / Reduced spending on untargeted energy subsidies (July 2014). / Passed a new investment law to facilitate FDI (March 2015). / Committed to raise spending on health/education to 10% of GDP (Jan 2015). / UK role and economic policy engagement / The UK has an important role to play in supporting reform-minded ministers. From both a UK and Egyptian prosperity angle, as well as a stability interest, we have significant equity already invested in the Egyptian Government being able to shepherd the economy to sustainable and more inclusive growth. Over the past four years, the Arab Partnership Economic Facility (APEF) has enabled us to contribute to some significant policy reforms (e.g. the work on subsidies and social safety nets through the World Bank, as well as the passing of the new micro-finance law). Also through the Arab Partnership the UK has supported greater demands for accountability and economic reforms, and developed a portfolio that directly promotes economic opportunities for vulnerable people, and / The appraisal case sets out the current UK view on policies that would warrant support in Egypt based on experience from previous technical assistance work and meetings with key officials. However, given the rapidly changing external context, these policies will be continuously reviewed to ensure greatest value for money. A narrow focus will be taken initially on policy areas that the UK has already engaged on with the Egyptian Government with a view to building linkages to other critical policy reform areas during implementation. These will all be areas where there is: / a high level of Government ownership and willingness to reform. / strong international evidence base on what works. / clear HMG comparative advantage, and technical expertise to offer. / On the UK comparative advantage; / We have solid partners with track records on delivery. Under the Arab Partnership, the UK has established relationships promoting greater accountability over spending decisions through partners such as the Ministry of Finance and the Egyptian National Competitiveness Council (ENCC). / We have a reputation for quality economic advice. Practical policy advice through HMG counterparts such as Infrastructure UK, the better regulation delivery unit and HMRC has been well received to date. / An intervention could have wider beneficial impact on our objectives. UK niche technical support is able to leverage and influence much larger programmes funded by the Egyptian Government or IFIs. For example, an infrastructure plan would improve the return of billions of Dollars spent on new roads, ports and housing. / Rationale for HMG/DFID intervention / The overarching policy framework is the National Security Council strategy for Egypt, which lists a stable economy as one of four pillars of UK engagement with Egypt. / A country level operational plan for implementing the CSSF in Egypt was agreed by the CSSF regional board in April 2015. The activities being proposed are consistent with this plan. / This approach, of providing technical assistance rather than financial aid, is consistent with the DFID framework for engaging with Middle Income Countries. / Gender Equality Act / Studies have shown the women’s labour force participation is 25% nationally, and much lower in many places. In terms of the opportunity, a recent study by Booz Allen[11] consulting firm found that raising the level of female employment to male levels could boost Egypt’s GDP by as much as 34%. / A strong gender lens will be brought into this programme, through assisting the Ministry of Finance (MoF) with gender budgeting or the Ministry of Trade and Industry or MoSS with analysis and advice on the specific barriers to women and youth participation in the labour market or access to finance. From a management perspective, we will ensure that where possible, logframe data will be gender disaggregated, particularly at the impact level (i.e. jobs, and extent of public resources targeted to women). / Expected Impact and Outcome / This programme represents a limited amount of technical assistance funding in a middle income country with a number of other active donors. This programme will aim to improve the policy framework and its application and, significantly, to also influence the Egypt programmes of key multilateral partners such as the World Bank, African Development Bank, European Union and EBRD who are also working closely with the Government and private sector in similar economic sectors and reform initiatives. / The overall impact of the programme is to contribute to better and more accountable economic policies in Egypt. Examples of such policies include; / Supporting a better investment climate in Egypt. / Improving the effectiveness of state spending on basic services. / Improving the targeting of new cash transfer programmes / As an outcome, this will be delivered through improving the Government’s formulation of economic policy and the public’s understanding of the need for difficult reforms. This will be done through technical advice, and support to campaigns and initiatives led by local think tanks and grassroots organisations. This will be tracked mainly through following: / Feedback on the quality of technical advice being offered by the UK. / Satisfaction with the quality of trainings being offered. / Effectiveness of public campaigns being led by select local think tanks. / This programme will work alongside: / The governance strand, and security strands of Egypt’s CSSF plan. / The remaining Arab Partnership projects that will be ongoing (e.g. Arab Women’s Enterprise fund). / The £20m BIS-funded Newton-Mosharafa Fund which aims to build research skills, innovation and partnerships between the UK and Egypt on five key challenges that face Egypt.
3. Appraisal Case
Identifying feasible options / The Strategic Case identified the need for a DFID intervention focused around improving economic policies through the provision of technical advice. Aside from the counterfactual (Option 1 - Do nothing), we identified 2 possible options. / Option 2 – An integrated approach working on policy support, policy advocacy and direct support to innovative models of inclusive development. / Option 3 – A focused approach working primary through Government using a technical assistance facility. / Options appraisal. / Option 1: Under the counterfactual (do nothing), we can expect to see the following (although the UK is not a major player in terms of total aid flows, there are significant gaps in other donor programmes and government policies and initiatives): / The Government of Egypt (GoE) embarks on some poorly planned infrastructure projects that deliver little economic value, and drain public resources. / The private sector remains subdued, workers search public sector jobs, draining scarce fiscal resources, and women’s economic participation remains subdued. / The new cash transfer programmes being implemented by GoE and World Bank remain poorly targeted, ignoring feedback from beneficiaries (the disbursement linked indicators agreed with the World Bank[12] indicate that 40% of programme beneficiaries are expected to be above the poverty line). / Option 2: This is the most comprehensive of the 3 options, and allows the greatest potential for learning lessons on the most effectively approach for the future. We appraise this option against the 6 criteria as set out below, and find that it offers the chance to work on policy areas where supporting the state would not be appropriate, while offering tangible outcomes and be seen to be ‘doing’ things, not just talking policy. At the same time, it means an approach where we are seen to be challenging the state. / Option 3: This option is politically attractive, as its primarily supporting the Egyptian state. And focusing on policy would allow a broader range of policy topics we could support. We judge this to be a higher risk approach as we’re not likely to see eye-to-eye with Government on all reforms, and will be unable to play a challenge function. It is also a less diversified approach. / The full pros and cons are set out in the table below. In light of the lower risk, and higher potential to deliver tangible results, we propose working exclusively on the approach as set out under option 2. / Table appraising options. / Evidence base under option 2. / Under option 2, UK support can improve the targeting and effectiveness of Government policies and larger public and donor funding flows. In particular, the evidence suggests: / GoE is willing to reform (medium): The Government maintains an ambitious set of plans for reform over the coming 12 months (e.g. implementing VAT, two new cash transfer programmes). The credibility of these plans rests on actions that have been taken in the past 12 months, including reduction in energy subsidies, the positive IMF article IV review and the upgrading of Egypt’s sovereign rating). / Some of the new GoE policies are based on sound international evidence (medium). The benefits of conditional cash transfers are well documented in the international evidence. A 2012 DFID funded systematic review[13] concludes that (CCTs) lead to a rise in overall household consumption, increase investment in productive assets, reduce child labour and increase school attendance. There is also increasing evidence that the use of citizen feedback loops and participatory monitoring and evaluation can provide rich insights into programme effectiveness and impacts, and also contribute to enhancing the accountability of the programme, strengthening state-citizen relations[14]. / The UK has a strong reputation for economic support (medium): Our work through the Arab Partnership and other ODA programmes such as the £20m Newton-Mosharafa research and innovation fund, show that UK advice and expertise is actively sought and appreciated. However, the evidence for accountability as the means to support is more limited, as discussed in a recent ODI discussion paper[15]. / Option 2 entails three strands of cooperation (A, B, C): / A. Technical support to social and economic line ministries (£300,000) / This builds on the work of the Arab Partnership Economic Facility which has enabled us to gain access and trust with the Ministry of Finance (MoF) and the Ministry of Trade and Industry. The Ministries of Social Solidarity (MoSS) and Investment (MoInv) have also both expressed a strong interest to work with us and learn from UK experience. / The technical assistance would be in support of those policies, currently driven by Egyptian policymakers, where we believe they may transform the lives of ordinary Egyptians, and the UK has quality technical advice to offer. More specifically, our policy work has 2 primary objectives: i ) Support a better investment climate in Egypt, and ii) Support Macro-economic stability / Objective 1: Supporting a better investment climate: In 2014-15, the Better Regulation Unit made 3 visits to Cairo to offer 4-day trainings to the ERRADA team inside the Ministry of Trade and Industry. The feedback on their training has been positive, with a desire to see this happening more regularly. / Options for specific activities include: / Support ERRADA team in taking a policy reform from appraisal to implementation. For example, the team has already advised on how to do a stakeholder consultation on the new franchising law. The next steps would be supporting the ERRADA team as this law is enacted, and implementation begins. / Build the capacity of the ERRADA team through specialist skills. For example, there is a lot of desire within ERRADA, amongst the economists, to learn the skills of cost benefit analysis. It is a tool used to great effect within the UK Government Economic Service, and something the team would benefit from. We would offer a 2 week secondment shadowing an economist in the BRDO team in Sheffield. There are 2 economists qualified to learn this in the ERRADA team. / A policy discussion on ‘deliverology’. Much of the focus on the better regulation unit is around reducing and rationalising regulation to support the delivery of public objectives, and better functioning markets. Part of this includes expertise on how to deliver public services (the BRDO unit migrated from the initial PM delivery unit in cabinet office). They would be well placed on leading a public debate around delivering health/education services in Egypt. / Support ERRADA’s communications work to advocate for evidence based policy across Egyptian Government. ERRADA is establishing satellite units across line ministries, intended to rationalise regulation within these ministries. Given their limited mandate, they will need support to make the case for a significant behaviour change. / Objective 2: Supporting Support Macro-economic stability: In 2014-15, we built a strong relationship with the Ministry of Finance, and successfully promoted a number of important policy priorities. This remains arguably the best entry point to support macro-economic stability, in a ministry led by a competent minister willing to work with us. / Options for specific activities include: / Continuing the capacity building of the Public Private Partnership unit. They have taken foundation training, and a more advanced course on financial modelling. But they still need support on legal aspects of contracting, as well as advocating within ministries on the use of PPP’s through their satellite units. Courses can be delivered in the UK or in Egypt. PPPs are one way for Egypt to fund its infrastructure without worsening the fiscal deficit. / Performance based budgeting to support service delivery. The Government has a constitutional commitment to increase spending on health and education to 10% of GDP from the current 7%. There is a risk this increase is absorbed by increasing salaries, and other measures that don’t lead to improved outcomes. The Ministry of Finance needs, and is willing to, lead the effort to demand that funding is results based (ie linked to improvements in learning and health outcomes). / Infrastructure planning. In the same light as the earlier point on performance budgeting, the ministry of finance has an interest to see that the considerable infrastructure currently being built by the Sisi led Government yields the maximum return to Egyptian economy. But to do so requires integrating the various standalone projects into a single coherent plan that links roads, public transport, schools and hospitals in a way that build liveable communities. The UK has expertise, and Infrastructure UK are willing to visit Egypt to advise on this. / Capacity building and training for Customs. Egyptian customs unit are vital to the screening process to ensure goods are taxed at entry, but are notoriously incompetent. DFID (through the FACT team) has an agreement with HMRC that allows HMRC specialists to be deployed in DFID priority countries to advice on building local tax systems. This includes access to a number of specialist training courses offered by HMRC to carefully selected individuals from developing countries. / Rapid response facility: Egypt remains a rapidly changing context. In order to be effective, we need to adapt and respond to emerging priorities. Over a period of time, and in the context of a 4 year engagement, we should push for more strategic engagement. But over the next 12 months, we should remain open to responding to good new ideas that emerge. / B. Increased accountability of public expenditure (£500,000) / The Egyptian National Competitiveness council (ENCC) follows the model of the Institute for Fiscal Studies in the UK, and is an independent think tank that undertakes analysis and offers policy recommendations focusing on better public financial management. It was selected as a partner under the Arab Partnership but implementation was delayed due to changes in the NGO registration rules in Egypt. This programme is an important pillar of balancing our support to the Government by having a credible challenge function working from the outside. TheENCC is led by a former Deputy Minister of Finance and offers a well-connected yet constructively critical actor to promote accountability. / The work plan agreed with the UK is primarily about promoting more transparent and more accountable public financial management. Their approach involves identifying public champions of reform, and arranging seminars, studies and media coverage to target carefully crafted policy messages to these policy makers. / C. Targeting support directly to the poorest Egyptians (£950,000). / The most exciting reform taking place in Egypt is around providing better targeted public support for the poorest, in the form of fewer untargeted subsidies, and more targeted cash transfers. This work is being led by the Minister of Social Solidarity, and already has the support of the World Bank in the form of a $400 million performance based instrument that reimburses Government based on outreach and efficacy. / The support to poor Egyptians comes in the form of 2 new Government led national programmes, Takaful (conditional) and Karama (unconditional). These programmes will benefit 1.5 million poor people by the end of 2017 through three roll-out phases (waves). Takaful Program beneficiaries are poor households with children under 18, while Karama beneficiaries are poor elderly (age 65 and above) and poor persons with severe and permanent disability. / In addition to supporting the state, we propose to support Alfanar, in support of an innovative non-state led model of targeted support. Alfanar operates exclusively in one of the poorest regions of the country (Minya, Upper Egypt), working exclusively with female headed households. Their work focuses around i) empowering women directly, through providing finance, technical advice and support in running small enterprises, and ii) building women’s awareness of what public services they have a right to demand, including direct support and liaison with local Government in providing such required services. / Alfanar is a model that was supported under the Arab Partnership in 2013-14, and has demonstrated a proven record of success. It was arguably the most promising of the pilots that were tested under the Country Impact Fund, and scaling this up is well worth the UK investment. / Theory of change / The approach being proposed under this business case rests on the basic premise that our effort works best when we simultaneously support the state, challenge the state and provide targeted (state and non-state) led support to the poorest, most vulnerable Egyptians. / The ultimate contributor to stability will be the restoring of a social contract, where the state is able to deliver services instead of public sector jobs and subsidies. But in order to deliver services, the state needs a better handle on managing public resources. Hence Public Financial Management (PFM) and service delivery are themes that run across this business case. / Technical appraisal / Social appraisal / This programme will have a strong theme of inclusion. In the past, mega projects in Egypt have resulted in huge waste of public expenditure and often what benefits there are have been captured by the elite through deliberate intent, poor design or corruption. Many of the new resorts and cities and housing complexes have been built exclusively for the rich and politically connected or have been so poorly designed so as to exclude the vast majority of the population, e.g. by pricing the housing units, lack of jobs and public transport. Although the rhetoric of the new Government is of inclusion, there is a substantial risk that the many new infrastructure and real estate schemes will result in similar outcomes without a better integrated planning process and analysis on the social implications of infrastructure programmes. This will be a part of this technical assistance. / On other issues of economic governance, a strong gender lens will also be brought in. This could be through assisting the MoF with gender budgeting or the Ministry of Trade and Industry or MoSS with analysis and advice on the specific barriers to women and youth participation in the labour market or access to finance. / The complementary work, through the Governance Strand, to broaden parliamentary and public awareness of financial issues would also include a core component of how resources are allocated, who benefits and what more can be done to enhance the impact on different groups. The analytical pieces on the consequences of legislation and budgets will have a gender focus as one of their themes. / Conflict Sensitivity / This programme should make a direct contribution to improving Egyptian Stability. Through ENCC’s work on accountability we will also have a connection to the communities affected by the reforms, and this connection will provide an avenue for monitoring and assessing any potential harmful impact. Ensuring that we are doing no harm will be a key part of our monitoring strategy, including ensuring that we are not unintentionally contributing top strengthening the elite’s control of the economy. / All our focus areas we will be looking to reduce the barriers for marginalised groups but testing for potential negative consequence will form a key part of the terms of reference for our implementers. / Climate and environment appraisal / As a policy intervention, we expect no major impacts on climate or environmental objectives. Shortages of Government resources, especially foreign currency, has led to fuel shortages. For many subsidised energy-intensive industries, this has caused considerable dislocation. Under pressure from this lobby, and despite a Minister of Environment and civil society campaign, the Government has authorised the introduction of coal to power plants and some factories. The Government is clear that it wants to expand renewable energy to 15% of its mix by 2020 and has a number of IFI-funded programmes underway in this regard. It will be a slow and difficult process but in the long run, reducing energy subsidies will make these energy-intensive industries untenable or at least more efficient. While the economics of climate change could be an area of focus under the policy component, this would need to respond to a desire from the GoE to focus on this, and be based on a credible plan put forward by credible counterparts. / Economic appraisal / The design of this programme does not lend itself to a full cost-benefit analysis or the calculation of internal rates of return: the choice of Ministries and areas for support using technical assistance will be determined during the initial three-month inception phase. During this design process, the benefits and costs of providing technical assistance to different institutions will be considered to determine how the resources available can have the biggest impact. / One of the primary benefits of this programme is the continued and strengthened working relations between HMG and the GoE. Although difficult to quantify and value, a discrete set of technical assistance with a few key ministries and public institutions will allow HMG to identify potential areas for future engagement which could lead to increased bilateral engagement including trade and investment opportunities. / Regardless of which Ministry or sector is chosen, the beneficiaries are the range of Egyptian institutions, both governmental and civil society, which will receive technical support and capacity development. By improving the policy of the Egyptian Government and the allocation of their public resources, the assistance will ultimately benefit the Egyptian people who own firms, supply labour or consume. Under strand b, greater transparency and accountability of public finances will ultimately lead to greater efficiency and effectiveness in public finances. The ENCC will benefit directly from increased capacity to implement programmes and delivery quality policy advice. / Value for Money measures / The activities being proposed are all ones where a small amount of UK investment is influencing something much greater, whether its overall Egyptian Public Spending (£ billions). / Using DFID’s 3 E’s framework to assess value for money, we will track the following unit costs over the course of this programme: / Economy / Daily fee rates of contractors providing technical assistance. / Unit cost of accommodation, flights and venue expenses for trainings. / Efficiency / Choice of area/Ministry for TA based on largest potential impact. / Effectiveness / Cost per job created. / Cost and economic benefit of each £1 transferred to the poor. / Throughout, we will ensure that these unit costs are consistent with the average across DFID, and consistent with all DFID travel and expense policies.
4. Commercial Case
Delivery of the preferred option / We propose one new contract (£300k, through PEAKS framework), amending one existing contract (£500k with ENCC), one new Externally Financed Operation (EFO) (£600k with the World Bank), and one new accountable grant (£350k through Alfanar). We would not transfer any funds to the Egyptian Government given the fiduciary risk. / The technical assistance component will be delivered through a single contract for £300,000 that will be procured through the PEAKS framework. The consortia have been pre-selected on the basis of experience, reputation and competence, and we would benefit from an additional round of screening as we conduct the full selection process. We will support PEAKs to supplement the TA facility with HMG experts and practitioners where they are available. / The accountability strand (B) will be delivered by the Egyptian National Competitiveness Council (ENCC), with whom we have an existing agreement (under the Arab Partnership). The project was awarded to ENCC at the start of 2014/15 but due to the state’s slow and opaque process for approving foreign funding, ENCC only received approval in early 2015. They have not been able to undertake most of the work as originally intended but are now ready to deliver. They are a credible organisation, led by a former Deputy Minister of Finance and delivering well on a similar type of US-funded project around food subsidy reform and food security. / Thirdly, the cash transfers component of strand C will be delivered through an EFO with the WB. The EFO is the most appropriate instrument for DFID and the WB to partner on for a project of this size. The work will be in support of the goals of the Strengthening Social Safety Nets programme, a $400m performance based loan the World Bank has agreed with the Government of Egypt. The World Bank will lead the work, with reporting synchronised to the reporting of their $400m loan. DFID will attribute a proportionate share of the results of this, and will participate in bi-annual reviews of the programme, as well as other programme activities. Copies of final reports funded under the DFID EFO will be shared, as will 6 monthly narrative reports and final copies of review aide memoires. A draft work-plan has been shared with DFID, which focuses on beneficiary feedback and grievance redressal mechanisms. / The work with Alfanar under strand C will be underpinned by an accountable grant. Alfanar is a tested and trusted partner under the Arab Partnership, and the new agreement with them will build on the previous partnership model of the Arab Partnership. / 4.2 Value for Money in contract management / The contract for Strand A (technical assistance) will comply with the management guidance as set out under the relevant framework (PEAKS). In particular, our experience has been that the use of output based contracts, with relevant milestones provides the right incentives, and the right level of oversight given the types of activities being undertaken. / The key costs drivers are: / Security situation in Egypt. / Complexity of the assignment and the size of the team. / The level of technical oversight and due diligence to be borne by DFID, and the extent required from the contractors. / We will work closely with Procurement and Commercial Department (PCD) to ensure we minimise costs and get the best value for money from the contract.
5. Financial Case
5.1 Programme Budget / This proposal is for a total of £1.75 million to be funded from the CSSF allocation to Egypt. This will be a one year programme. / We would propose a budget breakdown as follows: / A - Technical assistance to support economic policies (£300,000). / B - Increased citizen accountability on public spending (£500,000). / C - Support to the state on cash transfers (£600,000) and support for inclusive development (£350,000). / This budget is required to deliver the programme’s expected results. The amount allocated to the technical assistance component enables us to provide in-depth support in a small number of focused policy areas. Experience from the Technical Support Fund under the Arab Partnership was that slightly longer-term intense consultancies and secondments enabled the consultant or HMG staff to build trust with Egyptian Government counterparts. The budget allocated to this component provides the programme with the flexibility to utilise both private sector consultants and HMG experts for more intense periods. / Detailed proposals and budgets have been provided by Alfanar, the World Bank and ENCC to support these strands. A terms of reference will be developed to cover the policy work. / 5.2 Flow of funds / Under Strand A, money will be provided to the relevant contractor on a reimbursable basis, directly from DFID upon receipt of satisfactory completion of work. / Under Strand B, funds will flow directly from DFID to ENCC. / Under Strand C funds will flow directly from DFID to WB or to Alfanar. / 5.3 Costs to be incurred directly by DFID / A portion of the costs will be borne by DFID. These would include project management support (0.2 B2) and some proportion of regional advisory time. The CSSF is funding two DFID secondees in British Embassy (BE) Cairo (A2 Head of Programmes and A2 Economist) as well as a B1 Programme Manager and B2 programme official. / 5.4 Cost profiling and forecasting - / ........................................2015............................................. ....................2016.................. / Month Jun Jul Aug Sep Oct Nov Dec Jan Feb Mar Total / Strand A - Technical support / (£’000s) - - - - 50 50 50 50 50 50 300 / Strand B - ENCC / (£’000s) 60 60 60 60 60 60 60 80 500 / Strand C part 1 - WB / (£’000s) 300 150 150 600 / Strand C part 2- Alfanar / (£’000s) - - - 50 50 50 50 50 50 50 350 / Total / (£’000s) 1,750 / 5.5 Financial and Fraud risk assessment / Programme management oversight is to be provided by the CSSF Programme Manager, working to the supervision of the Head of Programmes, BE, Cairo. The management and reporting procedures will be consistent with those of the FCO funds managed at post. Due diligence will be provided by the DFID MENAD programme manager. / 5.6 Monitoring, reporting & accounting for funds / The three suppliers will provide an initial budget, and financial statements following completion of activities alongside an invoice for payment on a quarterly basis. / The World Bank component will comply with the articles of arrangement under Externally Financed Operations on reporting schedule and financial management. We will receive an Annual Progress Report and/or a Completion Report, plus other narrative progress reports on a six-montly basis. The Bank will not provide any form of financial reporting on EFOs, nor reporting on actual expenditure of the EFO contribution because the EFO funds will be commingled with Bank budget. / 5.7 Financial accounting considerations / We do not anticipate the purchase of assets through this programme.
[1] Verme, Paolo, Branko Milanovic, Sherine Al-Shawarby, Sahar El Tawila, May Gadallah, and Enas Ali A.El-Majeed. 2014. Inside Inequality in the Arab Republic of Egypt: Facts and Perceptions across People, Time, and Space. World Bank Studies. Washington, DC: World Bank. doi:10.1596/978-1-4648-0198-3. License: Creative Commons Attribution CC BY 3.0 IGO
[2] Egypt's Economic Predicament: A Study in the Interaction of External pressure, political folly and social tension, By Ğalāl A. Amīn
[3] Assaad, R., Nazier, H. and Ramadan, R. (2014) “Estimating Poverty and Inequality in the Absence of Consumption Data; An Application to the Egypt Labor Market Panel Survey.” Mimeo.
[4] The Military Crowds Out Civilian Business in Egypt, Ahmed Morsy, Carnegie Endowment for International peace, 2014.
[5] See Article IV assessment, January 2015, IMF
[6] Household Income and Expenditure Survey (HIECS), 2013, CAPMAS
[7] Females’ Labor Force Participation and Job Opportunities in the Middle East , Ida A. Mirzaie
[8] Empowering the Third Billion: Women and the World of Work in 2012, Booz and Co.
[9] Shanta Devarajan, A new Social Contract for Egypt, World Bank chief economist papers, 2015.
[10] EGYPT - TOWARD A MORE EFFECTIVE SOCIAL POLICY: SUBSIDIES AND SOCIAL SAFETY NET, World Bank 2005
[11] Empowering the Third Billion: Women and the World of Work in 2012, Booz and Co.
[12] World Bank Project Appraisal Document Egypt - Strengthening Social Safety Nets.
[13] Kabeer N, Piza C, Taylor L (2012) What are the economic impacts of conditional cash transfer programmes? A systematic review of the evidence. Technical report. London: EPPI-Centre, Social Science Research Unit, Institute of Education, University of London.
[14] Samuels, F. and Jones, N (2013) Holding Cash Transfers to Account: Beneficiary and Community Perspectives, ODI, London
[15] E.g. Welham, Krause & Hedger (2013) Linking PFM dimensions to development priorities, ODI

6. Management Case
6.1 Management Arrangements / This programme will be DFID led, managed through the North Africa and Regional Team in MENAD and from Cairo by the CSSF Economic Advisor and programme staff. The Senior Responsible Owner (SRO) will be the CSSF Economic Advisor based in Cairo, currently Zahir Dasu. / Oversight will come from multiple sources. In the first instance, line management oversight will come from the Head of Programmes at the British Embassy Cairo, immediate line manager of the CSSF economic advisor. Similarly, the reporting line into DFID will be to the head of the North Africa Regional Team. Technical oversight will come from the North Africa regional economic advisor. / Final accountability for this work lies with the CSSF regional board. Since the work is below £2 million, operational decisions can be signed off by the CSSF country board. While the CSSF boards will be the final decision makers on all aspects of CSSF work, the DFID representative, head of MENAD will oversee the DFID position during board meetings. Additional support will be provided by the MENADgovernance, social development, private sector development and conflict advisers. / Roles and responsibilities / On a day to day basis, the CSSF Economic Advisor will: / Management implementers and be the first line of communication with them. / Build relationships and influence economic policymakers at highest level. / Ensure reporting is accurate and on time (including the completion report). / Undertake frequent monitoring of the programmes, incl. site visits. / Arrange visits for DFID management or technical teams to view/monitor projects and meet implementing partners. / Meanwhile, the consultants contracted to conduct the technical assistance facility work will: / Convert approved concept ideas (including those set out in this business case) into detailed proposals based on a standardised template which includes basic information such as high level champion, cost, and source of technical expertise. The approvals model we will follow will be as is the case with the DFID funded IFUSE programme. / Preparing these proposals will require proactive contact with policymakers at the working level. Proposals will need to be detailed enough to be deliverable. / Proposals will need to approved by the technical review team, and the head of programmes. Once approved, the role of the consultants depends on the nature of the activity: / For trainings: Arrange the trainer, arrange all logistics, book the venue, provide materials and take feedback from participants. / For technical studies: A complete report and presentation. / For visit of HMG expert. Arrange flight, visa, hotel, and pay them if needed. / All other strands of this work (World Bank, Alfanar and ENCC) will be delivered by the contracted partner, and not require day to day management by DFID. Best practice will be followed regarding programme management and oversight of implementers. / 6.2 Monitoring and Evaluation / The programme will draw upon the regional evaluation fund at an early stage for a short-term consultancy to help us set up an overarching approach to monitoring to ensure the most effective approach to monitoring TA and accountability programing. Alternatively we could use a 10% contribution from a DFID Evaluation Adviser to assess overall performance. / For the technical assistance facility each intervention/policy engagement work strand will have its own output indicators and the supplier will report against progress. At the six monthly and one year point these reports would be consolidated and overall progress against the outcome indicators assessed. / ENCC and Alfanar will report on progress and expenditure quarterly against agreed logframes and deliverables. We will also undertake surprise spot checks of partners’ financial records and attend as many events as we are able, ensuring that we see the project delivery and have the opportunity to gain beneficiary feedback. The PCR at the end of the programme will be completed jointly by the CSSF economist and the Nort Africa Regional economist. Lessons learnt will be used to shape future programmes. / The World Bank component will be bound by the normal World Bank terms of agreement under Externally Financed Operations. Bi-annual narrative reports will be provided. Other terms are as set out under the World Bank work-plan proposal. / Risk and mitigation / The primary area of risk is that the Government fails to adjust its economic decision making. Although some positive steps have been taken to cut fuel subsidies, reform food subsidies and bring in a new investment law, the March Economic Conference exhibited a return to large-scale infrastructure projects announced with little planning or consultation. Rights groups have also condemned some of the measures to protect and encourage investors as detrimental to transparency and legal accountability. However, the dependence of the reforms on a few key ministers, does also represent a risk to the programme if they are removed, or give up because their efforts are frustrated by an entrenched bureaucracy. To mitigate this risk the inception phase will be used to determine which areas GoE is more likely to make progress and focus technical assistance there. This will also be monitored through the quarterly review process. / The second area of risk is around the programme being allowed to operate by the various state bodies required. This is particularly true of the complementary work under the parliamentary and media strands of the governance pillar, both areas where donors have found it hard to gain traction and space. ENCC has MoSS approval to begin the project (after a 9 month wait) but will require ongoing tacit support for its engagement and advocacy work, so will be weakened if progress on the complementary governance programme is less than expected. The choice of partners, ENCC and private sector consultants, were selected to mitigate this risk, as the former have approval to undertake these activities and the private sector is not governed by the more restrictive NGO Law. Further, we e will remain engaged with the various line ministries and the Ministry of International Cooperation through the Embassy and senior visitors to sustain access. / Risk Prob Imp Mitigation / 1. Reduced political will to reform Medium High - Political pressure through FCO, HMA etc. / - Pressure through regional players (UAE/Saudi). / - / 2. Administrative ability to operate Low high - Maintain transparent UK operations within bounds of MOIC requirements. / - Regular briefings and dialogues with senior counterparts to brief on progress. / 3. Major human rights abuses by Government of Egypt Medium Medium - Maintain clear UK partnership principles. / - Be prepare to work exclusively outside of State. / - Clear public communications: The UK does not give financial aid to the Government of Egypt. / 4. Security situation in Egypt deteriorates. - Clear duty of care guidelines to implementers.

Annex A: Summary of log-frame indicators

Impact: Better and more accountable economic policies in Egypt.
- Total state spending towards social sectors (health education and cash transfers)
- Number of households receiving cash transfers under the Takaful and Karama schemes (and proportion of those below the poverty line).
Outcome: A better understanding of economic policies, and improved public understanding and support for implementing difficult reforms.
- Proportion of recommendations implemented through policy support work.
- Satisfaction with the quality of trainings provided
Output 1: Technical advice to support the state in delivering reforms
- Number of civil servants trained
- Number of high level champions trained on better Public Financial Management
- Number of technical advisory visits that take place
Output 2: Increased citizen accountability on public spending.
- Number of citizens polled on their views and perceptions around corruption
- Number of publicly broadcast TV debates on anti-corruption
- Number of workshops on international best practice on tackling corruption.
Output 3: Supporting state and non-state led models of inclusive growth
- Number of beneficiaries surveyed and feedback obtained under the cash transfer programmes.
- Number of social enterprises develop crowd-funding videos
- Number of women receiving financial literacy training in poorest districts of Upper Egypt.
Annex C: References.