Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: United Nations Peacebuilding Fund
Programme Value: £63m (2011 – 2016)		Review Date: October 2015
Programme Code: 201064	Start Date: August 2011	End Date: August 2016

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	A	A	A	A
Risk Rating	M	M	M	M

Summary of progress and lessons learnt since last review

This annual review has been able to take advantage of the recent expert panel report of the UN Peacebuilding Architecture Review. This found that the Peacebuilding Fund ‘play[s] an important role in providing financing to countries emerging from conflict’, and has been ‘rapid, flexible and provided funding for crucial interventions that were too “risk-laden” for more conventional funding streams’. The PBF is a unique financing instrument, created to address a ‘market failure’ in the UN and international donor system by providing quick, flexible finance when fragile states need it most to progress critical peacebuilding interventions.

The nature of this role is that the PBF operates in high-risk environments, and frequently has to re-programme or suspend its activities as part of an active risk management strategy. In the reporting period, this has included suspending activity in South Sudan, Mali and Yemen due to relapses into large-scale violence, and re-orienting a number of activities in Sierra Leone, Liberia and Guinea, where the trust built with local communities through peacebuilding interventions was used to support the Ebola response. The risk associated with PBF’s interventions is most sharply illustrated by the murder of their local coordinator in Guinea, Mr. Thierno Alioune Diaoune, in February 2015.

Despite these challenges, the PBF continues to deliver good peacebuilding results on the ground in a wide range of countries. PBF-funded projects kept the police on the streets of CAR during a tense moment in the peace process by paying salary costs, and helped demobilise hundreds of ex-Seleka fighters. In Guinea, PBF peacebuilding projects delivered Ebola public health information in the troubled Forestiere region. And in South-Central Somalia, the PBF provided catalytic finance to a stabilisation strategy that is establishing interim administrations and delivering security and services in 25 newly recovered districts.

The Multilateral Aid Review in 2011 identified three reform priorities for the PBF, around results-based management, risk management and alignment with country systems. The 2013 MAR update identified improvements in all three areas, and these have continued in the reporting period, in particular with the development of a new ‘risk marker’ allowing a differentiated approach to programme management based on risk level. Nevertheless, these remain key challenges, highlighted by the Peacebuilding Architecture Review recommendation that the PBF focuses on its comparative advantage as a risk-taking and flexible ‘investor of first resort’.

The Peacebuilding Fund is well-positioned following the UN Peacebuilding Architecture review, which recognised its important role as a flexible, risk-taking funder. The main thrust of the review was that peacebuilding should be less a siloed activity in the UN, and more a thread that runs through an integrated UN approach at country level. Although it is far from a silver bullet, the PBF is well placed to support this ambition, given its focus on driving coherence across the UN, and its ability to provide finance to a wide range of UN partners, contingent on their ability to work together. Going forward, the recommendations set out below will help to further strengthen core oversight and management functions, delivering the core recommendation of the Peacebuilding Architecture Review that the PBF should play to its strengths as a ‘funder of first resort’ for peacebuilding.

Securing sufficient donor finance continues to be a challenge for the PBF. The UK’s burden share has decreased in recent years, from over 50% in 2013 to around 30% in 2015. The UK will continue to work with the PBF, building on the recommendations of the Peacebuilding Architecture Review, to broaden and deepen the donor base whilst sustaining the effectiveness of the Fund.

Summary of recommendations for the next year
Capacity of country-based UN Agencies, Funds and Programmes: build on the recommendations of the Peacebuilding Architecture Review to strengthen country-level delivery, in particular ensuring UN planning processes include a peacebuilding lens and engaging with the findings of the planned evaluation of the peacebuilding capacity of UN agencies, funds and programmes.

Partnership with World Bank and IFIs: build on existing work with the World Bank to deliver the Peacebuilding Architecture Review vision of increased strategic alignment between the UN and IFIs on peacebuilding.

Risk and Gender markers: Ensure implementation of the new risk and gender markers, and continue to use these to ensure a flexible and active approach to programme management.

Revision of logframe: UK and PBF to revise the logframe to ensure alignment with the new Performance Management Plan and new risk and gender markers.

Complete revision of PMP and include indicators in the revised plan to track strengthening of country-level Joint Steering Committees

Continue to strengthen M&E functions, using the new unit to ensure country-level M&E processes are as robust as possible.

Participatory conflict analysis: consider expanding the participatory approach piloted in Madagascar.

Country alignment: ensure robust lesson learning from the innovative approach in DRC, and consider applicability elsewhere.

Value for Money: Continue to strengthen understanding and implementation of VFM at country level, including through close accompaniment of Joint Steering Committees where needed.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3719316.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3717402.xls

Outline of the programme

Context
Preventing violent conflict and building peace are UK international priorities. Whilst the UK addresses such challenges bilaterally, we recognise that we cannot do so alone. By supporting UN agencies and secretariat bodies, the UK has a wider reach and impact than it can achieve bilaterally.

While building peace is primarily the responsibility of national actors, the international community can play a critical role. However, too often the international response has been too slow, failing to deliver tangible results at crucial moments.

The UN Peace Building architecture was established to address better the special needs of conflict-affected and fragile states, help them in their recovery and reconstruction efforts, and thus lay the foundations for sustainable development. These instruments are the Peace Building Commission (PBC), the Peace Building Support Office (PBSO) and the Peace Building Fund (PBF). Together, their mandate is to help foster peace in countries emerging from violent conflict through well-co-ordinated international support that brings development, diplomatic and security actors together behind joint priorities and objectives.

The PBF’s mandate is to help build peaceful societies by providing fast and flexible funding for UN peace-building efforts around the world. To achieve this end, it focusses on four themes:

1. Implementation of Peace Agreements and Political Dialogue
2. Promotion of Coexistence and Peaceful Resolution of Conflict
3. Economic Recovery and Immediate Peace Dividends
4. (Re-)building Essential Government Services and Infrastructure

The recent UN Peacebuilding Architecture panel report found that given the PBF was delivering well, in particular addressing the global peacebuilding ‘market failure’ by acting as a rapid, impactful, risk-taking ‘investor of first resort’. The PBF fills a gap in the UN system by helping when other funding sources are not yet available, for example immediately after a peace agreement has been reached or in countries with limited international aid such as the Central African Republic or Guinea Bissau. The Fund can also support interventions in countries that are further along in their peace-building process but which need urgent support to address unexpected challenges that could seriously threaten the road to sustainable peace, for example Burundi. The PBF is intended to be “catalytic” in helping to jump-start peace-building initiatives or un-block them when they are stuck.
The PBF does not implement projects itself but acts as a system-wide financing instrument for the UN specialised agencies, funds and programmes. Priorities are developed at country level by a Joint Steering Committee chaired by the highest-ranking UN official and involving representatives of all UN agencies and of national actors. The PBF is managed by a small team within the PBSO headquarters in New York. The fund is administered by the Multi Partner Trust Fund Office (MPTFO) in UNDP.

Outline of the programme
The UK has contributed US$140 million to the Peacebuilding Fund since its inception in 2006, amounting to approximately 22% of the PBF’s overall 2006-2015 budget. A four-year multi-annual funding agreement was agreed in 2011, committing £55m 2011-2015, which significantly increased the UK’s contribution. This support was recently extended for 1 year, to August 2016, with an additional £8 million committed in May 2015 – comprised of £4 million in September 2015, and a further 4 million in February 2016 - taking the current commitment up to £63 million. As part of the UK’s commitment to reduce our burden share, on a calendar year basis, the UK now funds around 30% of the PBF’s budget. This is a significant drop from previous years (2013: 55%; 2014: 48.8%). We have continued to work with PBF to get other donors to increase contributions, an effort which is supported by the recommendations of the Peacebuilding Architecture Review.

The desired impact is that post-conflict societies manage risks of internal conflicts peacefully through enhanced inclusive policy dialogue and commitment to peaceful coexistence.

The expected outcome of UK funding from 2011-2016 is that the PBF addresses critical funding gaps and plays a catalytic peacebuilding role by creating the conditions that enable longer term peacebuilding to take place.

The outputs expected from this PBF support are:

1. PBF reporting demonstrates contributions to peacebuilding and improved and consistent delivery at country level
2. Effective results-based management and reporting on outputs and outcomes at the country level
3. Country systems and conflict-sensitive review criteria are used and supported consistently
PBF responds efficiently to demand with strong financial management.

The UK’s Multilateral Aid Review (MAR), published in 2011, found the PBF represented good value for money and merited further UK funding. However, it also highlighted several weaknesses for which the UK set out the following reform priorities:

- Effective results-based management and reporting on outputs and outcomes at a country and organisation level;
- Consistent use of country systems and conflict-sensitive review criteria; and
- Flexible and effective response to demand, with appropriate risk management.

The MAR was updated in 2013 and found that PBF was making reasonable progress overall to meet these priorities. The forthcoming 2015 Multilateral Aid Review will update this assessment.

The results of the 2015 United Nations Peacebuilding Architecture Review were published in June 2015.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The Peacebuilding Fund continues to deliver real peacebuilding results on the ground in a wide range of countries, including UK priorities such as Sierra Leone, DRC and Somalia. There is a growing evidence base that these interventions support longer-term stabilisation and sustained peace.

The UN Peacebuilding Architecture Review described the added-value of the PBF as being a risk-taking, responsive ‘funder of first resort’. The PBF continues to play this role, addressing a critical market failure in the UN system by bridging post-conflict funding gaps, piloting high-risk high-return interventions, and providing quick finance for key interventions at critical moments in peace processes.

The UN Peacebuilding Architecture Review, based on a number of detailed country case studies, found that PBF interventions have been effective on the ground - for example keeping the police on the streets in CAR. It also noted that the PBF’s speed, flexibility and risk appetite frequently enables the UN system to take peacebuilding opportunities that it would otherwise miss.

The PBF continues to improve its operational performance and effectiveness, strengthening risk management and results reporting, and finding innovative ways to align with national and donor strategies. However, the inherent challenges of this field of work mean that a continued focus on these areas is needed.

As noted in the Peacebuilding Architecture Review, sustainable donor finance is a continued issue. The PBF, with support from the UK, will need to continue efforts to extend its donor base.

Overall output score and description: A, outputs met expectations

PBF performance in output 1 met expectations overall, and exceeded them on for three of the four indicators. This output relates to Fund delivery at country level and is 70% of impact weighting. Outputs 2 and 3 moderately exceeded expectation, and expectations were met on output 4. .

Key lessons
The PBF’s adds value to the UN system by being flexible, responsive and risk taking. This clearly exposes its activities to significant levels of risk in particular contexts, so a flexible and active approach to risk management is central to effective delivery of its mandate. PBF will need to continue to build on the good work progress already made in strengthening and embedding this.

The quality of peacebuilding results in-country is extremely depended on the capacity of UN agencies to design and deliver interventions with PBF finance. In the last year, PBF has strengthened an improved the support it provides to country teams to good effect, for example on issues around M&E. Again, this will need to continue in the future.

Key actions
- UK to consider future funding levels, and continue supporting PBF to broaden donor base.
- PBF to build on recommendations of Peacebuilding Architecture Review to better understand and support peacebuilding capacity of UN agencies in country.
- PBF to continue and strengthen partnership with World Bank and other IFIs.
- PBF to fully implement risk and gender markers, and continue strengthening capacity and understanding of M&E and VFM both centrally and at country level.
- PBF to finalise new Performance Management Plan, and then work with UK to revise logframe in alignment with this.

Has the logframe been updated since the last review?
Yes - indicators for output 1 amended in line with recommendations of last review.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	PBF reporting demonstrates contributions to peace-building and improved and consistent delivery at country level.
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	70%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress (2014 in Brackets)
1.1 Achievement of targets set out in the PBF Performance Management Plan that track whether security sector reforms and judiciary systems have been put in place and are providing services at national and local level that reinforce the Rule of Law	Active programmes meet > 75% of targets set out in the PBF Performance Management Plan.	80% / (2014: 88%)
1.2 Achievement of targets set out in the PBF Performance Management Plan that track whether conflict has been resolved peacefully and in a manner that supports the co-existence of all relevant actors/groups that were involved in conflicts that undermine peacebuilding efforts	Active programmes meet > 85% of targets set out in the PBF Performance Management Plan	96% / (2014: 86%)
1.3 Achievement of targets set out in the PBF Performance Management Plan that track whether youth act as a catalyst for peace and whether youth and other actors benefit from peace dividends including job creation.	Active programmes meet > 85% of targets set out in the PBF Performance Management Plan	100% / (2014: 75%)
1.4 Achievement of targets set out in the PBF Performance Management Plan that track whether essential functions of government institutions are restored	Active programmes meet > 85% of targets set out in the PBF Performance Management Plan	78% / (2014: 91%)

Key Points

Despite the challenges of this reporting period, PBF has met or exceeded most targets, and continued to demonstrate reliable project implementation at country level. Taken as a whole, PBF investments have delivered real peacebuilding results on the ground, particularly around interventions related to conflict prevention and mediation – areas identified by the recent Peacebuilding Architecture Review as important building blocks for the reduction of instability. Some specific country level examples include:

Central African Republic. Kept the police on the streets at the most fragile period by paying salary costs for 3,400 officers, helping to ensure safety and safeguard core government services. Supported demobilization and re-integration through voluntary relocation of more than 800 ex-Seleka fighters from their camps in Bangui to their communities of choice and origin.

Chad. Supported peaceful resolution of 150 local conflicts before they escalated into wider violence. This was enabled by 14 Local Peace Committees, linked to local authorities, and the creation the "Mediateur de la Republique", as well as key economic empowerment projects. .

Colombia. Mass communication campaign supporting peace negotiations and reintegration of ex-combatants. National awareness of ways to support reconciliation process increased to around 30%, and positive attitudes to re-integration increased to 60% in key communities.

Kyrgyzstan. Community based peacebuilding programme has enhanced the conflict resolution capacity of both citizens and their local authorities, and led to increased trust between the two.

Burundi: a national PBF-funded network of over 500 mediators has helped to resolve around 2,500 local conflicts, including adapting to the election-related political crisis of 2015. For example, local mediators helped resolve tensions between protesters and police without violence in Mugongo Manga municipality, and have initiated dialogue to reduce tension between political parties at community level.

Niger: Income generation opportunities and linkages in to conflict resolution mechanisms, have been provided for 1,500 youth (including 300 women) in an area at risk of recruitment into armed groups.

Myanmar: catalytic PBF funding has enabled a Government-led centre for conflict early warning and resolution to start work, nudging policy makers beyond their divisive public positions.

Output 1.3 - on peace dividends - was significantly exceeded. This reflects good performance, but is also influence by a small total number of projects in this area, especially after the suspension of some work in Ebola-affected countries last year.

Output 1.4 was missed, relating to work on restoration of essential government functions. In part, this reflects the fact that as a high-risk ‘investor of first resort’ the PBF is exposed to a relatively high risk of project failure. This risk-taking approach is one of the PBF’s most important features, and the Peacebuilding Architecture Review highlighted its importance in enabling the UN system to bolster peace processes at key moments - opportunities that would otherwise be missed.

PBF continues to take a dynamic and innovative approach. A new monitoring approach introduced in the reporting period encourages regular recalibration during implementation. This has enabled flexibility to deliver results, for example in Ebola-affected countries:
Liberia. PBF-supported land disputes resolution mechanism has built good community trust, resolving 200 cases last year. This allowed it to be re-directed to deliver trusted messaging about the health response to local communities.

Sierra Leone: An existing PBF-funded security sector reform project was rapidly refocused to provide human rights and civilian-relations training for security personnel Ebola checkpoints. NGOs and media monitors reported the absence of any serious abuses at Ebola checkpoints and a reduction of conflicts between citizens and security personnel.

Summary of responses to issues raised in previous annual reviews
Risk Management. PBF has designed a risk marker, which will be introduced in project tracking in future. Risk marker ratings will trigger different approaches to identification of outcomes, monitoring and evaluation. Emerging practice indicates that projects associated with higher risk benefit from more flexible implementation arrangements underpinned by more frequent monitoring. As a result, projects scored as high risk will receive increased monitoring and technical support.

Peace Dividends. PBSO is co-leading with the World Bank a working group (including ILO and UNDP) to build the evidence base on peace dividends. Research and guidance will be completed by end 2015, and all four participating organisations have committed to funding projects utilising the new guidance during 2016.

Gender. Similar to the risk marker, PBF will introduce a gender marker and ensure this is captured within overall project reporting.

Logframe revision: as recommended, reporting has been amended for output 1 so that it reflects only active programmes, excluding those suspended due to a major spike in armed conflict or other circumstances. In the reporting period, programming was suspended in Mali, South Sudan and Yemen, with some programmes also suspended in Ebola affected countries.

Recommendations
Capacity of country-based UN Agencies, Funds and Programmes: As a fund, the PBF is reliant on UN agencies in-country to design and implement programmes. PBF should therefore build on the recommendations of the Peacebuilding Architecture Review to strengthen this relationship, in particular ensuring UN planning processes include a peacebuilding lens and engaging with the findings of the planned evaluation of the peacebuilding capacity of UN agencies, funds and programmes.

Partnership with World Bank and IFIs: As noted above, the PBF has a good partnership with the Bank in its work on Peace Dividends. They should build on this to deliver the Peacebuilding Architecture Review vision of increased strategic alignment between the UN and IFIs on peacebuilding.

Risk and Gender markers: Ensure implementation of the new risk and gender markers, and continue to use these to ensure a flexible and active approach to programme management.

Revision of logframe: UK and PBF to revise the logframe to ensure alignment with the new Performance Management Plan and new risk and gender markers.

Output Title	Effective results-based management and reporting on outputs and outcomes at the country level.
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress (2014 in brackets)
2.1 Quality of PBF results framework and country level reporting	> 75% of funding recipient agencies use PMP relevant indicators as a reference for a project based performance monitoring and reporting on results	81% / (2014: 81%)

Key Points

Findings from the 2013 Global Review of the Peacebuilding Fund, as well as the 2015 Peacebuilding Architecture review call upon PBF and PBSO more generally to seek opportunities for helping in-country partners increase their capacity to design and implement peacebuilding programming. In response, PBF has scaled up its accompaniment of country-based partners, particularly in the programming design phase, to ensure that programming is focused on appropriate outcomes and outcome indicators from the beginning. In Madagascar, for example, PBF’s programme officer and M&E officer built consensus on meaningful but achievable outcomes through in-depth and participatory discussions with partners.

PBF began revision of its Performance Management Plan in the fourth quarter 2014, with a series of internal reviews that culminated in a two-day widely consultative external workshop that included colleagues from World Bank, UN Secretariat, Agencies, Funds and Programmes, and peacebuilding NGOs. Since then, PBF has been refining its outcomes, theories of change and indicators for each of its thematic focus areas. PBF anticipates finalising the PMP by October 2015, in consultation with the UK and other key stakeholders. This has been slightly slower than anticipated in order to insure a fully inclusive process that gets the buy-in of all relevant partners.

In addition to PBF support from headquarters, the Fund has launched efforts to strengthen the in-country bodies that oversee peacebuilding implementation, from PRF Joint Steering Committees to Executive Committees set up to accompany IRF packages, with an eye toward improving programmatic results. In Somalia, for example, PBF is joining other donors in channelling its investments through the Somalia Development and Reconstruction Facility in order to line up behind the New Deal Compact.

Summary of responses to issues raised in previous annual reviews
Strengthening Joint Steering Committees. In November 2015, PBF and will host their third annual global workshop, bringing together government, civil society, UN, and donors. As in past years, the workshop is divided between a focus on politically-informed priority settings and oversight, and training on a technical aspect of implementation. This year focus on accountability and the oversight function of JSCs.

Workshops/training. On training, in addition to a global face-to-face training, PBF also is partnering with PeaceNexus to produce on-line training tools that can be paired with a comprehensive year-long experiential learning approach for country partners.

Results of improvements in DM&E. PBF is in the early stages of implementing its expanded monitoring and evaluation function and is still recruiting necessary posts to fully operationalise the plan. The UK is supporting a JPO position as part of this.

Recommendations
Complete revision of PMP and include indicators in the revised plan to track strengthening of country-level Joint Steering Committees

Continue to strengthen M&E functions, using the new unit to ensure country-level M&E processes are as robust as possible.

Output Title	Country systems and conflict-sensitive review criteria are used and supported consistently.
Output number per LF		3	Output Score	A+
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 - % of PRF countries where in-country systems are used	> 75% of new PBF programmes utilise in-country systems	86% / (2014: 83%)
3.2 - % of Priority Plans for Peacebuilding approved with programmes designed consistent with conflict analysis	100% of Priority Plans for Peacebuilding approved with programmes design consistent with conflict analysis	100% / (2014: 100%)

Key Points

The PBF continues to demonstrate its commitment to maximizing its use of country systems. The Fund is using country systems wherever it is possible to do so while still ensuring value for money (strategic programming). In practice, this means aligning funding to national strategies and linking Joint Steering Committees to national structures. Of the 14 countries where PBF has programmatic investments, only two are not utilising in-country systems: Comoros and Kyrgyzstan. In both cases, an overarching national peacebuilding strategy does not exist.

In DRC, for example, PBF is supporting Government and MONUSCO’s stabilization priorities in the east through an innovative funding approach, allocating $8 million in funding immediately, with an additional amount through matching contributions from other donors. As of late August 2015, PBF’s matching incentive has leveraged financial support for the ISSSS Trust Fund by two additional donors. This PBF support is fully aligned to the revised MONUSCO International Security and Stabilization Support Strategy (ISSSS) and the Government’s Provincial Stabilization Strategies and Action Plans, which identify five pillars of intervention, adapting them to the specific conflict drivers and contexts of 13 prioritized geographic zones in the east. DFID country office feedback has praised the PBF approach in DRC for both its political sensitivity and its success in catalyzing other donors. This approach pre-empts the recommendation of the Peacebuilding Architecture Review that PBF should catalyse larger country-level pooled funding mechanisms.

Conflict analyses to underpin new PBF programming is now standard practice, though the form such analyses takes is driven by local context and timing. In Liberia, for example, a PBF support mission in April 2015 as the Ebola crisis was winding down resulted in a commitment by UNMIL and its partners to undertake a conflict analysis in light of new challenges and opportunities for peacebuilding resulting from the historic health crisis.

In Madagascar, PBF and partners piloted a new approach for a more inclusive utilisation of conflict analysis. Too often, the local communities who are prioritised by peacebuilding interventions are not consulted prior to their selection. The more participatory approach employed in Madagascar was successful in correcting this and has informed the design of new, more inclusive programmes.

Summary of responses to issues raised in previous annual reviews
Use of in-country systems. As outlined above, this is predominantly about alignment and coordination with existing national plans or frameworks, and established government decision-making and reporting structures. In some contexts, the fund has additionally engaged through national financial systems, as in Central African Republic in 2014, with the delivery of salary support to security actors through the National Treasury.

Recommendations
Participatory conflict analysis: Based on lessons from the Madagascar pilot, consider expanding the participatory approach to conflict analysis and prioritisation of outcomes.

Country alignment: Ensure robust lesson learning from the innovative approach to alignment and catalytic funding in DRC, and consider the applicability of this as a model elsewhere.

Output Title	PBF responds efficiently to demand, with strong financial management
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 - % of PBF supported programmes with quick turn-around time for IRF proposals and country eligibility notes	> 85% of all programmes (IRF/PRF) approved within 21 business days after submission being compliant with PBF quality norms and standards	86% / (2014: 95%)
4.2 - % of PBF funding applications that include value for money assessments	100% of PBF programmes demonstrate value for money and full compliance with UN systems and procedures	91% / (2014: 75%)

Key Points
PBF strives to ensure that all of its allocation decisions are taken within 21 days of formal proposal submission and has consistently met this target. In the three instances during the reporting period where it has not met the target, approval was achieved within one additional week.

Given differences in decision-making and governance of its two funding facilities, PBF’s results display a certain measure of variance in guaranteeing Value for Money considerations upon project approval. As noted in past reviews, IRF projects are approved by Project Appraisal Committees (PAC) within PBSO. For this set of allocations, minutes of PAC meetings demonstrate that VfM considerations are taken into account when recommending projects for approval, conditional approval or rejection. For PBF’s PRF modality, broad strategic plans, with budgets assigned per outcome area, are approved within PBSO, while approval for the projects that operationalise the plan are decided upon at country level by a committee that is co-led by government. This arrangement is meant to foster national leadership and working through national systems, a key consideration for output 3.1. For PRF approvals, PAC minutes of demonstrate that VfM is among the key considerations for PBF in determining allocation levels and distributions across outcomes within a strategic plan.

As part of the implementation of its current Business Plan, PBF also is exploring direct funding of qualified international NGOs at country level, with a pilot ongoing in DRC. The competition induced by including proposals by specialised NGOs in the decision-making process at country level should improve the quality of proposals overall, and encourage more robust VfM consideration.

Summary of responses to issues raised in previous annual reviews
Value for Money. At country level, PBF has provided clear guidance to Joint Steering Committees on VfM, including tools such as a VfM checklist to be utilised for decision-making. PBF has been testing additional measures to ensure VfM, including much closer accompaniment with in-country UN organisations as they undertake project design,

Recommendations
Value for Money: Continue to strengthen understanding and implementation of VFM at country level, including through close accompaniment of Joint Steering Committees where needed.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
As noted in previous reviews, cost drivers will vary depending on specific projects or interventions, and how each is being delivered. Number and pace of emerging crises will impact on demand for and availability of funds. This is more clearly demonstrated this year, as the narrative draws out, with the need for flexible programming in the face of specific emerging crises - e.g. increased violence in Mali, and the impact of Ebola. Such crises require the re-direction of funds, with some loss of sunk costs for terminated projects. However, PBF have endeavoured to reduce the impact on sunk costs by adapting existing projects where possible, e.g. in Sierra Leone they were able to quickly adapt the project to provide Standard Operating Procedures and Human Rights training for border personnel – reducing the number of reports of Human Rights violations.

Forex fluctuations will also play their part. The UK’s contribution is direct to the fund, and not aimed at any specific intervention, or at the admin costs of the PBF team.

VfM performance compared to the original VfM proposition in the business case
As noted in the introduction, and in the two previous Annual Reviews, the PBF was rated as good value for money by the Multilateral Aid Review (MAR) in 2011, which set out three reform priorities. PBF is making strong progress against these priorities. The 2015 MAR process will evaluate this is more detail.

The business case VFM proposition centered on the cost of conflict, and cost control considerations in PBF’s operations. It was noted there was room for improvement in the latter. The MAR update (2013) found that PBF was making reasonable progress overall to meet the reform priorities. The Fund’s first Business Plan is now in place and their internal Results Framework is iterative and evolving. A full-time M&E adviser has been engaged and has established a DM&E Unit within PBF – although it is not yet fully staffed. This unit is becoming increasingly engaged at the design stage of projects, working with stakeholders to establish and agree meaningful outcomes.

Indicator 4.2 aims to ensure demonstration of VFM in PBF funding. It was previously acknowledged that this is challenging. Immediate Response Facility (IRF) project proposals are scrutinized and often yield budget savings, but it has historically been more difficult to identify and realize budget savings from the Peacebuilding and Recovery Facility (PRF) projects. THE DM&E Unit is developing a training and certification process for country partners, including on VFM identification, which will become part of the project approval process. Additionally, PBF now works much more closely with in-country UN organizations to develop better understanding of VFM and cost considerations, and embed this at the project design stage. PBF are able to demonstrate where this closer support is realizing savings and increased VFM.

PBF plan to conduct a meta-evaluation of a broad range of projects to establish whether certified projects perform better than similar un-certified projects.

Assessment of whether the programme continues to represent value for money
PBF continues to demonstrate evidence of increased VFM being achieved through:
- Competitive selection processes for identified projects
- Institutionalising Results Based Management approaches with time-limited eligibility for PBF funding
- Investment in enhanced M&E, with a focus on increasing accountability
- Stronger design, implementation and reporting – resulting in off-track projects being brought back on track

The combination of reducing the cost of conflict, and more-effective delivery, gives confidence that PBF continues to represent VFM, and that this is increasing. PBF are committed to keeping this on an upward trajectory.

Quality of financial management
The UK’s contribution to the fund goes straight in to the UNDP Multi-Partner Trust Fund Office (MPTFO), who administers the fund in accordance with its regulations, rules, directives and procedures. The MPTFO is audited at different levels, and in accordance with the Framework for auditing multi-donor trust funds, which has been agreed to by the Internal Audit Services of Recipient UN organisations.

The MPTFO Gateway provides live data on PBF receipts and spend, along with the narrative annual financial and progress report, and the annual Certified Financial Statement. The UK’s contribution is un-earmarked. This allows PBF to have full fiduciary and strategic responsibility in deciding which countries and which areas of intervention receive funds based on the Fund’s allocation criteria.

Date of last narrative financial report	May 2015
Date of last audited annual statement	May 2015

E: RISK (½ page)

Overall risk rating: Low/Medium/High

Overview of programme risk
The overall context for programmes, and therefore the risks they face, varies considerably between fragile and conflict affected countries in which PBF supports programmes.

As noted above, PBF’s mandate and core principles call for it to be a risk-taking funder of first resort, thus helping to address a global market failure in peacebuilding finance. This is a key part of the added value of PBF, but does expose individual projects to considerable risk in some contexts. The risk marker that PBF have developed and will look to apply in the coming reporting period is an appropriate response to this, allowing a more flexible approach in which high-risk projects are managed and supported appropriately, whilst lower risk projects are held to a higher standard of delivery.

Key risks outlined in the business case include:
- Insecurity and instability in PBF countries
- Failure to achieve intended programme results
- Insufficient capacity for fund management
- Insufficient donor support
- Risk of corruption / fraud

These risks remain pertinent but mitigating measures have proven effective. The UK remains confident in the PBF as a fund manager. The biggest strategic risk remains the limited donor support base. The recent Peacebuilding Architecture Review may help to address this, and the UK is working with PBF to encourage and support new and existing donors to increase contributions.

Assessment prior to preparation of the Business Case indicated that the PBF has sufficient measures in place to assess requests and allocating resources to relevant UN agencies to ensure that funds are being directed to appropriate projects. Internal procurement systems and audit measures are cited as fit for purpose. Funds will not be re-directed within the system without significant oversight.

Outstanding actions from risk assessment
None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The PBF delivers a range of discrete projects, identified by recipient UN organisations. Timeframes are agreed separately for each, on the basis of appropriate factors. Through the work we are doing with PBF to strengthen the log frame, improving the results-based approach, and greater linkage of these to the Business Plan and Performance Management Plan, PBF are becoming stronger on design, implementation and reporting – resulting in off-track projects being brought back on track.

In addition, PBF plans to limit eligibility to funding to a maximum five-year period: Continued eligibility will be based on a set of criteria mutually agreed with country-based partners that will look for evidence that peacebuilding has been mainstreamed into key national and UN strategic planning frameworks. This will help drive delivery within finite timeframes, eliminate lag, and reduce the likelihood of drip-feeding funds. All of the above should contribute to tighter cost control and reduced costs.

PBF ad hoc involvement in country-level Joint Steering Committees will also help ensure adequate focus on strategically relevant interventions and value for money.

Performance of partnership(s)
PBF is capitalising on lessons learned through the 2013 Global Review and annual reviews such as this, and institutionalise changes to boost Results Based Management. Aside from demanding more of fund recipients, as mentioned in the section above, the introduction of competitive selection processes for projects will help drive increased performance, accountability, savings and value. Lessons learned from this approach, include the use of competitive concept notes, allowing decision makers to assess quality and likely impact before scarce resources are spent on detailed proposals. This approach also allows PBF to help shape projects and desired results.

Asset monitoring and control
N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

PBF finalised two evaluations of its investments in Sierra Leone and Liberia in early 2015. In Sierra Leone, a summative evaluation of the full PBF portfolio indicated evidence of peacebuilding results in areas related to reduced tensions around elections and compensation to victims of past conflict. It also highlighted that setting time-appropriate peacebuilding outcomes remains a challenge for country-based partners, and pointed to the need to better adapt sluggish UN administrative systems to better respond to rapidly changing peacebuilding environments. In Liberia, the evaluation focused on assessing the effectiveness and efficiency of the Peacebuilding Office, housed within the Ministry of Interior Affairs and acting as the Secretariat for the Joint Steering Committee overseeing implementation of PBF-funded projects. In light of the anticipated drawdown of UNMIL and resulting changes for both the UN and the Government of Liberia, the evaluation pointed to a series of measures meant to bolster national ownership and sustainability of the PBO within the Ministry beyond PBF support, as well as for how UN accountability can be improved. The results of both evaluations, delivered before the height of the Ebola crisis, will help inform future programming in the post-Ebola context.

In addition to these evaluations, the PBF launched its new global evaluation plan in 2015, including recruitment of staff necessary to implement the ambitious schedule PBF is commissioning summative evaluations of its investments in Guatemala, Colombia and Guinea, work which will be implemented during the third and fourth quarters 2015. In Colombia, the PBF is collaborating with the Government of Norway to conduct a joint evaluation of a project they co-financed; this is PBF’s first joint evaluation with another donor, and the Fund looks forward to additional opportunities with other donors in the future. An evaluation of PBF’s initial investment in Niger is currently underway and will be joined by an additional country-managed evaluation of PBF’s investments in Nepal in the last quarter of 2015. In total, the evaluation plan for 2015 represents a doubling of evaluative exercises over past years, which is expected to boost both accountability and learning.

Additional evidence for this review comes from the recent report of the high-level Peacebuilding Architecture Review panel, and feedback from DFID Country Offices.

Monitoring progress throughout the review period

In line with its current Business Plan, PBF has begun to implement beneficiary feedback through community-based monitoring schemes, launching its first initiative in Mali. PBF is working closely with UN Volunteers and Saferworld in Kyrgyzstan to launch a community monitoring network there, including among ethnic enclaves along the tense Kyrgyz-Tajik border area. Beyond these two pilots, PBF is working together with PeaceNexus to develop guidance on inclusive monitoring to assist field colleagues and beneficiaries. This guidance is scheduled to be completed by end 2015.

In an effort to increase evidence about higher-level peacebuilding results, PBF has continued to support the implementation of perception surveys and other data collection exercises aimed at assessing impact. During the reporting period, PBF has supported perception surveys in Liberia, Kyrgyzstan and Colombia, yielding important feedback on attitudinal shifts of average citizens’ toward other social or political groups, confidence in judicial or security actors, and support for peace processes. Expanding the use of perception surveys, together with the implementation of the community-based monitoring mechanism noted above are expected to yield improved evidence for both monitoring and evaluation of PBF investments in the future.

In addition to establishing monitoring schemes in country, PBF has continued to assist in-country partners through dedicated technical support missions, largely launched during critical prioritisation and programme design stages. In total, PBF and its partners (notably PeaceNexus and ACCORD) conducted 29 missions to 10 PBF countries, a more than 38% increase over last reporting period. Among the support missions, the Fund fielded a month-long deployment of a PBF staff member to Guinea, following the loss of its JSC Secretariat Coordinator.