## Sheet1
PROJECT NAME | Accelerating the Rise in Contraceptive Prevalence in Uganda
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 2012 (Oct 11-Sept 12) | Milestone 2013 (Oct 12-Sept 13) | Milestone 2014 (Oct 13-Sept 14) | Milestone 2015 (Apr 15-Sept 15) | Milestone 2015 (Oct 15-Sept 16) | Target 2016
Women's lives are saved during pregnancy and childbirth | Maternal mortality ratio (national, deaths per 100,000 live births) | Planned | 438 |  |  |  | 135 | 135 | 135 (2015, MDG and National Development Plan target)
Achieved
Source
DHS 2011 and 2016
| Impact Indicator 2 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016
| Number of unintended pregnancies averted (DFID attributable) | Planned | 0 (2011) | 150000 | 200000 | 90000 | 59262 | 167660 | 666922
Achieved
Source
Modelled from national estimates
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016 | Assumptions
Increased use of modern contraception in Uganda | Contraceptive prevalence rate (modern methods: women of reproductive age), to be disaggregated by poorest 40%, and women 15-19) | Planned | 25.6% (UBOS) | 28.1%, 2.5%pt increase from baseline | 30.6%, 5%pt increase from baseline | 33.1%, 7.5%pt increase from baseline | 35.6%, 10%pt increase from baseline | 35.6%, 10%pt increase from baseline | 35.6%, 10%pt increase from baseline
|  | Achieved |  |  |  |  | 31.8% (PMA2020)
Source
2011 and 2016 DHS; annual panel survey
| Outcome Indicator 2 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016
| Couple Years of Protection delivered through ARC (attributable to DFID) | Planned | 0 | 956596 | 1323988 | 1366000 | 174194.808 | 850374.3708 | 4671153.1787
|  | UHMG contribution | 0 | 486596 | 543988 | 396000 | N/A | N/A | 1426584
|  | MSU/MSI contribution | 0 | 470000 | 780000 | 970000 | 174194.808 | 850374.3708 | 3244569.1787
|  | Total achieved |  | 771290 | 1048040 | 1,186,059*
|  | Achieved UHMG |  | 271260 | 262667 | ND | N/A | N/A | 533927
|  | Achieved MSU/MSIU |  | 500030 | 785373 | 1,186,059* | 79486
Source
Quarterly and annual reporting from MSU and UHMG
| Outcome Indicator 3 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016
| Cost per CYP by delivery channel (DFID attributable) | Outreach |  | 4.5832 | 4.5832 | 4.5832 | 5 | 2.5 | 2.5
|  | Achieved |  | ND | ND | ND | 8.57
|  | Social franchising |  | 18.5528 | 18.5528 | 18.5528 | 7 | 3 | 3
|  | Achieved |  | ND | ND | ND | 24.91
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| £35m |  | 0 | 0 | £35m |  | 100
INPUTS (HR) | DFID (FTEs)
0.2 x Health Adviser, 0.1 x Programme Officer, 0.1 x Results Adviser, 0.2 x Deputy Programme Manager
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016 | Assumption
Women and men have better information to make healthy reproductive choices | Number of people reached with FP messages through DFID supported IPC and community mobilisation activities of MSIU disaggregated by age | Planned |  | ND | ND | 700,000 (15 – 24yrs 70,000) (25 yrs & above 630,000) | 25,706 (12,081): 15 – 24yrs and 13,625 : 25 yrs & above ) | 125,772 (59,112 : 15 – 24yrs and 66,660 :25 yrs & above ) | 851,478 (15 – 24yrs 141,193 (25 yrs & above 710,285) | Public and private family planning services are increasingly available and accessible.
|  | Achieved |  |  |  | 553,430 (15 - 25 yrs: 157,548), 25yrs & above: 395,882) | 25911 (15-24 yrs 8,926) (>25 yrs 16,985)
Source
MSIU quarterly and annual reporting
| Output Indicator 1.2 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016
| Number of IPC touch points through CHC disaggregated by age (attributable to DFID) | Planned | 0 (2014) | N/A | N/A | N/A | 2840 (15- 19yrs 1,704), (20 to 25yrs 1,136) | 51,750 (15- 19yrs 31,050), (20 to 25yrs 20,700) | 54,590 (15- 19yrs 32,754), (20 to 25yrs 21,836)
|  | Achieved |  |  |  |  | 5,000 (15-19 yrs 3,000) (20-25 yrs 2,000)
Source
FHI quarterly and annual reporting
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016
20 | Number of family planning radio mentions on local radio through CHC in the 5 districts (attributable to DFID) | Planned | 0 (2014) | N/A | N/A | N/A | 1350 | 5400 | 6750
|  | Achieved |  |  |  |  | 1350
|  | Source | [7 empty] | RISK RATING
|  | FHI quarterly and annual reporting | [7 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 2200000 |  |  |  | 2200000 |  | 100
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016 | Assumptions
Women and men face fewer barriers to accessing family planning services | Number of LAPM vouchers redeemed through accredited service delivery points (attributable to DFID) | Planned | 0 | 21000 | 59000 | 79000 | 13531.21 | 71038.8525 | 243570.0625 | Vouchers do not have a significant adverse impact on the broader market for private family planning services.
|  | Achieved |  | 8463 | 56733 | 92547 | 3312
Source
MSIU quarterly and annual reporting, from claim forms
| Output Indicator 2.2 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016
| Number of LAPM services provided by outreach at public sector facilities (attributable to DFID) | Planned | 0 | 62000 | 72000 | 83600 | 27929.998 | 131819.276 | 377349.274
|  | Achieved |  | 94641 | 116805 | Unable to report due to concerns about reporting of permanent methods. | 14932
Source
MSIU quarterly and annual reporting
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016
40 | Percentage of HCWs that score above 85% on the QTA score after the training and mentoring process | Planned |  | N/A | N/A | N/A | 70% | 75%
|  | Achieved |  |  |  |  | Not done
|  | Source | [7 empty] | RISK RATING
|  | MSIU quarterly and annual reporting | [7 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 10000000 |  |  |  | 10000000 |  | 100
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016 | Assumptions
A better choice of family planning methods is available and being used | Number of implants and IUDs provided by MSIU programmes (attributable to DFID) | Planned | 0 (IUDs) 0 (Implants) | 23000 (IUD) 47000 (Implants) | 45000 (IUD) 90000 (Implants) | 57,000 (IUD) 117,000 (Implants) | 9,132(IUDs) 25,542 (Implants) | 45,619 (IUDs) 124,541 (Implants) | 179,751 (IUDs)404,083 (Implants) | This is an ambitious target, as an assumption has been made that MSU can promote the use of IUDs at a certain ratio to implants through its outreach and private provider activities. We have assumed a ratio of 2:1 for implants and IUDs on outreach. For private providers, we have assumed a ratio of 1:1.
|  | Achieved |  | 18649 (IUD) 57374 (Implants) | 33,509 (IUDs) 113,616 (Implants) | 47,934 (IUDs); 115,179 (implants) | 1,689 (IUD) 15,237 (Implants)
Source
MSIU quarterly and annual reporting
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | Milestone 2012 | Milestone 2013 | Milestone 2014 | Milestone 2015 | Milestone 2016 | Target 2016
40 | Numbers of tubal ligations / vasectomies performed by MSIU programmes (attributable to DFID) | Planned | 0 (V) 0 (TL) | 2400(V) 24000 (TL) | 3100 (V) 28000 (TL) | 3,420(V) 31,200 (TL) | 155 (V) 6,632 (TL) | 750 (V) 31,948 (TL) | 9,825(V) 121,780 (TL)
|  | Achieved |  | 831(V) 26250 (TL) | 570 (V) 25,568 (TL) | 755 (V) TLs not reported due to concerns raised about quality of results reporting. | 83 (V) 1,235 (TL)
|  | Source | [7 empty] | RISK RATING
|  | MSIU quarterly and annual reporting | [7 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
| 6800000 |  |  |  | 6800000 |  | 100
INPUTS (HR) | DFID (FTEs)
Note: Cost per CYP includes medical salaries, travels including vehicle purchases, medical supplies, and all other direct costs apart from trainings.
*To note concerns during this year with falsification of results around LTM.