Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Policy Development Facility 2
Programme Value: £18.5m		Review Date: 12/10/2015
Programme Code: / 203922	Start Date: / 01/04/2015	End Date: 31/03/2020

Summary of Programme Performance

Year	2014	2015
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

This report serves as an inception review of the Policy Development Facility 2 (PDF), a period where extensive thought and planning has been put into the ways that PDF 2 can respond to the new Nigerian political environment and build on the success of PDF 1. Whilst this is the second official review of the PDF 2 programme, it is the first review since contract mobilisation of the service provider, and covers the first six months of the programme’s mobilisation activities (since April 2015). There has also been the beginning of programming in areas that may prove to be important over the next five years.

DFID delayed the start date of PDF 2, originally planned for September 2014 due to lower than anticipated finances available for the 2014/15 financial year. Commencement was rescheduled to the start of the 2015/16 financial year. The 2014 Annual Review was carried out in the absence of a service provider having been contracted and therefore focused on commercial milestones in contracting the programme as well as the political outlook pre-election. The new inception period (from April 2015 to September 2015) aligned nearly perfectly with Nigeria’s own post-election period and the programme carried out a Political Economy Analysis (PEA) of the post-election political landscape in July, considering potential opportunities and implications for the programme over the next few years.

Delays from the Nigerian Government to appoint a Cabinet meant it has not yet been possible to identify new Ministerial appointments to support and the first round of PEA focused on some of the internal dynamics within the party and how these may impact on policies. Ministerial nominations have now been submitted to the Nigerian Senate for confirmation (October 2015) and a second PEA is scheduled for early November 2015. This will help to complement and inform internal HMG thinking around potential ‘champions of change’ within the new government and policy areas which the UK can support.

In the six months since award of contract, the PDF 2 team has delivered an inception report, a revised logframe, procedures manual, along with 18 procedural annexes. It has contracted its first two embedded advisers, facilitated a policy dialogue in Lagos, produced a draft of the ‘Unrecorded Trade and Financial flows’ study, worked with DFID advisers to initiate broader support to the Office of the Auditor General’s office, and carried out in-depth planning for a ‘Youth Employment’ summit.

Early indications are that the programme has shaped itself to be responsive to opportunities with the new government, and to also help facilitate consultation on policy areas that may be having unintended harm on economic growth and the livelihoods of the poor. The political environment in the first six months has demonstrated enough promise to indicate that there should be sufficient reform opportunities in the new government’s agenda to enable PDF 2 to support and enhance a number of important policy successes over the lifespan of the programme.

Table 1: Action on recommendations from 2014 Annual review of PDF

	Recommendations from 2014 Annual review	Action(s) Taken
1	Ensure a seamless transition from PDF 1 to PDF 2. All relevant sub-projects such as the Embedded Adviser (EA) support to key Nigerian Ministers are smoothly carried over in order to ensure continuity before the new Nigerian economic management team is selected.	Achieved – PDF 2 commenced in April 2015 with a smooth handover of contracts. Most existing embedded adviser contracts were concluded in May 2015 to coincide with the change of government.
2	Complete a robust Political Economy Analysis of the post-election political environment – this will help the PDF 2 programme to identify who the new ‘champions of change’ are likely to be under the next Nigerian administration.	Partially achieved: First round of political economy analysis completed. Second round based on the new Ministerial names to be completed before the end of December 2015. Delayed due to slow appointments of new cabinet by the President.
3	PDF 2 Inception phase should further shape the nature of the programme. Given the elections, the inception phase will be critical to determine whether the shape, nature and size of the programme is still appropriate given the political economy of Nigeria. The logframe and capabilities of the team should be adjusted appropriately. By the time of the 2015 annual review this needs to have been concluded.	Achieved: First round of political economy analysis fed into approved inception report and accompanied by appropriate revisions to logframe.
4	PDF 2 should have developed a robust Value for Money (VfM) strategy and define VfM indicators in line with the 4Es of economy, effectiveness, efficiency and equity.	Completed: This will be integrated within each individual project.

Summary of recommendations for the next year

The decisions that are taken on programming within the next 12 months may well prove pivotal to the results that are achieved by PDF 2. Understanding which areas to support and the right ways to provide the support will be critical.

- Quickly complete the second phase of political economy analysis on the new cabinet Ministers to help inform programming decisions;
- Develop a five year plan to strengthen Consumer Groups within Nigeria, including their base of representation and how they feed into policy processes.
- Identify high-impact non-government groups that may help demand more inclusive policies from government and consider appropriate approaches to help strengthen them.
- Develop and grow the use of social media and the proposed website platform for the dissemination of policy research, learning and policy influence. Identify a target audience and explore different ways of recording and disseminating key messages from PDF facilitated events.
- Establish a policy within PDF and agreed with DFID on the types of content that will be made public, and a risk mitigation policy to avoid reputational risk and ensure no damage to the UK government’s partnership with the Nigerian Government.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203922/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203922/documents/

Outline of the programme

PDF 2’s objective is to provide targeted assistance over a 5 year period to help Nigeria’s ‘champions of change’ implement economic and social policies that lead to poverty reduction, enabling HMG to back reform through:

- Backing key economic and public sector reformers in Nigeria with technical support
- Conducting research and studies that can be used to influence and shape Nigeria’s economic reform agenda.
- Initiating explorative studies for potential complimentary DFID programming.

The Impact of PDF phase 2 is that the Nigerian Government implements policies that lead to poverty reduction. The Outcome is that Nigeria’s ‘champions of change’ make increased use of capacity and evidence to enable them to pursue vital economic and social reform.

Context

Nigeria, with much the largest population and economy on the continent, a delicate security situation with a history of internal conflict, and a large diaspora with strong links to Britain, matters greatly to West Africa, Africa as a whole, and the UK.

Yet after over 50 years of independence, nearly 50 years since oil revenues came on stream, and more than a decade of robust economic growth, a third of Nigerians still live in extreme poverty, while a small elite is extremely wealthy. Why is this? “The system [in Nigeria] is deeply rooted in vested interests, a history of intrinsic tension between traditional values and electoral government, systemic violence and conflict often fuelled by ethnic rivalry”[1]. This review and those of its predecessor programme finds that these fundamental features of Nigeria, identified in a DFID paper of 2005, remain valid, and help explain persisting mismanagement of public resources, weak accountability, and a personalised public policy process which in general gives little weight to evidence of what would most effectively achieve wider national objectives. These contribute to weak institutions and government agencies, pervasive corruption, and to poor governance and policy outcomes.
[1] C Heymans, C Pycroft, DFID 2005.

For 15 years, Nigeria has been embedding democratic politics after decades in which military government predominated, with a harmful effect on public ethics and the quality of governance; with the exception of the last year, economic growth has accelerated (though the benefits are poorly distributed); and some (but by no means all) social indicators have improved (though far below potential)[2].The 2015 elections created increased reform momentum, and with the dominant incumbent political party losing the election and allowing a peaceful transition to the opposition, there is hope that this democratic landmark for Nigeria may increase public accountability and help shift policy making to be more reflective of a broader constituency rather than just the will of a small dominant elite.
[2] http://unstats.un.org/unsd/mdg/Data.aspx

The external economic environment for the new government is harsh, with oil prices half of what they were just over a year ago. With 90% of export revenue and 75% of government revenues coming from oil, this represents a substantial fall in the resources available to be mobilised for the new government’s agenda. Recent forecasts on oil prices from the IMF do not signal a fast recovery in oil prices and it is possible that this will be the economic environment through-out the five years of PDF 2 and President Buhari’s government.

The economic policy agenda of the new government, is broadly positive and well intentioned, but has been varied in terms of early impact. Unprecedented progressive reform has begun on the Nigerian National Petroleum Corporation (NNPC), pushing for the agency to clean up its act and move towards operating as a commercial entity that is a net contributor of value to the Nigerian economy. There has also been early demonstrative commitment to the private power market development through decisive action by the Vice President. Public financial management has been given a ‘shot-in-the-arm’ with the announcement of forensic audits on key revenue generating agencies with an effort to increase resources available for national development. The 2016 Budget process has also begun with a move towards zero-based budgeting- presenting an opportunity to challenge old assumptions that have sat within countless previous budgets. Yet monetary and trade policy remain concerning, with poorly thought through policies such as capital controls introduced to maintain a strong currency and access to foreign exchange restricted on key imports having a negative impact on domestic business activity and foreign investment. The delay of appointments to key economic Ministries has meant some of the post-election good will from international markets to invest in Nigeria has been lost and will need to be re-awoken by the new economic team taking pro-active steps to engage and reassure.

Given the importance of Nigeria to achieving the SDGs, and promising early signs from the new government there is a strong case for DFID continuing to be engaged in influencing Nigeria’s policy process for better development outcomes. Progress is possible, and the potential gains in security, and development are very large. However, realism is necessary on the risks and uncertainties involved. Despite the democratic progress and positive demonstration of accountability in the 2015 election, old and new vested interests will be positioning themselves or regrouping to attempt to influence the new government public policy agenda. In some instances the influence of this group may well outweigh both evidence and the wider national interest. In certain cases even the best efforts of PDF will not be able to overcome this influence.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The intended outcome of PDF 2 is that Nigeria’s ‘champions of change’ use increased capacity and evidence to enable them to pursue vital economic and social reform. There is no formal milestone on this until 2017 when the programme will be expected to demonstrate at least seven substantial case studies as part of its mid-term review. These case studies should show how the programme’s support has influenced the policy process in a way that could plausibly feed-through to poverty reduction (the programme’s overall intended impact). Until 2017 this will be assessed in a qualitative way.

The programme has established and shaped itself with the appropriate competencies and approach to be on the right trajectory to achieve its intended outcome and the reform environment in 2015 looks sufficiently promising. Whilst it is too early to view any actual progress from the programme, an impact level baseline considering policies within the APC manifesto and early policy announcements is scheduled to be delivered before the end of the calendar year as part of the second PEA in November. The programme looks set to deliver some substantial results by the end of the five years, with interesting interim case studies available by 2017.

Overall output score and description

The overall output score of the programme is ‘A’, recognising a successful inception period that has provided all expected deliverables and has established promising ways of working under both outputs. The logical framework output milestone targets for this year are zero given that the inception phase concluded in September. The six months prior to April were used to procure the programme with a successful open process that delivered a good value contractual agreement for DFID and enabled the programme to start as per last year’s revised schedule.

Policy Development Facility team competencies and co-ordination.

PDF 2 is a small programme that works closely with DFID advisers and has the ability to ‘punch above its weight’. DFID Nigeria recognises the positive changes that have been made within the small in-country team. Additional capabilities have been brought to the team with the introduction of an experienced knowledge manager. The National Programme Manager has led a recognisable change in culture that has led to the broader team seeming more engaged and taking a more prominent role than under the previous Policy Development Facility. This bodes well for getting the most out of what is a small team and has already paid dividends with the in-country team being able to successfully cover a period of leave from the National Programme Manager without having to bring central DAI staff (as would previously have been the case) and maintaining programme standards through-out the period. This extended capability of the team has encouraged DFID to be more ambitious with what it can delegate to the in-country team shown by their rapid response to the opportunity to carry out a policy dialogue on the Central Bank foreign exchange restrictions with the Nigerian Economic Summit Group in September.

PDF 2 is increasingly playing a valuable co-ordination role among DFID programmes. The establishment of a Knowledge Management network (led by PDF) as a channel for distributing knowledge products and learning across programmes has been promising. Planning of the ‘Youth Employment’ Summit (scheduled for January 2016), which will showcase various innovations from programmes in DFID’s Growth and Governance Portfolios, as well as the Nigerian government, private sector and other donors will help demonstrate the value that this coordination role can potentially have. Furthermore, PDF 2 is actively engaging other donor organisation particularly in the trade policy space as part of its coordination role, and in line with the revised approach towards trade policy work in Nigeria.

Has the logframe been updated since the last review?

Yes, the logframe has been revised as part of the inception period discussions. This was to reflect annual milestone targets commencing a year from inception and also to include a third indicator to the two outputs. Indicators were also adjusted at impact and outcome level to better represent measurable progress of the programme.

## C: DETAILED OUTPUT SCORING

Output Title	Relevant and high quality PDF II organisational support delivered to beneficiaries
Output number per LF		1.	Output Score	A
Risk:		Medium	Impact weighting (%):	60%
Risk revised since last AR?		No.	Impact weighting % revised since last AR?	Yes (increased from 55%)

Indicator(s)	Milestones (2015)	Comment
Number of projects assessed as executed satisfactorily (as planned) or better during implementation	0	Target of 18 for 2016. This appears challenging but achievable.
Beneficiary, user perceptions of relevance and quality of PDF II funded organisational support	0	Target in 2016 for relevance score of 90% and quality score of 80%
Number of instances where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation2	0	Target of 3 for 2016. This appears challenging but achievable.

The majority of embedded advisers finished their contracts at the end of May 2015 in line with the handover to the new government. Two have since been appointed (a communications adviser for the Nigerian Sovereign Investment Authority and a public financial management expert for the Office of the Auditor General).

Political Economy Analysis of the New Cabinet

Given the delays to forming the President’s cabinet, the first political economy analysis carried out in July focused mostly on the dynamics within APC and how this may impact on policy formation, style and dynamics. The second PEA in early November 2015 will have a focus on individuals within the cabinet and potential policy opportunities and will complement internal DFID efforts to identify areas of promise on the development agenda.

Despite the absence of a cabinet, some areas of support were explored that did not depend on new appointments.

Office of the Auditor General of the Federation

Arguably President Buhari’s most prominent policy priority is his anti-corruption agenda. One of President Buhari’s first directives in August 2015 was to the Auditor General to resolve all outstanding audit issues within 30 days. He also made a public statement that empowered the rather neglected audit function by demanding that all outstanding audit queries should be responded to within 24 hours[3]. This quickly led to substantial volumes of audit responses, stretching the capacity of the Auditor General’s office.
[3] http://www.premiumtimesng.com/news/headlines/187670-audit-queries-must-be-answered-in-24-hours-buhari-tells-public-officials.html

The role of the Office of the Auditor General fits neatly into the prominent anti-corruption agenda and complements DFID’s broader approach towards building accountability in public service reform. DFID/PDF 2 has responded to this by agreeing to fund an embedded adviser to this function, initially for six months. During this time to complement this support PDF will help coordinate missions from the UK’s National Audit Office (through DFID’s iFuse programme) and potentially form links between the UK and Nigerian Public Accounts Committee. These partnerships together will aim to help Nigeria think through its high-level audit strategy for the next five years and consider how they can strengthen accountability through parliament and adopt more transparent approaches to increase public engagement in this work. If the partnership works well, the aim is for the DFID Nigeria’s new public service reform programme to pick up this relationship next year with DFID having helped established a strong strategic direction.

Office of the Vice President

DFID has also had requests to fund technical support to the office of the Vice President, some of which may eventually be picked up by the Policy Development Facility. Other DFID programmes, notably Nigeria’s Infrastructure Advisory Facility (NIAF 2) and Federal Public Administration Reforms Programme (FEPAR) moved early to provide much welcomed technical assistance to this office, DFID has held back on PDF support pending further clarity on Ministerial portfolios. There is potential for PDF to provide some future support to this office on issues such as job creation or investment policy, but it will be important to understand which part of government will have the lead influence on which area first. The November political economy analysis should help inform this decision.

Trade Policy Support

The political economy of trade policy remains challenging with certain groups dominating the policy discourse and many other local voices unrepresented. An event facilitated by local news magazine ‘Africa Matters’ on the European Economic Partnership Agreement (EPA) in August, sponsored by government agencies and the Manufacturers Association of Nigeria, demonstrated that the voices of certain groups that tap into nationalistic sentiment and promote attractive but technically superficial arguments, still dominate Nigeria’s position. Permanent Secretaries from the Ministries of Trade, Investment and Commerce, National Planning Commission and Foreign Affairs all provided passionate speeches on why Nigeria needed to protect its local industries by restricting trade.

Approaching trade policy as purely an issue of limited capability within government would negate an understanding of the deeper political incentives working within this policy space. There are already donors such as GIZ, who are working primarily on addressing capacity constraints within government institutions on trade policy formulation. Whilst this may be helpful and DFID/ PDF should work closely with GIZ, it will unlikely be sufficient in itself to promote a more inclusive, pro-poor trade policy. As such, rather than traditional institutional support the balance of PDF 2’s efforts will be better focused in strengthening alternative (or under-represented) voices that can feed into policy processes. PDF 2 has already started to explore how it might strengthen the role of relatively weak consumer groups to feed into policy formation as well as consider how it could work to reflect a broader group of manufacturers into policy discussions (including SMEs and the informal sector).

Pressure points to help make government policies more inclusive

Beyond trade, PDF should also explore how it can work with Non-Government actors to help make government policy more inclusive. As part of its non-government political economy analysis (planned for 2016) the programme should understand the approach that DFID’s ENABLE programme has used to strengthen media groups and Business Membership Organisations (BMOs) and see if there are lessons from this that can be applied more broadly to help make policy formation approaches to be more inclusive. It should also consider how it might strengthen direct feedback mechanisms such as radio phone-in shows that respond to government policy (e.g. Brekete Family Radio show).

Table 2: Recommendations on Output 1 from PDF 1 Project Completion Review (May 2015)

	Recommendations from PDF 1 Programme Completion Review	Action (s) taken
1	UK Government and other international donors to advocate for protecting key institutions delivered in partnership with the previous Nigerian Government under PDF 1 (i.e. the new Nigeria Development Bank and the Nigerian Sovereign Investment Authority). Encouraging the new administration to maintain these institutions will ensure the longevity of the reforms and increase their development impact.	DFID has advocated for NSIA to be protected and was a priority growth policy post-elections (including with the Transition Committee). The new government has responded positively with additional resources likely to be allocated to the NSIA under the medium term expenditure framework. / There has been slower progress for the Development Bank of Nigeria. Discussions between DFID and the World Bank with the office of the Vice President are currently highlighting how the DBN might help the new government to address access to finance constraints.
2	PDF phase 2 inception period should further shape the nature of the programme. Given the Nigerian elections and the new incoming government, the inception phase will be critical to determine whether the shape, nature and size of the programme is still appropriate given the political economy of Nigeria. The logframe and capabilities of the team should be adjusted appropriately.	This has been achieved and is reflected in the inception report from PDF and the new approved logframe.
3	Complete a robust Political Economy Analysis of the post-election political environment – this will form a sense check on DFID’s post-election networking and help DFID/PDF programme identify who the new ‘champions of change’ are likely to be under the next Nigerian administration.	Partially achieved. First PEA completed, with second one scheduled in November due to delays in appointment of Cabinet.
4	Give PDF phase 2 more flexibility to work with non-state partners in areas where policy change is highly desirable but unlikely to come about through engagement with the Executive alone. Complete a political economy and stakeholder mapping of potential non-government actors who could be supported in ways to put pressure on improving the pro-poor nature of Nigeria’s Policy Formation processes	PEA on this side intended for 2016. PDF has already explored how it might partner with Consumer Groups to strengthen their voice in policy matters. There may also be opportunities to work with the Public Accounts committee.
5	Encourage greater engagement between PDF and other DFID-funded programmes. Particularly important to have good join-up with the Federal Public Administration Reforms Programme (FEPAR), Growth and Employment in States (GEMS 3) business environment programme, and Nigeria’s Infrastructure Advisory Facility (NIAF). Other donor programmes such as GIZ’s trade programme will also be useful for coordinating trade policy work.	PDF has taken leadership in this area, demonstrated clearly through the Youth Employment summit and their role in mobilising inputs from other DFID programmes as well as the new Knowledge management network that PDF have led.
6	PDF phase 2 should develop a robust Value for Money (VfM) strategy and define VfM indicators in line with the 4Es of economy, effectiveness, efficiency and equity.	Achieved: within TORs VfM measures will be identified across 4Es. Case study approach will be reviewed at Mid-Term review point. Restriction on embedded adviser pay remains in place and has already been applied.
7	Build on the greater rigour that the PDF unit has introduced in defining the results sought, and building them into TORs and monitoring and reporting systems, including introducing a few tracer studies to track impact on policy	This has been included as part of the inception report.

Recommendations

- Quickly complete the second phase of political economy analysis on the new cabinet Ministers to help inform programming decisions.
- Develop a five year plan to strengthen Consumer Groups within Nigeria, including their base of representation and how they feed into policy processes.
- Identify high-impact non-government groups that may help demand more inclusive policies from government and consider appropriate approaches to help strengthen them.

Output Title	Relevant and high quality PDF II policy research, explorative studies and consultation products delivered to beneficiaries
Output number per LF		2.	Output Score	A
Risk:		Low	Impact weighting (%):	40%
Risk revised since last AR?		No.	Impact weighting % revised since last AR?	Yes, decreased from 45%

Indicator(s)	Milestones (2015)	Comment
Number of projects assessed as executed satisfactorily (as planned) or better during implementation	0	Target of 12 for 2016. This appears challenging but achievable.
Beneficiary, user perceptions of relevance and quality of PDF II-supported policy studies and events	0	Target in 2016 for relevance score of 90% and quality score of 80%
Number of instances where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	0	Target of 2 in 2016.

Work under this output has both continued where PDF 1 left-off with plans for dissemination of two major studies funded under the previous programme, but also tried to enhance how PDF generally goes about disseminating key studies. Following recommendations from the programme completion review (PCR) of PDF 1 there are plans to create a PDF website as a learning platform, and making greater use of social media to highlight policy implications of PDF’s work. This new approach for the programme was tested in September with a policy dialogue that PDF facilitated that attempted to use a range of social media and conventional media approaches to try and have policy impact (see Forex Policy Dialogue below).

Unrecorded Trade and Financial Flows Study- Chatham House

This study will show the under-recognised role of informal trade activities in the Nigerian economy that may reflect as much as 70 to 80% of trade between Nigeria and its neighbours. The purpose of this report is to highlight the activities which do not show up in formal economic statistics and look at the implications of this large informal sector for government policies. The report has now been drafted and is in the final stage of editing with plans for dissemination in three locations in Nigeria (Lagos, Abuja and Kano) and London in early December 2015. It will be important for Chatham House to engage with a range of policy makers at different levels of government so that they understand the implications that their policies have on the informal sector, and can look to help support and eventually formalise this vibrant part of the economy.

Forex Policy Dialogue with the Central Bank

This policy dialogue demonstrated how PDF can rapidly respond to policy issues and strengthen voices that may have been unrepresented in the policy formation process. In response to a Central Bank’s ban on access to foreign exchange for the purposes of importing key economic inputs into the country, PDF was able to quickly put together a format that allowed different business voices (including informal traders) to be discussed by a prominent panel in Lagos, including the Central Bank director for Monetary Policy. PDF commissioned a short film[4] that included interviews with Nigerian businesses that were suffering challenges as a result of the policy. This drew on other linked PDF workstreams, interviewing a light manufacturer that was a former ‘You Win’ competition awardee, who was able to show how restrictions on FOREX for imported steel plates were forcing him to spend 35% more on inputs for his table-top gas cookers. Another example included a woman fish farmer whose business model depended on both selling locally produced fish as well as imported fish, and her case study demonstrated how her livelihood was being affected. The panel discussion was also able to draw in the early findings on unrecorded trade flows study by using one of the Chatham House team to present during the event and be part of the panel. The CBN agreed a consultation process on the policy as part of the outcomes of the event. A week later the Vice President announced that in the future Nigeria would relax restrictions on foreign exchange. At the time of this review this policy has not yet been fully relaxed, but the event does demonstrate the catalytic role a programme like PDF can play in providing a platform for under-represented voices on government policies.
[4] https://t.co/R5FN8he9c2

Youth Employment / Job Creation Summit

The World Bank has now published the evaluation of the ‘You Win’ programme using the three rounds of extensive surveys funded under PDF 1. This innovative study made use of a randomised component of the selection process under the first round of You Win in 2011 to enable a control group and treatment group to be established and followed up on over a period of three years. The findings have been powerful, showing that three years after applying for the competition the 1,200 winners of round one of ‘You Win’ created 7,000 more jobs than the control group and were more likely to be innovating, with higher sales and profits[5]. Internationally there have also been a number of positive blog posts around this evaluation and the ‘You Win’ initiative[6].
[5] For access to the full evaluation see http://documents.worldbank.org/curated/en/2015/08/24899889/identifying-spurring-high-growth-entrepreneurship-experimental-evidence-business-plan-competition
[6] http://priceonomics.com/what-happened-when-nigeria-created-the-worlds/

A key objective for PDF 2 has been to ensure an appropriate dissemination of this work with the new Nigerian Government so that they understand the implications of this work for job creation initiatives within Nigeria. Importantly, PDF 2 have seized upon this as an opportunity to learn lessons from past Nigerian initiatives and also show-case innovative approaches to creating jobs and raising incomes in Nigeria, with discussions ongoing for a Youth Employment summit with the Office of the Vice President by January 2016. During this summit there would be a presentation from David McKenzie the author of the evaluation, a short-film produced by the Federal Public Administration Reform Programme (FEPAR) on the impact of other job creation schemes in Nigeria, and a vibrant ‘ideas market place’ showcasing innovative ideas from DFID programmes and the private sector.

Despite delays in the timing of this event in order to accommodate the Office of the Vice President, extensive work has gone into preparing the format and content for this event which should have a powerful demonstration of where the Nigerian Government can help make a real impact. In order to capitalise on momentum from the new government a firm date should now be set for the event. New potential government partners from the Cabinet may also be keen to be involved.
Table 3: Recommendations on Output 1 from PDF 1 Project Completion Review (May 2015)

	Recommendation	Action(s) Taken
1.	Ensure dissemination of key studies developed under PDF phase 1 during PDF phase 2. The two most prominent undisemminated studies include the Chatham House ‘unrecorded trade and financial flows report’ and the World Bank evaluation of the youth unemployment programme ‘You Win’. Be alert to opportunities where dissemination of PDF-funded work would contribute more substantially to informing public policy debates in Nigeria; and to record more systematically, for monitoring purposes, the dissemination, use and uptake of PDF outputs both in policy and in programme design.	On Track: Chatham House study due to be presented in December. ‘Youth Employment’ summit due in January 2016.
2.	Encourage the PDF unit in continuing to take a more active role in initiating policy studies in consultation with embedded advisers.	This has been factored into the PDF model of monitoring, learning and knowledge management
3.	Reconsider establishing a PDF website, such as is done under other DFID-funded programmes.	Tendering for website has commenced.

Recommendations

- Develop and grow the use of social media and the proposed website platform for the dissemination of policy research, learning and policy influence. Identify a target audience and explore different ways of recording and disseminating key messages from PDF facilitated events.
- Establish a policy within PDF and agreed with DFID on the types of content that will be made public, and a risk mitigation policy to avoid reputational risk to DFID and ensure no damage to the UK government’s partnership with the Nigerian Government, particularly relevant for when PDF may be facilitating voices that challenge policies.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Building on the recommendations in the 2014 ITAD review of Value for Money (VfM) in Nigeria’s Economic Growth Portfolio, PDF 2 has set-up an approach to monitoring value for money during its inception period which covers the following:

1. Recording cost data and, where meaningful, calculating moving six monthly averages of unit costs (e.g. fee rates and knowledge products/deliverables) and ratios of programmable to overhead costs (Economy);
2. Relating these to the changing values of the Outputs’ indicators (Efficiencies); and
3. Learning about how and to what extent the services and products made available through the programme’s outputs are being used, or rejected, by the Champions of Change and others, including DFID, and supporting changes that promote inclusive growth and other pro-poor policy impacts (Effectiveness and Equity).
The key questions regarding VfM (including the four Es) will be also tracked through individual project terms of reference and reports and assessed against the Programme’s Output and, later on, the Outcome’s indicators[7].
[7] The requirements for comparing their values would be with the previous six monthly report and among those at output level for the current reporting period

A strict cap remains in place on overall salaries for embedded advisers to control costs of this sensitive expenditure and has already been applied on two embedded advisers recruited during the period under-review.
Quality of financial management

Financial management has been challenging given the high dependency on government counter-parts and the delays in Ministerial appointments. The majority of embedded advisers finished their contracts at the end of May. Only two have since been appointed (a communications adviser for the sovereign investment authority and a public financial management expert to the Office of the Auditor General). The net result has been that a programme that was forecast to spend £2 million through-out the financial year may now spend closer to £1 million.

The Senior Responsible Owner (SRO) will work with the programme to adjust forecasts for the financial year to appropriately accommodate the slow-start to government activity but also push forward any activities that might have been planned for the fourth quarter and put into the third quarter where possible.

A financial audit was carried out on PDF 1 at the end of the programme and recommendations have been provided to DFID and actions are currently being agreed with the service provider who has continued with PDF 2.

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK

Overall risk rating: Medium

Overview of programme risk

Context: The operating context is broadly positive (as set-out within the context in para 13), with some real opportunities for significant economic reform from the new government in areas such as oil and gas sector reform, and continued commitment to the power market development. Trade policy and monetary policy remain problematic. At the time of writing this report Ministers had not been allocated portfolios within the Cabinet and therefore there were few embedded advisers provided by the programme, but this situation will likely change rapidly over the next three to six months. [Medium risk]

Delivery: The service provider has been contracted in a flexible responsive way which minimises delivery risk due to its ability to be adaptive to the reform environment. Within each terms of reference there is a screening for gender and climate change issues (both opportunities and risks within the intervention) and the programme is at low risk of doing harm towards conflict and fragility – however this low risk would be reconsidered should PDF supply technical assistance to higher risk agencies such as the National Security Adviser. The main delivery risk to the programme is that short-term embedded adviser support can undermine long-term institutional strengthening. This risk is mitigated to an extent by PDF coordinating support with other DFID programmes and where possible, putting together a cohesive long-term package of support to build the capabilities of the agencies [Low risk].

Operational: DFID currently has the capability to manage this programme, although it should be noted that as PDF has a small in-country team it relies on DFID adviser strategic direction disproportionately compared to other programmes. [medium risk]

Fiduciary:  No funds are put through Nigerian Government systems and currently no grants are provided from the programme. If the programme does start providing grants in the future it will need to have appropriate procedures in place at this risk rating will be re-evaluated. There is an associated reputational risk due to use of embedded advisers that in some cases may have a degree of influence over the use Nigerian Government funds. [low risk]

Reputational:     As PDF starts to host more policy dialogues and make more of its studies public there is an increased risk that critical comments may be attributed to DFID harming the UK’s Government relationship with Nigerian counterparts. To mitigate this, PDF is reviewing its internal approach to making reports public and staff will avoid providing comments to the media. There is also reputational risk from the use of embedded advisers who are not directly managed by the programme. This risk is mitigated to an extent by regular performance reviews with the beneficiaries, and taking prompt action if problems are identified. [medium risk]

The overall risk rating remains unchanged at medium. The substantial uncertainty about the political environment for reforms that PDF 2 might be entering into has largely been cleared. As a result there was no need for fundamental redesign of the approach during the inception period as may have been required had the political environment for reforms been less favourable.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Contracting commenced as planned in April 2015, after an open tender process, and the inception period has been successfully completed by the programme within six months.

Performance of commercial partnership

The service provider has performed well for PDF 2 and been responsive to DFID and beneficiaries during this period. Formal feedback will soon be provided as part of DFID’s key supplier relationship process.

Asset monitoring and control

Appropriate systems and processes have been put together for asset monitoring and control and are updated regularly and shared with DFID.

G: CONDITIONALITY

Update on partnership principles (if relevant)

DFID does not provide direct financial aid to the Nigerian government although the provision of technical assistance to selected Ministers within the Nigerian Government means that the partnership principles are relevant. Improvements in the political environment since last year present a better environment for providing technical support to beneficiaries in the Nigerian Government. Yet, DFID will also need to apply careful consideration to those within the government that technical assistance is provided to. Join up with the Foreign and Commonwealth Office (FCO) in their assessment on the background and prospects of individual appointees will be important to ensure we adhere to the partnership principles along with the second phase of the political economy analysis carried out by PDF.

H: MONITORING & EVALUATION

Evidence and evaluation

There is no formal evaluation planned for PDF 2. A review of key case studies from the programme is scheduled for the mid-term review in 2017 which will provide an important opportunity for lesson learning and path-correction.

Monitoring and Knowledge Management

A logical frame work has been agreed with DFID and is in place to guide PDF II’s outputs and activities. Monitoring and Project Management tools and processes have been put in place and continue to be tested and improved upon. Through a light touch monthly project monitoring approach, PDF II has begun collecting knowledge on opportunities, threats, and lessons learned which are being fed back to DFID for better coordination and planning of DFID interventions.

PDF II Abuja office team developed templates and procedures for project administration and monitoring that incorporated new features for monitoring VfM, environmental/climate impacts, gender impacts, progress of projects towards achieving outputs and outcomes

Beneficiary Feedback

There are relatively few new partners to get feedback from at this stage. A good relationship has been forged with Directors working at the Office of the Auditor General’s office which has proved an important steering committee for DFID support. The Nigerian Sovereign Investment Authority continues to be grateful for DFID provided support (including the new communications adviser funded under PDF 2). A new working relationship has been forged between PDF and the Nigerian Economic Summit Group (NESG) in the foreign exchange policy dialogue which worked well and could be a useful partnership to continue in the future. More comprehensive beneficiary feedback will be systematically gathered as part of next year’s annual review process.

Review Process

This was a desk based review carried out by DFID’s SRO for the PDF 2 programme with inputs from the programme and reviews of the deliverables.