Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Ecosystem Services for Poverty Alleviation (ESPA)
Programme Value: £40 million / DFID contribution: £30 million, NERC contribution £7m, ESRC contribution £3m		Review Date: September 2015
Programme Code: 112082	Start Date: 30/11/2009	End Date: 31/12/ 2017

Summary of Programme Performance
Year	2009/10	2010/11	2011/12	2012/13	2013/14	2014/15
Programme Score	50.00(3)	91.25(1)	66.25(2)	A	A	A
Risk Rating	Medium	Medium	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

ESPA is an established programme that continues to produce high quality scientific research, which is reflected in the large number of peer-reviewed journal articles and citations of ESPA research. It has substantially exceeded expectations in these areas and has reached or moderately exceeded most of its other milestone targets for 2015. The future priorities for ESPA will be synthesising the findings from ESPA research, and increasing the impact of ESPA research both in development and academic terms.

Examples of ESPA’s development impact are growing as projects mature, including work in Tanzania where ESPA research has helped to inform conservation and land use policy and practice in pastoralist savanna and Miombo woodland. ESPA’s research has been used to empower local communities to demand a more equitable share of benefits derived from wildlife management.

One of ESPA’s projects was included in UKCDS’s list of the top twenty research projects contributing to global development. These were selected by an UKCDS-appointed panel from the 6,975 impact case studies submitted to the UK’s Research Excellence Framework (REF). The ESPA project chosen was the programme on conserving mangrove trees in Africa to protect local livelihoods http://www.ukcds.org.uk/the-global-impact-of-uk-research/essential-coastal-ecosystems. A further three three REF Impact Case Studies were published citing ESPA-funded activities.

During the year the contributions of a number of ESPA researchers were recognised in through the following awards:

- Miss Julie Razafimanahaka from the NGO Madagasikara Voakajy in Madagascar who works as a Co-Investigator in ESPA’s P4GES project, was recognised by The Africa Section of the Society of Conservation Biology (SCB) through their Young Women Conservation Biologists Award (YWCB).
- Professor Julia Jones at the University of Bangor, Wales was awarded the British Ecological Society’s Founders’ Prize. This award recognised her ground-breaking interdisciplinary research including her ESPA research programme, ‘P4GES: Can Paying for Global Ecosystem Services reduce poverty?’
- Professor John Dearing at the University of Southampton received the Royal Geographical Society’s Murchison Award, which is awarded for publications judged to have contributed most to geographical science in preceding recent years.  ESPA’s Programme Framework Grant “Poverty and ecology: developing a new evolutionary approach” contributed to two of ESPA most highly cited publications.
The management arrangements for the programme are working well now, with much clearer roles and responsibilities between the ESPA Directorate, the ESPA Secretariat at NERC, the Programme Executive Board (PEB) and the Programme Management Unit (PMU).

There has been some noticeable progress is improving communications from the programme although this aspect could be further improved to achieve full impact and potential. The most significant development in this area has been the ESPA website,which now has a new project finder tool that helps visitors search for projects working on specific themes and other new content produced by the Directorate. This includes: a new page on the website discussing the concept of ecosystem services; a makeover of ESPA’s monthly newsletter to provide more information describing the results generated by the programme; and a range of stories and feature articles describing ESPA’s success and ESPA’s research. This has included a leaflet describing ESPA’s work in South Asia and a feature on ESPA’s work in Bolivia,

ESPA’s Responses to Key Actions highlighted in the last Annual Review

Five areas were flagged in last years review: 1. approve strategy and workplan; 2. review and agree logframe indicators; 3. improve engagement with other agencies and initiatives on ecosystem services; 4. develop and agree a process for synthesising ESPA’s research; 5. review the commissioning progress. Progress is as follows:

The PEB has approved the forward strategy, work plan, and budget for FY 14-15 and FY 15- 16.

The Directorate has reviewed the impact indicators and metrics for the programme in the current Logframe Report (2014-15) and has made recommendations for the revision of specific indicators as part of the report. Changes to the Directorate’s KPIs were not considered necessary by PEB. Further revisions to the Logframe as per recommendations made in the Annual Review will be concluded by the end of December alongside the revision of the Impact Strategy.

With regard to engaging with other initiatives and institutions, the ESPA programme has shown some progress. ESPA organised a session at the Poverty Environment Partnership in Edinburgh in 2015 and is now planning a side event in conjunction with the UN Environment Programme at ESPA’s 2016 Annual Science Conference in Nairobi to examine the interface between Science and Policy. UNEP will also be represented at ESPA’s 2015 Science Conference.

The ESPA Directorate also plans to involve UN representatives in the Rockefeller Foundation Bellagio meetings, which will review the ten years of progress since the UN’s Millennium Ecosystem Assessment (MA) was first published in 2005.

ESPA researchers (including G. Mace and B. Reyers) have also co-authored the IPBES scientific conceptual framework - connecting people and nature, which will underpin all IPBES functions and provide structure and comparability to the syntheses IPBES will produce.

A synthesis review commissioned by the Directorate that examines the links between ecosystem services and poverty alleviation (Suich et. al., 2015), was published in January 2015. Another paper synthesising ESPA activities on frameworks linking ecosystem services and poverty alleviation has been commissioned by Aiden Keane and should be published on the ESPA website soon.

In addition, two important papers describing the need to disaggregate measures of human well-being (Daw et al., 2011) and the application of transdisciplinary research in sustainability science (Lang et al., 2012) continue to be well-cited and will contribute to the synthesis of ESPA research planned as part of the ESPA-2016 call.

These synthesis papers will be used as a framework for the 2016 call which will be focused on synthesising ESPA’s research. Further internal analysis – including the development of project typologies – will be carried out by the Impact team in preparation for the 2016 call.

ESPA has previously commissioned and published a review of the commissioning process for interdisciplinary research which is available on the website. Discussions with the ESPA Secretariat suggested that there had been limited change in processes since that report had been published and hence there would be limited value in repeating this work. The ESPA Directorate also plans to revise the Impact Strategy, which includes commissioning lesson learning studies.

The Research Councils are now interested in bringing together lessons on enhancing the capacity to do research and build impact. The ESPA Directorate is planning to hold a capacity strengthening event around impact next year. The new Impact team is planning to launch the revised Impact Strategy early next year, and to incorporate a capacity strengthening dimension to this.

Summary of recommendations for the next year

This section has the recommendations for taking forward ESPA’s prorities over the coming year and on financial and programme management (there are a number of recommendations relating to the programme outputs that can be found in Section C):

1. Synthesis. In order to take this work forward, the final ESPA call in 2016 should focus on on research projects that synthesise the main outcomes of ESPA research and should also include a synthesis of ESPA research on gender. This has been agreed in principle by the PEB but the criteria for the 2016 call will need to be finalised at the next PEB meeting in November 2015. The Directorate also has a role in undertaking research synthesis to complement the 2016 call, and this will be also discussed at the next PEB.
2. Impact. Building and enhancing programme impact will be a priority for the ESPA Directorate this year the coming year. A new Impact Strategy is being developed and this needs to be finalised by the end of December. ESPA will need to develop its impact narrative and show clear evidence of the impact of ESPA research by the time they prepare their next Annual Report for the period from April 2015-March 2016.

1. Logframe: following detailed discussions held during this AR exercise we agreed that the DFID logframe should be further revised to ensure that this focuses specifically on DFID priorities and objectives and that some of the indicators and milestones that have proven notoriously difficult to monitor and measure be redrafted and recalibrated to allow for more streamlined monitoring.(to be done by end of March 2016).
2. Communications: the programme has made noticeable improvements in this area but this has been so far limited to a few key outlets, noticeably the website. Going forward it should continue to build on the progress made so far and try to expand the remit of its communications strategy to include activities (e.g. targeted use of social media and other platforms) that could give the programme more public exposure and bring ESPA on par with other programmes of its calibre. The Directorate has also agreed a revised plan for the co-production and publication of communications outputs to target DFID needs and audiences. This should be adhered to strictly and we look forward to seeing the first outputs as planned over the remainder of this financial year..

1. Post-2015 Development Agenda. The adoption of the Global Goals, particularly Global Goal 15, Life on Land, will have important implications. Over the coming year ESPA will need to demonstrate how ESPA research can contribute to the targets under Global Goal 15.
2. Value for Money: Over the past year the Directorate has consolidated and expanded its staff and the number of people employed on a variety of roles and functions by the programme. This included new roles on impact and communications and impact advisers in two of the ESPA regions. The Director should continue to ensure that the utility of and need for these roles is reviewed regularly as the programme evolves. It is proposed that the Director report back on this in the next ESPA Annual Report.
3. Financial management: the financial management of the programme has improved significantly over the past year and the programme is now regularly hitting planned spending targets and matching yearly financial forecasts. Going forward it needs to ensure that the same level of accuracy is maintained. This is an ongoing process to be monitored by the DFID programme manager.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

ESPA is a seven year interdisciplinary research programme funded by the United Kingdom's Department for International Development (DFID), the Natural Environment Research Council (NERC) and the Economic and Social Research Council (ESRC), as part of the UK’s Living with Environmental Change partnership. DFID is providing a total of £30million (from 2010-17) to fund research on the linkages between ecosystem services and poverty alleviation, in partnership with NERC (£7 million) and the ESRC (£3 million). The total budget for ESPA is £40 million.

ESPA’s goal is to ensure that, in developing countries, ecosystems are being sustainably managed in a way that contributes to poverty alleviation as well as to inclusive and sustainable growth.

ESPA was conceived following the Millennium Ecosystem Assessment (MEA) in 2005 to explore the relationship between ecosystem services and poverty alleviation.

The global context within which the ESPA programme operates requires urgent action and a concerted international effort to avoid a global environmental collapse in future decades. Current scientific evidence shows that ecosystems are being degraded at a significant rate: 60% of ecosystem services have been assessed as either severely degraded or as being used unsustainably.

In addition, impacts arising from exogenous change, such as climate change and economic volatility are accelerating ecosystem deterioration and presenting much more acute policy and management challenges. Such changes have the potential to initiate large-scale ecosystem collapse and irreversible change. All this has significant consequences for development. The poorest and most vulnerable groups, especially those living in rural areas, tend to be most directly dependent on ecosystem services and are most likely to suffer the consequences of change. This is because poor people are also less able to access substitutes to services provided by ecosystems. Additionally ecosystems services provide a direct source of wealth for developing countries, such as through forest and fisheries products, as well as their underpinning of key economic sectors such as agriculture.

Despite international, national and local efforts to prevent the deterioration of ecosystem services, success remains limited. This is because there are many apparent trade-offs and tipping points in the policies and methods for managing ecosystem services and poverty reduction. Understanding how to manage these more effectively remains limited. ESPA aims to generate new evidence on the relationship between ecosystem services and poverty and whether these can be used sustainably to promote economic growth and improve the livelihoods of poor people across the developing world.

The ESPA programme memorandum was signed in mid-2010 and programme activities launched shortly afterwards. Since then five research calls have been commissioned generating a total of 90 projects of various sizes and duration. There will be a final research call in 2016.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

ESPA continues to make strong progress in delivering the programme outcome ‘to positively influence end users and decision makers through the generation of cutting edge evidence on ecosystem services, their full value, and links to sustainable development.’ There are four indicators to measure this outcome, which provide different angles on ESPA’s effectiveness in influencing external actors:

1. ESPA research outputs reflected in national, regional or international development policies. The target for 2015 was 8 but 19 examples of policy influence have been reported to date, including ten new examples in the last year, including influencing alternative systems for water management in Bangladesh, discussions with policy makers on biofuels in several countries in Africa and influencing new ecosystem services legislation in Peru.
2. New ESPA-related projects or activities funded by agencies outside the ESPA programme. The target for 2015 was that £30m of new research investments would have been generated for ESPA related projects. By 2015, £37.5m of new investments had been recorded.
3. Development activities or investments informed by or utilising ESPA research. The target for 2015 was that ESPA research would have influenced and shaped up to £30m on new investments or programmes on ecosystems services. By 2015 ESPA recorded £32.5m of investments and processes that had been informed by ESPA research.
4. Number of payment for ecosystem services (PES) or equivalent schemes informed by ESPA research. The target of 2015 was five PES schemes influenced by ESPA but the programme influenced ten such schemes. The 100% increase from last year, when five such investments influenced by ESPA were recorded, has been as a result of scaling up from earlier schemes in East Africa and South America to include new countries or contexts.

We have awarded ESPA an overall score of A for this review. While ESPA has reached or exceeded these outcome milestone targets for 2015, there are a number of areas where DFID would have liked to see more progress at this stage in the programme; these are communications, synthesis and value for money. Further details on these are provided in the recommendations above, particularly numbers 1, 4 and 6. Given the excellence of ESPA’s research outputs and increasing evidence of impact, there is a real opportunity for the ESPA Directorate to be more proactive in communicating theprogramme’s research findings and in seeking to analyse and synthesise the evidence emerging from the different research projects. The 2016 Call and related activities could make a major contribution to this.

Overall output score and description A+

ESPA is a mature research programme that is making strong progress against the output milestones for 2015. Of the four outputs, one was awarded an A++ scores (with a weightings of 40%), and the others were A+, A, and B (each weighted 20% each). Details on the scores for each of the milestone indicators are provided in Section C but some of the key highlights are presented here:

Research outputs. ESPA projects have now published a total of 138 journal articles to date (exceeding the 2015 milestone of 100) and over 78% of these have been published in ISI-listed publications. Furthermore, ESPA projects have produced 337 other research outputs including six books, 19 book chapters, policy briefs, reports, conference papers and working publications.

Capacity-buildng on multi-disciplinary research. ESPA projects have developed 61 new tools, guidance notes and conceptual frameworks for undertaking multi-disciplinary research on ecosystem services.

Demand for and uptake of ecosystem services for poverty alleviation. 40 new partnerships and networks by ESPA projects and 30 ESPA researchers have joined national, regional or international processes on ecosystem services.

Developing country-led partnerships. All of the 2013 projects and 80% of the 2014 projects listed at least one developing country researcher in the research team. 62% of academic papers attributed to ESPA have authors from developing countries.

Key lessons

An number of key lessons have emerged over the past year that have been identified in the ESPA Annual Report, April 2014-March 2015, and which were further discussed during the DFID Annual Review visit to ESPA.

- The importance of landscape approaches in ESPA research.
- The concepts of equity and justice are emerging as key emerging research questions and as enabling conditions to make the link between ecosystem services and poverty alleviation.
- The important of soils and soil processes in ESPA is being recognised in a growing number of projects.
- The role of integrative tools in delivering ESPA in delivering effective interdisciplinary research in this area is being highlighted by a number of projects, but this raises a new challenge of dealing with complexity and uncertainty when using these tools and approaches.
- The need to link ESPA’s research into broader macro-economic analysis has been highlighted as a key area that future research needs to address.

Some of the key lessons on building impact are highlighted below:

- Impact normally requires the application of results from more than one research project. All of the examples of impact described in ESPA’s Annual Report 2014/15 involve ESPA research being used in conjunction with results from other research projects and programmes and often other types of investment including development or conservation projects and in some cases private sector investment. .
- Interdisciplinary research delivers dividends. All but one of the examples of impact cited in the ESPA Annual Report demonstrates strong linkages or integration between social and natural sciences.
- Working in partnership: better science and enhanced impact. There is increasing anecdotal evidence from ESPA projects that working in full and effective partnership with policy makers and practitioners increases both the quality of ESPA science and the potential for building impact derived from that science. Every impact example cited in the Annual Report has clearly benefitted from the full and effect contribution of local partners, researchers and impact or development practitioners.
- Working positively with the private sector. A growing number of ESPA projects are citing examples of their positive engagement with private sector organisations to build impact. It is significant that three of the four REF Impact Case Studies that are linked to ESPA projects have described how their partnership with private sector organisations contributed to building their impact.
- Impact takes time. All of the examples of impact described in the Annual Report have taken a period of continued investment and activity of up to ten years from the first research investment. The examples provided in the report have also shown how effective ESPA investments can be in building impact from research initially funded outside the programme.
- A number of new ESPA projects are now generating evidence of the relevance of cities when describing the links between ecosystem services and poverty alleviation.

Key actions

The key action for this year will be commissioning the 2016 research call. This is a very important call for ESPA as it will commission research that will synthesise the evidence emerging from the wide range of ESPA research projects and offers a real opportunity to highlight both the scientific relevance and strength of ESPA research and its potential impact on policy and development programmes.

Has the logframe been updated since the last review? No. However we have agreed to a further revision of the logframe to enable easier monitoring of progress. We also agreed that the current set of indicators and milestones are recalibrated to better reflect DFID objectives and priorities. ESPA Directorate is, however, encouraged to maintain a broader version of the logframe that would also reflect the priorities of NERC and ESRC.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	A high quality, multi/ interdisciplinary[1] and extensive body of knowledge on ecosystem services, their dynamics and human use generated.
Output number per LF		1	Output Score	A++
Risk:		Low	Impact weighting (%):	40
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No
[1] Inter-disciplinary defined as research collaboration from at least one natural and one social or economic science discipline, multi-disciplinary defined as being research collaboration from at least two disciplines.

Indicator(s)	Milestones (2015)	Progress
1.1.1 Annual review of strategy documents identifies gaps and opportunities that shape ESPA Programme focus.	Annual review complete.	A light-touch assessment of ESPA’s strategy documents was undertaken during the year. Further revision will take place in 2015 as part of preparation for the ESPA-2016 call.
1.2.1 Total number of journal articles attributed to ESPA projects.	100	ESPA projects have continued to publish journal articles at an impressive rate, totalling 138 at the end of the reporting period. Over 78% of the articles have been published in ISI-listed publications.
1.2.2 Number of other research outcomes (books, book chapters, briefing papers, conference papers, grey literature).	300	Up to September 2015, there have been 337 other research publication outcomes including books (n=6) and book chapters (n=19), policy briefs, reports, conference papers and working publications. The majority of these outcomes could be represented as “Grey Literature”. / The ESPA Directorate suggests the 2017 target for indicator 1.2.2 should be increased to 600.
1.2.3 Percentage of total journal articles published as open access.	50% since previous milestone.	The proportion of ISI-listed publications published as open access since 1 April 2013 is 50%, equalling the target for the period. ESPA is unlikely to meet its 2017 target but suggests retaining the 100% target to acknowledge the longer-term aspiration.
1.3.1 External citations of ISI journal articles from ESPA projects in research publications.	600	ESPA continues to perform extremely well against this target achieving 1,689 citations by the 1st September. The programme has revised its targets regularly since the start of the programme and continues to exceed each revision. / The Directorate has now extrapolated the trends observed since the start of the programme and is suggesting a new, more ambitious target for 2017 of 5,000 citations of ISI-listed journal articles.

Key Points

ESPA continues to make excellent progress in delivering high quality research outputs. The number of citations of ESPA ISI journal articles increased from 800 in 2014 to 1,689 in 2015, which reflects positively on the quality and relevance of ESPA research. ESPA has also made impressive progress on gender; 42% of principal investigators for current projects are women, compared with 23% for the closed projects. Open access remains an issue for ESPA, although largely due to matters beyond its control. While ESPA has reached the milestone target for 2015 it is unlikely to meet the 2017 milestone of 100% Open Access. This largely due to the fact that many ESPA partners are not UK institutions and are not covered by RCUK financial arrangements for open access publications. DFID and RCUK have not been able to find a solution for funding open access for non UK institutions.

Summary of responses to issues raised in previous annual reviews (where relevant)

ESPA’s current policy on supporting Open Access is consistent with that of the Research Councils and DFID but this means that many of ESPA’s non UK partners do not have funding for open access.The ESPA Directorate, however, has proposed an alternative solution to address this issue. The Directorate is exploring the option of publishing articles as ’green’ open access, utilising institutional archives. For non-developed country institutions that do not have the infrastructure to self-archive, the Directorate is looking at the option of providing this service using existing infrastructure at the University of Edinburgh. If this is possible, it may also provide an option to archive a proportion of the programme’s “Grey Literature”. It is relevant to note that the ’green’ option does not fully meet the aspirations of either RCUK or DFID policy and is presented as a compromise than may help to achieve the intent if not the detail of the existing policies.

Following the latest AR discussions and recommendations to the Directorate, ESPA’s new Impact team will revise the communications strategy as part of the ongoing process to rationalise the existing suite of strategy documents (i.e. the new Impact Strategy will supersede the existing Impact, Communication, Research Into Use and Capacity Strengthening strategies). Since the last review, the communications manager has organised quarterly meetings, to which the communications representatives from all three funders have been invited. This Annual Review also provided an opportunity to discuss key DFID specific products. It was agreed that two Insight notes and a brochure will be produced before the end of the financial year focusing on key themes of interest to DFID and the wider international community.

Within the current commissioning process, the Directorate monitors outputs for gender references, monitors the gender balance of teams and recommends that projects use disaggregated data. A recent analysis shows that 42% of the Principal Investigators on active projects are women, which compares to 23% for closed projects. This analysis shows there has been a significant improvement in gender balance. Subject to a preparatory consultation exercise – alongside discussion with the Research Councils to further scope out the commissioning process – the Directorate will propose to PEB that the call includes a set of themes where research would be strongly encouraged and to include gender issues in this set as part of the ESPA 2016 call.

Recommendations

DFID and RCUK to continue to seek a solution to funding open access for non-UK research partners. This needs to be done at an institutional level and is not ESPA specific (ongoing).

- If no solution to open access is found, then ESPA will need to revise its milestone target of 100% by 2017 as this will not be achievable. (Dec 2015).
- Directorate to review communications strategy and ensure that this fits with the needs of all funders, including DFID (March 2016).

Output Title	Capability built amongst ESPA researchers to conduct multi-/inter-disciplinary ecosystems services and poverty alleviation research, supported by new interdisciplinary methods, frameworks, data, tools and syntheses.
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (2015)	Progress
2.1.1 Tools/ methods/ guidance/ frameworks that support projects to deliver multi-/interdisciplinary research.	5 new tools/ methods/ framework from ESPA projects.	61 new tools have been developed, far exceeding the target for 2015. The Directorate intends to revise the 2017 target for this indicator upward but will analyse the data collected to date before suggesting a new figure. A report will be submitted to ESPA’s PEB in November 2015. The new outcomes include a range of models and datasets from the ESPA Deltas project in Bangladesh. There was also a new interdisciplinary conceptual framework of Livelisystems in a 2014 paper “Livelisystems: a conceptual framework integrating social, ecosystem, development, and evolutionary theory” (an open access publication).
2.2.1 For each project that has published journal articles, at least one is of a multi-/interdisciplinary nature (social and natural sciences).	60% of total projects.	PPD 86% / PFG 100% / ESPA-2011 100% / ESPA-2012 67% / ESPA-2013 100% / The programme is exceeding the 2015 target and seems likely to have all main research projects (from the 2010 PFG call) meeting this target by 2017.

Key Points

ESPA has exceeded expectations on this output. There has been a proliferation of tools, methods and frameworks for conducting multi-/interdisciplinary research. Most projects have published journal articles that are of a multi-disciplinary or interdisciplinary nature involving social and natural sciences.

Summary of responses to issues raised in previous annual reviews (where relevant)

As highlighted in the Annual Report, there have been a number of difficulties with the new RCUK Researchfish system. However, the Directorate has made significant progress on integrating Researchfish into ESPA’s reporting system working with RCUK staff to extract information from the new reporting system.

It was recently discussed at the Programme Executive Board (PEB) that capacity strengthening opportunities for developing country researchers, other than fellowships, would be explored. ESPA is holding its first Summer School planned for April 2016. The School aims to enhance participants’ understanding of the way in which ecosystem services can sustainably enhance the well-being of poor people in developing countries. In addition, reflecting a request by the ESRC, the Directorate is planning to hold a ‘lessons learned’ event on approaches to capacity strengthening in 2016.

The new Impact team proposes delivering two events during 2016, in Nairobi and Delhi, to launch the Impact Strategy and enhance capacity around building impact. The Directorate will submit a short brief to PEB outlining this proposal. The Impact team will also work with stakeholders to develop strong, impact-oriented proposals for Regional Opportunities Funding, with a focus on transferring ownership to developing country partners wherever possible in terms of designing and delivering relevant and impactful projects.

Recommendations

The Directorate should consider disaggregating the data between tools, methods, guidance and frameworks given that frameworks are an important outcome and should be highlighted. The Directorate has suggested revising the 2017 target for indicator 2.1.1 upwards (by Dec 2015) as the number of methods/tools is already significantly exceeding the 2015 and 2017 targets.

Output Title	Increased demand for and uptake of ecosystems for poverty alleviation research.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (2015)	Progress
3.1.1 ESPA projects engaging in knowledge exchange: Number of impact-related records reported to ROS.	400	The latest figures for the impact related records show a total of 1,082 items across all ESPA projects. The significant increase is because the Directorate has been able to adapt this indicator to make use of data taken from the new RCUK Researchfish system. The ESPA Directorate suggests increasing the 2017 target to 1,500.
3.1.2 New partnerships and networks formed by ESPA projects and the ESPA programme and the % of these that are multi-/inter-disciplinary.	40 (60%)	This milestone has been met with 40 (62%) new partnerships developed to support the delivery of research and building impact from research. The Directorate is unable to make use of Researchfish data for this indicator. ESPA will consider options to improve reporting for this indicator in future years.
3.2.1 ESPA Directorate and researchers present their evidence to national/regional/international development panels/committees on the policy relevance of their work.	32 plus ESPA Director	There have been 19 recorded instances of researchers plus the Director presenting at various panels and committees. The ESPA Directorate is considering how alternative data might be obtained and if the 2017 target remains realistic.
3.2.2 ESPA researchers join national/ regional/ international processes.	30	This milestone has been met with 30 reported instances of ESPA researchers joining national/regional/international processes.
3.2.3 ESPA research outputs reflected in national, regional or international development policies.	8	A range of 10 new examples were reported up to the 1st September, bringing the total to 19 which far exceeds the 2015 milestone.
3.3.1 Additional co-financing for ESPA funded research.	£500 k	This currently stands at £1.2 m. Improved reporting systems have led to the very significant improvement of progress against this indicator. The largest investment was made by USAID to expand activities linked to an ESPA-2013 project in Malawi (NE/L001624/1, £500k). Contributions in-kind have not been included here, and would add an additional £500k. This will be accounted for in the revised logframe.

Indicator(s)	Milestones (2015)	Progress
3.3.2 New ESPA-related projects or activities funded by agencies outside the ESPA programme.	£30 m	ESPA projects have leveraged over £37m of additional funding for related projects and activities. One recent project is a £500k grant from the Netherlands Organisation for Scientific Research (NWO) on “Conflict and Cooperation in the management of climate change” in Bangladesh building on the ESPA evidence and impact grant EIRG-2011-175.
3.4.1 Development activities or investments informed by or utilising ESPA research.	£30 m	£32.6 million has been secured for activities informed by ESPA research. The programme is on track to exceed the 2017 target of supporting the development and implementation of projects with a combined value equal to the UK’s investment in the ESPA programme.
3.4.2 Number of Payment for Ecosystem Service (PES) or equivalent schemes informed by ESPA research.	5	10 PES schemes have been implemented, already hitting the 2017 target. The growth in the number of PES schemes influenced by ESPA over the year has been as a result of scaling out from earlier schemes in East Africa and South America to include new countries or contexts. It is not yet clear if further progress is likely for the remainder of the programme and the Directorate recommends reviewing this indicator in 2016.

Key Points

ESPA has performed strongly against the milestones for Output 3. Given the difficulty of measuring increased demand and uptake, nine indicators have been used to provide a number of different approaches to measuring this output. Most of the targets for these indicators have been exceeded but the indicator on number of ESPA researchers that have presented at international, regional or national panels and committees on the policy relevance of their work is off track.

Summary of responses to issues raised in previous annual reviews (where relevant)

The ESPA Directorate has made suggestions for the revision of targets, where evidence has been available and these have been highlighted in the Logframe Report. For example, the target for the number of citations and publications has been increased. It was agreed at the July PEB that indicators in the Logframe could be revised. This will be done by the end of December.

Over the last year, ESPA has engaged with a number of programmes, included a number of DFID-funded programmes such as IPBES, DARWIN and WAVES. ESPA also organised a session at the Poverty Environment partnership in Edinburgh in 2015 and is now planning a side event in conjunction with the UN Environment Programme at ESPA’s 2016 Annual Science Conference in Nairobi to examine the interface between Science and Policy. UNEP will also be represented at ESPA’s 2015 Science Conference. The ESPA Directorate also plans to involve IPBES representatives in the Rockefeller Foundation Bellagio meetings which will review the ten years of progress since the UN’s Millennium Ecosystem Assessment (MA) was first published in 2005. ESPA researchers (including G. Mace and B. Reyers) have also co-authored the IPBES scientific conceptual framework – connecting people and nature, which will underpin all IPBES functions and provide structure and comparability to the syntheses IPBES will produce.

The new Impact team are currently reviewing the Impact Strategy. This will involve rationalising the existing suite of strategy documents i.e. the new Impact Strategy will supersede the existing Impact, Communication, Research Into Use and Capacity Strengthening strategies.

Recommendations

The Impact team will develop a Delivery Plan to operationalise the revised Impact Strategy and make explicit links with all ESPA functions.(By Dec 2015)

In consultation with DFID, the Logframe indicators for Output 3 will be rationalised and the number of indicators reduced to remove overlap. (By Dec 2015)

Output Title	New developing country-led partnerships and networks formed and delivering ecosystems services and poverty-alleviation, research, influencing and impact.
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (2015)	Progress
4.1.1 Percentage of projects with developing country researchers listed in project applications, disaggregated by call.	75% of projects since last milestone / (ESPA-2013 and ESPA-2014	All ESPA-2013 projects listed at least one DC staff member as part of their project teams on the application. / 80% of ESPA-2014 projects also include at least one developing country researcher listed on the application.
4.1.2 Proportion of cost allocated to developing country researchers as shown in project applications.	40% DC or unknown	DC 26% / Non-DC 38% / Other 4% / Unknown 31% / The proportion of staff costs going to DC institutions and researchers is within the range of 26-57% for all ESPA projects, with a significant proportion unknown due to how data is collected during application. The 2015 and 2017 targets have been achieved.
4.2.1 Percentage of academic papers attributed to ESPA with developing country authorship.	65%	The ESPA programme has slightly underachieved against this target at 62% of academic papers with developing country authorship. The Directorate will continue to encourage projects to include developing country partners in their publications. / It is important to note that further progress against this indicator requires both culture change and capacity strengthening for ESPA researchers and hence will take time. Recognising this, ESPA and DFID agreed to reduce the 2017 target to 70% at the AR meeting.
4.2.2 Percentage of publications attributed to ESPA with a developing country lead author.	35%	26% of publications currently have a DC lead author. The programme is underachieving on this indicator, in part because academic institutions will only allocate Open Access funds if one of their academics is the lead author for a paper. The Directorate will continue to encourage projects to have developing country authors leading the production of more papers. / As with 4.2.1, progress against this indicator requires both culture change and capacity strengthening for ESPA researchers and hence will take time. Recognising this, ESPA and DFID agreed to reduce the 2017 target to 35% at the AR meeting.

4.3.1 Number of DC researchers who are recognised for the quality of their research by advising or participating on national or international advisory, planning or decision-making bodies related to ecosystem services and poverty alleviation.	10	14 researchers have been reported by projects as contributing to national or international advisory, planning or decision-making bodies related to ES for PA. / New outcomes reported during the year included the development of a community-based lake monitoring protocol in Kenya to respond to policy makers' objectives to provide communities with the capacity to share in the monitoring of the resources on which they depend. Also in Kenya, ESPA research has contributed to the development of a Community Forest Association for coastal mangroves which required the project and local communities to work with government planning authorities to adapt the legal instrument and process to meet the needs of the coastal context. / It is suggested that the 2017 target is reviewed in 2016.

Key Points

Overall ESPA met expectations for Output 4. There are high levels of developing country participation in ESPA projects (nearly 50%) and most major research projects have significant representation in the team leading the research. There are good levels of developing country authorship of publications but this is one area where the programme has just missed its very ambitious 2015 target of 65% since the start of the project with a total of 62% reported. One indicator that did not meet the targets are the percentage of ESPA papers with a developing country lead author.

Summary of responses to issues raised in previous annual reviews (where relevant)

The ESPA Directorate routinely encourages researchers to create more opportunities for developing country authorship. There has been noticeable progress in improving the percentage of papers that have developing country authorship, although the programme slightly underperformed against this indicator this year and remains off target for 2017. Data shows that on the 1st April 2014, 47% of papers had DC authorship. By the 1st September this number stood at 62% of papers – a 15% increase in the last year. This change can be attributed to a change in ESPA policy, which improved dialogue with projects and made it a requirement for ESPA projects to include developing country researchers at the proposal stage in all newly launched ESPA projects. Both the Directorate and DFID recognise that further progress against this indicator requires both culture change and capacity strengthening for ESPA researchers. The Directorate does not expect to achieve the 100% target for 2017, but will retain the target as an aspiration. The ESPA Directorate will continue to remind researchers of their obligation to recognise the contribution of developing country authorship.

The ESPA Directorate has improved its ability to collect supplementary data through the constant evolution of existing reporting tools and the introduction of new tools. ESPA routinely collects data on additional staff on the research projects, including students and gender information (64% of students are female). The ESPA Directorate has also developed an impact template, which all projects have been asked to complete detailing any social, economic and environmental outcomes flowing from their project work. The Directorate has received several completed templates and will analyse these results. The Impact team will also support researchers going forward to ensure templates are completed appropriately.

Recommendations
The Directorate should step up its efforts to improve developing country authorship across the programme. The Directorate should develop an action plan for this by the end of this financial year.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for ESPA are staff costs and associated expenditure related to undertaking research activities which are consistent with the original business case. These have not changed since the last annual review. Capital costs, consumables and other subsidiary costs such as travel incurred by downstream implementing partners are kept within fixed limits that have been set by the UK Research Councils based on a system of benchmarking.

The programme management costs, which include a financial allocation to the Directorate were the subject of intense discussion during the last reporting period. As a result of extensive negotiations at the PEB level these issues have now been resolved with a revised spending profile for the Directorate agreed. Anticipated Directorate administration spend for FY 15/16 will equate to roughly 3% of the total programme budget.

VfM performance compared to the original VfM proposition in the business case

The programme continues to represent VfM. The VfM indicators identified during the design process for the Programme Memorandum (pre dates the Business Case template) remain valid. ESPA continues to adopt the principles outlined in the Programme Memorandum of Economy, Efficiency and Effectiveness.

Assessment of whether the programme continues to represent value for money

Overall the programme continues to represent good VfM, especially in relation to the level of scientific/academic outputs generated and their recorded impact in expanding the body of knowledge in the field covered by the programme.

As highlighted above we have worked with the Directorate to maximise VfM to ensure that administrative costs are kept to a minimum. We will continue to monitor this through the PMU and PEB meetings.

Quality of financial management

The quality of financial management and accuracy of financial forecasting is good. Invoices are received on time and are consistent with forecasts provided to DFID. Funds held by the Directorate for working capital are within the agreed limits as set out by the PEB.

At quarterly PMU meetings the Directorate provides a financial update report, which outlines the spending profile of the ESPA Directorate for the current financial year-to-date, provides a narrative of explanation for the key areas of variance and a current year-end prediction of actual expenditure.

During this reporting period an audit , commissioned by the ESPA Directorate, was concluded on a sub component of the programme. The report highlighted a number of control weakness around the management of downstream partners. All recommendations from the audit report have been actioned in accordance with the report. In addition, DFID have undertaken extensive work with NERC to establish and develop a proportionate due diligence process for downstream developing country partners. This has now been put into operation.

Date of last narrative financial report	June 2015
Date of last audited annual statement	N/A HMG

E: RISK (½ page)

Overall risk rating: Low/Medium/High

The overall risk rating for the programme is Medium. No change since the last annual review.

Overview of programme risk

Programme level risks are reviewed and assessed on a quarterly basis by the PMU. During the reporting period the programme remained responsive to both the outbreak of Ebola and the Nepal earthquake which impacted on delivery. These were new risks which had not been anticipated during the design of the programme. In the case of Ebola, ESPA produced a business continuity plan which was subsequently approved by DFID. With regards to the Nepal earthquake, there has been a significant impact on 2 ESPA projects which are physically active in the country resulting in significant delays in implementation. At present both projects consider that it should be possible to complete their research activities through the standard 6-month no costs extension that is available to NERC administered grants.

As noted under section above relating to ‘Quality of financial management’ DFID worked with NERC to develop a proportionate Due Diligence assessment for developing country partners, as this was an area highlighted in the audit report. All recommendations have been actioned.

Outstanding actions from risk assessment

There are currently no outstanding actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is not on-track to finish by the original end date for ESPA of January 2018. As highlighted in the last review, due to some initial delays in commissioning research calls a final call for proposals will be made in 2016. ESPA will commission a final set of academic synthesis studies of key topics that have emerged in the field since the ESPA programme commenced. ESPA has requested a no-cost extension until March 2019. NERC and ESRC have already agreed to this and DFID will make a decision on this in the second half of 2016.

Performance of partnership (s)

The overall programme level partnership between DFID, ESRC and NERC is working effectively and ensuring that the programme remains on track and continues to deliver high quality results in accordance with the original business case. The partnership has continued to mature and all parties now have a clearer understanding of our respective institutional priorities and differences in operational standards and procedures.

Asset monitoring and control

ESPA is a jointly funded programme with the UK Research Councils and we rely on their internal systems and controls. In addition, the ESPA programme principally commissions research which does not involve the procurement or purchase of significant assets or infrastructure. Where assets are procured the Directorate monitors the use and disposal whilst adhering to RCUK procedures.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable in this instance.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

An independent mid-term review of ESPA was commissioned by the Programme Executive Board following DFID’s express request. The mid-term review started September 2013 and was completed in March 2014. It was conducted by Ricardo-AEA, with scientific support from Professor Jouni Paavola (University of Leeds), and has been managed by the ESRC on behalf of the funders. The MTR team found that the ESPA Programme is making positive progress in a number of areas:
- Delivery against the logical framework indicators;
- Delivery of academic/scientific outputs;
- Strengthening the ability of academic stakeholders to deliver academic impacts;
- Making conceptual advances in understanding and reframing issues relating to policy and practice for Ecosystem Services.

More details of the mid-term review were provided in last year’s annual review.

Monitoring progress throughout the review period

Throughout the reporting period the ESPA Directorate has provided regular reports to DFID, including a comprehensive ESPA Annual Report in June 2015 and a Logframe Report in September that reported on progress against each of the logframe milestones. The ESPA Directorate has a strong reporting system to monitor progress on individual projects. They have also been able to respond quickly to DFID requests for additional information when required. In additional to ESPA reports, further information is gathered through discussions at the ESPA PEB and PMU which the DFID SRO and DFID programme manager are members of respectively.

 This annual review was undertaken by Andrew Clayton, Alessandro Moscuzza and Kevin Leitch.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process