## SSW
PROJECT NAME | Africa Enterprise Challenge Fund: SSW
IMPACT | Impact Indicator 1 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Global market conditions are likely to be worse than baseline year. Political events are likely to increase the current and already high perceived risk of investing in South Sudan. Market system improvements and investments in businesses in South Sudan are likely to be limited. Positive demonstration effect achieved and proved.
Expansion of innovative and commercially viable agricultural and agribusiness sector that benefits the rural poor | Increase in the percentage contribution of agriculture to overall non-oil economy GDP | Actual / projected
Source | bar: 2008 to 2017
| Impact Indicator 2 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Increased lending by commercial banks to the agribusiness sector | Actual / projected
Source | bar: 2008 to 2017
OUTCOME | Outcome Indicator 1 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Assumptions
Jobs created and income increased for the rural poor. Wider market systems improved. | Cumulative development impact: (a) total net benefit (US$); (b) total net wages (US$); (c) development rate of return (DRR) = ratio of development impact (a + b) to funds disbursed (4.5f). | Planned | a) Total net benefit | 2014: 7500000; 2015: 15000000; 2016: 20000000; 2017: 20000000; 2018: 20000000; 2019: 20000000; 2020: 20000000 | AECF successfully identifies business concepts with pro-poor potential. Positive demonstration effect achieved and used to influence market systems. AECF has the appropriate skills and capacity to support African agri business to implement successful initiatives. Global market conditions are likely to be worse than baseline year. Political events are likely to increase the current and already perceived risk of investing in SouthSudan.
|  |  | b) Total net wages | 2014: 240000; 2015: 370000; 2016: 500000; 2017: 635000
c) DRR | bar: 2011 to 2017
|  | Achieved | a) Total net benefit | 2013: 224000; 2014: 0; 2015: 0; 2016: 0; 2017: 0
|  |  | b) Total net wages | 2013: 120000
|  |  | c) DRR | 2013: 0.31647; 2014: 0; 2015: 0; 2016: 0; 2017: 0
Source | bar: 2008 to 2016
M&E reports submitted by grantees verified by AECF and independent evaluation of the AECF (EMU).
| Outcome Indicator 2 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Cumulative (US$): (a) grantee matched funding (sum of grantee: cash, in-kind, re-invested profits); (b) third party funding (sum of actual third party: equity investments, loans, in-kind, supplier credit, grants from other funders, bank loans, bank overdrafts); and (c) funding successfully facilitated by AECF Connect. | Planned | a) Grantee matched | 2013: 1731000
|  |  | b) Third party | 2013: 50000
|  |  | c) AECF Connect | 2013: 0
|  |  | d) Total | 2013: 1781000; 2014: 3500000; 2015: 4500000; 2016: 5500000; 2017: 5500000
|  | Achieved | a) Grantee matched | 2013: 1750000
|  |  | b) Third party | 2013: 440000
|  |  | c) AECF Connect | 2013: 0
|  |  | d) Total | 2013: 2190000; 2014: 0; 2015: 0; 2016: 0; 2017: 0
Source | bar: 2008 to 2017
M&E reports submitted by grantees verified by AECF and independent evaluation of the AECF (EMU).
| Outcome Indicator 3 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Number of ongoing projects: (a) bringing a new technology or business model; (b) replicated by other market players in some way; or that have (c) led to other systemic changes (regulatory, factor and other markets). | Planned | a) New tech or model | bar: 2011 to 2014
|  |  | b) Replicated | 2013: 0; 2015: 2; 2016: 4
c) Systemic change | bar: 2011 to 2014
|  | Achieved | a) New tech or model | 2013: 0
|  |  | b) Replicated | 2013: 0
|  |  | c) Systemic change | 2013: 2
M&E reports submitted by grantees verified by AECF, independent evaluation of the AECF (EMU), and commissioned case studies on systemic impact.
OUTPUT 1 | Output Indicator 1.1 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Assumptions
Business initiatives supported by the AECF generate development benefits with high outreach, in particular to: those in rural areas; very poor; women; and youth. | Net number of primary beneficiaries benefitting from ongoing AECF funded projects, by year, expressed as number of: (a) households; and (b) people. | Planned | a) Households | 2013: 10000; 2014: 15000; 2015: 20000; 2016: 30000; 2017: 50000 | Smallholder farmers have skills and capital to take advantage of new demand for agricultural products. The poor in rural areas have the skills to take advantage of new job opportunities created by increased demand/ new technology/ new business models. Political events do no negatively affect business performance. Conditions for doing business will be challenging. Global market conditions are likely to be worse than baseline year.
|  |  | b) People | 2013: 50000; 2014: 75000; 2015: 100000; 2016: 150000; 2017: 250000
|  | Achieved | a) Households | 2013: 2800; 2014: 0; 2015: 0; 2016: 0; 2017: 0
|  |  | b) People | 2013: 14000; 2014: 0; 2015: 0; 2016: 0; 2017: 0
Source
M&E reports submitted by grantees verified by AECF, commissioned verification studies and independent evaluation of the AECF (EMU).
| Output Indicator 1.2 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Average net benefit per household per year (US$). | Planned | Average net benefit | 2014: 0; 2015: 80; 2016: 85; 2017: 85
|  | Achieved | Average net benefit | 2013: 80; 2014: 0; 2015: 0; 2016: 0; 2017: 0
Source
M&E reports submitted by grantees verified by AECF, commissioned verification studies and independent evaluation of the AECF (EMU).
| Output Indicator 1.3 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Percentage of direct primary beneficiaries that live in rural areas. | Planned | Percentage rural | 2011: 60%; 2012: 60%; 2013: 60%; 2014: 60%; 2015: 60%; 2016: 60%; 2017: 60%
|  | Achieved | Percentage rural | bar: 2011 to 2013
Source | bar: 2008 to 2017
Extrapolated data from commissioned verification studies.
| Output Indicator 1.4 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Percentage of direct primary beneficiaries that are poor (i.e., earn less than US$2 per day). | Planned | Percentage poor | 2011: 50%; 2012: 50%; 2013: 50%; 2014: 50%; 2015: 50%; 2016: 50%; 2017: 50%
|  | Achieved | Percentage poor | bar: 2011 to 2013
Source | bar: 2008 to 2017
Extrapolated data from commissioned verification studies.
| Output Indicator 1.5 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Percentage of direct primary beneficiaries that are women. | Planned | Percentage women | 2011: 50%; 2012: 50%; 2013: 50%; 2014: 50%; 2015: 50%; 2016: 50%; 2017: 50%
|  | Achieved | Percentage women | bar: 2011 to 2013
Source | bar: 2008 to 2017
Extrapolated data from commissioned verification studies.
| Output Indicator 1.6 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Net additional jobs created (FTE) through/in enterprises supported by AECF: (a) men; (b) women; and (c) youth (18-35 years). | Planned | a) Men | bar: 2011 to 2014
b) Women | bar: 2011 to 2014
IMPACT WEIGHTING |  |  | c) Youth (18-35 years) | bar: 2011 to 2014
|  |  | Total = (a) + (b) | 2015: 80; 2016: 85; 2017: 90
30% |  | Achieved | a) Men | 2013: 53
|  |  | b) Women | 2013: 23
|  |  | c) Youth (18-35 years) | 2013: 54
|  |  | Total = (a) + (b) | 2013: 76; 2014: 0; 2015: 0; 2016: 0; 2017: 0
Source | bar: 2008 to 2017
M&E reports submitted by grantees verified by AECF, commissioned verification studies and independent evaluation of the AECF (EMU).
OUTPUT 2 | Output Indicator 2.1 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Assumptions
The business initiatives supported by AECF (and the products and services delivered through them), are sufficiently commercially viable that the associated development impacts are sustainable. | Ongoing projects that are profitable 36 months from date of contract: (a) total number; and (b) percentage Profitable = EBITDA greater than zero. | Planned | a) Number | 2015: 0; 2016: 2; 2017: 4 | The business ideas chosen by AECF IC are viable and profitable. Global market conditions are likely to be worse than baseline year and conditions for doing business remain challenging. Companies are able to repay the repayable grants. The private sector has the opportunity, capacity and resources to invest. Profitable private sector businesses can sell products that improve the lives of poor people
|  |  | b) Percentage = (a) / (3.1) | 2015: 0%; 2016: 40%; 2017: 80%
|  | Achieved | a) Number | 2014: 0; 2015: 0; 2016: 0; 2017: 0
b) Percentage = (a) / (3.1) | bar: 2011 to 2017
Source | bar: 2008 to 2017
M&E reports submitted by grantees verified by AECF.
| Output Indicator 2.2 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
IMPACT WEIGHTING | % repayable funds due for repayment that are repaid. (a) = cumulative total repayable grants due (US$); and (b) cumulative total repayable grants repaid (US$), (c) = percentage. | Planned | a) Total repayable due | 2015: 0; 2016: 325000; 2017: 593468; 2018: 1023468
b) Total repayable repaid | bar: 2011 to 2014
25% |  |  | c) Percentage = (b) / (a) | bar: 2011 to 2017
|  | Achieved | a) Total due | bar: 2011 to 2013
b) Total repaid | bar: 2011 to 2013
c) Percentage = (b) / (a) | bar: 2011 to 2017
Source | bar: 2008 to 2017
AECF Grants Team.
OUTPUT 3 | Output Indicator 3.1 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Assumptions
AECF identifies and supports business initiatives which generate sustained and positive development impacts and which are innovative. | Total number of ongoing projects. This is used for the percentage calculation for indicators 3.2b, 3.3b, and 3.4b. | Planned | Number | 2015: 5; 2016: 5; 2017: 5 | Innovative business models are adopted and copied by other businesses, including those supported by the AECF. Investment climate/business environment constraints do not prohibit replication across countries.
|  | Achieved | Number | 2013: 5
Source | bar: 2008 to 2017
AECF Grants Team.
| Output Indicator 3.2 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Ongoing projects that are marked 3 or above on the AECF innovation scale: (a) total number; and (b) percentage. | Planned | a) Number | 2015: 3; 2016: 3; 2017: 3
|  |  | b) Percentage = (a) / (3.1) | 2015: 60%; 2016: 60%; 2017: 60%
|  | Achieved | a) Number | 2013: 4
|  |  | b) Percentage = (a) / (3.1) | 2013: 80%
Source | bar: 2008 to 2017
M&E reports submitted by grantees verified by AECF, commissioned verification studies and independent evaluation of the AECF (EMU).
| Output Indicator 3.3 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Ongoing projects achieving high development impact: (a) total number; and (b) percentage. High development impact: generates a total net benefit of US$250k or more per annum. | Planned | a) Number | 2015: 0; 2016: 0; 2017: 0
b) Percentage = (a) / (3.1) | bar: 2011 to 2017
|  | Achieved | a) Number | 2013: 0
b) Percentage = (a) / (3.1) | bar: 2011 to 2017
Source | bar: 2008 to 2017
IMPACT WEIGHTING |  | M&E reports submitted by grantees verified by AECF, commissioned verification studies and independent evaluation of the AECF (EMU).
| Output Indicator 3.4 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
25% | Ongoing projects where innovation is recognised: (a) total number; and (b) percentage. | Planned | a) Number | 2015: 1; 2016: 2; 2017: 3
|  |  | b) Percentage = (a) / (3.1) | 2015: 20%; 2016: 40%; 2017: 60%
|  | Achieved | a) Number | 2013: 0
b) Percentage = (a) / (3.1) | bar: 2011 to 2017
Source | bar: 2008 to 2017
Dissemination by third parties* through the media, conferences, case studies, or published documents, as identified and referenced in the M&E reports submitted by grantees and verified by AECF. *excludes dissemination by AECF, FM, donors and AGRA.
OUTPUT 4 | Output Indicator 4.1 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Assumptions
AECF identifies, selects, contracts and provides managed support to business initiatives. | Cumulative number of: (a) competitions closed; (b) registrations completed; (c) applications received; and (b) eligible concept notes marked. | Planned | a) Competitions | 2012: 1; 2014: 2 | Additional donors can be persuaded to support complementary value chain initiatives with sufficient funds to contribute to impact at scale. Other programmes are effective in supporting South Sudan such that business environment improves over time.
b) Registrations | bar: 2011 to 2014
|  |  | c) Applications | 2012: 150; 2014: 200
d) Marked concept notes | bar: 2011 to 2014
|  | Achieved | a) Competitions | bar: 2011 to 2014
|  |  | b) Registrations | 2011: 493; 2012: 493; 2013: 493; 2014: 493
|  |  | c) Applications | 2011: 187; 2012: 187; 2013: 187; 2014: 187
|  |  | d) Marked concept notes | 2011: 116; 2012: 116; 2013: 116; 2014: 116
Source | bar: 2008 to 2017
AECF Operations Department.
| Output Indicator 4.2 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Cumulative number of: (a) full applications (i.e. business plans) submitted; (b) approved; and (c) approval rate. | Planned | a) Full applications | 2012: 20; 2014: 20
|  |  | b) Approved | 2012: 11; 2014: 11
|  |  | c) % : (b) / (a) | 2012: 55%; 2014: 55%
|  | Achieved | a) Full applications | 2011: 15; 2012: 15; 2013: 15; 2014: 15
|  |  | b) Approved | 2011: 6; 2012: 6; 2013: 6; 2014: 6
|  |  | c) % : (b) / (a) | 2011: 40%; 2012: 40%; 2013: 40%; 2014: 40%
Source | bar: 2008 to 2017
AECF Operations Department.
| Output Indicator 4.3 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Cumulative number of projects successfully contracted. | Planned | Projects contracted | 2012: 11; 2015: 5; 2016: 5; 2017: 5
|  | Achieved | Projects contracted | 2011: 5; 2012: 5; 2013: 5; 2014: 5
Source | bar: 2008 to 2017
AECF Grants Team.
| Output Indicator 4.4 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Cumulative number of contracted projects that closed before their original contract end date. | Planned | Closed projects | 2015: 0; 2016: 0; 2017: 1
|  | Achieved | Closed projects | 2013: 0
Source | bar: 2008 to 2017
AECF Grants Team.
| Output Indicator 4.5 |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Cumulative project funding pipeline metrics: (a) new funds available to projects (US$); (b) funds committed to projects at IC stage, pre-contract signature (US$), (c) % available funds committed; (d) funds contracted to projects (US$); (e) % available funds contracted; (f) funds disbursed to projects (US$); and (g) % available funds disbursed | Planned | a) Total funds available | bar: 2011 to 2014
b) Total funds committed | bar: 2011 to 2014
c) Percentage = (b) / (a) | bar: 2011 to 2017
d) Total funds contracted | bar: 2011 to 2014
e) Percentage = (d) / (a) | bar: 2011 to 2017
f) Total funds disbursed | bar: 2011 to 2014
g) Percentage = (f) / (a) | bar: 2011 to 2017
|  | Achieved | a) Total funds available | 2013: 4472000; 2014: 4472000
IMPACT WEIGHTING |  |  | b) Total funds committed | 2013: 3935000; 2014: 3935000
|  |  | c) Percentage = (b) / (a) | 2013: 87.99%; 2014: 87.99%
20% |  |  | d) Total funds contracted | 2013: 3935000; 2014: 3935000
|  |  | e) Percentage = (d) / (a) | 2013: 87.99%; 2014: 87.99%
|  |  | f) Total funds disbursed | 2013: 1087000; 2014: 1087000; 2015: 1087000; 2016: 1087000; 2017: 1087000
|  |  | g) Percentage = (f) / (a) | 2013: 24.31%; 2014: 24.31%
Source | bar: 2008 to 2017
AECF Grants and Finance Teams.
INPUTS (US$) | Cumulative donor funds committed (US$). |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
|  | DFID |  | 2011: 10722000; 2012: 10722000; 2013: 10722000; 2014: 10722000; 2015: 6021766
|  | Sida |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | DFAT |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | RNE/MNFA |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | Danida |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | IFAD |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | CGAP (World Bank) |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | AusAid |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | SEDF |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | Netherlands |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | Other 4 - insert as necessary |  | 2011: 0; 2012: 0; 2013: 0; 2014: 0; 2015: 0
|  | Total |  | 2011: 10722000; 2012: 10722000; 2013: 10722000; 2014: 10722000; 2015: 6021766; 2016: 0; 2017: 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Outcome 1.a |  | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 7500000 | 15000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000
|  |  | Achieved | 0 | 0 | 0 | 0 | 0 | 224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Outcome 1.b |  | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 370000 | 500000 | 635000 | 0 | 0 | 0
|  |  | Achieved | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Outcome 1.c |  | Planned | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Achieved | 0 | 0 | 0 |  |  | 0.31647 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Outcome 2 | Planned | a) Grantee matched | 0 | 0 | 0 | 0 | 0 | 1731000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | b) Third party | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | c) AECF Connect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Achieved | a) Grantee matched | 0 | 0 | 0 | 0 | 0 | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | b) Third party | 0 | 0 | 0 | 0 | 0 | 440000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | c) AECF Connect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Output 1.1b |  | Planned | 0 | 0 | 0 | 0 | 0 | 50000 | 75000 | 100000 | 150000 | 250000 | 0 | 0 | 0
|  |  | Achieved | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Output 1.2 |  | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 85 | 85 | 0 | 0 | 0
|  |  | Achieved | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Output 1.6 |  | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 85 | 90 | 0 | 0 | 0
|  |  | Achieved | 0 | 0 | 0 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Output 2.1b |  | Planned | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40% | 80% | 0% | 0% | 0%
Achieved | bar: 2011 to 2013; 2018 to 2020
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Output 3.1 |  | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0
|  |  | Achieved | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Output 3.3a |  | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Data by round
Data disagregation by Window Round
Outcome Indicator 1a: Total net benefit
|  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
AAW | Round 1 | Planned | [5 empty] | 10038000 | 20000000 | 50000000 | 55000000 | 67500000 | 67500000 | 67500000 | 67500000
|  | Achieved | 2013: 11258000
| Round 2 | Planned | bar: 2014 to 2019
Achieved | bar: 2014 to 2019
| Round 3 | Planned | bar: 2020
Achieved
General Window | Early bird | Planned |  |  | 5000000 | 27500000 | 50000000 | 150000000 | 250000000 | 250000000 | 250000000 | 250000000 | 250000000 | 250000000 | 250000000
|  | Achieved | 2009: 31000; 2010: 127000; 2011: 37590000; 2012: 50820000; 2013: 53280000
| Round 1 | Planned | bar: 2008 to 2014
|  | Achieved | 2009: 974000; 2010: 4000000; 2011: 7300000; 2012: 10700000; 2013: 13500000
| Round 2 | Planned | bar: 2008 to 2014
|  | Achieved | 2009: 1446000; 2010: 8303000; 2011: 16350000; 2012: 30675000; 2013: 40649000
| Round 3 | Planned | bar: 2009 to 2015
|  | Achieved | 2010: 4372000; 2011: 8875000; 2012: 11740000; 2013: 11785000
PCW | Round 1 | Planned | [5 empty] | 650000 | 2500000 | 5625000 | 7500000 | 10000000 | 12500000 | 12500000 | 12500000
|  | Achieved | 2013: 217000
| Round 2 | Planned
Achieved
| Round 3 | Planned
Achieved
REACT | Round 1 | Planned | bar: 2010 to 2016
|  | Achieved | 2012: 642000; 2013: 2727000
| Round 2 | Planned | bar: 2011 to 2017
|  | Achieved | 2013: 882000
| Round 3 | Planned | bar: 2014 to 2020
Achieved | bar: 2014 to 2020
RIB | Round 1 | Planned | bar: 2010 to 2016
|  | Achieved | 2011: 861000; 2012: 7913000; 2013: 36307000
| Round 2 | Planned | bar: 2010 to 2016
|  | Achieved | 2013: 87000
| Round 3 | Planned
Achieved
SSW | Round 1 | Planned | [5 empty] | 0 | 7500000 | 15000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000
|  | Achieved | 2013: 224000
| Round 2 | Planned
Achieved
| Round 3 | Planned
Achieved
TZ | Round 1 | Planned | 2015: 2250000; 2016: 3500000; 2017: 3500000; 2018: 3500000; 2019: 3500000; 2020: 3500000
|  | Achieved | 2011: 12000; 2012: 950000; 2013: 1647000
| Round 2 | Planned | 2015: 4000000; 2016: 5850000; 2017: 9025000; 2018: 9025000; 2019: 9025000; 2020: 9025000
Achieved | bar: 2011 to 2017
| Round 3 | Planned | 2015: 125000; 2016: 2000000; 2017: 4275000; 2018: 5500000; 2019: 7150000; 2020: 9000000
Achieved | bar: 2014 to 2020
ZW | Round 1 | Planned |  |  | 50000000 | 50000000 | 50000000 | 62500000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000
|  | Achieved | 2010: 3531000; 2011: 6350000; 2012: 9000000; 2013: 14059000
| Round 2 | Planned | bar: 2011 to 2017
|  | Achieved | 2011: 924000; 2012: 2894000; 2013: 4153000
| Round 3 | Planned | bar: 2012 to 2018
Achieved | bar: 2012 to 2018
Output Indicator 1.1a: Net number of primary beneficiaries benefitting from AECF funded projects, by year, expressed as number of households
|  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
AAW | Round 1 | Planned | 2008: 0; 2013: 50000; 2014: 100000; 2015: 200000; 2016: 275000; 2017: 300000
|  | Achieved | 2008: 0; 2012: 0; 2013: 67000
| Round 2 | Planned | 2008: 0
|  | Achieved | 2008: 0
| Round 3 | Planned
Achieved
General Window | Early bird | Planned | 2010: 40000; 2011: 120000; 2012: 200000; 2013: 350000; 2014: 500000
|  | Achieved | 2009: 340; 2010: 1300; 2011: 159000; 2012: 54000; 2013: 13000
| Round 1 | Planned | bar: 2008 to 2014
|  | Achieved | 2009: 33000; 2010: 44000; 2011: 58000; 2012: 53000; 2013: 61000
| Round 2 | Planned | bar: 2008 to 2014
|  | Achieved | 2009: 8000; 2010: 15000; 2011: 22000; 2012: 23000; 2013: 33000
| Round 3 | Planned | bar: 2010 to 2015
|  | Achieved | 2010: 15000; 2011: 45000; 2012: 23000; 2013: 17000
PCW | Round 1 | Planned | 2013: 25000; 2014: 25000; 2015: 40000; 2016: 50000; 2017: 75000; 2018: 100000
|  | Achieved | 2013: 3525
| Round 2 | Planned
Achieved
| Round 3 | Planned
Achieved
REACT | Round 1 | Planned | bar: 2010 to 2016
|  | Achieved | 2012: 7500; 2013: 78000
| Round 2 | Planned | bar: 2011 to 2018
|  | Achieved | 2013: 15000
| Round 3 | Planned | bar: 2014 to 2020
Achieved | bar: 2014 to 2020
RIB | Round 1 | Planned | 2011: 0; 2012: 40000
|  | Achieved | 2011: 4500; 2012: 177000; 2013: 154000
| Round 2 | Planned | bar: 2010 to 2016
|  | Achieved | 2013: 1700
| Round 3 | Planned
Achieved
SSW | Round 1 | Planned | 2013: 10000; 2014: 15000; 2015: 20000; 2016: 30000; 2017: 50000
|  | Achieved | 2013: 2800
| Round 2 | Planned
Achieved
| Round 3 | Planned
Achieved
TZ | Round 1 | Planned | 2012: 10000; 2013: 30000; 2014: 30000; 2015: 25000; 2016: 35000
|  | Achieved | 2011: 250; 2012: 10000; 2013: 18000
| Round 2 | Planned | 2014: 40000; 2015: 50000; 2016: 65000; 2017: 95000
Achieved | bar: 2011 to 2017
| Round 3 | Planned | 2014: 0; 2015: 25000; 2016: 50000; 2017: 95000; 2018: 110000; 2019: 130000; 2020: 150000
Achieved | bar: 2012 to 2020
ZW | Round 1 | Planned | 2010: 60000; 2011: 105000; 2012: 150000; 2013: 175000; 2014: 200000
|  | Achieved | 2010: 82000; 2011: 64000; 2012: 104000; 2013: 262000
| Round 2 | Planned | bar: 2008 to 2017
|  | Achieved | 2011: 34000; 2012: 57000; 2013: 16000
| Round 3 | Planned | bar: 2008 to 2018
Achieved | bar: 2008 to 2018
Output Indicator 1.2: Average net benefit per household per year
|  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
AAW | Round 1 | Planned | 2013: 200.76; 2014: 200; 2015: 250; 2016: 200; 2017: 225
|  | Achieved | 2013: 168.0299
| Round 2 | Planned | bar: 2014 to 2019
Achieved | bar: 2014 to 2019
| Round 3 | Planned
Achieved
General Window | Early bird | Planned | 2010: 25; 2011: 37.5; 2012: 50; 2013: 75; 2014: 100
|  | Achieved | 2009: 91.1765; 2010: 97.6923; 2011: 236.4151; 2012: 941.1111; 2013: 4098.4615
| Round 1 | Planned | bar: 2008 to 2014
|  | Achieved | 2009: 29.5152; 2010: 90.9091; 2011: 125.8621; 2012: 201.8868; 2013: 221.3115
| Round 2 | Planned | bar: 2008 to 2014
|  | Achieved | 2009: 180.75; 2010: 553.5333; 2011: 743.1818; 2012: 1333.6957; 2013: 1231.7879
| Round 3 | Planned | bar: 2010 to 2019
|  | Achieved | 2010: 291.4667; 2011: 197.2222; 2012: 510.4348; 2013: 693.2353
PCW | Round 1 | Planned | 2013: 25; 2014: 50; 2015: 75; 2016: 100; 2017: 125; 2018: 125
|  | Achieved | 2013: 61.5603
| Round 2 | Planned
Achieved
| Round 3 | Planned
Achieved
REACT | Round 1 | Planned | bar: 2010 to 2016
|  | Achieved | 2012: 85.6; 2013: 34.9615
| Round 2 | Planned | bar: 2011 to 2017
|  | Achieved | 2013: 58.8
| Round 3 | Planned | bar: 2014 to 2020
Achieved | bar: 2014 to 2020
RIB | Round 1 | Planned | bar: 2010 to 2016
|  | Achieved | 2011: 191.3333; 2012: 44.7062; 2013: 235.7597
| Round 2 | Planned | bar: 2010 to 2016
|  | Achieved | 2013: 51.1765
| Round 3 | Planned
Achieved
SSW | Round 1 | Planned | 2015: 80; 2016: 85; 2017: 85
|  | Achieved | 2013: 80
| Round 2 | Planned
Achieved
| Round 3 | Planned
Achieved
TZ | Round 1 | Planned | 2015: 90; 2016: 100
|  | Achieved | 2011: 48; 2012: 95; 2013: 91.5
| Round 2 | Planned | 2015: 80; 2016: 90; 2017: 95
Achieved | bar: 2011 to 2017
| Round 3 | Planned | [7 empty] | 5 | 40 | 45 | 50 | 55 | 60
Achieved
ZW | Round 1 | Planned | bar: 5
|  | Achieved |  |  | 43.061 | 99.2188 | 86.5385 | 53.6603 | bar: 5
| Round 2 | Planned | bar: 5 to 45
|  | Achieved |  |  |  | 27.1765 | 50.7719 | 259.5625 | bar: 5 to 45
| Round 3 | Planned | bar: 5 to 50
Achieved | bar: 5 to 50
Output Indicator 2.1a: Ongoing projects that are profitable 36 months from date of contract: total number
|  |  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
AAW | Round 1 | Planned | 2016: 10; 2017: 15
Achieved | bar: 2011 to 2017
| Round 2 | Planned | bar: 2014 to 2019
Achieved | bar: 2014 to 2019
| Round 3 | Planned
Achieved
General Window | Early bird | Planned | bar: 2008 to 2014
|  | Achieved | 2012: 1; 2013: 0
| Round 1 | Planned | bar: 2008 to 2014
|  | Achieved | 2012: 1; 2013: 0
| Round 2 | Planned | bar: 2008 to 2014
|  | Achieved | 2012: 3; 2013: 2
| Round 3 | Planned | bar: 2009 to 2015
|  | Achieved | 2013: 2
PCW | Round 1 | Planned | 2015: 0; 2016: 10; 2017: 12; 2018: 14
Achieved | bar: 2008; 2012 to 2018
| Round 2 | Planned | bar: 2008
Achieved | bar: 2008
| Round 3 | Planned | bar: 2008
Achieved | bar: 2008
REACT | Round 1 | Planned | bar: 2010 to 2016
Achieved | bar: 2010 to 2016
| Round 2 | Planned | bar: 2011 to 2017
Achieved | bar: 2011 to 2017
| Round 3 | Planned | bar: 2014 to 2020
Achieved | bar: 2014 to 2020
RIB | Round 1 | Planned | bar: 2010 to 2016
Achieved | bar: 2010 to 2016
| Round 2 | Planned | bar: 2010 to 2016
Achieved | bar: 2010 to 2016
| Round 3 | Planned
Achieved
SSW | Round 1 | Planned | 2016: 2; 2017: 4
Achieved | bar: 2010 to 2017
| Round 2 | Planned
Achieved
| Round 3 | Planned
Achieved
TZ | Round 1 | Planned | 2015: 3; 2016: 4
Achieved | bar: 2010 to 2016
| Round 2 | Planned | 2017: 3
Achieved | bar: 2011 to 2017
| Round 3 | Planned | 2018: 2; 2019: 5; 2020: 6
Achieved | bar: 2014 to 2020
ZW | Round 1 | Planned | bar: 2009 to 2015
|  | Achieved | 2013: 4
| Round 2 | Planned | bar: 2011 to 2017
Achieved | bar: 2011 to 2017
| Round 3 | Planned | bar: 2012 to 2018
Achieved | bar: 2012 to 2018
= round not yet launched / closed
= data not available
'ACHIEVED' INDICATOR DATA FOR 2014 TO BE INSERTED/UPDATED

## Window, rounds, year
Windows: Year each round launched and year impact first reported
YEAR
AAW | Round 1 | Launched | 15 October 2011
|  | Impact first reported | 2013
| Round 2 | Launched | 6 November 2014
Impact first reported
General Window | Early bird | Launched | 5 June 2008
|  | Impact first reported | 2009
| Round 1 | Launched | 5 June 2008
|  | Impact first reported | 2009
| Round 2 | Launched | 6 October 2008
|  | Impact first reported | 2009
| Round 3 | Launched | 1 May 2009
|  | Impact first reported | 2010
PCW | Round 1 | Launched | 15 April 2012
|  | Impact first reported | 2013
REACT | Round 1 | Launched | 1 November 2010
|  | Impact first reported | 2012
| Round 2 | Launched | 15 October 2011
|  | Impact first reported | 2013
| Round 3 | Launched | 15 July 2014
Impact first reported
RIB | Round 1 | Launched | 1 March 2010
|  | Impact first reported | 2011
| Round 2 | Launched | 15 October 2010
|  | Impact first reported | 2013
SSW | Round 1 | Launched | 15 October 2011
|  | Impact first reported | 2013
TZ | Round 1 | Launched | 1 November 2010
|  | Impact first reported | 2011
| Round 2 | Launched | 31 July 2011
|  | Impact first reported | 2014
| Round 3 | Launched | 20 January 2014
Impact first reported
ZW | Round 1 | Launched | 10 December 2009
|  | Impact first reported | 2010
| Round 2 | Launched | 1 July 2011
|  | Impact first reported | 2011
| Round 3 | Launched | 19 July 2012
|  | Impact first reported | 2014
shaded cells indicate that a round has not yet reported impact.