Annual Review - Summary Sheet

Title: / Africa-Brazil Partnership on Climate-Smart Agriculture and Food Security – ClimAA
Programme Value: / £ 13.4 m		Review Date: / September 2015 (review covers implementation period from October 2014 to September 2015)
Programme Code: / 203707	Start Date: / October 2012 (approved March 2012); no –cost extension approved October 2014	End Date: / March 2017

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	-	B	A	A
Risk Rating	-	Med	Med

Summary of progress and lessons learnt since last review

There has been good progress towards delivery of outputs during the review period. Most components of the ClimAA programme are well into implementation with some already showing promising results.

In line with DFID`s Emerging Powers` objectives, DFID works with Brazil to enhance development impact in Low Income Countries (LICs) by taking some of its learning and testing it in other contexts. Brazil has demonstrated that change is possible by transforming its agriculture sector and tackling hunger faster than most countries and this has prompted a clear demand from LICs to learn from its experience. The programme is enabling the transfer of Brazilian tools and innovative approaches to increase agricultural productivity and food security for the benefit of small farmers in Africa. Through the programme outputs - strengthened partnerships between credible Brazilian and African institutions, testing and adapting Brazilian models focused on improving access to local markets for smallholder farmers, increasing capacity of researchers and government institutions, and the generation of evidence, the programme is already showing positive impacts in targeted LICs. In addition, the programme is facilitating policy dialogue on global development challenges between the UK and Brazil, especially in the areas of food and nutrition security and climate-smart (sustainable) agriculture.

Overall, there has been good follow up to recommendations made in the 2014 annual review:

- The logframe was updated to better reflect the contributions of the different projects to each output
- The Theory of Change has been revised, unpacking the processes needed to go from expected outputs to outcomes
- A mechanism to scale up successful projects under the MarketPlace has been agreed (M-BoSS)
- The DFID Brazil Team have regularly kept DFID country offices up to date with programme implementation
- The IFPRI project was extended until March 2017.

Key highlights

1. The Brazilian Agricultural Research Corporation´s (EMBRAPA) MarketPlace programme continues to fund innovative research projects mostly between Brazilian and African researchers and has raised the interest of organisations like the International Fund for Agricultural Development (IFAD), which intends to use the platform model used by MarketPlace to support agricultural research collaboration between Brazil, China and Morocco. African researchers interviewed during the annual review emphasised the strong partnership, communication and professionalism of EMBRAPA and the fact that Brazil`s experience is more relevant and more recent for African countries than that of traditional donors.
2. The success of the MarketPlace has led to a new programme called M-BoSS (Building on Successes of the Africa-Brazil Agricultural Innovation MarketPlace) which will build on a selection of successful projects, aiming to replicate results at scale, policy influence and longer-term sustainability.
3. The International Food Policy Research Institute (IFPRI) programme is implementing two randomised control studies in Malawi and Senegal with encouraging preliminary results already available from the mid-line survey in Malawi. The use of Random Control Trial (RCT) methodology is allowing IFPRI to robustly test whether an adaptation of the Brazil’s Fomento programme might work in Low-Income Country (LIC) contexts.
4. CALBEE, the programme managed by the World Food Programme Centre of Excellence against Hunger (WFP CoE) component has responded to a massive demand for learning exchanges between Low-Income Country (LIC) governments and Brazil[1].
  [1] The WFP CoE received more than 40 country requests for assistance from 2014 to 2015
5. The Purchase from Africans for Africa (PAA Africa) programme has continued activities but has suffered from some delays in Government of Brazil funding for Phase 2 and has not yet secured resources for the planned scale up in the five pilot countries. This, together with delays in signing agreements between UN agencies involved (Food and Agriculture Organisation (FAO), the World Food Programme (WFP) and the Internal Policy Centre for Inclusive Growth (IPC-IG) have also affected evaluation and monitoring plans.
6. After exploring various options, EMBRAPA and DFID decided not to pursue the proposals on Technical Reference Units (TRUs) and training given the delays caused by internal re-structuring and the limited timeframe available within ClimAA to effectively implement these.
7. Engaging DFID country offices fully from project conception to implementation and evaluation remains a challenge. This is mainly due to time constraints of DFID country staff and the low visibility of Brazil in “traditional” donor coordination structures in many African countries.

Programme management has been strengthened over the past year, including through the completion of due diligence assessments and the development of a delivery plan. Despite some delays in the design of the PAA Africa M&E framework, the programme has continued to be on a solid footing, with strong relationships and governance structures supporting delivery.

The UK and Brazil have strengthened collaboration on a number of development policy issues. For example, building on the UK and Brazil partnership on nutrition launched at the London 2012 Hunger Summit, DFID Brazil has been working closely with Brazilian counterparts on preparations for a follow up Nutrition for Growth event at the 2016 Rio Olympics. This has included a high-level “Road to Rio” event held at the Brazilian Embassy in London in October 2015.

Following recommendations from the 2014 annual review, Brazil and the UK agreed to hold an annual strategic development dialogue and in April 2015 agreed to strengthen policy and programme coordination. Under a new director of Brazil`s Development Agency (ABC) a dialogue on new models for South-South cooperation is underway.

In addition, Brazil contributed to the High Level Panel on Humanitarian Aid and Cash Transfers called by DFID`s Secretary of State.[2] Following this, and a DFID Ministerial visit to Brazil in August 2015, UK and Brazil have agreed to work together to ensure a successful World Humanitarian Summit in May 2016.
[2] Doing Cash Differently: How cash transfers can transform humanitarian aid. Report of the High Level Panel on Humanitarian Cash Transfers, September 2015

Main recommendations for next year

Continue support to the MarketPlace through ClimAA to enable the generation of a pipeline of innovative research projects. Of these, a handful will be tested and a much smaller selection (those with the most promising results) will be taken to scale through the new M-BoSS programme.

IFPRI`s preliminary results and lessons on how to adapt Brazilian models to African contexts to increase their development impact need to be disseminated in Brazil and more widely, targeting sectors interested in South-South collaboration and the role of BRICS in development cooperation.

Continue support to the World Food Programme Centre of Excellence against Hunger and include a component to support Brazil`s cooperation on how to tackle malnutrition as well as preparatory activities towards the Nutrition for Growth event to be hosted around the Rio Olympics in 2016.

Support Brazil and implementing partners in a joint resource mobilisation plan to ensure that improvements and contributions to school feeding from PAA Africa can be sustained and scaled up. At the same time, prioritise the monitoring and evaluation component as evidence of impact is vital to secure additional resources.

Explore alternative options to ensure that DFID country offices in Africa are more engaged (e.g. through securing early commitments to ClimAA as part of the 10% advisory time and early engagement for new country work).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4446020.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4446027.xls

Outline of the programme

DFID is supporting a set of integrated interventions with a total budget of £13.4 m up to March 2017, to boost agricultural productivity, food security and poverty reduction in Africa through stronger Africa-Brazil cooperation. ClimAA is in line with DFID`s Operational Plan and the overall Emerging Powers objectives, focusing on encouraging a constructive role from Brazil on global public good challenges as well as expanding and improving the effectiveness of its development assistance to LICs. The Business Case was approved in March 2012 for 3 years at £10.8 m. An additional sum of £2.6 m was agreed in July 2013 for two additional projects giving a total of £13.4 m. The programme consists of a number of projects with different Brazilian organisations working in cooperation with Brazilian government institutions and international research institutes. The main projects are:

The Africa-Brazil Agricultural Innovation MarketPlace
Through a competitive application process MarketPlace supports small innovative research projects between EMBRAPA, African and Latin American and Caribbean (LAC) research institutions focused on benefiting smallholder agriculture. Since its inception in 2012, the MarketPlace is supporting 76 projects in 13 countries in Africa and eight countries in LAC.

Enabling Food Security Policy and Capacity in Africa: Leveraging Brazil’s Experience and Expertise - CALBEE (WFP Centre of Excellence against Hunger)
The WFP Centre of Excellence is an innovative partnership between the Government of Brazil and WFP. It serves as a global platform for South-South cooperation on school feeding, nutrition and food security by sharing best practices and lessons learned from the Brazilian experience. Through CALBEE, DFID supports this objective by funding support to six additional countries: Benin, Cameroon, Ethiopia, Kenya, Mozambique and Togo. The Centre is co-funded by the Brazilian Government and more recently other donors such as the Bill and Melinda Gates Foundation (BMGF).

IFPRI – International Food Policy Research Institute
Through an initial scoping study IFPRI identified two potential Brazilian programmes which might be suitable for application in Africa. One, PAA (a local food purchasing programme), was already being tested through PAA Africa. The other programme, Fomento (a business support package for small farmers), is being tested by IFPRI in Senegal and Malawi through local implementing partners and is already showing promising results on adapting Brazilian models to resource-constrained African settings.

Purchase from Africans for Africa project – PAA Africa
PAA Africa builds on two key components of Brazil’s Zero Hunger Strategy to increase food security through a local food purchasing programme (PAA) and a school feeding programme (PNAE). PAA Africa combines the approaches and learnings from PAA and PNAE in five African countries (Senegal, Niger, Ethiopia, Malawi and Mozambique) and builds on the expertise of the World Food Programme, the Food and Agriculture Organization (FAO), the Humanitarian Office (CGFome) of the Brazilian Ministry of Foreign Affairs (MRE), the Ministry of Social Development and Fight Against Hunger (MDS), the Ministry of Agrarian Development (MDA), the National Council on Food and Nutritional Security (CONSEA) and the International Food Policy Research Institute (IFPRI). The project is now in Phase 2 (consolidation and scale up). DFID funds the knowledge management component, which includes monitoring and evaluation of results as well as dissemination of the evidence and lessons generated.

The Africa-Brazil Technical Reference Units (TRU) and Training
The TRU project looked to set up TRUs (similar to model farms where new farming practices can be tested at scale) in up to four African countries to test Brazilian climate-smart agricultural technology within these contexts. However, structural changes within EMBRAPA and the dismantling of its training unit, have led to substantial delays and eventually a joint Government of Brazil and DFID decision not to proceed with this component was taken given the time available.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Through ClimAA, DFID works with Brazil to facilitate the application of Brazil’s successful development experience in agriculture and food security to Africa, given agro-ecological similarities and strong demand from African countries. By facilitating the transfer of technologies and innovations which have proven successful in Brazil and the adequate adaptation of these tools to LICs, ClimAA is contributing to increased agriculture and food security in Africa for the benefit of small farmers.

Despite initial implementation delays ClimAA is now delivering effectively, showing increased influence, and some visible results. Key observations from the annual review discussions are:

MarketPlace

- The MarketPlace has won considerable recognition from donors and partners over the years. Since 2010 it has received more than 600 applications from 27 countries in Africa and 21 in Latin American and Caribbean (LAC). The initiative has mobilised more than US$11 m in funding from partners, with a DFID contribution of £3.2 m.
- Examples of outcomes produced through the initial nine DFID funded projects which are now finalised, include the generation of nine agricultural technologies, products and services; 19 technical publications, exchange of 64 genotypes adapted to tropical agriculture; 12 events organised by project co-leaders, and advance knowledge through the generation of 12 identifiable knowledge products.
- Of the technologies generated, it is worth noting new technologies and policy for honey production in Ethiopia and for Rizhobium inoculation in cowpea. The latter has huge potential for Africa since it can reduce or eliminate the use of Nitrogen in cowpea, one of the most important crops in the continent. There are projects which have had a direct impact on smallholders and have potential for scale up, such as increased milk production for smallholders in Kenya through a local dairy innovation platform.

CALBEE
- There is a large and increasing demand from LICs for support from Brazil in the areas of school feeding, links to local agriculture, food and nutrition security. This demand is channelled through the WFP CoE. Proof of this demand is this year`s request from the African Union to work closely with the Centre. In August 2015, the African Union visited Brazil to formalise a partnership with the WFP CoE and has committed to raise the subject of home-grown school feeding within relevant African regional fora.
- CALBEE contributes to meeting this demand and ensures that study visits to Brazil have a sustainable impact. Six countries are receiving support from the WFP CoE, with evidence of policy changes in Cameroon, Togo and Ethiopia. After a learning visit to Brazil, Cameroon and Togo government officials have developed action plans which were validated by their governments. The action plans are informing the development and implementation of a school feeding policy linked to local smallholder production purchases. Following the learning visit, the governments of Togo and Benin requested support to develop national school feeding policies and this is underway. The Ethiopian government has launched a task force to design the National School Feeding Programme, informed by several learning visits to Brazil. In addition, CALBEE has stimulated the launch of a West African school feeding network and in September 2015 the African Union has requested to work closely with the WFP CoE.

IFPRI
- The IFPRI project is effectively conducting two randomised control trials in Senegal and Malawi and making solid progress.
- Mid-line survey results from Malawi are showing that small farmers who received inputs similar to those provided in Brazil (advice, cash) had improved food security indicators. Preliminary results also show important interaction effects of the inputs. Cash transfers plus a business plan for small farmers to manage their crop production and access local markets was the most effective intervention to improve food security, as opposed to inputs or business plans/advise only or no inputs (control group).
- The project is already providing significant contributions to ClimAA results, is generating a lot of interest among key Brazilian stakeholders and might become a useful element of Brazil’s development cooperation ‘offer’ to LICs. In depth discussions with a broader range of Brazilian officials and policy makers is planned for late 2015.

PAA Africa
PAA Africa is an excellent example of the Brazilian Government’s approach to South-South technical cooperation. Most smallholder farmers in African countries continue to face significant barriers to access local markets, an issue which Brazil has successfully addressed through PAA, a programme which procures food products directly from small farmers to supply the national school feeding and other public feeding programmes, thus guaranteeing small farmers a local market.
During its first phase the programme has implemented home-grown school feeding pilots in five countries (Ethiopia, Malawi, Mozambique, Niger and Senegal), benefiting 5,516 smallholder farmers, reaching 420 schools and 128,456 students. In its second phase, activities have been consolidated but resources for scale up have not yet been made available.
In phase 2, DFID is supporting the programme’s knowledge management component, to ensure that lessons are shared between implementing countries and that evidence of impact is captured.
- Routine monitoring through the different country systems is underway but there have been delays with the tailored monitoring and evaluation component, partly due to the funding problems but also to delays in signing agreements among the UN agencies involved. All staff are now in place and a draft M&E framework has been developed by the UNDP-Government of Brazil supported International Policy Centre for Inclusive Growth (IPC-IG). The proposed monitoring framework will be tested in the field at the end of 2015 and the evaluation design is set to be finalised in November 2015 . However, this poses special challenges if the programme does come to an end in mid-2016 (ideally evaluations have to start before the programme intervention). A process-type evaluation with self-reporting and qualitative components is being proposed to mitigate this challenge.
- There were two possible scenarios discussed in the PAA Africa advisory group in December 2014: 1) programme ending in 2015 and 2) potential scale up subject to additional resource mobilisation, under a renewed commitment and dialogue at the highest level (e.g. high level dialogue among Brazil, WFP and FAO). Since 2014 Brazil has led the implementation of a joint fundraising plan with WFP and FAO’s support, but with no concrete results to date. In this context, the PAA Africa partnership would require a fresh joint fund-raising plan backed up by the support of FAO and WFP, including reaching out to IFAD and DFID country offices.
- Despite limited funds all five African countries have developed strategies and recommendations for scaling up local food procurement from smallholders for school feeding. Implementation and government ownership is at different stages and is influenced by external factors which are beyond the scope of the project, with most progress made in Senegal and Ethiopia.

Despite current financial constraints and its thinly-spread development footprint, Brazil is committed to expanding and strengthening its development cooperation and activities in LICs, and ClimAA provides a good platform for the UK to work with Brazil in achieving this. The country has an impressive track record of growth and development and has significantly increased its investment in development cooperation (with estimates of expenditure in the five years to 2009 varying between approximately US$1.6 bn and US$4.17 bn). In the last 20 years average life expectancy increased from 64.7 years to 73.9 years and average income increased from 447 reais to 793 reais. Brazil has almost eradicated chronic hunger and malnutrition. Its development model has been strong on sustainability (reducing levels of deforestation by 80%) and inclusion in terms of both gender and minorities, and Brazil is the only one of the BRICS to have reduced poverty and inequality whilst continuing to grow economically. This is why many Low-Income Countries, particularly in Africa, look to Brazil as a source of learning in their own efforts to reduce poverty and why we are responding to this demand.

Our work with Brazil falls under our Emerging Powers` Programme, which has the following objectives: i) to make development assistance more effective; ii) to enhance the development impact of investment in poorer countries and regions; iii) to respond better to global challenges and iv) to work towards an international system that reflects the needs of poor countries. Our development collaboration with Brazil focuses primarily on objectives i, ii and iv.

The Brazilian Development Agency (ABC) wants to expand and strengthen its development cooperation, by for example making its sharing of experience more systematic. In addition, Brazil is a global advocate for change in areas where it has a strong domestic track record of success, as is the case with nutrition through Nutrition for Growth (N4G) and its active participation on multilateral food security and nutrition debates. Brazil values cooperation and collaboration with DFID because of DFID’s long experience, its policy capacity and its leading role in debates on international development. In turn, we look to Brazil as an increasingly influential global development actor with whom we share many core values such as the need to tackle hunger, inequality and gender and as a partner for implementing the new Global Goals. Through ClimAA, we are working with Brazil to address the Zero Hunger, Climate Action, Life on Land and Partnerships Global Goals and expect an increased contribution of Brazil’s development cooperation to poverty reduction in LICs.

Overall output score and description
The annual output score is A (Meets Expectation). The project is complex involving a variety of partners and testing a number of approaches - but good progress has been made over the past year, with the scaling up of some project activities, building on lessons and successes and leveraging other donors to increase support at scale.

Key lessons for Brazilian Development Cooperation, recipient countries and DFID

Prompted by significant and increasing demand from LICs, South-South cooperation and particularly the adaptation of successful Brazilian models to African contexts, is a relatively new area of work. Therefore monitoring and evaluation play an important role in generating lessons on what works and best practices, with the following emerging lessons to date:

1. ClimAA is facilitating and strengthening successful research partnerships between Brazil and LIC institutions through its collaborative projects and initiatives.
2. Open and transparent partnerships, information sharing and communication as well as the credibility of Brazilian researchers and the relevance of Brazil`s experience in tackling hunger for African countries, are all key factors leading to the success of the MarketPlace and CALBEE to date.
3. Understanding the local context and the political economy in LICs is key for adapting agricultural development models which have been successful in Brazil. This will also inform future scale up and sustainability of results.
4. Political instability and weak leadership in many African countries, some of which are receiving support from Brazil (e.g. Mozambique, Ghana) mean that learning exchanges do not always come to fruition and in some instances new African government officials need to be more fully engaged.
5. Limited capacity in many African settings, particularly at local level, means that long-term technical support is needed to effect change, and that change is often slower than it has been in the Brazilian context.
6. Beyond proofs of concept and testing approaches, there is a real need to think of value-addition and understanding the many barriers smallholder farmers face to access markets, financial services and agricultural knowledge and inputs.
7. The importance of irrigation solutions for smallholder farmers and the development of simple technologies which can work and be sustained in resource-poor settings is crucial.
8. As the revised Theory of Change shows, there is a more complex process to go from outputs to outcomes, with the need to understand and address key constraints smallholders face to access local markets, as well as the political economy and to undertake the necessary actions to influence policy and programmes.

Key actions

Key follow up actions are captured in the Summary Sheet and through detailed recommendations after each output.

Has the logframe been updated since the last review?
Yes. The logframe was updated after the 2014 annual review and it was later revised in August 2015 to take into account the decision not to pursue the EMBRAPA TRU and training components – targets agreed for these components have been removed from the expected targets for the remainder of ClimAA.

This annual review reports results against the “revised” set of milestones and targets (for milestones agreed in 2014). Targets for the remainder of the programme should be revised with partners to ensure they are ambitious but realistic.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased capacity of LIC researchers, government institutions and extension staff through participation in LIC-Brazilian pilots, training and policy dialogue
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of researchers participating in joint research/pilot programmes and exchange visits disaggregated by gender/institutional affiliation and seniority	50 / MKP 16 (5) / IFPRI 2 (1) / PAA 8 / WFP 24 (8)	Exceeded 147 / MKP – 76 (14 women) / IFPRI – 5 (1) / PAA – (16) EMBRAPA researchers / WFP – 50 (9)
Number of people trained in adaptive research, sustainable agriculture technologies, local food purchase systems and extension approaches to disaggregate by gender	115 / IFPRI - 90 (35) people, 35 of which are women / PAA - 25	Exceeded 180 / IFPRI – 120 (60) / PAA (60) 37 women
Number of training materials and capacity building events addressing gender issues	5 / IFPRI – 2 / CALBEE – 2 / PAA -1	Exceeded 11 / IFPRI- 3 / CALBEE – 6 / PAA – 2

Key Points
Partnerships with credible Brazilian institutions are showing evidence of positive change in African country contexts. Significant progress has been achieved on output 1 with both an increased number of researchers participating in joint programmes, and a wider variety of people that have participated in lesson sharing events and received training on sustainable agriculture and food security - from researchers to public officials, farmers, farmer associations and school teachers.
In the period covered by this review the MarketPlace has significantly contributed to learning exchanges, including an event in March 2015 to discuss regulation of Genetically Modified Organisms (GMOs) in Africa with participation of project co-leaders, five monitoring visits in Africa and the September 2015 annual forum, which brought together more than 70 researchers from Africa and LAC to share results from completed projects and exchange lessons. See list of publications of individual projects and the MarketPlace model in Annex 1.

In May 2015, PAA Africa held an exchange of lessons workshop in Malawi for officials involved in school feeding programmes in Malawi and Mozambique with 35 participants (13 women) contributing to indicator 1.2. The programme also organised an exchange meeting focused on the role of civil society in the implementation of home-grown school feeding programmes (25 participants, 10 women), at the margins of the Committee on Food Security in Rome.
CALBEE has also organised four learning exchange visits in Brazil for officials from Cameroon, Mozambique and Ethiopia (one on school feeding in March 2015 and one on nutrition in May 2015). It also provided technical assistance to governments for the development of a school feeding policy and programme activities, through deployment of technical assistance to Zambia, Madagascar, Malawi, Benin, Togo and Kenya.
IFPRI reported that up until September 2015, five researchers participated in the pilot programme. This IFPRI project is also responsible for a large contribution to Output 1.2 with 120 people (60 women) being trained. Finally on output 1.3 IFPRI organised three events that specifically addressed gender issues.

Summary of responses to issues raised in previous annual reviews (where relevant)
There were no specific recommendations for this output in the 2014 Annual Review.

Recommendations

1. Alternative ways of engaging country office involvement and coherence across DFID country programmes need to be explored.
2. The 2014 Annual Review recommendation to ensure greater synergy between PAA Africa and CALBEE continues to be relevant for the remainder of the programme.

Output Title	Proof of concepts tested and validated for LIC- specific context for potential outscaling
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of proof of concepts/pilots (PoC) initiated	17	Exceeded 18 / IFPRI (2) pilots underway / MKP – 16
Number of PoC tested and validated, with at least 40% showing potential positive impact on women and girls	25	Achieved 25 / MKP – 25
Number of PoC identified with the potential for upscaling (and number of projects with upscaling initiated and completed)	10 / 2 (MKP) / 3 (M-BoSS) / PAA (5)	Achieved 10 / MKP – 5 / M-BoSs – 0 (not initiated yet) / PAA - 5

Key Points

All output milestones have been met, except the initiation of three projects under M-BoSs. There were delays in signing M-BoSs but the project is now in its inception phase with a planned call for proposals in October 2015. As the MarketPlace milestones were exceeded for indicator 2.3, the overall scoring for this output is an A.

The two Randomised Control Trials (RCTs) implemented by IFPRI are evaluating the impact of an adaptation of the Fomento programme in two different African contexts: Senegal and Malawi. The Randomised Control Trials (RCTs) include management/extension advice (with support for farmers to develop business plans) as well as transfers or inputs and/or cash to see if these lead to improved nutrition. In both countries IFPRI is working with “umbrella” farmer organisations: with GRET and FONGS in Senegal and with NASFAM in Malawi. Both pilots are well underway, with completed baseline reports available and mid-line data collection well advanced. In Malawi 40% of members from these clubs are women. Indicators measured include impacts on wages, food security and improvements in agricultural production. Preliminary results from Malawi are showing that compared to the control group, farmers in the intervention groups who receive inputs (advice, cash or a combination of both) experience significant improved food security. Preliminary results are also showing strong complementarities between the cash transfer and the business plan. The latter includes extension support and commercial advice to help small farmers plan better for the farming season and facilitate their access to local markets.

In 2015, the MarketPlace launched a new call for proposals and 11 new agricultural projects were approved. More than half of those proposals are directly dealing with smallholders and poverty-alleviation targeted technologies. The remaining proposals were mostly with a focus on policy development or productivity technology. Contracts for these proposals have been finalised and disbursements have started. The projects approved in 2012 and supported by DFID funds finished their activities in the first half of 2015 and evaluation reports were submitted by co-leaders through the online system. See examples of key results in the overall performance section.

Summary of responses to issues raised in previous annual reviews (where relevant)
Overall, there has been good progress towards following up recommendations from the 2014 annual review:

Through DFID`s agreement to support M-BoSs (Building on the Successes of the MarketPlace), a selection of successful projects from the MarketPlace will be supported for scale up, jointly with EMBRAPA and the BMGF. The objective is to replicate results from the first projects to reach more vulnerable farmers and generate sustained change, with a large focus on monitoring the uptake of initial research results.

The design of the IFPRI trials was modified to cover two cropping seasons to enable the capturing of “real transformation” and the generation of credible results.

Various options to revise and start the original TRU and training components from EMBRAPA were considered Finally a decision not to pursue this route was made jointly with EMBRAPA and ABC given time constraints.

The PAA approach is being scaled up under different partnership arrangements and support from FAO and WFP in Malawi, Ethiopia, Senegal, Niger and Mozambique.

A scaling up plan was approved by the Government of Senegal and has been included in the governmental multiyear plan. In Niger, a strategy document for a government owned scaled up local food procurement programme is still under consideration but with an increased number of farmers are participating in the project. In Mozambique PAA Africa contributed to the already approved PRONAE (National School Feeding Programme) by supporting the design of agricultural services linked to school feeding procurement, improved data on local food availability, design of menus and testing different procurement modalities. In Malawi and Ethiopia PAA Africa’s approach is being scaled up by strengthened partnerships between funders, WFP and African Governments.
Recommendations
M-BoSs selected projects should have a strong focus on monitoring and evaluation and include a training component for researchers to strengthen project planning and links with both policy makers and businesses.

The methodology of the IFPRI trials , preliminary findings and lessons relevant for Brazilian cooperation should be shared widely with Brazilian policy makers and technical personnel involved in development cooperation; also consider exchange visits from African partners and Brazilian officials and extension specialists (Malawian partners expressed interest in scaling up strategies with support from Brazil).

DFID and EMBRAPA to discuss a potential revised TRU and training proposal in the context of a new business case and partnership strategy, learning from the experience of traditional donor agriculture research units and those from China`s more recent experiences.

EMBRAPA and IFPRI to discuss with DFID sustainable options for some of the research pieces, beyond M-BoSs, by looking at potential leverage opportunities from other DFID departments such as RED and country offices. DFID should ensure dissemination of results to DFID country offices and enough buy-in in those countries to take proof of concepts beyond testing and validation.

Output Title	Lessons learnt and robust evidence generated on adoption of Brazilian technologies and interventions relevant for policy and programme development in LIC
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of best practices, lessons learnt documents, internet discussions and policy briefs widely disseminated with at least 30% of papers/briefs addressing gender dimensions	6 / WFP – 2 / PAA - 4	Exceeded 14 / WFP - 9 / PAA 4 - phase 1 report, 1 case study Malawi[3]; 1 scaling up brief[4], 1 document on PAA Africa and civil society / IFPRI[5] - 2 online policy briefs MKP[6] brief and publication produced; GFCN report finalised
Number of evaluation studies/action plans initiated and completed	11 / 1 - IFPRI / 2 – PAA / 5 – CALBEE / 3 – M-BoSs	Under-achieved 8 / 3 evaluations and case studies done through the MKP[7]; 2 studies initiated by IFPRI; 3 action plans through CALBEE; M-BoSs and PAA not initiated & reduced to 1
Number of learning and policy events organised by ClimAA partners	7 / MKP 1 / WFP 5 / PAA 1	Over-achieved 8 / 5 through CALBEE; 1 through MKP Forum; 2 through PAA
Number of presentations of lessons learnt from ClimAA at international and national events	11 / IFPRI 2 / MKP 3 / PAA 4 / WFP 2	Under-achieved 8 / 3 through MKP; 0 through IFPRI; 2 through CALBEE; 3 through PAA
[3] http://www.fao.org/3/a-i4291e.pdf
[4] http://documents.wfp.org/stellent/groups/public/documents/resources/wfp270352.pdf
[5] 1) www.ifpri.org/blog/poverty-reduction-smallholder-farmers-brazilian-style-can-it-work-africa (April 2015) and 2) massp.ifpri.info/2014/09/19/learning-from-brazil-adapting-fomento-for-malawi/
[6] www.mktplace.org/site/index.php/photos-and-videos/videos
[7] Africa-Brazil M&E visit, 07 May – 10 June 2015 (Quest)

Key Points
There has been good progress with the organisation of learning events but there has been limited progress with some planned evaluations. Most programme projects have contributed to output 3 this year, although the IFPRI evaluations were already taken into account in the 2014 annual review. Overall, given the importance of evidence-building, although milestones for indicator 3.2 and 3.4.are only slightly under-achieved, the overall score for this output is a B.
CALBEE has been the main contributor to output 3 this year. It held a regional school feeding workshop in Senegal and an event during the Global Child Nutrition Conference at the end of September 2015 in Cape Verde, with over 250 participants from 40 countries. The 17th Annual Forum focused on innovative financing for nutrition based on school feeding programmes. Now the largest global forum on school feeding, the GCNF plays a key role in enabling high policy dialogue, sharing experience and lessons learnt as well as fostering the establishment of regional home-grown feeding networks (indicator 3.4). In addition, it participated in national consultations in Cameroon, and it shared the Brazilian experience in regional seminars on school feeding in Peru, Egypt and the 2nd international conference on Global Food Security in New York in October 2015 (indicator 3.3)[8].
[8] This Week_09112015

IFPRI is leading two evaluation studies, one in Senegal and one in Malawi (Indicator 3.2) with two baseline reports completed.

PAA Africa presented programme objectives and experiences to IFAD in May 2015 and supported CGFome (Brazilian government) in the organisation of a social protection seminar in Senegal. However, the planned evaluation has not yet started. Given delays in designing and contracting the evaluation as well as funding challenges to scale up PAA Africa, a process type evaluation with some qualitative case studies is being planned. There is risk however that this is further delayed. The programme was also represented at the South-South expo Washington and has shared experiences with potential donors at FAO/WFP headquarters.

MarketPlace held a forum in September 2015 for concluded projects in 2015 and approved projects in 2014 where lessons learnt and experiences were shared as well as results from the first group of projects. In addition, the M-BoSs project was presented and much of the discussion focused on scaling up successful MarketPlace projects. During the forum delegates also visited a Brazilian example of a whole value-added chain enterprise, witnessing the process from farm production to processing and commercialisation (indicator 3.3). MarketPlace also presented at two IFAD events and at University of California Davis in the US.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. IFPRI has started to get buy-in from Brazilian institutions by sharing information on the Randomised Control Trials (RCTs)` approach and the results obtained so far. Meetings between IFPRI, DFID and a number of Brazilian stakeholders, including the Brazilian Development Agency, Ministry of Social Development (MDS), International Policy Centre for Inclusive Growth (IPC-IG) and EMBRAPA in August have raised much interest, with plans for a larger dissemination meeting later this year. The IFPRI trials are particularly relevant to help Brazil strengthen the effectiveness of its agricultural technology transfer to Africa by understanding what works and how much interventions need to be adapted.
2. ClimAA is clearly putting a stronger emphasis on evaluations and lesson learning across its projects in order to generate robust evidence about impact.

Recommendations

1. PAA Africa to urgently prioritise the monitoring and evaluation activities. To avoid further delays in launching the evaluations, an agreement with IPC-IG to lead on the implementation of the evaluations in country should be sought.
2. IFPRI to ensure that a large dissemination workshop with relevant Brazilian stakeholders takes place in Brazil before the end of 2015 and to develop a further communication plan for dissemination of final results.

Output Title	South-South collaboration strengthened between Brazil and LIC government, research and development institutions working on agriculture and food security
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N/a	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of Brazilian and LIC institutions collaborating as part of ClimAA	24 / MKP -11 / PAA – 7 / M-BoSs - 6	Over- achieved 26 / MKP is collaborating with 8 EMBRAPA centres and 10 foreign institutions (18) / PAA 7 with 5 country governments, NEPAD and EMBRAPA / CALBEE – with AU
Number of joint partnerships with signed MoU between LIC and Brazilian institutions working under ClimAA programme	19 / MKP 14 / PAA 5	Under-achieved 15 / 14 through MKP / 1 CALBEE - AU / 0 through PAA
Number of presentations to Brazilian institutes to demonstrate relevance of Brazilian expertise to South-South cooperation and technology transfer	4	Achieved 4 / IFPRI held meetings with more than 4 key Brazilian partners (larger dissemination event planned for Dec 2015)

Key Points
ClimAA is clearly helping to strengthen partnerships between African and Brazilian institutions. These partnerships are beginning to show positive impacts in African countries, through the uptake of Brazilian models and innovations which are helping to increase agriculture productivity and food security amongst poor populations. Many of the agreements were already signed at the beginning of the project and these form the baseline in the new ClimAA logframe but the programme has facilitated new agreements. Given that indicator 4.1 was over-achieved and indicator 4.2 slightly under-achieved, the overall score for this output is A.

For this reporting period, MarketPlace, which has substantially exceeded targets, signed new partnerships with foreign institutions, including University of California Davis which will act as a resource centre for African and LAC researchers.
PAA Africa has consolidated its partnership with the five pilot countries and entered into new collaborations, including with EMBRAPA and NEPAD. EMBRAPA was asked to provide technical support for the productive development and technology transfer component of PAA Africa led by FAO and succeeded in securing funding for a project from the Research Network in Food Security in Africa and Unasul in December 2013. The Project had researchers from three units - EMBRAPA Horticulture, EMBRAPA Rice and Bean and EMBRAPA Maize and Sorghum working with local African research institutions to discuss technology challenges and to assess availability of technologies and professionals available to support farmers and institutions benefiting from the PAA Africa Programme. Out of five PAA Africa countries, all but Malawi and Senegal (due to the Ebola crisis) participated in the field data collection. Possibilities to build on this project are being discussed.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID Brazil keeps DFID country offices up to date with developments of the ClimAA programme but full engagement of country offices remains a challenge. This means that the main interaction with government officials and beneficiaries is with UN agencies.

Even with the challenges encountered by PAA Africa this year, the teams have sought to follow up recommendations regarding the need to better understand the political economy of PAA African recipients. This is especially important for some of the ambitious, high risk reforms, such as decentralisation and effective inter-ministerial coordination, that only work under specific conditions. Experience up to now has been good with the project adapting to different contexts but if resources for scale up are granted, this needs to be carefully monitored.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

During twelve months of project activities DFID disbursed £1,850,070 covering the period of October 2014 to September 2015. Spending pace is currently at 56% of total funds committed, mainly due to delays in approving up to £1,200,000 for the M-BoSs component which has only had the first instalment disbursed. The spending rate increases to 62% of total commitment value after excluding M-BoSs. An outstanding balance of £3,837,077 – 44% of the total commitment for live projects - remains to be disbursed by end March 2017, which is the closing date for all components with the exception of CALBEE, which ends in September 2016. Total approved funds for ClimAA were £13.4 m but since the EMBRAPA TRU and capacity building components will not go ahead, it is expected that by the end of the programme, total funds disbursed will amount to 65.5% of the original approved funds with current commitments. There is scope though to allocate additional funding to the MarketPlace and CALBEE.

ClimAA Programme	Total Commitment	12 months Financial Execution / (Oct 14-Sep 15)	Total amount disbursed to date	Balance
1. PAA Phase I (CG Fome, WFP, FAO)	(closed)	0	(closed)	0
2. PAA Phase II (CG Fome, WFP, FAO)	£1,300,000	£387,046	£673,065	£626,935
3. CALBEE (WFP)	£1,300,000	£565,104.89	£852,160.64	£447,839.36
4. IFPRI	£1,870,139.50	£297,919.07	£1,087,836.57	£782,302.93
5. MarketPlace (EMBRAPA)	£3,100,000	£350,000	£2,070,000	£1,030,000
6. M-BoSs / (EMBRAPA)	£1,200,000	£250,000	£250,000	£950,000
7.Training (EMBRAPA)	£580,000	£0	£0	N/A
8.TRU (EMBRAPA)	£580,000	£0	£0	N/A
Total	£9,930,140	£1,850,070	£4,933,062	£3,837,077

Following recommendations from the 2014 annual review, an extension of ClimAA to March 2017 was approved in November 2014.

With the approval of the ClimAA extension, an additional £700,139 was approved for the IFPRI project and an additional £900,000 was approved for MarketPlace for one more round of proposals.

In addition, up to £1,200,000 was allocated for the new M-BoSS project, which will be split over two years to scale up successful results of the MarketPlace component. The first instalment of £250,000 was disbursed in September 2015.

The largest share of expenditure under ClimAA is on fees/personnel and logistics. For some projects, such as with EMBRAPA, staff costs are part of their in-kind contribution. The costs for both are within reasonable limits for the nature and scope of interventions.

Spending is well underway despite delays in signing the M-BoSs component and has been largely in line with forecasted amounts.

VfM performance compared to the original VfM proposition in the business case
No formal VfM assessment was carried out during this review, but the team was able to consider whether systems currently in place are adequate to ensure VfM. Measuring value-for-money in triangular cooperation programmes is difficult. The OECD’s Development Assistance Committee (DAC) acknowledges that this is rarely the “cheapest” means to deliver development results in recipient countries, as the transaction costs of working with a number of partners are high and complex. But there are wider benefits that make these interventions a worthwhile investment.

Although the project does not have an agreed, routinely reported against set of VfM metrics at output level, partners confirmed their commitment during the annual review to drive project costs down, and many good examples were provided. It should be noted that in several of the projects Brazil supplies experts as an in-kind contribution. Thus projects with EMBRAPA do not include staff costs. Considering the world-leading expertise of the staff provided on agriculture in the tropics, and the institutional support behind this, these in-kind costs can be substantial.

A number of examples of VfM were provided:
- EMBRAPA in kind contributions – MarketPlace and their research projects have mobilized about US$1.7 m/year of in kind resources (about 20% of total costs). Overall, DFID`s commitment is 43% of total resources mobilised (US$11 m).
- EMBRAPA was able to demonstrate that placing research funding for MarketPlace projects directly into the hands of researchers encouraged them to find best-value options, such as finding cheaper accommodation during study visits for partners, to enable them to benefit from more time working with Brazilian researchers. Also, relatively small grants ensure the researchers manage their funds well (and grants do not include salaries).
- WFP Centre of Excellence had a particular focus on ensuring that they only funded high-quality delegations for visits to Brazil. They explained that this meant they needed the right expertise and influence to be able to benefit from the time spent with Government of Brazil interlocutors, and implement the learning they had acquired once they had returned to home countries. This involved working closely with partners on delegation lists, and cancelling visits when they were not convinced by the calibre of the delegation.

Assessment of whether the programme continues to represent value for money

Yes. Although assessing the complexity of trilateral cooperation is complicated, there is good evidence which shows that the project represents value-for-money. This is demonstrated by the strengthened research partnerships and sharing of experiences with LICs which are beginning to show positive impact on smallholder agriculture and food security. In addition, the programme is playing an important role in leveraging larger contributions from other partners including the Brazilian Government, Bill and Melinda Gates Foundation (US$7 m for M-BoSs) and the International Fund for Agricultural Development (IFAD) (new grant under discussion). Lastly, in the medium to long-term, strategically the programme represents value for money given the increasing importance of Brazil as a global development actor and their role in supporting the new Global Goals.

Quality of financial management
Funds for projects are channelled to project partners from DFID’s Global Partnerships Department in Brazil in the following way:

ClimAA Annual Programme	Recipient Institution
1. PAA Phase I (CGFome, WFP, FAO)	WFP Centre of Excellence
2. PAA Phase II (CGFome, WFP, FAO)	WFP P4P Unit in Rome
3. CALBEE (WFP)	WFP Centre of Excellence
4. EMBRAPA (MarketPlace)	FUNARBE[9]
5. EMBRAPA (M-BoSs)	FUNARBE
6. IFPRI	IFPRI (Washington)
[9] Due to the Brazilian Constitution EMBRAPA cannot spend funds outside of Brazil without congressional approval for each spend. FUNARBE, a charitable foundation, works with EMBRAPA on its overseas projects facilitating their implementation.

Recipient institutions have been working in Brazil and with DFID for a long time, with clean audits and no apparent issues. Due diligence was conducted by DFID in March 2015 for FUNARBE and in November 2014 for WFP.

Date of last narrative financial report	Varies across partners 2015
Date of last audited annual statement	NA

E: RISK (½ page)

Overall risk rating: MEDIUM

The programme encompasses some components that are low risk (e.g. delays in approval and transfer of funds by DFID) and some that are medium risk (e.g. where Brazilian models may not be sufficiently adapted to context). The commitment to the programme by Brazilian partners has clearly matured, reducing the risk identified at the outset of the Business Case in 2012 (with some risks moving from high to medium). In addition, the main risks identified at the outset were related to the TRU and training components which have now been removed.

Overview of programme risk

Risks	Level		Mitigating factors
	Probability	Impact
1.Lack of commitment from partners by virtue of shifting political priorities	Low	Medium	Continue to work with focal points in Government and forge partnerships with civil society
2.Resistance of partner Governments and international agencies in reviewing national policies, procedures and programmes to apply lessons and take up new approaches	Low	Medium	Continue to engage local authorities (formal and/or traditional) in all project planning and evaluation stages. Work with focal points in Government and forge partnerships with civil society. / Improve the Brazilian institutions knowledge and understanding of the political economy of the recipient African countries
3.Brazilian models not sufficiently adapted to context	Medium / (it was high)	Medium	Processes of lesson learning, testing and multi-stakeholder dialogue built into or the primary focus of recommended components. / Better consultation with DFID African countries where and when suitable
4.Insufficient ownership by African participants and DFID country offices	Low	Medium	DFID Brazil to agree for appropriate engagement opportunities with African country offices / Lead partners build an effective multi-stakeholder network to build buy-in and capacity to engage in recipient countries / Seek country specific road maps for the dissemination & adoption of technology or evidence from research
5.Capacity of developing country partners insufficient to engage effectively with Brazilian actors	Medium	High	Capacity strengthening built into all main components of ClimAA
6.Insufficient evidence base to measure results	Medium (it was high)	High	M&E must be part of the engagement with project partners, built into each component, supported by analysis and decision support
7.Financial mismanagement or fraud within project partners	Low	Medium	No DFID funds are channelled through government systems: / EMBRAPA manages annual funds of US$1bn and Funarbe’s fiduciary systems channel significant international funds, and meet DFID requirements / WFP has a good track record, DFID delivers more humanitarian assistance through WFP than any other agency. WFP meets all of DFID’s fiduciary risk requirements. / IFPRI has a track record of managing DFID funds, and meets CGIAR standards

Risk 3 has been revised downwards from high to medium given that the PAA approach is being adapted and scaled-up in Malawi and Ethiopia and that both M-BoSs and IFPRI are looking at how best to adapt Brazilian models and technologies to African contexts.

Outstanding actions from risk assessment

Overall risks to the project are outlined in the updated risk matrix with the following highlighted as key risks:

During the review it was clear that the engagement with DFID country offices remains a challenge. Country advisers could play an active part to make sure Brazilian models are fit-for-purpose and are sufficiently adapted to each recipient African country context

M-BoSS: Projects are capped at US$700,000 (higher value than under the MarketPlace as it is seeking to scale up successful projects). Funarbe will be responsible for overall management of DFID funds and has agreed to conduct in-country audits of grantees. Grantees will be informed of a zero tolerance policy towards fraud. Financial capacity and track record will be part of the assessment process. Funds will be released against clear expected outputs and financial reporting requirements. Funding will be terminated if any evidence of financial mismanagement or fraudulent activities is identified or if performance targets are not met. In addition, more rigorous evaluation and monitoring arrangements have been agreed with EMBRAPA and budgeted for.

There is some collaboration between PAA Africa (managed by WFP in Rome since the inception of phase 2) and CALBEE, but this could be strengthened. DFID in Brazil needs to encourage effective cooperation between the two projects and ensure that PAA Africa lessons are being fed back to Brazil.

The current political and economic crisis in Brazil poses some challenges to Brazil expanding its South-South cooperation, at least in the short-term. In addition, Ministerial budget cuts mean that the expansion of Brazil’s development activities is limited. It also means there are detrimental impacts on existing activities – e.g. PAA Africa and MarketPlace are unlikely to receive more Brazilian government funding for the time being. DFID in Brazil might need to consider whether to support implementation activities to ensure continuity.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
On Track?	N

There were initial delays which prompted the decision to extend the programme to March 2017. Although overall programme implementation has accelerated over the past year, there have been delays in signing the new M-BoSs component and in starting a strengthened M&E framework for PAA Africa 2.

Performance of partnership (s)
ClimAA is an umbrella programme with decentralised management and a diversified set of partnerships. DFID has established good clear relationships with the key implementing partners and has avoided a centralised programme management service provider, which would be costly and defeat the purpose of having ClimAA as an influential tool to strengthen the UK-Brazil relationship. Instead, the programme does not have a single Brazilian institutional lead, but uses a variety of institutions. This reduces risk and increases the flexibility of DFID support.

Discussions held with programme beneficiaries and African partners highlight how much they value the support of Brazilian implementing partners. As partnerships mature, expectations for more support are growing and Brazilian partners will need to define what steps to take next.

Overall, implementing partners are adhering to reporting agreements and have improved their financial management and forecast. The increase need of documentation from partners to support payment requests though has required constant communication from DFID to explain new requirements and ensure that partners are familiar with these.

Asset monitoring and control

N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)	N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The project is based on outputs related to formative research between research institutes in Brazil and Africa and on pilot programming. A significant number of programme results are associated with the publication of scientific research that provides strong evidence of the potential of Brazil’s agricultural development and food security programmes in African countries. Most of the implementation is conducted by project partners - Brazilian institutions with Brazilian expertise - subject to continuous evaluations and peer-reviews.

Monitoring progress throughout the review period
The annual review was largely based on a desk-review of programme documents, meetings with implementing partners in Brasilia and teleconferences with partners in Rome and Africa. Due to budgetary and staffing issues and the fact that the 2014 annual review was an in-depth review, the review did not include country visits. However, a number of discussions were held with beneficiaries and programme partners in Africa to ensure their views were fed into the review, including with Benin and Togo officials benefiting from support from the WFP CoE and with IFPRI partners in Malawi.
The review also coincided with the hosting of the MarketPlace Forum 2015 and the lead adviser had the opportunity to interact with researchers from Africa and LAC and to hear directly about their experience and results to date. In addition, the semi-annual consultative meeting on PAA Africa took place during the review and provided the opportunity to gather perspectives from government, UN agencies involved, PAA Africa country representatives and Brazilian civil society (CONSEA).
List of documents reviewed and supportive documentation:
1. ClimAA Business Case
2. ClimAA Annual Review 2014
3. MarketPlace annual report
4. IFPRI baseline reports for Malawi and Senegal
5. IFPRI online policy briefs and presentations to partners in Brasilia
6. CALBEE annual report
7. M-BoSs project proposal
8. PAA Africa presentation
9. Global Child Nutrition Forum report (2014)
10. Programme financial reports
11. Due diligence report