Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Programme for Improving mental Health Care (PRIME) – Research Programme Consortium (RPC).
Programme Value: £6,017,407		Review Date: September 2015
Programme Code: 201446	Start Date: May 2011	End Date: April 2017

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	A	A+	A+	A+
Risk Rating	High	High	High	High

Summary of progress and lessons learnt since last review

PRIME is performing strongly and on track to provide world class evidence on implementation and scaling up of treatment programmes and having this adopted by policy makers for the benefit of the poor. There has been a substantial (on average 239% higher) increase in treatment for those suffering from mental health disorders in PRIME countries. PRIME has a strong country and global resonance amongst policy-makers, particularly within the health sector and academia. Examples include Ethiopia’s National Mental Health Strategy, Ministers championing the cause, developing state plans in India, and improving national training curricula.

PRIME have completed their baseline and Mental health Care Plan (MHCPs) studies in five countries. However, the cohort studies, faced recruitment challenges and are not complete. It is recommended that PRIME now focus in on 3 countries (rather than 4) to ensure good study depth and quality and provide adequate time for dissemination.

PRIME has addressed the key recommendations from last year’s review. Progress includes improved budget spend against agreed projections. There was no significant underspend and variance (allocation to spend) remained under 10%.

Summary of recommendations for the next year
Output 2: To maintain emphasis on quality and country context, Output 2.1 should reduce from “Evaluation of scale up completed in 3 PRIME countries (instead of 4) by January 2017.

Output 3: PRIME should clarify areas where user participation in Community Advisory Boards (CABs) has not been successful and how they will overcome this. In areas where there is good participation, they should maintain emphasis on the quality of participation and level of influence, to be reported in the next annual report.

Output 4: PRIME should continue to seek advocates and opportunities within their country partnerships and champions within Government Ministries and report progress in the next annual report.

Risk: PRIME to follow up WHO and Addis Ababa University to ensure all financial risk audits are complete across all RPC partners by March 2016.

Commercial: PRIME should provide a brief comment on the status of their asset register and the frequency of review, in their next annual report.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/

Outline of the programme

The need for mental health services is extremely high. Life time prevalence for mental disorders is between 12.2% and 48.6% globally and the one year prevalence is between 8.4% and 29.1%. More than 13% of the global burden of disease is due to neuropsychiatric disorders. Almost three quarters of this huge burden lies in low and middle-income countries (LMIC) and this burden is projected to grow dramatically in the next decade, in part due to demographic and epidemiological transitions in LMIC. Mental disorders are a major contributor to economic hardships and are strongly associated with social and economic disadvantage.

Despite this enormous burden, a multi-country survey supported by the World Health Organisation (WHO) showed that almost four out of five people with severe mental disorders in LMIC had received no treatment whatsoever in the previous year. “Treatment Gaps” were especially large for depression and alcohol use disorders. There treatments are accessed, they are often inappropriate and involve considerable out of pocket payments, leading to catastrophic health expenditure.

The UK is providing £6 million over the period 2011 to 2017 to generate world-class research evidence on the implementation and scaling up of treatment programmes for priority mental health disorders in primary and maternal health care contexts in low resource settings.

PRIME is based in Ethiopia, India, Nepal, South Africa and Uganda. Comparing experiences across these diverse settings, which include fragile settings, will enable PRIME to generate knowledge with local and international relevance. By the end of the RPC, the following key research questions will have been answered:

- What are the feasible and acceptable components and packages of care for priority disorders and how can they be integrated into routine primary health care and maternal health care?
- What is the feasibility, acceptability, costs and impact of various models for delivery of the packages of care in routine primary health care and maternal health care settings?
- What are the health system requirements for scaling up: human resources; training and supervision needs; infrastructure; drugs; budgets; and the incremental cost of increasing coverage per new patient treated?
- What are the specific barriers which influence access to services for people living in poverty with mental disorders, particularly women during the perinatal period.
- What is the impact of scaling up of the integrated mental health care plan on coverage and utilisation of mental health care?

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment : A+ - Outcome moderately exceeded expectations

PRIME is on track to meet their outcome of world class evidence on implementation and scaling up of treatment programmes and having this adopted by policy makers for the benefit of the poor. There are several good examples of their research evidence used in citations, health plans and speeches. There has also been a substantial (239% higher) increase in treatment for those suffering from mental health disorders om PRIME countries. PRIME also has a strong country and global resonance amongst policy-makers, particularly within the health sector and academia. Examples include Ethiopia’s National Mental Health Strategy, Ministers championing the cause, developing state plans in India, and improving national training curricula.

PRIME has made significant contribution to beneficiaries and people living with mental illness. Two strong examples include the documentary film project in Nepal and South Africa and strong media coverage from World Mental Health Day.

Overall output score and description: A+ - outputs moderately exceeded expectations

The programme met or exceeded each of the four output areas. Each output scored A+. PRIME has produced a strong, coherent body of literature in mental health and has influenced standards of care at global and country level. However, it will take time to create this level of change at scale and in a package of care model. Fragmentation and parallel services for mental health remain the norm in most low and middle income countries. PRIME faces several external challenges in working at scale and bringing together all the strands into an overall package of care.

Two key challenges this year include advancing specialist areas of maternal mental health and alcohol use disorder and in securing financial commitments from government ministries. By making strong progress with academics and beneficiaries (mental health users), the seed changes are likely to grow and build over time. In several countries already, PRIME evidence has influenced and shaped district-based mental health care plans, quality training, and technical support to treatment services.

Key lessons

PRIME has produced strong, solid progress on producing evidence, bringing mental health to the global forefront and influencing WHO, country governments and raising public awareness.

Over the course of the last four years, PRIME has successfully worked through structural and capacity challenges with partner institutions in country. PRIME has proactively managed and mitigated management, delivery and capacity issues. This year has been similar as PRIME are working through capacity issues with their partner in Uganda.

PRIME have encountered structural, system-based, and societal challenges within their maternal mental health and alcohol use agendas. Services are provided separately in maternal mental health making it difficult to identify and access people in need. Within alcohol services, access is also low, particularly amongst men, as there is a reluctance to come forward. The impact of this is that it has been more difficult to recruit or get a large enough sample size for some studies. This has created some delays in the research agendas. Mental health issues are complex and multi-faceted, requiring long-term concentrated efforts.

Key actions

PRIME are entering the last stages of the research cycle and they must continue to focus on dissemination and uptake while not compromising quality and attention to beneficiaries. PRIME have made tangible progress in producing evidence and improving mental health policy and practice at global, country, and district level. They should continue to sustain these gains whilst commencing the synthesis work and lesson learning. Specific recommendations related to output areas are listed under summary of recommendations on the first page.

Has the logframe been updated since the last review?

No, the logframe indicators have not changed. These were last updated in 2013. However, last year, the risk rating was upgraded from medium to high in order to more accurately reflect the complex challenges of creating change within this neglected area of health and the likelihood of reaching substantial scale up during the programme life-course. The programme has adjusted well to the risk modification and has provided detailed assessments and mitigation strategies to areas where improvements are needed (primarily staffing and government engagement).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Establish and maintain an efficient and well managed RPC which draws on the strengths of each partner to deliver a high quality research programme that achieves the RPC’s goal and purpose.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Proportion of the following RPC deliverables completed in consultation with all consortium partners – Contracts between partners – PRIME country personnel recruited – M&E framework including logical framework refined – Detailed financial management plan for Phases 2 and 3 – Capacity Building Plan agreed – Research uptake plan agreed.	Key programme documents reviewed and revised as needed during project to improve progress towards achieving outputs, purpose and goal of the RPC, by 2017	On track. Programme successfully achieved most of its Phase 2 objectives. Some variability for policy-making at country level but has been effectively managed through the consortium
1.2 Number of meetings held during inception and implementation phases of key governance groups (PMG; CAG; CMG).	No specific milestone for 2015.	Milestone achieved in 2014
1.3 Draft mental health care plans (MHCPs) for priority disorders in primary care and maternal health care available.	No specific milestone for 2015.	Milestone achieved in 2014

Key Points
PRIME has moderately exceeded expectations for output 1. The RPC has taken on board points from last year’s annual review and addressed its budgeting predictability and planning as well as completed most of its tasks for stage 2 (implementation). Strong progress in 2015 includes MHCPs implemented in all sites, Community Advisory Boards (CABs) functioning well and an active and engaged CAG. Outputs 1.2 and 1.3 have been completed and the programme is in the final stages of the implementation phase. The programme has balanced making good progress at individual country level and capacity building alongside joining this up into a coherent narrative on global mental health research priorities and progress.

Summary of responses to issues raised in previous annual reviews (where relevant)
Improve disbursement against spend. This year PRIME achieved 94% of their budget actualisation (forecast/spend) which is a large improvement over previous years. PRIME should prioritise the timeliness of funding submissions.

Finalise research studies in order to commence dissemination and research uptake: The baseline studies in phase 2 are complete, recruitment has commenced for the cohort studies. PRIME are commencing successful research uptake with target groups.

Recommendations
None
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	A coherent body of high quality, peer reviewed and policy relevant research that makes a significant contribution to understanding the implementation and scaling up of packages of care for mental disorders.
Output number per LF		2	Output Score	A+
Risk:		High	Impact weighting (%):	50
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Research project is implemented in countries	Cohort studies complete in all PRIME districts by end of year 5 (2016/17)	On track: RPC has made strong progress during the year. Anticipate meeting target by end Yr 5
2.2 # of high quality relevant primary research papers by RPC partners published in peer reviewed publications. # of conference presentations by RPC partners	20 papers published, 10 conference presentations by 2015	Milestone exceeded: 26 papers, 19 conference presentations, 4 posters and 1 film
2.3 Number of partner institutions who collaborate and publish with each other	All partners collaborate on publications between 2013 and March 2015	Milestone exceeded: all collaborations achieved ahead of target date

Key Points

The programme has made substantial progress in developing a body of strong research that is relevant to policy makers at country level and globally. The RPC has taken on a large complex mental health agenda (spanning from addiction to maternal-specific areas) as well as a broad-based research agenda. For example, PRIME contributes systematic reviews and primary research, including developing a body of formative research. On Output 2.1: Recruitment for the cohort studies has been slightly slower than expected. PRIME have managed the tension of providing capacity and support to countries, they have applied the learning on why recruitment has been slower than anticipated (variations in care seeking behaviours and health service use, undiagnosed or untreated conditions), to identify ways to make up lost time.

There is a clear demonstration of the quality and capacity building nature of this RPC. As well as quantifying publications, the programme tracks progress on first authorship from LMIC and female first authors over time. PRIME has doubled or tripled its outputs on LMIC and female first authors. PRIME also monitors the quality of collaboration between partners. The major contribution on joint collaboration this year was their British Journal of Psychiatry supplement, including 10 papers on Mental Health Care Plans (available online on 7 October 2015).

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

To maintain emphasis on quality and country context, Output 2.1 should reduce from “Evaluation of scale up completed in 3 PRIME countries (instead of 4) by January 2017.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective communication of relevant research findings and their uptake by national and international stakeholders to influence policy and practice in the study countries and other low and middle-income countries.
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 # of PRIME products disseminated to policy makers and donors across relevant sectors via multiple channels (conferences, high level briefings, workshops etc.) at Local, National, International levels	At least 15 PRIME products disseminated to policy makers and donors by 2015	Milestone exceeded: 21 products disseminated
3.2 Participation of mental health service users and community groups in mental health care	MH service users represented on CABs in all districts by 2015	On track: Service users represented in most districts
3.3 # of PRIME citations in the media.	At least 50 media citations of PRIME or PRIME outputs by 2015	Exceeded. 61 citations
3.4 # of citations of PRIME outputs in research articles or other academic pubilications, curricula or training materials	150 citations of PRIME outputs by 2015	Exceeded. 428 by Google Scholar and 228 by Scopus

Key Points

PRIME continues to excel at communication and policy influence at global and country level. This will become increasingly important in the final stages of the programme. On output 3.2, although there are many individual examples of success at country level, PRIME have not yet reached their target of service users on every CAB by end 2015. This is not necessarily a problem, as the quality of participation (depth) highlights this as a continued strength and other external factors determine committee membership. Service user participation and influence remains a key strength as demonstrated through the documentary film and photo essay.

All outputs exceeded their milestones ahead of schedule, and PRIME is well placed for their next phase of scaling up and dissemination.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

PRIME should clarify areas where user participation in CABs has been less successful and how they will overcome this. In areas where there is good participation, they should maintain emphasis on the quality of participation and level of influence and report back in the next annual report.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Capacity exists in study countries to conduct and effectively disseminate research to improve access to mental health care.
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Number of externally funded policy relevant research grants successfully applied for; and level of funding achieved	4 externally funded research grants successfully applied for > £10,000,000 in value by 2017	On track: (currently exceeds £10,000,000), a substantial achievement
4.2 Number of researchers who complete higher training and/or successfully apply for fellowships	4:10 (Female: Male) PRIME researchers registered and PhD programme started, 50 registered or completed master’s programme started, 1 successful fellowship applied for by 2015	Exceeded milestone: 5 Male:8 Female PRIME researchers registered or in the process of completing registration for a PhD; 104 students have registered and begun structured Masters programs supported by PRIME; 3 researchers have sucessfully applied for fellowhsips and 1 fellowship for PhD studentship awarded
4.3 Number of research publications and other research outputs by PRIME partner groups.	Research publications by partner groups increase by 10% from 2012 to 2015	Exceeded: publications increased by 20%

Key Points
All milestones have been met or exceeded. PRIME’s country teams, and work with junior researchers, is a key strength. There is some variability of engagement in the PRIME countries within government (Ministry of Health and Ministries of Finance). Integrated mental health and advocacy appears to influence policy and practice when there are particular champions within government. PRIME have maximised their opportunities to disseminate research and evidence to guide policy, strategy and decision-making to improve mental health.

The capacity building needs vary across each of the PRIME countries. PRIME has successfully adapted the consortium to meet the needs of each of the local contexts. They have coupled this with strong leadership to support the drive to produce high quality global research outputs. The RPC benefits from each country’s experience.

Summary of responses to issues raised in previous annual reviews (where relevant)
Multiplier funding has been monitored and DFID expenditure has not been affected. PRIME has improved budget forecast to expenditure (below 10% variation in 2015).

Risk rating adjusted to high and PRIME deal with risk in a transparent, proactive fashion by frequently updating DFID and other stakeholders on developments, highlighting emerging trends, and discussing mitigation strategies.

Recommendations
PRIME should continue to seek advocates and opportunities within their country partnerships and champions within Government Ministries and report progress in the next annual report.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers are personnel, programme costs, overheads and communications. PRIME is fully aware of the need to contain costs and work within the planned budget. Spending has been consistent over time and is done in accordance with DFID guidance on VfM. PRIME measures VfM through the principles of transparency, accountability and balancing cost and quality of goods. PRIME have a strong narrative on leveraging staff time, additional resources and maximising opportunities within their country and professional networks.

The RPC is achieving or exceeding all of its milestones and remaining within the budget. Economies of scale are made through cross-partner collaborative working wherever possible and capitalising on broader experience and expertise within partners institutions.

VfM performance compared to the original VfM proposition in the business case

PRIME does not explicitly report on the three VfM measures of economy, efficiency and effectiveness, although it implicitly follows DFID guidance, through efforts to contain costs and maximise outputs against resources. PRIME met or exceeded the majority of its outputs and indicators and seeks to ensure VfM through focusing on prioritising areas of strategic importance to the consortium; cost containment and cost efficiency; investing in capacity building to improve research quality and programme effectiveness; and; leveraging co-funding. They have remained flexible through institutional, political and economic changes at the country level which have impacted on engagement and fluctuating currencies.

Assessment of whether the programme continues to represent value for money

This RPC continues to offer good VfM for DFID, for mental health research and for beneficiaries. The RPC has consistently scored highly and delivered strong tangible research results. It has also sought to integrate mental health into wider heath systems strengthening at policy, government systems and community levels. By doing this, PRIME has led a strong narrative that good mental health policy can be built into existing systems rather than additional or parallel structures. PRIME has made a strong economic argument for the inclusion of mental health care as well as addressing the unmet burden.

Quality of financial management

PRIME has applied their principles of transparency and accountability and demonstrated how they implement this in practice. Finances are fully reviewed quarterly by the management team and country teams. There are additional scrutiny and spot check measures in place to examine discrepancies or to improve timeliness.

PRIME Management Team apply financial management systems at all levels, scrutinise audited statements and review financial reports. This year one country office, Uganda, did not provide high quality satisfactory responses to the financial questionnaire. PRIME are encouraged to continue to apply additional scrutiny and monitoring, apply their mitigation plan and inform DFID of any changes required to programme delivery.

PRIME has a slight underspend on their budget allocation for the UK financial year 2014/15. The underspend amounts to approximately 5% which is reasonable and an improvement in forecasting accuracy from previous financial years.

Date of last narrative financial report	11 Aug 2015
Date of last audited annual statement	18 Sept 2015

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk
The risk areas outlined in the original business case remain valid. Risk levels have not changed in the past year. Intellectual risk and management risk remain medium but output and context risk remain high resulting in an overall high risk rating. The primary risk relates to programmatic and technical delivery. The greatest risk is insufficient research uptake by Governments and Ministries of Health. This risk is largely external and relates to the challenging country environments, encouraging host governments to progressively implement a new and largely untested health agenda, in the contexts in which they work.

PRIME recognise the critical importance of policy-relevant research. Uptake and dissemination are two of their key objectives in the final two years. PRIME employ a number of communication and influencing strategies to improve uptake. This has been particularly successful at the global level (e.g. within WHO) and within research and academic settings. PRIME continue to focus on the country level.

The fiduciary risk has not changed since inception of the programme. There is clear, regular reporting and oversight on finances at management and operational level. The PRIME Counter Fraud and Anti-Corruption policy has been in place for two years. To date there have been no reported cases of mismanagement or misappropriation.

Outstanding actions from risk assessment
PRIME to follow up WHO and Addis Ababa University to ensure all financial risk audits are complete across all RPC partners by March 2016.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme has met and, in many cases, exceeded its milestones and is on track against its planned workplan. The programme continues to make significant traction in a wide range of research areas. Work continues on the complex areas of maternal mental health and detection and treatment of alcohol use disorder but these two areas have not progressed as quickly as expected, due to factors external to the RPC. For example, maternal care and mental health services are led and delivered as separate services in most country contexts. In spite of this separation, PRIME has managed to do a number of critical studies and programmes in maternal mental health. As discussed in earlier reports, PRIME also encountered a lower detection of alcohol use in primary care. PRIME has used this to their advantage to explore and understand patterns and perceptions of alcohol use at a community level.

PRIME continues to work well in a challenging and underserved area of health. In addition to delivering strong research outputs PRIME has also explored and revealed important global health issues such as mental health stigma, gender and access (low rates of men seeking support services).

Performance of partnership (s)
The RPC is well run and functioning well at all levels of management and organisational delivery. PRIME have highlighted to DFID specific areas where research capacity remains low and where specific strategies are needed to improve performance in one country. The CAG meets bi-annually and appears to engage well with programme delivery.

Asset monitoring and control
PRIME maintains an asset register recording single items with a value in excess of £1,000. The register was most recently submitted to DFID on 17 July 2015 and reviewed by the RED programme staff. Due to the nature of the programme there are only a small number of entries recorded, the register is fit for purpose and accurate. PRIME will continue to monitor and update the asset register as necessary and submit to DFID as part of their annual report.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable. DFID provides funding to the RPC through the lead institution and no funding flows directly through any Governments.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

An independent midterm review was conducted in the summer 2015. The findings and recommendations were shared with PRIME and used as part of this annual review process.

Monitoring progress throughout the review period

This review was carried out by members of the Human Development Team in DFID’s Research and Evidence Division with input from health advisers in Policy Division and members of the consortium. During the reporting period, members of the DFID team have met with RPC members, had frequent telephone and email engagement with the Senior Management Team and with the CAG. A first draft of this annual review was prepared by the team conducting the independent midterm review.