Cover page
Title: Humanitarian Assistance and Resilience Building in South Sudan (HARISS)
Project Purpose: Save lives, avert suffering, maintain dignity and reinforce coping capacities of those affected by conflict and shocks in South Sudan.
Programme Value: up to £443million		Country/ Region: South Sudan
Senior Responsible Owner: Vicky Stanger (Lead Adviser Anais Lafite)
Project Code: 204019	Start Date: 1 April 2015		End Date: 31 March 2020
Quest Number: 5207793

CHF	Common Humanitarian Fund
FAO	Food and Agriculture Organisation
FEWS NET	Famine Early Warning Systems Network
FSL	Food security and livelihood
GAM	Global acute malnutrition
GBV	Gender based violence
GUN	Greater Upper Nile
HC	Humanitarian Coordinator
HCT	Humanitarian Country Team
H/SRP	Humanitarian/ Strategic Response Plan
ICRC	International Committee of the Red Cross
ICWG	Inter Cluster Working Group
IDP	Internally displaced person
IGAD	Intergovernmental Authority on Development
INGO	International nongovernmental organisation
IOM	International Office for Migration
IPC	Integrated Food Security Phase Classification
IRC	International Rescue Committee
MAM	Moderate acute malnutrition
NGO	Nongovernmental organization
OCHA	Office for the Coordination of Humanitarian Affairs
OXFAM	Oxford Committee for Famine Relief
PoC	Protection of Civilians
RRM	Rapid response mechanism
SAM	Severe acute malnutrition
SGBV	Sexual gender based violence
SRP	Strategic Response Plan
UN	United Nations
UNHAS	United Nations Humanitarian Air Service
UNHCR	United Nations High Commissioner for Refugees
UNICEF	United Nations Children’s Fund
UNMISS	United Nations Mission in South Sudan
WASH	Water, sanitation and hygiene (Cluster)
WFP	World Food Programme
WHO	World Health Organisation

Figure 1. Reference map of South Sudan

List of tables
Table 1. South Sudan Humanitarian Response Plan and UK contributions, 2014 and 2015
Table 2. Programme budget per scenario
Table 3. Appraising options b to e
Table 4. Procurement types, indirect spend
Table 5. Procurement timeline
Table 6. Indicative annual spends per delivery channel
Table 7. RDEL and CDEL budget shares, in million GBP
Table 8. Main risks to the humanitarian programme and mitigation measures
Table 9. Evaluation questions

List of figures
Figure 1. Reference map of South Sudan
Figure 2. Severely food insecure people in percentage to total population, IPC data, 2011- 2015
Figure 3. Preferred option, target beneficiaries, delivery channel and selection process
Figure 4. Theory of Change for the preferred option
Figure 5. Components of the programme logical framework
Figure 6. Decision tree for the Internal Risk Facility

Executive summary
Why is UK support required?
1. South Sudan is engulfed in a severe, protracted humanitarian crisis. Since the start of the conflict in December 2013 more than 50,000 people have been killed, over 2.2 million displaced (1.6 million internally) and 3.9 million people (34% of the population) were severely food insecure in September.
2. Grave human rights abuses and international humanitarian law violations are being reported[1]. The communities that are most severely affected by the conflict are surviving by selling any assets they have, eating wild food (such as water lilies), hiding in swamps and making treacherous journeys to flee violence. Much of South Sudan is also vulnerable to seasonal food insecurity, acute malnutrition and disease as well as droughts, floods and inter-communal conflicts.
  [1] Flash Report on escalated fighting in Greater Upper Nile region, United Nations Missions in South Sudan (UNMISS), June 2015.
3. South Sudan is the world’s newest country. It is also officially the world’s most fragile country. It has practically no institutional capacity or infrastructure. A combination of rampant corruption and patronage politics has led to much of its considerable oil wealth being squandered. It is now immersed in a disastrous internal conflict and threatened by a looming economic crisis.
4. To date, in 2015 1.7 million people have been reached with humanitarian assistance[2]. However, humanitarian access is increasingly difficult due to insecurity, poor infrastructure and an increasingly hostile operating environment. The US$1.63 billion 2015 UN Humanitarian Response Plan is only 55% funded. Prior to independence in 2011, during the decades-long war of independence against Khartoum, South Sudan was severely aid dependent. The resumption of conflict means the country continues to rely heavily on external assistance. Substantial multi-donor support (in part led by the UK) helped avert famine in 2014 and reduce the number of people facing severe food insecurity in 2015. The UK is the second largest bilateral humanitarian donor in South Sudan. We have contributed £272 million since December 2013 and in 2014 UK funding was almost 10% of the country’s humanitarian appeal. We estimate one million people have been assisted with UK funds since the beginning of the crisis. However, the number of people affected by the humanitarian crisis keeps growing.
  [2] ibid
What support will the UK provide?
This Business Case argues for a new approach to supporting the most vulnerable citizens of South Sudan. We are proposing a significant change in the delivery of humanitarian aid. This programme will enable us to move away from short-term assistance which meets only immediate needs to a flexible, multi-year approach which will work to increase the resilience of affected populations, including to climate variability, and improve the efficiency of the overall humanitarian response. The programme will also be scaled up or down according to needs and according to commitments from other donors and the Government. This approach will not only save lives, but also build the capacity of people to recover and cope better with shocks. This will ultimately contribute towards greater resilience, with the express aim of contributing to move South Sudan out of the vicious cycle of aid dependency.
Funding of up to £443 million[3] is proposed, which is expected to reach an estimated 3 million people between 2015 and 2020. Multiyear agreements will be established with partners giving them the flexibility to set amounts (within their overall allocation) and adapt their approach annually, based on the evolving context and needs and with DFID’s validation. DFID will also have the flexibility to adjust annual amounts based on performance over the previous year. We will have some flexibility on our overall budget (hence the ‘up to’) as the amounts set for the Common Humanitarian Fund (CHF, £62m) and the Internal Risk Facility (IRF, £24m) can also be flexed over the course of the programme.
[3] Out of these £443 million, £110 million has already been approved (£40 million in February 2015 (Quest number 4904302), £40 million in July 2015 (Quest number 5064879), £30 million in October 2015 (Quest number 5190558).
What are the main programme activities?
The programme has four components:
1. Life-saving humanitarian assistance to reduce the vulnerability of people through: (i) the provision of food, water, sanitation and hygiene, health, nutrition, shelter and emergency non-food items; (ii) making the humanitarian coordination system more effective and accountable. This component will focus on the Greater Upper Nile region where peace is fragile and humanitarian needs are growing.
2. Resilience-building to help vulnerable populations prepare for, cope better with and recover from conflict and natural hazards that cause humanitarian disasters and stresses. Some work will address the implications of climate change too since those aggravate existing vulnerabilities. The resilience approach will focus on food security and livelihoods (including restoration of environmental capital and strengthening climate resilience), protection and reducing violence against women and girls (VAWG), emergency preparedness and response and building the capacity of national NGOs and relevant local Government authorities. This component will target the most vulnerable populations who have historically resorted to perverse coping strategies to cope with conflict, displacement, disease outbreaks or climatic shocks. It should help them move towards increased self-sufficiency. Our assumption (to be tested) is that with more consistent, regular humanitarian assistance via the multi-year approach, this population will no longer be forced to adopt extreme coping measures and will therefore no longer require expensive emergency/humanitarian aid.
 (3) Monitoring, evaluation, accountability and learning (MEAL) to ensure that the programme learns and adapts. Real-time evaluations and reviews will assess project quality against humanitarian standards and contractual targets, and measure progress against three criteria: (i) conflict-sensitivity, (ii) accountability to affected populations (AAP) and (iii) Value for Money (VfM). ‘Real time’ data will ensure we detect and act quickly on any aid diversion or losses, thereby limiting our risk exposure.
(4) An Internal Risk Facility of £6 million per annum will be introduced. Based on successful Somalia and Ethiopia facilities, this will provide the programme with flexibility to respond rapidly to shocks and unforeseen needs across the country. Risk mapping, prevention options and response strategies may be supported.
This multi-year programme is a key part of HMG’s draft National Security Strategy for the Sudans as well as the DFID South Sudan Bilateral Aid Review. Both of which focus on the need to move the South Sudanese from aid dependency to resilience, whilst ensuring the GRSS is both accountable and responsible for its citizens.
What are the expected results?
1. Moving to a flexible, multi-year programme will not only deliver better outcomes for the people of South Sudan, it will also be more measurable and achieve greater VfM. It increases predictability, provides partners with greater flexibility, incurs lower operational costs and allows donors and their partners to develop more strategic partnerships and a longer term vision. It will also provide better value for money, which we will measure through our MEAL and with VFM metrics in each project, as it can facilitate operational savings through earlier response, longer term planning, staff costs and ability to preposition stocks.
2. Our objective is to save lives, relieve suffering and maintain the dignity of those affected by the crisis and rebuild foundations for sustainable livelihoods. This includes internally displaced people and vulnerable host communities in the three conflict-affected states of Upper Nile, Unity and Jonglei states, as well as IDPs sheltering in Protection of Civilian (PoC) sites across the country. The UK contribution will be critical to averting starvation and a public health crisis in the country. We will:
- Reduce the vulnerability of people in need in conflict-affected states: an estimated two million people will be supported over the course of the programme with at least one form of humanitarian assistance.[4] We expect to lessen the risk of mortality and morbidity amongst displaced populations and vulnerable host communities. Over 75% of all children admitted into nutrition programmes should recover and their lives saved.
  [4] This figure is cumulative. It is assumed that beneficiaries of this programme component will be new from one year to another except in IDP camps / Protection of Civilian sites, which only account for 10% of the displaced population caseload in country. Each beneficiary will receive at least one form of humanitarian assistance (eg. Food assistance), and often receives more (eg. health, nutrition or water). These are therefore unique beneficiaries.
- Build resilience of the most vulnerable populations to prepare, withstand, adapt to and recover from disasters and shocks (conflict, disease and climate-related). This will target an estimated one million people who will be identified early in the programme and supported for 3 to 4 years as resilience requires longer-term investment. We will focus on:
(i) livelihood opportunities as alternatives to food aid such as diversified local food production systems and designs, stimulating market recovery through cash interventions supporting traders to source supplies and the most vulnerable to access them and cash for work schemes building community and household level climate change adaptation measures (e.g. flood defences, environmental regeneration, water retention landscapes, soil conservation measures);
(ii) protection activities, helping vulnerable populations better cope with and reduce their exposure to protection abuses, including Gender Based Violence (GBV); activities will include support to community-based protection mechanisms, increased access to Gender Based Violence (GBV) response services and GBV risk reduction and prevention.
(iii) emergency preparedness and response, supporting early planning, warning and action ahead of and in response to disease outbreaks and population displacements particularly. Rapid response should be deployed within 72 hours of a crisis.
We expect that the number of households resorting to negative coping strategies (e.g. selling assets) will reduce, that livelihood opportunities will be more diverse and more resilient to climate induced shocks and stresses, and that vulnerable populations including women and girls will experience less violence and feel safer.
Better monitor and evaluate the impact of our investments. The monitoring and evaluation component will help us to learn more about the impact of our interventions and the effectiveness of multiyear programming. It will also provide systematic feedback from beneficiaries and enable adaption of programming according to their needs and priorities. A team will be contracted to work with our partners to deliver this component. The results will help not only DFID, but the broader humanitarian community.
How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?
This programme is consistent with UK’s planned approach in South Sudan following the signing of the peace agreement (August 2015). Peace will be fragile and our office priority will be to support the embedding of the Agreement whilst protecting the most vulnerable. DFID South Sudan draft Bilateral Aid Review (BAR)’s vision is that of an increasingly peaceful and stable South Sudan where people are supported with high quality, life-saving humanitarian and development assistance. Our humanitarian programme supports the second Country strategic objective (Protecting the Most Vulnerable).
What are the key risks to the success of the programme?
1. South Sudan is an extremely high risk operating environment, given the unpredictability of the ongoing conflict. This has made the delivery of assistance very difficult and made South Sudan one of the most dangerous places in the world to be a humanitarian aid worker – 30 humanitarians have been killed since the beginning of the conflict and many more injured. Other risks include rising criminality, insecurity and political instability, fraud, corruption and theft, the economic crisis and poor infrastructure. Armed hostilities displace populations and also increase costs of operations. The loss of assets through looting and theft is also a risk.
2. It is therefore important that humanitarian support is provided by agencies with proven capacity to operate at scale in extremely hostile conditions and who have rigorous measures to safeguard aid personnel, infrastructure and supplies. It is also critical to plan for, mitigate and regularly monitor risks. A detailed risk mitigation and management strategy is at Annex E. DFID South Sudan was audited by DFID’s Internal Audit Department (IAD) in 2015. They assessed DFID South Sudan’s controls as “adequate to mitigate the risks in practice”. It further noted that the office was “cognizant of the high risk environment and pro-actively manages these, particularly within the humanitarian programme[5]”. IAD recommended the office could learn from the Humanitarian Team’s mix of approaches to managing risks.
  [5] Internal Audit Department, April 2015

Strategic case
Context and need for a DFID intervention
Context
1. Civil war erupted in South Sudan in December 2013, triggered by a long-standing power struggle between President Salva Kiir and former Vice President Riek Machar. Violent, armed conflict rapidly spread from the capital, Juba to the majority of the country, engulfing the Greater Upper Nile region (Jonglei, Unity and Upper Nile states). The peace agreement signed in August 2015 is fragile and fighting has continued despite the cessation of hostilities that came into force the same month. The IGAD Monitoring and Verification Mission (MVM) has been unable to hold the parties to account and the United Nations Mission in South Sudan (UNMISS) does not have a presence in opposition-controlled areas and despite praiseworthy efforts recently, it has been regularly denied access to critical areas by the GRSS[6]. There is also evidence of horrific human rights and international humanitarian law (IHL) violations during the escalation of fighting between May and July 2015 particularly.
  [6] Flash Human Rights Report on the escalation of fighting in Greater Upper Nile, United Nations Missions in the Republic of South Sudan (UNMISS), 29 June 2015; Humanitarian Country Team meetings, October 2015
2. The civil war is exacerbating pre-existing inter-communal and ethnic violence. Other political groupings beyond the main warring parties are being excluded from peace negotiations, which can lead to marginalisation from future power sharing. This may fuel grievances and generate further insecurity. Beyond the Greater Upper Nile region tensions are building and instability is spreading, which could lead to increased displacement and new humanitarian needs.
3. South Sudan’s leaders are hampering rather than enabling the delivery of humanitarian assistance. Access to conflict-affected populations has been increasingly difficult since May 2015 as conflict parties have not upheld their responsibility to ensure the safety and security of humanitarian organisations in areas such as southern Unity or western Upper Nile. Essential river transportation routes have been cut off and flight clearances refused. Progress was noted after the signing of the peace agreement but continuous pressure is necessary and critical areas remain inaccessible. The increasingly repressive GRSS seems determined to push through restrictive laws on the operation of non-governmental organisations (NGOs) further exacerbating the ability of partners to deliver. The GRSS interaction with donors and others is becoming increasingly belligerent, although HMG continues to work for a constructive relationship with GRSS.
4. The dramatic fall in global oil prices combined with a significant reduction in oil production has resulted in a steep decline in oil revenues.[7] This, combined, with the escalating costs of the war has resulted in an economic crisis. Despite discussions with international financial institutions and partners, it seems unlikely that the GRSS will manage to control its budget deficit or reduce security sector spending whilst the war continues. Rising inflation is significantly weakening purchasing power of ordinary people and the minimum basket of food expenditures has risen by 119% in Juba over the last year. The United Nations estimate that over the next few months 610,000 urban poor could require food assistance if the economic situation deteriorates further.
  [7] The Government earned $45 per barrel (after making payments to Sudan) before the conflict when crude sold at $110 on the international market. In June 2015 oil was trading at $65 per barrel, the Government earned $13 per barrel and produced half what it did before the war as production is largely concentrated in the conflict affected Greater Upper Nile region.
Humanitarian Needs
1. South Sudan has suffered from decades of conflict and insecurity leaving the country with enormous humanitarian needs, including chronic food insecurity. Over the last decade, 10% of the population has suffered from severe food insecurity. Where people were unable to plant or move freely with their livestock, reliance on humanitarian aid for survival grew. Even before this current conflict there were significant humanitarian needs in South Sudan. From 2006 – 2011 the UN Humanitarian plan targeted c. 1.2 million people per year.[8] By 2013, 3.3 million people were targeted. The humanitarian impact of the ongoing civil war, which broke out in December 2013 has been dramatic. One out of six South Sudanese people is displaced. Since December 2013 over 2.2 million South Sudanese people have been displaced. 622,000 have sought refuge in the region, an estimated 200,000 people live in eight Protection of Civilian sites across the country[9] and 1.4 million live in spontaneous settlements and with host communities. 600,000 children are estimated to have been displaced, putting them at risk of abuse or exploitation.[10] 83% of IDPs are in the three states of the Greater Upper Nile Region[11] where 60% of people are suffering from acute malnutrition.
  [8] Information is based on multiple sources including: Sudan Work Plan 2007, Sudan Work Plan 2010, Consolidated Appeal Plan (CAP) 2011 mid-year revised figure, CAP 2012, Comprehensive Response Plan (CRP) 2014 mid-year update.
  [9] Information communicated by the International Office for Migration (IOM), to DFID South Sudan May 2015.
  [10] Child protection information sheet, UNICEF, February 2015.
  [11] Jonglei, Upper Nile and Unity states.
2. Seasonal climatic patterns and conflict combine to increase food insecurity, disease and malnutrition, exacerbating humanitarian needs. Numbers of severely food insecure people and the rates of acute malnutrition dramatically increase during the rainy season (May to August), which is also known as the lean or hungry season.[12] During the hungry season, people deplete their stocks but have not yet harvested, food prices increase and 60% of roads become impassable (underwater). Diseases such as malaria and acute water diarrhea increase significantly. Humanitarian actors need to plan to address seasonal vulnerability spikes whilst also responding to conflict-induced humanitarian needs – or the combined effect of the two. Critical mitigation actions include prepositioning life-saving aid supplies during the dry season, acting early ahead of seasonal spikes, and aligning funding cycles to seasonality.[13]
  [12] Seasonality desk study on South Sudan, DFID/IDS (PEAKS), April 2015.
  [13] The HCT has developed dry season planning for 2015. Although it is too early to tell how effective it has been, achievements have been noted in food and nutrition where the World Food Programme (WFP) and UNICEF have respectively prepositioned 80% to 100% of critical food and nutrition items before rains started.

Figure 2. Severe food insecure people in percentage to total population, IPC data, 2011- 2015[14]
[14] Information is based on IPC data extracted from each report available since 2011, as communicated by the FAO to DFID South Sudan in May 2015. The IPC key messages released in May 2015 undertake a similar exercise but only go back to 2013. Information is available upon request to DFID South Sudan.
1. The impact of climate variability and climate extremes is being felt already. It is expected to worsen as climate changes, with increasingly erratic rainfall patterns contributing to either drought conditions or flooding, in turn affecting livelihoods and health (with an increased risk of outbreaks, pest and diseases)[15]. The country’s agriculture and food security is still overwhelmingly based on rain fed, smallholder farming, with very low use of inputs, irrigation and storage. Households depend heavily on markets during the agricultural lean season. If seasonal rainfall declines or is poorly distributed, food access can be affected in two ways: i) Reduced seasonal crop production due to low rainfall can force households to purchase more of their food; ii) Climate-induced food price volatility can require households to spend more of their income on food. In addition, climate-related events such as floods can limit physical access to markets, make assets such as cattle more vulnerable to raiding, destroy ecosystem services (e.g. siltation of rivers, access to wild foods) and create standing pools of water with greater disease risk.
  [15] Changing patterns are hard to quantify, as high-quality climate information is not widely available in South Sudan. However, recent rainfall data shows a trend of decreasing annual rainfall contributing to drought conditions in many parts of South Sudan, noticeably in the south-eastern and northern semi-arid areas. Whilst in other agriculturally productive areas there is evidence of frequent, increasingly high rainfall leading to flooding, where the flood cycle is intensifying and is leaving less time for recovery. In addition, analyses suggest that there has been a shift in the start and cessation of rainfall, leading to more erratic and unpredictable rainfall patterns. Global and regional climate model performance is weak for this region; satellite data provides the bulk of meteorological data and makes downscaled predictions on flood and drought development of climate hazard indicators difficult. Nationally, the expected impacts of climate change in South Sudan are broadly: increased water scarcity, accelerated desertification and soil erosion processes, decreased crop productivity (a 20% drop in yields is predicted), increased damage by extreme climate events (droughts and floods), increased health-related illnesses and risk of pest and disease risk.
2. In South Sudan, an estimated 3.9 million people were severely food insecure (IPC phases 3 and 4) in September, after the harvest has taken place. This number exceeds any previously seen at this time of the year.[16] 30,000 people are already believed to be experiencing levels of food insecurity consistent with starvation. The risk of famine is real if humanitarian assistance is not scaled up according to the IPC[17]. People in phase 4 are unable to meet their own food needs and require urgent humanitarian assistance to avoid slipping into famine, at which point it is too late to save their lives[18]. Lives are most at risk in Greater Upper Nile where the effects of violence, displacement, food insecurity, malnutrition, disease and access constraints converge. However, food insecurity is also deteriorating in neighbouring states of Northern Bahr El Ghazal, Warrap and Lakes as they witness flooding, inter-clan cattle raiding, market disruption and increased arrivals of IDPs.[19]
  [16] Integrated Food Security Phase Classification System (IPC), October 2015. Findings were endorsed by the Government that however warned against the use of the word famine in a press release on October 22nd, 2015. If starvation reaches 20% of households in a county (currently at 10% in counties worst hit by conflict), a famine will be declared
  [17] Famine will be declared if catastrophic food insecurity (IPC Phase 5) is experienced by more than 20% of the population in a county. In the most critical counties today (4 counties in Unity state) 10% of the population is estimated to be facing catastrophic food insecurity. IPC, the Republic of South Sudan, September 2015.The information is restricted as the results have not yet been endorsed by the government of South Sudan.
  [18] Food Security and Nutrition Key Messages, IPC, the Republic of South Sudan, May 2015. The IPC is a set of standardized tools which classify the severity and magnitude of food insecurity.
  [19] Humanitarian snapshot, OCHA, June 2015. DFID is launching a food security resilience programme in 5 states this year including Northern and Western Bhar El Ghazal, Warrap, Lakes, Eastern Equaoria.
3. Rates of acute malnutrition are above emergency levels and the conflict has led to an increase in the number of children at risk. The number of under-five children at risk of acute malnutrition increased threefold between 2013 and 2014.[20] 235,000 children under-five are now at risk of Severe Acute Malnutrition (SAM) with acute malnutrition admissions into nutrition programmes reaching a four-year high.[21] In the Greater Upper Nile region Global Acute Malnutrition (GAM) rates[22] are above the emergency threshold (15%), with several counties at double that (30%).[23]
  [20] 2015 South Sudan Humanitarian response plan (HRP), United Nations (UN), November 2014
  [21] Scale Up Joint Report, WFP-UNICEF, March 2015
  [22] Global Acute Malnutrition (GAM) is a measurement of the nutritional status of a population that is often used in protracted refugee situations. Along with the Crude Mortality Rate, it is one of the basic indicators for assessing the severity of a humanitarian crisis.
  [23] Food Security and Nutrition Key Messages, Integrated Food Security Phase Classification ( IPC), Republic of South Sudan, May 2015 and October 2015
4. The conflict has created a protection crisis with extreme violations of Human Rights and International Humanitarian Law (IHL) committed by both sides. Civilians - often targeted because of their ethnicity or gender - have been exposed to a multitude of abuse, including killings, attacks and sexual gender-based violence (SGBV), arbitrary arrests and child solider recruitment.[24] The vast majority people who have fled their homes live in informal sites which offer little personal protection or basic services. Thousands have been killed, maimed, raped and forced to take huge risks to support their families.[25] Escalated fighting since early May has razed entire towns; schools, hospitals, homes and markets have been looted, bulldozed and burnt to the ground. Humanitarian personnel have been harassed and killed, humanitarian supplies and property have been looted and destroyed and humanitarian access has been blocked.
  [24] Sources include: “Children killed, abducted and raped in South Sudan attacks”, Press release - UNICEF, 18 May 2015; South Sudan Humanitarian Response Plan, 2015; UNMISS Human Rights report, May 2014.
  [25] Protection information sheet, UNICEF South Sudan, October 14; Protection Trends Analysis, South Sudan Protection Cluster, October 14 and May 2015.
5. Women and girls have been amongst the worst affected by the conflict. Violence against women and girls (VAWG), was pervasive prior to the current crisis and has significantly worsened since. While reliable data on overall numbers of survivors is not available, it is reported that both parties to the conflict have used sexual violence as a tactic of war and terror. According to social norms, women are primarily responsible for bringing food and water to their families often requiring them to walk long distances and cross front lines, exposing them to risk.[26]While the Government has made commitments to address conflict-related sexual violence,[27] on the ground GBV is getting worse, not better. Services for survivors are limited, especially outside PoCs; stigma and lack of trust discourages reporting among survivors. Short term humanitarian funding cycles (often one year at best) make it difficult for GBV programmes to build up trust between service providers and communities. Multi-year programming will give us the opportunity to develop longer term approaches that can prevent exposure to risks of GBV and VAWG while increasing access to services for survivors.
  [26] Protection Trends Analysis, protection cluster, January and April 2015; GBV in South Sudan, GBV sub-cluster, May 2015.
  [27] Joint communique, SRSG for Sexual Violence in Conflict and President Kiir, October 2014.
6. Traditional South Sudanese mechanisms to cope with multiple shocks have been severely eroded by the conflict, leading to increased reliance on humanitarian assistance. Abnormal cattle migration and unusual levels of livestock sales have been reported in conflict-affected communities.[28] People are increasingly reliant on food assistance in the Greater Upper Nile region with 30% to 60% of households not having cultivated in 2014 due to the conflict. Markets have been disrupted, income opportunities have drastically reduced and food prices are very high.[29] Household and community vulnerability has been exacerbated by the loss of some traditional livelihood systems. Historically, communities were well adapted to the impacts of floods and droughts due to transhumance[30] nature of their agro-pastoralist livelihood, but restrictions on mobility caused by conflict means that resilience options to flooding and drought have reduced.
  [28] South Sudan Food Security and Nutrition Monitoring, World Food Programme, December 2014.
  [29] Ibid.
  [30] Transhumance refers to cattle migration patterns in particular, whereby cattle and people move to different locations during the dry and the rainy season.
7. Although it remains difficult to predict, it seems highly likely the current crisis will be protracted. While the extent of the damage done to the country’s social fabric and communities’ resilience is yet to be understood, humanitarian actors are increasingly concluding that the levels of abuses suffered are unprecedented. The prospect of fighting continuing in the Greater Upper Nile region and spreading further is high. Based on our experience after the Comprehensive Peace Agreement (CPA), even if all fighting was to cease (best case scenario) humanitarian needs will remain extremely high for months, if not years to come, as we transition towards recovery and development assistance. Recovering from the devastating impact of this war will be a huge, long-lasting challenge. Upon eventual return to their communities many IDPs will find their homes and livelihoods destroyed. The physical, mental and social consequences will take a long time to address.
Strategic Fit with DFID Policies
Our proposed response is consistent with:
- The UK Government’s Humanitarian Policy (2011), which underscores DFID’s commitment to respond on the basis of need, ensure UK humanitarian action contributes to preventing and responding to VAWG, and to building resilience.
- DFID Country Poverty Reduction Diagnosis (CPRD) (2014), which outlines our ‘no regrets’ approach to UK humanitarian response and aims to maintain the UK burden share at 10% of the overall UN Humanitarian Response Plan. The ‘no regrets’ approach was developed following the 2011 Horn of Africa famine and recommends investing in early and preventative action in order to prevent the risk of famine again. The CPRD places significant emphasis on strengthening resilience, particularly in the area of food security.
- UK’s planned approach in South Sudan following the signing if the peace agreement. Peace will be fragile and our office priority will be to support the embedding of the Agreement whilst protecting the most vulnerable. DFID South Sudan draft Bilateral Aid Review (BAR)’s vision is that of an increasingly peaceful and stable South Sudan where people are supported with high quality, life-saving humanitarian and development assistance. Our humanitarian programme supports the second Country strategic objective (Protecting the Most Vulnerable).
- The International Development Gender Equality Act (2014). It considers gender in its analysis and design. DFID will promote the use of international standards, request partners to report using gender and age-disaggregated data and to demonstrate how they have engaged men, women, boys, and girls throughout the project cycle.
This Business Case is part of a strong cross-HMG approach. We are cognisant of the fact that to lessen the need for humanitarian aid in this country, more needs to happen politically and in the fields of essential services for instance. We are working very closely across the office (DFID, the FCO and the MoD) to advocate to the government that its takes increased responsibility for its people, and to the signatories to the peace agreement that they uphold their responsibilities to secure safe and unhindered humanitarian access to populations in need of humanitarian assistance. This approach is detailed in paras 114-116.
UK burden share
The UK is the second largest bilateral humanitarian donor in South Sudan after the United States. Our £272m contribution to the humanitarian response to date has had a significant impact on alleviating suffering. So far this financial year £110 million has been approved for the response in South Sudan, this money forms the first year 2015/16 funding administered under this business case[31].
[31] Quest number 4904302 (February 2015) , 5064879 (June 2015) and 5174555 (October).
	Total SRP (in $)	UK contribution (£)	UK contribution ($)	UK contribution (%)
2015[32]	1,633,000,000	110,000,000	165,770,000	10%
2014	1,600,000,000	132,000,000	198,924,000	12%
[32] This table shows funding per calendar year, not UK financial years.

Table 1. South Sudan Humanitarian Response Plan and UK contributions, 2014 and 2015
1. The $1.63bn UN humanitarian appeal for 2015 is currently 55% funded. At the pledging conference in Geneva on 16th of June, $275 million was raised - half the amount raised at last year’s humanitarian pledging conference. This year to date DFID has provided 14.2% of the humanitarian funding which has been made available.[33] Most donors are focusing on Food Security and Livelihoods (FSL), Health, Nutrition and WASH.[34] Given the funding shortfall, the UN humanitarian country team is prioritising life-saving activities. DFID is continuing to encourage other donors to increase their funding contributions to South Sudan to meet the large humanitarian needs.
  [33] FTS Total funding per donor at 21 October 2015
  [34] These 4 sectors are over 60% of all donor funds put into the HRP (Mid-Year Review, OCHA, June 2015).
2. This HARISS multi-year programme is a significant longer term commitment to - and investment in - the people of South Sudan in a context of protracted conflict and displacement, and in a country where the parties to the conflict have proven unwilling and unable to make necessary compromises to put an end to the suffering of their people.
What have we learned about delivering humanitarian assistance in South Sudan?
1. Acting early saves lives and money. The ‘no regrets’ policy adopted in 2014 helped avert the risk of famine and reduce the number of people in the IPC emergency phase in 2015.[35] We also encouraged partners to preposition supplies which meant we were able to reach vulnerable populations at a lower cost and in a timely manner. We also focused on pooling logistics support, which drove down costs and enabled agencies such as WFP to transport people and supplies throughout the year.
  [35] IPC data confirms this. See Integrated Food Security Phase Classification Key messages, IPC, The Republic of South Sudan, December 2014 and May 2015.
2. New approaches to delivering aid in hard-to-reach locations were critical in 2014: rapid response and mobile teams helped the UN-led response reach 1.5 million people that year. Nevertheless current rapid response modalities need to be further improved. We are working with other donors and operational partners to reduce the slow overly bureaucratic co-ordination and decision making and to improve prioritisation of life saving assistance. The role of a number of NGOs has been pivotal in reaching the most vulnerable, responding quickly and tailoring solutions to local contexts. Increased direct support could enable them to replicate and scale up their projects and to better influence the broader humanitarian system.
3. We need to get better at learning from doing and demonstrating impact and VfM, given the exceptionally high costs of humanitarian operations in South Sudan. This programme will include a separate component on monitoring, evaluation, accountability and learning (MEAL). The design of this component builds on learning from other country programmes, in particular Somalia.
Objectives and Expected results
1. This business case is for £443m over five years of which £110 million has already been approved and will be disbursed by December 2015. We request the approval of the remaining £333m. A five year commitment will significantly increase predictability, help build resilience, and drive down costs. This programme is part of our wider NSC and DFID strategy which calls for an effective peace and increased Government accountability and responsibility towards its citizens. A five year commitment also enables us to programme more strategically, using these significant investments of humanitarian funds to lay the foundations for improved resilience and development.
2. The intended impact of this business case is to: save lives, avert suffering, maintain dignity and reinforce coping capacities of those affected by shocks and conflicts in South Sudan.
3. There are three intended outcomes of multi-year humanitarian assistance in South Sudan:
1. Reduced vulnerability of people in high-need conflict areas;
2. Increased capacity to withstand and adapt to disasters and shocks (natural and man-made); and
3. Improved quality and impact measurement of humanitarian action.

The programme will have three outputs:
Output 1: Life-saving assistance: the approach will be twofold. We will:
1. Ensure humanitarian assistance is provided in high-need areas in sectors such as food assistance, water, sanitation and hygiene, health, shelter and non-food items;
2. Engage with the humanitarian coordination system to make it more effective and accountable.
This output will include the provision of critical supplies for the humanitarian response in field of food, nutrition, health (immunization), non-food items and shelter. It will support performing agencies to deliver assistance across the Greater Upper Nile region. It will systematically include and use results from beneficiary feedback mechanisms.

Output 2: Resilience-building: We will provide goods and services, but will also focus on building knowledge and capacity of vulnerable populations to make more informed choices about how to adapt livelihoods to prepare, respond to and recover from conflicts, hazards and climatic shocks..
This component will target the most vulnerable populations who have historically resorted to perverse coping strategies to cope with conflict, displacement, disease outbreaks or climatic shocks. It should help them move towards increased self-sufficiency and increase the capacity of whole communities to withstand man-mad and natural hazards. Part of our assumption (to be tested) is that with longer term resilience-building initiatives, will reduce the number of people forced to adopt extreme coping measures and will therefore no longer require expensive emergency aid. We will focus on:
  - Food security and livelihoods: our objective here is to provide vulnerable communities with alternatives to food aid and reduce their dependency on food assistance over time. Cash-for-work interventions and strengthening markets – including cash grants to traders, cash transfers to vulnerable households will be considered. This programme component will draw heavily on lessons learnt from our resilience and livelihoods programme so far, detailed in Annex B. It will also include climate change adaptation schemes to enhance ecological systems when desirable and feasible, e.g. soil fertility, water and natural resource management – since climatic variability is aggravating existing vulnerabilities and the erosion of resilience.
  - Protection including, as top priority, violence against women and girls: the idea is to help vulnerable people develop better informed and safer protection strategies, and to reduce their risk of exposure to protection threats including sexual gender-based violence (SGBV). Activities may include support to community-based protection committees, increased access to life-saving response services for GBV survivors, strengthened referral pathways with key services such as health, community dialogues and prevention work with all segments of society. Given the close relation of protection and GBV risk with narrowing livelihood opportunities, the two components will be implemented in the same target areas.
Emergency preparedness and response: we will support and steer the establishment of a cost-efficient early action and rapid response mechanism in country to allow for quick assessment, early action and rapid response to emergencies such as population displacement and disease outbreaks. This component will contribute to saving lives yet is included under our resilience portfolio as it will focus on reinforcing the system’s capacity to prepare and act early.
Output 3: Monitoring, evaluation, accountability and learning (MEAL) will ensure learning and adaptive programming. Real-time evaluations and ongoing project reviews will help us adjust activities and manage risks in a systematic manner. Partners’ performance will also be assessed against three criteria: conflict-sensitivity; accountability to affected populations (AAP) and VfM.
The programme will achieve the following results[36]:
[36] Beneficiary numbers are indicative planning figures. They are likely to change during the contracting process and discussions with operational partners. These have estimated by taking the average ‘cost-per-beneficiary’ figures of similar interventions over 2014.
1. An estimated 2 million people over five years will be reached with multi-sectoral humanitarian assistance. They are unique beneficiaries who will be reached once with at least one form of humanitarian assistance (eg. food assistance) and often receive more (eg. health, water or nutrition).
2. An estimated one million people will have greater livelihood opportunities, protection strategies and will be supported to prepare and cope with shocks;
3. We will build a robust evidence base on what works (or doesn’t work) in humanitarian and resilience programming in South Sudan to adjust our programme in real-time and provide evidence to the humanitarian community to do better. Some of this evidence will be useful globally to inform policy and practice when working in fragile states.
1. This programme will be designed so that Ministers can engage at key strategic points. Twice a year, an information note will be submitted to Ministers taking stock of progress and proposing next steps. An annual update on performance will be provided via annual reviews. Although not a requirement according to the smart rules, an annual information note will be shared on the outcomes of strategic discussions with partners and on any proposed changes to the future year’s plans.
2. We anticipate that there will be significant humanitarian needs in South Sudan for at least five years. This business case seeks approval for up to £333million from 2016 – 2020, considering that £110 million have already been approved via submissions for the first financial year (2015/16)[37]. Although the annual funding allocation is high, it represents a decrease from 2014/2015 level where the UK committed £132 million to the South Sudan humanitarian programme. Different allocations are forecast against different scenarios as follows. In each scenario the respective share allocated to life-saving and resilience building will change.
  [37] See submission to UK ministers, quest number 4904302 (February 2015) and 5064879 (June 2015).
	Financial year and budget (£ million)					Total	Indicative programme component shares
Scenario	15/16	16/17	17/18	18/19	19/20		Life-saving	Resilience-building
Fragile peace agreement, continued fighting and insecurity (current situation)	110	100	75	67	56	408	60%	40%

Further breakdown of state authority and fragmentation, increased insecurity (worst case scenario )	110	101.5	87.5	78.5	66.5	443	70%	30%

Peace agreement with formation of transitional Government leading to stabilisation (best case scenario )	110	90	70	60	50	380	35%	65%
Incl. MEAL		3	3	3	3	12
Incl. IRF		6	6	6	6	24

Table 2. Programme budget per scenario
1. This multi-year approach will enable us to increase our focus on prevention. There is clear evidence that benefit to cost ratios of investing in resilience range between $2.3 and $13.2 of benefit for every $1 spent.[38] More prevention and earlier action also reduces the loss of lives since it helps helps reduce the number of people in emergency phase (IPC phase 4) and the risk of famine.[39] By investing in resilience we will also help halt or slow down further decline and increase the self-reliance of households and communities.
  [38] Value For Money of multi-year approaches to humanitarian funding, Cabot-Venton, April 2013, https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/204946/Cost_Effectiveness_of_Multi-year_Humanitarian_Funding_-_Final_Report.pdf , accessed June 2015
  [39] Food Security and Nutrition Key Messages, IPC, Republic of South Sudan, December 2014 and May 2015
2. Given how unpredictable the current situation is and the probability that humanitarian needs may rise outside of the current conflict areas due to worsening insecurity, intercommunal conflicts and climate shocks, we have built in an Internal Risk Facility (IRF). We will set aside £6 million each year, which we will only allocate in case of natural disaster (e.g. floods), disease outbreaks (e.g. cholera) or spikes in conflict or seasonal needs outside the Greater Upper Nile region. This will allow us and our partners to prepare, act early and respond quickly. It will only be used when existing resources (DFID and non-DFID) are insufficient.
3. This programme works alongside other programmes implemented by DFID South Sudan. It has identified potential areas of collaboration with essential services (health and education), resilience and governance programmes (see Annex C). For instance, we are limiting our engagement with the health sector as the Health Pooled Fund (HPF) programme has continued in conflict-affected states. We are complementing the Girls’ Education in South Sudan (GESS) programme by supporting some of its partners deal with the consequences of the destruction of schools in conflict areas.
Appraisal case
Feasible Options
Five potential options have been identified for the delivery of this programme. Our assumption in developing these options is that we will achieve value and efficiency gains by moving from a single to a multi-year financing model in South Sudan. This is based on strong international evidence which is covered in section B.[40] We would make efficiencies in programme management through multi-year funding, and also increase our chances of making progress on building resilience and moving away from the trap of dependency.
[40] Review of multiyear humanitarian business cases, lessons learned, CHASE, February 2015
We have five different options.
1. The first option (a) is to do nothing. This assumes that other donors cover the gaps left by a UK withdrawal. We judge this to be highly unlikely. This option would therefore leave a gap of an estimated 3 million people without assistance. This would have severe humanitarian consequences and would cause a reputational risk to DFID if we choose to do nothing. The UK would no longer be able to influence other donors or the government of South Sudan across broader HMG priorities. This option is not recommended and is therefore not appraised.
2. The second option (b) is the continuation of annual funding cycles. It would focus on emergency response only. Our funding would be reactive rather than proactive and would prevent us from working with partners to think more strategically and more long term about building resilience. It would also hamper our ability to drive down costs and to influence the humanitarian system. It is not a preferred option either but it is appraised in order to compare annual versus multi-year programming (see table 3 below).
3. There are three multi-year options. They would all target the same geographic areas and beneficiaries. They are differentiated by the respective share allocated to emergency response and resilience building.
1. Option (c) would be a multi-year humanitarian programme with an emphasis on life-saving assistance and a lesser focus on resilience-building. The majority of UK funds would be allocated to life-saving assistance (up to 65%) and some funds to resilience-building (35%);
2. Option (d) would be a multi-year humanitarian programme with an emphasis on resilience-building and a smaller component of life-saving assistance (up to 65%) and the rest to life-saving assistance (35%);
3. Option (e) would be a flexible multi-year humanitarian programme. It would also combine life-saving assistance and resilience-building but sets no fixed ratio of fund allocation for each component. The split between both types of interventions would be dictated by local contexts, agreed upon between DFID and its partner at project level and reviewed annually.
1. All of these options (c-e) would include dedicated resources for monitoring and evaluation and also include a pre-approved internal risk facility (IRF) of £24 million over 5 years (see earlier para 43 and annex A).
2. These options have been appraised against critical success criteria in table 3 below. Scoring goes from 1 (poor) to 5 (excellent). All success criteria are given the same weighting.

Table 3. Appraising options b to e

Preferred option
1. Option e is the preferred option. The resilience component aims to strengthen peoples’ ability to cope with shock (see para 38 above, and annex B). Therefore, option e proposes a more flexible programme structure that will enable both delivery of life-saving assistance and, where conditions allow, resilience programming, but also give DFID (and our partners) unprecedented flexibility to scale-up or down our activities in either area depending on the feasibility of delivery in the context(s) and impact. Partners would be allowed to submit proposals that would cover a wide spectrum of interventions from emergency response to resilience-building. Flexibility is explained in more details in the commercial case (paras 99-101).
2. Humanitarian partners work on annual planning cycles and therefore will need to adapt in order to transition to a multi-year approach. We will engage with partners at the start of the programme to support the shift from short term, reactive programming towards longer term, flexible programming. We have already been working with partners to prepare for this approach, to which they are very receptive, as they recognise it would reduce administration time and allow for more strategic programming.
### What delivery channels should we consider for our preferred option?
1. No single partner or delivery channel can deliver a programme on this scale. By working with various partners, based on comparative advantage, we plan to achieve the most efficient and effective delivery of individual components. We have extensive experience with a range of partners and mechanisms in South Sudan, including the Common Humanitarian Fund (CHF), the International Committee of the Red Cross (ICRC), individual United Nations Agencies and non-government organisations. We will continue to work with tried and tested humanitarian delivery partners that have proven to deliver results.
2. Under output 1 (life-saving assistance), the Common Humanitarian Fund, UN agencies and the ICRC will be our preferred partners given their comparative advantages detailed in the commercial case below. The multi-year approach will give us increased leverage and influence over these partners, which will enable more robust, accountable performance monitoring.
3. We will run a limited local competition for the selection of grants to agencies under output 2 (resilience building). For each of the three components of resilience-building that we have chosen to prioritise (livelihoods, protection, emergency preparedness), we will put out calls for proposals that seek to stimulate the market. We will also run an international open competitive tender for the monitoring, evaluation and learning components. The Commercial Case discusses the merits of each of these approaches, captured in figure 3, in more detail. No funding will go through the Government of South Sudan. However our partners will need to build good relationships with government entities at the sub-national level in order to be allowed to operate. In areas of ongoing conflict partners will need to demonstrate the ability to effectively negotiate with armed actors.
.

Figure 3. Preferred option, target beneficiaries, delivery channel and selection process
### Value For Money: (VfM) risks and mitigation measures for the preferred option
1. VFM is a key driver of this new approach. The preferred option will provide better VfM because it will help us drive costs down, negotiate strong agreements with partners, free time for strategic leadership to shape overall humanitarian response, think and work long-term, and adapt to an evolving and fluid context. We will move from a reactive administration heavy approach to a more preventive, agile and longer-term one.
2. We have looked at key risks on the economy of the programme. Currently, 70-90% of funds spent in the field of food assistance, shelter and non-food items, and nutrition go on purchasing commodities (food, non-food items, and nutrition supplies) and transportation. These costs are driven by poor transport infrastructure and insecurity. In comparison less commodity-heavy sectors such as protection spend highest on field staff (55% of project costs) e.g. case workers and community mobilisers. We have identified VfM measures including early preposition of commodities during the dry season, local purchasing and alternative transport providers. We also propose to invest in building more resilient livelihoods which will help explore alternatives to food aid or lessen the need for it over time.
3. We have looked into the impact of key risks on the efficiency and effectiveness of the programme. Early planning, enhanced preparedness, early action, improved coordination and a cross-HMG approach on issues such as humanitarian access and the implementation of the peace agreement are amongst the mitigation measures we have identified and are actively promoting. More details can be found in our VFM annex (Annex H).
4. We need to do more to build the evidence base on VFM in humanitarian programming, especially in such an environment as South Sudan where the cost of doing humanitarian work is very high. We are currently undertaking a detailed analysis of our partners’ VFM together with international partners including with the European Union Humanitarian Office (ECHO) and the Office of Foreign Disaster Assistance (OFDA). We have identified partner-specific VFM measures which we will refine in each of our partner agreements through the introduction of tailored VfM metrics. VfM will also be an area of focus of our MEAL component: VfM measures will be defined at the onset of the programme which the MEAL will track and measure jointly with partners in order to identify best practice and make VfM gains during the programme
5. Based on key costs identified in para 56, amongst the measures that we will ask all our partners and the MEAL provider to track and monitor are the following:
1. Transportation
2. Purchase of food
3. Purchase of shelter and/or non-food items
4. Nutrition delivery including purchase of supplies and support to nutrition centres
1. A study is ongoing under the leadership of the National Audit Office (NAO) which is looking into crisis preparedness and response for DFID as a whole, including VFM of humanitarian programmes. We have fed into this study and will review its findings to see what we can implement in this programme. There will also be evidence coming out of our resilience programmes (BRACE 2) to add to the evidence base.
2. In addition the evaluation process will examine and answer questions and our assumptions relating to the benefits of the overall multi-year programming. It will seek to provide an evidence base for the following assumptions:
- Loss of lives is prevented/reduced by acting early.
- Adaptive programming enables better choices leading to greater impact/VfM.
- An investment in nutrition programmes saves lives but also leads to better quality of life for children. This includes increased learning, better life choices and ultimately increased economic productivity[41].
  [41] Since the Health Pooled Fund will expand in nutrition starting in 2016 yet not cover 2 states out of 3 in the Greater Upper Nile region and not include nutrition supplies, we have kept a nutrition component in our humanitarian programme.
- Partners are able to improve the quality of response.
- Transaction and operational costs can be reduced. The multi-year approach should help reduce transaction and administrative costs for DFID and partners as well as creating opportunities for savings within operational costs.

Theory of Change for the preferred option:

Cross-HMG approach on peace, governance, essential services and vulnerable populations

Engage with the humanitarian community in South Sudan

Support humanitarian coordination

Support the creation of enabling environment

Streamline and improve the RRM in the country

Engage with M&E advisers/ systems of partners and the humanitarian

Foster resilience approach in the humanitarian response (including building climate resilient livelihoods)

Engage with national and local DM/EWS bodies/actors

1. Nb of ppl reached in high-need areas with multisectoral humanitarian assistance
2. Reliable, accountable and effective coordination of the humanitarian response

Technical/strategic advice from DFID office team in South Sudan, and London

Programme Support from DFID South Sudan

Delivery of assistance, support to provision of food, nutrition, shelter and non-food items through common pipelines, support to common logistical services
Dedicated resources for M&E and research, and accountability to affected populations

Reduced vulnerability of people in need

Save lives, avert suffering, maintain dignity and reinforce coping capacities of those affected by conflict, disasters and shocks and conflicts in South Sudan.

1. Nb of ppl with increased access to food security and livelihood opportunities
2. Nb of people with increased climate resilience as a result of ICF support
3. Nb of ppl with strengthened protection strategies
4. Effective and efficient Emergency Preparedness and Response Mechanism
5. National and local partners have an increased capacity to manage programmes in a transparent, accountable and efficient way

2. Improved capacity of the most vulnerable populations to withstand, adapt to and recover from conflict, disasters and shocks

1. DFID and partners have a programme-specific M&E that monitors humanitarian action in real time, evaluates results and impact on a yearly basis and helps adjust activities accordingly
2. Lessons learned are shared more broadly with the humanitarian community

3. Improved quality and impact measurement of humanitarian action

IMPACT
OUTCOMES
OUTPUTS

PROCESSES
INPUTS

 Figure 4. Theory of Change for the preferred option
The assumptions underpinning this Theory of Change are that:
- Multi-year programming enables stronger partnerships, programme adaptation based on learning and evidence, and allows for adjustments based on evolving national and local contexts.
- Regional countries keep their borders open for influx of refugees and for cross-border operations to allow those in need to access services.
- The UN-led Humanitarian Strategic Response Plan (SRP) for South Sudan continues to prioritise humanitarian assistance.
- The funding for the SRP is sufficient to allow at least the minimal humanitarian activities to be implemented (65-70% funded by end of the year)
- The SRP promotes cooperation and harmonisation of the humanitarian community and donors.
- Peace remains fragile with persistent insecurity across the country, fighting occurs in the GuN region and in other states (on a more localized scale)
- DFID-funded humanitarian interventions are implemented in a conflict-sensitive manner.
Strength of evidence for the feasible options
### Multiyear humanitarian business cases
The evidence for multi-year humanitarian business cases is medium. It includes:
- The February 2015 ICAI report Assessing the impact of the scale-up of DFID support to fragile states which concluded that achieving sustainable impact and local ownership in fragile states takes time: “transformative impact … take many years to achieve … and there are real challenges with sustainability of impact, rolling out pilot approaches and embedding them in locally-owned systems” (ICAI report, February 2015).
- A 2015 CHASE review of multi-year humanitarian programmes concluded that DFID reduces process and transaction costs by supporting multi-year programmes. This leaves staff to more time for meaningful engagement to monitor and adapt programmes as well as to advocate for changes and improvements with partners.
- The CHASE review also found that multi-year arrangements strengthen the humanitarian system in-country by providing predictable financing and a greater focus on delivery as time is freed up from the annual cycle of programme design and fundraising. This is likely to result in better preparedness and early action.
### Cross cutting considerations
### Conflict
The programme will adopt a conflict sensitive approach and work to ensure that – at a minimum our support puts the ‘do no harm’ principle into practice. This means it will work to understand: i) the context (history, causes, actors and dynamics of conflict) ii) the interactions between this programme and the population and iii) how the programme can address causes of conflict and avoid negative impacts. It will develop tools with partners to ensure a consistent conflict sensitive approach.
We have identified the following risks which may exacerbate conflict:
1. Armed actors loot humanitarian supplies, giving them an advantage over the other side and prolonging the war. Mitigation: robust security analysis and risk management frameworks; avoiding carrying out distributions in areas with armed actor presence; use of armed escorts and reduction of storage points in high-risk areas;
2. Actors direct humanitarian assistance to specific communities, exacerbating tensions between groups. Mitigation: objective humanitarian needs assessments and local level conflict analysis; partners develop targeting criteria to promote transparency, participation and inclusiveness; cross-HMG approach to promote humanitarian access and the safe delivery of humanitarian aid to affected populations;
3. Foreign exchange for humanitarian assistance is pumped into the local economy and fuels the war. According to informal analysis made by a senior economist, it is estimated that an annual $200 million of humanitarian aid money is exchanged through the central bank system and gained as revenue, given the difference between formal and informal foreign exchange rates[42]. Managed: we believe the possible financial gains that could be made and used towards fuelling the war to be low in proportion to the total humanitarian funding for the country ($1.4 billion in 2014) and not significant in shaping the conflict dynamics so this will be tolerated against the risk of not providing life-saving humanitarian assistance in South Sudan. The risk is also mitigated by the high proportion of procurement that is made internationally, and the fact that partners increasingly switch to dollar-based payments in country when desirable and feasible (including for staff salaries).
  [42] This was in August 2015. At the time of writing the formal exchange rate was at 3.16SSP per 1USD and over 14.15SSP per 1USD on the black market Statistical Bulletin August 2015 by Bank of South Sudan (BSS)
Overall the risk of humanitarian aid diversion by warring parties is reduced compared with during the Sudan civil war. During this period the warring parties made significant gains through the then aid system, Operation Lifeline Sudan (OLS),[43] primarily via aid taxation, diversion or redistribution. While expectations of such gains remain, the humanitarian community have stronger frameworks in place to mitigate this; plus the political appetite for it has waned[44].
[43] OLS was a major and long-lasting humanitarian operation implemented during Sudan’s long civil war. It started in 1989 and ended after the signing of the CPA in 2005. It was a tripartite agreement between the UN, the Government of Sudan and the SPLM/A that facilitated ‘negotiated access’ to conflict-affected populations. It was led by the UN and included 40 operational agencies.
[44] Questions and challenges raised by a large-scale humanitarian operation in South Sudan, Feinstein International Centre, May 2015.

### Protection, Gender and Violence Against Women and Girls (VAWG)
1. This humanitarian programme complies with the 2014 International Development (Gender Equality) Act and considers gender in the analysis and design. DFID will promote the use of international standards, including the Interagency Standing Committee (IASC) Gender Marker and the IASC Guidelines on GBV in Emergency Contexts. DFID will also request partners to report using gender and age-disaggregated data as well as demonstrate how they have engaged men, women, boys, and girls throughout the project cycle. Beneficiary feedback and participation will be sought throughout, targeting those that have not traditionally had a voice or role in community consultations, including women and girls from the displaced population as well as within host communities.
2. Multi-year programming in the field of protection and violence against women and girls in South Sudan will be new to DFID and partners. It will allow for longer term interventions, which in turn should result in stronger resilience of women and girls as well as other vulnerable groups, as gains made towards improving help-seeking behaviour and empowerment of marginalised groups can be built year on year. It should reduce their exposure to violence or if they do experience it, enable them to have greater access to referral pathways and services. Multiyear funding for partners with either specialised protection interventions or mainstreaming protection will strengthen partner engagement with beneficiaries. Trust in service providers fosters the timely reporting of incidents of violence against women and girls that is essential for the full range of medical services to be effective (including post-exposure prophylaxis and collection of evidence if criminal justice is pursued).

### Institutional environment and accountability
1. South Sudan’s national architecture for coordination and oversight of humanitarian assistance is extremely weak. The proposed option recognises the Government’s preference for ownership and oversight of humanitarian aid and our desire, in the long-term, to build a constructive relationship with the Government in humanitarian coordination, provided it effectively commits to its people and to enabling, rather than hampering, aid delivery. All indications and evidence to date point to a concerning downwards trend: South Sudan is one of the most dangerous places on earth to be an aid worker, access to affected populations is reducing and NGO space is narrowing[45].
  [45] Introduction of NGO Bill which narrows operating space for NGOs. The GRSS argues that this Bill will allow it to monitor NGO activities more effectively (given the huge proliferation) and allow it to help nurture local/grass-root NGO’s/Civil Society Organisations (CSO’s).
2. Humanitarian assistance has also been affected by theft, fraud and corruption. Option e will tackle fraud by ensuring due diligence of implementing partners, especially through continuous monitoring and oversight of lower levels of the delivery chain. Through stronger partner engagement and documentation of practice, MEAL findings should help us identify as well as manage and mitigate risks including “corruption surcharge” prevalent in South Sudan, (i.e. transit fees, etc.) and of elite capture especially in community resilience programmes.
### Climate Change and Environment
1. Programming under HARISS will incorporate three key approaches which address the context within which the programme will work: (i) resilience and climate adaptation, (ii) conflict sensitivity, and (iii) gender equality. This will ensure that its International Climate Fund (ICF) funded component is consistent with the ICF methodology and can draw on the experience of the main DFID financed climate resilience programmes in South Sudan such Building Resilience through Asset Creation and Enhancement (BRACE,1 and 2).
2. Climate adaptation will be a working theme under the Output 2 - Building Resilience - of HARISS and will only be applied where realistic gains can be achieved. The approach will be consistent with BRACE 2. We will consider funding climate adaptation interventions such as flood protection measures and measures against environmental degradation. We will pay particular attention to areas where hazards are multiple. We will consider funding interventions that help local communities learn more about climate change, its impact and how to adapt including using techniques used elsewhere in the country. In the resilience programme we implement already, we have seen that limited local knowledge, inadequate practices (eg. in farming) and weak capacity of local governments and communities were key constraints to the programme. We will therefore consider supporting capacity-building interventions (eg. in the fields of farming and wild foods’ usages for example).
3. Whether displaced by conflict or climactic changes - affected populations will have a concentrated impact on their environment. Biomass is used for fuel and shelter and opportunities for sustainable use may not be available. Waste generated, and if not suitably managed may contribute to groundwater pollution, poses other hazards and host pests and diseases. Options for sustainable resource use for building, agriculture and water-sanitation services will be explored at local levels, cognisant of the different climate and environment context in each location. The intention will be to reduce further environmental damage while enhancing ecological capital.
4. Other environmental impacts include emissions from fuel consumption by generators and transportation (road vehicles, river and air transport for relief supplies). An effort will be made to better understand alternative and explore (cleaner) approaches during programme implementation where feasible. These may lead to cost saving through the more efficient deployment of transport and higher efficiencies in use of diesel and aviation fuel and emission reduction benefits. Low-cost renewable energy options will be explored to reduce carbon emissions, environmental degradation and cost for end users. Linkage with the DFID-funded Moving Energy Initiative will be sought to build on lessons learned, best practice and good VfM around energy options for low-income communities in Africa. Energy in the context of South Sudan includes cooking, lighting, power and mechanical energy services (e.g. pumping).
5. Emergency response interventions may include medical intervention. Where this is the case best practice guidelines should be enforced for the management of medical and clinical waste disposal.
Commercial Case
Clearly state the procurement/commercial requirements for intervention
All values are indicative and will depend on the scale of need and on partners’ proposals. The programme will work through a range of partners using both indirect and direct procurement, as follows:
Intervention	Indicative Value (£m)		% of Total			Method
INDIRECT PROCUREMENT
CHF/ ICRC/ Stand-by partnership programme for life-saving		110.5		25%	A Contribution Arrangement with CHF and an Memorandum of Understanding (MoU) with ICRC
Life-saving with UN agencies		243.5		55%	MoU arrangements with UN agencies such as FAO, UNICEF, WFP, International Organisation for Migration (IOM).
Internal Risk Facility (IRF)		24		5%	Depending on the selected delivery channel this could be one or a mix of MoU or AG arrangements.
Livelihoods, Protection, Emergency Preparedness and Response with NGOs		53		12%	Accountable Grant arrangements with I/NGOs (open to consortia approaches)
Total Value of Indirect Procurement (£m)					431
DIRECT PROCUREMENT (competitive process)
Monitoring, Evaluation, Accountability and Learning (MEAL)		12		3%	Contract(s) through Official Journal of European Union (OJEU) procurement process.
Total Value of Direct Procurement (£m)					12

Table 4. Procurement types, indirect spend
How does the intervention design use competition to drive commercial advantage for DFID?
Indirect Procurement
Humanitarian aid is delivered by multilateral partners and NGOs that have distinct mandates and clear comparative advantages. The UK funds UN and ICRC appeals, and although such mechanisms do not make it possible to introduce a high degree of competition, our investment allows us to influence strategic direction. The partners/instruments selected through indirect procurement are as follows:
- The Common Humanitarian Fund (CHF) in South Sudan is a multi-donor trust fund managed by UNDP and the Office for the Coordination of Humanitarian Affairs (OCHA). The CHF provides grants to UN Agencies and NGOs to fund activities in the Humanitarian Response Plan (HRP). Our 2014 Annual Review of the CHF found that; it is an efficient vehicle for the delivery of humanitarian assistance; it is a flexible and adaptive fund, delivering greater results for less intensive effort than other potential delivery models. It scored an A in our last Annual Review. Risk management and control over delivery improved in 2015 with the introduction of a risk management framework, risk management toolkit and various pre, during and post project completion checks and controls. They will deliver on component 1.
- The International Committee of the Red Cross is an important humanitarian partner in South Sudan. Since the outset of the crisis, the ICRC has demonstrated that it has the expertise and capacity to deliver life-saving assistance to hard-to-reach populations. Their speed, agility and reach was proven when the fighting erupted in Unity in May 2015. ICRC were the first partner to reassess needs and provide survival kits to those impacted by the fighting – weeks before any other partners. They also engage and train warring parties on IHL and manage to successfully operate in areas where NGOs have struggled to scale-up delivery. They are the largest non-UN provider of food assistance. They will deliver on component 1.
- We will also work with specific UN mandated organisations such as Food and Agriculture Organization (FAO)/United Nations Children Fund (UNICEF)/World Food Programme (WFP), International Organization for Migration (IOM): These agencies have strong experience providing humanitarian assistance in South Sudan. They will be our partners in the delivery of component 1 and, potentially, component 2. UN agencies are leaders in a number of key sectors and have a track record in fast delivery including in hard-to-reach areas. They include: WFP in food assistance; FAO in agriculture and livestock emergency support; UNICEF in nutrition, health, child protection and education; and IOM in non-food items and camp management. For component 2, we expect to provide multi-year funding for resilience programmes. UN agency proposals will either be in consortium with NGOs or will need to demonstrate comparative advantage over NGO proposals, with whom they will be in competition for DFID funds. Performance, reach, flexibility and VFM considerations will inform our decisions.
1. There is good evidence that partners identified for indirect procurement have the technical and commercial capacity to deliver quality aid representing value for money: successive Multilateral Aid Reviews (MAR) of multilateral partners and recent due diligence assessments completed for (e.g. WFP, UNDP, FAO etc) on the multilateral agencies outlined in this business case provides a comprehensive overview and assurance of partner performance and capability in delivery that will be used in the decision making process.
2. We will run a limited local competition for the resilience element of the programme (livelihoods, protection and emergency response and preparedness). This approach will ensure that we select the most appropriate partners, which represent best value for money for DFID. It will be open to all organisations with existing programming in South Sudan. In order to deliver these ambitious results it is important that the organisations we work with are familiar with the operating context and constraints in South Sudan. A manageable number of international organisations will be selected where we are confident that they can achieve specific results that are not prioritised by the CHF and that they have strong links with local communities and are able to reach the most vulnerable people. Support through Accountable Grants is a tried and tested mechanism for securing results. Potential partners include existing international non-governmental organisations (INGOs) which currently implement livelihoods and GBV programmes, such as Mercy Corps, International Medical Corps, and International Rescue Committee.
3. If a joint donor initiative is possible then we will prefer it as this is more efficient and will guarantee effective coordination. We have had several meetings with the European Union Humanitarian Office (ECHO) and the Office of Foreign Disaster Assistance (OFDA) for a common approach to Protection and Emergency Preparedness and Response. Discussions are at an early stage and as we progress we will seek an equal split of our financial contributions.
4. It is anticipated that both calls for proposals will start once this business case is approved. The call for proposals will better define how partners will adopt new or different approaches in tackling problems over the medium term rather than in an annual manner. Performance, reach, a long-term vision, previous track record in the required fields of expertise, flexibility and VfM will help us choose which organisations to partner with. Local understanding and previous work in the target areas will also be critical elements for contracts’ award.
5. For the resilience component, the call for proposals will provide strategic guidance on the main sectoral issues to be addressed by potential partners and outline all DFID’s policy requirements. We will be open to collaborative arrangements that help achieve the greatest coverage and ensure appropriate coordination amongst actors.
Direct Procurement
1. Although indirect procurement offers the best route to market in terms of delivery for much of the response, we are keen to use a competitive approach for the procurement of the MEAL element. This process will help DFID achieve value for money where we know there are multiple potential partners, and test as well as stimulate the market.
2. We will work based on the OJEU procedures as there is added value in putting this out to the market for tender. We would like to open the competition to all existing service providers (Altai consulting, Forsier, Integrity, Silk, Charlie Goldsmith Associates, Impact, REACH) since prior experience and existing presence in South Sudan is one of our key requirements.
How do we expect the market place will respond to this opportunity?
1. For both our indirect and our direct bilateral spend, it is anticipated that take up will be high. South Sudan has attracted a large number of partner NGOs and many have been active for a number of years. Most of our NGO and UN partners have been requesting multi-year funding for some time.
2. There are several private companies which work in the country on monitoring and evaluation, some of which are DFID partners for other programmes (including Altai, REACH and Charlie Goldsmith Associates). The market is competitive and it is expected that there will be extensive interest amongst them. The capacity of South Sudanese companies is not known at this stage and it is our preference to work with them, based on assessments of capacity and capability. It is expected that the winning bidder will, in any case, work in collaboration with local South Sudanese consultants / companies based on their experience, capacity and capability.
3. Existing presence in the country, track record in working in the Greater Upper Nile region and expert skills in the technical areas of work we will open competition for will be amongst our key requirements. Consultancy firms based in South Sudan and that have worked with DFID in the past can meet DFID’s requirements thus improve our choice of suppliers. This will increase competition and drive down costs in the longer term. We have coordinated this with the procurement unit and chosen procurement routes accordingly.
What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?
This business case sets out the arguments for a number of grants and/or contracts to different organisations. The cost elements will be determined at project level. However, South Sudan is one of the most fragile, high risk operating environments in the world making it expensive. There are a number of common cost drivers that affect most programmes. These include:
- Security: South Sudan is a high risk and low comfort environment. Expatriate staff are compensated for risks by receiving salaries which are higher than in other countries in the region. Salaries and benefits also take into consideration the fact that Juba has recently been assessed as the world’s most expensive location for expatriates.[46] In addition, security staff must be employed in greater numbers than in stable countries as offices, warehouses and staff accommodation all have to be guarded 24/7. Cost mitigation measures: pre-positioning in secure sites to avoid looting, living in shared accommodation compounds, delivering through local partners on the ground, investing in capacity-building of national staff and actors.
  [46] ECA International's cost of living surveys, June 2015, http://www.eca-international.com/news/press_releases/8191/Juba_tops_the_list_of_most_expensive_cities_for_expatriates
- Transport: Decades of conflict means South Sudan’s infrastructure, particularly the road network, is extremely poor. Few tarmac roads exist outside the capital and 60% of roads become impassable for months during rainy season.. Cost mitigation measures: making the best use of road and river to transport; delivering and pre-positioning supplies during the dry season by truck or barges. However, given poor road conditions and insecurity large amounts of humanitarian supplies are airlifted, significantly increasing transportation costs[47].
  [47] On average, it costs $2500 to transport 1MT of food by air versus $350 by road in South Sudan (WFP).
- Multiple offices: Due to the poor transportation infrastructure there are also difficulties moving personnel around the country. Many organisations therefore have field offices in several locations. Cost mitigation measures: sharing field office and accommodation spaces in humanitarian hubs; establishing field offices in locations from where large areas can be covered; expanding outreach through mobile teams and local partners.
- Capacity of local staff: Decades of conflict means human capital within South Sudan is very low. Few adults finished school and only 24% of people can read. Many educated South Sudanese left during the conflict. There is therefore a very small pool of qualified local labour. As a result, the price of local labour is driven up and a greater proportion of expatriates are required. Cost mitigation measures: investing in staff and partners’ training, mentoring and retention.
- Inflation. Annual inflation stands at 91%. Severe foreign exchange shortages due to the plummeting oil price and reduction in oil production since the conflict has led to a rapid depreciation of the South Sudanese Pound (SSP). Goods paid for in SSP are therefore increasing in price. Mitigation measure: much procurement is done internationally by humanitarian agencies; several partners have also switched to dollar-based payments in-country. Inflation however remains an extremely critical cost driver and will be carefully monitored.
What is the intended Procurement Process to support contract award?
The indicative timeframe for contract award is as follows:
	Activity	Date
1	Business Case Approval	November 2015
2	Procurement plan agreed with PRG	November- December 2015
3	ToRs revised and quality assured	November- December 2015
4	Invitation to tender issued	January 2016
5	Bids submitted and evaluated	February – April2016
6	Post tender clarification	May 2016
7	Contract awarded and implementation	May- June 2016

Table 5. Procurement timeline
The first year of this programme (2015/16) will focus on emergency response and will utilise existing MoUs and agreements we have with the CHF, the ICRC and UN agencies. This will allow time for us to run rigorous competitive processes run for objectives 2 and 3.
How will contract & supplier performance be managed through the life of the intervention?
1. All partnerships envisaged under this business case will be managed by the DFID South Sudan Humanitarian and Livelihoods team (HLT), with support from the DFID South Sudan commercial adviser, the regional fragile states adviser and senior regional humanitarian adviser. This team will form a peer group and develop a robust monitoring framework for the MEAL component. The winning bidder will be held to account through the submission of an inception report, quarterly and annual progress reports which will be considered against clearly defined milestones set out in a log-frame and through quarterly and annual programme and progress meetings with the DFID team (programme and advisory). An annual review of the overall programme will be carried out by an independent team.
2. A crucial tool for monitoring quality will be beneficiary feedback, coming both from partners’ own monitoring systems and from the MEAL component. This way DFID will understand how communities are being affected by the programme and will work with its partners on adjusting projects accordingly when desirable and feasible.
Value for money through procurement
1. The proposed humanitarian programme does not involve DFID procuring any goods directly. We will carry out a procurement assessment on all our implementing partners as part of a wider due diligence assessment to ensure we partner with agencies that have robust procurement practices and well integrated value for money procedures (see para 106 for information on due diligence conducted to date).
2. All funding is conditional upon performance, and upon progress against pre-agreed output and outcome indicators. Should our quarterly and annual reviews of our partners find that performance is inadequate or progress too slow, we will reserve the right to revise or withdraw funding. DFID will examine budget lines across partners to ensure consistency and request justification for any variance.
3. Monitoring of budgets and forecasts provided by the partners will be done on a ongoing basis. Consultancy firms will be bound by output based contracts which will help to ensure that they deliver value for money and the intended results for the evaluation assignment. Payments will be pegged to delivery of agreed results.
Financial Case
What are the costs, how are they profiled and how will you ensure accurate forecasting?
The proposed programme has a total value of up to £443 million over five years from 2015/16 to 2019/20. Indicative expenditures will be profiled as follows. They are not broken down by output (e.g. life-saving; resilience-building) as we will offer each of our partners the possibility to bid against both outputs.
	2015/16	2016/17	2017/18	2018/19	2019/20	Total
ICRC	18	12	9	5	4	48
CHF	21	15	10	8	8	62
International organizations (UN)	70.5	56	46	38	33	243.5
Emergency Preparedness and response consortium		3	4	4	3	14
Protection consortium		3	4	5	3	15
Livelihoods consortium		3	5	8	6	22
National NGOs capacity-building		0.5	0.5	0.5	0.5	2
MEAL - Third party monitor		3	3	3	3	12
Standby partnership programme	0.5					0.5
Sub-total	110	95.5	81.5	71.5	60.5	419
IRF		6	6	6	6	24
Grand total	110	101.5	87.5	77.5	66.5	443

Table 6. Indicative annual spends per delivery channel
1. Cost estimates for CHF and ICRC (output 1) assume a gradual decrease of humanitarian need over time, on the assumption that populations may graduate towards longer-term (resilience / developmental) assistance. Estimates for international organisations (e.g. UN agencies) also anticipate progressive savings and better VfM over time.[48] Costs for the MEAL component are based on experience in Somalia and a doubling of the budget for an existing third party monitoring programme in South Sudan since our MEAL partner will work in the GuN region, for which transport costs are higher and the area to cover is greater.[49] The costs of the IRF are based on past experience of contingency funds in the country.
  [48] Estimates for livelihoods, protection and nutrition consortia have been generated by tripling the values of existing partnerships in relevant sectors, given that the programme coverage (geographical reach and activities’ scope) should expand threefold in each of these sectors.
  [49] The DFID South Sudan BRACE programme Third Party Monitoring is implemented in non-conflict affected states. A higher budget is estimated to allow for implementation in more unstable contexts that imply more frequent and a lot of air-based travels in and out project areas.
2. Cost estimates for the ICRC, the CHF and international organisations focus on life-saving assistance. They will be set at the start of the programme. Other cost estimates (protection, livelihoods, emergency preparedness and response, capacity-building and MEAL) will be adjusted once we have gone through the competitive processes outlined in the commercial case.
3. The flexibility we are offering to partners is about:
  1. Adapting their approach to the needs and switching to more resilience or more emergency as they deem fit, in consultation with DFID. WFP could, for instance, decide to allocate the funds at the onset of the programme for its emergency programme (the Emergency Programme, EMOP) to its resilience instrument (the Protracted Resilience and Recovery, PRRO) if the context is fit for it and it considers it can switch from food aid to cash-based interventions.
  2. Deciding each year the amount they wish to spend the following year, based on the evolving context and other resources coming in from the government or other international partners. UNICEF could, for instance, decide to allocate more funds to cholera preparedness if, based on its and WHO surveillance, it expects a bigger than usual outbreak.
1. DFID will have the possibility to reduce annual amounts to be allocated based on partners’ performance. Findings from partners’ monitoring, beneficiary feedback mechanisms, field visits, our annual reviews and the MEAL will be used to inform our decisions annually.
2. We will have some flexibility on our overall budget (hence the ‘up to’ £443m) thanks to two programme components. The CHF (£62m) costs and contracting will be annual, since the fund is dedicated to life-saving and can only contract its partners annually. The estimates we have drafted may be revised downwards if the situation improves in the country. The IRF (£24m in total, £6m per year) might not be spent entirely every year or not at all on a given year, if existing actors can respond to emergencies across the country with existing DFID and non-DFID resources.
3. Payments will be made bi-annually (UN) and quarterly (NGO’s), being mindful of seasonal cycles. Indicative timings for fund disbursement are:
- October/November to allow for dry season planning and prepositioning;
- February/March to allow for early action ahead of the ‘lean season’;
- July to allow for scaling-up assistance during the lean season.
We will review plans to avoid any slippage and spending risks and aim for less than 5% variance from year-on-year budgets/forecasts.
How will it be funded: capital/programme/admin?
Based on historical spend of previous humanitarian programmes in South Sudan, 92% of the funding will be programme (RDEL) and 8% will be capital (CDEL). The majority of our current spend on CDEL is on IDP camps and PoC sites’ rehabilitation and engineering work.
Total	RDEL	CDEL
443	407.56	35.44

Table 7. RDEL and CDEL budget shares, in million GBP
We seek to fund up to 10% of our programme budget from the ICF based on ICF funding for our food security and livelihoods programme component (under resilience) and on work we plan to undertake with UN agencies to increase the share of activities improve resilience to climate variability and environmental risks for up to 10% of the planned budget for international organisations (hence an estimated £24 million). Results will be measured against the ICF indicator 4. (Number of people with improved resilience as a result of ICF support).
What is the assessment of financial risk and fraud?
1. Delivering humanitarian aid in a fragile context such as South Sudan is high-risk. Recognising the pressing humanitarian needs, UK Ministers have previously agreed that some level of risk is acceptable. DFID South Sudan will take all steps necessary to mitigate risk and ensure the programme adheres to our zero tolerance policy on fraud and corruption and UK country fraud and bribery legislation (see risk assessment and mitigation measures in the Management Case below). DFID standard agreement templates include anti-fraud and corruption provisions. Furthermore, DFID SS has already conducted Due Diligence Assessments (DDAs) on all of our existing multilateral partners which assessed their governance and internal controls, their capacity to deliver, their financial management and the capacity of their downstream partners[50] Overall these assessments provided DFID with assurances that our implementing partners have sufficient internal controls to deliver UK aid, most recommendations which emerged were classified as medium or low risks. Findings common to more than one implementing partner included low quality risk management frameworks, an inadequate audit plan for downstream partners and a lack of Host Country Agreement for their operations, due to the length of the process. DFID South Sudan is following up on the recommendations resulting from the DDAs with implementing partners to ensure the risks identified are addressed. We will conduct DDAs on new implementing partners in line with smart rules. The MEAL component of the programme will include evaluations of specific interventions and third party monitoring. As the security situation permits, DFID South Sudan will also conduct regular monitoring visits.
  [50] IOM, OCHA, WFP, FAO, UNICEF, UNDP, UNHCR, UNOPS, ICRC.
2. Where fraud is detected we will work with partners to attempt recovery of UK assets / funds. The Counter Fraud and Whistleblowing Unit (CFWU) will be immediately notified of any incidents of fraud and DFID South Sudan will assist as requested in any necessary investigations.
3. To mitigate the possibility of money being diverted, a significant amount of goods (Food/Cereals/NFI’s) are purchased outside South Sudan.
4. DFID South Sudan has developed an intervention risk matrix and put in place a series of risk mitigation measures. They are presented in the management case and detailed in Annex E.
How will expenditure be monitored, reported, and accounted for?
1. Partners will be required to report on expenditure and results achieved on a quarterly basis. For multilateral agencies, central Framework Agreements and MoU templates will determine reporting arrangements. Where the centrally agreed schedule is considered insufficient, DFID South Sudan will negotiate for more regular reporting in country. All partners, discussions will be held quarterly to determine project progress and issues. The level of detail of information required from partners will be proportionate, realistic and obtainable.
2. In compliance with DFID Smart Rules the project will have an annual review and project completion review. For both Memorandums of Understanding (MoUs) and Accountable Grant Agreements, requirements will be set out at the start including performance criteria, targets to breached annually, reporting and policy.: requirements will be set out as described in the commercial case, section F, para 91.
3. Consultancy firms will be bound by output based contracts which will help to ensure that they deliver value for money and the intended results for the evaluation assignment. Payments will be pegged to delivery of agreed results.
How will expenditure be monitored, reported, and accounted for?
Accountability and monitoring requirements will be agreed by each recipient of UK funding through their MoU or grant agreement. Requirements vary between implementing partners. However, all partners will be required to report to DFID on a quarterly basis. Given that multilateral partners are only required to report formally on a six-monthly basis, informal discussions will be held quarterly to determine progress and any issues. Contractors will be bound by the terms of their contract, which will specify that payment is contingent on completion of agreed deliverables. Annual Reviews and Programme Completion Reviews will be conducted.
Exit Strategy
1. This business case argues for continued UK investment in humanitarian assistance for South Sudan whilst significant needs exist and the Government is unable or unwilling to respond. Should opportunities arise to exit from humanitarian support to longer-term development assistance, these will be explored including through systematic work with our development programmes and coordination with the GRSS, including through the government partners’ forum which the UK currently chairs. However, it is our assessment that the situation is sufficiently serious to justify sustained humanitarian programming at the financial levels proposed for the duration of the programme.
2. It is hard to foresee a possible transition from humanitarian to development within the next five years as needs will remain high and critical elements conducive to development are unlikely to materialize in this period of time, including effective good governance, a sustained return to peace and community reconciliation. This programme will however enable us to move in the right direction. We will build communities’ resilience and contribute to lessening their reliance on humanitarian aid. Part of our livelihoods’ component’s ambition is, for instance, to reduce the number of months households cover with food aid, and instead increase the number of months they may cover through either production or purchase. Overall the investment we will make in resilience-building will allow us to lay the foundations for development programmes and opportunity-creation. We will also be able to work on exit strategies with our partners from the onset of the programme. Such strategies are extremely hard to envisage right now, and rarely get beyond local capacity-building, as our partners time horizon of 6 to 12 months of funding is simply not conducive to either think about or effectively work towards exit.
3. We are working very closely across the office (DFID, the FCO and the MoD) to advocate to the government that its takes increased responsibility for its people. This includes close coordination with our development programmes, both essential services and governance, to push for increased government budgeting for and spending on essential services and humanitarian assistance. We also work together with the FCO to ensure the signatories to the peace agreement uphold their responsibilities to secure safe and unhindered humanitarian access to populations in need of humanitarian assistance. The Embassy has regular joint meetings/briefings (DFID/ FCO/ MoD) to ensure that safe access is one of the priority messages that Her Majesty’s Ambassador, other officials and the UK special representative deliver in relevant meetings with the Government, and other parties. We also work with the UN to ensure so that they provide more systematic ‘evidence’ of access restrictions which can be used in our efforts. As a result, humanitarian issues were addressed in a collegial manner on several occasions including in August 2015 to obtain the lift of access denials on the Nile river in Upper Nile state, in September 2015 through a joint visit with the UN and other diplomats in Unity state and most recently at the October 2-15 Government Partners’ Forum.
Asset Management
1. Looting or confiscation of humanitarian assets or supplies and informal taxation of supply convoys is a significant risk to the programme. This is an ongoing problem, and both the government and opposition have been involved in looting, especially when areas change hands. UNMISS Force Protection, and the location of humanitarian hubs and prepositioned stocks within UNMISS bases provide some mitigation, although UNMISS bases have been stormed during the conflict. The use of mobile teams also provides some mitigation, although it is much more expensive.
2. Further mitigation measures include: reducing prepositioned sites and locating them outside of the main conflict areas and introduction of mobile based stock monitoring systems which enable better monitoring of supplies at each transfer point.
3. At the end of this programme, the senior responsible officer (SRO) along with the lead advisor will ensure maximization of the value from the disposal of any remaining equipment and assets.
# Management Case
What are the Management Arrangements for implementing the intervention?
Accountability/Governance Structure for the Overall Response
1. In-country oversight of the overall humanitarian response is managed by the Humanitarian Country Team (HCT). The HCT is chaired by the UN Humanitarian Coordinator and includes representatives from donors, NGOs and the UN. DFID is represented on the HCT.
2. The HCT provides oversight of the work of the Inter-Cluster Working Group (ICWG). The ICWG, in turn, brings together the Cluster Leads of the Cluster Groups, responsible for coordination of the response at a sector level. During the first six months of 2014, the ICWG and Clusters were slow to develop and implement shared, prioritized and actionable operational plans. Since that time, and with DFID support, their performance has improved considerably.
DFID structure and arrangements
1. This is a large and complex programme, requiring a significant investment of effort from DFID. Currently the team manages ten partnerships. The SRO is the Deputy Head of Office (Humanitarian and Livelihoods). The programme team consists of two A2 Humanitarian Advisers, an A2L Senior Programme Manager, one B2 Programme officers and 50% of a C1 project assistant. This programme will require the team to manage two more partners, hence the change is marginal. Also, the fact that multiyear agreements will be drawn with partners, as opposed to annual agreements with proposals required for every tranche, as is the case currently, should lessen the administrative workload. That said, the programme will be heavy at the start when competitive processes will be launched and partners selected, and periodically when the programme is reviewed. Surge support will be available at peak periods, if and when required.
2. The programme will be managed through a single logical framework (logframe) as the primary management tool. It will be an aggregated version of individual partner logframes (see diagram below). It will track progress against measurable indicators and provide the results against which the Annual Reviews and Project Completion Review will score the programme. It is anticipated that the logical framework will be updated after we have selected all of our partners and gotten all their project logframes (May-June 2016), and then regularly with input from partners’ beneficiary feedback mechanisms, project results and the MEAL component. It is attached in Annex G.

Figure 5. Components of the programme logical framework
1. Updates on the humanitarian situation in South Sudan are sent to the Regional Director on a regular basis. Information Notes will be submitted to Ministers every six months. Should changes in the situation, or the performance of the programme, require a strategic steer, we will seek advice from management or Ministers at the appropriate level of delegated authority.
2. The Internal Risk Facility will be managed at the country office level based on the following decision-making tree. An early action tracker (annex A) details the triggers and thresholds that will be used. The IRF will be accessible to existing partners in priority, and will be activated upon sign-off by the Head of Office. Recommendations for additional funding from the IRF will be made to the Head of DFID South Sudan, who will then seek approval for funding from the Regional Director.

Figure 6. Decision tree for the Internal Risk Facility
What are the risks and how will these be managed?
1. There are different risks to the South Sudan humanitarian programme which we have learned to mitigate and intend to continue to manage consistently in order to protect the significant investment which this programme represents to the UK government and tax payers. Our existing risk mitigation measures are adequate, according to the draft 2015 assurance review of DFID South Sudan by DFID’s Internal Audit Department (IAD). Country and department controls, as well as programme and project controls, as designed and as operated, were assessed as “adequate to mitigate the risks in practice”. DFID South Sudan is cognisant of risks and actively manages them. Auditors stated: “within the Humanitarian aspect of the portfolio we found in-depth and detailed risk assessments and analysis to inform the programme of its risk appetite”, and recommended the risk management strategy of the humanitarian team be rolled out to the remaining development portfolio. The risk matrix and associated risk mitigation measures are detailed in annex E. Part of risk mitigation includes not channeling any funds through the Government of South Sudan, instead relying on non-governmental organisations, private sector firms and multilateral agencies that have been subject to due diligence assessments.
2. The main risks and mitigation measures are as follows. Our risk matrix is attached (Annex E).
Risk	Mitigation based on experience and practice
Resumption of major hostilities	Advocacy on the political side, support to the peace process, regular dialogue with GRSS through the Troika, working collectively with the HCT, planning for potential consequences including increased humanitarian needs (IRF)
Economic crisis	Support to common pipelines for critical items (food, nutrition, health), international procurement, advocacy to GRSS to engage on economic reforms, dollar-based payments when feasible/desirable, contingency planning
Looting and commandeering of humanitarian assets	Engagement with warring parties on respect and protection of humanitarian staff, assets and operations, pre-positioning in secure sites, distribution of items and relocation of assets ahead of attacks when possible, systematic loss reporting
Poor relationship with parties to the conflict/ dealing with aid blockages	Use 1 HMG approach to support and promote humanitarian space, prevent and limit rent-seeking, document and advocate blockages together with OCHA access unit, maintain a clear and joined up cross-Whitehall position on the need for a political solution accompanied by principled aid.
Insufficient preparedness and scale-up ahead and during disease outbreaks / spikes in needs	Early warning, early action, prepositioning during dry season, no regrets approach, support the establishment of a rapid response mechanism to speed up response time, set funds aside for acting early/responding quick (IRF), contingency planning, proactive role with food, health and nutrition clusters
Reputational risk of the failure to prevent a famine.	A coherent ‘no regrets’ response supported by a credible communication strategy setting. Proactive role within the Food Security, Health and Nutrition Clusters and maintain a close and direct working relationship with those tasked to provide assistance – ICRC, WFP, UNICEF, MSF. Plan ahead and be ready to swiftly provide support to the right agency should food security deteriorate further.
Humanitarian aid dependency	Support to the peace process, promotion of / support to resilience-building projects when possible, effective humanitarian-development coordination and collaboration and continuation of development programmes where possible, pilot innovative cash-based support to help sustain markets also where possible, work on exit and graduation strategies from the onset
Losses, Fraud and corruption	• Reducing storage locations of the majority of prepositioned humanitarian supplies to six key hubs; • Locating stocks in safer areas and with better security provisions; • Requiring partners to use convoy and unmarked vehicles to transport supplies; • Encouraging partners to have tracking devices on trucks • Supporting security training for partners including on handling looting and hijacking; • Conducting due diligence assessments of multilateral delivery partners with special attention to how they manage risk; and • Following up with partners to ensure commodities are insured. / • Having and following up upon risk management frameworks, anti-fraud and corruption strategy and tools,
Weak coordination of response	Regular dialogue with ICRC and MSF who join meetings and support coordination in an active and transparent way, proactive role in Humanitarian Country team, weekly donor coordination meetings both strategic and operational, active engagement with key clusters, continuous push for clearer and improved inter-cluster and inter-agency mechanisms.
Insufficient funding of the overall response, impacting capacity to deliver the response	Scale up efforts to lobby other donors to increase their response - use key communications opportunities to raise awareness and increase engagement of other donors. Look for opportunities to increase VfM e.g. prepositioning supplies in the dry season, cost-savings, response prioritization, pooled resources when possible. Continue to monitor donor funding through the CHF and engage with donors to make the case for greater burden sharing of future costs.
Climate risks, bad / erratic weather	Improved mainstreaming of climate variability and risk adaptation strategies in partners’ agreements. Triggering the IRF for climatic shocks including droughts and floods. The use of air assets to reach inaccessible areas during the rainy season or when rains occur unexpectedly (rainfall is increasingly erratic in the country). Exploration of a co-ordinated donor strategy on infrastructure including maintenance of infrastructure required for humanitarian purposes.
Insufficient DFID staffing for effective design and oversight	Staffing numbers have been uplifted, staggered recruitment and short term gap filling put into place to ensure full staffing complement. Strong handovers are being implemented to assist in knowledge transfer.
Security constraints limit field visits	Clear forward planning with OSM. Careful adherence to security protocols. In spite of challenges, we have made one trip per month on average.

Table 8. Main risks to the humanitarian programme and mitigation measures
Lost, stolen or damaged commodities as a result of the conflict remain a risk. To date looting of commodities has amounted to less than 0.1% of the overall approved budget. As outlined in the above table, we are working closely with partners to identify strategies and learn lessons to minimize the risk of further losses.
What conditions apply (for financial aid only)?
n/a
How will progress and results be monitored, measured and evaluated?
1. A five year implementation timeframe provides the UK with a real opportunity to better assess the impact of our interventions. The £12m MEAL component will provide an impartial and external overview of programme performance and contribute to the emerging evidence base on multi-year humanitarian financing.
2. The MEAL will be responsible for designing a robust monitoring system capable of capturing results accurately. The MEAL will also develop systems to verify outputs have been delivered (including looking at systems such as: third party monitoring, remote sensing and beneficiary feedback loops etc.) Evaluation questions will be designed during the inception phase, but are expected to examine how multiyear UK aid has helped deliver lifesaving humanitarian assistance, built resilience and contributed to reducing the culture of dependency.
3. How does it fit with the evidence base: one of the key challenges in South Sudan is the quality, availability and reliability of data to support any assessment of results or performance. We will prioritise strengthening the quality of monitoring and evaluation (M&E) data collection, analysis and findings, and the use of this information for decision-making. We will focus on the opportunity to compare and contrast different delivery approaches (within a multiyear context and between emergency and resilience programing) and to build in from the start and monitor overtime the programme performance in conflict-sensitivity, accountability to affected populations and VfM.
4. Key users: Using findings from the MEAL component we will have an opportunity to develop more systematic and robust discussion on lessons learned and corrective actions with clusters and OCHA. This way we will put and encourage a stronger emphasis on reporting results, particularly at outcome level, and working with beneficiaries to improve accountability for response. Specific findings on conflict-sensitivity will be disseminated to wider audiences using the UK-led Joint Conflict research Centre.
5. Timing: a proxy baseline data set will be constituted at the start of the programme. Real-time evaluations (RTE) of each project will be undertaken and will feed into the DFID annual reviews. A mid-term review will take place at the end of year 3 (2017/18). Routine M&E data will feed in the RTEs and mid-point programme review. A programme completion review will be undertaken at the end of the programme. The findings of annual RTE will be discussed in a committee comprising DFID implementing partners, DFID and the third party monitor. Key evaluation questions will be further designed during the inception phase, but are expected to include:
DAC criterion	Possible questions
Relevance & appropriateness	What are the benefits of DFID’s multiyear approach? / Is DFID assistance being directed to the most needy areas & sectors? / How has DFID assistance been adapted in the light of changes in the context since the last evaluation or Annual Review? / Is the programme approach relevant given the humanitarian needs and context in South Sudan? / Has the programme adapted to feedbacks from affected populations? In what ways?
Connectedness	Is assistance being provided in ways which will reduce vulnerability and not exacerbate it?
Coherence	Is the humanitarian programme being supported by other HMG programmes (e.g. diplomatic, security etc), and what have been the results of these efforts? / How coherent are the programmatic elements of the portfolio?
Coverage	Is DFID assistance reaching the neediest areas (including people not in camps or areas of protection)? / Is DFID assistance reaching the most vulnerable people in these areas (especially women, children)
Efficiency	VfM issues, including: what are the trends in transport costs for relief supplies? Are there differences in unit costs between partners and what are the explanations for these differences? How successful are partners in pre-positioning their relief supplies? Are partners always looking for ways of improving their VfM? / Does multi-year funding increase value for money (VFM)?
Effectiveness	Questions will be sector-specific but are expected to cover the following issues: / Food Security & Livelihoods: ask questions about people’s coping capacity, including the extent to which they are selling assets, and are able to plant/ harvest crops. / Nutrition: what are the trends in Severe Acute Malnutrition in different locations where partners are working? How do GAM & SAM rates in settled communities and in IDP & refugee camps compare? / Resilience: Are vulnerable individuals and households more resilient to shocks and stresses as a result of the work of DFID’ funded interventions? How do investments in resilience contribute to/compromise delivery of humanitarian outcomes? / Gender and Violence Against Women and Girls: How have the specific needs of women and girls been taken into account by partners? / Multiyear: What gains have been made thanks to multiyear funding (cost-savings, efficiency, effectiveness, learning)? / Early Action and Rapid Response: Has the IRF proven to be an effective mechanism for rapid funding for unforeseen emergencies or acute spikes in needs?

Table 9. Evaluation questions
Budget: the MEAL component is estimated at 3% of the programme. DFID will explore with other humanitarian donors (EU, US, Sweden, Norway) whether a common monitoring service can be developed that would help drive down cost.
Value for money evaluations
A Value for Money matrix will be designed at the onset of the programme and VfM will be one of the core themes that will be evaluated every year. We hope this way to assess and document better major cost drivers, their evolutions and the triggers for them, and potential cost-savings and opportunities for improving VfM. The mid-point programme review will take stock of all results and achievements. VfM will be part of this review.
Helping strengthen the Humanitarian Response Plan monitoring
The monitoring and evaluation component will help strengthen and adjust existing cluster M&E systems. In particular, the third party contracted for our MEAL component will work together with the CHF Monitoring and Reporting officer at the start and throughout the programme life to ensure that Real Time Evaluations can feed in CHF monitoring visits, and the other way round.
ANNEXES
1. Internal Risk Facility and Early Action tracker
2. Humanitarian resilience approach
3. Humanitarian-development approach
4. Economic appraisal
5. Risk matrix and mitigation measures
6. Scenario
7. Programme log frame
8. VFM risks and mitigation measures
9. Quality Assurance Unit Report