Annual Review - Summary Sheet

Title: UNITAID
Programme Value: £790 million		Review Date: November 2015
Programme Code: 111074	Start Date: Feb 2007	End Date: Mar 2026

Summary of Programme Performance

Year	2008	2009	2010	2011	2012	2013	2014	2015
Programme Score	81.25	72.5	64.0	80.75	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium	Medium	Medium	Medium	Medium

Progress against 2015 reform objectives: A
UK funding for 2015: £44m

Summary of progress and lessons learnt since last review

2015 has been a year of change for UNITAID. Following the arrival of a new Executive Director in October 2014 and a Functional Review end-2014, UNITAID has embarked on an ambitious set of reforms. Several key initiatives have been launched to transform UNITAID’s operating model and create a more robust approach to capture the impact of its projects, including:
- A new operating model to deliver increased alignment with partners, greater strategic focus, more sustainable impact, and transparency in a process that is faster and more agile;
- A more robust approach to Value for Money;
- Strengthened risk management;
- A new organisational structure and revised operating procedures to strengthen the Secretariat.

The Secretariat is making good progress on reforms across the board and on recruiting staff. Going forward UNITAID needs to embed these reforms and continue to strengthen relationships with the Global Fund and other major health agencies to ensure that all its activities contribute to well-defined strategies for addressing specific and critical public health problems.

This review is largely setting the baseline and log frame following the UK’s 3-year commitment over 2015-2017 of up to £44m per year in March 2015. UNITAID has made good progress across all outputs over 2015.

Summary of recommendations for the next year

UNITAID
- Continue to implement the New Operating Model and Board-approved reforms to schedule – most pressingly working with WHO to ensure all outstanding job posts are advertised and filled as quickly as possible (Outputs 4 and 5)
- Collect systematic evidence and rigorously analyse the ways that UNITAID’s landscape reports are used (Recommendations 1.1)
- Ensure that monitoring and evaluation systems track why and when products are (or are not) successful in transitioning to national programmes as well as to programmatic support from the major global health players in order to learn from success and failure (recommendation 3.1)
- Provide a clear workplan on how the Secretariat aims to develop and reach agreement on a new 2017-2021 strategic framework with clear targets and milestones, with robust processes for data collection underlying these (Recommendation 6.1)

DFID
- Review the UNITAID branding report, the proposals for consultation around the strategy development, and plans for assessing the value and future role of the landscape reports in Q1 2016 to ensure that these will provide adequate evidence on partner perceptions of UNITAID’s contribution to greater market understanding (Recommendation 1.2)
- Work with the Executive Board to articulate the Board’s risk appetite and tolerance (Recommendation 4.2 and Section E)
- Remain engaged through the Board in the 2017-2021 strategy development (Recommendation 6.3)
- Update the logframe to provide more quantitative targets and milestones
- To award UNITAID £44m for 2015 (100%), in accordance with the terms set out in the Memorandum of Understanding (Section B).

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-111074/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-111074/

Outline of the programme

UNITAID was launched in 2006 to improve access to vital medicines, tests and prevention products for people living with HIV/AIDS, TB and malaria (the “three diseases”) in low income countries. Using resources from a levy on air tickets and long-term government contributions, UNITAID invests in high impact market interventions to make health products more affordable, more available, and better adapted. UNITAID fills a niche between the upstream generators of new ideas for health technologies and the downstream funders of large scale programmes (such as developing country governments, the Global Fund, the US President’s Emergency Plan For AIDS Relief, PEPFAR) to address the needs of communities living with the three diseases.

UNITAID is hosted by WHO and works in partnership with a range of implementing partners from the public and private sectors. Its strategy 2013-2016 has six strategic objectives:

1. Increase access to simple point-of-care (POC) diagnostics for HIV/AIDS, TB and malaria
2. Increase access to paediatric medicines to treat HIV/AIDS, TB and malaria
3. Increase access to treatment for HIV/AIDS and co-infections
4. Increase access to treatment of malaria
5. Increase access to second-line TB medicines
6. Increase access to preventatives for HIV/AIDS, TB and malaria

The UK was one of the founding members and is UNITAID’s second most important donor after France. We have a 20 year donor arrangement within which we agree financial contributions in a series of three or four year agreements, with disbursement conditional on performance. In 2015 the UK confirmed a 2015-2017 tranche of funding of £44million per annum, with £9m (20%) each year conditional on the achievement of Board-approved reform priorities.

This is the first Annual Review of the UK’s 2015-2017 funding. It sets the baselines for the new log frame, including Board-approved reform milestones, as agreed in March 2015. The log frame was finalised in July 2015 to capture the design of the New Operating Model. For most log frame indicators, the most recent data is for 2014, thus setting the baseline. We have tried to supplement this wherever possible with relevant quantitative and qualitative data for 2015 in order to track progress. The indicators have been harmonised as much as possible with UNITAID’s own corporate reporting. Where log frame indicators are KPIs, this is noted in square brackets. For many indicators it is too early in the reform programme to develop clear milestones for 2017.

When UNITAID’s 2013-2016 strategic period comes to an end, and new objectives and indicators are developed for the 2017-2021 strategic period, the DFID log frame will be updated accordingly to reflect milestones and targets for DFID’s funding over 2017-2021.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

Project Outcome: low income country markets have greater availability and lower prices for products related to the diagnosis, treatment and prevention of HIV, TB and malaria.

Since inception, UNITAID has had an important impact on health commodity markets, particularly in introducing paediatric diagnostics and medicines for HIV/AIDS and TB, and reducing prices for ACTs and second-line ARVs. UNITAID’s 2014 KPI Report shows good evidence of significant positive impact in some key areas. For example UNITAID investments in the Medicines Patent Pool are estimated to have saved the international community US$79m through lower prices of anti-retroviral (ARV) medication for HIV, equivalent to one-year treatment for 625,000 people; UNITAID’s investment in TB diagnostics through GeneXpert TB has led to its adoption by the national programmes of 145 countries, with price reductions already resulting in over $70m saved; and UNITAID has enabled over 750,000 children worldwide to access better adapted HIV treatment, as well as accelerating product development and policy adoption of injectable and rectal Artesunate for severe malaria (about 80% of malaria deaths occur in under-5s).

UNITAID has now diversified the range of grants it supports so that it can act at different points along the value chain, with the aim of sustaining market changes and bringing quality, innovative products quickly to market at lower price. It is too early to say what impact this change in approach will have, although the Mid-Term Review of the 2013-16 Strategy informs that “UNITAID has successfully expanded its Established Business beyond its initial procurement-focus, to include a variety of different types of projects addressing other parts of the value chain, together with disease areas that were initially not well known to it, such as HIV/HCV co-infection”. Overall, we judge that UNITAID is on track to deliver the required market outcomes and public health impact.

The next three years will be critical for UNITAID. To achieve real sustainability it needs to broaden its donor base, and this in turn requires it to give a much clearer demonstration of value for money and comparative advantage within the global health architecture.

Overall output score and description

A – met expectation. UNITAID has undergone a radical transformation over the past year to strengthen its operating model and reorganise its staff. This score reflects the positive direction and that reforms appear to be progressing well. However, implementation is still at an early stage.

In many cases this review is setting the baseline for the 2015-2017 period and it is too early in the reform process to note the impact these changes will have. Nevertheless UNITAID is making an important difference to health commodity markets and is strengthening its management. It has made good progress over the last year and is generally on track to meet the end 2015 milestones.

Assessment of performance against agreed reform conditions

£44m (100%). 20% of UK funding each year is conditional on the achievement of Board-approved reform priorities. This Annual Review finds UNITAID’s performance against Board approved reform milestones to be meeting expectation on 4 out of 5 indicators; and we are content (see Indicator 5.1) that the delay in meeting the 5th indicator has been for reasons that are outside UNITAID’s control. We therefore recommend that UNITAID is awarded £44m for 2015 (100%), in accordance with the terms set out in the Memorandum of Understanding.

Log frame output indicator	By end June 2015	Progress
4.1 Board approved reforms to UNITAID’s operating model are implemented to time	Secretariat presents key principles and rationale for changes to June Board; new standard operating procedures (SOPs), role charters and process flows drafted	A
UNITAID introduces new Board approved risk management tool to time	Risk management tool introduced. Risk committee Terms of Reference (ToRs) finalised.	A
4.5 Procurement reform is on track and delivering savings	Grantee procurement review ToRs finalised	A
4.6 Value for money framework developed and implemented effectively	Draft framework presented to Board with 3 illustrative examples	A
5.1 Board-approved restructure is completed and demonstrates improved performance	New structure approved by WHO and all job descriptions submitted to WHO for approval	B

Key lessons

There is a long causal chain from market intervention by UNITAID to improvements in health. UNITAID and DFID need to get better at attributing UNITAID’s impact and learning what does and doesn’t work in order to support future strategy formulation.

Key actions

When the 2013-2016 strategic period comes to an end, and new strategic objectives and indicators are developed, the log frame will need to be update accordingly over the 2015-2017 period.

Has the log frame been updated since the last review?

This is the first Annual Review of the UK’s 2015-2017 funding. The log frame has been updated in March 2015 to incorporate the Board-approved reform indicators. Outputs have been added and weightings of some existing outputs reduced in order to facilitate this. Wherever possible, indicators have been harmonised with UNITAID’s own corporate reporting for the 2013-2016 period, with Key Performance Indicators (KPIs) shown in square brackets.

## C: DETAILED OUTPUT SCORING

Output Title	Markets for products for the three diseases are more transparent
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes (10% lower)

Indicator(s)	Milestones	Results
1.1. UNITAID contributes to greater market understanding and better targeted action by key market actors, through work to increase market visibility (e.g. forecasting efforts, landscape reports, market fora and other consultations)	Baseline (2013): Landscape reports published in each disease area / Disease Area # / HIV and co-infections 4 / TB 3 / Malaria 3 / Milestone end-2015: Forecasting, landscape reports, and consultations undertaken, referenced by key partners	A Landscape reports published in each disease area, but less than in 2013. / Year Disease area # / 2014 HIV and co-infections 4 / TB 2 / Malaria 2 / 2015 HIV and co-infections 3 / TB 2 / Malaria 2 / Market dashboard updated quarterly and market fora held in each disease area in 2014. Landscapes circulated amongst key partners for validation prior to publication (e.g. WHO, USAID, GF). / Demand forecasting supported: / - ACTs and malaria RDTs / - Active Pharmaceutical Ingredients (APIs) for selected products / - Licensing opportunities / Resources referenced by key partners via: websites, meeting background documentation, partner reports etc. but lack of evidence on the impact these are having.
1.2. Market analyses and dialogue with global health actors give rise to a shared understanding of markets for the three diseases and the key failures inhibiting access to appropriate medicines, diagnostics and preventive products in LICs	Baseline (2013): Priorities identified through landscape development and market forum in each disease area / Milestone end-2015: Of areas for intervention identified, 100% reflect agreed priorities	A June 2015: Presented 3 areas for intervention to the UNITAID Executive Board (content and rationale); all 3 reflecting agreed priorities.

Key Points

UNITAID invests in regular landscape reports and market fora aimed at developing a shared understanding across funders and industry of key market weaknesses including inappropriate or unaffordable technologies. Based on the landscape reports and partner fora, the Secretariat quarterly prepares a market dashboard to summarise access and market shortcomings in terms of quality, affordability, availability and delivery, as well as the opportunity for UNITAID to intervene in the short or longer term to improve health outcomes across the three diseases. These dashboards form the basis for identifying UNITAID’s Areas for Intervention (AfIs).

In 2014 UNITAID produced 8 landscape reports and held market fora in each disease to share market intelligence about products to prevent, test and treat HIV/AIDS, TB and malaria with the global public health community [Indicator 1.1]. In addition, UNITAID published 11 drug specific patent landscapes (8 in 2014 and 3 in 2015), and extended and expanded demand forecasting for malaria products to include Rapid Diagnostic Tests (RDTs), injectable and rectal artesunate (for severe malaria) in addition to the Artemisinin Combination Therapies (ACTs) and artemisinin raw ingredients and Active Pharmaceutical Ingredients (API).

The landscape reports are widely read, with anecdotal evidence that UNITAID’s landscapes and analytical frameworks are used by partners to inform their understanding of markets – but it is not clear to what extent they have led to increased investment in critical innovations.

The New Operating Model (NOM) formalises deep engagement with global health players as a key element of how UNITAID works, including with the Global Fund. Through the NOM UNITAID selects Areas for Intervention (AfIs) based on its own market intelligence and through extensive dialogue with partners (including funders, countries, technical partners, civil society, and private sector). Its new Strategic Investment Framework links the global goals and challenges to where UNITAID would be best suited to intervene, and then ensures that UNITAID’s projects and results feed back into reaching these goals. Board approved Areas for Intervention in 2015 are focused on issues of drug- and insecticide-resistance and innovative approaches to meeting the needs of particularly neglected and vulnerable groups [Indicator 1.2].

UNITAID, together with the Global Fund and Clinton Health Access Initiative (CHAI), are strategic partners in the development of the E-marketplace, intended to improve market transparency by making commodity prices more readily available to purchasers (e.g. implementing organisations and principal recipients). UNITAID is co-leading the “innovation work stream” of the E-marketplace to identify ways to introduce new and/or innovative products into the market (particularly UNITAID funded products for scale-up).

Furthermore, UNITAID uses transparency in market data and licensing agreements through the Medicines Patent Pool (MPP) to improve the competitiveness of markets for health commodities for the three diseases and drive reductions in prices. In 2010 UNITAID established the MPP to reduce costs and increase competition in the market for anti-retroviral (ARV) drugs for HIV/AIDS through addressing intellectual property (IP) issues; it remains the sole funder. UNITAID investments in the MPP are estimated to have saved the international community US$79m, equivalent to one-year ARV treatment for 625,000 people.

UNITAID is in the process of conducting a branding exercise to understand better how it is perceived and valued (or not) by key stakeholders. This will report by end 2015. It is also developing proposals on evidence-gathering in preparation for the development of the next strategy 2017-21.

Summary of responses to issues raised in previous annual reviews

The 2014 Annual Review and Commercial Expertise Review suggested UNITAID develop a more commercial approach to delivering the strategy – providing clarity around UNITAID’s role and determining how value for money is achieved. They also called for UNITAID to engage more directly with industry, strengthen the MIS platform and collaborate with the Global Fund to ensure the sharing of market data. They also noted similar concerns regarding the usability of UNITAID’s market analysis.

These are all being taken forward under the New Operating Model as discussed above, under which UNITAID will be directly engaging with the private sector and industry. Value for Money is discussed in greater detail under Output 4, and Global Fund collaboration under Output 3. UNITAID is revisiting its plans to create a market intelligence system (MIS) in view of the potential overlaps to leverage its investments to date in the Global Fund’s much larger e-marketplace project.

Recommendations

UNITAID
  1. By mid-2016 collect systematic evidence and rigorously analyse the ways that UNITAID’s landscape reports are used – looking at the most appropriate information, timeframe and types of products to report on to ensure achieving desired impact.

DFID
  1. Review the UNITAID branding report, the proposals for consultation around the strategy development, and plans for assessing the value and future role of the landscape reports in Q1 2016 to ensure that these will provide adequate evidence on partner perceptions of UNITAID’s contribution to greater market understanding

Output Title	Affordable innovations that effectively address key public health problems for the three diseases are accelerated, with a focus on meeting the needs of lower income countries
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		n/a – new output	Impact weighting % revised since last AR?	n/a – new output

Indicator(s)	Milestones	Results
2.1. No. of products entering the market with UNITAID support for each disease [KPI 2.1]	Baseline 2013: 32 medicines prequalified (8 HIV, 7 malaria, 17 TB); 8 diagnostics prequalified / Milestone end- 2014: At least 25 medicines and 6 diagnostics prequalified	A+ 2014 prequalified medicines: 28 (15 HIV, 7 Malaria, 6 TB) / 2014 prequalified diagnostics: 9 (2 Malaria RDTs, 6 HIV/AIDS, 1 Hepatitis B virus), exceeding expectation. / 2015 (30 June 2015) prequalified medicines: 5 (5 HIV) / 2015 (29 July 2015) prequalified diagnostics: 9 (6 Malaria RDTs, 4 HIV/AIDS, 3 Hepatitis C virus)

Key Points

There is strong evidence of a consistent strategic focus on low resource/income settings. Over 2013-2015 UNITAID has invested an average of $226m each year in interventions, with a particular focus on simple point of care (POC) diagnostics for low resource settings (37%), preventatives (19%), affordable, adapted paediatric medicines (18%), and treatment of 2nd line TB (14%). Paediatric ARVs, for example, are only needed in countries where weaknesses in health systems have led to a failure to prevent mother to child transmission of HIV, predominantly low income countries. UNITAID investments have enabled 750,000 children to be placed on treatment. UNITAID’s investment in the MPP, which monitors patent status of ARVs and negotiates licensing agreements with innovator companies to allow introduction of less expensive generics, is estimated to have saved the international community $79m.

UNITAID’s constitution requires that at least 85% of funds used to purchase commodities should be spent in low income countries (LICS), with no more than 10% in lower middle income countries (LMICs) and a maximum of 5% in upper middle income countries (UMICs), with a priority given to those with a high disease prevalence, and subject to co-financing requirements.

Over 2006-2014, 83% of UNITAID’s commodity purchases went to LICs, 15% to LMICs and 2% to UMICs. These figures are broadly in line with the constitutional requirement. Results also show that low and lower-middle-income countries are the main beneficiaries of UNITAID secured prices [KPI 2.3]. For example UNITAID’s investment in TB diagnostics through GeneXpert TB has led to its adoption by the national programmes of 145 countries, nearly all of which are low or lower-middle income countries.

In addition, UNITAID funds cross-cutting initiatives that support access in LICs more explicitly. In particular, UNITAID is the main funder of WHO pre-qualification, which is the key regulatory pathway for donor-funded purchases of health commodities in low income countries. This helps ensure that medicines and diagnostics entering countries are safe and effective. In 2014 28 key products were prequalified. 21% of the prequalified15 products were for TB, 25% for Malaria and the remaining 54% were for HIV [Indicator 2.1].

Since inception, UNITAID’sproposal submission templates have required proposers to explain how their project would “contribute to greater equity for key and vulnerable populations in lower income countries”. This reflects a longstanding commitment to the most vulnerable populations.
Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable. This is a new log frame indicator following the agreement of the UK’s 2015-2017 funding to ensure DFID’s Annual Review assesses UNITAID’s contribution to and focus on Low Income Countries in accordance with its mandate; and to ensure UNITAID continues to accelerate innovations in order to have maximum public health impact. The previous log frame did not make such an annual assessment at the output level.

Output Title	UNITAID fully aligns and harmonises with international efforts to improve the health of people living with the three diseases
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Results
3.1. Number of grants that include co-investment with other global public health donors and national programmes [KPI 6.1]	Baseline 2013: 11 active grants (out of 25), including 3 market entry grants, receive support from other global partners. / Milestone end-2014: At least 10 active grants including 3 market entry grants, receive support from other global partners.	A End-2014 10 active grants (out of 28), including 3 market entry grants, received support from other global partners: Gates Foundation (4); USAID (3); Global Fund (1); Private Sector (2), meeting expectation. / 2014 result less than 2013 baseline due to two large co-funded projects closing in 2014.
3.2. Number of countries with UNITAID-supported medicines and diagnostics being part of their national programmes [KPI 6.2]	Baseline 2013: HIV: 7 countries. Malaria: 6 countries. TB: 104 countries. / Milestone end-2014: HIV: 7 countries. Malaria: 6 countries. TB: 130 countries	A+ End 2014: / HIV: 31 for paediatric ARVs / 22 for adult 2nd-line ARVs / 9 for POC CD4 tests / 2 for POC viral load tests / Malaria: 6 for severe malaria / TB: 145 for GeneXpert
3.3. UNITAID and the Global Fund determine areas and means of effective collaboration to amplify and sustain impact	Baseline 2014: Agreement signed / Milestone end-2015: (i) Global Fund Directors and Regional Managers fully informed about quality and availability of all relevant UNITAID-supported products; (ii) Collaboration across key work streams.	A Quarterly meetings at the strategic and operational levels of collaboration / Co-leading the innovation work stream of the E-marketplace project.
3.4. Credible and functional policies developed on transition of grants away from UNITAID funding	Baseline 2014: Transition approach described in project plans (Grant Agreements) / Milestone end-2015: 20% of active grants and 100% of new grants include a transition plan	A 21% (6 of 28) of active grants have a transition plan / However, 46% (6 of 13) of active grants that should have a transition plan (i.e., in their final years of implementation) have a developed plan / All new grants have a transition approach developed with the project plan and will be monitored during implementation.

Key Points

Partnership is integral to UNITAID’s governance structure and ways of working. The new operating model approved by the Board in March 2015 formalises deep engagement with other global health players as a key element of how UNITAID works. This is evidenced in practice by, for example, the areas for intervention approved by the Board in June 2015, which were derived through “strong and structured partner engagement (including funders, countries, technical partners, civil society, private sector)” as well as UNITAID’s own analysis. In addition, UNITAID has developed Disease Narratives for all diseases, developed through extensive engagement with partners throughout the process.

UNITAID’s structured approach to partner engagement is an important element in defining the niches where UNITAID should work, and the areas where it should be working with others to deliver maximum impact. In 2014, 36% of UNITAID grants included co-investment with other major global public health donors (e.g. GF, USAID, BMGF, DFID) [Indicator 3.1].

UNITAID has active formal partnership arrangements with the Global Fund and the Children’s Investment Fund Foundation (CIFF). UNITAID and the Global Fund signed an MoU in June 2014 and plan to revise this to reflect the increased engagement that has gone far beyond what the MoU initially envisaged. Since then UNITAID has signed the lease on new offices next to the Global Fund, which will help to thicken relationships with these organisations, and have identified three distinct levels of collaboration to increase impact – including meetings and information sharing at strategic, operational and technical levels [Indicator 3.3]. More recently the partnership with the Global Fund includes a proposal to the November Board for co-financing of their new e-marketplace initiative, where UNITAID is co-leading the workstream on innovation. This collaboration has the potential to deliver an important pathway for scaling up innovation. A successful partnership with the Global Fund is key to maximising UNITAID’s impact.

Sustainability and transition planning are also central to UNITAID’s ability to deliver impact. Success for UNITAID is measured partly by how well and consistently their programmes are taken to scale by others. By the end of 2014, 145 countries had included GeneXpert in their national programmes, 31 had included UNITAID-sponsored paediatric ARVs, 22 had included UNITAID-sponsored adult 2nd line ARVs, and 6 had incorporated UNITAID-sponsored treatments for severe malaria [Indicator 3.2].

UNITAID organises multi-stakeholder consultations to bring together governments, civil society organisations and implementers to build engagement in UNITAID projects. Following 6 consultations over 2011-2013, in 2014-15 they carried out 2 consultations in Tanzania and Ethiopia. In Ethiopia the Minister of health had a good understanding of UNITAID and praised its important role, but felt it was important for UNITAID to engage governments more robustly as country buy-in is necessary to take an innovation to scale through national resources and national plans.

UNITAID’s approach to transition planning has evolved over time. Under the NOM, planning for scale-up is built into programme design and implementation through ongoing partner engagement. However, prior to this, transition planning was less consistent. At the end of 2014, of the 13 active grants in their final 12-18 months of the implementation, only 6 (46%) had a developed plan [Indicator 3.4].

Summary of responses to issues raised in previous annual reviews (where relevant)

The MAR update 2013 highlighted the importance of a credible and functional policy on transition of UNITAID grants away from UNITAID funding. DFID’s 2014 Annual Review and Commercial Expertise Review highlighted partnership working and transition planning as critically important to UNITAID’s success, particularly with the Global Fund. These have been addressed as above and progress is closely monitored and reported to the Board

Recommendations

UNITAID:
  1. By end-2016 ensure that monitoring and evaluation systems track why and when products are (or are not) successful in transitioning to national programmes as well as to programmatic support from the major global health players in order to learn from success and failure.

Output Title	UNITAID’s grant making and management processes are efficient and effective and deliver value for money
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes (10% lower)

Indicator(s)	Milestones	Results
4.1. Board approved reforms to UNITAID’s operating model are implemented to time	Baseline 2014: Reforms approved by Board / Milestone June-2015: Secretariat presents key principles and rationale for changes to June Board; new standard operating procedures (SOPs), role charters and process flows drafted	A The Secretariat presented, and the Board approved, the principles and rationale for the new operating model in June 2015. / A mapping exercise to determine the required SOPs (new and modified) has been completed and their development included in the work streams.
4.2. Board approved risk management tool implemented to schedule	Baseline 2014: Reforms approved by Board / Milestone June-2015: All proposals for Board consideration are risk assessed. Risk committee Terms of Reference (ToRs) finalised	A Risk management tool development and piloted in three active grants (Access SMC, MSF HCV and DNDi). Risk Committee Terms of Reference have been finalised and the RC first met formally in April 2015. The one grant presented for approval to the June 2015 Board was accompanied by a risk assessment, meeting expectation. All proposals coming to the Board in November 2015 will be accompanied by preliminary risk analyses. Secretariat will review the remainder of the portfolio through 2015 and finalise the methodology.

4.3. % grantee satisfaction with grant related processes [KPI 4.2]	Baseline 2014: Survey completed December 2014 / Milestone end-2015: N/A	A The overall grantee satisfaction rate in the 2014 survey was 56.6%. This represents a baseline from which improvement can be measured over time.
4.4. Median number of days from Board go ahead to grant signature [KPI 4.4]	Baseline 2013: 153 / Milestone end 2014: 140 / Milestone end-2015: 120	B Median 172 days to sign 11 grants in 2014. 2 projects took more than 300 days. Delays were due to 2 grants being difficult to negotiate and resulted in a higher average for 2014.
4.5. Procurement reform is on track and delivering savings	Baseline 2014: Reforms approved by Board / Milestone June-2015: Grantee procurement review ToRs finalised	A An independent consultant has completed a review of UNITAID’s grant procurement process. UNITAID is reviewing the recommendations and expects to start implementing changes in the first quarter of 2016.
4.6. Value for money framework developed and implemented	Baseline 2014: Reforms approved by Board / Milestone June-2015: Draft framework presented to Board with 3-5 illustrative examples	A Value for money framework presented at Executive Board Retreat in April 2015, including 3 illustrative examples (GeneXpert TB, Access SMC, 2nd line ARVs)

Key Points

Following the Functional Review end-2014, UNITAID has embarked on an ambitious set of reforms. Several key initiatives have been launched to transform UNITAID’s operating model and create a more robust approach to capture the impact of its projects, including: a new operating model; a more robust approach to Value for Money, and; strengthened risk management. The Secretariat is making good progress on all of these reforms, and meeting expectation across Output 4 as highlighted below.
Indicator 4.1 - Board approved reforms to UNITAID’s operating model are implemented to time, meeting June 2015 milestone. Approved at the June 2015 Executive Board meeting, UNITAID has begun implementing its New Operating Model (NOM), has presented key principles and rationale for any changes, and developed new standard operating procedures to underpin implementation of the model...

Indicator 4.2 – All proposals for Board consideration are risk assessed and risk committee Terms of Reference (ToRs) finalised, meeting 2015 milestone.The New Operating Model (NOM) includes a more explicit focus on grant risk management. The Functional Review in late 2014 identified the need to develop a comprehensive risk management framework. Since then, UNITAID have embarked on implementing a more uniform, standardised approach to strengthen risk management, embed it in the culture of the Secretariat, and ensure the Board have earlier sight of risks and due diligence assessments prior to approval.

The new approach applies to all staff involved in grant management activities. A Grant Risk Management Guideline and associated Standard Operating Procedures have been developed in line with ISO 31000 standards. They include a risk taxonomy categorising potential risks, tools for documentation of risk identification, assessment and treatment, and a template for agreed risk treatment measures with an allocated owner. Plotting of risk levels in a heatmap allows for prioritisation of high risks and corresponding follow-up and resource allocation. Risk management is reviewed by a Grant Risk Committee co-chaired by the Directors of Operations and Strategy & Results, which first met formally in April 2015 and has met three times since.

UNITAID piloted the new approach in the first half of 2015 with three existing grants. The pilots highlighted the need for stronger, more targeted capacity assessments; stronger risk assessment prior to grant signature and for greater definition of UNITAID’s oversight duty and distinction with the grantee’s implementing duty. All proposals coming to the Board in November 2015 following Review Committee ‘go-ahead’ will be accompanied by a preliminary risk analysis. Risk Analysis has also been done on two grants which will be brought to the Board for approval before the end of 2015. The Secretariat will review the remainder of the portfolio through 2015, integrate the lessons from the pilots, and finalise the methodology. UNITAID will also revisit all grant implementation processes to identify areas when greater assurance is needed on actions taken by grantees to enable differentiation of grant oversight based on the level of risk. This will however not be concluded until March 2016.

Indicator 4.3 – Grantee satisfaction survey undertaken, meeting expectation. A major focus of the restructuring in 2015 was to increase the focus on grant management by 30% to improve UNITAID’s ability to manage its projects and deliver value for money. UNITAID carries out grantee satisfaction surveys which include questions on UNITAID’s impact, processes and staff. UNITAID’s 2014 grantee satisfaction survey scored 56.6%. While grantees had mixed (often negative) views on UNITAID’s processes, they were however extremely positive about UNITAID staff. For example, 63% rated the UNITAID Secretariat as above or far above the average for professionalism and technical expertise compared to similar organisations, and 58% rated the quality of contact with UNITAID project leads as “excellent”. In November 2014 UNITAID also hosted a grantee forum with 107 participants to facilitate mutual learning and receive feedback from grantees in their working relationship with UNITAID. Grantee feedback highlighted that the Grantee Forum provided a great opportunity for grantees to interact, get to know UNITAID better, and facilitated greater understanding of the challenges faced by both UNITAID and by grantees. A new grantee survey is planned for end-2015 with results available early-2016 through which – given the changes already implemented - we expect to see improvements.

Indicator 4.4 – In 2014 UNITAID took an average of 172 days to sign each of 11 grants, not meeting 2014 or 2015 milestones. The NOM was initiated to increase the speed of grant review and approval processes, although this has not yet been achieved . In 2014 two projects took more than 300 days, with delays due to difficulties within negotiations, and resulting in a higher average for 2014.. A fully staffed Secretariat should however help to streamline some of these processes to run in parallel rather than sequentially, decreasing the time to signature.

Indicator 4.5 – UNITAID’s grant procurement process has been reviewed, meeting expectation. Milestone 2 (June 2016) is for UNITAID to have implemented all relevant recommendations. In 2014, UNITAID disbursed $114.3m to grantees, of which 43% was for commodity purchases. Because UNITAID tests and pilots innovations for scale-up by others, commodity prices are an important element in the grant negotiations – if the intervention does not get prices down to affordable levels, the projects will not have sustainable impacts. Each grantee is required to develop a procurement strategy which is “designed to maximise competition among product manufacturers … and to ensure affordable pricing, value for money and optimal access.” Where products are being tested or piloted (and are therefore not in a competitive market) grantees are expected to complete a Cost of Goods Sold (COGs) analysis, review margins, and understand any price premiums associated with new products coming to market before negotiating the best prices, terms and conditions for a term-limited procurement. There is clear guidance on what other costs are appropriate in UNITAID grants, and good evidence of UNITAID actually negotiating cost reductions. In 2015 an independent consultant reviewed UNITAID’s grant procurement process. UNITAID is reviewing the recommendations and expects to start implementing changes in the first quarter of 2016.

Indicator 4.6 – Draft value for money framework presented to the Board with 3 examples, meeting expectation. Under its NOM UNITAID has focused on value for money, seeking to strengthen the collection of data and evaluating economic and public health impact to help determine how products are contributing to the global response against the three diseases. . It has designed a new Strategic Investment Framework, which links the Global Goals and challenges to where UNITAID would be best suited to intervene, and then ensures that UNITAID’s projects and results feed back into reaching these. This is evidenced in practice by, for example, the areas for intervention (AfIs) approved by the Board in June 2015. These AfIs have now been translated into calls for proposals from the global health community. The first call for proposals under the NOM was made in July 2015. It generated 29 proposals, between 7 and 11 for each area for intervention. These will now be assessed against a comprehensive set of criteria which include an assessment of value for money. The large number of proposals received in response to the first targeted call under the NOM gives a high level of confidence that UNITAID will be able to make good value for money investment choices.

UNITAID now needs to formalise its value for money framework to better communicate linkages between investments and outcomes.UNITAID is currently working with partners and external experts to validate its initial model and will implement the value for money framework across the portfolio through end of 2016. Prior to this however, UNITAID has not systematically collected data on value for money or impact. Value for money needs to be seen by UNITAID as a continuous process which guides their investment decisions and is used to gather evidence of their impact and influence future programming.
Summary of responses to issues raised in previous annual reviews (where relevant)

The MAR Update 2013 and 2014 Annual Review recommended strengthening and streamlining the grant approval process to ensure that priority is given to those proposals that offer the greatest value for money, and to ensure a grantee satisfaction survey was undertaken in December 2014. Several changes have been made over the past year to streamline the grant agreement development process and improve value for money and risk management following a review by the Secretariat, as described above.

Recommendations

UNITAID
  1. As UNITAID develops a more robust framework to quantify impact and value for money, the linkages between investments and outcomes should become clearer and more measurable and it will be important for UNITAID to better communicate this.
  2. By end-2016 ensure lessons are documented and learned from ,with regards to the difficult negotiations delaying grant signature under Output 4.4

Output Title	UNITAID governance and management structures are economical, efficient and effective
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes (10% less)

Indicator(s)	Milestones	Results
5.1. Board-approved restructure is completed and demonstrates improved performance	Baseline 2014: Structure approved by Board / Milestone June-2015: New structure approved by WHO and all job descriptions submitted to WHO for approval	B New structure was approved by WHO in March 2015. / To June 2015 31 of 38 (82%) job descriptions have been submitted and approved by WHO, below expectation. To November 2015, all job descriptions have been submitted to WHO.
5.2. Secretariat costs relative to total value of active grants [KPI 7.1]	Baseline 2013: 1.93% / Milestone 2014: 2% / Milestone end-2015: 2%	A+ End-2014 Secretariat costs were 1.7% of the total value of active grants
5.3. Level of respondent staff satisfaction with working at UNITAID [KPI 7.2]	Baseline 2014: No survey / Milestone end-2015: Survey shows improvement over 2014 in at least 2 standard measures	A Setting baseline. Survey undertaken in 2015 with 83% response rate. 40% reported to being satisfied and motivated by their job.
5.4. Governance reforms agreed and implemented to schedule	Baseline 2013: 2014- Governance reform proposed to the Board (EB 21) / Milestone end-2015: Clear and transparent process established for the election of the new Board Leadership	A Board have agreed a clear and transparent process for electing the new Board leadership. ToRs were informally agreed in September and will be formally approved in November to launch the nominations process. Steering Committee on Governance reconvened. Finalised a new Chairman’s letter and ED performance assessment process in October.

Key Points

A Functional Review conducted by the Secretariat in late 2014 identified UNITAID’s structure and resource allocation as an area for potential strengthening. Over 2015 as part of UNITAID’s transformation process, UNITAID has restructured the Secretariat to better meet the needs of the New Operating Model. With a targeted structure focusing on increasing capacity in UNITAID’s core business, the restructuring has: created a Strategy and Results Unit responsible for strategic issues and a focus on impact assessment, value for money, and monitoring and evaluation; strengthened Operations with additional Programme Managers and Officers to improve capacity within grant management; strengthened grant finance functions; and has created cross-functional disease teams to give input to work together on grant development and implementation. In addition it is transforming many short term positions into fixed term to create more stability within the Secretariat. The restructure will deliver an increase of 30% in staffing focused on UNITAID’s core business of grant management.

This new HR structure was approved in March 2015 and UNITAID is making good progress on recruiting staff, receiving record numbers of applications [Indicator 5.1]. Of the 28 positions advertised over January to September 2015, 7782 applications were received. To September 2015 22 posts have been filled, representing 58% of UNITAID’s total vacant positions in the organogram. Recruitment is well underway and UNITAID expect to be fully staffed by March 2016. Given the volume of posts to be filled in the new structure, and lengthy processes to recruit through the World Health Organsiation (WHO), there have been significant delays in recruitment. While UNITAID is working to implement the new operating model alongside high priority initiatives on risk management and value for money, these delays to staffing the Secretariat has resulted in high workloads and an important risk of lack of capacity at this critical time. This is a concern, albeit one that the Secretariat is actively addressing.

UNITAID undertook a staff satisfaction survey end-2014. The staff satisfaction survey highlighted that only 40% of staff were satisfied and motivated by their job [Indicator 5.3]. This was however conducted end-2014 when the change programme was taking place. The staff survey will be repeated end-2015 and reported on in the 2016 Annual Report. Judging from our own contact with UNITAID staff, we expect that the results from next year’s survey will highlight progress made by UNITAID senior management in creating a positive and empowering work environment.

UNITAID has a lean Secretariat costing 1.7% of the total value of its active grants in 2014, compared to a Board target of 2% [Indicator 5.2], with operating expenses (OpEx) of $16.841m, of which $12.5m was for staff and other personnel costs, $0.9m was for staff travel and the remainder was for consultancy and other contractual services. The OpEx budget fell by 9% in nominal terms over 2013-2015; despite a major organisational restructuring and office relocation and the 2016 operating budget request is 16% less ($5.1m) than requested in 2015. UNITAID has restructured within the same overall staffing budget, increasing the number of professional staff by 5% and funding this through cuts elsewhere.

Regarding governance, the Board unanimously approved the Executive Director’s plan for reform in December 2014 and the Chair is extremely supportive of these. A governance working group was established at the April Board Retreat, chaired by Norway, with representation from Brazil, France, NGOs and the UK. To date this group has proposed a Board Chair selection process, to be finalised at the November Board meeting, alongside finalising the process and framework for assessing the Executive Director’s performance [Indicator 5.4].
Summary of responses to issues raised in previous annual reviews (where relevant)

The MAR Update 2013 and 2014 Annual Review highlighted the need for improvements in UNITAID’s strategy and business model and for stronger leadership and management capacity to deliver an efficient and well-led Secretariat, in response to the concerns raised in the 2013 risk of wrongdoing paper and functional review. The Secretariat has worked hard over the past year to strengthen the grant assessment process and address the concerns raised.

Recommendations

UNITAID:
  1. Continue to implement Board-approved reforms to schedule
  2. Work with WHO to ensure all outstanding job posts are advertised and filled as quickly as possible

Output Title	Robust Strategy developed for 2017-2021, delivering greater impact for low-income, high-burden countries
Output number per LF		6	Output Score	A
Risk:		Low	Impact weighting (%):	10
Risk revised since last AR?		n/a – new output	Impact weighting % revised since last AR?	n/a – new ouptut

Indicator(s)	Milestones	Results
6.1. Consultative and evidence-based Strategy development process is developed	Baseline 2014: N/A / Milestone end-2015: Plans for robust Mid Term Review in place	A Mid-term review paper distributed to the Board for discussion in November
6.2. Clear narrative and linkages developed between resource needs and impact	Baseline 2013: N/A / Milestone end-2015: N/A	No results yet to report.
6.3. Meaningful KPIs reported to and regularly monitored by management and the Board [aligned to the strategy]	Baseline 2014: KPI report in place but not covering key interests / Milestone end-2015: N/A	A UNITAID’s annual KPI report published in July 2015 (2014 results)

Key Points

In recent years UNITAID has made significant progress in articulating its performance framework, defining and reporting against Key Performance Indicators (KPIs) to measure the overall performance of its grants and enable the Board to assess the impact of UNITAID’s interventions. There are 7 KPIs and 23 associated measures of performance for the 2013-2016 Strategy [Indicator 6.3]. However, very few of the current KPIs have associated targets and as such it is difficult to ascertain whether progress is above or below expectation, or whether UNITAID is performing well or where additional progress is required. There is also no reference to how much it costs to achieve the various KPIs and whether progress is reasonable given these costs. In future it would be useful to consistently have reference to previous years’ results per indicator to show trajectory of progress over time, and to measure against indicators which are within UNITAID’s own areas of influence to appropriately monitor performance. A full revision of the KPIs and associated reporting will occur as part of the development of the new strategy.

The Mid-Term Review of the current 2013-2016 Strategy has been distributed to the Board and will be discussed in November 2015. It documents lessons UNITAID has learnt from current and previous investments and analyses the evolution of both UNITAID and its partners. It draws upon the recently completed Functional Review, although makes no reference to the Key Performance Indicators (KPIs). The Review does however set out a timeline for a consultation on the development of the new strategy [Indicator 6.1]. The new strategy will draw upon the results of the Mid-Term Review and is expected to be presented to the Board in draft in June 2016 for finalisation at end 2016.
Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable. This is a new indicator under the 2015-2017 log frame to ensure enough emphasis is placed on preparing for the next strategic period.

Recommendations

UNITAID

6.1 Provide a clear workplan on how the Secretariat aims to develop and reach agreement on a new strategic framework in 2016 – including evidence-gathering and consultation periods to develop an entirely new strategy rather than a refresh of the old
6.2 Ensure the next strategic period 2017-2021 has clear targets and milestones, with robust processes for data collection underlying these.

DFID
6.3Remain engaged through the Board in the 2017-2021 strategy development.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Value for Money

UNITAID’s current performance against the four “E”s of the DFID value for money framework is set out in the table below. Overall, our assessment is that there is some clear and promising evidence of value for money being delivered by UNITAID. They have directly and indirectly supported increased access to, and affordability of, a number of important medicines and diagnostic tests, and have shaped markets by catalysing and expediting generic production possibilities. However, the Secretariat acknowledges the need to better measure value for money and impact across the grant portfolio [Output 4].

Performance against the four “E”s of DFID’s value for money framework
Economy	Efficiency	Effectiveness	Equity
The Secretariat is lean, with costs relative to value of active grants of 1.7% at the end of 2014, against a Board-approved target of 2%. / The current reform programme is working within this overall budget to improve performance by reorganising and reallocating staff across functions.	Operational efficiency is improving against a range of performance indicators, and will improve further under the reform programme. / The New Operating Model is designed to streamline processes for grant management – although indicator 4.4 is not meeting expectation. / Good allocative efficiency. The focus on drug resistance is strongly based on the evidence of the economic costs of the three epidemics, which is in all cases much higher for drug (and insecticide) resistant strains. / The grant portfolio is spread fairly evenly across the three diseases. / A key focus of the reform agenda is for grants to form part of a broader strategy geared at addressing specific problems to maximise its impact.	UNITAID sets public health impact goals for all projects and tracks delivery against these / UNITAID can point to some important achievements. For example UNITAID investments in the MPP are estimated to have saved the international community US$79m. UNITAID’s investment in TB diagnostics through GeneXpert has led to price reductions resulting in over $70m saved / At this stage in UNITAID’s evolution it is not possible to clearly specify the precise results that would be achieved over the next three years. However, available estimates give returns on investment of past projects of between 3:1 and 17-23:1 within a clear framework of supporting the global fight against HIV/AIDS, TB and malaria.	Strong equity dimension with a focus on: / paediatric formulations - children are a key under-served population / point-of-care diagnostic tests - the most suitable tests for those living in rural areas; / drug resistance - the most expensive and time-consuming, and hence the most impoverishing disease strains; and / HIV and Hepatitis C treatments for most at risk population groups / UNITAID’s new proposal submission form under the NOM requires proposers to explain how their project would “contribute to greater equity for key and vulnerable populations in lower income countries”, including regarding gender equity

Assessment of whether the programme continues to represent value for money

The original investment decision predates the introduction of Business Cases. However, since 2006, UNITAID has evolved as an organisation, shifting its focus from procurement activities to a mixture of interventions along the value chain. This is viewed as a positive evolution, avoiding duplication of activities with other organisations who dovetail in UNITAID’s policy space.

Recent changes in organisational structure, and the continued evolution of the institution under the New Operating Model has helped to better define UNITAID’s offer, sharpen the grant decision making process, and contribute directly to better access to new treatments and tests in a complex marketplace. We are satisfired that UNITAID continues to represent value for money – and will represent even greater value for money as the reform programme progresses and the full value for money framework is rolled out across the portfolio over 2016 [Indicator 4.6].

Quality of financial management

UNITAID’s financial management is steadily improving. The UK’s position as Chair of the Finance and Accountability Committee is giving us good oversight of this, and the Secretariat is continuously improving the quality of reporting to the FAC. Each of UNITAID’s current set of projects has a nominated lead who is responsible for scrutinising the budget and activity plan, negotiating costs, advising on disbursement requests, monitoring progress and recommending corrective action as necessary. UNITAID guidelines require that disbursements clearly fund approved activities and are not made in advance of need. There is good evidence of UNITAID monitoring project performance and taking corrective action as necessary, including through closing non-performing projects.

UNITAID’s hosting arrangement within WHO means that it cannot enter into contracts without having received the full value of the supporting donor commitments. Significant underspend in 2014 has resulted in UNITAID having a cash balance of $821m, of which $360m is uncommitted, at the end of 2014, and it is neither appropriate nor possible for the Secretariat to develop sufficient high quality proposals to commit these funds in 2015. This situation has led to UNITAID accumulating large (committed and uncommitted) cash balances. For the 2015-2017 funding period the UK has therefore moved to a Promissory Note (PN) mechanism with release of PNs tied to liquidity assessments at the time of each Annual Review to manage these issues.

Date of last narrative financial report	05 August 2015
Date of last audited annual statement	31 December 2014

E: RISK

Overall risk rating
Medium

Overview of programme risk

UNITAID is a hosted partnership under the WHO, although it has recently moved out of WHO offices into its new offices next to the Global Fund and Stop TB. The WHO hosting arrangements offer benefits (for example in hedging foreign exchange exposure) but also mean that UNITAID needs to comply with lengthy WHO recruitment procedures. This has significantly slowed down recruitment and the transformation, and going forward there is a risk that it will make it more difficult for UNITAID to be fast, flexible and linked in with the private sector.

Lack of capacity within the Secretariat is currently the most important risk. While UNITAID are working to implement the new operating model alongside high priority initiatives on risk management and value for money, there is a high workload with a number of processes running in parallel without the Secretariat yet fully staffed. There is therefore a risk of burnout or that the momentum behind the reform agenda diminishes.

Outstanding actions from risk assessment

UNITAID’s risk management policy was approved by the Board in 2013. An updated organisational risk assessment was completed in February 2014. In discussing it, the May 2014 FAC noted that although risk management practices already existed (including risk identification and assessment, grantee fiduciary and capacity assessments, and reporting on financial risks), they needed to be reviewed and integrated into a coherent and structured set of risk management processes. UNITAID recruited a new Risk and Compliance Officer (RCO) in November 2014 to take this forward.

The Functional Review in late 2014 identified the need to develop a comprehensive risk management framework. Since then, UNITAID have embarked on implementing a more uniform, standardised approach to strengthen risk management, embed it in the culture of the Secretariat, and ensure the Board have earlier sight of risks and due diligence assessments prior to approval.

The New Operating Model (NOM) approved in March 2015 includes a more explicit focus on risk and a clearer role within this for the Board [Output 4]. The Board acknowledged it as an excellent framework for moving to a culture within the organisation of dialogue, openness and willingness to discuss and recognise risks, whilst stating that further work is required to articulate clearly the tolerance of risks. There is an important role for the Executive Board in articulating this appetite and tolerance.

F: COMMERCIAL CONSIDERATIONS

Performance of partnership (s)

As described under Output 3 UNITAID has initiated a more comprehensive and strategic collaboration with other partners including the Global Fund. The introduction of the New Operating Model and value for money framework [Output 4] highlights the work underway to drive commercial improvement and VfM throughout UNITAID’s activities.

G: CONDITIONALITY

Update on partnership principles (if relevant)

UNITAID does not have an in-country presence, although it does fund partners to operate in-country on a small scale. As a multilateral organisation, it is exempt from DFID’s partnership principles.

Conditions

20% of UK funding each year is conditional on the achievement of Board-approved reform priorities. This Annual Review finds UNITAID’s performance against Board approved reform milestones to be meeting expectation on 4 out of 5 indicators; and we are content (see Indicator 5.1) that the delay in meeting the 5th indicator has been for reasons that are outside UNITAID’s control.

H: MONITORING & EVALUATION

Evidence and evaluation

Grantees submit reports twice a year, including on monitoring and evaluation, finance and procurement. Independent evaluations are made available on the UNITAID website.

In 2015, under its New Operating Model, UNITAID has focused on value for money, seeking to strengthen the collection of data and evaluating economic and public health impact. UNITAID has also restructured the Secretariat to better meet the needs of the New Operating Model – including creating a Strategy and Results Unit responsible for monitoring and evaluation.

The Mid-Term Review of the current 2013-2016 Strategy will be discussed at the Board in November 2015. It documents lessons UNITAID has learnt from current and previous investments and analyses the evolution of both UNITAID and its partners. It draws upon the recently completed Functional Review and sets out a timeline for a consultation on the development of the new strategy [Indicator 6.1].

DFID is currently conducting a Multilateral Aid Review (MAR) assessment of UNITAID. This Annual Review draws upon the evidence gathered for the MAR.

Monitoring progress throughout the review period

Progress will be monitored through UNITAID’s own reporting (most of the log frame indicators are UNITAID’s own KPIs), through discussions with UNITAID staff and with other Board members.