LOGICAL FRAMEWORK
Migrating out of Poverty
Research Programme Consortium

PROJECT TITLE	Migrating out of Poverty Research Programme Consortium
GOAL/IMPACT	Indicator	Baseline / 2011	Milestone 1 / 2013	Milestone 2 / 2015		Milestone 3 / 2017	Assumptions
State and societal actors have utilised a strong evidence base on internal and regional migration to develop/ produce pro-poor policies on migration. / Pro-poor refers to positive references to poor migrants. / Vulnerable migrants in precarious occupations and unfree labour arrangements are better protected and more able to benefit from migration	G1a. # of current government national or regional plans that contain pro-poor references to internal or regional migration in 5 countries and their regions	9	14	19		24	Not required
			ACTUALS 2015	23
		Source: Annual review of national and regional plans
		Review to be undertaken by partners in July/August each milestone year. Includes plans in neighbouring countries where partners have access to them.
	Indicator				Baseline / 2015	Milestone 2017
	G1b. By 2017, a significant example of new legislation or the improved implementation of existing legislation to better protect poor and vulnerable migrants				?	1

	Indicator				Baseline / 2015	Milestone 2017
	G1c. By 2017, an example of the incorporation of new evidence on migration and poverty into development planning				?	1

	Indicator	Baseline / 2011	Milestone 1 / 2013		Milestone 2 / 2015	Milestone 3 / 2017
	G2. # of current donor country programmes and strategy documents that contain pro-poor references to internal or regional migration	8	10		12	15
			ACTUALS 2015		10
		Source: Annual review of new country programmes and broader strategy documents of World Bank, ADB, AfDB, UNDP, EU, DFID
		Review to be undertaken by secretariat in July/August each milestone year. Covers only countries in which the RPC conducts significant work. Number of documents/programmes covering stated year
	Indicator	Baseline / 2011	Milestone 1 / 2013		Milestone 2 / 2015	Milestone 3 / 2017
	G3. % references in G1 above that address gender dimensions of migration	25%	50%		50%	50%
			ACTUALS 2015		70%
		Source: as above
		Review to be undertaken by Partners in July/August each milestone year

PURPOSE/OUTCOME	Indicator	Baseline / 2011				Milestone 1 / 2013					Milestone 2 / 2015				Milestone 3 / 2017					Assumptions
Improved access to and demand for internal and regional migration evidence by targeted development policy stakeholders in 5 countries /regions (as a result of an improved understanding of migration and poverty linkages and how this can be used to maximise benefits of migration for development and minimise risks or negative impacts) / Policy makers and practitioners will have a greater understanding of the relationships between migration, gender relations and poverty	P1. # of policy documents related to RPC countries reflecting the new understandings of migration developed by the RPC	1				5					10				15					Governments have political will and resources to implement policies, which maximize the poverty reduction and development impacts of migration; and minimise the costs and risks of migration for the poor / International organisations and donors support government efforts / Multilateral and bilateral agencies are committed to developing evidence based policies / Commitment across different parts of DFID to integrating new thinking on migration / Policy framing processes on migration are required and are occurring on at least an annual basis in each country
				ACTUALS 2015					11
		Source: Annual review of documents compiled as goal indicators
		Review to be undertaken by Partners in July/August each year
	Indicator	Baseline / 2011				Milestone 1 / 2013					Milestone 2 / 2015					Milestone 3 / 2017
	P2. % policy makers and senior researchers responding to survey and reporting positively on contribution of RPC evidence base / % policy makers, practitioners and senior researchers responding to survey; % of those saying they have benefitted from MOOP research; and % of respondents recognising the importance of migration and its impact on gender and social relations	0%		0%		10%		25%			20%			50%			30%	75%	?
				ACTUALS 2015					40%			72%
		Source: Annual perception survey
		Perception Survey to be sent out by RPC secretariat and Partners in July-August each year to mailing list of key stakeholders. Above % are of those responding to survey and the % of these responding positively.
	Indicator	Baseline / 2011				Milestone 1 / 2013					Milestone 2 / 2015					Milestone 3 / 2017
	P3. # requests to southern partners to participate in government, donor and/or civil society policy framing processes on internal and regional migration	36				80					300					450
				ACTUALS 2015					348
		Source: Annual reporting of such requests by partners
		Cumulated number of individual-level requests per year by close of accounting year
	Indicator	Baseline / 2011				Milestone 1 / 2013				Milestone 2 / 2015					Milestone 3 / 2017
	P4. # of downloads, citation, database requests	0	0		0	0[1]	0		0	3000			25		5		4500	100	15
				ACTUALS 2015				3435			178		1
		Source: Annual review of downloads of RPC working papers, citations of working papers and articles derived there from, and requests to use databases
		Review to be conducted in July/August by RPC secretariat using google analytics, scholar and recorded database requests.
INPUTS (£)	DFID (£)	Govt (£)				Other (£)					Total (£)					DFID SHARE (%)			Risk Rating
	5,660,254					Medium
INPUTS (HR)	DFID (FTEs)

OUTPUT 1	Indicator	Baseline / 2011				Milestone 1 / 2013				Milestone 2 / 2015				Milestone 3 / 2017				Assumptions
A coherent body of high quality, policy relevant new knowledge on internal and regional migration / High quality and policy relevant knowledge on internal and regional migration	1.1 # of internal and regional migration databases made available to the research community (i) qualitative and (ii) quantitative	[*]		*		*		*		3		3		6		5		Policy makers willing and able to use improved knowledge and evidence in decision making / Political circumstances in RPC countries permit application of insights and users able to participate in policy dialogue and advocacy / Knowledge at high policy levels in development organisations filters down to and informs country programmes/policies
						ACTUALS 2015				1		3
		Source: Annual review
		Review in July/August by RPC secretariat of databases that have been made available to researchers following the UK archive data ethical protocols
	Indicator	Baseline / 2011				Milestone 1 / 2013				Milestone 2 / 2015				Milestone 3 / 2017
	1.2 internal and regional migration policy relevant projects comprising research and related engagement activities completed according to plan	0				8				18				29
						ACTUALS 2015				17
		Source: Annual review
		Monitored by RPC secretariat against GANTT chart
	Indicator	Baseline / 2011				Milestone 1 / 2013				Milestone 2 / 2015				Milestone 3 / 2017
	1.3 # research outputs (peer reviewed articles, working papers, policy briefs, conference papers/presentations and book chapters)	0	0	0	*	0	12	3	*	3	27	12	15	12	40	15	25
						ACTUALS 2015				9	29	20	24
		Source: Annual review
		Monitored by RPC secretariat and partners
IMPACT WEIGHTING	Indicator	Baseline / 2011				Milestone 1 / 2013				Milestone 2 / 2015				Milestone 3 / 2017
50%	1.4 # research outputs that significantly address gender dimensions, including a focus on women and girls	0	0	0	*	0	6	1	*	1	10	6	7	6	15	7	12
						ACTUALS 2015				2	15	7	7
		Source: Annual review NB. Gender was not a focus of Y1 Oct11-Sep12
		Monitored by RPC secretariat and partners
	Indicator	Baseline / 2011				Milestone 1 / 2013				Milestone 2 / 2015				Milestone 3 / 2017				RISK RATING
	Highlighted achievement / 2015	Completion of the Zimbabwe quantitative survey generating a high quality dataset in a context where surveys have been scarce. These data will be a valuable resource for researchers in southern Africa and beyond.																Medium
INPUTS (£)	DFID (£)	Govt (£)				Other (£)				Total (£)				DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)
[*] Greyed out boxes with * denote changes to logframe since last reporting period end 30 Sep 2013. On this page they represent 1.1 a split between types of database, 1.3 and 1.4 an addition of conference papers/presentations and book chapters to reported outputs. On the following page 2.2. adds the element of proportion surveyed and those reporting enhanced understanding.

OUTPUT 2	Indicator	Baseline / 2011			Milestone 1 / 2013					Milestone 2 / 2015			Milestone 3 / 2017				Assumptions
Improved engagement and dialogue with key stakeholders (Policy Makers, Media, NGOs, Migrant organisations and Research Users) to promote research uptake and understanding of research findings related to internal and regional migration and poverty linkages / Effective engagement and dialogue around research findings by policy makers, practitioners and the media	2.1 # of external events attended by RPC partner staff in which pro-poor approaches to regional and internal migration are discussed	20			40					70			100				Political circumstances in selected countries permit application of insights and users are not restricted in participating in policy dialogue and advocacy / Governments have political will and resources to publish policy documents incorporating migration and poverty issues / Multilateral and bilateral agencies are committed to developing evidence based policies
					ACTUALS 2015					190
		Source: Annual reporting of such attendance by partners
		Cumulated number of events by end of accounting year
	Indicator	Baseline / 2011			Milestone 1 / 2013					Milestone 2 / 2015			Milestone 3 / 2017
	2.2 # of key stakeholder representatives participating in RPC external facing events, proportion surveyed and % of these reporting enhanced understanding of pro-poor approaches to migration	30	*	*	200		*	*		600	60%	70%	900		75%	75%
					ACTUALS 2015					990	12%	40%
		Source: Post-event attendance lists and feedback surveys
		Cumulated number of individuals by end of accounting year
IMPACT WEIGHTING	Indicator	Baseline / 2011				Milestone 1 / 2013				Milestone 2 / 2015				Milestone 3 / 2017
30%	2.3 # of RPC external facing events sensitive to gender dimensions of migration	0				7				50				75
						ACTUALS 2015				60
		Source: Annual review of above events
		Cumulated number of individuals by end of accounting year
	Indicator								Baseline 2015					Milestone 2017
	2.4: # of media items published which promote MOOP research	?				?
						ACTUALS
		Cumulated number of items by end of accounting year															RISK RATING
	Highlighted achievement / 2015	Success of RMMRU in clearly influencing two elements of Bangladeshi migration policy: (a) the agreement between the governments of Bangladesh and of Malaysia to permit private contracts for migrants rather than the government-to-government regime that had ruled previously and largely eliminated migration and (b) the MoU with the Saudi government to ensure that female migrants from Bangladesh had access to their mobile phones.															Medium
INPUTS (£)	DFID (£)	Govt (£)				Other (£)			Total (£)					DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 3	Indicator	Baseline / 2011	Milestone 1 / 2013		Milestone 2 / 2015		Milestone 3 / 2017		Assumptions
Strategic capacity of consortium members to conduct research, and of key stakeholders in government and civil society to participate in policy framing processes is enhanced enabling them to collectively shift the terms of the debate / Strengthened capacity of consortium members and partners to design and deliver academically rigorous and policy relevant research, and to share findings with external audiences	3.1 # of interns reporting improved capacity to do research (or engage with it)	0	4		11		17		Policy makers willing and able to use skills and knowledge in decision making / Political circumstances in RPC countries permit application of insights and users able to participate in policy dialogue and advocacy
			ACTUALS 2015		10
		Source: Annual review
		Review in July/August by RPC secretariat; cumulated number of interns
	Indicator	Baseline / 2011	Milestone 1 / 2013		Milestone 2 / 2015		Milestone 3 / 2017
	3.2 # of consortium partner staff reporting improved capacity as a result of attending a training course, placement or fellowship	0	5		40		50
			ACTUALS 2015		37
		Source: Annual review
		Review to be undertaken by partners in July/August each year, and details provided to secretariat; cumulated number of individual event duplets, and excludes secretariat members
IMPACT WEIGHTING	Indicator	Baseline / 2011		Milestone 1 / 2013		Milestone 2 / 2015		Milestone 3 / 2017
20%	3.3 # of boundary partners and key stakeholder representatives who report improved capacity after participation in consortium training sessions	15		50		300		400
				ACTUALS 2015		510
		Source: Post-event feedback surveys
		Cumulated number of individuals
	Indicator	Baseline / 2011		Milestone 1 / 2013		Milestone 2 / 2015		Milestone 3 / 2017	RISK RATING
	Highlighted achievement 2015	The creation and continued functioning of the Ghanaian Media Network on Migration (MENOM). This has resulted in at least 9 stories in mainstream media in Ghana.							Medium
INPUTS (£)	DFID (£)	Govt (£)		Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)