Annual Review Report

Title: Reducing Maternal and Neonatal Deaths in Kenya
Programme Value £ (full life): £64.6m		Review Date: October 2019
Programme Code: 202549	Start Date: 14/11/2013	End Date: 31/03/2023

Summary of Programme Performance
Year	2013/2014	2014/2015	2015/2016	2016/2017	2017/2018	2018/2019
Programme Score	B	A	B	B	A	B
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4264533.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/49358515.xlsx

Abbreviations and acronyms used in this report

ANC Antenatal Care / BEmONC Basic Emergency Obstetric and Neonatal Care / CEmONC Comprehensive Emergency Obstetric and Neonatal Care / CICF County Innovation Challenge Fund / DALY Disability Adjusted life years / DHIS District Health Information System / EmONC Emergency Obstetric and Newborn Care / EmOC Emergency Obstetric Care / GoK Government of Kenya / HMB Human Milk Bank / HSS Health Systems Strengthening / KDHS Kenya Demographic and Health Survey / KEMSA Kenya Medical Supplies Authority / KMC Kangaroo Mother Care	KMTC Kenya Medical Training College / LSTM Liverpool School of Tropical Medicine / MDTF Multi-Donor Trust Fund / MNH Maternal and Newborn Health / MoH Ministry of Health / MPDSR Maternal and Perinatal Death Surveillance and Response / MSI Marie Stopes International / NHIF National Hospital Insurance Fund / QoC Quality of Care / TA Technical Assistance / UBT Uterine Balloon Tamponade / UHC Universal Health Coverage / WB World Bank / WHO World Health Organisation

Glossary of key terms used in this report

EmONC – A health care package required to treat complications that arise from pregnancy and childbirth. At a higher level of care, Comprehensive EmONC includes all Basic EmONC interventions, plus blood transfusion and caesarean section services (WHO).
HIV/AIDS – HIV stands for Human Immunodeficiency Virus. This is the virus that causes AIDS (acquired immune deficiency syndrome). HIV-related indirect maternal deaths are deaths of HIV-positive women caused by the aggravating effect(s) of pregnancy on HIV- where the interaction between pregnancy and HIV/AIDS becomes the underlying cause of death. These are counted as indirect maternal deaths.
Infant mortality – this is the number of deaths under one year of age per 1,000 live births occurring in a given geographical area during a given year.
Maternal death - the death of a woman while pregnant or within 42 days of termination of pregnancy, irrespective of the duration and site of the pregnancy, from any cause related to or aggravated by the pregnancy or its management but not from unintentional or incidental causes (WHO).
Maternal mortality ratio (MMR) – is defined as the number of maternal deaths occurring during a given period per 100 000 live births during the same time (WHO).
Neonatal mortality – this is the number of newborn deaths per 1000 live births. Neonatal death is defined as a death during the first 28 days of life.
Obstetric case fatality rate - The percentage of women admitted to a hospital or an emergency obstetric and newborn care facility with major direct obstetric complications, or who develop such complications after admission and die before discharge.
Obstructed labour - Labour is considered obstructed when the presenting part of the foetus cannot progress into the birth canal, despite strong uterine contractions.
Postpartum haemorrhage (PPH) is defined as a blood loss of 500 ml or more within 24 hours after giving birth.
Skilled delivery – births attended to by a skilled birth attendant - a health professional (nurse, doctor or midwife) who provides essential and emergency care to women and their newborns during pregnancy, childbirth, and the postpartum period.
Stillbirth - is defined as foetal death at or after 20 to 28 weeks of pregnancy. It results in a baby born without signs of life.

A. Summary and Overview

Description of programme: The Reducing Maternal and Neonatal Death in Kenya programme (referred to as the Maternal and Newborn Health (MNH) programme), supports the Government and the people of Kenya to reduce maternal and neonatal mortality through increased access to and utilisation of quality MNH services. The programme supports the delivery of essential health care for pregnant women, newborns and children, improved health system coordination through health sector planning and financing and increased demand for and access to high-quality MNH services. The outputs to date have focused on improving the knowledge and skills of health workers to provide emergency obstetric and neonatal care (EmONC) and strengthening health systems and interventions to increase demand for MNH services. This programme was originally a £75.3 million programme over five-years (2013-2018), however after a DFID wide Portfolio Quality Review (PQR) in 2017, the budget was reduced to £60.6 million. Following the agreed cost extension to March 2023 in 2018, the budget was increased again to £64.6 million. The programme has therefore been running in two five-year phases as described below:

Phase one of the programme (2013-2017)

The first phase of the programme was worth £48.2 million and implemented by three partners: i) the Liverpool School of Tropical Medicine (LSTM), who was responsible for scaling up training in Emergency Obstetric and Newborn Care (EmONC) in 32[1] of Kenya’s 47 counties; ii) the United Nations Children’s Fund (UNICEF) was supporting health systems strengthening (HSS) and demand creation in five counties (Homa Bay, Garissa, Kakamega, Nairobi [in two peri-urban sub-counties] and Turkana[2]); and iii) Options Consultancy Services (referred to throughout as Options), part of Marie Stopes International (MSI) which was supporting HSS and demand creation in one county (Bungoma). UNICEF was also responsible for HSS support to the national level MoH and overall programme management and coordination. Options, together with KPMG, were managing a County Innovation Challenge Fund (CICF) to support testing and scale up of innovative solutions, this work ended in June 2019. Following a DFID Portfolio Quality Review in 2017, a decision was taken to focus on the stronger performing elements of the programme, which resulted in the closure of the UNICEF component at the end of 2017.
[1] The 32 counties were selected to provide a national coverage of the training support, since DFID had supported the other 15 counties through a centrally managed Making it Happen Programme.
[2] These five counties (plus Bungoma) were selected as they had the worst maternal and newborn health indicators, plus very limited support from other donors at the beginning of the programme.

Phase two of the programme (2018-2023)

The second phase of the programme is worth £16.4 million. The funding is being provided to four agencies as follows: (i) the LSTM component has been extended from March 2019 to March 2023, (ii) Options has been contracted from April 2019 to March 2022 to provide technical assistance to strengthen quality of MNH care in four targeted counties. (iii) Funding is being provided to the World Bank administered Multi-Donor Trust Fund (WB-MDTF) for five years from September 2018 to September 2022 to replace the health system strengthening support that was initially provided by UNICEF. The WB-MDTF is funded by the United States Agency for International Development (USAID) - $7 million), DFID (£4 million) and Danish International Development Agency (DANIDA) ($2.3 million) to provide technical assistance and capacity development of Kenya’s devolved health system covering 18 priority counties. (iv) Funding is being provided to the Program for Appropriate Technology in Health (PATH), an international Non-governmental organisation (NGO) for one year (April 2019 to March 2020) to complete the set -up of the first regional human milk bank in Kenya[3].
[3] This was the one CICF-supported intervention which the fund managers felt strongly warranted a bit more support and so additional time-bound support was agreed.

Additionally, separate funding of £300,000 has been allocated for an impact evaluation of the entire programme through Health Research for Action Limited (HERA) from 2015 to 2020. This annual review covers the period from November 2018 to October 2019, which includes some of the work that continued from phase one – specifically the support provided on CICF and all activities under the second phase of the programme.

Key policy changes and implementation challenges that occurred in this review year:

1. Focus on achieving Universal Health Care (UHC) by 2022. This was announced as one of four Government of Kenya (GoK) priority areas following the 2017 election, with implications for national and county health sector financing and access to and demand for health services. UHC is currently being piloted in four counties: Machakos, Kisumu, Isiolo, and Nyeri. The pilot runs for one year from December 2018 and GoK plans to scale up to all 47 counties after the pilot ends in December 2019. If the national rollout of UHC goes ahead in all the 47 counties, it will hopefully provide more resources to the health sector, helping to complement the technical support provided by this programme by addressing some of the health system challenges such as ensuring availability of essential supplies that is not covered by the programme. However, any increased finances are unlikely to be seen before the next financial year, as there was no significant increase in this year’s budget for health.
2. Health care financing issues. Insufficient financing at national and county levels for heath overall, coupled with irregular financial flows, affected timely reimbursement for free maternal care (e.g. Pumwani hospital reported up to six months of delayed payment), the regular payment of health worker salaries leading to strikes and staff absenteeism, and the ability of counties to purchase medicines. These broader health systems challenges all pose major problems for this programme/MNH outcomes in Kenya. Adequate and regular transfer of funding from national to county level is essential to sustain free maternal care and primary health care and to enable counties to address health system weaknesses, including infrastructure and human resources for health.

Summary supporting narrative for the overall score in this review

The programme has scored a B (Outputs moderately did not meet expectations) in this annual review. The focus this year was the successful closure of all activities under the first phase, and a good transition into the second phase. The programme met expectations on Output one “Improved health worker knowledge and skills and sustainable systems for training and mentoring”. However, it did not meet the expected milestones for indicators two and three, on “Increased county and facility capacity to monitor and use data to improve MNH quality of care” and “Increased county capacity to plan, budget for and manage MNH services”. The two indicators did not perform well because of the weaknesses in the health system in this review year. Indicator two was not met because of low staff capacity at the health facility level, and a lack of reporting tools at the health facility level reported this year. Indicator three was not met due to the health care financing challenges experienced in this review year. These ranged from delayed, irregular transfer and partial transfers of funds from the national to the county level, resulting in shortages of essential supplies and health worker strikes, among other challenges.

Key lessons and recommendation for the year ahead:

- Strengthening health systems sustainably requires time in order to be effective. Investing in comprehensive health system strengthening, including intensive competency-based EmONC training improves MNH outcomes. But to sustain gains, longer-term investments are required, and domestic financing strategies need to be developed and implemented by the programme in the remaining phase. Fundamental system constraints contributing to the delays in the transfer of funding from the national to the county level needs to be addressed to help in improving the performance of the programme in the coming year. This is something the DFID Kenya health team is working with the governance team on as an area the new devolution support programme could address (public financial management and fund flows). The current iteration of the programme (in phase two) is not as strategic or holistic as phase one was. This is partly because the amount of money available for the programme extension was far less than was available for phase one. With the contextual challenges already outlined, the programme is quite limited in its ability to really address some of the underlying systemic challenges relating to maternal and newborn mortality. Recommendation.
  - As part the current thinking about DFID Kenya’s health strategy, the team will need to think about how to most strategically address maternal and newborn mortality in Kenya. This could involve a re-design and scale up of this existing programme or the design of a new programme and a phased closure of this programme. For example, a new programme could be designed which provided TA, focussed on supporting health systems strengthening in a few key counties in a more holistic way and complemented the work that the devolution support programme will be undertaking (E.g. on governance and fund flows etc).
  - High-level advocacy by DFID Kenya’s Head of Office and/or high commissioner is also needed to address the challenges relating to insufficient overall domestic financing for health, weak public financial management and delayed fund flows to counties.
  - DFID Kenya health programme partners (from this programme and others) should participate in the national budget planning exercises, and where possible, also at county level to advocate for increased financing for health. (Action for DFID Kenya Basic Services Team).

Competency-based training in EmONC effectively builds the capacity of health workers who provide maternity services but may not be cost-effective if underlying challenges in the broader health system are not addressed. EmONC training supported by the programme has achieved high coverage of health workers in high-volume facilities. However, training staff is of limited value if a) funds are not flowing to counties and so staff are either not being paid/striking or essential drugs/equipment are missing or b) there is a high attrition and turnover of skilled health workers which is a crucial challenge nationwide. Recommendation. All implementing partners can help, especially at the county level to develop a county staff transfer strategy and guidelines, aiming at keeping skilled / trained MNH staff in MNH departments. Also, in order to sustain the effect, regular supportive supervision and mentorship are required, delivered in a manner that is fully integrated in existing systems for service provision and supervision. The programme to develop and present at the national level technical working group a county staff transfer strategy by February 2020 (Action for the programme SRO and LSTM).

Low progress noted in reducing the stillbirth rate. Even though there has been positive progress reported this year in increasing access to skilled care at birth in most counties, the stillbirth rate is not improving. Stillbirths are preventable through high quality antenatal and intrapartum care within the continuum of care for women and children. Recommendation. DFID to work with all the delivery partners to help bring attention to this issue, especially highlighting the importance of delivering proven high impact interventions. Implementing partners can work on strengthening perinatal death audits at health facilities to correctly identify preventable stillbirths, and to understand the causes and institute corrective measures. The programme to develop a case study on stillbirths, and a workplan to support the GoK to address this issue by February 2020 with support from other development partners. High-level advocacy from DFID Kenya’s Head of Office and/or the High Commissioner on the scale of the problem and the number of deaths could help. (Action for DFID Kenya Basic Services Team/ LSTM partners for the coming year of implementation).

Many counties are progressively increasing their funding for the health sector. The programme has provided technical support on planning and budgeting for the counties. This has resulted in an evidenced-based annual work plan and budget. Even though many counties are now allocating a quarter of their budget to health, this is not enough to cover all the required functions. Recommendation. DFID to lead in bringing donors together to review whether or not the levels of finance going to counties now under devolution are sufficient to cover health and other devolved sectors as well. This would help GoK consider its policy position with regards to delivering against the President’s commitment to provide UHC. (Action for DFID Kenya Basic Services Team to be completed by February 2020).

The technical support provided through the MDTF has been valuable at the county level, but its impact at the national level is limited due to slow progress in implementing the national level technical assistance. The objective of the MDTF was to strengthen both the national and county-level health systems, however the interventions to support the national level have not commenced in some areas such as health financing. Recommendation. DFID to second technical advisory capacity into the World Bank to help in progressing HSS support at the national level, including looking at helping the GoK to develop a realistic national blood supply system. (Action for Human and Social Development Team Leader by the November 2019).

Governance and leadership challenges. In this review year – there was a major reshuffle of key technical staff at the national level MoH that were supporting this intervention. There is also a high turnover of key county government officials, requiring implementing partners to repeat efforts to establish relationships and build capacity. The changes and reshuffle have been happening very frequently in Kenya since the devolution of health services in 2013. Since such changes are inevitable, the programmes must develop the ability to work around on-going country political and administrative shifts through regular contact with the GoK officials at all levels.

Widely disseminate the findings from programme impact evaluation. The programme evaluation has produced high-quality evidence showing the effects of the different interventions financed through this programme. These results will be disseminated widely to the GoK and health stakeholders in the coming year to support the delivery of MNH interventions across the country. (Action point for the SRO of the programme to be completed by January 2020).

The following ranges are used to measure achievement against output indicators in this review:
Progress against target	Definition	Score
Indicator achieved in excess of 125%	Significantly exceeded expectations	A++
Indicator achieved between 110-124%	Moderately exceeded expectations	A+
Indicator achieved between 100-109%	Met expectation	A
Indicator achieved between 70-99%	Moderately did not meet expectations	B
Indicator achieved less than 69%	Significantly underachieved on expectations	C

## B: DETAILED OUTPUT SCORING

Output Title	Output 1: Improved health worker knowledge and skills and sustainable systems for training and mentoring
Output number per LF		1	Output Score	A
Impact weighting (%):		30	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of health workers trained in Emergency Obstetric and Newborn Care (EmONC) skills (i) pre-service and (ii) in-service for Garissa, Uasin Gishu, Kilifi, Vihiga, Taita Taveta county / Service Provider responsible - LSTM	220	527 / Scored: A++
1.2. Numbers of (cumulative) pre-service-tutors trained to deliver EMONC training for Garissa, Uasin Gishu, Kilifi, Vihiga, Taita Taveta / Service Provider responsible - LSTM	65	0 / Scored: C
1.3. Number of pre-service institutions delivering competency-based EmONC training within the pre-service curriculum for both (i) nurses, (ii) clinical officers / Service Provider responsible - LSTM	23	18 / Scored: B
1.4. Proportion of counties meeting at least 70% of training costs for Garissa, Uasin Gishu, Kilifi, Vihiga, Taita Taveta / Service Provider responsible - LSTM	60%	60% / Scored: A

Provide supporting narrative for the score

This output has scored an A (Outputs met expectations), since one key indicator greatly exceeded expectations, whilst two indicators were not met. Through this output, funding was provided to LSTM to provide training for health workers to be better able to safely deliver babies, contributing to reducing the high maternal and newborn death rates in Kenya. It involves pre-service training (when health workers are still in training colleges) and in-service training (when health workers have qualified and are working in health facilities). With the start of phase two of the programme – the support provided through LSTM has shifted from conducting the training directly to more of a supportive quality assurance role to the counties, who are now doing their training. This shift is in line with our new approach from shifting from direct service delivery to technical support as part of sustainability and transition.

Output indicator 1.1. This output indicator measures the number of health workers trained in EmONC. EmONC training is a five-day skills and drills competency-based training using a variety of interactive training techniques, tailored to address the most common causes of maternal and newborn mortality. The training covers key interventions (signal functions) that must be available at healthcare facilities designated to provide either comprehensive EmONC (nine signal functions) or basic EmONC (seven signal functions)[4]. The mode of delivery has changed from LSTM delivering trainings directly to them providing quality assurance to the counties to do the trainings. This is an important shift from a sustainability perspective and helps reach a greater number of health workers. This output has exceeded expectations in this review year since LSTM provided the quality assurance of the training that was provided by the counties reaching more health workers with the same quality of training with less resources. The budget for the programme in the second phase is less than what it was in the first phase, and thus programme is now focussing on five selected counties of Uasin Gishu, Vihiga, Taita Taveta, Kilifi and Garissa[5], plus 18 training institutions, though the first phase of this programme had reached 32 counties.
[4] Basic EmONC (BEmONC) functions: (i) Administer parenteral antibiotics;(ii) Administer uterotonic drugs; (iii) Administer parenteral anticonvulsants for pre-eclampsia and eclampsia (magnesium sulphate); (iv) Manual removal of retained placenta; (v) Removal of retained products of conception (e.g., manual vacuum aspiration); (vi) Assisted vaginal delivery (vacuum extraction) ;(vii) Neonatal resuscitation (with bag and mask). Comprehensive EmONC (CEmONC) functions: Perform signal functions i-vi above, plus (vii) Perform surgery (e.g., caesarean section) (viii) Provide blood transfusion.
[5] These five counties were selected because they were not covered by other funders. The five counties were also agreeable to a matched funding arrangement.

Have health workers’ skills improved as a result of training?
The impact evaluation of the programme has confirmed that there is a notable improvement in the skill level of the health workers who received the training. The impact evaluation indicated that the overall confidence levels to carry out any of the nine EmONC signal functions in case of complications was high among surveyed graduates of in-service and pre-service training. Also, during the field visit undertaken by DFID programme team to Uasin Gishu county for this annual review, health workers reported that their knowledge and skills had improved as a result of EmONC training and, for example, they are now able to perform obstetric emergency functions that were previously referred to the referral hospital.

The health workers reported that they had not recorded any maternal deaths this year as a result of the EmONC skills they have received through this programme. They also reported that there were fewer caesarean sections and other surgical interventions because staff were better able to perform assisted vaginal delivery, and that improved skills at lower level facilities had reduced referrals. Also, the county officials that were interviewed, confirmed that the EmONC training had improved health workers’ skills and confidence in performing procedures. However, they also indicated that there is still the need for post-training follow-up since most health workers will lose some of the skills over time especially as the obstetric emergencies, they were trained on do not occur frequently.

Preservice training - Output Indicator 1.2 and 1.3: The programme has supported 18 Kenya Medical Training Colleges (KMTCs) out of the total 65 in Kenya, and two Universities through strengthening and equipping of skills labs and supportive supervision of teaching faculty/clinical instructors. DFID’s implementing partner (LSTM) has been working with the national MoH, central KMTC, and the Nursing Council of Kenya (NCK) to revise the pre-service training syllabus to incorporate EmONC. The process of syllabus review and consequent approval is not yet complete. The NCK expects this to be completed by December 2019. The revised curriculum syllabus is awaiting approval from the Nursing Council. For the targets of both logframes indicators to be achieved, the process of syllabus review must be completed and approved by the NCK. To achieve indicator 1.2 - the revised syllabus needs to be approved nationally – so that LSTM can proceed to train the tutors. The syllabus was not approved because it is still in the process of review by different technical and professional bodies within the MoH, which has taken longer time than was expected.

As part of this annual review process, one KMTC that was visited by the DFID programme team confirmed their appreciation of the support they have received from LSTM. One crucial input that is valued was the equipment that is not only used by the KTMC but also used by the County to train their staff.

Output indicator 1.4. This is a new indicator that was introduced in this review period as part of the sustainability approach of the programme. This indicator measures the proportion of counties that provided resources to meet the cost-share of EmONC training for their staff. Three counties (60%) – Kilifi, Garissa, and Uasin Gishu – have successfully conducted the in-service EmONC training through the cost-sharing model by providing 70% of the cost of the training to date. Prior training for Taita Taveta and Vihiga county was rescheduled from July and is yet to be undertaken due to the delayed budget approval and disbursement of funding for the counties from the national level. Discussions and advocacy initiatives through work plan dissemination and meetings with the counties, were undertaken by LSTM for the counties to embrace the cost-sharing model. Good performance on this indicator shows that with good planning and advocacy – counties are able to provide funding to sustain the delivery of this intervention.

Lessons identified this year, and recommendations for the year ahead linked to this output
All lessons and recommendations linked to this output are indicated below. All recommendations will be considered by LSTM in the implementation of the programme activities for the coming year.

Frequent contact and proactive communication between DFID, implementing partner, and the Ministry of Health is key. In this review year – DFID initiated a regular joint quarterly meeting with all the programme implementing partners, plus also a monthly meeting with each partner. These meetings were useful in ensuring the optimal sharing of lessons learned and synergies among the implementing partners and the MoH. This lesson will be continued in the coming year.

Attrition and turnover of skilled health workers is a key challenge nationwide. To help in solving this issue, the programme implementing partners, especially at the county level can support county staff to develop transfer strategies and guidelines by February 2020, aiming at keeping skilled / trained MNH staff in MNH departments. If transfers are necessary, these should at best happen between MNH departments of different facilities, in order to reduce the volume of EmONC training wasted and increase the VfM of training. Action for LSTM to follow- up on this.

Post-training follow-up is needed. The programme should support the counties to combine different training modalities, like classroom training with mentorship and on-the-job training as an effective, efficient, and less disruptive of capacity building. This training approach should be developed in close collaboration and coordination with the MoH and partners, to ensure the national mentorship package is fully embedded within the national system and structures and builds on the collective experience of partners working in this area. Action for LSTM to follow- up in the coming year.

LSTM to continue work through the Pre-Service Taskforce to ensure the inclusion of EmONC and Maternal and perinatal death surveillance and response into the standard curricula for nursing/midwifery and clinical/medical officers. Also, LSTM should work towards full coverage of pre-service EmONC training in all KMTCs and universities training nurses, midwives, clinical and medical officers. Other partners could be approached to support equipping the skills labs.

LSTM with DFID support to push the Nursing Council of Kenya to fast track the approval of the revised curriculum to ensure the indicators that were not met in this review year can be achieved in the coming year.

Output Title	Increased county and facility capacity to monitor and use data to improve MNH quality of care
Output number per LF		2	Output Score	B
Impact weighting (%):		30	Impact weighting % revised since last AR?	Yes ↓ reduced from 50%

Indicator(s)	Milestone(s) for this review	Progress[6]
2.1 Percentage of (i) maternal deaths and (ii) perinatal deaths (facility level) for which review forms are submitted to the District Health Information System (DHIS2) and (iii) % of health facilities that have made required adjustments to service provision / or management practices based on Maternal & Perinatal Death Surveillance and Response (MPDSR) (17 counties) / Service Provider responsible – World Bank, Options, and LSTM	Bungoma - (i) 100% (ii) 74% / Marsabit (i) 86% (ii) 20% / Kilifi – (i) 100% (ii.) 6% / Samburu (i) 80% (ii.) 20% / Garissa- (i) 90% (ii.) 4% / Lamu- (i) 60% (ii.)10% / Mandera- (i) 68% (ii.) 10% / Tana River-(i) 70% (ii.) 10% / U. Gishu –(i) 95% (ii.) 6% / Wajir –(i) 80% (ii.) 10% / W. Pokot (i)100% (ii.) 12% / Vihiga- (i) 95% (ii.) 6% / Taita Taveta-(i) 75% (ii.) 3% / Kericho-(i) 30% (ii.) 15% / Nandi-(i) 30% (ii.) 15% / Kwale-(i) 30% (ii.) 15% / Mombasa-(i) 30% (ii.) 15%	Bungoma - (i) 100% (ii) 50% / Marsabit (i) 0% (ii) 4% / Kilifi – (i) 0% (ii.) 0% / Samburu (i) 0% (ii.) 6% / Garissa- (i) 67% (ii.) 0% / Lamu- (i) no death (ii.) 0% / Mandera- (i) no death (ii.) 0% / Tana River-(i) 0% (ii.) 0% / U. Gishu –(i) 0% (ii.) 0% / Wajir –(i) 33% (ii.) 0% / W. Pokot (i) no death (ii.) 12% / Vihiga- (i) 100% (ii.) 3% / Taita Taveta-(i) no death (ii.) 0% / Kericho-(i) 0% (ii.) 0% / Nandi-(i) 0% (ii.) 2% / Kwale-(i) 0% (ii.) 0% / Mombasa-(i) 67% (ii.) 0% / Scored: C
2.2 Number of counties[7] with capacity to conduct facility readiness assessment - Service Provider responsible – Options	2 Counties	3 Counties / Scored: A+
[6] Progress on indicator coloured for -- has been “achieved”, (green) “partially achieved” (amber) or “not achieved” (red).
[7] In four counties of Kericho, Nandi, Kwale and Mombasa

Briefly describe the output and provide supporting narrative for the score
Overall this output has scored a B (Outputs Moderately did not meet expectation) even though one milestone was exceeded. Under this output the programme funded three partners to support counties to improve their capacity to monitor and use MNH data. The World Bank supported eight counties[8], whereas LSTM[9] and Options[10] supported five and four counties, respectively.
[8] The counties are: Bungoma, Marsabit, Samburu, Lamu, Mandera, Tana River, Wajir and West Pokot
[9] The Counties are: Uasin Gishu, Vihiga, Garissa, Taita Taveta and Kilifi
[10] The counties are: Kericho, Nandi, Kwale and Mombasa

Indicator 2.1: This indicator measures the percentage of counties that are tracking maternal and newborn deaths in real-time and responding effectively based on the reviews. Maternal and perinatal death surveillance and response (MPDSR) is classified by the World Health Organisation (WHO) as an essential high‑impact element of obstetric and newborn care. The GoK made maternal death notification mandatory in 2004, by putting in place a maternal death review (MDR) system. In this review year – the programme provided technical support to 17 counties through establishing and supporting the MPDSR committees to function. The programme trained 178 health workers on MPDSR across four counties. At the national level, the programme through LSTM supported the national MDSR Secretariat based in the MoH’s Division of Family Health, specifically to coordinate and support counties in the implementation of the MPDSR guidelines.

The performance on this indicator is poor across the counties- with only seven out of 17 counties meeting the expected milestone for a subset of the output milestones. Bungoma County has performed well overall on this indicator. Bungoma county which has been supported through this programme since 2015, is the leading county for review and uploading of maternal and perinatal deaths in Kenya. The good performance in Bungoma County shows that the capacity was well developed through the programme inputs, plus good county ownership. Reason for poor performance on this indicator. Experience collected from health workers as part of this annual review process indicated that most health facilities are now conducting maternal death reviews, but they are not recording through the health information system. While in some counties, the lack of a travel budget allocated to this activity for sub-county level staff is hampering the functionality of monthly MPDSR committees’ meetings.

Use of MPDSR findings to improve the quality of care. In Bungoma county which was visited by the DFID programme team as part of this annual review, MPDSR data has been used to improve care. For example, hospitals have revised on-call systems, taken steps to improve the reliability of power supplies, undertaken blood drives, and provided training in newborn resuscitation, to address problems identified by the MPDSR process.

Indicator 2.2: This is a new indicator that was added to the logframe this year. It measures the capacity of counties to conduct health facility EmONC readiness assessment. EmONC is an integrated strategy to equip facilities to attend to major causes of maternal and newborn deaths effectively. The indicator measures the capacity of the health facility in providing the critical interventions provided to pregnant women and newborns experiencing fatal complications. These interventions include: safe blood transfusion, giving oxytocin and antibiotics, performing caesarean sections, manual removal of the placenta, assisted vaginal delivery, and resuscitation. In this review year, this programme supported three counties through Options with capacity building to help the Sub-County Health Management Team (CHMT) to be able to carry out this assessment regularly and to enable early identification of gaps and solutions. This is a critical intervention that needs to be routinely implemented to ensure that facilities are ready to manage obstetric emergencies. The overachievement on this indicator is because our implementing partner (Options) was able to do this training more efficiently.

The major challenge reported by counties to the DFID programme team during the annual review field visit, is the acute shortages of blood that is affecting many counties. The main problem is a lack of financing for laboratory reagents for screening the blood, which was previously funded by USAID. Besides, most counties lack the requisite infrastructure to collect and store blood. Postpartum haemorrhage (PPH) is the most common cause of maternal mortality in Kenya, accounting for an estimated 40% of all (direct and indirect) maternal deaths. The current acute shortage of blood means that the lives of mothers in need of blood transfusion are at risk.

Other barriers reported by the county teams are poor infrastructure – most maternity hospitals are congested – the infrastructure needs to be expanded. The other issue is the funding flow from the national government to the county. The counties reported delays of between three to six months in receiving the reimbursement for the services provided under the GoK’s free maternity policy from the National Hospital Insurance Fund. The delays in funds disbursements is hindering the timely delivery of health services, since health facilities are not able to purchase the needed supplies on a timely basis.

Lessons identified this year, and recommendations for the year ahead linked to this output are indicated below.
All recommendations will be considered in the implementation of the programme in the coming year.

- The programme to continue to support counties on MPDSR specifically with training for the health facility level. The programme implementing partners to advocate with the counites to include a budget line for this activity in their annual work plan to ensure that the meetings are happening regularly. Action for all implementing partners.
- Expand the activities under indicator 2.2 to all supported counties, since this is a useful process to assess the capacity of the health system regularly. Action for all implementing partners.
- The programme to work with other partners to support the GoK to develop a robust and sustainable blood supply system. Action for DFID and all implementing partners.
- There is a need for a joint donor high level advocacy with the National Government, including National Treasury on fund flow. Action for DFID Basic Services Team.
- The programme should provide evidence-based technical support to counties during the annual budgeting and planning process to help them to use MPDSR findings to inform the budget allocation and use at the county level. Action for all implementing partners.

Output Title	Increased county capacity to plan, budget for and manage MNH services
Output number per LF		3	Output Score	B
Impact weighting (%):		40	Impact weighting % revised since last AR?	Yes, ↑ increased from 20%

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of counties allocating at least 30% of their budget to health in the nine focussed counties / Service Provider responsible – World Bank	4 counties	6 counties / Scored: A++
3.2. Percentage of facilities reporting stockouts of life-saving MNH commodities / Service Provider responsible - World Bank	60% in nine counties	Results are only available for four counties: / Homa Bay: 55%, Migori: 27%, Kilifi:45% / Nairobi:48% / Scored: C
3.3. Number of continuous medical education sessions held on breastfeeding health initiatives for (i) clinical and (ii) non- clinical staff / Service Provider responsible – PATH	6	9 sessions / Score: A++
3.4. Proportion of staff who demonstrate competency in operating the Human Milk Bank (HMB) and use of the HMB guidelines to improve quality control / Service Provider responsible – PATH	50	26 / Scored: C
3.5. Number of quarterly county & facility HMB coordinator meetings held / Service Provider responsible – PATH	4	2 / Scored: C

Provide supporting narrative for the score
This output has scored a B (Outputs Moderately did not meet expectations). The output covers the support that was provided to two agencies – (i) the World Bank-led Multi-Donor Trust Fund (MTDF) (ii) PATH- to complete one project that was outstanding from the CICF. The MDTF was created in 2017 to support the GoK in addressing existing capacity gaps by delivering high-quality Technical Assistance (TA), specifically at the county level and thus, contribute towards promoting equitable delivery of quality health services, especially for women, children, and adolescents.

Indicator 3.1. This indicator measures the commitment and prioritization of health within the planning and decision making at the county level- with a recommendation for at least 30% of the total county budget to be allocated to health, based on an assessment that was done by the World Bank on how much counties were spending on health before 2018 - which was an average of 21%. In this review year, the World Bank-led MDTF provided technical support to 18 counties on planning, budgeting, monitoring, and reporting that was aligned to the country planning and budgeting cycles. They supported the revision of the existing planning and budgeting templates and tools to standardize the budgeting development process at the county level. The revised tools were handed over to the council of Governors for onward dissemination to all counites. Also, the MDTF provided political economy analysis to capture county-specific influences on health planning and budgeting. Out of the 18 supported counties –six counties have allocated at least 30% of their county budget to health. These counties are Embu, Kajiado, Kiambu, Kisii, Machakos, and Muranga.

During the field visit for this annual review, county officials shared their appreciation of the technical support they had received from MDTF on planning and budget. They stated that the support had enabled them to develop evidenced-based and realistic plans and budgets, which helped them to advocate with the county leadership for more budgetary allocation for health. However, they shared concerns about the duration of the support: that it was too short and not enough to enable them to operate independently.

To ensure that counties are budgeting and utilising the resources as per the plan, the MDTF also supported quarterly expenditure tracking. A quarterly expenditure tracking tool and a county public expenditure review tool were developed and piloted in five counties to track health expenditure by line item within each programme. The results from the pilot indicated mixed performance – most counties are not using the resources as per the plan and the budget. The experiences collected from the counties shows that there are several challenges associated with funding flows between the national and county government. These include delayed and irregular transfers, partial transfers, and use of funds for unintended purposes. The counties are not receiving their total allocation in good time to enable them to spend as per the annual work plan. Also, 15% of national revenue allocated to counties may not be enough to allow them to discharge all their duties. To address these challenges, some counties, like West Pokot and Kiambu, have passed legislation to ring-fence health funding that is generated by the health facilities. This allows the retention of user fees collected and ensures the smooth flow of other health funds to service provider accounts from the national level. This initiative is still new, and the programme will monitor its effect in the coming year.

Indicator 3.2. This indicator measures the number of government health facilities that experienced a stockout of any of the 13 RMNCAH life-saving commodities[11]. On request, the MDTF provided technical support to four counties on health commodities management and it did not cover the nine counties, because the technical support was planned to be provided on request by the counties and only four counites requested for this technical support. Part of this support included training of 291 health staff on commodities quantification, forecasting, and supply planning. As reported under output two and indicator 3.1 above, the main challenge contributing to the high stock- out levels of essential medicines, is the delays in the flow of funding from the national to the county level. These delays are hampering service provision across the entire health sector and in some counties health workers have gone on strike due to delays in receiving salaries.
[11] These commodities are- 1. Oxytocin for post-partum haemorrhage 2. Misoprostol for post-partum haemorrhage 3. Magnesium sulfate for eclampsia and severe pre-eclampsia 4. Injectable antibiotics for newborn sepsis 5. Antenatal corticosteroids for – preterm respiratory distress syndrome 6. Chlorhexidine for newborn cord care 7. Resuscitation devices for neonatal asphyxia 8. Amoxicillin for pneumonia 9. Oral rehydration salts (ORS) for diarrhoea 10. Zinc for diarrhoea 11. Female condoms-family planning/contraception 12. Contraceptive implants –family planning/ contraception 13. Emergency contraception – family planning/ contraception.

Indicator 3.3 - 3.5. These indicators cover interventions that were provided under the one project which was continued from the CICF. In this review year, additional funding was provided to PATH to ensure the successful establishment and operation of the Human Milk Bank (HMB) which was launched in March 2019 at the Pumwani Hospital, Nairobi. The focus of this support was to build the capacity of the staff to be able to operate the HMB competently. Two milestones indicators were not met in this review period since the HMB has been operational for only six months, and the milestones were too ambitious for such a short period of implementation. For example, on indicator 3.5 - the programme had only been operational for two quarters and two quarterly meetings had been held. More time is still required to build the competency levels of staff.

The DFID programme team visited the human milk bank as part of this annual review. The hospital team expressed their appreciation of the HMB and indicated that it has been useful to the hospital. They reported that HBM had benefitted 70 newborns, mostly preterm and low birth weight babies. Donated human milk had resulted in better outcomes for the newborns such as shorter hospital stays, less frequent infections, and decreased rates of feeding intolerance. In very high-volume maternity facilities where births of very low birth weight infants are constant, the establishment of a human milk bank is a WHO-recommended upgrade of the standard of care.

Pumwani Hospital is the biggest maternity hospital in Kenya. The hospital provides close to 100 obstetric deliveries daily and serves many of the informal settlements in Embakasi and Kamukunji constituencies in Nairobi. At the time of the visit – it accommodated about 150 newborn infants. The HMB is located within the newborn unit in the hospital and has adequate space for management, registration, and milk donation as well as a clean room for processing and storing the donated milk. Equipment and systems for donor screening, milk pasteurisation and storage were established and appeared to be state of the art, including an elaborate system of registers and consent forms for donors and recipients. Donations exceeded usage, and the storage freezer was filling up with donated milk. DFID provided funding for the HBM equipment, while the county government of Nairobi provided the laboratory equipment and supplies for screening. The HBM has been in operation so far with the regular resources of Pumwani Hospital. This shows good prospects of sustainability beyond the programme.

Lessons identified this year, and recommendations for the year ahead linked to this output:

Fiscal challenges are affecting financial flow between the national and county government. While the capacity of counties to develop evidenced-based plans and budget has been established with the support provided through this programme and other partners, the counties are not able to implement these plans as expected due to delays in receiving funding from the national level. This then means that resources are not utilised well as per the plan and service delivery is disrupted. Recommendation. There is a need for a joint donor high level advocacy with the National Government (MoH and National Treasury) and future collaboration with the DFID-funded devolution programme on fund flow issues. Budget tracking of health expenditures at the county level should be done regularly to check the implementation of the costed work plans. Action for the MTDF and DFID from November 2019.

Context-specific evidence on the impact of human milk banking is necessary to understand if the intervention is cost-effective. While the programme has been successful in establishing the first functioning human milk bank in East Africa, the impact of this project in contributing to reducing newborn mortality in this setting is not yet documented. The programme should support a robust research study to evaluate the effects of human milk banking in the Kenyan context and to establish the feasibility for scale-up. Action for DFID and PATH, a way forward on this to be agreed by December 2019.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The programme theory of change was revised at the output level in this review year to incorporate the adjustment made to the programme as described in section A of this report. The impact of the programme remains to improve maternal and newborn health in Kenya, as measured by reduced maternal and child mortality. The outcome is increased access to and utilisation of quality Maternal and Newborn Health (MNH) services. The outputs in the original business case related to: emergency obstetric and neonatal care (EmONC) training for health workers; health systems strengthening (HSS) to improve management and delivery of maternal and newborn health (MNH) services in six of the 47 counties in Kenya (Bungoma, Garissa, Homa Bay, Kakamega, Nairobi and Turkana); and interventions to increase demand for MNH services in the same six counties. However, the programme was revised in 2018 through a business case addendum to consolidate progress to date with training, strengthening county-level health systems and piloting innovative approaches. The changes included maintaining the direct support for HSS in Bungoma through Options until December 2018, phase-out of direct support through UNICEF and, instead, the provision of Technical Assistance (TA) and capacity-building support to these five counties and an additional 14 priority counties through the World Bank-managed MDTF as indicated in figure one below.

As indicated in the summary page, the programme in the second phase of implementation has a reduced budget, and it is not covering all the components that were covered under the first phase of the programme. The programme is only supporting the supply side- that is, the health facility-based activities, and it is not supporting community demand creation activities. The new outputs are designed to improve health worker knowledge and skills on EmONC, increase the capacity of counties to deliver quality MNH services, which will lead to the outcome - which is the improvement in the quality and ability of health facilities to offer MNH services, and thus the achievement of programme impact of reduced maternal and neonatal mortality in Kenya. The primary programme assumption was that the GoK continues to invest in health systems such as infrastructure and human resources for health and use budgeted funds from other donors efficiently to support MNH (e.g., the World Bank Transforming Health System project). As indicated in the summary page above, the health system was affected a lot in this review year, especially on health financing.
Figure 1. Theory of Change

Inputs and programme activities:

Outputs:

Improved health worker knowledge and skills and sustainable systems for training and mentoring

Increased county and facility capacity to monitor, evaluate, and use data to improve quality of MNH care

Increased county capacity to plan, budget for and deliver quality MNH services

Outcome:

Increased and sustainable availability of quality MNH services

Impact:

Reduced maternal and neonatal mortality in Kenya

TA for counties to manage in-service competency-based EMONC training and follow up
Increased number of counties able to manage and sustain in-service EmONC training

Increased health worker EmONC knowledge and skills

Increased number of KMTCs providing pre-service competency-based EmONC training

TA and equipment for integration of competency-based EmONC training into pre-service training
Increased confidence of health workers at lower level health facilities
Increased number of facilities able to provide all signal functions for BEmONC and CEmONC

TA for development of national mentorship package and county implementation of mentoring
Reduced obstetric case fatality rate

Increased county capacity to assess facility EmONC readiness
Increased number of health workers receiving mentoring support

Fewer maternal and newborn deaths

Reduced stillbirth rate
Increased proportion of maternal and perinatal deaths reviewed and reported by counties

Increased quality of MNH care provided at referral and lower level facilities

Increased proportion of county budgets allocated to health

TA to strengthen national and county MPDSR
Increased proportion of women delivering with a skilled birth attendant

Improved county capacity in quantification, procurement and logistics management

Improved availability of essential MNH commodities in health facilities

TA to strengthen county planning and budgeting
Increased access to MNH services

TA to strengthen county SCM systems

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Table 1: Summary of progress against outcome indicators
Indicator	Baseline 2018	Milestones - 2019	Achieved results - 2019[12]
1. Skilled birth attendance rate	Bungoma:57% / Kilifi: 69% / Samburu:37% / Garissa: 52% / Lamu: 74% / Mandera: 36% / Marsabit: 70% / Tana River: 37% / U. Gishu: 65% / Wajir: 43% / W. Pokot: 43% / Vihiga: 54% / Taita Taveta: 68% / Kericho: 62% / Nandi: 44% / Kwale: 68% / Mombasa: 73%	Bungoma:59% / Kilifi: 71% / Samburu:39% / Garissa: 54% / Lamu: 75% / Mandera: 38% / Marsabit: 72% / Tana River: 39% / U. Gishu: 67% / Wajir: 45% / W. Pokot: 44% / Vihiga: 56% / Taita Taveta: 70% / Kericho: 64% / Nandi: 46% / Kwale: 70% / Mombasa: 75%	Bungoma:68% / Kilifi: 73% / Samburu:41% / Garissa: 53% / Lamu: 83% / Mandera: 59%` / Marsabit: 65% / Tana River: 49% / U. Gishu: 67% / Wajir: 45% / W. Pokot: 50% / Vihiga: 60% / Taita Taveta: 75% / Kericho: 63% / Nandi: 47% / Kwale: 72% / Mombasa: 75%
2. Functioning health facilities supported by the programme that are able to provide (i) BEmONC and (ii) CEmONC[13] for 9 counties (5 LSTM, 4 Options)	1. Kilifi: 17 BEmONC, / 3 CEmONC / 2. Garissa: 27 BEmONC, / 5 CEmONC / 3. U.Gishu: 20 BEmONC, / 1 CEmONC / 4. Vihiga: 19 BEmONC, / 1 CEmONC / 5. Taita Taveta: 21 BEmONC, / 3 CEmONC / 6. Kericho: 0 BEmONC, / 0 CEmONC / 7. Nandi: 0 BEmONC, / 0 CEmONC / 8. Kwale: 0 BEmONC, / 0 CEmONC / 9. Mombasa: 0 BEmONC, / 0 CEmONC	1. Kilifi: 17 BEmONC, / 4 CEmONC / 2. Garissa: 27 BEmONC, / 6 CEmONC / 3. U.Gishu: 21 BEmONC, / 1 CEmONC / 4. Vihiga: 20 BEmONC, / 2 CEmONC / 5. T.Taveta: 22 BEmONC, / 4 CEmONC / 6. Kericho: 0 BEmONC, / 0 CEmONC / 7. Nandi: 0 BEmONC, / 0 CEmONC / 8. Kwale: 0 BEmONC, / 0 CEmONC / 9. Mombasa: 0 BEmONC, / 0 CEmONC	1. Kilifi: 17 BEmONC, / 3 CEmONC / 2. Garissa: 27 BEmONC, / 5 CEmONC / 3. U. Gishu: 21 BEmONC, / 1 CEmONC / 4. Vihiga: 19 BEmONC, / 1 CEmONC / 5. T. Taveta: 21 BEmONC, / 3 CEmONC / 6. Kericho: 0 BEmONC, / 1 CEmONC / 7. Nandi: 0 BEmONC, / 0 CEmONC / 8. Kwale: 2 BEmONC, / 1 CEmONC / 9. Mombasa: 1 BEmONC, / 3 CEmONC
3. OBSTETRIC CASE FATALITY RATE (Percentage of women with obstetric complications admitted to a facility who die) for 9 counties (5 LSTM, 4 Options)	1. Kilifi: 2.2% / 2. Garissa:4.4% / 3. U. Gishu:2.0% / 4. Vihiga:3.5% / 5. Taita Taveta:3.8% / 6. Kericho:3.9% / 7. Nandi:1.8% / 8. Kwale:3.9% / 9. Mombasa: 3.8%	1. Kilifi: 1.3% / 2. Garissa:3.4% / 3. U. Gishu:1.0 / 4. Vihiga:2.5 / 5. Taita Taveta:2.8 / 6. Kericho:2.9% / 7. Nandi:1.0% / 8. Kwale:2.9% / 9. Mombasa: 2.8%	Kilifi: 1.3% / Garissa:5.8% / U. Gishu:0.02% / Vihiga:2.0% / Taita Taveta:0.0% / Kericho:1.6% / Nandi:4.1% / Kwale:1.8% / Mombasa: 4.7%
4. Still Birth Rate; Number of still births per 1000 total births for 17 counties (9 WB, 4 Options, 5 LSTM)	Bungoma:15 / Garissa: 22 / Kericho: 23 / Kilifi: 27 / Kwale: 23 / Lamu: 26 / Mandera:24 / Marsabit: 28 / Mombasa:30 / Nandi: 22 / Samburu: 21 / Taita Taveta: 20 / Tana River: 41 / Uasin Gishu: 18 / Vihiga: 19 / Wajir: 22 / West Pokot: 28	Bungoma:14 / Garissa: 21 / Kericho: 22 / Kilifi: 26 / Kwale: 22 / Lamu: 25 / Mandera:23 / Marsabit: 27 / Mombasa: 29 / Nandi: 21 / Samburu: 20 / Taita Taveta: 19 / Tana River: 40 / Uasin Gishu: 17 / Vihiga: 18 / Wajir: 21 / West Pokot: 27	Bungoma:16.8 / Garissa: 67.9 / Kericho: 54.1 / Kilifi: 23.1 / Kwale: 28.1 / Lamu: 36.3 / Mandera:18.2 / Marsabit: 33 / Mombasa:13.4 / Nandi:31.2 / Samburu: 30.2 / Taita Taveta: 20.6 / Tana River: 24.4 / Uasin Gishu: 42 / Vihiga: 20 / Wajir:19.1 / West Pokot: 22.9
[12] Progress on indicator coloured for -- has been “achieved”, (green) “partially achieved” (amber) or “not achieved” (red).
[13] BEmONC- Basic Emergency Obstetric and Neonatal Care/ CEmONC- Comprehensive Emergency Obstetric and Neonatal Care.

Source of data. District Health Information system (DHIS2).

The performance of the programme against the outcome indicators is mixed as indicated in Table one above. The programme has made good progress against two indicators (one and three) and limited progress on indicator (two and four). Further details explaining the progress is given below.

Indicator 1: This indicator measures the percentage of births attended by a skilled birth attendant (doctor, nurse/midwife and a clinical officer). It is also used to measure the health system’s functioning and potential to provide adequate coverage for MNH services. There is good progress on this indicator in general across the programme focussed counties (15 out of 17 counties met the milestone). The main reason contributing to this good progress is provision of free maternity services provided by the Government of Kenya in the public sector facilities and selected private sector facilities across the country. Also, most supported counties have increased their support for the health sector through the recruitment of additional health workers, and through increasing the number of health facilities with the capacity to provide skilled care at birth among others. The TA provided by the programme on planning and budgeting, training of health workers, and the innovation challenge fund projects have all contributed to improving the capacity of the counties to offer this essential service.

Indicator 2: Increasing the numbers of functioning facilities able to provide BEmONC and/or CEmONC are a result of a mix of factors such as availability of staff with the right skills, available equipment, supplies and infrastructure, and sufficient financial resources to maintain the services. Progress against this indicator has been mixed (only three counties out of nine met the milestone), but it’s largely due to the fact these results are dependent on factors beyond the control of the programme such as a lack of equipment and supplies. For example, the recent World Bank supported-Kenya Health Service Delivery Indicator Survey conducted in 2018 [14] showed that: (i) health service provider knowledge and ability to deliver health services is limited[15]; (ii) high absenteeism persists (52.8%); (iii) access to quality health services is inequitable; and (iv) availability of essential medicines is alarmingly low (54.1%). Also, data collected by the DFID programme team as part of this annual review indicates that the least performed signal functions were manual removal of the placenta and assisted vaginal delivery. The most common reasons for non-performance of signal functions are lack of training and lack of equipment and supplies. As reported in section B of this report on the delays in disbursement of funding from the national to county level is impacting the delivery of this intervention.
[14] Government of Kenya. (2019). Kenya Health Service Delivery Indicator Survey 2018 Report. Report No: 2.
[15] This was assessed across 3 dimensions (% clinical cases): diagnostic accuracy (67.5%); adherence to clinical guidelines (43.5%); management of maternal and neonatal complications (34.5%).

Indicator 3: This is a proxy indicator for the quality of care, and a value of 1% or less is the expected standard. This standard was achieved in two out of nine counties. However, five out of nine counties have recorded a decrease from the baseline. Activities that have contributed to a reduction in direct obstetric case fatality rate under this programme are EmONC training and the use of MPDSR. Availability of EmONC equipment and essential supplies are also crucial to improving the quality of care for women and their newborns. Most facilities are still lacking all the required supplies due to the challenges with delays in disbursement of funds from the national to the county level, as explained in section B of this report.

Indicator 4: The stillbirth rate indicates the quality of care given during labour and delivery and prenatal care. There has been limited progress on this indicator in this review year with only six out of 17 counties meeting the milestone for the year. This is because there is still low uptake of antenatal care services across the supported counties. This limited progress may also be linked to poor quality of care provided during labour and delivery – which the programme is continuing to address through the EmONC training offered. The programme will put more focus on this indicator in the coming year through the MPDSR activities.

Explain major changes to the logframe in the past year
Major changes were made to the logframe in this review year. Specifically, the logframe was revised to align to the programme changes as described above in the theory of change section. The impact indicator targets for maternal and neonatal mortality were updated to be in line with GoK revised goals from 2018 to 2023. The outcome indicators were updated to increase the number of focus counties from six to 17 for outcome indicator 1. New milestones targets were added for outcome indicators two to four. Two outcome indicators were removed from the logframe specifically on the number of (additional) births delivered by a skilled birth attendant and the percentage of caesarean section rate- though the programme is still tracking these indicators through improvement in the skilled birth rate. All outputs indicator targets were updated upwards to take into consideration the programme time extension. The output indicators for the components that closed in 2018 - specifically on the CICF and on the specific health systems activities that were done in Bungoma county were removed from the logframe. The impact weighting for output two and three were adjusted as indicated in section B above.

Describe any planned changes to the logframe as a result of this review

The logframe will be updated after March 2020 to remove the component that is currently supporting the human milk bank once it is completed. The logframe could also be updated with new indicators added to incorporate the recommendations from this report once the DFID Kenya health strategy is approved.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

As described in the summary page of this report, the programme funded the impact evaluation of the funding provided for CICF, training, and health systems. The summative cost-effectiveness analysis of the programe was done in this review year.

Economy. All programme partners track economy measures, and there are several processes and activities in place to track economy measures. For LSTM in this review year - the key costs included salaries and technical assistance (43%), office running costs (12%) and training costs (12%). For Options - the key costs are: grants for CICF projects (39%), fees for staff and consultants (36%), and programme activities such as trainings (17%). The programme recorded a cost savings of £985,357 under the CICF component, since the projects spent less resources but achieved the expected results.

The cost per training offered. Through LSTM – the programme has trained about 11,000 health workers on EmONC to date. The direct cost per trainee (in-service) was estimated by the programme evaluator (HERA) as part of the impact evaluation for the programme to be around £500 (USD 636). This (direct) unit cost per trainee comprises mainly of accommodation and subsistence for trainers and trainees as well as trainers’ fees. In terms of international comparisons, it compares favorably with a course in Rwanda e.g. the cost of short courses (Supply Chain Management) provided by the Regional Centre of Excellence for Vaccines, Immunization and Health Supply Chain Management (RCE-VIHSCM, University of Rwanda): full cost of US$ 1,716 per trainee, of which US$1,000 is for tuition fees (five days course, two trainers and two facilitators). Also, another similar DFID MNH programme that is ongoing in Nigeria recorded the cost of training a health worker as £386 in year two reducing to £211 in year five.

Efficiency. The management cost of the CICF programme was limited to less than 40% of the total CICF cost (management plus grants), which is considered by the evaluation team as reasonable, since this management cost (50% according to Options) was used for capacity building activities rather than for pure management/control activities. The management of the CICF projects was considered as highly cost-efficient by the programme evaluator. This assessment still holds when the management costs incurred by the grantees are added. They were generally budgeted in the range of 15% of the grant value plus the cost of project personnel. The programme has achieved efficiency gains through the training projects, by changing the training model with LSTM from direct delivery of training to working with counties to provide quality assurance of the training given by counties. The training that were provided this year was cost- share between this programme with the three counties indicated in section B under output one - with the counties contributing 70% of the cost.

Cost -Effectiveness of the programme. The programme cost -effectiveness was assessed this year as part of the overall programme evaluation with a focus on Bungoma County. The choice of Bungoma was because it received all the support provided by the programme in all the three output areas. The county received the support through CICF, health systems and through LSTM on training. The cost per Disability-Adjusted Life Year (DALY[16]) averted by the total MNH programme investment (health systems, CICF, and training) in Bungoma County is presented in Table two below. The year 2014 was used as baseline to reflect the fact that the substantial support to Bungoma County started in 2015 and all 2014 initial values and rates/ratios were kept the same in the following years.
[16] The programme’s cost-effectiveness was measured in disability-adjusted life years (DALY), which applies a treatment cost (through medical intervention e.g. provision of skilled delivery at birth) to reduce the number of years lost by a person due to ill-health, disability or early death.

Deliveries in health facilities as a proportion of expected deliveries (based on population estimates) increased by 30% in Bungoma County between 2013 and 2018, from 42% to 72%. This increase of 30 percentage points compared favorably with the average increase of 17 percentage points in the 10 Western Counties (from 49% to 66%) and of 16 percentage points in Kenya. The trend in Bungoma County was driven entirely by the increases in the six programme-supported sub-counties. The increase in facility deliveries was translated into maternal and neonatal deaths averted, and then into DALYs averted. The table below shows that the cost per DALY averted was £328 for the whole period of intervention (2015-2018). This would categorise the programme as ‘highly cost-effective’, a condition that according to WHO is met when the cost of a DALY averted is lower than the annual Gross Domestic Product (GDP) per capita, estimated at GDP £1,286[17] in 2018. The programme cost effectiveness ratios for 2015-18 compare favourably with a similar programme funded by DFID in different regions/townships in Myanmar. The 2015 cost-effectiveness ratio (cost per DALY averted) ranged from US$ 257 (Magway Region) to US$ 1,832 (Chin Region - specific terrain (mountainous area and very low population density).
[17] World Bank data, accessed July 2019

Table 2. Cost -effectiveness analysis for Bungoma County
BUNGOMA (Programme supported Sub-Counties)		2014 (baseline)		2015	2016	2017	2018	Total 2015/18
	Population	1,041,954		1,038,944	1,111,753	1,164,325	1,070,236
	Expected deliveries	41,195		38,597	41,135	44,823	41,740
Baseline (what if expected deaths and DALYs remained at the 2014 level?)	MMR (258/100,000)	258		258	258	258	258
	NMR (19/1000)	19.0		19.0	19.0	19.0	19.0
	Expected maternal deaths	106		100	106	116	108	429
Actual data Bungoma County: Coverage increase	Skilled delivery in health facilities coverage rate	55.4%		59.6%	63.0%	60.8%	79.7%
	Coverage increase (on 2014 baseline)			4.3%	7.6%	5.4%	24.4%

Impact of coverage increase (100% efficacy)	Maternal deaths averted			4.25	8.12	6.25	26.23	45
	Neonatal deaths averted			31.3	59.8	46.0	193.1	330
	Total deaths averted			35.5	67.9	52.2	219.4	375
	Maternal DALYS averted			260	498	383	1,609	2,750
	Neonatal DALYs averted			3,139	6,001	4,618	19,389	33,147
	Total DALYs averted			3,399	6,499	5,001	20,998	35,897
Cost-effectiveness (GBP) (100% attributability to DFID additional funding)	DFID MNH expenditure Budget (GBP)			2,133,115	3,550,266	3,707,522	2,394,074	11,784,977
	Total MNH expenditure (DFID + County) (GBP)			3,623,061	5,464,161	5,922,633	4,738,609	19,748,464
	DFID MNH expenditure/Total MNH expenditure			59%	65%	63%	51%	60%
	Cost per DALY averted (GBP)			628	546	741	114	328
	Cost per death averted			60,065	52,290	70,965	10,914	31,425

Equity. The programme targets disadvantaged communities and counties with poor health outcomes e.g. Bungoma. The programme’s focus on MNH prioritizes women and young children who, in most settings, have worse health outcomes than the rest of the population. Specifically, Bungoma is one of the counties which, in 2014, when the programme started had some of the worst MNH indicators in Kenya, with most basic MNH coverage statistics below the national average. With the support from the programme, the indicators in Bungoma have improved e.g. now recording a skilled delivery coverage of 68% from a baseline of 33% in 2013. The programme in the second phase has now expanded to 17 counties with the lowest MNH indicators in Kenya.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

Even though the programme has not met expectation scored a B in this review year, its VfM performance is positive. As outlined in the table above, the performance across the VFM indicators demonstrates that the MNH programme is providing good value for money against the recommended global cost-effectiveness benchmarks. The programme costs are within the approved budget. The programme in the second phase has shifted from providing direct service delivery to providing more strategic technical assistance to help the country to be able to self-finance its health care. This is in line with the new priorities for DFID Kenya.

E: RISK

Overall risk rating: Major. Due to the findings of this review, the overall risk rating for the programme has been upgraded to major due to the key risks identified below majority of which are outside the control of the programme.
The current implementing partners continuously identify and monitor the risks at national and county level that may impact on implementation. The programme has put in place mitigating measures for the risks that exist, reducing their impact on its performance. All the current partners have risk registers that are reviewed and updated every quarter.
Key risks that are of concern include:

Table 3: Programme key risks in this review year

Key risk	Mitigation strategy/ risk category
Delivery/operational
Governance and leadership challenges resulting from changes in senior MoH staff at national/county level.	Implementing partners have initiated relationship building with new MoH staff to ensure awareness and understanding of programme. / (major pre-mitigation, moderate post-mitigation).
USAID discontinuing funding to the WB MDTF from June 2020, effectively reducing the total budget for the fund from $15million to $10 million.	The World Bank is working to identify additional funders and was able to secure $2 million from DANIDA in this review year. / major pre-mitigation, moderate post-mitigation).
Health financing challenges – delays in funds disbursement from the national to county level- which would lead to shortages of essential commodities and health workers strikes due to delays in receiving salaries.	The programme provided TA to 18 counites on planning and budgeting. The programme supported both public and faith-based facilities for EmONC and MPDSR support. Implementing partners are supporting the counties to prepare for and respond to industrial action. / Fundamental challenges affecting the financial flow from the national level are not yet addressed. / severe pre-mitigation, major post-mitigation).
Health worker rotation and attrition which will continue to affect service delivery and the training provided by the programme	LSTM has an agreed MoU with the counties not to frequently rotate staff who are trained on EmONC. The partner is further exploring ways to ensure continued training of new staff through this programme support. / (major pre-mitigation, moderate post-mitigation).
Fiduciary
Fund leakage and financial mismanagement of innovation funds	Robust financial management oversight ensuring zero tolerance for corruption, transparent processes and policies and extensive grantee due diligence done. / (major pre-mitigation, minor post-mitigation).
Reputational
Grantee exit and transition strategies do not work out as envisaged leading to poor sustainability of project gains such the work on human milk bank	The DFID programme team worked with Options/grantees to enhance execution of the exit and transition plans and is monitoring the progress. Targeted advocacy with the county governments for takeover of some projects. / (major pre-mitigation, moderate post-mitigation).
Safeguarding
Products and services targeting pregnant women fail to adhere to quality standards and a beneficiary experiences an adverse event[18]	The GoK standard operating procedures have been used to manage adverse events and continuous training provided by the programme will ensure that all providers are aware of what to do in case of an adverse event. Referral mechanisms have also been put in place to ensure adverse events are referred to higher level facilities quickly and efficiently.
[18] An adverse event is a medical occurrence temporally associated with the use of a medicinal product, but not necessarily causally related.

Update on partnership principles

The last update of the DFID Partnership Principles, which was conducted in June 2019 concluded that, while the GOK has a strong commitment to poverty reduction, DFID Kenya will not be channelling bilateral funds directly through GOK financial systems until there is evidence of substantial improvements in the integrity of financial management systems. The World Bank, Options and LSTM have worked with national and county governments to deliver shared objectives but have not channelled programme funds directly through GOK systems.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners

The programme is currently being implemented by five partners i.e. HERA, Options, PATH, the World Bank and LSTM. Generally, DFIDs relationship with all the partners has been very positive and productive with DFID coordinating joint quarterly meetings with all the partners. These meetings have proved useful in getting programme updates especially from partners like the WB who submit annual reports as opposed to the other partners who submit quarterly. Two such meetings have been held during the period under review. Some of the partners like the LSTM and Options have engaged in national and county coordination and technical committees like the National MPDSR committee and the Reproductive Health Technical Working Groups. They have also developed strong relationships with the county health management teams in the focus counties. This has allowed them to influence how maternal health is managed in these counties.

Delivery against planned timeframes

Although the programme score for this review has mainly been due to the issues mentioned in section A and B - which some were beyond the control of the programme - some partners like LSTM and the World Bank could have done more to address some of the challenges experienced. A detailed assessment of each partners delivery is as follows:

HERA’s quality of the evaluation reports have been very high and delivered in accordance with the terms of reference.

MSI/Options have demonstrated strong management and technical capacity. Reports are always on time and are clear, accurate and concise. The contract between DFID and MSI to manage CICF ended in June 2019. An accountable grant was signed in April 2019 to support the quality of care in target counties. The last supplier review that was done on Options scored them in the ‘Good Performance’ category with the main positives around effective communication, timely reporting, accurate and timely responses, strong partnerships and good risk management.

PATH has demonstrated good technical capacity in supporting the milk bank in Pumwani Maternity Hospital. They have met the DFID quarterly narrative and financial reporting requirements. Going forward, PATH need to improve on branding as the required recognition is not given to DFID for the support to the milk bank.

LSTM continue to engage in technical committees both at the national and county level. Their performance has been good as they have made progress despite challenges faced at the county level e.g. health workers strikes in some focus counties. LSTM have recognised that their coordination of the various stakeholders especially on the revision of the health workers training curriculum has been slow. To strengthen this, they have increased their in-country presence and capacity by hiring a country director who will lead on coordination with senior official from the GoK and other implementing partners.

The World Bank technical assistance through the Multi-Donor Trust Fund has helped build capacity within the programme focus counties. However, it was noted during the field visit for this annual review that close monitoring of the work of individually contracted experts or partners responsible for distinct systems and service components was not strong at the county level. The World Bank should improve on monitoring especially at the county level and initiate the expected technical assistance for the national level Ministry of Health. Following a request from the World Bank, DFID is planning to second a DFID national health adviser to the World Bank to amongst other things, support the work of the MDTF among others.

Financial Management
As mentioned in the summary section, the programme has been running in two five-year phases.

Phase one (2013-2017): The original programme budget which was £79.8m was reduced to £60.6m following the 2017 DFID Portfolio Quality Review. Some of the funds that became available following the end of the first phase were mainly reallocated to the World Bank, MSI (QoC) and LSTM. By the time phase one was ending in 2017, the programme had spent £48.2m.

Phase two (2018-2023): In this phase, the programme budget was increased to £64.6m bringing the total amount available for this phase to £16.4m. To date, £7.65m has been spent by implementing partners with the balance of £8.75m consisting of £7.6m committed to various partnerships and £1.15m of uncommitted funds. The table below provides a detailed breakdown of spend for each implementing partner in this phase. Good to note that the MANI and HERA components were carried forward from phase one. All the other components began in phase two.

Table 4. Spend to date for partners in phase two

Component	Total Budget (£)	Balance (£)	19/20 Forecast (£)	19/20 Spend to date (£)
LSTM	3,000,000	2,497,343	1,104,279	502,657
MSI/Options (MANI) / (ended in June 2019)	4,976,264	171,255	342,510	171,255
MSI/Options (QoC)	1,500,000	1,386,505	596,989	113,495
HERA	299,970	39,205	225,105	185,900
World Bank	4,000,000	2,000,000	1,000,000	1,000,000
PATH	250,000	231,553	250,000	18,447

The overall quality of the financial management for all the above-mentioned partners has been satisfactory with each partner submitting quarterly financial and expenditure reports to DFID (except the MDTF who report annually). Forecasting performance has been satisfactory for all the partners with little variances.

Asset monitoring: All partners maintain an asset register of all assets procured with DFID funds. These registers are updated and submitted quarterly to DFID. Disposal of assets for closed components has already taken place. A spot check was conducted by DFID’s Risk and Results Officer and the Programme Officer in July 2019 to verify and get assurance that some of the assets transferred as part of the CICF component closure are being put to good use as per the conditions of the transfer. The findings from this spot check were positive, except lack of maintenance of some equipment such as the blood banks. The DFID programme team notified the service provider (Options) on this issue. They promised to take it forward with the suppliers.
Date of last narrative financial report(s)	LSTM Sept 2019; Options Sept 2019; PATH Sept 2019
Date of last audited annual statement (s)	LSTM for FY ending 31 July 2018; Options for FY ending December 2018.

Summary information from recent audits was as follows:
MSI (Options) – The audited financial statement covers the period Jan-Dec 2018. The auditor’s opinion was that MSI's group financial statement and company financial statements give a true and fair view of the state of the group's and of the company's affairs as at 31 Dec 2018.
LSTM - The audited financial statements cover the period for the year ended 31 July 2018. The auditor’s opinion is that proper books of account have been kept and the accompanying financial statements give a true and fair view of the financial position of LSTM as at 31 July 2018.

G: MONITORING, EVIDENCE & LEARNING

Monitoring

All implementing partners have put in place monitoring systems to ensure regular monitoring of the programme delivery. For example – the human milk bank data is collated weekly for monitoring purposes, and to inform practice and processes on a continuous basis. The data is collated from the HMB data registers and tools and compiled into a weekly monitoring database. Also, all implementing partners conducts regular visits to counties to conduct follow-up visits to facilities and monitor programme activities.

The programme was monitored during this review period through quarterly programme management meetings with all partners. The meeting covered the progress on activities carried out during the quarter and planned future activities, programme risks, and progress on follow up action points from the previous annual review. Monitoring also included the submission of quarterly technical, and financial reports against the project logframe from all partners, except the MDTF which provided an annual report. Monthly meetings were held between DFID and all implementing partners.

A field visit was carried out to three counties as part of this annual review by the DFID programme team, which included meetings with county leadership and health personnel at county and sub-county hospitals.

Evidence

As indicated in section A of this report, the HERA consortium was appointed to undertake the summative evaluation of the MNH Programme. The terms of reference specified the expectation that their evaluation would generate more evidence on the effectiveness of strengthening health systems as a means of reducing maternal mortality. The summative evaluation was carried out in 2018-2019 and included a mix of quantitative and qualitative methods such as a household survey, an online-survey, a health facility and services assessment (HFA), focus group discussions (FGD), key informant interviews (KII), observations and document reviews.

Summary of Evaluation findings

Strengthening the health system in Bungoma county
The health system in Bungoma County was substantially strengthened at the end of the DFID funded project in 2018. The project (MANI) delivered better quality MNH services compared to the baseline. The HFA confirmed the overall improvement of MNH services delivery in Bungoma County, while the household survey confirmed the increased accessibility and satisfaction of mothers with the quality of antenatal care (ANC) and delivery care but access and use of PNC did not change. Governance, coordination, partnership, planning and budgeting, health information and service delivery capacity were strengthened. The HFA of the summative evaluation confirmed the increased capacity of health facilities to deliver MNH services. Health system areas where the MANI project was less successful in building local capacity included management of infrastructure (not covered in the MANI project), human resources, health financing (especially at county level) and commodity management at sub-county level. This is because the county did not give the sub-county teams the overall responsibility of the procurement and supply chain, and thus capacity building was not developed at this level.

The household survey study in Bungoma County confirmed an increase in utilisation, perceived quality and satisfaction with MNH care between 2015 and 2018, however with equivocal or negative trends in postnatal care. The main challenge noted was poor reporting at health facility level of postnatal care services. The study also generated evidence of a contribution of the MNH Programme to perceived quality and increased satisfaction, however no evidence for an overall contribution to increased utilisation of MNH services except for facility deliveries. The analysis of national and county trends in MNH service utilisation based on HMIS data, on the other hand, consistently show steeper trends of increase in Bungoma County and especially in the sub-counties supported by the MNH Programme.

Evaluation of the County Innovation Challenge Fund
The CICF aimed at generating innovative solutions or at supporting the scale-up of proven solutions to problems in maternal and neonatal health. The evaluation examined the extent to which the CICF succeeded in funding new solutions and/or the scaling of such solutions. It was not an evaluation of end-user outcomes but delivered a contribution to this objective of the overall MNH Programme evaluation.
The evaluation concluded that the CICF scaling grants supported interventions for maternal and neonatal health in Kenya and contributed to their sustainability. The potential for sustainability and scalability of the solutions funded with innovation grants varied from project to project (see further details in Annex 1).
Evaluation of LSTM training supported through this programme
The objective of the training programme was to (i) increase the availability and improve the quality of Skilled Birth Attendance and EmONC through inventions such as in-service competency-based training in EmONC (as from 2014); and (ii) strengthening EmONC training capacity within pre-service training institutions nationally (as from 2016). A large number of health workers received in-service competency-based training, including almost 11,000 health workers trained in EmONC by LSTM or by government/partners supported by LSTM, which was a major achievement.
According to the online-survey respondents[19], students and health workers’ confidence increased as a result of the training in carrying out the EmONC signal functions. Capacity was built to continue in-service EmONC trainings through the establishment of a pool of trainers, comprising staff from counties, KMTCs, Universities and the national MoH. Building this decentralised capacity was a major achievement of the training programme, facilitating continuing training in EmONC throughout the country if maintained as a priority at national and county level. Sustainability of in-service training was addressed through ensuring pools of trainers but requires a county-based financing strategy. Pre-service training, started in 2016, is not yet sustainable. This still requires full acceptance and integration in the existing curricula of all training schools.
[19] An online survey was sent out via SurveyMonkey to training graduates (for whom an email address was available) since 2014. Of the 7,222 participants the survey was sent to, 5,030 effectively received the survey (the other bounced) and a total of 737 responses (15%) were received.
Overall MNH programme
The summative evaluation of the programme concludes that the programme contributed to establishing MNH as a main priority in the political agenda at national and county levels. The MNH Programme effectively influenced national and county MNH policies and guidelines, through contributions by all three implementing agencies (LSTM, Options and UNICEF). Some main results to which implementing partners contributed together with other partners include the Reproductive Maternal Newborn, Child and Adolescent Health (RMNCAH) investment framework, the Community Health strategy and guidelines, the inclusion of RMNCH score cards, Human Milk Banking and KMC in national policy, the national MPDSR guidelines, the CEMD, the EmONC guidelines and training packages. Bungoma HSS experiences and CICF project results were documented, published and shared in a variety of national and international fora.
Learning

Key learnings from the programme are summarised in section A. As indicated earlier, the evidence and lessons emerging from the 19 CICF innovations were disseminated widely and have influenced policies and practice. Some of the innovations have already achieved government-backed replication and scaling up, while others have received additional funding to continue with further refinement of their conceptual design and testing. The evidence from the programme evaluation have informed the design of the second phase of the programme. The programme will disseminate further the evaluation findings with the national level MoH and with the counties in the coming year.

Table 5: Progress on recommendations from previous reviews

Recommendation	Progress and status of implementation
R1). Detailed lessons learned from this review will be used to inform the future design (next phase) of the programme – which predominantly focuses on support to LSTM and the MDTF.	This was achieved. All the lessons from the previous annual review was used to inform the design of the next phase of the programme -for example, the decision to provide further funding to Options and PATH.
R2). Options and DFID should hold a structured debriefing of the Bungoma programme to review achievements, challenges and lessons learned to inform the next phase of the MNH programme as well as wider programming for MNH within the universal health coverage (UHC) agenda. Lessons learned from Option’s experience of operationalising Linda Mama[20] would be particularly useful for the latter. Lessons learned can also inform future work with the MDTF.	Achieved. Options held various debriefing sessions with the county officials in Bungoma. Options is sharing their experiences in operationalising Linda Mama in Bungoma in the four counties they are working in.
R3). Options’ approach to transition planning has been exemplary and it would be useful to document this so that other programmes can learn from the experience.	Achieved. This has been documented by the programme evaluation and was one of the reasons for extending the work with Options.
R4). Options and KPMG to consolidate and share with DFID learning from the CICF regarding the design and management of innovation challenge funds.	Achieved. Two learning events were conducted (November 2018 and June 2019) to share the evidence from CICF projects.
For the future phase (next five years) of the programme
R5). DFID to explore options for continued funding for one of the CICF-supported innovations which stands out as warranting ongoing support – the human milk bank (HMB) CICF project (either from DFID or other partners) which PATH is implementing, to allow the project to complete set-up, evaluate implementation and impact.	Achieved. Additional funding was provided to PATH for another one year to complete the set-up of the Human milk bank.
R6). DFID to ensure that the logframe (and possibly the theory of change) is revised to reflect changes to the programme. The logframe for the next five years of the programme will be significantly different to the logframe for the past five years of the programme.	Achieved. The logframe and the theory of change for the programme was updated in 2019 and approved by the DFID recommended approval level.
R7). DFID to consider how the impact and sustainability of interventions in the six counties can be tracked after the end of programme activities, including through subsequent annual reviews and the independent evaluation; this could provide useful learning about the sustained impact of different approaches taken by Options and UNICEF.	Not achieved. The programme was not able to extend the contract with the evaluation contractor beyond the current expected end date of January 2020.
R8). DFID to consider whether a PCR for ‘part one’ of the MNH programme (covering what has been achieved at outcome level in the first five years) is a sensible approach given the next five years of the programme (‘part two’) will involve different components and partners.	Achieved. The programme conducted a mid-term review of the programme which covered phase one of the programme.
R9). DFID to extend the contract with HERA to reflect the programme extension (to 2023).	Not achieved. DFID procurement rules did not allow the extension of the contract with HERA.
[20] The Linda Mama programme is the Government of Kenya’s ambition to remove fees from maternity care/make giving birth free in Kenya.

Annex 1: County Innovation Challenge Fund- Grantee Overview
Grantee	Project	Achievements		Lessons learned
Health-E-Net Ltd / Turkana / Budget - £249,851[21][22]	Networked referral management & decision support (telemedicine support for providers)	The project improved the efficiency of referrals both in terms of time and cost. It was estimated that the platform saved the county government more than half a million Kenyan shillings in transportation costs alone, for patients who would otherwise have been referred for care. / As more volunteer providers were recruited on n-REM, the turnaround time for specialist consultation reduced from several days to less than 24 hours.		The project demonstrated that despite challenges such as weak health and ICT infrastructures, telemedicine is feasible in contexts such as Turkana. Telemedicine solutions should however incorporate both online and offline modules and be simple and user-friendly.
International Rescue Committee (IRC) / County- Turkana / Budget-£1 million	Improving access to and demand for quality MNH services through enhanced capacity at facility and community levels (Pambazuka Project)	52 % of pregnant women enrolled in the 10 health facilities completed at least 4 ANC visits as compared to less than 10% at baseline / An increase was observed on proportion of women who delivered at health facilities, with 44.6% of mothers delivering at health facilities compared with only less than 5% in both sub-counties at baseline.		All of the women who utilised the MWHs had a positive birth outcome. Women who stayed in the MWHs reported high levels of satisfaction with their stay and services offered. More information can be found here
Malteser International / County Nairobi / Budget-£249,875	Prepayment system for maternity services in private facilities (M-Afya Project)	There were increases in access to and utilisation of MNH services. Data from Embakasi sub-county (intervention sites) was compared with data from non-intervention sites in the neighbouring Kamukunji sub-county. This comparison showed some differences that could partly be attributed to the project, for example, more women in Embakasi (79%) had attended at least 4 ANC visits compared to those in Kamukunji (74%).		Qualitative data from the survey showed that poor mothers whose household’s main source of income was informal wage-based occupations, were the most likely to use the M-Afya platform. Another interesting finding was that mothers who successfully managed to save for their maternity care through the M-Afya platform, were willing and able to continue saving even after birth. / More information can be found here
Mount Kenya University (MKU) / County-Bungoma / Budget-£338,575	Collaborative newborn support project (newborn care units and training/mentoring)	After the period of implementation lasting from November 2015 to December 2018, the number of health facilities with capacity to provide newborn care increased from two to eight thus improving the quality of care available to newborns, especially those born prematurely.		Findings from the end line evaluation noted and recommended the design of an engagement strategy to ensure buy-in and overcome resistance of adoption by end-users of innovations. Strong collaboration with County Governments is important to address emerging challenges such as staff shortages.
Pathfinder International / County- / Homa Bay / Budget £999,969	Community-facility linked continuous quality improvement project	Forty (40) health facilities were mentored on the formation of QITs and developed their QI plans (of these 20 used the CF-CQI model while the other 20 were comparison sites where standard KQMH was used). / There was also remarkable improvement in community-to-health facility referrals. In total, 11,198 referrals were made to the various facilities by both CHVs and TBAs enlisted in the project (CHVs – 8,279 and TBAs – 2,919). / In the 20 health facilities targeted by the project, the proportion of ANC clients who completed at least 4 ANC visits increased from 40% to 60% despite the momentary drop in Q5 and Q6 during the nation-wide health workers’ strike. / Within the catchment area of the supported health facilities, the proportion of mothers who received skilled birth attendance from health facilities increased from 62% at baseline to 73% at the end of the project. / Additionally, the proportion of deliveries that were monitored with a complete and correct partograph increased from 47% at baseline to 64% at the end of the project.		Recommendations for Policy & Practice: / At the national level, strengthen QI in health by updating the KQMH guidelines to emphasize CF-CQI approaches, with detailed guidance on how to operationalize facility to community linkages. / At the county level, ensure the county budget includes resources for QITs to implement their change initiatives, and include QI efforts into routine county and sub-county supervision. / At the facility level, use data to track and review performance against targets, and embrace QI as a routine part of clinical work and of health facility management. / At the community level, ensure the community is actively involved in QITs, and leverage the good will and contributions of male partners as champions for MNH. / More information can be found here
Research Care and Training Program (RCTP- FACES) / County - Homa Bay / Budget-£249,884	Maximising access and utilisation of maternal and newborn health services using mobile technology	As compared to those not covered by the intervention, mothers who were enrolled on M-ACCESS were: / Five times more likely to have 4 or more ANC visits, / Three times more likely to take 30 to 60 minutes to reach a health facility for delivery, / Two times more likely to have a live birth.		These findings provided sufficient evidence that delay 1 and 2 could be addressed by leveraging a mobile phone-enhanced community text and transport system. The findings were shared with stakeholders within Homa Bay County.
Program for Appropriate Technology in Health (PATH) / County- Nairobi / Budget-£665,000	Mother-baby friendly initiative plus model for human milk banking	By the end of the grant period the project had established the HMB and an official launch conducted, with the attendance of the Governor of Nairobi City County, DFID representative, senior Ministry of Health officials and health implementing partners in Nairobi County. / PATH received a direct DFID grant for an additional one year to focus on consolidating the gains and putting the innovation on a firm path towards sustainability.		A cohesive mechanism for ensuring quality assurance, cross learning and adherence to quality standards will be imperative, perhaps through a future national or regional association of human milk banks / More information can be found here
Gertrude's Children's Foundation / County-Garissa / Budget-£242,496	Enhancing public-private partnerships in the delivery of maternal and newborn health services through technology (Tele Afya Project)	718 mothers and dependents registered on the M-wallet platform. A total of 535 pregnant women utilised the M-Wallet to receive cash transfer. / Over Kenyan shillings 2.5 million from the M-Wallet was utilised by mothers to access maternal and child health services thus removing their financial barriers. / Over 70 remote consultations were conducted through the telemedicine component of the project, resulting in clients receiving better quality care and saving referral costs. / Both Dadaab hospital and Alinjugur Health Centre were mentored by PharmAccess to implement SafeCare.		The combination of the m-Wallet platform and SafeCare standards addressed both the demand and supply side barriers that hindered access to and utilisation of maternal and newborn care services. This resulted in improvements in maternal and newborn health indicators. The telemedicine initiative demonstrated that through an effective public-private partnership model, telemedicine can solve some of the complex barriers Kenya faces to reaching Universal Health Coverage, including addressing equity gaps.
Afya Research Africa (ARA) / County- Homa Bay / Budget -£938,642	Community-owned health facilities (Ubuntu-Afya Kiosk Project)	16 Ubuntu-Afya Kiosks co-owned by and serving rural communities were established. Some of these facilities have been taken over the county government. / All 16 kiosks established social enterprises running alongside health services to generate supplementary revenue. / Over 30,000 clients – including 11,000 mothers and 5,237 children – were served. / The proportion of women who attended four ANC visits during their previous pregnancy within the communities served by Ubuntu-Afya Kiosks rose from 64% to 71% in the study period (Ombech et al, 2018). This was higher than the county-wide average of 47% of women attending four ANC visits.		Findings suggest that the model may have contributed to increasing demand for maternity care in lower level facilities and reducing pressure on referral facilities. However, as the end line evaluation period coincided with a prolonged health worker strike which affected access to services in public health facilities, the evidence is not conclusive. / More information can be found here
African Population and Health Research Centre (APHRC) / County-Nairobi / Budget-£246,507	Using a decision-support smartphone application to enhance CHVs’ effectiveness in reducing maternal complications and newborn deaths	At baseline, only 30% of mothers with newborns were visited at home by a CHV in the intervention site, but this had increased to 63% at end line. In contrast, only 37% women in the control were visited by a CHV after discharge at end line, a small increase from 32% at baseline. / More children in the intervention site (62%) than in comparison site (55%) were exclusively breastfeeding at six months of age. / Slightly more mothers in the intervention site (28%) than in control (21%) reported that a CHV had visited them at home when their baby was ill. / Further, 67% of the mothers in the intervention site said that the CHV had identified danger signs during the home visit, compared to only 38% in the control site.		The CHV decision-support tool demonstrated positive effects in some significant areas of a CHV’s role, including recognition of danger signs and subsequent referrals. The project therefore concluded that implementation of the community health strategy should take advantage of digital solutions such as m-PAMANECH, which could contribute to improving the performance of the CHVs and could be used to transfer essential knowledge and skills. / More information can be found here
Research Care and Training Program (RCTP- FACES) / County-Homa Bay / Budget-£368,885	Electronic maternal child health record	A total of 3043 pregnant women were enrolled onto the e-MCHR platform, received services at the participating health facilities and were tracked as they transitioned between the various MNCH services and points of care. / Community to health facility linkage improved, including community referrals and follow-up of mothers and newborns.		A final evaluation showed increased uptake of MNH services and increased retention of mothers and babies across the continuum of care, for facilities where the e-MCHR was piloted.
Save the Children (SCI) / County- Bungoma / Budget -£822,271	1. Increasing access to quality care for preterm and low birth weight babies through kangaroo mother care / 2. Improving the monitoring of labour through the use of a digital partograph	The proportion of premature newborns enrolled for KMC more than doubled over the project period. / Among the babies enrolled for KMC, the project recorded an increase of those that attained an average daily weight gain of 15-30g/kg/day (from less than 20% to 44% at the end of the project), indicating an improvement in quality of care. / The project supported the Ministry of Health to develop standardised KMC training manuals and registers. / The CICF grant contributed to the growing national momentum for scaling-up KMC. By the end of the project, a total of 21 out of 47 counties were implementing KMC; / The results from this project did not show clear evidence that digitising the partograph would result in an increased proportion of labour monitored using e-partograph or improved birth outcomes. One key conclusion was that health workers’ use of the partograph was influenced by gaps and challenges in the wider health system including adequacy of the staffing in the labour ward, provider skills and attitudes, availability of essential equipment and supplies among other factors.		Improvement in the quality of maternal and neonatal health services will promote the scaling up of KMC services. For KMC to work well, basics of good quality of maternal and neonatal health care should be put in place, including adequate infrastructure (room, beds and related supplies) and medical supplies / The MOH and county governments should take action to equip health facilities so that they can provide high quality routine care. / More information can be found here / The e-partograph was well received by some of the healthcare staff and stakeholders in the local facilities, who saw it as relevant, easy to use and adopt at a wider scale. On the other hand, there were some other health workers who perceived the digital tool as complicated to fill and likely to add to an already heavy workload. / More information can be found here
Massachusetts General Hospital (MGH) / Budget-£821,086	Every second matters for mothers and babies - uterine balloon tamponade	A social enterprise (Centre for Maternal Health Innovation (CMHI) Limited) was set up in Kisumu to locally produce the kits. / Over 8500 ESM-UBT™ kits were assembled at CMHI. About 1,550 kits were distributed in five counties through CICF support (250 in Bungoma, 750 in Garissa, 250 in Turkana, 250 in Kakamega, 50 in Nakuru) and 3000 more sold across the country. Over 10,000 kits were shipped to other African countries. / Training of trainers on the use of UBT was conducted reaching 130 master trainers. The master trainers in turn cascaded the training to 7318 health workers in over 1200 health facilities across the country. / Over 620 of those kits were used to manage unresponsive PPH in various health facilities across the targeted counties. With a 98% success rate, nearly all the PPH cases where UBT was used were saved. / ESM-UBT™ was endorsed by professional associations including the Kenya Obstetrics and Gynaecological Society and National Nurses Association of Kenya. / The MoH recommended UBT as one of the priority interventions in the National Maternal and Newborn Health Implementation Strategy 2016-2018. / In March 2018, the MoH issued a communiqué requesting county governments to roll-out UBT as part of the essential obstetric care package.		To scale up UBT and integrate it into their maternal health services, county governments in Kenya and county health departments should consider implementing the following actions: / Give priority to basic emergency obstetric and new-born care and ensure that the county has enough staff trained in the service / Ensure that health facilities are prepared for timely emergency response, to reduce delays in initiating treatment following the identification or diagnosis of a birth-related complication / Increase budget allocation to health services, to enable staff to receive regular training, and ensure facilities are well equipped with the required infrastructure to provide emergency care / Include UBT as an essential component in the package of health products and technologies for PPH and ensure that funds are allocated for its purchase, / Address socio-cultural issues that lead women to deliver at home / More information can be found here
Centre for Public Health and Development (CPHD) / County- Turkana / Budget- £425,608	Increasing nomadic pastoralist communities’ access to and utilisation of sustainable CEmONC services through digital technologies, medical innovations and clean energy.	Established two solar powered CEmONC centres. / Supported training of a total of 26 healthcare providers / Developed a digital platform of the WHO Surgical Safety Checklist that was aimed at improving confidence and skills of providers. / CPHD committed to continuing implementation of the innovation for another year to get enough case load for outcome level assessment. Grantee is scaling this model to two other facilities in Turkana County		Even though it was too early to assess outcome level results during the project end term evaluation, the progress shows a positive trajectory. Knowledge products from the project including a short video will be useful in advocating for replication here.
Afya Research Africa (ARA) / County- Turkana / Budget- £399,954	Connecting maternal and newborn health providers with young mothers. (Ubuntu Digital Collaboration)	A 16 Ubuntu-Afya Kiosks co-owned by and serving rural communities were established. / A Over 30,000 clients – including 11,000 mothers and 5,237 children – were served. / A The proportion of women who attended four ANC visits during their previous pregnancy within the communities served by Ubuntu-Afya Kiosks rose from 64% to 71% in the study period (Ombech et al, 2018). / A There was a drop in the proportion of women delivering at home, from 17% in 2016 to 11% at endline, and a general increase in women delivering under a skilled birth attendant, from 85% to 90%. / The results showed a notable increase in women seeking care at private facilities (including the Ubuntu-Afya Kiosks), from 3% at baseline to 31%.		The evidence showed that the ARA model of diversifying health care financing had proven to be effective in enabling rural households to access healthcare services. The evidence and lessons were documented and disseminated to county health authorities and stakeholders through MNCH TWG meetings. In addition, the lessons learnt from implementing STONE-HMIS were shared at a national level, with ARA leading a policy dialogue roundtable on inter-operability of eHealth solutions.
Lexlink Consulting / County- Nairobi / Budget-£170,346	Improved tool to standardise supervision of MNH services at health facilities (Boresha Uzazi)	The project was able to achieve its targets in terms of care of the newborn and women with PPH in terms of receiving uterotonics / The project however surpassed its target of women monitored using a partograph from a target of 80% to 98% / The project has received remarkable buy-in and support from both the County and sub-county health teams whereby, the support supervision tool (afyakit) has been rolled out to all sub-counties in Nairobi County. / The grantee was amongst the 30 finalists for the WHO innovation fund.		App development: Need to plan for scale from the beginning to minimise the need to transfer platforms, and to ensure the architecture of the platform is well designed from the beginning. / User needs: The EMONC dashboard was a favourite of various users. Analytics became a distinguishing and key factor of the platform utilisation. / Scaling: There was need to develop an acquisition roadmap and costing methodology to guide engagement with national government and implementing partners.
Management Sciences for Health (MSH) / County- Kakamega / Budget- £421,903	Testing and evaluating a group ANC model (Lea Mimba)	Over the implementation period with CICF funding, the pilot had achieved the following results: / 1,652 women were enrolled in the pregnancy clubs, with an average cohort size of 10.2 women / Effect on ANC retention: The study found an improvement in the proportion of women who made four or more ANC visits in the six facilities. / There was substantial increase in time spent receiving education, in discussion, and connecting with other women and with the health provider. / Satisfaction with ANC services among the survey respondents almost doubled from baseline to endline in all respondents (OR: 1.96; CI: 1.23 - 3.08).		Women across all age groups found the most important aspect of participation in Lea Mimba to be the interactive learning, focusing not only on the what, but also on the why. / Among the key lessons from the project was that group ANC is a “disruptive innovation” that changes how primary health care services are traditionally provided. As a result, careful consideration must be given on how to accommodate this new model, in terms of scheduling, workflow and routines, staffing and rotations, infrastructure, and other management considerations, to introduce, sustain, and scale group ANC. / More information can be found here and here
African Population and Health Research Centre (APHRC) / County- Garissa / Budget-£355,626	CHV Decision Support: Enhancing Community Health Volunteers’ Effectiveness to Improve Maternal and Newborn Health	Majority of the CHVs (87%) and half (50%) of the formal healthcare workers found the application easy to use and to learn. The healthcare workers particularly appreciated that the platform made it easy to track referrals and CHV performance / The use of the device by the CHVs in Kamukunji Sub-County was nearly universal, with 80% of the CHVs interviewed reporting that their most common method of data collection was electronic.		The CHV decision-support tool demonstrated positive effects in some significant areas of a CHV’s role, including recognition of danger signs and subsequent referrals. The project therefore concluded that implementation of the community health strategy should take advantage of digital solutions such as m-PAMANECH, which could contribute to improving the performance of the CHVs and could be used to transfer essential knowledge and skills.