## Logframe 2015-16
PROJECT NAME | Support to the economic recovery of Somalia (SERS)
IMPACT | Impact Indicator 1 |  | Baseline (2014) | Milestone 1 (2015) | Milestone 2 (2016) | Target (2017)
A more stable and prosperous Somalia | GDP per annum | Planned | US$5.7 billion | US$6billion | TBC | TBC
Achieved
|  | Source: IMF/World Bank estimates |  | World Bank currently in process of calculating 2015 GDP. Update once figures confirmed.
RISK RATING: HIGH
OUTCOME | Outcome Indicator 1 |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017) | Assumptions
More effective core economic institutions contributing to socio-economic recovery | Increase in domestic revenue collection | Planned | FG: $96m PL: $0.72m | FG: $96m PL: $0.72m | FG: $120m PL: $1m | FG: $144m PL: $1.3m | i) Political and security situation remains sufficiently stable over time period so as not to significantly undermine reforms/improvements, ii) A combination of internally generated funds and predictable donor financing means the Federal Government of Somalia has sufficient funds to to meet its budgetary needs, iii) Capacity improvements lead to improvements in Ministries' service delivery functions, iv) Projects deliver in the regions, and the programme is not solely Mogadishu focused.
Achieved
|  | Source: PFM project reporting/IMF reporting | Budget out-turn figures provided by FGS. Note: baseline requires updating as latest figures show that revenue in 2014 was in fact $84.3M for FGS. | Don’t have final 2015 outturn figures yet, but WB has confirmed that there has been a 30% increase on 2014 which would bring revenue out-turn for 2015 to $109m
| Outcome Indicator 2 |  | Baseline (Jan 2015) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017)
| Total number of direct jobs created in enterprises supported by the SCORE project | Planned | Project not approved | Project makes first disbursement | 400 | 1000
Achieved
|  | Source: SCORE (PSD) project reporting |  | Project approved by the SDRF in Aug 2015. Grant agreement signed with FGS and SL in February 2016. First disbursement not made by Dec 2015 so milestone missed due to delays in effectiveness. | Will require methodology note from Bank on how jobs are to be counted. This milestone will need updated post-annual review as targets downgraded in final PAD. 2016 target now 1000 jobs.
| Outcome Indicator 3 |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 16) | Target (May 2017)
| Annual increase of intergovernmental transfers to sub-national governments | Planned | No official intergovernmental tranfers to sub national governments | First official fiscal transfer is made to a sub-national government | 10% increase in fiscal transfers | 20% increase in fiscal transfers
Achieved
|  | Source: RCRF project reporting |  | The FGS transferred the an advance of $30,000 to JL and PL in mid-2015, and a subsequent $79,133 for salary costs in JL and non-salary recurrent costs in PL. Payments for salaries in JL should now continue on a regular basis but updated reporting required from the WB to confirm this. | Note: this milestone may need updating to clarify that this means a 10% increase from the 2015 figure.
| Outcome Indicator 1.3 |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 16) | Target (Oct 2017)
| [Not needed for 2015, but may include later] | Planned | N/A | N/A | N/A | N/A
Achieved
Source: if needed
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
39400000
INPUTS (HR) | DFID (FTEs)
RISK RATING: HIGH
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017) | Assumptions
Strengthen core public capacities | Primary expenditure variance* *this indicator measures reduced variance between actual primary expenditure and the original budgeted primary expenditure. (Primary expenditure is defined as total expenditure minus interest on debt and any donor-funded project expenditure) | Planned | 45% | 45% | 35% | 25%*
Achieved
|  | Source: PFM Project Reporting |  | Do not yet have 2015 outturn figures in order to calculate this but signs are that milestone likely to be met. Accumulation of arrears lower than previous years so varience maybe as low as 10%.
*in 2017 budget
| Output Indicator 1.2 |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017)
| Staff appointed to key positions by Capacity Injection Mechnaism through approved procedure (disaggregated by gender and with FGS/ PL breakdown) | Planned | No CIM | 75 (20% women) | 140 (20% women) | 200 (20% women)
Achieved
|  | Source: Capacity Injection project reporting |  | Milestone not met as delays in effectiveness meant that adverts for key positions were not issued until after Dec 2015. In February 2016 FGS filled 7 positions for their first batch of hires and advertised for 55 additional positions. By Feb 2016 Puntland had advertised 60 positions. The first batch of recruits are expected to be in their posts by end April 2016. | Milestone will need to be updated post-annual review as final PAD downgrades results for 2016 due to delay in project effectiveness.
| Output Indicator 1.3 |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 16) | Target (May 2017)
| Number of monthly payroll reports published on MoF websiste | Planned | 4 | 4 | 12 | 12
Achieved
Source: RCRF project reporting
| Output Indicator 1.4 |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 16) | Target (May 2017)
| The share of salaries of the non-security civil servants financed by the government | Planned | 0 | 0 | 30% | 40%
Achieved
|  | Source: RCRF project reporting | 0 indicates that the total cost of civil servants salaries are currently covered by the RCRF. | Over 2015 the FGS took on an increasing share of salary payments - from 24% in March and April 2015 to 34% in June 2015. Awaiting figures for the second half of the year.
Inputs (£) | 18.5M
Inputs (HR)
Total impact weighting (40%) | [6 empty] | RISK RATING: HIGH
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (Jan 2015) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017) | Assumptions
Productivity of high priority sectors enhanced | Private sector investment generated through co-payment by Catalytic Fund recipients | Planned | No Catalytic Fund | Catalytic Fund established | $1.0M | $3.0M | i) Political and security situation remains sufficiently stable over time period so as not to significantly undermine reforms/improvements
Achieved
|  | Source: SCORE (PSD) project reporting |  | Milestone not met due to delays in project effectiveness. However, tenders for the implementing partner for the Calaytic Fund were issued by end 2015 and the WB hoped to have the fund established in Q1 2016. | Milestone may need revising given delays in project effectiveness.
| Output Indicator 2.2 |  | Baseline (2014) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017)
| Contribution of ICT sector to public treasury (through taxes, and licence fees)* *nb this is an element of domestic revenue collection | Planned | 0 | 0 | $1M | $6M
Achieved
|  | Source: ICT sector support project reporting | Note: this baseline requires updating as latest Bank reporting confirms that the ICT sector in fact contributed $4.3M to the public treasury in 2014. | Milestone exceeded - WB reporting states that the ICT sector contributed $4.8M in 2015. However, this was in the form of a negotiated contribution, rather than formal taxation system as envisaged under the draft Communications Act.
| Output Indicator 2.3 |  | Baseline (2014) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017)
| Feasibility and preliminary design studies for specific urban investments completed. ( primary roads in Mogadishu and Garowe; secondary roads in Mogadishu; solid and liquid waste in Hargeisa. | Planned | No design studies conducted | Design studies underway | 2 completed design studies | 5 completed design studies
Achieved
|  | Source: Urban investment project reporting |  | Contracts for the studies have been signed and work will commence immenently. Overall project delayed due to security concerns around operating in down town Mogadishu and Garowe. | Milestone may need revising due to project implementation delays.
| Output Indicator 2.4 |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017)
| Enhanced supervisory capacity within the remittance sector. | Planned | Programme under design | Procurement of the Trusted Agent (TA) underway | TA fully operational | Number of on-site and off-site reports produced by TA (to be updated)
Achieved
|  | Source: 'Supporting Remittance Flows to Somalia' project reporting |  | Milestone met. Procurement of Trust Agent commenced November 2015. IP has now been selected and contract is being negotiated.
Inputs (£) | 20.9M
Inputs (HR) | 1
Total impact weighting (40%) | [6 empty] | RISK RATING: HIGH
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (August 14) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017) | Assumptions
MPF is effectively managed | Enhanced risk management framework for MPF is effectively implemented (Indicators: Risk Management Meetings held and Third Party Monitoring established) | Planned | 0 RMM held. No TPM. | 2 RMM held. TPM IP procured through open tender. | 3 RMM held. X Reports produced by TPM (TBC) | 6 RMM held. X reports produced by TPM (TBC)
|  | Achieved | Achieved
|  | Source: WB six monthly progress report |  | Milestone met. 2 Risk Management Group meetings have been held between Sep and Dec 2015 and the Third Party Monitoring agent is in place.
| Output Indicator 3.2 |  | Baseline (August 14) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017)
| MPF portfolio is gender and conflict sensitive | Planned | Agree with WB that gender and conflict are the key cross cutting issues for MPF | Agree approach to reporting gender mainstreaming and conflict senistivity | 70% of MPF projects receive WB gender flag | 70% of MPF projects receive WB gender flag
|  | Achieved | Achieved | Achieved
|  | Source: WB annual progress report |  | Achieved - November 2015 annual report included % active projects informed by gender and conflict analysis | Gender flag means projects assessed by the WB to systematically consider and address gender inequality.
| Output Indicator 3.3 |  | Baseline (August 14) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017)
| % of live MPF projects receiving a 'satisfactory' rating in annual WB implementation and status reports | Planned | No live projects yet reached annual review stage | 1 project reaches annual review stage and receives satisfactory rating | 90% | 90%
Achieved
|  | Source: WB six monthly progress report and Implementation Status Reports |  | The RCRF is currently the only programme to have reached the annual review stage. In August 2015 (one year after effectiveness) it received a moderately satisfactory rating. RCRF phase II received a satisfactory rating in November 2015, 6 months after effectiveness.
Inputs (£) | 0
Inputs (HR)
Total impact weighting (20%) | [6 empty] | RISK RATING: MODERATE

## Updated LF October 2016
IMPACT | Impact Indicators |  | Baseline (end 2014) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (Dec 2017) | Source | Assumptions
A more stable and prosperous Somalia | I.1. Nominal GDP per annum ($, current prices) | Planned | US$5.7 billion | US$6billion | $6.3 billion | $6.5 billion | IMF SMP reporting, WB SEU annual estimates
|  | Achieved |  | World Bank currently in process of calculating 2015 GDP. Update once figures confirmed.
| I.2. Real GDP growth per annum, % [new indicator Oct 2016] | Planned |  | [not in logframe for 2015 AR] | 3.4% | 2.5% | IMF SMP reporting
Achieved
| I.3. Domestic Revenue as a % current GDP [new indicator Oct 2016] | Planned |  | [not in logframe for 2015 AR] | 3% | 3.8% | IMF SMP reporting
|  | Achieved | [5 empty] | RISK RATING: HIGH
OUTCOME | Outcome Indicators |  | Baseline (Dec 14) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (Dec 2017) | Source | Assumptions
More effective core economic institutions contributing to socio-economic recovery | O.1. Nominal value of domestic revenue collection at federal and regional member state level ($, current prices) [To add Somaliland and others as and when data available] | Planned | FG: $96m PL: $0.72m | FG: $96m PL: $0.72m | FG: $120m PL: $1m | FG: $144m PL: $1.3m | PFM project reporting/IMF reporting | i) Political and security situation remains sufficiently stable over time period so as not to significantly undermine reforms/improvements, ii) A combination of internally generated funds and predictable donor financing means the Federal Government of Somalia has sufficient funds to to meet its budgetary needs, iii) Capacity improvements lead to improvements in Ministries' service delivery functions, iv) Projects deliver in the regions, and the programme is not solely Mogadishu focused.
|  | Achieved | Budget out-turn figures provided by FGS. Note: baseline requires updating as latest figures show that revenue in 2014 was in fact $84.3M for FGS. | Don’t have final 2015 outturn figures yet, but WB has confirmed that there has been a 30% increase on 2014 which would bring revenue out-turn for 2015 to $109m
| O.2. Total number of direct jobs created in enterprises supported by the SCORE project (disaggregated by Women and Youth) | Planned | Project not approved |  | 100 (W: 30; Y: 40) | 500 (W: 150; Y: 200) | SCORE (PSD) project reporting (follows WB methodology)
|  | Achieved |  | Project approved by the SDRF in Aug 2015. Grant agreement signed with FGS and SL in February 2016. First disbursement not made by Dec 2015 so milestone missed due to delays in effectiveness.
| O.3 Private sector investment mobilised (committed as co-payment) by Catalytic Fund recipients [annual target aggregate but reporting should break down by region] | Planned |  |  | $1,000,000 | $4,000,000 | SCORE (PSD) project reporting
|  | Achieved |  | Milestone not met due to delays in project effectiveness. However, tenders for the implementing partner for the Calaytic Fund were issued by end 2015 and the WB hoped to have the fund established in Q1 2016.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | RISK RATING: HIGH
39400000
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 [revised] | Output 1 Indicators |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (Dec 2017) | Source | Assumptions
Strengthened fiscal and public finance management capacity | O1.1. % of annual civil service (non-security sector) wage bill financed by: (i) government; (ii) RCRF [adjusted indicator] | Planned | (i) 0%; (ii) 100% | (i) 0%; (ii) 100% | (i) 30%; (ii) 70% | (i) 40%; (ii) 60%) confirm targets in April 2017 AR | RCRF project reporting; Third Party Monitor reports
|  | Achieved |  | (i) 20%; (ii) 80% According to TPM reports - but note Nov and Dec salaries not paid. Through 2015 the % increased month on month from 24% in March and April 2015 to 48% in October 2015.
| O1.2. Regularity of salary payments: (i) average days between payments during year (ii) # of months outstanding [new indicator - to be explicitly monitored as need improvements but no explicit target set for i] | Planned |  | [new indicator - baseline now set as per what was achieved in 2015 below] | (i) improvement on previous year ; (ii) 0 | (i) improvement on previous year; (ii) 0 | RCRF project reporting; Third Party Monitor quarterly reports
|  | Achieved |  | (i) 37; (ii) 2 months (Nov, Dec)
| O1.3. Non-salary recurrent costs eligible for RCRF funding: (i) $ budget allocated and (ii) % execution of budget [new indicator] | Planned | None. | [new indicator 2016] | (i) $500,000; (ii) 50% | tbc during annual review | RCRF project reporting
|  | Achieved |  | (i) 0; (ii) n/a (establishes baseline)
| O1.4. Implementation of intergovernmental transfers to sub-national governments: (i) number of RMS receiving transfer; (ii) % annual increase in total volume of transfers [adjusted indicator] | Planned | No official intergovernmental tranfers to sub national governments | (i) 1; (ii) n/a | (i) 2 (PL and JL); (ii) 10% | (i) 4 (PL, JL, ISWA, Galmadug); (ii) 20% | RCRF project reporting
|  | Achieved |  | The FGS transferred an advance of $30,000 to both JL and PL in mid-2015, and a subsequent $79,133 for salary costs in JL and non-salary recurrent costs in PL. Payments for salaries in JL should now continue on a regular basis but updated reporting required from the WB to confirm this.
| O1.5. Improved capacity as evidenced by implementation opf TA activities in relevant areas (revenue, treasury mgmt, procurement etc.) FGS, member states and SL [new indicator ] | Planned |  | [new indicator] | Firms recruited to provide revenue and broader PFM TA; Satisfactory assessment of progress against workplans for the year in key areas | Satisfactory assessment of progress in implementing the activities as detailed in the project workplans for 2017 | Comparison of progress reports against workplans for year to inform assessment
Achieved
INPUTS (£) | 18.5M |  |  |  |  | IMPACT WEIGHTING: 40% |  | RISK RATING:
INPUTS (HR)
RISK RATING: HIGH
OUTPUT 2 [NEW] | Output 2 Indicators |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (Dec 2017) | Source | Assumptions
Strengthened public sector management capacity | O2.1. Staff appointed to key positions in FGS and regional member states through approved CIP procedure (cumulative, % women) | Planned | Capacity Injection Project not yet started | TOTAL: 75 (20% women) | FGS: 50 PL: 25 W: 20% | FGS: 90 PL: 50 W: 20% | Capacity Injection project reporting
|  | Achieved |  | Milestone not met as delays in effectiveness meant that adverts for key positions were not issued until after Dec 2015. In February 2016 FGS filled 7 positions for their first batch of hires and advertised for 55 additional positions. By Feb 2016 Puntland had advertised 60 positions. The first batch of recruits are expected to be in their posts by end April 2016. Subsequent targets adjusted
| O2.2 Ministries/agencies with operational HR functions | Planned | 0 | 0 | FGS: 1 PL: 1 | FGS: 3 PL: 3 | CIP Project reporting
Achieved
| O2.3 Improved civil service managmeent functions [new indicator ] | Planned |  |  | Code of conduct developed; Work on pay and grading started | Comprehensive payroll audit completed | CIP project reporting; TPM Monitoring reports
Achieved
| O2.4. Number of monthly payroll reports published on MoF websiste | Planned | 4 | 4 | 12 | 12 | MPF Reporting
Achieved
INPUTS (£) | [5 empty] | IMPACT WEIGHTING: 20% |  | RISK RATING:
INPUTS (HR)
RISK RATING: HIGH
OUTPUT 3 | Output 3 Indicators |  | Baseline (Jan 15) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (Dec 2017) |  | Assumptions
Productivity of high priority sectors enhanced | O3.1. Operationalisation of the SBCF and SMEF [Reporting to cover (i) grant applications received; and (ii) awarded, by region] | Planned | No SBCF or SMEF | Catalytic Fund established | Catalytic Fund operational - reporting to break down information as per indicator | targets to be defined at AR | SCORE (PSD) project reporting
|  | Achieved |  | Milestone not met due to delays in project effectiveness. However, tenders for the implementing partner for the Calaytic Fund were issued by end 2015 and the WB hoped to have the fund established in Q1 2016.
| O3.2 Number of individuals receiving: (i) subsidized BDS or advice financed by the SMEF; and (ii) subsidized TVET or other forms of training financed by the SMEF [Reporting to break down by region] | Planned | No SMEF | n/a | SMEF operational | (i) 100; (ii) 200 | SCORE (PSD) project reporting | i) Political and security situation remains sufficiently stable over time period so as not to significantly undermine reforms/improvements
Achieved
| O3.3 # of diagnostic reports on legal, regulatory, institutional and infrastructure setting aimed at supporting private sector development (cumulative) | Planned | 0 | n/a | 0 | 4 | SCORE (PSD) project reporting
Achieved
| O3.4 Supervisory capacity within the remittance sector: Trusted Agent operations, including # MTBs supervised (on or off-site) | Planned | Programme under design | Procurement of the Trusted Agent (TA) underway | Key regulations drafted for Money Transfer Businesses (Customer Registration, AML/CFT/Operational); supervision of 2 MTBs | Supervision of 4 MTBs | Supporting Remittance Flows to Somalia' project reporting
|  | Achieved |  | Milestone met. Procurement of Trust Agent commenced November 2015. IP has now been selected and contract is being negotiated.
| O3.5. Contribution of ICT sector to public treasury (through taxes, and licence fees) | Planned | 0 | 0 | $10million contribution to domestic revenues; ICT Licensing and taxation framework established | $11M | ICT sector support project reporting
|  | Achieved | Note: this baseline requires updating as latest Bank reporting confirms that the ICT sector in fact contributed $4.3M to the public treasury in 2014. | Milestone exceeded - WB reporting states that the ICT sector contributed $4.8M in 2015. However, this was in the form of a negotiated contribution, rather than formal taxation system as envisaged under the draft Communications Act.
| O3.6 Feasibility and preliminary design studies for specific urban investments completed. (primary roads in Mogadishu and Garowe; secondary roads in Mogadishu; solid and liquid waste in Hargeisa. | Planned | No design studies conducted | Design studies underway | 3 (Mogadishu, Garowe, Hargeisa) | follow on indicators to be determined | Urban investment project reporting
|  | Achieved |  | Contracts for the studies have been signed and work will commence immenently. Overall project delayed due to security concerns around operating in down town Mogadishu and Garowe.
INPUTS (£) | [5 empty] | IMPACT WEIGHTING: 30% |  | RISK RATING:
INPUTS (HR)
RISK RATING: HIGH
OUTPUT 4 | Output 4 Indicators |  | Baseline (August 14) | Milestone 1 (Dec 2015) | Milestone 2 (Dec 2016) | Target (May 2017) |  | Assumptions
MPF is effectively managed | O4.1 Implementation of an effective MPF wide approach to risk management [revised] | Planned | No risk management meetings (RMM); no Third Party Monitor (TPM) | 2 RMM held. TPM IP procured through open tender. | Quarterly RMMs; TPM fully operational with reports shared and discussed; MPF risk management matrix developed | Quarterly RMMs; Quarterly reporting by TPM; evidence of a risk management response to issues raised. | WB progress reports; TPM reports
|  | Achieved |  | Milestone met. 2 Risk Management Group meetings have been held between Sep and Dec 2015 and the Third Party Monitoring agent is in place.
| O4.2 Disbursement and commitment rates: (i) including RCRF; (ii) excluding RCRF [new] | Planned |  |  | use AR to set baseline | see increase in both - especially (ii) | WB annual progress report
Achieved
| O4.3. Transparency and reporting on project activities | Planned |  |  | Improvements evidenced by: improved access to aide memoires, participation in meetings, access to info on websites | Improvements evidenced by: improved access to aide memoires, participation in meetings, access to info on websites | DFID access to these sources of info
Achieved
| O4.4 MPF portfolio is gender and conflict sensitive | Planned | Agree with WB that gender and conflict are the key cross cutting issues for MPF | Agree approach to reporting gender mainstreaming and conflict senistivity | Evidence that gender and conflict issues effectively considered in programme design and implementation; including reporting on % with an active gender marker and % informed by conflict analysis | Evidence that gender and conflict issues effectively considered in programme design and implementation; including reporting on % with an active gender marker and % informed by conflict analysis | WB MPF annual progress report
|  | Achieved |  | Achieved - November 2015 annual report included % active projects informed by gender and conflict analysis
INPUTS (£) | [5 empty] | IMPACT WEIGHTING: 10% |  | RISK RATING:
INPUTS (HR)
RISK RATING: HIGH
Notes:
O.4: this indicator measures reduced variance between actual primary expenditure and the original budgeted primary expenditure. (Primary expenditure is defined as total expenditure minus interest on debt and any donor-funded project expenditure). What about supplementary budgets?

## comments to accompany revision
General approach to revision
- Make sure outcome and output indicators at right levels; output indicators should be things directly within control of the project
- Split output 1 to capture the econ/PFM angle as well as wider public sector mgmt
- Try to capture a greater breadth of the type of activities being undertaken - not just things that can have a number assigned to them
- Aim at producing a new LF that can serve as the basis for the extension – would just need to add new columns rather than a whole load more indicators.
- revise impact weightings to better reflect focus of efforts
Specific changes summary - and questions:
Impact: | GDP - include growth as well as nominal amount
Bring revenue to GDP to this level
Outcome: | O.1 | Nominal revenue targets need reviewing - and good to add in SL
| O.2 | SCORE jobs targets adjusted to realign with updated project plans (project year 1 ends May 2017) - follows WB methodology and may be challenges in aligning to DFID methodology
| O.3 | bring up the investment mobilised indicator from output level where was previously
Note that the LF would still benefit from a higher level indicator to measure capacity improvements - one for next iteration/SERS extension
Split Output 1 into 2 new ones and output weightings changed
Output 1 - econ/PFM | O1.1 | make it annual salary (not most recent month) - have discussed with the WB the need to revisit the sliding scale and put into a medium term context
| O1.2 | Suggest using the wealth of data in the TPM to monitor - would need to ask them to produce FY period average stats
| O1.3 | add in a non-salary RCRF indicator
| O1.4 | inter-gov transfers
| O1.5 | Indicator included to allow DFID to make judgement in progress on implementing the more qualitative aspects of revenue and PFM reform support - link annual assessment to detailed project work plans
output 2 - public sector mgmt | O2.1 | recruitment
| O2.2 | HR function - from MPF Results Framework
| O2.3 | civil service mgmt - capture some of qualitative progress through TA supported activities e.g. payroll audit. Decide on rolling basis
| O2.4 | Kept this indicator as placeholder for transparency - but should push for MPF to be more ambitious going forward e.g. FMS transparency too
output 3 - productive sector | O3.1 | SCORE - implementation of SBCF
| O3.2 | SCORE - implementation of SMEF
| O3.3 | capture TA activities on regulatory environment - define on rolling basis
| O3.4 | Remittances
| O3.5 | Would prefer to focus on qualitative progress (and ICT framework unlikely by end 2016) but kept to align with MPF reporting framework
output 4 - MPF mgmt | O4.1 | reflect an evolving approach to risk mgmt
| O4.2 | financial performance, with and without RCRF
| O4.3 | transparency and reporting - push on Aide Memoires etc. Will be assessed somewhat subjectively by DFID
| O4.4 | gender - capture revised approach pushed by WB through MPF reporting
Others |  | Have dropped indicator on primary expenditure variance - this now more effectively monitored through IMF SMP
Dropped indicator monitoring moderately satisfactory MPF performance as was not adding much

## Graphic
Impact: A more stable and prosperous Somalia
Outcome: More effective core economic institutions contributing to socio-economic recovery
Output 1: Strengthened fiscal and public finance management capacity | Output 2: Strengthened public sector management capacity | Output 3: Productivity of high priority sectors enhanced
- government covering an increasing share of its own wage bill
- improved regularity of salary payments
- i