Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Sixth General Capital Increase (GCI) of the African Development Bank
Programme Value: £43,986,199		Review Date: July 2015
Programme Code: 202280	Start Date: 2011	End Date: October 2018

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	B	A	A
Risk Rating	L	L	L

Summary of progress and lessons learnt since last review
The African Development Bank experienced significant upheaval and disruption due to the return from the Bank’s temporary HQ in Tunis to Abidjan. It is understandable that some of the Bank’s institutional performance targets have been missed during the period of the move.

The Independent Development Evaluation undertook an evaluation of the AfDB’s GCI VI, ADF12 and ADF13 for the period 2010 – 2014 which was published in September 2015. The report said: “Overall, the evaluation found a Bank that is on the move… The Bank is on the road to positive reform, in the direction that both it and its stakeholders want to see. The journey is of course ongoing… Put simply, the evaluation finds a Bank that delivers on its commitments; produces important documents, tools and structures; and launches exciting initiatives. But the evaluation is less able to conclude positively on the Bank’s ability to resource these initiatives, implement them effectively, and bring them to their full conclusion, thus realizing the intended final benefits.” The report reaffirms the considerable progress made and the base created for ongoing improvements in effectiveness and efficiency to be made.

The Bank should be commended for keeping its operations running efficiently and for enduring business continued during this major change process. The Bank has been able to streamline its processes alongside this move through further decentralisation of posts to country and regional office and delegating authority. This enabled the AfDB to reduce the amount of time it takes to approve a project and to make its first disbursement. It has also potentially had a positive impact on project performance as the number PCRs rated satisfactory or higher have increased. In addition the Bank has updated its procurement policy to bring about increased efficiency and effectiveness in the use of resources, and the implementation of this project should start to have an impact in 2016.

Implementation of parts of the Bank’s reform plans was effectively put on hold in 2014 because the Bank’s return to Abidjan. The staff survey was postponed to May 2015. Initial results show that there has been little change in the results even though the Bank underwent significant change during 2014. This can be attributed to the Bank strong communication with its staff during each phase of the move.

Summary of recommendations for the next year
Output 1.
DFID and the UK ED should continue to monitor the decentralisation process and press the Bank to submit the decentralisation MTR and revised roadmap by the end of 2015.

Review the MTR and roadmap to decide on key UK priorities and push these with others to ensure full implementation of the plans and improved portfolio performance and assess whether decentralisation has promoted better Bank-Client relationships.

Output 2.
We should revise indicator 2.2 as this no longer reflects the current reality of the Bank’s HQ being located in Abidjan. We should agree a revised figure by April 2016 in the light of further discussion of the Total Compensation Framework and reflect the outcome of the 2016 Budget discussions.

Output 3.
The UK’s Executive Director should use his role as Vice Chair of the Human Resources and Admin Board Committee to continue to encourage the Bank to address the HR challenges by;
- Push for early resolution to the new business model, decentralisation plan and reorganisation
- Ensuring the HR Director and Corporate Services VP are recruited in good time and to a high standard. Once appointed to work closely with them to define the appropriate HR strategies within the Bank
- Pushing for greater emphasis on dealing effectively with poor performance

The UK should continue to encourage the Bank to consider restraint and cost effectiveness when finalising the new compensation framework, whilst ensuring it reflects the realities of being based in Abidjan and competitive with its market comparators.

Output 4.
The UK should continue to monitor progress of new strategies and initiatives, encouraging the Bank to focus its efforts more strategically in line with the IDEV Evaluation recommendations.

Through the UK ED continue to contribute to Board discussions on corporate, policy, and programme issues and support the Bank’s reform programme.

The UK through the ED and in direct contact with the Bank should ensure that the new strategies for agriculture, energy and [others] are consistent with the Ten Year Strategy and do not extend the scope of the Bank beyond its limits.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Pre-business case
DevTracker Link to Log frame:	http://eks-web-03/AMP/Project/Documents/202280

Outline of the programme
In 2010 the UK subscribed to additional shares in the African Development Bank (AfDB) to enable the AfDB to increase the amount it loans to governments in Middle Income Countries (MICs) and to private sector organisations to reduce poverty and promote economic growth and development.

The AfDB has 78 members, of whom 53 are African regional member countries. The Bank is 60% owned by its regional members The UK at 1.679% is a relatively small shareholder.

The General Capital Increase (GCI) increased its authorised capital by 200% from £22 billion to £65 billion, and it’s paid in capital by 200% from £1.23 billion to £3.484 billion The UK subscribed to 73,434 new shares at a total value of £734 million. Of the allocated shares, 6% are paid for at a cost of £43,986,199.50, in eight equal annual instalments of £5.5 million per year. The remaining 94% or 69,028 callable shares, valued at £689,123,781, have been recorded in DFID’s Annual Resource Accounts as a contingent liability. This investment is proportionate to the UK’s current shareholding at the Bank of 1.679%.

The GCI proposal was supported by a series of reforms to improve the Bank’s operational effectiveness, including strengthening risk management, human resources, the return moving staff HQ to field offices, and a stronger focus on results. It also committed the AfDB to developing new energy and private sector policies, and to transfer at least £35m of its operating profits (known as ‘net income’) each year to the African Development Fund – benefiting the poorest countries on the continent.

The African Development Bank uses its shareholders’ capital to lend to middle-income countries (MICs) at near-market rates, and to lend to and invest in the African private sector. Before the global financial crisis, the Bank loaned and invested around £1.8 billion a year. In 2009, this rose to £5.4 billion to enable the provision of counter-cyclical finance to help countries through the crisis. The AfDB’s response depleted its reserves, and regulations on its levels of capital adequacy meant that without a General Capital Increase (GCI) it would have been unable to do any new lending in 2011 or 2012. The GCI has enabled the Bank to maintain and increase the amount it lends and invests in Africa.

In early 2015 the UK confirmed its intention to purchase additional Bank shares. These shares have become available to non-regional member countries and comprise unsubscribed or forfeited shares previously allocated to non-regional member states, and shares that have become available for subscription by non-regional countries following the ratification of South Sudan as a member of the Bank in order that the Bank maintains the approximate shareholding balance between non-regional and regional member countries 60%:40% respectively. This share acquisition was debated and passed through Parliament in September 2015 and will be captured in next year’s annual review.

The breakdown of the share offer is as follows:
Share issue	Total shares allocated to the UK	Paid-in shares	Paid-in Capital	Callable capital shares	Contingent liability
GCI VI (share transfer)	1453	87	£868,542.75	1,366	£13,637,120
SCI (South Sudan balance)	3157	189	£1,886,834.25	2968	£29,630,286
Total	4610	276	£2,755,377[1]	4334	£43,267,406

As of September 2015, the UK is in possession of 113,020 total shares £1.06 billion contingent liability.

The GCI enables the Bank to increase its investments in the private sector across Africa. The AfDB typically lends and invests around £1 billion a year in the private sector in Africa – 40% of which is in low-income countries (by number of loans). It was envisaged that with a GCI this will be able to double within six years.

The GCI primarily benefits Africa’s MICs eligible to borrow from the Bank on near-market terms: Algeria, Botswana, Egypt, Equatorial Guinea, Gabon, Libya, Mauritius, Morocco, Namibia, Seychelles, South Africa, Swaziland and Tunisia. Many of these face a number of development challenges similar to those of low-income countries, such as fostering sustainable growth, and addressing high unemployment rates and poverty. About 128 million of Africa’s 320 million poor (below USD1/day) live in MICs. Basic health services and basic infrastructure remain inaccessible to a high proportion of the population in a number of MICs, such as Botswana, Namibia, and Swaziland where HIV-AIDS affect more than 15% of the population.

The AfDB focuses on accelerating growth to reduce poverty, working in a small number of core sectors: a) infrastructure, b) private sector development, c) governance, d) higher education, science and technology, and e) regional integration. The AfDB has the potential to scale up and be a major player in developing a Pan-African free trade area – both politically and through its infrastructure investments. A 2012 client survey found that among the range of bilateral and multilateral agencies funding African development, the Bank is ‘a preferred partner’ for 84% of stakeholders, and the number one partner for 22%.

Some of the intended outcomes for the GCI VI period are:
- Population living below $1.25 a day. From 39% in 2009 to 22% in 2015.
- Under 5 child mortality (per 1000 live births). Reduced from 109 in 2009 to 70 in 2015.
- Percentage of population with access to an improved water source. From 64.9% in 2009 to 70% in 2015

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Annual outcome assessment

The AfDB either met or exceeded its planned outcome targets in 2014. However, the Bank only reports results from projects that have submitted a PCR. In 2014 the number of PCRs completed on time fell to 66%, and the number of projects being extended also rose. The robustness of the data is therefore weaker and it is too soon to be confident of any trend.

AfDB enhances its portfolio performance by making key reforms
As part of the GCI VI, the Bank committed to a number of measures to improve the speed and cost effectiveness of programme design and implementation and to give greater emphasis to a number of cross cutting policies. As of 2015 32 of the 34 commitments had been completed, with two outstanding commitments on track for completion by the end of 2015. A number of follow-up initiatives stemming from these reform commitments are closely monitored to ensure they yield tangible results. These initiatives include: a committee chaired by the Bank President to monitor private sector development implementation; a staff survey which focuses on the four pillars of the Bank’s people strategy and a framework of a policy on guidelines on integrity, due-diligence and non-sovereign operations.

Outcome indicator	Planned	Achieved
Country strategy papers rated satisfactory (1 – 6)	2014 - 5	2014 – 5
Percentage of Project completion reports rated satisfactory or higher.	2014 - 76%	2014 – 93%

Indicator 1 Country strategy papers rated satisfactory (1 – 6)
2014 target 5 achieved 5.
2013 target 4.8 out of a possible 6 achieved 4.2
2012 target 95% achieved 100%
2011 92% achieved

The Bank introduced the Readiness Review process to enhance quality at entry of Country Strategy Papers. This involved a desk review by both the Quality Assurance and Results Department at various stages of preparation. In 2012 all CSPs achieved a 100% satisfactory rating.

In 2015, the number of CSPs rated satisfactorily using the CSP readiness methodology were able to meet their targets. Following the Bank CSP readiness review in January 2013, the Bank changed its rating system in anticipation of the new CSP format approved in 2014. This new rating has a stronger emphasis on the priority areas identified in the Ten Year and had an overall rating of 1 (low) to 6. The first year of using the new system, the Bank were unable to meet its target, but in 2014 the Bank was able to do so.

Indicator 2 - Percentage of Project Completion reports rated satisfactory or higher.
The 2014 target for the AfDB was 76%, but achieved 93%. There was a very marked improvement in the proportion of completed projects marked satisfactorily. However, the Bank only reports results from projects that have submitted a PCR. In 2014 the number of PCRs completed on time fell to 66% and the number of projects being extended also rose; often by just one year into 2015. The robustness of the data is therefore weak and it is too soon to be confident of any trend.

Overall output score and description A

Overall the Bank was able to meet most of its output indicators in 2014. However there have been some delays in results as some corporate activities were delayed due to the return of the HQ to Abidjan. For instance the staff management survey was delayed until May 2015, following the move. A number of the targets are the same as the baseline figures set in the 2014 ADER which shows that the Bank decided to focus on keeping operations to remain constant during a potentially disruptive year, rather than set the bar too high and risk disappointing outcomes and outputs for 2014.

Key lessons
The relatively successful move of HQ from Tunis to Abidjan, maintain operations and staff engagement demonstrate that careful management and leadership in change processes is crucial and that realistic targets are required in order not set an organisation up for failure. The return to Abidjan has seen a significant increase in the underlying administrative costs of the Bank. It is not yet known precisely by how much but for 2016 the Bank’s management has requested approval from the Board of a 16% increase for a new staff compensation package associated with the move. This has been significantly higher than expected and a key lesson would be to have engaged and pressed the Bank to cost the move and associated longer term increases in admin budget sooner and within the planning process.

Key actions
The arrival of the new President in September 2015 is likely to bring considerable organisational change and possible policy reprioritisation as well. He has committed to decentralise further, improve portfolio performance and grow the business. These should all have a positive impact on the Bank if managed well. However, the latter will come at an upfront admin cost for which the President has made a request for the Board to approve an 8% increase for 2016 arguing the cost-income ratio would be returned within three years. Through direct contact with the DFID and through our constituency office in the Bank we will seek to ensure that the President’s understandable ambitions to raise the profile of the Bank after a year of being distracted by its return to Abidjan does not undermine the critical requirement of improving the Bank’s agility, responsiveness and reliability to deliver.

Has the logframe been updated since the last review?

Yes. Output 4 is a rolling indicator, changing every year to highlight pieces of work being undertaken by the Bank, which hold a keen DFID interest. These are mostly policies and strategies so as one completes, new work for the next year is inserted. See the recommendations at Output 4 to see what we shall monitor for 2015/2016.

C: DETAILED OUTPUT SCORING
Output Title	Output 1: AfDB decentralises to improve operational effectiveness
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Indicator 1.1 - Operations professional staff based in field offices.	2014 target 40% achieved 50% / 2013 target 35% achieved 39% / 2012 target 35% achieved 36% / 2011 target 30% - achieved 29%	Targets significantly exceeded
Indicator 1.2 - Projects tasked from field offices	2014 target 50% achieved 51% / 2013 target 45% achieved 50% / 2012 target 35% achieved 42% / 2011 target 22% achieved 25%	Targets Met

Key Points
The target for managing projects has been exceeded reflecting progress in implementing the decentralisation of staff to regional and country offices and in adoption of the revised Delegated Authority Matrix (DAM). This has also been at least partly responsible for improvements portfolio performance which is outlined in the Bank’s Africa Development Effectiveness Review (ADER).

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation: DFID will continue to consult with the UK Executive Director in his role as Vice Chair of the Bank’s HR committee to ensure that the Bank takes on the recommendations made in the decentralisation MTR. The Mid-term review of the decentralisation roadmap was delayed and is currently being reviewed.

The proposed draft of the reviewed roadmap was placed before the Board in July 2015 but the UK and others rejected it as it lacked sufficient and robust budget information. The new President is expected to make an announcement on this before the end of 2015.

Recommendations
DFID and the UK ED should continue to monitor the decentralisation process and press the Bank to submit the decentralisation MTR and revised roadmap by the end of 2015.

Review the MTR and roadmap to decide on key UK priorities and push these with others to ensure full implementation of the plans and improved portfolio performance and assess whether decentralisation has promoted better Bank-Client relationships.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	AfDB improves its business processes and practices streamlining its operations
Output number per LF		2	Output Score	B
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Indicator 2.1 Lapse of time between project approval and first disbursement of funds decreases.	2014 target 11 achieved 10 / 2013 target 12 achieved 11 / 2012 target 10 achieved 13 / 2011 target 11 achieved 13	Target exceeded
Indicator 2.2 Decrease in admin costs spent per UA 1million disbursed	2014 target 87k achieved 98k / 2013 target 89k achieved 92k / 2012 target 93k achieved 86k / 2011 target 105K – achieved 79K	Target not met.

Key Points
The IDEV GCI VI Evaluation rated the efficiency of the process for agreeing commitments as satisfactory. It noted “Efficiency of the GCI VI process is reflected in the number and management of meetings, the small number of papers, and the Bank’s internal management of the overall process. Given the resulting 2005 increase in capital, the time and effort invested in this process was cost effective. In addition the process was inclusive – involving all shareholders through the extended Governors Consultative Committee and regional and civil society consultations.” (Different trends were noted for the ADF).

The further welcome reduction in the time required for projects to progress from project approval to first disbursement reflects the impact of positive steps such as decentralisation and a greater focus on solving problem projects.

The 2015 budget approved in December 2014 saw a decrease in costs of 4% excluding the costs of the return to Abidjan. Overall according to the Bank’s annual financial reporting, there is an increase in admin spend in 2014 and 2015 due to the additional costs associated with the return of the Bank’s HQ to Abidjan but exact figures are not available.

There will be a permanent increase in the admin budget for 2016, as it is recognised that the HQ move saw it go from one of the cheapest cities in Africa to one of the most expensive. The cost of having the Bank’s HQ in Abidjan will need to cover a revised compensation package that can ensure competitiveness within the market to attract and retain good quality staff. Nevertheless, the Bank have been slow to share information on the cost of the move and likely impact on the admin budget. This will affect expectations against indicator 2.2.

The UK supported the IDEV budget evaluation has been incredibly helpful for the Board, management and the new President. The aim of the evaluation was to produce recommendations that will focus on improving the value and effectiveness of the AfDB’s budgeting process, which will in turn improve value for money with the admin budget. This evaluation was funded from DFID’s TCFA project, which due to a number of delays in nailing down the final details of the Framework Arrangement meant that project approvals and funding releases were delayed until late 2014. The Evaluation is due to be completed in 2016.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation: Management should continue to work towards improved disbursement performance by continued focus on improving project readiness, fine-tuning and implementing the measures in the Decentralization Roadmap to strengthen FOs, reducing the number of aging operations and accelerating portfolio clean-up. We should also push management to explore ways to improve project coordination and resource management as well as support clients in order to strengthen their capacity in areas such as project design, project preparation, and financial management.

As noted above, the Bank has made progress across the reform agenda (both institutional and programme related) but to varying degrees. We should continue directly and with others to encourage further progress.

Recommendation
We should revise indicator 2.2 as this no longer reflects the current reality of the Bank’s HQ being located in Abidjan. We should agree a revised figure by April 2016 in the light of further discussion of the Total Compensation Framework and reflect the outcome of the 2016 Budget discussions.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 3: AfDB improves efficiency by improving HR management
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Indicator 3.2– Staff engagement index %	2014 target 64% achieved 64% / 2013 target 62% achieved 61% / Baseline 53% in the year 2012.	Target met.

Key Points
The Employee engagement Index and Managerial Effectiveness Index are used to measure the Bank’s People Strategy’s progress. Due to the return of the Bank’s HQ to Abidjan in 2014, the Bank delayed the survey until May 2015, hence the delay in presenting the results to the Bank’s HR committee. The Employee Engagement survey was presented to the board on 29th September 2015.

Overall, the survey results indicate that there were no significant changes between the scores for 2014/2015 when compared to the 2013 results. These results are notable given the amount of change that the Bank went through because of the return to Abidjan. The consultants responsible for disseminating the survey noted that normally scores would deteriorate between 4% to 6% points in such periods of significant change. However, there remains a gap between the Bank and its IFI peers in the degree of staff engagement.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation: The Bank is strong at keeping all shareholders informed of the HR reforms, relocation and decentralisation through the Executive Board and committees. The UK’s Executive Director will continue to use these channels to actively manage risks around these issues and seek opportunities to influence and improve the reforms.

During 2014 there was a proposal developed for a new total compensation framework which was to be aligned to the return to Abidjan and a new HQ reference point for cost of living. This framework was to be the document that determines the Bank’s ability to recruit and retain the best staff it can. The proposal stalled due to lack of agreement at the Board. Since mid-2015 the Bank has had key vacancies in the HR Director and Corporate VP with temporary staff acting until permanent appointments are made. These appointments are unlikely to be made until Q1 2016 at the earliest. This, along with the arrival of a new President means that much of the strategic HR work is effectively on hold while the temporary team manage the basic and core HR functions of the Bank. In addition many of the L&D activities were suspended due to the zero growth budget in 2015. Many of these issues will be addressed when the new appointments are made and they get to grips with the strategic HR issues during the course of 2016. In addition the new President is likely to introduce institutional changes including further decentralisation, a new business model and a reorganisation, all of which will have an impact on the HR reforms, accelerating some but potentially delaying others depending on the final sequencing of reforms.

Recommendations
The UK’s Executive Director should use his role as Vice Chair of the Human Resources and Admin Board Committee to continue to encourage the Bank to address the HR challenges by;
- Push for early resolution to the new business model, decentralisation plan and reorganisation
- Ensuring the HR Director and Corporate Services VP are recruited in good time and to a high standard. Once appointed to work closely with them to define the appropriate HR strategies within the Bank
- Pushing for greater emphasis on dealing effectively with poor performance.

The UK should continue to encourage the Bank to consider restraint and cost effectiveness when finalising the new compensation framework, whilst ensuring it reflects the realities of being based in Abidjan and competitive with its market comparators.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 4: The AfDB strengthens its strategies and policies to guide long-term activities and improve efficiency and effectiveness.
Output number per LF			Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Indicators 4.1 – 4.3 were completed by end 2014.
Indicator 4.4 procurement policy finalised by end of 2015 meets UK priorities		Target met.
Indicator 4.5 the non-sovereign operations policy finalised by end of 2015 and meets UK priorities		Target met.

Key Points
The IDEV Evaluation of GCI VI found a mixed picture; it said that “the Bank has made progress between 2010 and 2014 in all areas highlighted in ADF and GCI discussions, though to varying degrees… While the Bank has been strong on delivering key outputs, it has not yet followed through with the resources, tool, incentives and the will to implement in practice… with less attention paid to following through on ensuring implementation and therefore securing intended outcomes.” It noted the disconnect between those agreeing commitments and those who need to deliver and implement, and that fully costed plans in practical terms did not exist. It recommended the Bank “Focus on fewer and more strategic commitments, with realistic timelines and estimated costs for delivery”.

More specifically, the Bank’s procurement policy document was approved in October 2015. The UK are satisfied that this new policy model is more flexible allowing for a fit for purpose (FfP) procurement solution including use of Government systems or alternative procurement systems based on risk identification. However we will have to wait and see whether these changes will change the culture within the Bank especially enabling staff so that they feel empowered to make better use of their new delegated authority.

The non- sovereign operations policy was approved in November 2014.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation: We should continue to monitor the progress of new strategies, policies and initiatives; contributing to Board discussions through the UK Executive Director at the Bank.

This is an ongoing and regular part of DFID’s direct interaction/cooperation with the AfDB, and will continue to be a priority.

Recommendation: We should ensure the procurement policy and non-sovereign operations policy are concluded in a timely manner. These are opportunities where we can influence the Bank’s thinking and ways of working and support so DFID’s interest in economic development.

Following substantial input from DFID the final procurement policy was approved in October 2015 largely achieving our objectives (see above)

Recommendation: IFID will update the logframe with two new output indicators for 2015 to reflect that the current indicators have been fully delayed: Indicator 4.4 will be “new procurement policy finalised by end of 2015 and meets UK priorities” and 4.5 that “the non-sovereign operations policy finalised by end of 2015 and meets UK priorities.

Indicator updated with progress set out above

Recommendations
The UK should continue to monitor progress of new strategies and initiatives, encouraging the Bank to focus its efforts more strategically in line with the IDEV Evaluation recommendations.

Through the UK ED continue to contribute to Board discussions on corporate, policy, and programme issues and support the Bank’s reform programme.

The UK through the ED and in direct contact with the Bank should ensure that the new strategies for agriculture, energy and [others] are consistent with the Ten Year Strategy and do not extend the scope of the Bank beyond its limits.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

A key cost measure is the annual administrative budget. One of the measures used the Bank is to assess cost efficiency is the administration costs per UA 1 million disbursed. This has continued to fall from UA 109,000 in 2009 to UA 92,000 in 2013. In 2014 the Bank failed to meet its target of UA 87k for every UA1 million spent and increased to UA 98k. The Bank’s increased spend in admin resources in 2014 was due to the additional costs associated with the return of the Bank’s HQ to Abidjan. Admin costs for 2015 excluding the additional costs associated with the move saw a decrease of 4% although the Bank has proposed that in 2016 an off increase by up to 16% due to the higher costs of having the HQ located in Abidjan. This measure has its limitations and does not reflect the relationship between costs and income which is an important factor in the financial sustainability of the Bank. We will consider amending the indicator for VfM under output 2 to reflect the Bank’s desire to ‘grow the business’ in the coming years and use the Cost to Income ratio. The cost to income ratio (CIR) decreased from 43% at the end of 2013 to 39% at the end of 2014; the historical target has been 30%.

The main cost driver is personnel comprising staff remuneration (50%), pensions (13%) and consultants (10%). The Bank has continued with a zero real administrative budget increase every year since the 2011 MAR. This has been achieved even with decentralisation being a major driver of additional costs, e.g. five new field offices in 2011 and two new regional resource centres in 2012. Costs are expected to increase as the Bank attempts to ‘grow the business’ although this should lead to increased income for the Bank.

The Bank has frozen the salaries for all senior staff since the 2011 MAR, the only exception being the President and Executive Directors who received small raises in 2012 - these were the first increases since 2007 and 2008 respectively. The Bank froze its headcount in 2012. This has meant that any new critical staffing requirements in core priority areas have been addressed by internal redeployments or giving up other vacant posts.

In the coming year fundamental reforms will be required to refill vacancies and grow the business of the Bank. This will mean concluding the total compensation framework, adjusting to the higher cost of being in Abidjan while still maintaining cost control and seeing credible plan to grow the business and increase income in the Bank.

VfM performance compared to the original VfM proposition in the business case

The 2011 MAR assessed AfDB as delivering satisfactory VfM (scoring ‘3’ out of a possible ‘4’), identifying particular strengths in assisting clients with public financial management, considering VfM through its systems, procurement (strong systems and publication of data), and keeping admin budget and salary increases under tight control. However, there was little evidence that AfDB directly challenges its partners to subject their decisions to robust VfM criteria. The 2013 MAR Update assessed that the Bank had demonstrated some progress on costs and value consciousness, but the Bank needed to be clearer on how it’s ensuring its policy and programme choices are delivering value for money.

Areas identified in the MAR 2013 Update for further development include directly challenging its partners to subject their decisions to robust VfM criteria; including VfM considerations in all project appraisals, completion reports and/or evaluations; improving performance against indicators where progress renders the Bank off-track to meet its targets - this includes tackling staff attrition rates and expediting the first disbursements once projects have been approved.

DFID will continue to measure the Bank’s organisational and operational efficiency through the Bank’s Results Framework, which is analysed in the Bank’s Annual Development Effectiveness Reports. Based on the above, the UK will proactively push for, and monitor, improvements in the Bank’s management and accountability systems with a strong focus on delivering of results and achieving value for money in programme and administrative spend. This includes the Bank giving greater emphasis in its procedures for programme design to require Bank staff to provide different options when designing programmes and challenging and supporting implementing partners justify the value for money in their policy and programme options

Assessment of whether the programme continues to represent value for money

In February 2011 DFID published the Multilateral Aid Review of the African Development Bank. The review was primarily an assessment of the AfDB, but in other parts of the review it was impossible to distinguish between the AfDB and the AfDF as a whole, such as on Bank-wide reforms and policies.

The MAR found that the AfDB represented good value for money for the UK having a critical role in meeting UK and international objectives and being integral to the UK’s support to poor African countries. The MAR Update found that the Bank had made some progress in addressing the areas identified for reform.

Some of the factors that support the conclusion that the AfDB is good value for money for the UK’s investment are:

•The Bank has a significant focus on economic development, and following the Ten Year Strategy, increased focus on growth, infrastructure, regional integration and a strong focus on wealth creation.
•The AfDB’s unique African ownership and its ability to work closely with African governments are seen as key strengths, enabling the AfDB to focus on delivering in critical sectors in 38 of Africa’s poorest countries.
•On the management side the joint AfDB/AfDF Results Management Framework is well focused and has clear inputs and expected outcomes that are continually being developed.
•The AfDB has an independent evaluation department, whose findings are often acted upon and a strong governing body that holds management to account.
•The AfDB’s funding allocation process is seen as transparent, their procurement systems are robust, and cost and value consciousness is encouraged at the project design stage.
•The AfDB offers strong client support particularly in the areas of project design, country strategy consultations and public financial management.
•Finally the Bank continues with its reform agenda which continues to build on its strong reform record.

Quality of financial management

The main financial oversight functions, apart from the Board of Directors, are the responsibility of the following three Bank units: the Office of the Auditor General (independent financial assurance), the Ethics Office (ethical behaviour), and, the Integrity and Anti-Corruption Department (mainstreaming integrity programmes in Bank operations and investigating suspected fraud). The three offices work at arms-length from the rest of the Bank (operations and management).

The Bank is rated by all of the four major rating agencies (Standard & Poor, Moody’s, Fitch Ratings and the Japan Credit Rating Agency – all four have regular update reports on the Bank on their websites) to have sound financial management processes in place. The rating agencies’ positive rating reflects the Bank’s strong financial position (based on sound capital adequacy) and prudent financial and risk management policies. This, together with a positive assessment on its financial systems by the MOPAN 2012, provides external evidence of the Bank’s financial structures, systems and processes.

Audit processes

The Bank is considered by external reviewers to have good audit procedures. The 2012 Multilateral Organisation Performance Network (MOPAN) reported the AfDB as strong in the areas of internal auditing, organisation-wide external audit and its anti-corruption policy. However, MOPAN were less confident about audits at country and project level due to the AfDB using local country auditors. Using country systems means that the responsibility to engage the auditor lies with the borrower as does the decision of whether to release audit reports to the public which could protect the borrower from further scrutiny. However, given the documentary evidence that such audits are taking place, the MOPAN review scored the country and project level auditing as “adequate”.

The Board of Directors of the Bank have established an Audit and Finance Committee (AUFI) to assist the Board, among other things, in their oversight responsibility for the soundness of the Bank’s accounting policies and practices and the effectiveness of internal controls. AUFI, which is comprised entirely of selected members of the Board of Directors, oversees the process for the selection of external auditors and makes a recommendation for such selection to the Board of Directors, which in turn makes a recommendation for the approval of the Board of Governors. AUFI meets periodically with management to review and monitor matters of financial, accounting or auditing significance. The external auditors and the internal auditors regularly meet with AUFI to discuss the adequacy of internal controls over financial reporting and any other matter that may require AUFI’s attention.

In 2014 the leadership of the AUFI committee was weak and the UK pushed to get the performance of the committee improved which has happened, but there were delays in approval of the 2015 workplan. This is in part due to weak performance of the audit committee and the departure of the Auditor General who declined to move to Abidjan and subsequently left the Bank in February 2015, the substantive replacement is now in place and the AUFI committee is performing much better.

DFID Audit of the AfDB 2013.

In 2013 DFID’s Internal Audit Department (IAD) undertook an audit of the African Development Bank. The IAD focused its audit activities on what it judged to be the most significant risks which could hinder DFID’s ability to deliver its core objectives. IFID has since followed up with IAD to take action on issues where action is required, providing annual progress reports.

The September 2015 Progress report showed all remaining activities as either completed, remaining or ongoing, with none of the activities showing as being off target.

Date of last narrative financial report	2014 (June 2015)
Date of last audited annual statement	June 2015

E: RISK (½ page)

Overall risk rating: Low

The overall risk rating continues to be Low.

Overview of programme risk

The Bank faces four primary types of risk: fiduciary risk, credit risk, market risk and operational risk. These are closely monitored by the newly created Group Risk Office (GCRO).

Fiduciary risks are assessed by the procurement team during project design and prior to disbursement. The UK has been working with the Bank to strengthen their oversight of fiduciary risk management this is a work in progress.

The GCRO aims to strengthen credit risk management and ensuring full risk governance by reviewing all credit risk related issues and making recommendations to the Operations Committee.

In order to manage operational risks such as an Ebola outbreak or a security incident the Bank has a well tested business continuity plan which is implemented when incidents occur. The Bank’s regional resource centres have extra capacity in Pretoria and Nairobi to house extra business critical staff. Parts of the current temporary HQ in Tunis have also been retained following relocation of the HQ to Abidjan to provide further business continuity capacity.
.
Outstanding actions from risk assessment

Reform processes within the Bank do not proceed and (and the return to Abidjan HQ) fail to maintain quality of staff. The Bank’s plans for taking forward institutional reforms including Human Resource (HR) reforms was delayed by the return to Abidjan and a failure between Management and the Board of Directors to agree how best to respond to the higher cost of living in Abidjan.. DFID will continue to place the highest priority on ensuring a renewed commitment to these reforms through meetings of AfDF donors and through its Executive Director at the Board

The weak institutional capacity of AfDB countries, especially fragile states, reduces the likelihood of sustainable outcomes from programmes The AfDB has committed to undertake more thorough institutional and political economy analysis before committing investments. This should be made easier through the Bank’s increased field presence. Substantial support to strengthening partner countries’ institutions should accompany infrastructure and sector interventions

Low political will and capacity in partner countries undermines achievement of the Bank’s climate change commitments. The Bank’s Climate Change Action Plan should open the way for greater dialogue in partner countries and increased technical support and institutional strengthening projects. We will encourage the new AfDB President to continue to show strong leadership on the importance of Africa being prepared for climate change.

External economic risks and the long term viability of the AfDB

Risk	Probability	Impact	Mitigation

Deterioration of global economic environment undermines ability of governments to provide matching finance and put in place complementary conditions for projects to achieve outputs.	Low/Medium	High	When preparing Country Strategy Papers and during project preparation the Bank considers in detail the ability of the recipient Government to repay a loan or to provide the counterpart funding. The final proposal will explicitly state what the recipient Governments contribution will be and ensure that the project will not exceed the country’s debt sustainability based on IMF figures...
Reform processes within the Bank do not proceed and there is a failure to maintain quality of staff.	Medium	High	The Bank needs to renew its commitment to taking forward institutional changes including Human Resource (HR) reforms which includes a commitment to open, transparent and merit-based recruitment systems.

The weak institutional capacity of AfDB countries, especially fragile states, reduces the likelihood of sustainable outcomes from programmes.	Medium	High	The Bank undertakes Country Portfolio Performance Reviews to assess the Bank’s in-country performance and a country’s institutional, political and economic capacity before committing investments. The Bank’s increased field presence also supports constant monitoring. .
AfDB projects involved in corruption cases, misused or misappropriated.	Low	Medium	AfDB has the systems and procedures in place to identify fraud and take the necessary anti-corruption measures. We assess that these systems provide reasonable reassurance that funds are used for the right purpose.
Inadequate monitoring leads to failure to take action on poorly performing programmes and projects.	Medium	High	The Bank is introducing a new online system for tracking performance. We will work closely with the Bank to ensure that this system if rolled out effectively and does not damage the implementation of the current portfolio.
Low political will and capacity in partner countries undermines achievement of the Bank’s climate change commitments.	Medium	Low	The Bank’s Climate Change Action Plan should open the way for greater dialogue with partner countries and increased technical support and institutional strengthening projects. We will encourage the new AfDB President to continue to give a strong leadership on the importance of Africa being prepared for climate change The Bank is also working with other MDBs and financing instruments to create incentives for the private sector to deliver climate smart investments.
Not sufficient Bank attention to gender issues.	Medium	Medium	The Bank finalised the revised Gender Framework and Action Plan in 2014, and since then the Bank’s results have shown an increase in projects with gender informed design and an increase in completed projects showing satisfactory gender outcomes. Where relevant the Bank publishes results that disaggregate between sex and gender. MTR papers note continued challenges given resource limitations.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The spending profile agreed between DFID and the AfDB and approved by the UK government is being followed.

Performance of partnership (s)
The UK has a small share (1.69%) of the Bank. The UK’s close relationship with the Bank means there is opportunity to influence at policy level corporate issues, less so at project level due to the non-regional voting share being only 40%. The UK also collaborates closely with its constituency countries (Italy and the Netherlands) holding twice yearly constituency meetings and working with other like-minded non-regional and regional members where appropriate.

Asset monitoring and control
The Bank maintains an asset registry of its office assets in HQ and field offices. Management of the assets is the responsibility of designated staff. Asset management is routinely audited by internal audit. .

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The Bank assesses its own portfolio performance and reports on this to the Board. This is an internal, self-assessment process and is closely monitored by senior management.

The Bank’s Independent Development Evaluation (IDEV), though independent is guided by the Bank’s Independent Evaluation Strategy 2013-2017, which focuses on the complimentary objectives for learning, accountability and the promotion of an evaluation culture, in support of the overarching goal of improving evaluation effectiveness.

One of the commitments to the GCI VI was for independent evaluation of the delivery of commitments. In September 2015, IDEV delivered an independent evaluation of the GCI VI and both the ADF 12 and 13.

The evaluation acknowledged that the Bank is an institution that is delivering its commitments, but there were too many of them; some insufficiently strategic and some that could have been dealt with exclusively by Board and Bank management. The efficiency of the bank’s processes were evaluated as satisfactory and inclusive of stakeholders.

IDEV’s Recommendations on AfDF:

1. Focus on fewer and more strategic commitments with realistic timelines and estimated costs for delivery
2. Enhance monitoring and managerial accountability for effective performance and results in terms of continued implementation, not only one off deliveries.
3. Simplify the process: longer cycle, fewer papers and formal meetings, review the shape of the participation of the AfDF Deputies.
4. Seek early board ownership of commitments

On programme budget reform the report noted that this is still a work in progress and far from producing the expected results on institutional efficiency and strengthening the link between resource allocation and operational priorities. The report also acknowledged that the admin budget was still a work in progress, being integrated with other components of the Bank’s reforms, including organizational changes, HR reforms and the decentralization strategy & roadmap.

IDEV’s Recommendations on the GCI:

1. Expedite full implementation of budget reform.
2. Strengthen the monitoring and accountability framework.
3. Simplify the planning and budgeting process and better articulate it with the strategic priorities of the Bank.
4. Streamline and strengthen relations with the Board

Monitoring progress throughout the review period

In 2014 a number of evaluations were completed such as:

•	Transport sector
•	ADOA Framework for private sector operations
•	Country strategy and programme evaluations for Botswana, Madagascar and Chad
•	Quality at Entry for CSPs/Regional Integration Strategy papers (RISPS)
•	Procurement functions within the Bank

The aim of these is to provide credible evidence based information that can help inform the Bank’s strategic direction on inclusive growth and transition to green growth; in addition these evaluations inform the production of annual publications such as the African Development Effectiveness Review (ADER), and the AFDB Annual Report. They are feeding in to the 2015 MAR and will in turn update the theory of change for development of the AfDF14 Business Case.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process