Annual Review - Summary Sheet

Title: Humanitarian Emergency Procurement Programme (HEPP)
Programme Value: £12 million		Review Date: 31 October 2015
Programme Code: 203416	Start Date: 9/5/2012	End Date: 31/6/2017

Summary of Programme Performance
Year	2013/14	2014/15
Programme Score	A	A
Risk Rating	Medium	Low

Period of review: April 2014 – April 2015

Summary of progress and lessons learnt since last review

Since the last Annual Review:

- The stockpile has played an important role in DFID’s bilateral responses in South Sudan, Syria, Iraq, Sierra Leone, the Balkans, Gaza, Ukraine and Nigeria;
- Significant progress has been made increasing the size of the stockpile to meet the needs of 75,000 beneficiaries, with tenders concluded for blankets, Shelter Kits, Tents, Armoured Vehicles and Aircraft Handling Equipment (ACHE); and with tenders for Solar Lighting, Sleeping Mats, and Hygiene Kits underway.
- CHASE OT assessments have reaffirmed Kemble and Dubai as the best locations for the stockpile, based on access and value for money;
- OCHA’s Global Stockpile Mapping review has begun, and will take time to deliver results, but there is an opportunity for DFID to influence this review and CHASE OT staff have already begun to do so;
- Where common standards did not already exist, CHASE laboratory and field testing have helped develop new quality standards, which are being shared with the rest of the humanitarian community to help drive improvements in the whole sector;
- New innovations and technology have been adopted to improve the quality and safety of stockpile and deployment module;
- Testing the market and conducting competitive tendering processes have delivered significant savings compared to original cost estimates.

Summary of recommendations for the next year

1. Complete the tender processes already underway for solar lights and lanterns, hygiene kits, sleeping mats, cook stoves and toilet systems to enable the stockpile to fully meet the needs of up to 75,000 beneficiaries.
2. Continue to explore and research new and innovative equipment to enhance the quality, safety and comfort of items held in both the stockpile and deployment kit, linking with Research & Evidence Department as appropriate.
3. Continue to test the market and using competition to drive value for money, using savings generated to invest in further research and innovation.
4. Agree a new improved air brokerage contract that delivers DFID a better integrated response capacity, making greater use of scheduled airlines as appropriate.
5. Actively engage to shape and influence OCHA Stockpile Mapping review, offering UK support and expertise as needed to drive the process forward.
6. Continue to research and field test NFI’s for the stockpile, developing new standards where they do not already exist, and sharing the findings with the rest of the humanitarian community to drive improvements in the whole sector.
7. Explore how new technological advances such as QR Labels and Active RFID tracking might be used to track the performance of DFID NFI’s in the field, with feedback informing continual improvement.
8. Review and update logframe and milestones for the next reporting year (April 2015 – April 2016).

A. Introduction and Context

DevTracker Link to Business Case:	Link
DevTracker Link to Log frame:

The Humanitarian Emergency Response Review (HERR), published in April 2011, highlighted the increasing numbers of people affected by humanitarian emergencies every year. It emphasised the importance of preparedness in providing a better emergency response, and that the DFID stockpile was part of the global humanitarian community’s preparedness toolkit. The review called for a step change in the way DFID approached humanitarian response, including a requirement to innovate and bring best-practice in the supply chain. As a result, a Humanitarian Emergency Procurement Programme (HEPP) was set up, with an initial capability to meet the needs of least 38,000 people.

Following the ICAI review of the Typhoon Haiyan response, and reviews of UK government humanitarian stockholdings in March and May 2014 as requested by the Minister of State, it was agreed that DFID should increase its range of emergency supplies held in UK stocks and enhance official deployment capacity to meet the needs of more than 75,000 people, by April 2017.

As a result, DFID increased its support to the HEPP to £12 million over a five years, to ensure non-food items (NFI) can be delivered to those in need in sudden onset emergencies. The increase in funding of £8.75m, from £3.25m, triggered a 2 year extension to the original 3 year programme, which will now run until June 2017.

The rationale for holding a stockpile is clear. In humanitarian emergencies people need certain things immediately, but can do without others for longer. Immediate needs usually centre on water, shelter, health and hygiene, food/nutrition and security/protection. Without items to address these needs, people may not survive and they may be placed at significant risk to secondary effects, such as violence which can particularly affect women and girls.

In order to meet these needs DFID has established UK humanitarian stockpiles, currently located in Dubai and Kemble with material and equipment that can be drawn on in a response. DFID has also developed a network of suppliers, who can supplement these resources as needed. This capability has been particularly useful in enabling us to meet more specialist or less predictable needs.

The humanitarian stockpile works in parallel with a similar Stabilisation Unit (SU) support package and shares warehousing, labour and maintenance services. To meet future challenges the UK needs to maintain these resources, while undertaking an on-going process of reviews of need, of performance of materials, locations of the stockpiles, and that takes advantage of innovation and new technology.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The Outcome of the project is that: the UK Government humanitarian stocks enable DFID to respond quickly, effectively and appropriately to humanitarian crises. The International System is better prepared to respond quickly, effectively and appropriately to humanitarian crises and their changing nature and scale. Innovations in shelter materials and NFI’s assessed properly and brought into routine use as part of the humanitarian response.

Outcome Indicator 1: Ability to respond quickly, effectively and appropriately to humanitarian crises by drawing on equipment and materials that enable DFID to meet the basic shelter and emergency survival needs for affected communities across a wider range of humanitarian cases.

Milestone 1: New Framework Agreements for new commodities should be used to increase the scope of commodities held in the DFID Emergency Stockpile. Items for which we hold existing agreements (tents, shelter kits, buckets, blankets) should be increased to meet the needs of 75,000 people by April 2017.

Nearly 90% of the items purchased under the HEPP programme are procured through Framework Agreements. In 2014 tenders were concluded for blankets, Shelter Kits, Tents, Armoured Vehicles and Aircraft Handling Equipment (ACHE). Tenders were also conducted for Solar Lighting, Sleeping Mats, and Hygiene Kits.

The stockpile was used on multiple occasions to respond to emergencies in: South Sudan, Syria, Iraq, Sierra Leone (in response to the Ebola outbreak), floods in the Balkans, conflict in Gaza, and to supply armoured vehicles across HMG and to partners. Following each emergency stocks are routinely replenished. A full list of the items held in the stockpile can be found at Annex A.

Outcome Indicator 2: Effective system in place that ensures all members of the international community can quickly identify and access shelter materials and NFI’s (and complex and hard to access specialist equipment and materials) held by individual organisations in the international community.

Milestone 1: Review of existing system completed with recommendations for subsequent work, underpinned by performance indicators, developed for consideration.

CHASE OT has begun a review of OCHA’s Stockpile Mapping system. This is not yet complete, but has already identified some shortcomings, including:

- A lack of global buy-in, meaning that not all agencies stocks are mapped;
- No common standard specification for items;
- A lack of up to date or real time information, making accurate mapping of stock levels difficult;
- No real system to enable inter-agency use of the various stockpiles.

OCHA has begun its own Global Stockpile Mapping and CHASE OT staff will support and contribute to this review. This will however take time to deliver results. Progress against this Output is closely aligned with DFID’s Disaster Emergency Preparedness Project (DEPP), and CHASE OT staff are involved in the DEPP as DFID Logistics Focal Points. They will help ensure progress against this Output is achieved in coordination with the DEPP. During the reporting period a preparatory meeting was held between UN agencies (WFP, UNCHR, UNICEF, OCHA) and CHASE OT Logisitics and Procurement team to discuss the DEPP’s relationship to the HEPP.

Given the time it is anticipated the OCHA review will take to deliver results, DFID is strengthening its own Stockpile Mapping and improving information sharing through the NGO Portal and the CHASE OT NFI catalogue.

Overall output score and description

Output 1: UK Government humanitarian stocks and agreements with suppliers in place so that the UK can meet the needs of affected communities across a wider range of humanitarian crises.

Score A+: The stockpile has played an important role in DFID’s bilateral responses in South Sudan, Syria, Iraq, Sierra Leone, the Balkans, Gaza, Ukraine and Nigeria. Considerable procurement has taken place during 2014/15 to increase the size of the stockpile to meet the needs of up to 75,000 beneficiaries. More remains to be done, but the target has been met for shelter kits, tents, blankets, kitchen sets, buckets and water filters. Tender processes are currently underway for solar lights and lanterns, hygiene kits, sleeping mats, cook stoves, and toilet systems. These will be concluded in 2015/16.

Output 2: DFID’s Global Stockpile(s) appropriately located and complements the International System’s own stockpiles. Implementation of agreed recommendations to support, improve and replace existing international systems.

Score A: The stockpile is currently split between Kemble and Dubai. CHASE OT conducted a review to determine if these locations remain optimal, considering alternatives both in the UK and also overseas. The conclusion of the review is that Dubai remains the best oversea hub for access and value for money, with Kemble and East Midlands airport the best location in the UK. Work has begun to review the international community’s stockpile management system and CHASE OT Logisitics and Procurement staff are feeding into this review, however it is anticipated this will take time to show tangible results.

Output 3: Implementation of agreed recommendations on standards and dissemination and compliance.

Score A: Items in DFID’s stockpile are procured to agreed international standards. For example, plastic sheeting, blankets and kitchen sets are all procured to the specification set out in the IFRC Catalogue. Buckets are procured to Oxfam’s specification, which is generally regarded as the benchmark. Marks are stamped on DFID procured items which allows them to be tracked and monitored once they have been distributed. This allows their durability in the field to be monitored, assisting in feedback to the manufacturers and lesson learning.

Output 4: DFID held stocks support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of environments for up to three simultaneous deployments.

Score A: CHASE OT hold deployment kit for DFID staff and contractors and during the reporting period deployed over 160 core staff and consultants. The composition of the kit is regularly reviewed, updated and improved. Innovations over the reporting period, amongst others, include procurement of a solar generator and power pack, allowing the diesel generator to be shut down at night, and VSAT capability with provides broadband and videoconferencing capability, and through which the DFID telephone is also able to function.

Has the logframe been updated since the last review?

Yes, the logframe has been updated to reflect the increase to the stockpile to meet the needs of 75,000 beneficiaries and the 2 year extension of the programme to 2017.

## C: DETAILED OUTPUT SCORING

Output Title	UK Government humanitarian stocks and agreements with suppliers in place so that the UK can meet the needs of affected communities across a wider range of humanitarian crises
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	50%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Output Indicator 1.1: UK stockpile (quality, content, volume) kept under regular review to ensure it is able to meet humanitarian needs on an on-going basis and respond to emerging needs.

Milestone 1: Significantly enhanced stockpile, both in terms of scope and scale, to meet the needs of 75,000 people. Increase in holdings of solar products and hygiene kits achieved. Procurement of enabling equipment for airports complete, and the equipment will be under production for delivery by end the of 2015.

Key Points

The stockpile has played an important role in DFID’s bilateral responses in South Sudan, Syria, Iraq, Sierra Leone, the Balkans, Gaza, Ukraine and Nigeria. In addition considerable activity has taken place during 2014/15 to increase the size of the stockpile and procure goods necessary to meet the needs of up to 75,000 beneficiaries. By April 2015, the target for the following items had been met or exceeded:

- Shelter Kits - 20,000
- Tents- 7,500
- Blankets - 75,000
- Kitchen Sets - 15,000
- Buckets - 40,224
- Water Filters -15,000

Shelter Kits – The target stock for Shelter Kits has been achieved with stock split between Dubai (15,000) and UK (5,000). Further Shelter Kits may be procured depending on recommendations coming out of the Shelter Strategy, which is currently being drafted.

Tents – The current stock of tents allow DFID to meet the needs of 36,700 beneficiaries, with the Shelter Kits providing the additional necessary capability to meet the needs of up to 75,000. No further increase in the number of tents is proposed, however the development of fire retardant tents is being tested.

Blankets – The stock of blankets has been increased to 77,375, meaning that 2 blankets can be included in the Family Assistance Package.

Kitchen Sets – The current stockholding of 15,000 Kitchen Sets allows DFID to meet the needs of 75,000 beneficiaries, based on a 5 person family. Research is currently underway to develop a basic Kitchen Set that can be included with the Shelter Kits.

Sleeping Mats – A Framework Agreement for the Sleeping Mats was established in March 2015, and a mini competition was run to purchase 37,500. The number of sleeping mats will match the current level of tents, and will mean DFID will be able to provide 5 Sleeping Mats for every tent held in stock.

Hygiene Kits – A framework agreement was established in March 2015 and a mini-competition will be run in 2015/16 for 15,000 Hygiene Kits. These will be added to the Family Assistance package.

Buckets – The current stockholding of 40,224 buckets is sufficient to meet the needs of 100,000 beneficiaries, based on 2 buckets per household. This will provide 28 litres of water storage, in line with Sphere minimum standards. It also means households are able to have separate buckets for drinking and washing. The buckets will be deployed as part of the Hygiene Kits.

Outstanding items that will be procured during 2015/16 include:

- Small Solar Lights - 15,000
- Solar Lanterns - 12,500
- Hygiene Kits- 15,000
- Sleeping Mats - 37,500
- Cook stoves - Specification to be decided
- Toilet System - Specification to be decided

Solar Kits – Intertek were contracted to carry out comparative testing of the Solar products. Their findings will inform the decision on final procurement of solar lights and lanterns. A Framework Agreement for Solar Kits was established in March 2015, and mini competition will be run to bring the number of solar products in line with the Kitchen Sets and Water Filters.

Household Water Treatment – DFID currently holds stocks of 15,431 Lifesaver Cubes, sufficient to assist 75,000 beneficiaries, based on one Lifesaver Cube per family of 5 people. In 2015/16 a new framework will be created that will include new solutions available in the marketplace for household water treatment.

Transitional Tents – During 2014/15 research was conducted into the concept of Transitional Tents, including work with potential suppliers to develop prototypes for Lab and Field testing. Some budget had been aside for possible product development, however this is now on hold pending publication of the Shelter Strategy. Work will continue with UN and NGO partners to understand their own plans to develop Transitional Tents.

Airport Cargo Handling Equipment (ACHE) – During 2014/15 DFID, in association with WFP, began the purchase of airfield handling equipment for use during emergencies. Outstanding items will be procured during 2015/16.

Procurement for the HEPP Deployment Module - was also undertaken during 2014/15, with the purchase of 2 x Global Coverage VSAT, 6 x Armoured Vehicles, plus 2 x forklift trucks. Further procurement is planned for 2015/16, including a K-Loader, 8 Tonne Forklift, 5 Cargo Dollies, Slave Pallets and Warehousing Tents.

During 2014/15 the stockpile was used on numerous occasions to respond to emergencies around the world, with items from the stockpile accessed by DFID Country Offices. Items are replenished as soon as they have been used to help recycle the stockpile and ensure expiry dates are not exceeded. Equipment used includes:

- South Sudan – Buckets
- Syria - Solar Lanterns, DFID Atlantis Tents
- Iraq - Tents, Shelter Kits, Blankets, Lifesaver Cubes, Solar Lanterns, Kitchen Sets, Buckets
- Sierra Leone - Shelter Kits
- Malawi - Kitchen Sets, Shelter Kits, Pole and Peg Sets
- Vanuatu - Shelter Kits, Solar Lanterns
- Yemen - Petrol Armoured Cars

Summary of responses to issues raised in previous annual reviews

Following the uplift decision further development and procurement work will be required on the NFI range in association with relevant partners. Strategic decisions on the content of the uplift will be taken by the Head of HRG on the basis of recommendations by the HEPP team and based on lessons learned from recent large responses including Typhoon Haiyan, Iraq and Ebola. Progress: Significant progress has been made during 2014/15 to increase the size of the stockpile to meet the needs of 75,000 beneficiaries. This has been done through this conducting new tenders for items such as shelter kits, tents and aircraft handling equipment (ACHE). The uplift is however not yet complete, and further work will continue in 2015/16. Regular meetings are held between DFID and CHASE OT to discuss progress.

Output Indicator 1.2: Effective links made with private sector suppliers and public sector/NGOs that enables rapid access to goods, equipment, materials not held in UK stockpile. Links made with potential private sector suppliers and innovators of international humanitarian products.

Milestone 1: Utilise new frameworks to continue to purchase additional products, materials, and equipment for enhanced UK stockpile. Continue to explore and test new innovations or inventions that further enhance the stockpile. Improve the regular, scheduled and systematic use of Innovation Filter and Innovation Log.

Key Points

Nearly 90% of the items purchased under the HEPP programme are procured through Framework Agreements. In 2014 tenders were concluded for blankets, Shelter Kits, Tents, Armoured Vehicles and Aircraft Handling Equipment (ACHE). Tenders were also underway for Solar Lighting, Sleeping Mats, and Hygiene Kits.

In addition to the Framework Agreements CHASE OT maintains a Procurement Database of approximately 50 suppliers that can be used to purchase low value goods or niche items at short notice during an emergency. September to November 2014 witnessed unprecedented emergency procurement in response to the Ebola crisis as the normal Framework Agreements did not cover the specific needs of the response and new items such as hospital equipment, Personal Protective Equipment (PPE), medical consumables, and medicines had to be procured at very short notice and in huge quantities.

During the reporting period CHASE OT undertook testing for Solar Lanterns, Fire Retardant Tents, and Fuel Efficient Stoves. Comparative testing has been undertaken for tent designs and sleeping mats. CHASE OT Logistics and Procurement staff also continued to research technological advances in water filtration and lighting supplies. Dashboard mounted tablets were added to vehicles, linked to cameras, to enabled the drivers to monitor tailgating of the vehicle, expected to improve the safety HMG staff being transported in insecure areas. DFID’s Deployment Kit has also been modified and adapted, and benchmarked against those of similar organisations. New digital VHF comms and a new IT infrastructure have been adopted, designed to work with the VSAT satellite.

Summary of responses to issues raised in previous annual reviews

The further development of framework agreements should remain under review, in particular with those that will allow for devolved stock responsibility. The expansion of the stockpile may necessitate additional or expanded frameworks and this will be a consideration in the discussions around implementation of the uplift and the stockpile’s overall fitness for purpose. Progress: CHASE OT have concluded a number of tenders for supply of NFI’s for the stockpile as part of the uplift, with other tender processes currently underway. CHASE OT Logisitics and Procurement staff are also exploring the feasibility of storing goods with suppliers to reduce storage costs.

Recommendations

1. Complete the tender processes already underway for solar lights and lanterns, hygiene kits, sleeping mats, cook stoves and toilet systems to enable the stockpile meet the needs of up to 75,000 beneficiaries.
2. Continue to explore and research new and innovative equipment to enhance the quality, safety and comfort of items in the stockpile and deployment kit, linking with Research and Evidence Department as appropriate.
3. Continue to test the market and use competition to drive value for money, re-investing the savings in further research and innovation.
4. Review and update logframe milestones.

Output Title	DFID’s Global Stockpile(s) appropriately located and complements the International System’s own stockpiles. Implementation of agreed recommendations to support, improve and replace existing international systems.
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Output Indicator 2.1: That the UK is assured that the location of items in the stockpile programme are optimally situated to reduce suffering and morbidity, offer value for money and are resilient

Milestone 1: The use of innovative storage locations and solutions will be implemented for Global Stocks, improving speed of delivery to UK and International Airports. Storage at supplier’s premises overseas utilised to increase specific country stocks.

Key Points

At the end of 2014 DFID’s stockpile was held in warehouses in three locations: Kemble Disaster Response Centre; East Midlands Airport and Dubai – Jebel Ali Free Zone. Warehouse facilities are leased at Kemble, with storage at Dubai provided by a third party logistics provider. The cost of storage in Dubai depends on the amount of goods stored at any one time, so savings can be made after a large response when stocks are usually low.

During the reporting period CHASE OT explored the option of holding a range of NFI’s at airports in the UK to reduce the overall cost of storage and to improve the speed of response when using military or civilian aircraft. East Midlands airport and Doncaster were identified as best suited to meeting DFID’s requirements. The review was based on ability to provide:

- secured covered storage
- free or low cost storage of relief items and Mechanical Handling Equipment
- security screening of cargo prior to transport by air charter
- palletisation of goods prior to air transport
- ability to receive and dispatch aircraft internationally and at short notice
- receive and consolidate stocks from DFID suppliers at short notice
- dispatch pre-screened DFID stocks to alternative airports (including MOD sites) in secure vehicles.

Work has also been undertaken to scope out the feasibility of storing some limited amounts of stock at supplier’s premises, such as High Thermal Synthetic Blankets which are now being stored at the supplier’s premises in New Delhi, India.

Summary of responses to issues raised in previous annual reviews (where relevant)

Continued work will need to be undertaken on reviewing locations and appropriateness, in light of the decision to expand the HEPP programme. The recommendations from these reviews will be factored into the work plan for next year and progress reported on in next year’s Annual Review. Progress: CHASE OT have undertaken reviews to determine the best location of the UK stockpile, both in the UK and overseas. Kemble, with close links to East Midlands Airport, and Dubai were reaffirmed as the optimal locations.

Output Indicator 2.2: DFID held relief items linked effectively with DFID air service provider operations and those of other logistics/transport providers to ensure a seamless supply/deployment process.

Milestone 1: Review of Air Charter arrangement and make recommendations to DFID for how the existing contract could be improved. Review of stockpile locations will ensure a continued seamless supply/deployment process.

Key Points

During 2014/15 CHASE OT examined whether the hub in Dubai remained the optimal location for DFID’s stockpile, or whether alternative locations might offered better solutions and value for money. Hong Kong, Malaysia, and Singapore were all considered, but were eventually rejected in favour of Dubai, based on warehousing costs and / or difficult customs procedures. Holding stock with suppliers in India, Pakistan and Kenya is however considered an attractive option and is being actively pursued.

Following the confirmation that Dubai remained the best location, CHASE OT investigated options to strengthen the transport arrangements from this location, in particular how to make greater use of scheduled airlines to move items from suppliers and to provide a more integrated response capacity. DFID’s air brokerage contract is coming up for renewal and these ideas were floated at an aviation industry open day held in 22 Whitehall. CHASE OT has also been working to develop an online portal for the submission of air options, and a database to streamline analysis and activation of air services. Both systems are currently being tested and will go live when the aviation contract is finalised. The air brokerage agreement, which was due to expire in 2014, has been extended for one year whilst alternative contracting methods are considered.

Output Indicator 2.3: Support the development of a system that ensures all members of the international community can quickly identify and access NFIs and deployment equipment held by individual organisations in the community.

Milestone 1: Initial review tests the appetite for delivering change in the international system (e.g. OCHA Central Register and Global Mapping of Emergency Stockpiles System) for stockpile monitoring, reporting, inventory management, quality control. Identifies potential partners and considers UK comparative advantage in supporting change.

Key Points

CHASE OT have begun to review of OCHA’s Stockpile Mapping system. This is not yet complete, but the following shortfalls in the current system have been identified:

- A lack of global buy-in, meaning that not all agency’s stock is mapped;
- No common standard specification for items;
- A lack of up to date or real time information, making accurate mapping of stock levels difficult;
- No real system to enable inter-agency use of the various stockpiles.

The review will continue into 2015/16, and OCHA is also conducting its own Stockpile Mapping review which will include consultation with stakeholders from across the humanitarian community. CHASE OT will input into this review and encourage OCHA to make improvements to its current system. This will however take time to time to deliver results. In the meantime, DFID is strengthening its own Stockpile Mapping and the information its makes available to others by improving the NGO Portal and the CHASE OT NFI catalogue.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. A work plan needs to be in place to identify how DFID will address this Output in the coming year of the programme, identifying who will lead each component and timescale for delivery. 2. A study is required to understand the current international capability in this area, its shortcomings and how improvements can be made. This is likely to form the basis of an outsourced research agenda. Progress: Limited progress during the reporting period, however is an area of greater attention in 2015/16, and is closely aligned to the Disaster Emergency Preparedness Project (DEPP). The work plan for this programme, including improvements to stockpile mapping, will be complete by late 2015, with improvements expected by 2017. DFID’s engagement with OCHA has led to it conducting wider research of the system. This survey will be completed by late 2015. DFID has also conducted its own in-house research to understand the shortcomings of the Stockpile Mapping system.

Recommendations

1. New improved air brokerage contract agreed that delivers DFID better integrated response capacity, making greater use of scheduled airlines.
2. Complete DFID review and actively engage to shape and influence OCHA Stockpile Mapping review, offering UK support and expertise as needed to drive process forward.
3. Review and update logframe milestones.

Output Title	Implementation of agreed recommendations on standards and dissemination and compliance
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Output Indicator 3.1: Effective system in place to establish and monitor minimum acceptable standards for shelter materials and NFIs provided in response to emergencies

Milestone 1: Consider what, if any, further work is needed to drive improvements in this area, and working with other key stakeholders, how this might be delivered. Consider how changes to DFID’s own funding policies might help to drive change.

Key Points

Items for DFID’s stockpile are procured against commonly agreed standards and the specification for DFID’s NFIs are always referenced in Framework and Call Down Contracts. For example, Plastic Sheeting, Blankets and Kitchen Sets are all procured to the specification set out in the IFRC Catalogue. Buckets are procured to Oxfam’s specification, which is generally regarded as the benchmark. Goods in the stockpile are also regularly inspected to ensure they meet quality standards and are not held beyond expiration dates.

Where a common agreed standard does not already exist, DFID undertakes laboratory and field testing to help develop new standards. During the reporting period testing was conducted on: solar lighting, fire retardant tents, clean cook stoves and lightweight insulated mats. The results of this testing has informed CHASE’s procurement decisions on these items. CHASE has also shared the results of this testing with the wider international community to help improve the quality of items procured by the whole humanitarian sector.

CHASE OT is able to monitor stock once it has been left the warehouse through DFID Shelter Marks that are physically printed on all HEPP stock items held in Dubai and Kemble. This mark includes the date and a reference code and allows the contract, supplier and manufacturer to be traced. This helps track the quality and durability of items from the field. CHASE OT are exploring the possibility of stamping items with QR Labels and Active RFID tracking in the future.

Recommendations

1. Continue to research and field test NFI’s for the stockpile, developing new standards where they do not already exist, sharing the findings with the rest of whole humanitarian community to drive improvements in the whole sector.
2. Explore how new technological advances such as QR Labels and Active RFID tracking might be used to track the performance of NFI’s in the field, with feedback informing continual improvement.
3. Review and update logframe milestones.

Output Title	DFID held stocks support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of environments for up to three simultaneous deployments
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	15
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Output Indicator 4.1: DFID has the equipment and resources in pace to enable the immediate deployment of up to twenty people to a range of environments and which can be scaled up in line with changing UK response capability. Instigate on-going review and testing of innovations and emerging technology in deployment platform holdings to ensure they are properly assessed and, where appropriate brought into standard stock holdings and referred to other relevant actors in the international humanitarian community and UKTI as appropriate.

Milestone 1: Continual review of DFID deployment support stockpile in response to lesson learning from previous responses. Improvements made to IT and Communications Hardware to ensure deployment equipment remains current.

Key Points

CHASE hold deployment kit for DFID staff and contractors, comprised of: (i) PPE, first aid and vehicle trauma kits; (ii) personal communications, such as sat phones; (iii) vehicles, such as armoured vehicles, trucks, 4x4, forklifts and (iv) field support equipment such as radios, sat phones, generators, accommodation, cooking and washing facilities. Between April 2014 – April 2015 CHASE OT deployed over 160 core staff and consultants.

The composition of the Deployment Kit is kept under regular review, with changes made following the Typhoon Haiyan response. Recent innovations include mounting the deployment module on remote controlled trailers, thereby reducing risks of damage from manual handling. The Logisitics team received training in use of VSAT which led to changes to the communications equipment for the deployment module. Other developments include:

- A solar generator and power pack, which allows for the generator to be shut down at night, saving fuel, and allowing some office comms to run during the night;
- Battery powered solar lighting to enable night time illumination of the camp, using energy saving LED technology;
- Digital VHF radio communication, which includes a tracking system for staff;
- A pneumatic mast, accommodating multiple antenna;
- VSAT, which is light weight, portable, and can operating globally giving broadband and videoconferencing capability;
- Integration of the Vodaphone Echo network through VSAT, allowing the DFID telephone system to be used;
- Turnable trailers, which facilitate packing and unloading, with remote controlled battery powered motors;
- Stronger, lighter tables and padded seats;
- Quick to erect waterproof tents, with cold weather insulation and semi-rigid flooring;
- Single shower cubicles with solar heated water bladders and manual foot pumps.

Looking ahead, CHASE OT will be examining further possible improvements including: (i) lightweight deployable tents; (ii) lightweight deployable water purifiers; and (iii) portable power banks.

Recommendations

1. Continue to explore and research new and innovative equipment to enhance the quality, safety and comfort of items held in the deployment kit.
2. Review and update logframe milestones.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The principle cost drivers for the project are the costs of the additional items added to the stockpile associated with the uplift and the costs of storage, warehousing and maintenance.

Where new or increased quantities of NFI’s have been required open competitions have been run in order to test the market and ensure value for money is obtained. CHASE OT Logistics and Procurement team have undertaken these competitions at no additional cost to DFID, their costs being met from the Humanitarian Emergency Operations Support Services (HEOSS) contract.

The cost of warehousing in Dubai varies depending on the amount of goods stored there. This means following a sizeable response savings can be achieved when stock levels are low. Options are also being explored, and taken, to store goods directly with manufacturers and suppliers, thereby minimising storage costs e.g. High Thermal Synthetic Blankets which are now being stored at the Supplier’s premises in New Delhi, India. The supplier is only charging 2 pence per blanket per month for storage.

VfM performance compared to the original VfM proposition in the business case

A number of competitions and tenders have been conducted that have resulted significant savings compared to original estimates. Some examples, amongst others, include:

Sleeping mats: Initial estimated costs for the sleeping mats were £300,000, however after rigorous independent testing of all framework providers the cheapest supplier was also judged to offer the best overall technical performance. This resulted in a £236,596 saving compared to original estimates.

Hygiene Kits: Originally £450,000 was budgeted for the procurement of 15,000 hygiene kits, but by splitting the contracts by line items and awarding the contracts to 4 different suppliers instead of purchasing as a full kit, a saving of £185,000 was achieved against the original cost estimates.

Warehousing: The warehousing agreement where DFID only pays for storage based on monthly volume rather than a set rate, helps achieve savings, particularly following a large response when the quantity of stock held is low.

Kitchen Sets: Competition under the Kitchen Sets framework agreement resulted in £118,000 savings against the original cost estimates.

Transitional Tent Development: During the current HEPP period a review of DFID’s Shelter strategy was undertaken by shelter advisors. This review indicated that less focus should be put on tents and transitional structures, and more focus should be put on plastic sheeting and local materials. The Transitional Tent project has therefore postponed, resulting in a saving of £126,000.

Other examples of savings achieved are:

- Refurbishment of redundant analogue radio equipment that was no longer needed by CHASE (due to the move to digital) to the Serbian authorities following the Balkan floods, saving £10,000;
- The provision of Land Cruiser 200 base vehicles to armourers, and the use of customs warehouse agreements to minimise duty and VAT, resulting in savings of approximately £100,000;
- Replenishment of deployment first aid kits before they expired, rather than purchasing new kits, resulting in a 50% saving (over £7,000), based on 85 kits.

Assessment of whether the programme continues to represent value for money

It is judged the programme continues to offer DFID good value for money, although it must be recognised holding such a large stockpile is not cheap, with significant monthly costs associated with warehousing, maintenance and storage, plus the need to regularly refresh stock to ensure it is not held beyond its expiry date.

Quality of financial management

DFID staff and CHASE OT Procurement and Logistics team meet on a regular basis to discuss the performance of the HEPP programme, including expenditure against the budget. CHASE OT produce monthly expenditure and forecast reports and these form the basis of DFID’s forecasting. Total project expenditure to date is approximately £7 million. The monthly meetings provide an opportunity to discuss any changes to the previous months’ forecast and agree options for reallocating funds if savings or overspends have been identified. 2014/15 has been a year of significant expenditure as goods have been procured to meet the uplift. Expenditure in future years is anticipated to decline as the uplift will be complete and the main costs will be replenishment of stocks and routine warehouse and maintenance costs.

E: RISK

Overall risk rating: Low

Overview of programme risk

The overall risk rating for the project is judged as being low. Crown Agents manage the stockpile on behalf of DFID, and are one of DFID’s three approved procurement agents with strict anti-corruption and anti-bribery policies in place.

The project builds on a series of previous projects (Stockpile projects 1 – 5), and Crown Agents Procurement and Logisitics Team are experienced in delivering humanitarian supplies in emergency situations, although it should be recognised this is never completely without risk.

Driving up the quality of procurement in the overall humanitarian system is clearly the bigger prize, but inherently risker and progress will depend on others’ appetite for change. As DFID’s own internal stockpile uplift is finalised this should become a focus for activity and influence going forward.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The decision to increase the size of the stockpile to meet the needs of 75,000 beneficiaries triggered an extension to the project, which will now run until 2017. Good progress has been made during 2014/15 increase the stockholding with the target met for shelter kits, tents, blankets, kitchen sets, buckets and water filters. Tender processes are currently underway for solar lights and lanterns, hygiene kits, sleeping mats, cook stoves, and toilet systems which will be concluded in 2015/16. The project is on track.

Performance of partnership (s)

Crown Agents are the sole implementing partner. They have arrangements with suppliers to ensure the adequate supply of non-food NFIs are maintained in storage and maintain relations with suppliers to ensure the delivery of NFI’s in humanitarian responses.

Asset monitoring and control

NFI’s maintained within the stockpile are procured to internationally agreed standards and are regularly inspected and monitored to ensure quality is maintained, that expiry dates are not exceeded, and that they remain fit for purpose. Items used in emergency responses are routinely replenished to ensure a good turnover and so that items are not held on the shelf for too long. Turnover, as percent of total stockholding, in 2014/15 was:

- Shelter Kits 55%
- Tents 49%
- Blankets 6%
- Buckets 10%
- Lifesaver cubes 85%
- Solar lanterns 181%

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

n/a

H: MONITORING & EVALUATION

Evidence and evaluation

The rationale set out in the Business Case and Business Case Amendment for the continued maintenance of a UK Government humanitarian stockpile remains valid and stronger than ever.

The project ensures that UK NFI’s, and those held by others, are maintained to meet the basic shelter and emergency survival needs of affected populations in humanitarian crises. It also promotes innovation and encourages the use of emerging technologies in the humanitarian sector, with these being brought into the stockholding when appropriate. The project also ensures that DFID staff (and those of partners) are able to deploy into a range of emergency situations, for up to three simultaneous deployments.

There will be an internal review of the programme towards the end of 2016. Given the strong evidence base for the existence of a UK stockpile, the focus of the evaluation will be on the success of the utilisation of UK stocks. The use and impact of stocks drawn down from the stockpile are also reviewed as part of Project Completion Reports for each individual humanitarian response.

Monitoring progress throughout the review period

DFID staff and CHASE OT Procurement and Logistics team meet on a monthly basis to discuss the performance of the HEPP programme. These meetings provide an opportunity to run through all current issues to do with the stockpile. Issues range from progress of mini-competitions or tenders to difficulties repatriating equipment from a most recent response. It also provides a opportunities for CHASE OT colleagues to seek approval to purchase new or innovative equipment, or test out new approaches such as holding stock with suppliers. Goods held in the stockpile itself are regularly inspected and monitored to ensure they remain fit for purpose and that expiry dates are not exceeded. Marks are stamped on DFID procured items which allows them to be tracked and monitored once they have been distributed. This allows their durability in the field to be monitored, assisting in feedback to the manufacturers and lesson learning.

Annex A - DFID EMERGENCY RELIEF STOCKPILE – NON FOOD ITEMS –14/10/2015
Product Code	Product Description	UK Stock	Dubai Stock	Other Stock	Total Stock
SHELTER KITS
SHELTER KIT	KIT CONSISTS OF 2x PLASTIC SHEET 4x7M and 2x ROPE 24M LONG	0	1,575	0	1,575
	KIT CONSISTS OF 2x PLASTIC SHEET 4x7M and 2x ROPE 24M LONG - UK AID BRANDED	4,140	0	0	4,140
SHELTER KIT POLE SETS
SHELTER KIT POLES	2x 1.9m POLES IN EACH SET	0	15,334	0	15,334
TENTS
WINTERISED TENT	DFID ATLANTIS DOUBLE FLY WINTERISED TENT(4X4M)	0	2,122	0	2,122
	DFID ATLANTIS DOUBLE FLY WINTERISED TENT(4X4M) - UK AID BRANDED	0	812	0	812
FAMILY TENT	DFID FAMILY TENT WITH WINTERISATION LINER	0	2,202	0	2,202
	DFID FAMILY TENT WITH WINTERISATION LINER - UK AID BRANDED	0	2,035	0	2,035
BLANKETS
PRESSED BLANKETS	50% WOOL BLANKET - PRESSED	0	33,120	0	33,120
RAISED BLANKETS	50% WOOL BLANKET - RAISED	0	8,900	0	8,900
SYNTHETIC BLANKET	HIGH THERMAL SYNTHETIC BLANKET	0	38,565	0	38,565
	HIGH THERMAL SYNTHETIC BLANKET – UK AID BRANDED	0	17,885	20,545	38,430
BUCKETS
BUCKET	14L BUCKET INC HANDLE AND LID (OXFAM SPEC)	0	15,510	0	15,510
	14L BUCKET INC HANDLE AND LID (OXFAM SPEC) – UK AID BRANDED	10,010	14,329	0	24,339
KITCHEN SETS
KITCHEN SET	KITCHEN SET IFRC SPEC	0	4,600	0	4,600
	KITCHEN SET IFRC SPEC – UK AID BRANDED	4,992	5,030	0	10,022
SOLAR LANTERNS
SOLAR LANTERN	SOLAR LANTERN WITH MOBILE CHARGING (Option 1 – JS30-MOB) – UK AID BRANDED	3,264	0	0	3,264
HOUSEHOLD WATER FILTER
WATER FILTER	HOUSEHOLD WATER FILTER (Option 1 – Lifesaver Cube)	0	5,075	0	5,075
	HOUSEHOLD WATER FILTER (Option 1 – Lifesaver Cube) – UK AID BRANDED	5,324	4,908	0	10,232