Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	November 2015

Title: Strategic Evaluation Fund (SEF)
Programme Code: 203069	Start Date: 20/01/2012	End Date: 31/08/2015

Summary of Programme Performance

No Annual Reviews have previously been completed on the Strategic Evaluation Fund (SEF) as the approval pre-dated SMART rules, when there was no formal requirement for Annual Reviews to be undertaken on programmes less than £1 million. In light of the new programme rules, a light touch and proportionate Project Completion Review is now being undertaken. In the absence of previous annual reviews, the SEF products from the period 2012 – 15 have been included in this review.

Financial Position

Original Programme Value	£ 300,000
Extensions/ amendments	May 2013: £350,000 / April 2014: £200,000 / The budget was then reduced in the f/y 14/15 by £168,964 to match remaining commitments
Log-frame revisions (with dates)	n/a
Total programme spend	£ 681,036

Follow up actions required following closure

The following ARIES actions need to be completed:

- Closure of PO 40052514, releasing committed funds of £1,049 in 2013.
- Closure of PO 40083568, releasing committed funds of £9,236 in 2014.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203069/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203069/documents/

Outline of programme and what it has achieved

The purpose of the SEF is to strengthen evaluation approaches, support learning from evaluation and improve the use of evaluation studies. It enabled the Evaluation Support Group (now known as the Evaluation Strategy Team) to respond flexibly to evolving opportunities to improve the focus and rigour of development evaluation practice in priority policy areas. Thematic advisers in the ESG commissioned a range of strategic analysis and guidance to inform evaluation practice in DFID and amongst its partners and to contribute to global communities of practice. Advisers prepared short submissions against the agreed outcomes to request project funding from the Team Leader following established Evaluation Department procedures. This proved an effective way of operating, was fit for purpose and less time consuming than preparing a full business case for each project. It is also in line with the new SMART Rules, which provide the basis for open and flexible programming decisions.

The original priority thematic areas for the SEF reflected the thematic leads within ESG:
- Governance
- Humanitarian
- Human development
- Climate and Environment
- Private Sector Development
- Gender, Equity and Vulnerability

Governance, health, gender and private sector development have been covered, although in general, products have focused on developing guidance around methods and approaches rather than thematic synthesis. No work was undertaken specifically in the areas of humanitarian evaluation or climate and environment evaluation. This may reflect the fact that the International Climate Fund has its own monitoring and evaluation unit which has commissioned its own stocktakes of the evidence base.

SEF initiatives have proved valuable and useful to DFID and the broader development evaluation community. Products have been widely disseminated online, through dedicated events, and journal publications. Beyond this, presentations of SEF projects have taken place at a number of international evaluation events over the period 2012-14, including the European Evaluation Society, the UK Evaluation Society, UNAIDS MERG and the DAC Evalnet. The SEF is playing a distinct role in informing the direction of travel in development evaluation.

Individual SEF projects
The majority of SEF products have been of high quality and well disseminated and received by audiences, where these have been consulted. In the minority of cases where products did not meet expectations, there were clearly identifiable reasons and lessons have been learned. However, the utility of SEF products has been difficult to assess during this review as information on uptake has not been systematically recorded, and the reviewer was largely reliant on anecdotal data. Tighter management at project level to monitor the uptake and use of SEF products – for example through more clearly specifying the intended audiences and setting out expectations for monitoring uptake, communication and dissemination in project contracts – could potentially increase the reach and impact of the SEF. Quality assurance arrangements have varied, but in general advisers obtained suitable expertise to review drafts and were confident in the quality of studies. Overall most SEF projects have proved to be valuable to the internal and external evaluation community, although feedback was not always available and assessing reach and accessibility was particularly difficult.

The SEF’s flexibility has enabled relevant projects to be funded, often at short notice. The SEF therefore fills an important gap as methodological pieces which are global public goods can be commissioned. Interviewees were clear that without this ability to be responsive to opportunities, key pieces of work would simply not have been undertaken. In conclusion, the SEF has proved to be responsive in matching funding to needs and investing in partnerships.

However, as SEF projects have been managed by different people at different times, the way that SEF projects add up to achieve the outputs is not always clear and an overarching theory of change (as included in the new SEF business case) would help to demonstrate more clearly how projects are related. Visibility of the fund’s outputs has been hindered by lack of central monitoring, as demonstrated by the log frame which did not include any milestones or targets. Greater transparency around how funds are allocated would help staff understand when and why resources are used on particular projects. This would dispel perceptions from some internal interviewees that the SEF is allocating resources on an ad hoc basis, as well as strengthen the strategic objectives of the SEF and help to ensure that all projects funded have maximum leverage. Simple communications tools – for example providing links to all SEF products on the DFID website – would also help to show what the SEF is achieving. This would include for instance more in depth knowledge in specific methods or synthesis of specific evaluation findings, both which deepen our broader understanding of evaluation.

A full cost-effectiveness analysis was not undertaken for this review. Based on the relatively low costs of individual projects and their relatively wide reach, value for money appears to be good overall. However, value for money could be better captured and enhanced both through more systematic tracking of how products are used, together with closer monitoring and analysis of input costs, which were quite variable, and actual outputs. In summary, bundling of SEF projects does help to provide strategic direction and minimise transaction costs, although stronger central management of the fund is needed.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

Outcome: Strengthened evaluation practice in priority sectors by DFID and with key development evaluation partners to deliver and learn from high quality evaluation of development policies, programmes and projects.

Outcome indicators:
- Increasing numbers of high quality evaluations in priority policy and programme areas
- Active communities of evaluation practice in priority policy and programme areas

Overall Outcome Score: A

SEF products in and of themselves are necessary but not sufficient to achieve the outcome of strengthened evaluation practice in priority sectors. According to a consultant interviewed for this review and the Evaluation Adviser in DFID Ghana, evaluation designs for the programmes Market Development (MADE) in Ghana and the Development of Agricultural Rural Markets Project in Zambia have been influenced by the paper Review of Making Markets Work for the Poor Evaluation Methods and Approaches. In some cases, practice has been strengthened further upstream, for example the Results Based Financing paper has produced a framework which is guiding DFID’s approach to commissioniong, managing and synthesising evaluations. The effect of this on the commissioning of individual evaluations would need to be explored in more depth to come to an evidence-based conclusion.

While there is some promising work underway on certain projects, based on the available information it is hard to assess whether this type of influence is exerted across the whole SEF portfolio and hence get an indication of aggregate leverage. More detailed analysis would be needed, for example to compare inception reports in a particular policy area before and after SEF papers became available. This would require an assessment of whether and how evaluation implementers and quality assurers used the SEF papers in the early stages of evaluation design. In conclusion, the extent to which this type of influence will be sustained and feed into high quality evaluations over their lifetime remains to be seen over time.

The same conclusion can be drawn for active communities of evaluation practice in priority programme areas (Output 3). The review communities of practice have been stimulated, with EGAP’s networks on evaluation of governance and politics being the strongest example of an active community of practice. The extent to which communities of practice will continue and grow over time remains to be seen.

Output Score and Description

Final Output Score: A

Output number per LF	Output Score	Risk	Output Description
1	A	Low	Key findings from evaluations synthesised and disseminated to inform evidence based decision making in priority sectors.
2	A	Low	Number of evaluation methods and guidance products developed
3	A	Low	Global Communities of practice established in key thematic areas.

Progress has been assessed using the indicators in the logframe as far as possible, however the logical framework was not updated during project implementation and did not include any targets, thereby limiting its relevance to this review. To assess the overall achievements of the fund and extract key lessons, the following criteria for success were developed:

Output/product level:
- Timeliness - commissioned before or on cusp of interest in a topic
- Focus - targeted at the right audience
- Accessibility - written and presented for relevant audiences
- Reach - communicated to relevant audiences
- Quality - Undertaken and reviewed by people with relevant expertise
- Credibility - conference paper/journal article produced/demand for products.

Fund level:
Is the SEF responsive, in matching funding to needs and investing in partnerships?
Does bundling of SEF projects help us to provide clear strategic direction (projects need to be related to make strategic sense) and minimise administration costs?

The table in Annex 1 assesses the success of those SEF products which have been completed, as far as possible with the available information. The purpose of including this table is to demonstrate how evidence collected throughout the review process from interviews and desk review has been used to form conclusions. Where the exercise is limited by lack of evidence on uptake use this is indicated. Consideration was given to using a points system or Red Amber Green rating for each product, however the quality of information meant that this type of aggregation would have limited value. A summary can also be drawn for each individual success criteria by looking down the columns. For example, it can be seen that almost all SEF projects were timely and had a good fit with the strategic objectives of the fund.

In conclusion, according to outputs in original logframe, the overall performance of the fund is contingent on numbers of evaluation synthesis reports developed, published and presented; numbers of evaluation methods and guidance products developed, published and presented; global communities of practice established and developed. Without targets or milestones it is hard to provide an objective assessment. However, the detailed output scoring shows that around a third of SEF projects have resulted in at least one formally published paper, and around half have led to a presentation at an international conference or meeting. Most of the projects were published online albeit not in a peer reviewed journal. In light of this, the overall output score is A, meaning it meets expectations.

Lessons and how these have been shared

The following lessons will be incorporated into the new SEF (2015-2018):

- Increase transparency through stronger central management of the SEF. This could be achieved through a small management group, or stronger programme management under the new SRO arrangements with one individual clearly accountable.
- Systematically monitor SEF outputs, uptake and use of SEF products to gauge value and impact. While a full evaluation would not be proportionate, tracking over time and in detail how two or three SEF products have been used and the effects on evaluation quality and subsequent programme decision making would be an informative exercise.
- Build requirements for dissemination and publication and monitoring of uptake of SEF products into project contracts. A SEF style guide and DFID website page may be useful.
- Greater oversight and comparison of costs (e.g. fee rates) to ensure tighter oversight of value for money, together with more guidance for EvD staff on costings.
- Importance of managing the SEF against a realistic and updated logical framework.
- Tracking uptake and use of SEF studies is central to monitoring the success of the fund
- Monitoring should take place both in real time and over a sustained period to assess the downstream as well as immediate effects of SEF studies.

## C: DETAILED OUTPUT SCORING

Output Title	Key findings from evaluations synthesised and disseminated to inform evidence based decision making in priority sectors.
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	40
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
Number of evaluation synthesis reports	N/A	Strictly only 3 noted below, however some of the guidance notes include summaries of evaluation literature as part of looking at methodological approaches. / Synthesis of literature on evaluability assessments (UKES, Evaluation Journal) / Evaluation of payment by results: current approaches, future needs(EES) / Synthesis report on HIV and AIDS (UNAIDS MERG; DAC Evaluation Insights Brief).
a) Number of published articles in priority sectors / b) Number of presentations at international evaluation conferences and meetings	N/A	2 published / 3

Key Points
The production and dissemination of detailed synthesis of sector evaluation findings has made less strategic sense as a standalone output, as this evidence mapping work is already undertaken through other channels within DFID. These include PEAKS, which covers four of the SEF’s thematic areas, standalone evidence pieces commissioned by policy and research teams, and work led by the Evidence into Action Team to carry out Policy Evidence Mapping. However, inclusion of thematic areas as a guide for topic selection is still relevant as in some cases it can be useful to analyse and develop evaluation methods on a thematic basis. Review of the evaluation landscape in a particular area is often an important preface to developing evaluation approaches and identifying short-term priorities.

Summary of responses to issues raised in previous annual reviews (where relevant)

n/a

Recommendations for future programmes

These thematic areas appear to still be relevant but may need to be reviewed as part of the implementation of Phase 2 of the SEF.

Output Title	Guidance on evaluation methods and approaches developed and disseminated to inform development evaluation practice.
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	40
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
Number of evaluation methods and guidance products developed (note: some of above-listed synthesis products also contain methods/guidance).	N/A	Review of evaluation approaches and methods for interventions relating to VAWG / (EES; 2 journal articles submitted). / Review of evaluation of economic empowerment of women and girls / (EES) / Synthesis of literature on evaluability assessments / (UKES, Evaluation Journal) / Review of M4P evaluation approaches and methods / (OECD DAC Event) / Review of the use of TOC in international development / EES; published as conference paper / Development of a code of conduct for HIV evaluations and peer reviewed journal article / Double check publication / Development of a compendium of indicators for sexual and reproductive health and HIV linkages.
a) Number of published articles in key evaluation journals / b) Number of presentations at international evaluation conferences and meetings	N/A	2 / 5

Key Points

SEF projects have made clear strategic sense in delivering the development of evaluation methods and guidance. SEF products have helped to strengthen evaluation approaches through building bodies of knowledge and guidance in technical and priority policy areas including impact evaluation, evaluation of gender, and evaluation of new funding modalities such as results based financing.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations
The main recommendation is around tracking uptake and use of studies.

Output Title	Global Communities of practice established in key thematic areas.
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
Number of dissemination activities completed: / a.) targeted conferences / b.) policy briefs / c.) TBD	N/A	It is not clear whether “targeted conferences” means in this context – perhaps an event set up specifically to disseminate the products as opposed to presentations at other policy conferences/meetings. / (A better indicator would be conference presentations, summaries and workshops).
Number of people who attend policy conferences, dissemination events: a.) policy makers; b.) development professionals; c.) researchers; d.) donors	N/A	Figures are not available

Key Points
It is hard to substantiate the extent to which through SEF, global communities of practice have been established in key thematic areas. Where the SEF has funded partnerships – notably the Experiments in Governance and Politics (EGAP) – there is evidence that a live community of practice is forming. Indicators for Output 3 focused on numbers of dissemination activities completed and people how attended these events. While a substantial number of such events have taken place, without defining more clearly what a community of practice looks like, it is hard to conclude that these have actually been established.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
Define “dissemination activities” and “community of practice” more clearly as numbers of people attending conferences and other events does not necessarily mean that an active global community is being established.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers are independent consultants’ fee rates, travel costs and DFID staff time.

The overall SEF budget profile and payments are maintained and managed by EvD staff and payments are normally made against milestone based contracts (EGAP is the exception as this is an Accountable Grant which is paid in arrears).

Procurement processes are normally single sourced but EvD staff have managed some limited mini-competitions to engage a wider range of suppliers and to negotiate some cost savings against the original budget forecast. Where the budget exceeds £25,000 a mini-competition is required. Budgets are scrutinised by EvD programme staff and reductions in budget lines have been achieved at an early stage of approval. A particular concern at the outset was a concern that high commercial fee rates would be paid to consultants to conduct evaluation research rather than contracting academics at lower fee rates with a similar evaluation research track record. As only the winning bids are saved on file, it is not possible to do a full analysis of fee rates. Fee rates from contracts range from £165 to £895 per day, this may include fees paid to masters students and copy editors as well as evaluation professionals. This is now subject to closer scrutiny with closer attention to the cost structures and fee rates charged by consultancy companies. While to some extent the market dictates what is paid, more structure and guidance for EvD staff may help to increase consistency in this area.

No record has been kept of how much DFID staff time has been spent on the SEF, however individual advisers who managed projects reported that they have been fairly low levels of input relative to the overall benefits produced by the projects. The extent of inputs needed depends, like many DFID projects, on the quality of the consultants undertaking the work. In some cases the close collaboration between staff and service providers was reported to be a helpful and constructive way of deliving a high quality product, benefiting DFID staff knowledge and expertise as part of the process.

VfM performance compared to the original VfM proposition in the business case

VfM performance is in line with expectations; overall the programme is on track to meet targets, and its intended purpose (to improve the focus and rigour of development evaluation practice in priority policy areas) is still a good fit. However, the original business case states that “the main costs element is consultant fees; these will be benchmarked for value for money against rates paid for similar specialist evaluation services”. It is not clear that this has been undertaken.

Assessment of whether the programme continues to represent value for money

It was not proportionate to undertake a full cost-effectiveness analysis for this review. In terms of overall effectiveness the SEF continues to offer good value for money, although improvements could be made in some areas. Outputs from the projects, which vary in cost but are relatively inexpensive by DFID’s standards, have been widely disseminated online, through dedicated events, and journal publications. Beyond this, presentations of SEF projects have taken place at a number of international evaluation events. Greater attention to ensure systematic dissemination and communication and track uptake of products would help to assess value for money more accurately.

The SEF has a range of processes and safeguards to ensure that VFM is assured throughout the programme cycle. At assessment of bid(s) stage, VfM is an assessment criterion and applicants are required to cost and justify all elements of the proposed evaluation work and DFID reviewers consider VfM as part of the technical and commercial assessment of bids when making funding recommendations. At contracting stage, all costs undergo scrutiny by the EvD programme manager and excessive costs are removed. These often relate to contingency costs built in to a proposal, and where costs for travel and subsistence are higher than we would usually pay. Alternatively it may be where we have asked for a different balance of inputs between junior and senior members of a team due to the requirements of the work.

Throughout the contract period, consultants and grant holders must submit budget invoices against the agreed budget lines and receipts must be kept for DFID inspection, if required. No one can exceed their awarded budget without prior approval from EvD. On average, projects are completed within full budget cost.

Quality of financial management during programme

The programme remained on track with minimum variances against forecasts across the financial years. Payments were made against agreed payment schedules under individual project contracts and were based on agreed outputs. There are reviewed and approved by the lead technical adviser before payments were implemented. No issues arising.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK

Quality of risk management over the life of the programme

Overall risk rating: Low

Overview of programme risk
The main risks relate to:

Findings communicated to DFID, policy makers and academics – risk that DFID staff and policy makers do not take account of findings from SEF funded activities due to factors outside control of project. EvD can, though, work on maximising dissemination of funded activities in order to give DFID staff and policy makers the best possible opportunity to use evaluation outputs. EvD will continue to develop ideas for improvement on this area in line with the new Evaluation Strategy.

Staff changes in EvD lead to ineffective or delayed delivery through reduced capacity or loss of expertise – management structures and adequate handovers need to be in place to minimise loss of capacity and expertise during staff changes/absences. This is particularly a risk in light of the Evaluation Department restructure, as staff are changing roles, some individuals are moving on and recruitment could take some time.

EvD is disappointed with quality of proposals – processes to mitigate against non-appointment on quality grounds have been identified and will be continually adopted e.g. need to have very clear, and agreed terms of reference from the outset. This risk has not materialised as on the whole good quality proposals have been received. In terms of quality of final outputs, EvD staff have put significant effort into getting the products right.

No risk register exists or annual risk report was prepared. Through close monitoring of the contracts and the EGAP grant, EvD ensures compliance with terms and conditions.

Outstanding actions from risk assessment
If a further SEF phase of support is approved, EvD should develop a risk register for each component created under the programme.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme progressed largely according to schedule.

Performance of partnership (s)
All service providers performed in line with the agreed outputs with no issues arising.

Asset monitoring and control
Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
For a relatively small fund, a full evaluation was not proportionate. However, closer attention to definiting and testing the theory of change as part of project management is recommended. Also, more detailed assessment of the impact of selected SEF products over time must be built into Phase 2.

Monitoring progress throughout the review period
As already discussed, closer monitoring of the communication, dissemination, uptake and eventual use of SEF products is needed to assess both the overall effectiveness and the value for money of projects. The log frame should have been kept up to date and used to monitor outputs, although with only three months remaining it is not worthwhile to now update it. Better monitoring and management of the fund as a whole is also required to assess on an ongoing basis what the SEF is achieveing in aggregate, and to increase transparency around the fund.

Annex 1 - Assessment of completed SEF products
Product	Fit with SEF objectives*	Timeliness / commissioned before/ on cusp of rising interest in topic	Focus / targeted at the right audience	Accessibility and Reach written and presented for, and communicated to, relevant audiences.	Quality / undertaken and reviewed by people with relevant expertise	Credibility conference paper/journal article produced
Review of evaluation approaches and methods for interventions relating to violence against women and girls / Cost: £47,701 / Masters’ students to undertook work following competitive process.	Yes – covers both technical evaluation guidance and a priority thematic area. / Focuses on use and effectiveness and what made evaluations useful.	High level of political interest in development interventions for women and girls.	People who commission evaluations and practitioners. / Appears to be broadly right but audiences could have been more clearly differentiated.	Hard to establish without more evidence on dissemination and uptake. / Final paper is quite technical, would be interesting to follow up to find about how it has been used in practice.	Good - a low cost, low risk project of sound overall quality. / Now understand how Qualitative Comparative Analysis works in practice. / Employed students rather than consultants: this model worked well.	European Evaluation Society best poster award / 2 publications pending (submitted, awaiting approval)
Review of evaluation economic empowerment of women and girls / Cost: £108,292 / Limited competition tender.	Yes – covers both technical evaluation guidance and a priority thematic area. / Could have had clearer idea of what exactly we wanted to help define scope.	High level of political interest in development interventions for women and girls.	Internal: DFID Evaluation Advisers / (commissioners). / External: evaluation community (evaluators).	ODI event; DFID launch with civil society, Oxfam which has a strong evaluation practice. / Internally – to four DFID advisory cadres. / More evidence needed on uptake.	Reference group although only 1 member really active. / Final version good but took many redrafts and work was delayed. / Interesting findings e.g. on age groups and transformational change.	Presented at European Evaluation Society.
Rapid Review of Embedding Evaluation in DFID / Cost:£19,221 / Co-authored by DFID staff.	Yes - audiences were both external and internal. Looked at implementation of DFID’s embedding evaluation model.	This review informed development of DFID’s evaluation strategy. Timing was critical and SEF released resources quickly and flexibly, enabling work to be completed in timeframe.	Well-focused piece of work. Targeted at DFID senior management; as well as external audiences with wider interest.	Concise report edited to professional standard. Used internally for strategy and planning. / Moderate wider reach: 885 webhits in 9 months.	Good – reviewed by reference group of internal and external members.	Not applicable for this type of report.
Study on demand and supply for evaluations in sub-Saharan African Countries / Cost: £100,000 / Limited competition as under £25,000 threshold.	Yes - support to global community of practice on evaluation capacity development.	Interest amongst external networks on ECD. / Study commissioned in advance of DFID developing a strategy for capacity building.	Countries (5 case studies – Ghana, Rwanda, Ethiopia, Malawi, Zambia); / Evaluation capacity development networks and global partnership centres.	Widely disseminated in target countries and beyond, through OECD DAC and various regional/national associations; and CLEAR forum. Received positive feedback. Reports read by Head of Evaluation at the AFDB. / Strong efforts made to follow up with countries, although information needed on uptake and use.	Reference Group of 6 international evaluation experts. / Good methodology, strong team and inception phase, although difficult and ambitious topic.	Submitted to Evaluation for journal publication; contributed to a published article the African Evaluation Journal.
Synthesis of literature on evaluability assessments / Cost:£15,223 / Under 25,000 threshold: consultant put in proposal.	Yes – literature review and development of guidance in a key cross-cutting area of evaluation practice.	Undertaken at time when use of evaluability assessments was increasing, yet there were different understandings and practices in undertaking them.	Global public good – targeted at development practitioners, including DFID staff. / Greater segmentation of audiences would help to track uptake.	Informal feedback internally indicates widespread use by DFID staff. Needs proper tracking of how guidance used. / Referenced in UEA training course on impact evaluation.	Internal reference group of 3 individuals, who were users of the product. / Broadly happy with the final product. This was also relatively easy to manage / commission.	Presented at UKES and submitted article in the journal “Evaluation” (undergoing peer review).
Review of Making Markets Work for the Poor M4P Evaluation and Methods Approaches / Cost: £31,230 / Direct appointment	Yes – focus on evaluation practice in topical area of programming. / Responded to immediate needs of DFID policy team, who were end users.	Several programmes were planning evaluations but there was a lack of clarity about what evidence was already available. Very few evaluations completed – some had failed due to poor methods.	Commissioners; evaluators. Internally, DFID’s Growth and Resilience Dept.	Disseminated at OECD DAC private sector event and at a well-attended DFID launch event. strategy. Put on R4D as a working paper. / Paper has stimulated blogosphere discussions; and been used by consultants for evaluations (e.g. MADE Ghana, Zambia Musika).	Final report good quality. Took a number of drafts to get there. Required relatively little resource (staff and financial) to manage. / Good content and engagement with the policy team. But hard to get into detail of methods without programme to apply it to. Would benefit from follow up work 2 years later to see effects on evaluation reports.	No publication. / In promoting SEF work, need to be careful that such papers don’t become a “bible” for contractors who interpret early stage guidance too literally.
Evaluation of payment by results: current approaches, future needs / Cost: £23,945 / Phone interviews with 5 candidates.	Yes - focus on evaluation practice in growing area of programming, as well as synthesis of existing evaluations.	Very timely. Strong stakeholder interest in topic area. Lack of understanding in how to assess new results based financing mechanisms prompted study.	Wide range of internal and external audiences. Greater differentiation of audiences would help to track dissemination, uptake and use.	Clear, accessible paper shared on range of M & E websites e.g. ALNAP. / EES Helsinki conference main forum for presentation. / 711 external webhits over 11 month period.	Well received. Methodology good, although could have been better. Has helped to catalyse further work, challenge received wisdom and highlight limited evidence. / Need to compare quality of RBF evaluations prior to and after the study and identify how the paper contributed.	Presented at European Evaluation Society (EES).
Review of the use of Theory of Change in International Development / Cost: £5,664	Yes – review of and guidance and training in cross-cutting area of evaluation practice.	International development community was grappling with theory of change; DFID business case format also prompted need for work on TOC.	International development community incl. NGOs, other donors, Ausaid, Comic Relief, Foundations. Also DFID staff.	Launched at a consultation workshop, published online e.g. Oxfam blogs, Research into Action guide, Knowledge Brokers’ Forum. Used at UEA training course on impact evaluation. / Used extensively within DFID for training, business cases etc. (specifics not recorded). / Relatively few hits on DFID website (394 in 20 months).	Produced through close collaboration between DFID adviser and consultant. / Produced helpful and influential report. Helped to open up “black box” on evaluation – the mechanisms of change, dealing with complexity.	Presented at UKES and published as conference paper
Synthesis report on HIV and AIDS Evaluations 2012 / Cost - £15,101 / Candidate identified based on earlier stocktake work.	Yes – synthesis study on key policy area plus questions, methods etc.	Followed up earlier report on mapping investments in HIV/AIDS evaluations.	Focused audience within UNAIDS MERG – reference group were key audience. Also internal audiences within DFID.	Published as DAC evaluation brief. / Endorsed by UNAIDS M&E reference group.	Reference group was very receptive, although difficult to get individuals to devote time as it developed.	Rejected by Lancet but being considered for publication elsewhere.
Development of a code of conduct for HIV evaluations and peer reviewed journal article / Cost - £4,500	Draft code of conduct for UNAIDS MERG Task Team, based on recommendations from above Synthesis Report.					This has been finalised and published.
Development of a compendium of indicators for sexual and reproductive health and HIV linkages / Cost: £11,102	Supporting global community of practice on technical measurement area? However terms of reference not well focused.		Poor – indicators need to be really specific to be useful.	N/A	Consultant did not have the right background for the task.	N/A
Summary	The majority of SEF studies and projects have a strong fit with the fund’s objectives.	Timing of SEF projects has been good, enabled by the responsive nature of the fund.	In general, audiences appear to be appropriate, however more detailed segmentation and targeting is needed in Phase 2 of the fund to ensure products reach target audiences.	Evidence in this area is mixed, with some strong examples of dissemination and initial uptake. However, this has not been sufficiently well tracked making it hard to assess.	Overall, the quality of studies has been high and advisers have suceeded in getting appropriate feedback from experts.	SEF projects have received good profile at international conferences. In a number of cases, publications are pending or completed.

*SEF objectives: Strengthens (1) evaluation practice in priority policy/cross cutting area; and/or (2)
learning from evaluations at global level (e.g. sythensis, good practice, support global communities of practice).