Annual Review - Summary Sheet

Title: Increasing Access to Reproductive Health commodities in Ethiopia
Programme Value: £18 million		Review Date: October 2015 / (Review Period: September 2014 to August 2015)
Programme Code: 202980	Start Date: November 2011	End Date: June 2016 (extended from June 2015)

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	A+	A+	A+	A
Risk Rating	Low	Low	Low	Low

Acronyms
AIDS	Acquired Immune Deficiency Syndrome
AR	Annual Review
BCIS	Behavioural Change Impact Survey
BCC	Behavioural Change Communication
BMGF	Bill and Melinda Gates Foundation
CPR	Contraceptive Prevalence Rate
CYP	Couple Years Protection
DALY	Disability-Adjusted Life Year
DFID	Department For International Development
DHS	Demographic Health Survey
DRS	Developing Regional States
EKN	Embassy of the Kingdom of Netherlands
EOC	Emergency Oral Contraceptive
FDA	Food and Drug Administration
FMOH	Federal Ministry of Health
FP	Family Planning
FSW	Female Sex Workers
GOE	Government of Ethiopia
HEI	Higher Education Initiative
HIV	Human Immunodeficiency Virus
IEC	Information Education Communication
IUD	Intrauterine Device
MA	Medical Abortion
MAP	Measuring Access and Performance
MDG	Millennium Development Goals
MoU	Memorandum of Understanding
MTA	Market Town Activities
MVA	Manual Vacuum Aspiration
OC	Oral Contraceptive
ORS	Oral Rehydration Solution
OTS	Output Tracking Survey
PCR	Project Completion Review
PSI	Population Service International
RH	Reproductive Health
RIF	Reproductive Health Initiative Fund
SRA	Stringent Regulation Authority
SRH	Sexual and Reproductive Health
TA	Technical Assistance
UNFPA	United Nations Populations Fund
USAID	United States Agency for International Development
USD	United States Dollar
USG	United States Government
VFM	Value For Money
WHO	World Health Organization
WRA	Women of Reproductive Age

Summary of progress and lessons learnt since last review
DFID provides funding to DKT to implement the “Increasing Access to Sexual and Reproductive Health (RH) commodities” programme in Ethiopia. This Social Marketing Plus programme is also being supported by the Netherlands, and the Bill and Melinda Gates Foundation (BMGF). To date, the programme has received funding of £35.4m, of which £15.5 million (44%) has been contributed by DFID.

This Annual Review (AR) of Increasing Access to Reproductive Health Commodities programme in Ethiopia programme has met it output targets for the year 2014/15 (Score: A). This AR has also assessed the programme against its outcome targets and concluded, the programme has also substantially met its objectives and targets (with some being moderately exceeded). However, detailed progress towards outcome and impact will be provided by the upcoming Project Completion Report (PCR), scheduled for September 2016.

At the outcome level, the programme has improved the consistent use of condoms by Female Sex Workers (FSW) from 86% to 94%; reduced unprotected sex among university students from 78% to 64%; and increased the use of modern contraceptives among rural women of reproductive age from 32.2% to 44%. The programme hasn’t fully achieved the goals to improve FSW condom use with non-paying partners.

In terms of key outputs the programme has:
- In the review period, the programme has provided 2 million couples with a year that was potentially free of unwanted pregnancies and related complication.
- This year, the programme exceeded its Couple Years Protection (CYP) target by 10 % (2,025,981 compared to a target of 1,832,730). Cumulatively over its planned 4 year life, it has achieved 113% of the overall programme target for CYP (9,362,666 compared to a target of 8,268,265). Overall the average annual CYP delivered in this grant period (2011-2015) was 34% higher than the previous grant period (2008-2011).
- Met / exceeded promotional and information and communication activity targets for the year;
- Attained behavioural change among target audiences (FSW, students and rural women) across the key domains of opportunity, ability and motivation. Maintained a high degree of penetration in rural Ethiopia with around 90% of pharmaceutical outlets and clinical outlets in market towns stocking at least three DKT products.
- Positively influenced Ethiopia’s Reproductive Health (RH) policy environment through registration of five new product types; provision of Medical Abortion (MA) training to lower clinics; training of parliamentarians on RH; and technical support for local pharmaceutical manufacturers.
The programme has also continued to provide very good value for money (VFM). In the year under review, the programme achieved cost per CYP of $4.36 which is considerably lower the previous year ($4.92/ CYP). To-date, the programmes’ overall cost per CYP is $5.8 which is much lower than the global average $8.00 per CYP cost estimated.

However there were challenges in the year under review:
1. There is a shift in the market that the programme needs to adapt to, the shift is mainly driven by an increased free distribution of similar commodities by the Government of Ethiopia (GOE) and United States Agency for International Development (USAID) programmes. Although we have met our targets, the rate of growth in total CYPs distributed is getting slower this year. The reduction was driven by reductions in sales of three key commodities – condom (-20%); Intrauterine Device (IUD’s) (-51%) and implants (-92%). The reduction in condom sales is linked to the ‘leakage’ of free condoms being provided by USAID into the commercial sector. The reduction in IUD’s and implants reflects the cessation of marketing to outlets of these products that had occurred in the previous year.
2. There was also a reduction in Oral Contraceptive (OC) sales from 2013/14 to 2014/15 (-16%). This is important to note the Demographic Health Survey (DHS, 2011) data on the 70% discontinuation rate for OC by users. OC is preferred by beginners, youth and rural women who had limited access to a broad choice, therefore OC are considered as a point of entry in to family planning. However, the main cause of this reduction is not clearly known if it is linked with a simple discontinuation or a shift to other types of contraceptives.
3. In terms of the Developing Regional States (DRS) focus the sales of all products, including contraceptives, continued to be low. Most form of contraceptives decreased from this year to last year mainly because of improvements in free supply of these products through public health system, with some growth in sales of emergency contraception and safe birthing products. This raises a more fundamental question about what strategies are likely to work in relation to family planning in these areas, and if social marketing is the most appropriate approach.
4. Finally, in the course of 2014/15, faced with the planned end of the programme and limited certainty of funding beyond that, DKT undertook an assessment of the priority and value for money for all its activities. This process led it to a decision to scale back the 3 specific behaviour change projects under the programme – the rural social marketing, the higher education initiative, and the Wise-Up programme.
These decisions were taken towards the end of 2014/15 (in anticipation of the planned end of the programme in June 2015) and hence did not materially affect performance in 2014/15. DFID has issued a Costed-Extension to the programme through June 2016.

Summary of recommendations for the next year
This AR notes the programme is now in its final (extended year) and is operating at a reduced level of funding. DFID has currently fielded a consultant to look more broadly at the strategic options for DFID support to social marketing going forward in Ethiopia. In this context, this AR makes few major strategic recommendations.
In the context of changing nature of the Ethiopian Human Immunodeficiency Virus (HIV) and Family Planning (FP) programmes and the pattern of product sales achieved by DKT over the life of the current programme, DFID should develop a strategic approach to guide any future programming support for social marketing.

DFID and the Government of Ethiopia should assess the most appropriate and effective strategies and programme modalities to increase the accessibility and uptake of sexual and reproductive health services in remote/poor/underserved parts of Ethiopia after June 2016. This would include a critical assessment of the role, if any, of social marketing in this strategy.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202980/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202980/documents/

Outline of the programme

DFID provides funding to DKT to implement the “Increasing Access to Sexual and Reproductive Health (RH) commodities” programme in Ethiopia. This Social Marketing Plus programme is also being supported by the Netherlands, and the Bill and Melinda Gates Foundation (BMGF). To date, the programme has received funding of £35.4m, of which £15.5 million (44%) has been contributed by DFID.

DKT is the only organisation in Ethiopia engaged in the social marketing of a wide range of reproductive health commodities that include male and female condoms, short and long term contraceptives, lubricants and technologies for abortion. Furthermore, DKT distributes other health products, such as Oral Rehydration Solution (ORS) and ‘ORS with zinc’, for the management of infant and child diarrhoea.

As a complementary approach to the supply of RH commodities, the programme reaches different populations through a variety of behaviour change communication (BCC) approaches to increase demand for Sexual and Reproductive Health (SRH) commodities. Key target groups are: a) rural men and women through the Market Town Activities (MTA) initiative; and, b) female sex workers and their clients through the Wise UP initiative; and, c) youth including students in higher learning institutions. In addition, the programme has ‘Young Marketers’ initiative to engage youth clubs to market condoms on a commission basis.

The Social Marketing Plus programme contributes to progress towards Ethiopia’s health Millennium Development Goals (MDGs) targets, in particular the MDG 4&5 targets of reducing child and maternal mortality by improving the Contraceptive Prevalence Rate (CPR) and reducing fertility.

It is important to note the context of this programme has changed over the past 10 years and we are now anticipating another major change. Initially the programme was established to respond for the HIV epidemic by making condoms at a large scale. As the country succeeded in controlling HIV infection and the need for family planning / maternal health services grew the programme added family planning and abortion care commodities in its portfolio. Further, the programme serviced as a stop-gap partner to GoE by providing logistics and procurement functions. The programme then evolved by bringing a new focus of serving unreached and disadvantage populations though a tailored package of services.

Currently, despite the inequality and quality of services, the Federal Ministry of Health (FMOH) programmes and capacity have reached at a strong point that they can procure and distribute commodities in a large scale. In the context of a more capable public health system delivering an increasingly complex array of services, a key question is now emerging of the relative contributions of the public, subsidised private, and fully private sectors should be making to population health in Ethiopia. This AR, and a companion consultant led exercise on the future direction of the social marketing programme, is very much framed by this changing context.

What are the expected results?

The programme’s outputs are: increased supply of RH commodities; increased demand for RH commodities; and, strengthened environment and capacity for the supply and promotion of RH products and services. These outputs in turn contribute to outcome indicators related to the consistent use of condoms by female sex workers; reduction in unprotected sex amongst university students; and increased contraceptive prevalence amongst women of reproductive age in market towns.

In terms of health impact, the Business Case estimated the programme would avert:
- 2.5 million unintended pregnancies
- More than 8,000 maternal deaths
- More than 240,000 total abortions
- Between 35,000 and 100,000 HIV transmissions
B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Overall at an outcome level this Annual Review concludes the programme has met / moderately exceeded its objectives.

The programme has 3 outcomes and 4 outcome indicators. The performances against these indicators are derived from baseline and end-line surveys which measured a range of behaviour change and access variables. We would like to note that this evaluation was a “Pre-Post implementation” comparison than an experimental design with controls. Due to inherited limitation of the non-experimental evaluations, we can’t single out DKT’s specific attribution on the behavioural improvements reported. However, the findings confirm that DKT’s contribution was very important given the level of statistically significant difference in outcomes at the beginning and end of the DKT’s activities.

Indicator(s)	Baseline (2011)	Target (2015)	Achievement / (2015)	Score
Percentage of female sex workers in DKT Wise Up towns reporting consistent condom use in the last 7 days with paying partners increases from 86% to 90%	86%	90%	94%	A
Percentage of female sex workers in DKT Wise Up towns reporting consistent condom use in the last 30 days with non- paying partners increases from 43% to 60%	43% / (27% OTS 2012)	60%	36%	B[1]
[1] See discussion below for justification of score

Outcome 2: Decrease in unprotected sex among students in DKT HEI Universities
Percentage of students reporting having unprotected sex in past 12 months declines from 78% to 70% in DKT Higher Education Initiatives (HEIs) Universities	78%	70%	64.3%	A+
Outcome 3: Increase in CPR in DKT project areas
Percentage of Women in Reproductive Age (WRA) in Market Town project areas who use a modern method of contraception increases from baseline to end line	32.2%	Increased	44%	A++[2]
[2] No formal target set but A+ based on significant difference between project exposed and non-exposed.

The programme has substantially met or moderately exceeded three of the four planned outcome targets). This positive behavioural change (in here and under Output 2) were achieved due to a systematic application of tailored BCC tools that combined enough doses of Interpersonal counselling, mass media and strong referral services.

The percentage of female sex workers who were exposed to these programmes increased their reported consistent use of condoms with paying partners from 86% at baseline to 94% at end-line. This exceeded the target of 90% and compares to 92% for those not exposed to the DKT intervention. From a high base this represents a good programme achievement.

The percentage of FSW who reported consistent condom use with non-paying partners showed less progress – albeit against a more ambitious target. The reported end-line data shows a rate of 36% of FSW exposed to DKT interventions reported consistent condom use with non-paying partners in 2015. This is less than the reported baseline of 43%; well below the target of 60%. Intervention. This is one of the most difficult behavioural indicators to track and compare over period of time, due to sensitivity and technical challenges. Moreover, the intention of this program to bring such a significant impact on one of the most difficult behavioural change needs to be reviewed in future programming. The programme team view is that the baseline figure of 43% was probably an overestimate. A revised measure of this indicator conducted in the output tracking survey (OTS) in 2013 produced a much lower estimate of 27% use.

The percentage of students exposed to the programme reporting having unprotected sex in the past 12 months decreased from 78% at baseline to 64% at end-line. This has moderately exceeded the target of 70%, and substantially better than the reported rate for those students not exposed to the DKT intervention (78.9%). Whilst this is a good achievement, the rates of unprotected sex are still high suggesting that more work is required to understand the drivers of behaviour change in this particular group.

The percentage of women of reproductive age in the project areas increased their use of modern contraceptives from 32.2% at baseline to 44%. Whilst there was no target set for this indicator, this is substantially higher than those not exposed to the DKT intervention and the estimated national CPR for rural women (estimated to be 34 and 37%, respectively).

Overall output score and description:

Overall, at an output level for this review period (2014/15), this Annual Review concludes the programme has met expectations all three outputs to score (A).

Key lessons:

DKT is operating effective, complex national social marketing operation across Ethiopia that is delivering tangible reproductive health services to the population in a cost efficient manner.

There is a tension between equity and efficiency in the delivery of the social marketing programme. As long as the objectives and payment incentives for social marketing companies remain on CYPs, if/when budgets get tight it is logical for these companies to reduce costly/low CYP return efforts and focus on larger, easier to reach, higher CYP yield population groups. This will often reduce the accessibility of the programme to the poorer/harder to reach. The Government and Donors will need to think carefully about their objective for social marketing and structure budgets and payment incentives accordingly.

There is a need to constantly calibrate social marketing programmes with the operating environment. It is clear that the Ethiopian public health system has strengthened over the past 10 years and is now providing efficiently and effectively some of the products/services also being provided by the social marketing programme.

Has the logframe been updated since the last review?
Yes. In August 2014, DFID and DKT agreed to reduce the 2014/15 end-line targets for output indicator 1.5 (% of non-pharmaceutical outlets in urban areas stocking condoms) and 1.6 (% of urban towns meeting minimum standards – 2/1000 population – for condoms in non-pharmaceutical outlets. These were reduced from 40% to 35% and 50% to 40% respectively. This reflected the challenge the programme was (and continues) to face from the freely distributed USAID/Population Service International (PSI) condoms.

C: DETAILED OUTPUT SCORING

Output 1	Improved supply of reproductive health products in rural and urban Ethiopia
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	60%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N

Score: A - This output has met its targets. All six indicators of the Output 1 have been assessed during this annual review.

Description: This core output measures the quantity of commodities distributed, the coverage and reach of products in the country. Data is gathered based on project documents, DKT sales figures and Market Penetration Surveys.

Indicator(s)	Target (2015)	Achievement / (2015)	Score
Couple years protection provided by reproductive / health products sold by DKT[3]	1,832,730	2,025,981	A+
1.2 % of pharmaceutical outlets in (rural) market towns stocking at least three DKT RH product categories	80%	91%	A
1.3 % of (rural) market town service providers (clinical outlets) stock at least three DKT RH products	80%	90.1%	A
1.4 % of urban (excluding rural market towns) pharmaceutical outlets stocking at least five DKT product categories	76%	71.2%	B
1.5 % of non-pharmaceutical outlets in urban areas stock condoms	35%	17.1%	C
1.6 % of the urban towns meet minimum coverage standards (2 outlets/ 1000 population) for condom in non-pharmaceutical outlets	40%	26.1%	C
[3] Data covers the period of July -June for each year.

Key Points
Cumulatively the programme has achieved 113% of the overall programme target for CYPs (9,362,666 compared to a target of 8,268,265). For the year under review, the programme exceeded its target by 10.5% (2,025,981 compared to a target of 1,832,730). Overall the average annual CYPs delivered in this grant period (2011-2015) was 34% higher than the previous grant period (2008-2011).

This year we have noted a stronger sign of shift in the SRH market: 3 products became popular, while 3 other products lost demand. Injectables, Medical Abortion pill and post abortion became more popular, while demand was lost for condoms and long-term contraceptives (IUD and Implants). However, in terms of total sales, offsetting the reduction in condoms, IUD’s and implants were increases in sales of emergency contraception (40%); injectables (32%); Manual Vacuum Aspiration (MVA) kits (237%); medical abortion drugs (41%).

There shift in the demand was probably shaped by shift in users’ preference, increased free commodities and to the improved GoE’s capacity in procuring and distribution of commodities. While we have met our targets, the rate of growth in total CYPs distributed is getting slower this year. The reduction from 2013/14 to 2014/15 was driven by reductions in sales of three key commodities – condoms (-20%); IUD (-51%) and implants (-92%). The reduction in condom sales is linked to the improved availability of quality free condoms being provided by USAID. The FMOH used grants from “the Large Anonymous Donor” to procure and distribute free IUDs. The reduction in IUD’s and implants reflects the cessation of purposeful marketing to outlets of these products by DKT. It is important to use this information to better understand the strategic role of social marketing in a national family planning programme. See table 1 (sales performance) for details.

Further in 2014/15, the programme achieved a revenue return of 28% - which was the highest ever for the programme. This result was based on a decision to review, and increase slightly the prices charged for certain products.

The programme has maintained a high degree of penetration in rural Ethiopia with around 90% of pharmaceutical outlets and clinical outlets in market towns stocking at least three DKT products. This is above the target of 80%. Over the life of the programme the proportion of pharmaceutical outlets with 3 or more DKT products remained constant, and a slight decrease in the proportion of rural market town service providers with 3 or more DKT products. Both remained above the ‘target’.

The Rural Social Marketing Programme through the market access teams operated in 835 towns before scaling back to 200 towards the end of the year to fit with the expected. Despite a high level of activity (at a relatively high cost) this activity provided only about 5% of the programme’s CYP.

In terms of the Developing Regional States (Afar, Gambella, and Somali) sales of all products, including contraceptives, continued to be low. Most form of contraceptives decreased from this year to last, although there were increases in sales of emergency contraception and safe birthing products.

The Young Marketers programme continued as an innovative and effective mechanism to distribute and reach young people with condoms. The programme deploys 200 anti-AIDS clubs nationwide to progress retail sales in their communities. In the year under review, this programme was responsible for selling 41% of DKT’s condoms – a substantial increase over the previous year.

The data suggests there is a continuing displacement problem between DKT socially marketed condoms and free condoms provided by USAID and distributed by PSI. Indicators related to the percentage of non-pharmaceutical outlets in urban areas stocking DKT condoms show decrease over the life of the programme and subsequently are substantially below target.

Recommendations

In the context of changing nature of the Ethiopian HIV and family planning programmes, epidemiology and the pattern of product sales achieved by DKT over the life of the current programme, DFID should review its approach for future programming support of social marketing. This strategy should be informed by the Government of Ethiopia and DFID strategic objectives for sexual and reproductive health services and the specific strategic value add of social marketing for individual products for specific populations.

Future programming needs to consider the relevance of non-traditional outlets as a main route of condoms distribution competing against free condoms.

Summary of responses to issues raised in previous annual reviews

Issues raised during previous annual reviews	Progress
While the success of the rural MTA programmes is noted, this approach needs to be evaluated in terms of its scalability (ability to reach out to all rural markets), cost and VFM. Also, the linkages between the rural MTA initiative and primary health care delivery system (particularly with Health Extension Workers and Health Development Army) need to be strengthened.	In the course of 2014/15, faced with the planned end of the programme in June 2015 and no certainty of funding beyond that (and indeed messages from donors that funding was unlikely to continue at the level of this grant), DKT was more or less forced to undertake an assessment of the priority and VFM for all its activities. This process led it to a decision to scale back the rural social marketing programme by reducing the number of teams from 15 to 6 and focussing on 200 high volume rural towns rather than 835. The selected towns were chosen on the basis of larger population and lower contraceptive prevalence. The strategy allowed these fewer towns to be visited more frequently.
The programme’s approach of promoting branded family planning products (of one agency) rather than promoting categories of family planning products needs to be evaluated.	DKT’s rural social marketing teams start with general family planning promotion and awareness. This process is not brand specific. DKT’s other work is brand led – this is the nature of their business model. The issue of a broader evaluation of competing approaches should be considered by the Government in its family planning strategy.
Sustainability is the main risk for this programme, any follow on to this programme needs to clearly outline strategies that increase sustainable access of RH commodities for different socio-economic groups in Ethiopia.	Both DKT and DFID are aware of this and progressing work to address the issue of sustainability in any follow-up programme. DFID has a strategic consultant currently considering options for possible future programming in this area – including objectives and balancing the efficiency/ equity trade-off.
To develop a condom promotion strategy, which is embedded in the national strategy; and is clear on the comparative advantage of DKT’s efforts in terms of the public health impact	A draft condom promotion strategy has been developed and is awaiting approval by the GoE. DKT contributed to this strategy via the technical working group. There would seem to be scope for all sectors – public, subsidised private and full private – to improve their audience segmentation vis-à-vis condoms.
Based on the Measuring Access and Performance (MAP) survey findings, DKT needs to understand why it has not been successful in promoting condoms and RH commodities in in urban non-traditional outlets and devise a strategy to increase coverage through these outlets.	This recommendation should have applied only to condoms as it is illegal to sell other reproductive health products in non-traditional outlets. DKT is working to use expand condom availability through non-traditional outlets via use of MAP results and the work of the Young Marketers. However they believe there is a point of diminishing return given the rapid expansion of pharmaceutical and drug stores that also carry condoms and United States Government (USG) aggressively distributing free condoms through non-traditional outlets.

Output 2.	Increasing demand for reproductive health (RH) products
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Score: A – This output has met its targets.

Description: Creating demand is important for making sure that products are purchased and used which is the main objective of this programme in order to reduce RH related death and morbidity.

Progress against targets: All 13 indicators of the Output 2 have been assessed through this annual review. In this review period DKT commissioned a final Behavioural Change Impact Survey (BCIS), which informed this review.

Indicator	Target (2015)	Achievement (2015)	Score
2.1 BCC for the sex workers activities / Opportunity: ‘Social Norms’ score increases from 3.12 to 4.5 among FSW / Ability: ‘Self Efficacy’ score increases from 4.63 to 4.80 among FSW / Motivation: ‘Attitude’ score increases from 4.23 to 4.6 / Number of FSW with non-paying partners received key HIV prevention messages including 'boyfriend' messages	4.50 / 4.80 / 4.6 / 4,000	2.78 / 4.83 / n/a / 4,335	A / C / A / n/a [4] / A+
2.2 BCC WRA in Market Town Project / Opportunity: score increases among WRA / Ability: score increases among WRA / Motivation: score increases among WRA / Number of counselled for FP in market towns	4.00 / 3.30 / 4.00 / 48,000	4.30 / 3.6 / 3.7 / 42,651	A / A+ / A+ / B / B
2.3 Higher Education Institutions BCC / Opportunity: score increases among HEI students[5] / Ability: score increases among HEI students / Motivation: score increases among HEI students / No of events with male target group / No of events with female target group	Improved / Improved / Improved / 250 / 500	Improved (3.77 vs 3.37) / Improved from 3.5 to 3.6 / Not improved from 3.3 / 371 / 247	A / A / A / B / A+ / C
[4] Not reported in the endline survey but on-track to meet target based on 2013/14 achievement in OTS.

Key Points
- DKT continued to perform well in terms of meeting and exceeding targets related demand creation and promotion activities across the programme. In the period under review, the programme:
  - Increased radio spots by 30% and television spots by 20% over the previous year;
  - Increased the number of billboards across the country by 23% over the previous year;
  - Branded 20 cross-country buses and 6 DKT vehicles;
  - Ran numerous sponsored events, including the social media selection of Sensation Brand Ambassadors which resulted in a 23 fold increase in facebook ‘likes’ of the DKT site;
  - Distributed 723,104 promotional materials, a 25% reduction over the previous year.

In terms of project specific behaviour change projects – rural social marketing, higher education institute initiative, and Wise-Up, DKT has substantially meeting their targets.
 In the period under review:
  - Despite reducing the reach of the rural social marketing from 835 to 200 towns towards the end of the year, the rural social marketing teams conducted 2,900 market town events that reached 891,921 people (63% women); hosted 15,026 small group discussions; and counselled and referred 42,651 and 26,383 people respectively.
  - 78% of all the mothers counselled and referred by the market town team received family planning services in collaborating local private clinics. The success rate in the referral increased from the 25% of last year.
  - The HEI initiative introduced gender specific block-to-block sessions. The programme exceeded targets for male block-to-block events but although increasing the number of female block-to-block sessions from the previous year fell short of the ambitious target of 500.
  - The Wise-Up outreach workers provided 247,283 services to female sex workers at drop-in centres in the year completed – a slight increase over the 244,316 services in 2013/14.

As described above, driven by an impending budget reduction, DKT has conducted a comprehensive cost driver analysis of its promotional activities. This has resulted in a radical shift in its rural social marketing programme and Wise Up programmes with in effect these programmes prioritising efficiency over equity by focussing more intensely on easier to reach/higher population areas. The HEI programme has been discontinued (although with a phased transition plan –see progress against recommendations below).

Recommendations

DFID should assess the most appropriate and effective strategies and programme modalities to increase the accessibility and uptake of sexual and reproductive health services in remote/poor/underserved parts of Ethiopia. This would include a critical assessment of the role, if any, of social marketing in this strategy.

Summary of responses to issues raised in previous annual reviews
Issues raised during previous AR	Progress
The VFM analysis for contraceptive commodities (as the principal cost driver of this programme) is strong. It is recommended that such rigorous VFM analysis should also be done for other cost drivers, in particular for the demand creation/ communication/ promotion activities.	This has been done by DKT in relation to the reduced programme budget for 2015/16 (see above).
Explore approaches to target young women, just after their first birth, for promoting the use of spacing method.	DKT has incorporated into the training of the rural social marketing teams the importance of focusing on first birth and young married women, including particular strategies to reach them at market sessions without producing stigma.
Continue assessing the opportunities and challenges in scaling up commodity distribution in Afar and Somali region. Investigate the reasons for the intermittent slowdown in the distribution of OCs in Somali region.	DKT has worked with the Regional Health Bureau’s in these regions to reach agreement for the market access teams to provide on the spot services, rather than refer to outlets (which are difficult to establish in these areas). / However as discussed under Output 1, this does not appear to be gaining traction and a different approach may be required.
Link DKT demand and supply side initiatives with DFID’s demand side programme in emerging regions (the Reproductive Health Innovation Fund – RIF).	DKT has made initial contact with Pathfinder (the RIF manager) but acknowledges that this has not progressed substantially, given RIF has not made a lot of progress at grass root level.
To start consolidating and transitioning out of HIV prevention programmes at Higher Education facilities.	DKT has developed a transition plan for the HEI recognising it is unlikely to continue to receive donor funding. This has involved several workshops with university management designed to encourage universities to allocate their own resources to carry on at least some of the activities, with DKT providing commodities and providing TA on a transition basis. DKT report that to date 11 of the 27 participating universities have agreed to this plan and allocated resources accordingly.
The follow-on to this programme could investigate linking with other initiatives to empower women and girls and maximize their non- reproductive functions to help them sustain their desire to manage their family size.	This is being taken forward by the DFID strategic consultant.

Output 3	Improved environment and capacity for the supply and promotion of RH products and services
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Score: A - This output has met its targets

Description: The provision of sexual and reproductive health services in Ethiopia exist in a complex institutional environment involving government, and non-state actors. An important aim of this programme is for DKT to interact and where possible influence this environment to facilitate improve access to RH products and services for the people of Ethiopia.

Progress against targets: All three indicators in output 3 have been assessed in this Annual Review.

Indicator(s)	Milestones	Progress	Score
Increased number of outlets reporting positive experience of DKT training, detailing visits	80%	82%[6]	A
Improved policies supporting private sector distribution of RH products	Improved policies	Progress satisfactory	A
Research methodology and results shared with RH community	Quality research conducted and disseminated	Progress satisfactory	A
[6] 82% represents the level of change in pre and post training tests taken by the trainees trained by DKT in 2014/15. This data was collected during training sessions for medical abortion (2115 participants) and LemLem plus (772 participants) as a proxy to measure the indicator 1.3

Key Points
DKT continued to engage productively with Ethiopia’s Reproductive, Maternal and Neonatal Health policy environment during the review period. DKT has been influential in negotiating for the registration, importation and decentralized use of life saving RH commodities. This year DKT sought first-time registration for five products in Ethiopia – three variants of emergency contraception, an IUCD and a misoprostol regime. Of these 2 have been successfully registered and the others are in process. The new EC products are single tablet doses that may be preferred by clients.

During the review period, the Government revised the National Technical and Procedural Guidelines for Safe Abortion which allowed providers from lower clinics to administer medical abortion. In response, DKT trained 1,851 providers on MA, 46% of which were from lower clinics.

- DKT also trained 200 members of the House of Peoples Representatives for Women Affairs in RH/FP advocacy.
- During the review period, DKT also supported a local pharmaceutical manufacturer to develop a product (chlorhexidine 7.1%) for the local market. Although funded by the Gates foundation, it does demonstrate the breadth and strategic nature of DKT support to Ethiopia.

DKT also continues to work closely with the Government of Ethiopia. It has just signed new 5 year Memorandum of Understanding (MoU) with the Government to cover its work for the next five years. DKT also participated in a wide variety of FMoH technical working groups related to family planning, contraceptive forecasting, abortion care, and HIV prevention.

- During the review period, DKT also conducted and disseminated a range of research. This included:
  - MAP survey of market towns and big urban areas (rounds 2 and 3);
  - MAP survey of condom coverage and penetration in non-traditional outlets in urban areas (rounds 3 and 4);
  - Rural behaviour change impact end-line survey (BCIS) in 6 regions;
  - Output tracking survey (OTS) and BCIS end-line university students;
  - OTS and BCIS (end-line) female sex workers;
  - Study on repeat use of Postpill
  - ORS market assessment

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

The programme has progressively achieved a high VFM level by as the capital investments in on promotion of commodities, logistic systems and community mobilization are increasing demand and efficiency. The programme continues to represent good VFM.
Key cost drivers and performance:

During the review period, the programme/DKT received a sum of £4.3m from donors of which DFID contributed £3m (70%); the Embassy of Kingdom of Netherlands (EKN) contributed about £1.3m. An additional £1.4m came from sales revenue. With a total expenditure of £5.7m, commodities consumed slightly over 28% of all expenditures; advertising, promotional Information, Education and Communication (IEC)/Public Relation consumed 32%; and training and advocacy consuming 14%.Transportaion and human resource expenses makes the remaining smaller proportion of the cost.

VFM performance compared to the original proposition in the business case

Commodity Procurement
The table below shows the unit costs of different RH commodities procured by DKT and other main suppliers, i.e. USAID and United Nations Populations Fund (UNFPA). Of the 16 product items procured, DKT enjoyed a favourable advantage in the costs of 11 items; added to this is the fact that DKT is the sole procurer of 3 of the products for which costs can’t be compared. Please refer the annex for a detailed table and source information of the figure below.

Fig 1. The 2014/5 unit cost in USD per selected contraceptive procured by DKT, USAID and UNFPA

DKT’s product costs shown in the figure above also include the cost of branded packaging whereas the products from USAID and UNFPA do not. This means that the actual cost of the commodity through DKT is in fact lower than the costs here. These prices reflect an extremely successful negotiation process that DKT has established with the suppliers which allows very competitive prices. However commodities procured by USAID have to meet the Food and Drug Administration (FDA)/ Stringent Regulation Authority (SRA) requirements, which usually make the production cost expensive. DKT advice when a product does not come from a SRA or a World Health Organization (WHO) prequalified supplier, DKT conducts independent international quality assurance tests on procured products.

Promotional Activities
Based on the recommendations of the last year’s Annual Review, DKT has conducted a comprehensive cost driver analysis of its promotional activities. This has resulted in a radical shift in its rural social marketing programme and Wise Up programmes with in effect these programmes prioritising efficiency over equity by focussing more intensely on easier to reach/higher population areas. Going forward this would reduce the proportion of the budget going to promotion/IEC from the relatively high 32% achieved in the year under review.

Cost per CYP generated

Fig 2: Cost per CYP compared over the last four years
The programme is achieving a very competitive cost per CYP. In the year under review, the programme achieved cost per CYP of $4.36 which is considerably lower the previous year ($4.92 / CYP). To-date, the programmes’ overall cost per CYP is $5.8 which is much lower than the global average $8.00 per CYP cost estimated.

Efficiency
Improvements in operational efficiency have been gained through DKT’s continued capacity building of FMOH and private sector actors/retailers in doing forecast, promotion, and distribution of RH commodities. DKT has trained 1,851 health workers in rational use of medical abortion drugs to increase efficiency and quality of services. DKT has also assisted the government to register two new products, making it easier for future importation of the commodities. This year, the programme has made a decision to scale back from its low yield and expensive out-reach rural towns.
Cost per Health Impact
Preliminary estimates suggest that over the course of the review period, contraceptives and other RH commodities that DKT distributed have: a) prevented an estimated 755,798 unintended pregnancies, and, b) averted an estimated 11,342 HIV transmissions. These outcomes in turn have produced an estimated 1,437,655 maternal healthy life years (DALYs). With these preliminary numbers, the cost at which this programme has averted reproductive morbidity and mortality appears impressive: $16.9/unintended pregnancy; and, $9/maternal DALY. These preliminary cost estimates are significantly lower than the global average of $28 and $62 respectively. DFID Ethiopia will carry out a robust modelling exercise to finalize these cost estimates as per the global and regional norms, and document lessons learnt while preparing the Project Completion Report (PCR) for this programme.
Assessment of whether the programme continues to represent value for money: This programme continues to be valid and offer good value for money. The programme’s ToC is valid and preliminary assessment at outcome and impact level suggests results have been attained as originally planned in the ToC. DKT has continued to be relevant in the national SRH landscape; we have provided 20-30% of all nationally distributed commodities. Our VFM has continued to be high as gauged by strong economy and effectiveness indicators. DKT’s cost per CYP of $5.80 is below the estimated global average of $8.00 per year per woman using contraception[7]. Continued efficiency improvement was attained by improving forecasting, logistics and rational use of SRH commodities.
[7] Singh S et al. adding it Up: The Costs and Benefits of Investing in Family Planning and Maternal and Newborn Health. Guttmacher Institute and UNFPA; 2009. P. 18 (also cited in DFID’s RMNH Framework for Results, December 2010. P. 10)

Quality of financial management: This is a milestone based payment contract arrangement. DFID has received unqualified audit report for the review period. DKT’s annual report provides an accurate picture of financial data for the period under review, including comprehensive expenditure summaries, and a cash flow analysis with opening and closing cash balances. The last external audit report covered the 2014 fiscal year and was completed by March 2015.

Year	Budget	Disbursement	Variance
2011	6,500,000	6,500,000	Nil
2012	2,800,000	2,800,000	Nil
2013	3,000,000	3,000,000	Nil
2014 / 2015	2,000,000 / 3,000,000	2,000,000 / 3,000,000	Nil / Nil

E: RISK (½ page)

Overall risk rating: Low

Overview of programme risk: There is an emerging risk as more products are added to the social marketing menu in Ethiopia, particularly those that have a clinical service delivery element (eg IUD insertion and medical abortion drugs) that the quality of services provided by pharmacies and clinics may be variable. DKT provides trainings for health workers. However, this risk and its mitigation actions shall be considered in-depth in future programming.

Sustainability has stayed to be the main programmatic risk for this programme. Given the dominance of the DKT brands, particularly the condoms in the Ethiopian market, a clear sustainability plan is required by both DFID and DKT. DKT has developed a five-year strategic plan to guide their own sustainably. DFID currently has a consultant working on strategic options for future social marketing support in Ethiopia which will take account of sustainability issues.

F: COMMERCIAL CONSIDERATIONS (½ page)

DKT is on target, or ahead of schedule, for programme deliverables. DFID needs to determine if and how it shall continue social marketing of SRH commodities. The current programme with its extension ends in June 2016.

In the years to come DKT plans to transition from a donor dependent entity to a partially self-supporting organization. This is prompted by the following considerations:
1. Plans by the Government of Ethiopia to achieve the status of a middle income country by 2025;
2. Growing urban population with increased purchasing power will facilitate the growth of private medical and RH suppliers.
3. The public sector’s increasing reliance on its own procurement system that has reduced its dependency on DKT’s commodities and services;
4. DFID’s and other donors funding capacity for such programmes may not stay the same during and beyond the next 5 years

Asset monitoring and control
No issues have arisen during the review period.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Given that this programme does not include direct funding to the Government of Ethiopia DFID’s conditionality policy and partnership principles are not relevant.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation: Monitoring progress throughout the review period:

M&E activities undertaken during the review period include:
Supportive supervision provided to all regions by DKT to ensure the smooth implementation of all programmatic activities.  The DKT M&E team undertakes supportive supervisions to all the regions on a monthly basis. These supervision visits focus on assessing: the coverage and penetration products; customer satisfaction and quality of services. The visits have proven to be very effective tools to assist DKT deliverables and support regional offices to increase coverage, quality and penetration of DKT commodities.

- Developing report formats and monitoring checklists for all Regional Heads, programme staff, and the Regional Management Team to track the MTA teams’ performance and identify gaps.
- DKT collected information on condom distribution outlets and RH service delivery facilities accessible to university students. This information was analysed and posted on the new TemariNet website.
- DKT has generating monthly regional sales data and compared them against performance indicators.
- Sales performance summaries and detailed reports were produced and disseminated to the Regional Offices for staff appraisal for programme monitoring, and developing action plans.
- A number of key surveys (the Behavioural Change Impact Survey and Output Tracking Survey - OTS) and other research pieces (listed under output 3) have been conducted to measure success of the demand creation and distribution activities.

The core team for this annual review included: Andrew McNee, Health Adviser in DFID’s Malawi Office; Kassa Mohammad, Health Adviser and Atsednesh Getachew, Programme Officer in DFID Ethiopia. The team also benefited from the input of Mr Bruce McKay and independent consultant commissioned by DFID to conduct a strategic review of the future direction of DFID’s social marketing support in Ethiopia. The review team carried out interviews with all key stakeholders including DKT national, regional and local staff, PSI, and DFID Ethiopia Human Development Team members. A number of key documents were also consulted as part of this review including: the BC, Logframe; previous annual reviews; and, DKT’s quarter and annual progress reports.

This Annual Review has been Quality Assured within DFID Ethiopia by Jyoti Shankar Tewari (Senior Human Development Adviser), Angela Spilsbury (Human Development Team Leader) and DFIDE OPEX team. Comments from the DFIDE OPEX team have been incorporated.

Annex 1