Type of Review: Project Completion Review

Project Title: Somaliland Election Programme – Project Completion Report

Date started: September 2012	Date review undertaken: November 2013
## Introduction and Context

What support did the UK provide?
The UK provided £3,447,093 under the Somaliland Elections Project to ensure that the 2012 local elections were free and fair and contributed to strengthening democracy in Somaliland. / The programme was initially intended to run from March 2010 to March 2012. However, the election date was repeatedly delayed and as a result no activities took place and no funding was disbursed during the original timeframe of the programme. As the election date became clearer, a project extension was provided up until the end of September 2013 which enabled support for both the elections themselves (which were held on 28 November 2012) and post-election work.
What were the Expected Results?
The three intended outputs of this intervention were: / Programme contributing to a successful election day / Somaliland democratisation process coordinated / Accountability of local councils strengthened through increased citizen participation / The programme was delivered by four implementing partners: International Republican Institute (who sub-contracted Progressio), Oxfam, Centre for Humanitarian Dialogue, and Saferworld.
What was the context in which UK support was provided?
Since 1991, Somaliland has stood out from the rest of Somalia as a result of its relative peace and stability. Success in Somaliland remains integral to the short and long-term development of the wider Somalia, as well as a stable Somaliland. The series of elections since 2002 (municipal 2002, presidential 2003, parliamentary 2005 and presidential 2010) have been milestones in post-conflict peace building and state building in Somaliland, with high public participation. DFID’s support for the 2012 elections was intended to help continue this trend. DFID was well placed to do this given the UK’s historic links and good relations with the Somaliland government and its leading role amongst international partners in supporting Somaliland’s development. / At the time this project was conceived, successful home-grown, clan-based mediation systems had helped deliver peace and reconciliation, and avoid major outbreaks of conflict in Somaliland. But despite the overall positive progress, elections in Somaliland were often faced with delays and irregularities. The most marked example of this was the introduction of a voter registration system in 2007/2008 prior to the Presidential elections where there were reports of fraud, with clans using the process to conflate their individual clan numbers so as to win the elections. As a consequence, the National Election Commission (NEC) declared that elections could be held without a voter list – spurring a political (and potentially violent) crisis. The international community, led by Ethiopia and the UK, managed to bring back Somaliland from the brink by facilitating an agreement between the political parties. / Presidential elections finally took place in 2010 after a delay of two years, with a peaceful transfer of power to the opposition, led by Ahmed Mahmoud Silanyo, from the Peace and Unite Party. The relatively free and fair manner in which the 2010 Presidential election was held indicated a continuing trend towards a political system of multiparty representative democracy in Somaliland. At the same time, the success of staging the election owed much to international diplomacy and technical assistance. / In February 2011, President Silanyo committed to holding new district council elections in 2011. This commitment was subsequently revised to “within 2012”, by which time the councils had been in post for nine years, and their re-election were five years overdue. In September 2012 it was finally announced that elections would be held on 28 November, 2012. / The 2012 district council elections served to determine which three (out of fifteen) political parties would achieve legal status under the Constitution, and would thus be able to contest Parliamentary and Presidential elections for the next decade. / The INGO Interpeace provides technical advisory services and critically coordinates donor engagement across wider Somalia around peace and democracy. For the elections 2012 Interpeace (separately financed by other donors) worked in close cooperation with the NEC, providing capacity building in the lead-up to the elections. DFID support for its four partners was divided along the following lines: IRI leading on political parties and local electoral processes who sub-contracted Progressio to coordinate election observation, Oxfam focused on increasing the participation of citizens, CHD embedding an electoral dispute mechanism, and Saferworld drawing on the non-state actors platforms to actively engage citizens in policy dialogue activities. Coordination of the UK’s bilateral support and Interpeace centred on the Nairobi-based ‘Democratisation Steering Committee’ – a donor agency coordination group.

## Section A: Detailed Output Scoring
Output 1: Programme Contributing to a Successful Election Day
Output 1 Indicators Baseline Target Actual Score / Indicator (1.1) / Number of political agents trained by the programme that deploy on Election Day 5381 polling agents were paid to deploy by NEC in 2010 500 Total / 50 women / 450 men 9,374 party agents trained ahead of election day (500 women). / The difference vis-à-vis the baseline is that in 2010 a significant number of polling agents were deployed, but not trained. / The relatively low target (with hindsight) was set to ensure that political agents were trained in advance of election day with clear roles and responsibilities. This represents a major quality differentiation but, as transpired, using implementing partners with extensive reach across Somaliland meant that the target of 500 was far too low as shown by the impressive result of 9,374 trained political agents (for which credit must be given to our implementing partners). A + / Indicator (1.2) / Election dispute mechanism framework in place including election dispute resolution mechanism and code of conduct Mechanism used for 2010 election Adapted mechanism agreed and in place A new election dispute mechanism, with clearer roles and systems, was approved by NEC and in place before the election. / Trainers for polling staff explained the relevance of the complaints form, the processing of the complaints form, and procedures to be followed. The complaints form system was included in the polling and counting manual. A registry for complaints recorded all complaints from all the districts for submission to the NEC. 20,000 complaints forms were available and distributed across all polling stations in all districts. / The election dispute mechanism was received positively from stakeholders, including the Registration of the Political Associations and Approval of National Parties Committee (RAC), the NEC and regional judges who were trained on its application. There was broad awareness of the mechanism across the voter population. A / Indicator (1.3) / Number of Voters Presidential elections in 2010: 538,246 Same or increased turnout as 2010 elections 810,858 voters / This programme is likely to have contributed to this impressive turnout as a result of the established electoral law, civic education and overall media coverage (such as a statement from the President). These activities enabled a peaceful election day in which the citizens of Somaliland were free to engage. A+ / Indicator (1.4) / Number of trained domestic observers trained and deployed on election day. Number from 2010 elections 400 3,477 polling station workers trained / This target was substantially overshot because polling station training was provided by more than one of the implementing partners, whereas the original target focused on IRI training only. During the programme IRI was asked to “train as many agents as possible.” / As with indicator 1.1 this results far surpasses the original target. Again this can be attributed to DFID financing and using implementing partners with extensive reach across Somaliland resulting in the training of 3,477 polling station workers trained (for which credit must be given to our implementing partners). A+ / Indicator (1.5) / Number of polling stations open and ready on time for polling on election day No baseline At least 85% of polling stations open There was no reporting of any polling stations being closed or disputed on polling day. / Domestic observers at almost 60% of polling stations – a 15% per cent increase on the coverage achieved in 2010 – reported that the overall atmosphere was calm and peaceful. There were no reports of any violent disturbances at the other 40% of polling stations on election day. 51 % of polling stations were chaired by women. The NEC had not prepared a map detailing where all 1,844 polling stations were located. / Domestic observers’ feedback stated that staff generally arrived at the polling station one hour before opening and remained until closing and counting was implemented according to the law, and the presence of agents for parties and associations confirmed that NEC staff adhered to the guidelines. A / Indicator (1.6) / Number of international election observers deployed Number from 2010 election Number from 2012 election 50 international election observers, from 17 countries, including 22 women, and 7 from the Somaliland diaspora. The international election observer mission successfully observed polling in 306 stations, a significant achievement. A+ / Final results: A + / Impact Weighting (%): 70 / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No
Output 2: Somaliland Democratisation Process Coordinated
Output 2 Indicators Baseline Target Actual Score / Indicator (2.1) / Number of policy position papers developed and shared with National Electoral Commission / Government of Somaliland Zero Three There was no direct reporting on the number of position papers developed and shared. / However, implementing partners influenced Government policy in significant ways, for example: i) large-scale consultations which informed prospective councillors on citizens’ concerns and development needs, ii) key decision-makers, including the President were successfully lobbied to hold a public meeting (broadcast over radio and television), on the voting procedure and discuss the forthcoming election itself; and iii) partners contributed to the formation of an Inter-Party Advisory Committee for coordination between political parties and the NEC. B / Indicator (2.2) / Scenario planning and monitoring process in place and responding as situation changes Scenarios planning from 2010 Scenarios planning responding to situation The implementing partner facilitated two scenario building workshops with key Somaliland interlocutors including government partners. The sessions analysed the situation in Somaliland in the lead up to the election and helped the Government and civil society consider the possible scenarios that could impact the electoral process negatively. / An analysis of the security situation and flash points was undertaken, and of the political leadership, and the legal framework (elections facts and figures). This helped inform government, political parties, and civil society of the potential political scenarios. A / Indicator (2.3) / Somaliland democratisation strategy paper produced and agreed by democratisation steering committee (DSC) and Government of Somaliland No agreed strategy in place Strategy completed The democratisation strategy was completed in August 2013 with recommendations being considered for future support to Somaliland's democratization. / The team from International Republican Institute consulted widely with political parties, civil society, donors and the media. A
Final results: A / Impact Weighting (%): 15 / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No
Output 3: Accountability of local councils strengthened through increased citizen participation
Output 3 Indicators Baseline Target Actual Score / Indicator (3.1) / Number of citizen groups that reach consensus on community issue prioritization at council level? Zero 10 citizen groups (5 per target local council) Zero citizen groups. The two focal districts were changed from Hargeisa and Gabiley to Salahle and Baki, as the UN was already working in the two original districts, (the implementing partner did not want to duplicate efforts). / Unfortunately, the implementing partner was unable to include work with any citizen groups within the Baki and Salahle districts. The reason was the lack of pre-existing local NGOs in these two districts to work with. Given this situation, the only other way to meet this target would have involved assisting citizens to get organized into NGO entities but there was insufficient time to do this. / In each district, however, a local polling firm conducted a poll on citizens’ priorities. Each councillor received a copy of the final report. The council members unanimously welcomed the survey and recognized its potential as a useful source of valuable information. C / Indicator (3.2) / Number of candidates promises that are tracked based on party manifestos documented before elections 9 political parties manifestos and candidates 379 political candidates by September 2013 / [Actual target reduced to 267 in advance of the 2012 election] 267 political candidates’ promises tracked; / 120 CSO officials selected using set criteria during stakeholder assessment to undertake election tracking; / 4 regional workshops attended by a total of 145 participants from CSOs trained on election tracking process, participatory techniques, and negotiation skills; and / Citizens reported feeling that the local government system could be responsive to their demands. As the promises are being tracked the real result of this initiative will become apparent in 2015 when the next election is scheduled to take place. A / Indicator (3.3) / Number of young women and men participating in the 26 democracy café centres established / Milestone 1 / Democracy cafes at youth hotspots formed and registering members / Milestone 2 / Post elections workshop held on influence of democracy cafés and case studies on youth political participation developed and disseminated Participatory pre-election study undertaken to determine level of awareness and youth on democratisation process At least 2000 youth actively participate in democracy cafes within two months of formation 2,600 young adults, 40% of whom were young women, participated in “Democracy Cafes” which enabled young people to learn about issues of concern through peer to peer learning. This intervention encouraged the participants to document their emerging priorities and challenges facing them and to propose ways of addressing them. / 26 youth hotspots and women centres were identified across all six regions of Somaliland, and democracy cafes set up in each. A further 350 (133 women) participants attended debates in ten districts of Somaliland which aimed to enhance youth capacity for debating and democratic and effective participation in the decision making process. / Two post-election workshops were held in Hargeisa and Buroa attended by 100 (60 men and 40 women) on the influence of the democracy café which indicated that youth in particular lack the collective organizations and skills to exercise their civil and political rights. A+ / Final results: A / Impact Weighting (%): 15
Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Achievement and Results
1.1 Has the log frame been changed since the last review? Yes / Output 3 in the log frame states that the campaign promises and community commitments of 379 local government political candidates were to be tracked. This has been adjusted to be in line with the project proposal which states 267 candidates’ promises will be tracked.
1.2 Final Output score and description: A – met expectation / Output 1: Programme contributing to a successful election day / The programme contributed to a successful election day and most targets were met or substantially exceeded. The programme’s outreach components look likely to have made a significant contribution to the record 810,858 Somaliland citizens that turned out to vote in spite of a highly challenging operating environment and a very short time frame to sensitise citizens around the election itself. The programme facilitated agreements on the electoral law and remained actively engaged with politicians and political problems in order to anticipate, avert and respond to problems that could have affected the electoral process. / Somaliland’s democratisation process was well coordinated and facilitated key institutions to consider and establish a workable division of labour between the Office of the President, the NEC and the Registration of the Political Associations and Approval of National Parties Committee (RAC) on election-related issues. Programme partners provided advice which led to the formation of an Inter-Party Advisory Committee which served as a formal consultative mechanism between the parties and the NEC. They engaged with the NEC, the RAC, the Electoral Monitoring Committee and all the political parties and associations prior to the elections and an intensive working relationship was established. Meetings with members of the NEC - including its Director of Organisation - took place almost daily. Key decision-makers, including the President were successfully lobbied by the implementing partners of this programme to hold a public meeting (broadcast over radio and television), on the voting procedure and discuss the forthcoming election itself. / There were challenges around disseminating the political party code of conduct and electoral regulations agreed to by parties. The NEC and civic education efforts did not highlight the party code of conduct adequately, and parties failed to fully share the content or importance of the code of conduct with their members or supporters. Despite this, the RAC town hall meetings and party trainings did disseminate information about the electoral process, but time and resource constraints led to the majority of training taking place in Hargeisa, a central location, and Burao, a location which allowed training to at least reach participants from Somaliland’s Eastern regions. A key lesson for the next round of elections is clearly the need for a voter registry. Without this kind of safeguard, elections will be hampered by the inadequacy of the indelible ink which made polling vulnerable to multiple voting. The voter registry was, however, outside of the remit of this DFID intervention. / Output 2: Somaliland democratisation process coordinated / A robust election dispute mechanism was put in place. This contributed significantly to space for dialogue and consensus building and enhanced the capacity of the electoral management bodies to manage disputes. The ability of the system to manage the post-election issues – in particular the political brinksmanship by Haqsoor, the party which took to the streets after losing – was enhanced as a result of the capacity building undertaken by programme partners. / The Government must take credit for increasing citizen participation by opening up political space for new political associations, and by reducing the age limit for political candidates from 35 to 25 years, marking a shift in Somaliland democracy. This enabled the formation of new political associations, which was a crucial component of the elections in deepening democratisation in Somaliland and renewing the political system through the emergence of new political parties and actors. The DFID intervention built on this increased interest and participation, for example by training 300 (50 women) representatives from the political associations on political party development and organization as well as campaign skills. It was also an opportunity to revitalise the process of decentralised government, to establish local government structures that can deliver on development, and to establish meaningful local democracy in both urban and rural settings and more inclusive governance. / Women and youth gained greater voice via the democracy cafes, which led to increased participation of women and youth in the election campaign - 150 (90 women) were targeted with three intensive one week-long campaign training on youth and women outreach skills, and campaign message development. / The major challenge for partners from civil society and political actors in Somaliland continues to be around building awareness and consensus around political inclusivity in the post-election period. Whilst the NEC performed well, significant work will be required to develop capacities and mechanisms to manage all aspects of the next rounds of elections (Parliamentary and Presidential). The short time frame of the programme was also a challenge and there is a significant unmet need to deepen and consolidate some of the processes such as deepening political buy-in and broadening public understanding. That said achievements in the short time available were critical and commendable. / Output 3: Accountability of local councils strengthened through increased citizen participation / Overall, this relatively short intervention led to positive change, manifested by sensitizing potential public voters, and encouraging the Somaliland electorate, including youth and women, to actively participate in democratization processes and, as it transpired, a large turn out on election day. Looking to the future, the tracking of promises that political candidates made to get elected was a positive step in enhancing accountability of elected leaders towards the electorate. This is providing an opportunity for the voters to track the performance of elected public officials which it is hoped will translate to greater transparency and subsequent developmental outcomes in the delivery of basic services. The democratisation strategy was completed in August 2013 and its recommendations are still being considered. The implementing partners’ team consulted widely with political parties, donors, civil society and the media. In order to operationalize the strategy, the Democratisation Steering Committee – which represents donors supporting the democratisation agenda in Somaliland – can use the strategy to coordinate future democracy enabling programmes. The strategy will also be utilised to initiate a process of dialogue with key organs of government around sequencing the democratisation processes in the short to medium term, especially around proposed support for the elections in 2015. / Longer-term funding (this was a one year activity) is required to ensure that gains made through youth and women’s initiatives are not lost. / 1.3 Direct feedback from beneficiaries / Output 1: Programme Contributing To A Successful Election Day / At the close of the RAC strategic planning meetings, the chairman of the RAC noted that the training sessions provided by the programme were the first time RAC members had ever defined their roles, and had clarity on their electoral functions. Numerous participants indicated that they would share the knowledge gained during the sessions with other members of their political organization. / Participants in the women and youth campaign schools similarly stated that their training was useful and relevant. In one example, Mohamoud Jama Ahmed from the Waddani political party (one of the Hargeisa youth campaign school graduates) confirmed to the media that he decided to change his campaign strategy to a more issue-based one with greater use of media, based on the skills he acquired at the youth campaign school training workshop, / Participants at the party poll agent training praised their training programme content and specifically stated that the poll agent manual was helpful. Participants indicated that, given the complexity of the subject, it was useful to have the manual available in their native Somali language so that they were able to fully understand and internalize the information. Participants also indicated that it was helpful to be provided with poll station checklists to assist in their observation duties as no similar document had been provided by the NEC or by political parties/associations before. / To gauge the effectiveness and relevance of the training materials and the training workshops, the NEC training department developed an evaluation tool that was provided to training participants. Based on feedback most participants found the training relevant for the work they had been assigned to carry out. / The international election observers were received positively at polling stations and there was significant news coverage and discussion around the international election observers’ activities.
Output 2: Somaliland Democratisation Process Coordinated
Four of the regional coordinators from the domestic election mission were interviewed at the end of the programme – all said that the mission had been successful and had been able to provide impartial oversight of the election. They commented that the mission included a diverse range of people from across Somaliland civil society and highlighted the strong links with the international observer missions, such as sharing information and holding joint press conferences. While the number of observers deployed had been doubled, the numbers and transport limitations meant remote areas could not be covered. They agreed that the period of observation should be extended for future elections to observe pre- and post-election activities. / Somaliland civil society was able to develop a single coherent voice which enabled them to gain access to high level stakeholders, including the President. The wide range of membership allowed them to gather information and perspectives from across Somaliland. They also highlighted the dispute resolution role that the programme was able to play, particularly in the post-election disputes between political associations. / Output 3: Accountability of local councils strengthened through increased citizen participation / Public voter education exercises provided relevant and timely information to the general electorate with most of the respondents stating that the mode of delivery through dramatized plays passed on information in an innovative way that appealed to audiences from different demographic groups. The public voter education exercises reached large and diverse audiences in convenient public spaces. / Through the workshops undertaken for key stakeholders, the programme team received useful feedback about the interaction with key decision and public opinion makers, politicians, CSO leaders, and community leaders who highlighted insightful views which had a positive influence on peaceful dialogue. / Working with youth in various hotspots was warmly welcomed, and members expressed an increase in their knowledge on areas of democratic governance, debating and advocacy skills. / 1.4 Overall Outcome score and description: Increased participation of Somaliland citizens in governance systems and strengthened institutional accountability = A met expectation / Significant progress was achieved in a very short period of time. Increased participation of Somaliland citizens in governance systems and strengthened institutional accountability were achieved through a wide range of activities, from tighter electoral management and procedures, improved voter education and engagement of women and youth in the process, through to improved conduct of those contesting the elections. This was supported by closer tracking of election promises and a functioning dispute resolution mechanism. / The two outcome indicators relate to election observation and women and youth representation. / The programme laid the ground for credible elections, which enabled a positive response from international observers regarding the legitimacy of the electoral process. The programme can point to significant successes that led to this outcome. As a result of pre-election activities the mandate of the NEC was clear, which ensured that the polling architecture was put in place. Crucially, an election dispute mechanism was put in place. The NEC was content with the system put in place, capacity building workshops were organised for the NEC staff, and the judiciary was capable of dealing with cases arising from the elections. The lack of a voter register was clearly the major omission and this is possibly the most important issue to take forwards to 2015. But overall the pre-election activities and support enabled both a domestic and international observer presence to give the 2012 elections the stamp of credibility. / The programme supported an expansion of youth and women’s involvement in the electoral process, both as citizens and candidates. It also helped to provide confidence and space for youth and women to engage in local governance in particular. For example, a large number of women’s umbrella networks and community based organizations were identified and trained for the election tracking process, including a total of 120 women’s representatives. Tracking of election promises of 175 candidates was conducted and documented, and community discussions were convened to influence voters to articulate their demands. The programme worked with the media to document, track and publicise electoral commitments. The identification and tracking of the promises of political candidates who were seeking elected positions should form a basis on which, subsequently, the electorate can engage with their elected leaders and track their performance. It is hoped this will translate into greater transparency and accountability of public officials to the electorate, and changed voter expectations for future elections. / Voter turnout on election day was clearly a success, exceeding the previous election by over 250,000 votes cast. But the more challenging expectation was for more women and youth to participate in the election. In the case of youth participation, there is no doubt that pre-election activities saw a surge in participation and interest – for example, 2,600 young adults, 40% of whom were young women, were actively participating in democracy cafés. The Government’s decision to lower the age for standing from 35 to 25 led to 48 youth running in elections and 14 (29.16%) succeeding in winning a seat in their district council. In the case of women’s participation the story was mixed – while the number of women elected to office increased by fivefold, this translates into just 10 women district councillors, or 2.6% of the total. / 1.5 Impact and Sustainability / This programme was intended to contribute to an overall impact of deepened peace and stability in Somaliland. By ensuring that election day was a success, with a large increase in voter turnout compared to the 2010 Presidential Elections, this programme did indeed contribute to that impact. This was in part due to the awareness raising activities carried out before the election. / The involvement of thousands of party agents in observing the poll, trained through this programme, itself shows a major level of outreach. The fact that the parties deployed the agents on election day without financial assistance from donors is also a positive sign for Somaliland’s democratization process. A precedent has now been set for parties to exercise their right to have party agents at polling stations in future elections. Broad-based engagement in the electoral structures, such as the NEC, meant they were perceived by many actors as neutral and this afforded them the ability to coordinate and intervene positively in disputes and monitor the elections and their conclusions with credibility. Broad-based and participatory engagement clearly can have significant impact and shows the strength of non-state actor platforms. / The programme also contributed to a more issues-based approach to political party outreach to citizens, which should improve the democratisation process and the extent to which citizens feel political parties respond to their needs. Based on pre-election training, political parties and associations quickly began to see how the information from citizens could help craft messages that appealed to their target regional audiences. Implementing partner reports suggest that although initially sceptical as to the value of such information, conversations were lively and enthusiastic as parties and associations began to think about how to develop (or change) party and candidate messages. The constructive reception to this training is a sign of the maturing of political parties. / The increased involvement of women and youth in the electoral campaign is a further positive sign of the democratisation process in Somaliland. The vast majority of women candidates attending the campaign schools supported by the programme had never run for public office before. 96 women from each of Somaliland’s administrative regions were trained, representing all seven political parties and associations. Although just 10 women were eventually elected as district councillors, or 2.6% of the total, this is, at least, a fivefold increase on the two women elected to office during Somaliland’s 2002 municipal council elections. Similarly, 48 youth ran in the elections and 14 (29.16%), succeeded in winning a seat in their district council. These figures represent the effect of the lowering the age of candidacy and demonstrate the gains that can be made through promoting youth political engagement and building their capacity to compete as candidates for electoral office. / On-going work will be needed to embed the benefits achieved through the elections, and to continue to sustain peace and stability in Somaliland. Newly elected district councillors are in need of intensive capacity building and material assistance to be able to deliver on their electoral promises and meet citizen expectations. One year after the elections, most of the newly elected district councils are still highly motivated but inexperienced and inadequately supported by the government or international organizations. Failing to meet the need of these mostly rural, underdeveloped districts could result in disillusionment by voters and an erosion of confidence in representative democracy as a political system.
2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes
2.2 Key cost drivers / This programme has shown that relatively modest budgets can deliver results if used effectively and efficiently. Despite a delayed start due to continued postponement of the election date, the programme made crucial contributions to the peaceful transfer of power in Somaliland, influencing policy and mediating disputes. This was made possible because our implementing partners have existing programmes of work in Somaliland with strong networks and constructive government relations. / The key cost drivers were as below: (See also section 5 below on how value for money was achieved in view of these cost drivers from both Saferworld and the Centre for Humanitarian Dialogue): / Travel expenses for programme participants, security and human resources costs; / Accommodation and the hiring of consultants; / Training on voter civic education, public awareness rising, engaging and tracking political candidates promises, and the production of materials; / Dialogue and debating sessions with women, youth, political parties and agents, mostly centred around workshops and training; / Engaging consultants to conduct baseline and final evaluation reports; and / The additional expense associated with finding experienced electoral experts willing to travel to Somaliland. / 2.3 Was the project completed within the expected timescale: Yes - based on the revised timescale / The local elections were repeatedly delayed and scheduled to be held “within 2012”, and were eventually held on 28 November 2012. The programme was then delivered within the revised timeframe of September 2013. The last activity from the International Republican Institute on a democratisation strategy for Somaliland started later than originally planned due to the prolonged post-election consolidation period, including the negotiation with non-threshold political associations and their elected councillors over joining one of the parties, as required by law. This caused a seven month delay in formally closing the project. / 3. Evidence and Evaluation / 3.1 Assess any changes in evidence and what this meant for the project. / Partners felt that overall the ‘Theory of Change’ used to inform programme design was effective and helped deliver the intended outcome. However, the design of the programme did not initially intend that the Somaliland civil society election forum would also become a space for mediation, which was an unintended positive result. / 3.2 Set out what plans are in place for an evaluation. / There were no plans for a formal evaluation.
4. Risk
4.1 Risk Rating (overall project risk): High / Did the Risk Rating change over the life of the project? No
The risk that the Somaliland administration remained committed to the democratisation process was rated as low at the start of the programme. This risk rating held throughout the lifetime of this project, despite delays to the process. Similarly, the assumption that donors would continue to support the election also held true and DFID’s programme alongside the Interpeace programme (financed by a number of other donors) supported a range of activities for the election from voter education, youth / women, core structures such as the NEC, and both domestic and international election observation. / The risk that political parties, government entities, and civil society would not participate in consensus building processes was rated as high and remained a source of underlying tension throughout the electoral process. Here credit is due to the long established implementing partners and the Somalilanders themselves for remaining steadfast in their commitment to the fair and peaceful election that ensued. / Implementing partners expressed the view that while Somaliland remains relatively stable, any programme operating in the broader Somali region is subject to security risks. These risks were mitigated by security procedures and protocols. None of the partners experienced any security threat. / Key takeaways from these risks are that voter education and empowerment underpin the electoral process, inject accountability, and an expectation from citizens of their electoral rights being upheld. And that the risks of supporting elections bilaterally are high and that wherever possible DFID should seek to co-finance elections to spread and manage risks. / 4.2 Risk funds not used for purposes intended / Implementing partners: / The International Republican Institute’s internal financial processes have not raised any concerns and their financial reports were of a high standard. Their management of the sub-grantees was fully transparent. An audit is underway and will be incorporated in the International Republican Institute’s organisational annual audit next year (this is within the required time frame given their work only finished in September 2013). / Saferworld provided monthly partner reporting to enable DFID to monitor and manage project expenditure and variance. A financial audit was undertaken as this project was providing matching funding to a larger EC grant, and their auditors raised no concerns. / Oxfam reported that all funds were used as planned. Audit report received, and reviewed internally with no cause for concern. / The Centre for Humanitarian Dialogue reported that all funds were used as planned. Audit report received, and reviewed internally with no cause for concern. / 4.3 Climate and Environment Impact / There were no climatic or environmental risks that had any impact on project interventions during project implementation. The greatest climatic impact of this project comes from international and domestic travel.
5. Value for Money
5.1 Performance on VfM measures / Economy / The proportion of total programme costs vs. administrative costs per implementing partner was as follows: / Implementing Partner Administration Costs (%) Programme Costs (%) / Saferworld 25% 75% / Oxfam 7% 93% / International Republican Institute 39.06% 60.94% / Centre for Humanitarian Dialogue 6.53% 93.47% / Reporting from implementing partners shows a wide degree of variance between the percentages of funds spent on administration when compared to programme spend. This requires further analysis and differences reported may be the result of different interpretations of calculating these costs. / Implementing partners – notably the International Republican Institute, Saferworld, and Oxfam – used local/national staff to carry out a large portion of programmatic activities. Using local staff is not only less costly but has the added benefit of building local capacity, and local staff were well suited to respond in an efficient way to changes in programming conditions in Somaliland. Saferworld monitored the actual cost per staff member and local office costs against planned costs. Staff costs were significantly lower than planned, while office costs were slightly higher. / Efficiency / The International Republican Institute has a well-established system in place for monitoring the qualitative and quantitative measures by outcome. The International Republican Institute sub-contracted Progressio, whose international election observer team was made up primarily of volunteers whose time was given free to participate in the observer mission, and who also paid their own travel costs to Somaliland. This allowed considerable expertise to be made available in the most cost effective and efficient way. Flights purchased by Progressio were economy and purchased in bulk through a travel service. There was a change in the insurance company used, which also resulted in lower costs than previously for the international election observers / Saferworld monitored the ‘cost per observer trained’ and ‘cost per participant’, achieving significant reductions against what was planned due to higher results for the same cost. A summary of Saferworld’s performance as per the VfM indicators, with costs that went over budget shaded, is presented in the table below. / EFFICIENCY / Expected Beneficiaries Expected unit costs of main inputs to achieve output Actual / 400 people trained as election observers. Total DEO budget (training & deployment): £83,493 / £83,493/400 = / £208 per Election Observer Total number of observers trained = 677. Actual cost per Election Observer: / £83,493/677 = / £123 per Election Observer / At least 150 citizens and NSAs participating in post- election consultations Total Regional Consultations budget = £7025 / £7025/150 = £46 per person Total number of participants= 220 / £7025/220 = £31 per person / ECONOMY / Indicator Target Actual / Average cost of Saferworld staff per month £9,033 per month Actual spend on staffing = £47,814 = £6830 per month / Average cost of SONSAF staff and operating costs per month £8,732 per month Actual spend on SONAF staff & operating costs = £62,985 = £8997 per month / Average costs of Saferworld local office per month £760 per month Actual Spend = £6143/7 months / = £877 per month / Oxfam reported that project partners ensured efficiency during implementation of project interventions through coordination of actions with other stakeholders involved in the election process, as well as targeting and including a maximum numbers of beneficiaries across all activities. On the latter, Oxfam established minimum baselines for the number of people attending democracy cafes and workshops to sensitise citizens on their political rights, which they measured against international benchmarks for free and fair elections. / The Centre for Humanitarian Dialogue monitored the ‘cost of establishing an election dispute mechanism’ as presented in the table below, which demonstrates they were able to achieve cost savings across the board, notably in transport costs. / EFFICIENCY / Expected Beneficiaries Expected unit costs of main inputs to achieve output Actual / Establishment of an election dispute resolution utilising a consultative forum with political parties and associations, the NEC office and staff, Judicial officials, and election stakeholders Representation and Meetings costs £10,970 / Transport costs - £25,435 / Travel related costs - £23,950 / Communication costs - £4,779 / Financial costs - £2,035 £8,380 / £15,691 / £22,637 / £2,748 / £929 / Cost Effectiveness / A potential cost effectiveness measure for assistance to elections is the cost per voter (in the case of this programme, the provision of civic education). It is recognised that international cost comparison is difficult given that the challenges involved in conducting elections vary so greatly, given the operating costs in each country and the type of support provided. However, DFID Somalia could work with UNDP and other donors to carry out a proper analysis of the determinants of the unit costs of different aspects of the electoral process (as was done by DFID for its election support in Yemen), to enable more rigorous choices to be made about what activities to fund for the upcoming elections in Somaliland (2015) and Somalia (2016). Similarly DFID could un-pack the reported differences in implementing partners’ administration costs. / 5.2 Commercial Improvement and Value for Money / Contracting by implementing partners was carried out in compliance with competitive bidding procurement rules, and solicited bids. These bidding processes used cost comparisons from previous work to ensure economical rates for all costs incurred. / During the project Saferworld undertook a cost mapping exercise to agree standard rates with Somaliland non-state actor platforms in Puntland and South Central Somalia, essential for accurate planning and budgeting. This provided standardised key cost drivers such as per diems, accommodation and travel. / 5.3 Role of project partners / Some implementing partners were prepared to scale up swiftly because they maintained an office in Hargeisa with full-time staff. This in-country presence meant the programme already had established and effective partnerships with local partners such as the RAC, NEC, political parties and political associations, without having to operate through a surrogate local organization. In-country presence also enabled implementing partners to react quickly and efficiently to political developments as they occurred, ensuring that programme implementation was responsive to the operating environment. / DFID’s programme partners were all well experienced in electoral processes and Somaliland, with strong networks and government relations, which led to well-coordinated results across the three outcome areas detailed in the logframe. Combined, these implementing partners supported a successful election that is helping to deepen peace and stability in Somaliland.
6. Conditionality
6.1 Update on specific conditions / No conditions were associated with this project.
7. Conclusions
This programme has shown that relatively modest budgets can deliver results if used effectively and efficiently. Despite a delayed start – due to continued postponement of the election date – the programme made crucial contributions to the peaceful transfer of power in Somaliland, influencing policy and mediating disputes. The electoral process was not without its challenges, but Somaliland remains relatively stable and is generating lessons for embedding democratisation processes across wider Somalia. / If DFID decides to support future electoral processes in Somaliland or elsewhere in Somalia: / Establish a voter registry for the proposed Somaliland elections in 2015; / Future elections programme activities should start at least a year in advance. This would allow them to provide a larger number of training and civic sensitisation sessions in a more geographically equitable way – i.e. beyond the urban centres, more in rural areas, and more in Eastern Somaliland; / Training for citizens and political actors should remain a priority. The earlier the start, the more time that can be spent with youth and women candidates, potentially leading to more women and more youth getting elected; / Successful elements of this programme should continue to be used in future programmes, including: issue identification, message development, targeting of voters, candidate selection, recruitment of volunteers, recruitment and thorough training of polling agents and campaign planning and execution; / The NEC training sessions resulted in high quality training material that could be built upon for future election cycles. The programme’s mentoring approach resulted in the establishment of a well-functioning and organised training unit. With further support in between elections, this unit and the NEC as a whole would continue to improve their human and technical capacity to deliver elections; / Large-scale observation missions are important to make informed and evidence-based decisions regarding the extent to which the elections are free and fair; and / Undertake (internal DFID) analysis on per capita calculations on civic education. This analysis could provide a useful benchmark for any similar activities for 2015 and 2016. / For democracy and accountability: / More capacity and time is required to institutionalise democratic electoral processes. Key political actors welcomed initiatives that provided space for political dialogue and the tracking of election promises. In order for these processes to be tracked in a sustained way civil society needs to facilitate interaction between citizens and their local councillors to build on in the future, and hold elected officials to account. / Civic education efforts could have been greater. The programme worked to address this by supporting RAC regional town hall meetings, but more time and energy could have been spent by the RAC and other partners in educating Somalilanders about “how” to hold elected officials to account in between elections (e.g. manifesto tracking). / The creation of a broad-based advocacy platform enabled programme partners to engage in advocacy and policy-dialogue efforts with the Government of Somaliland that led to direct policy change, which in turn contributed positively to the election process.
8. Review Process
There was a significant amount of press generated just after the election by Progressio who were sub-contracted by the International Republican Institute. They produced: / An internal pre-election assessment report that was provided to donors. / A press release on November 24, 2012 that identified issues and recommendations for consideration by election stakeholders. / A press conference on the report findings and their international election observers deployment on November 26, 2012 in Hargeisa. In its immediate post-election press releases, the team congratulated the people of Somaliland and the NEC for efforts to conduct a credible election. / Saferworld produced “Somalilanders Speak – Lessons from the November 2012 local elections” and undertook an engaging roundtable discussion in May 2013 in Nairobi to disseminate lessons from the election. Progressio produced “Swerves on the Road” a report by the international election observers on the 2012 local elections in Somaliland which was formally launched in London in June 2013. / DFID’s four implementing partners delivered regular reports throughout the programme period. An Annual Review was undertaken internally by the DFID team in December 2012, and the implementing partners themselves submitted material for this final project completion report, with their assessment of project delivery, and lessons for future support for the electoral process and wider democratisation processes in Somaliland going forward. / This PCR also drew on technical inputs from within DFID Somalia, across the governance and peace-building team, statistics, and senior management.