Annual Review

Title: Health Transitions: Improving Reproductive Maternal and Child Health (RMCH) outcomes in Mozambique
Programme Value £ (full life): £35.25 million		Review Date: November 2019
Programme Code: 205074	Start Date: Nov 2016	End Date: March 2020

Summary of Programme Performance
Year	2017	2018	2019
Programme Score	A	A	A
Risk Rating	Medium	Medium	Medium

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4833405.odt
DevTracker Link to Log frame:

A. Summary and Overview

Description of programme

The National Health Policy in Mozambique has prioritised maternal and child health by formally approving the Reproductive, Maternal, Neonatal, Child and Adolescent (RMNCH) Investment Case in July 2017.

In September 2016, the UK Government approved a new business case to reduce maternal mortality and strengthen health systems. This was based on the draft RMNCH Investment Case and had the following components:
£23.5 million channelled through the UN Joint Programme (WHO, UNICEF and UNFPA) to support the RMNCH Investment Case through supply-side interventions and technical assistance.
The programme aims to prepare health facilities to provide a minimum level of basic obstetric and neonatal care. Interventions range from procuring commodities and equipment to supporting policy reforms, training health workers and delivering water, hygiene and sanitation (WASH) in health care facilities. The UN’s added value of supporting planning and prioritization of interventions at national and subnational level followed by the provision of technical support is leading to good results, despite challenges in the broader context.

£5.5m to a consortium led by Population Services International (PSI), Nweti, Tuya, Thinkplace and Coalizão to pilot how to increase family planning uptake among adolescents through demand-side interventions.

£2.9 million for Rapariga Biz (Busy Girl in Portuguese) led by the UN (UNFPA, UNICEF, UNESCO), in collaboration with five line-ministries, to delay early marriage and pregnancy in Zambezia and Nampula provinces through several interventions including the provision of sexual reproductive health. The UK joined Sweden who had been supporting the programme since 2017 and Canada who also began their support this year.

£2.1 million to WHO to support the Ministry of Health to prepare for and respond to emergencies. This component considered the likelihood of climate and disease related disasters in the country, which continually disrupt health service delivery.

£400,000 for technical assistance including studies to inform the DFID programme team.

This annual review covers the period from November 2018 to October 2019.

Developments in the wider context had a detrimental effect in the pace of implementation over the last year.

This business case was approved at a time when the sector was facing fiscal constraints experienced since the Government’s hidden debt scandal in April 2016, and subsequent decision by Ministers that the UK would no longer channel funding directly through government systems. Most of the programme is delivered through the UN agencies. The fiscal constraints have persisted resulting in a shortage of funds for operational costs (utilities, fuel, supervision) and a reduction in the contracting of qualified health workers across the sector due to a budget ceiling for recurrent expenditure allowing only 2019 health workers to be absorbed into the payroll a year, when over 3,000 are trained. As a result, the UN were constantly getting requests from the Ministry of Health to purchase commodities (such as gloves needed to deliver babies) or pay for services.

Two category four cyclones in March and April 2019, the worst in Southern Africa over the last decade, left 2.2 million people in nine provinces across Central and Northern Mozambique in need of humanitarian assistance. Sofala and Manica provinces were already experiencing floods and the subsequent rains and floods that followed exacerbated the risk of disease outbreaks particularly cholera, typhoid and malaria. As a result of the cyclones, over half a million people (including health workers) lost their homes, 770,000 hectares of land were lost, 93 health centres were damaged, and half of the cold chain capacity to store vaccines was damaged. The UN and UK were involved in the immediate response, with WHO leading the Health Cluster (group for inter-agency coordination between all actors in the health sector in Mozambique) on the partner side. Routine programming was de-prioritised between March and September 2019.
[note] Reliefweb (2019) UNICEF Mozambique Cyclones Idai and Kenneth Situation Report #14 (September 2019) https://reliefweb.int/report/mozambique/unicef-mozambique-cyclones-idai-and-kenneth-situation-report-14-september-2019 (Accessed on 10th November 2019)

The country also had national elections in October 2019. Senior Government officials were therefore engaged in the cyclone response until June and then in campaigns before the elections.

£1.6 million from this programme was reallocated to support the cyclone response through UNFPA and WHO contributing to the UK humanitarian support.

We are proposing to extend both the Rapariga Biz and UN Joint programme to close in March and September 2020 respectively to make up for the delays mentioned above. WHO becomes the only project to close as planned (March 2020).

This business case has been implemented by several staff members - the Health Advisor who is also the Senior Responsible Owner (SRO), a Social Development Advisor dedicating part of their time to the Rapariga Biz Component until May, the Demography Advisor and a Project Officer, responsible for programme management. A health adviser from the Global Health Security Team supported the SRO during the cyclone response for a period of two weeks in April. There was also a transition in SROs with a new Health Adviser recruited in May 2019. The adviser was able to monitor projects, develop relationships with implementation partners and represent DFID in policy dialogue. The adviser left DFID for personal reasons in November. This team is referred to as the “programme team” throughout the document.

Summary supporting narrative for the overall score in this review

Overall the programme scored an A - moderately meeting expectations. All five components of the BC are now at implementation phase. This reduced the weighting of the UN Joint Programme from 80% to 60%. All projects faced delays due to the cyclones and then the elections. For the Rapariga Biz project this meant moderately not meeting expectations. However, this did not influence output 3 as it captures the effect of the PSI and Rapariga Biz programmes on generating demand for family planning and PSI has exceeded expectations resulting in the output moderately meeting expectations.

Successful delivery of the outcome appears feasible although significant issues exist that require immediate attention. Some of these can be resolved by September 2020, such as an exit strategy for the UN Joint Programme and WHO’s Emergency Preparedness Project through discussions with partners like the World Bank who are managing the Global Financing Facility (GFF) project. Funding through the GFF project increased substantially over the year, providing the Ministry of Health (MoH) with a reprieve from the fiscal crisis. For this to be effective however, it will require oversight by the government of all the support channelled to the RMNCH Investment Case to ensure existing resources are used effectively. The lack of engagement in policy dialogue by Senior Officials at the MoH and limited management capacity make this unlikely. Ongoing partner discussions on the RMNCH Investment Case may improve coordination of the support to the Investment Case. A new post-election government in February 2020 may also mean a change in the leadership dynamics at the MoH. Without this, the added value of this BC over the last three years will have been to enable the delivery of basic health services to the poor at a time when the sector was struggling to provide them.

With the increase of the GFF, the need for the UN Joint Programme diminishes. Other components such as demand generation for family planning remain relevant in the context of accelerating the country’s demographic transition.

Recommendations for the year ahead

Given that two components will close in March and a third in September, the recommendations below are actions that can be implemented within this short timeframe.

Recommendation	Responsible/ Date
Continue discussions to mitigate the effects of the fiscal crisis including the low absorption of health workers into the public system and having a maintenance budget for all districts that received equipment or ambulances.	UN agencies and DFID by July 2020
To advocate with the World Bank and other partners for the UN to maintain their technical assistance role.	DFID – July 2020
The UK should decide whether to continue supporting the Rapariga Biz programme in the demography BC.	DFID – December 2019
Continue advocating for Mozambique to be reclassified by WHO so that the country gets additional resources for emergency preparedness.	DFID – throughout 2020
Decide whether to request an extension to the PSI contract beyond February 2021, early in 2020.	DFID – by March 2020
Discuss an exit strategy for the Emergency Preparedness Project and UN Joint Programme with the UN agencies.	DFID – from March 2020
Track how long UNFPA take to disburse to the other UN agencies by including this in the value-for-money (VfM) matrix.	DFID and UNFPA – April 2020
Continue to discuss safeguarding with the UN so that they are more proactive at sharing any incidents in the programmes.	DFID – September 2020

## B: DETAILED OUTPUT SCORING

Output Title	Enhanced availability and quality of trained midwifery workforce and improved facility readiness at national level by 2020 (UN Joint Programme)
Output number per LF		1	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Yes ↓

Indicator(s)	Milestone	Progress
1.1 Number of maternal and child health (MCH) nurses available in health facilities	300 by March 2019	Not met: 298 nurses trained / (168 in initial course and 130 in promotional course)
1.2 Number of health facilities equipped with: / (i) ambulances, and / (ii) emergency obstetric and neonatal care (EmONC) kits, including safe abortion care and life-saving commodities	(i) 51 / (ii) 41	Exceeded: / (i) 53 ambulances (52 vehicles and one boat ambulance) / (ii) 41

1.1. Moderately did not meet expectation: The programme is on track to achieve the target of providing 320 (24%) of the total of 1,329 additional nurses that were supposed to be trained by January 2020 according to the National Human Resources Plan. UNFPA also procured and distributed equipment including computers to the 11 Training Institutes throughout the country, to improve the quality of the trainings. Most of the equipment arrived late, as happened with the Quelimane Training Institute in Zambezia province which only received their equipment in July this year, after classes had concluded. UNFPA held a workshop in the central province of Tete in October, to train representatives from each Training Institute on the use and maintenance of the equipment.

A challenge to this intervention has been the low absorption of nurses into the system. During the field visit, the Health Adviser talked to nurses that had waited between six months and a year at home or volunteering their services, before being integrated into the public service. DFID had flagged the latter as a risk from the start of the programme (see more in the risk section of the report).

1.2. Moderately exceeded expectation: UNFPA procured a total of 53 ambulances for the programme. Ambulances are important to help pregnant women or new-borns with complications in district health centres reach district hospitals where they can get specialised care. One of the ambulances replaced a previously procured ambulance that was washed away by the floods following the cyclone in Zambezia province. A boat ambulance has been procured for a rural community in Ibo Island, off Cabo Delgado province to ensure that communities on the island can access emergency care on the mainland when needed.

The EmONC kits arrived in-country by February 2019 and 80% of them had been distributed to 41 health centres by March. The kits equipped maternity wards and surgical blocks to improve the quality of services including caesarean sections. The kits which had not yet been distributed were diverted to the health centres damaged by the 2019 cyclones. UNFPA are now distributing the equipment to the initial target provinces.

The UN reported delays with the distribution of the equipment by government authorities as well as the lack of technical support and funding by district teams to maintain the equipment. UNFPA has had to provide technical assistance to ensure that local staff are able to maintain and monitor the equipment.

In agreement with the programme team, UNFPA re-allocated savings to the cyclone response. Interventions were to ensure that health centres could resume basic care for pregnant women and new-borns and prevent sexual abuse and gender-based violence. Results from DFID support in five districts are as follows:
- 339 kits and equipment were distributed in 49 health facilities:
- 8 referral hospitals were equipped with supplies to ensure the continuity of comprehensive emergency, obstetric and neonatal care;
- 168,000 people were reached with outreach interventions and awareness raising activities;
- 12 Women Friendly Spaces (WFS) were established and equipped with personnel and volunteers;
- 55,255 women and girls accessed WFS activities (GBV awareness and life skills);
- 260 people who experienced gender-based violence received psychosocial support. GBV survivors received individual psychosocial support;
- GBV safety audits were conducted in resettlement centers in three districts.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lesson: Local-level health authorities need training on how to use the equipment distributed and develop a maintenance budget. This is difficult to prioritise given the insufficiency of funds in district budgets.

Recommendation 1: Continue discussions to mitigate the effects of the fiscal crisis including the low absorption of health workers into the public system and having a maintenance budget for all districts that received equipment or ambulances.

Output Title	Platform for outreach through the community health worker (CHW) programme strengthened by 2020 (UN Joint Programme)
Output number per LF		2	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Yes - ↓

Indicator(s)	Milestone(s)	Progress
2.1. Proportion of CHW / (i) working in target districts of total needed / (ii) receiving at least 3 supervision visits per year	(i) 850 by March and 900 by December 2019	Exceeded: 864 trained and 1150 enrolled (to conclude in December)
	2	Moderately not met
2.2 Proportion of CHW equipped and using Upscale mobile platform in Zambezia province	30%	Exceeded: 35%

2.1. Moderately exceeded expectations: The CHW provide basic treatment and preventative health services in rural communities including nutrition (deworming and Vitamin A supplementation), testing and treatment for malaria and diarrhoea, delivery of family planning (pills and injectables), and health education. UNICEF provided technical assistance to draft the CHW National Strategic Plan (2018-2024), increase the number of female CHW and scale up CHW from 5,200 in 2018 to 8,800 by 2020. The government recommends one CHW for 500-2,000 people on average (during a field visit to Monapo district, the Health Adviser met a CHW with a large workload because he served 3,700 people). The newly trained CHW will be distributed to the central and northern provinces which have high population density. An additional 1,150 CHW will be trained by December 2019, exceeding this year’s targets.

53% (458) of the newly trained CHW were female, an increase from 2016 when they had been less than a third. This was achieved through community sensitisation interventions that led relatives to take on women’s child-care and other duties enabling them to participate in the five-month long training courses. Another factor that has facilitated women’s involvement in the programme is the decision to extend the training time if necessary. Women (whose educational levels are often lower than men’s,) need more coaching taking an extra month to conclude the course.

Poor supervision continues to be one of the CHW programme’s weaknesses. Only one supervision on average, took place this year, due to the shortage of funds for fuel and the high workload of the supervisors, who are often MCH nurses. This indicator should improve as the World Bank will start to pay supervision costs from next year.

2.2. Moderately exceeded expectation: The “Upscale” digital platform improves data collection, stock management, monitoring and support to the CHW by acting as a job aid. UK aid enabled the use of the platform to be scale up in Inhambane and Cabo Delgado provinces where rollout has reached 70% and 50% respectively. Rollout in Zambezia province was delayed by two years due to problems with procuring and then distributing the mobile phones. The province was also affected by the first cyclone in March 2019, putting all other interventions on hold for several months. Despite this, half (603) of the CHW in Zambezia province will be trained on the use of the mobile platform by December 2019. Plans are also underway to train the remaining CHW in Zambezia in the first quarter of 2020 and expand the rollout of the platform to Nampula, Maputo and Gaza provinces in 2020, with funding from the World Bank.

Lessons identified this year, and recommendations for the year ahead linked to this output
Lesson: Since April 2019, the Global Financing Facility (GFF) managed by the World Bank has been funding the CHW’s subsidies, with plans for them to cover all the programme costs from 2020. Until now the CHW programme had little Government ownership due to the fragmented nature of partner support. The World Bank is more aligned to Government systems, making the eventual transition from partner to government support, easier. The reduced fragmentation will enable the MoH to have oversight of the programme.

Recommendation 2: The UK to advocate with the World Bank and other partners for the UN to maintain their technical assistance role.
Output Title	Generating demand for family planning among adolescents (PSI and Rapariga Biz)
Output number per LF		3	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Yes - ↑

Indicator(s)	Milestone	Progress
3.1 Additional family planning users in the target areas as a result of DFID interventions	500	Exceeded: / 732 users (529 in Maputo and 203 in Nampula)
3.2 Learning and evidence used to inform programme adjustments and external policy	5 interventions	Not met: 3

3.1. Substantially exceeded expectation: The PSI project exceeded the milestone of additional users. A total of 2,800 family planning users was reached of which 732 are new or additional users. At the end of the inception phase in February, PSI had tested 13 pilots for increasing family planning demand through an adaptive learning approach. These were reduced to five approaches which are being refined and scaled up in the three target provinces through: delivery of youth friendly family planning, delivery of family planning in public health centres through a public-private approach and outreach in schools and delivery in areas of high population density. In both Nampula and Gaza provinces, the provincial health authorities selected districts with low demand for family planning or receiving little family planning support. Although this meant a slow start, there is now an increase in family planning uptake. For example, during a field visit in Mogovolas district, Nampula, the programme team noticed that implants are the preferred method among adolescent girls, going against the national norm where adolescents prefer short-term methods.

3.2 Not met expectation: DFID supported a review of the Rapariga Biz programme to help decide whether to continue with the programme and what effect the different interventions had on the outcome. The review presented in April 2019, showed that the project delayed early marriage and pregnancy among the 300,000 girls it reaches. However, it couldn’t establish which of the many interventions in the programme contributed to this effect, besides family planning. The study also identified areas for improvement including in the training of mentors, ensuring a greater share of the poorest quintiles are represented, poor coordination with local authorities raising questions about the sustainability of interventions and inconsistencies in the monitoring framework.

DFID, Sweden and Canada held several meetings to discuss the findings and the timeline for the implementation of the recommendations. Since then, there has been mixed progress. On the positive side, the UN is implementing some of the recommendations including a mentoring programme for adolescent boys and carrying out studies as recommended. However, most of the latter are delayed with concerns by the programme team that they will not be finished by December 2019 when DFID support ends. Population Council who carried out the review, are also supporting UNFPA to improve their monitoring framework until December 2019.

Nevertheless, other proposed changes have not happened. For example, some components identified as being low value for money have continued, such as the women’s economic empowerment pilot, the use of SMS to promote sexual reproductive health and rights (SRHR) among the girls and the revision of the comprehensive sexual education curricula. The reason for this is that significant changes to the programme require agreement from both the UN agencies and Government ministries.

Lessons identified this year, and recommendations for the year ahead linked to this output
DFID carried out the review to assess if the UK should continue supporting this programme. Given the issues that UNFPA has had at fulfilling DFID’s compliance requirements (see below in the management and finance sections) and the inertia at taking forward the lessons from the review, the programme staff recommend that we stop supporting this programme in March 2020 (extending the current agreement for 3 months). Canada and Sweden’s support is likely to continue ensuring that all districts in Zambezia and Nampula provinces are covered.

Recommendation 3: The UK should decide whether to continue supporting the Rapariga Biz programme in the demography BC.
Output Title	Strengthen the health sector’s capacity to respond to emergencies
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Yes - ↑

Indicator(s)	Milestone	Progress
4.1 MoH able to respond to disease outbreaks	MoH responds to disease minimising their effect.	Met: MoH responded to a cholera outbreak and managed other diseases.
4.2 Support the MoH to prepare for health emergencies	Put mechanisms in place to respond to emergencies	Met: WHO strengthened surveillance at bordering districts, trained staff on Ebola case management finalised the contingency plan.

4.1 Met expectation: WHO support helped prevent cholera and other disease outbreaks in the period in review. Early in the year (2019), WHO had been supporting the government to contain a cholera outbreak in central Mozambique, when cyclone Idai made landfall in Beira city. Faecal contamination of water sources and stagnant pools of water increased the risks of water and vector borne diseases spreading including cholera, malaria and dysentery. In April, WHO in coordination with UNICEF and the health authorities undertook a week-long campaign to immunise the general population against polio, measles and tetanus. Services delivered during the week included nutritional screening, Vitamin A and deworming as well as family planning. WHO covered operational costs in two out of the four provinces reaching a total of 1.7 million people, procuring medicine to treat 173,000 malaria cases and tested 225,000 people for malaria. The health week was considered a success as it prevented a major outbreak in the four provinces where the campaign took place.

WHO also redirected their work with the Clinton Health Access Initiative (CHAI) to establish an electronic early warning alert and response disease surveillance system (EWARS) in the cyclone-affected regions. These were reconfigured to collect real time data on the ten priority diseases in the districts. Health workers were trained to use the mobile devices and were able to collect data in collaboration with 70 community volunteers who were distributed throughout five districts. The volunteers had been trained to detect and report any suspected cases to the nearest health centre.

4.2. Met expectation: Before the cyclones and from September 2019, WHO have gone back to supporting provinces to prepare for disease outbreaks. This included writing an Ebola contingency plan in collaboration with the United States Centre for Disease Control and other partners. WHO also supported the MoH to visit border areas to ensure Ebola screening protocols were being followed. This was important when the increase in Ebola cases in the Democratic Republic of Congo raised the risk that an infected person could enter Mozambique by plane or in one of the porous borders. The Government finalised the Ebola Contingency Plan in mid-October. Although significant steps had been taken to detect and respond to an outbreak of Ebola, the country was still not fully prepared to respond to an outbreak in early November when the International Community decided that the disease no longer posed a credible risk to the country.

With WHO support, the Ministry of Health is setting up an emergency control centre to coordinate disease outbreaks. The centre will be run from the Ministry of Health although staff may be deployed to any of the provinces facing an emergency. The Emergency Control Centre should be finished by March 2020 when the project closes.

Lessons identified this year, and recommendations for the year ahead linked to this output
Having this programme in place enabled the UK to support the cyclone response in the health sector and prepare for a possible Ebola case. The endemic nature of diseases such as cholera and malaria as well as the high risk of climate related disasters makes support for disease outbreaks in Mozambique a necessity. DFID Mozambique has been advocating for WHO to reclassify Mozambique so the country office will get additional resources for future health emergencies.

Recommendation 4: DFID to continue advocating for Mozambique to be reclassified by WHO so that the country gets additional resources for emergency preparedness.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The theory of change aims to ensure that priority health centres are ready to provide basic and comprehensive obstetric and new-born care (programme outcome). This was to be achieved through several interventions ranging from equipping health centres with staff, equipment and basic utilities such as WASH to ensuring better decision-making at provincial and national level through reforms. The latter would not be achieved by the time the programme ended, but would initiate processes that could be taken up by other partners or the Government.

Changes in the past year
The programme’s theory of change remains relevant as it delivered against a rapidly changing external context including responding to Cyclone Idai in March 2019.

Another change earlier in the year was the decision by the Government to suspend the delivery of long acting methods of family planning in secondary schools, due to complaints from some parents. PSI responded quickly by shifting the delivery of family planning to just schools (to cover the gap left by the government), as well as places where large groups of young people gather. The NGO has also piloted approaches to get parental support for long acting methods. The eight-month delay in transitioning from inception to implementation phase, slowed down interventions, requiring adjustments to the budget forecasts and deliverables.

Reflections on the theory of change
An overarching question about the programme is whether achieving the programme’s outputs will contribute to the outcomes. In addition to the cyclones and elections, the following in the external context threaten the theory of change:
Insufficient government leadership in the health sector. Engagement from senior officials at the Ministry of Health deteriorated due to the shortage of qualified management staff and low morale. This was after discussions about staff salaries between partners and the MoH stalled as the MoH was reluctant to adopt a more efficient approach to staff management, beyond continuing with donor funded allowances to top-up existing salaries. Partners unanimously agreed at the end of last year not to continue paying allowances because they are not sustainable and do not guarantee an improvement in results.

Insufficient state funding to ensure a minimum level of health care. The effects of the fiscal constraints on recurrent expenditure in particular continue to be felt. This also raised questions about the value for money of some interventions supported by the programme such as training health workers who were not subsequently absorbed by the State.

Slow risk management by the UN agencies. The cyclone has stretched the capacity of the UN agencies, making them slower at coordinating with each other and engaging in more strategic discussions with the Government.

The GFF is minimising some of these pressures. As GFF funding has increased some recurrent costs are being supported. The placement of a Liaison Officer by the GFF to support the Ministry of Health’s oversight of the RMNCH Investment Case has had little effect at central level within the MoH. On the partner side discussions have started about how to align the different financing mechanisms.

In this final year of the Emergency Preparedness and UN Joint Programme components, the exit strategy becomes ensuring service delivery continues in the districts that have benefitted from DFID funding since 2016, and sustaining the gains made through the programme in system strengthening.

However, there are questions about the contribution of the programme at improving the readiness of health facilities to deliver basic and comprehensive emergency obstetric care. The programme relies on Government leadership, Government support for recurrent expenditure and alignment of support. The GFF raises hopes that the minimum level of care will be reached, while changes at the Ministry of Health post- elections may improve Government engagement with partners. If this is not achieved, the programme’s added value will be to have ensured that services were delivered at a difficult period of fiscal constraints and cyclones.

The DFID funded UN programme was intended as a segue-way for the World Bank programme when the Government had little support from partners due to the suspension of direct financial aid. With the World Bank taking on more of the RMNCH Investment case, the need for the UK to finance parts of the Investment Case is falling. However, the UN’s comparative advantage in providing technical assistance remains relevant as the World Bank’s results-based financing approach requires additional technical support.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
Below is an explanation of how each component is performing:

UN Joint Programme – progress towards the outcome is mixed. All the planned commodities and equipment have been purchased and most of them have been delivered or are in the process of being delivered. Most trainings will conclude in December. A few interventions such as the delivery of WASH in health facilities will not be completed by September 2020 when the programme closes. The GFF already has plans to take on the WASH interventions. However, the contribution of the programme at improving the readiness of health facilities is not always guaranteed and therefore raises questions about whether the project is on track.

PSI – largely on track despite delays in transitioning to an implementation contract and undertaking the baseline study. Even though activities are at a lower scale than initially planned, lessons from the approach and buy-in from local authorities will make it easier to expedite the pace of delivery once the implementation contract is signed this month. DFID will have to decide whether to request an extension to the contract in March 2020.

Rapariga Biz – largely off-track. Recommendations from the review of the programme are being implemented slowly because of the cyclone, elections and the cumbersome decision-making process of the programme. DFID will review whether to continue with this component beyond March 2020.

Emergency Preparedness – on track with trainings on preparedness happening now. An exit strategy needs to be discussed with WHO to ensure that support for emergency preparedness and response continues.

Summary of Recommendations (5 and 6)
DFID is to:
- Decide whether to request an extension to the PSI contract beyond February 2021, early in 2020.
- Discuss an exit strategy for the Emergency Preparedness and UN Joint Programme with the UN agencies.

Explain major changes to the logframe in the past year
The logframe has been amended over the last year, to reflect the four projects nested in the business case. This has meant:
- Reducing the overall number of outputs from 6 to 4.
- Reducing the number of outputs linked to the UN Joint Programme from 4 to 2. The weighting of this component has reduced from 80% to 60%.
- Increased the number of indicators under the demand side output from one to two: one for the PSI project and another for the Rapariga Biz projects. The weighting of this output doubled from 15% to 30%.
- Increased the weighting for the emergency preparedness component from 5% to 10%.

Describe any planned changes to the logframe as a result of this review
As the UN Joint Programme with phase out in September and the Rapariga Biz and WHO projects will phase out in March 2019 Outputs 1, 2 and 4 need to be revised.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

The main cost drivers over the last year are set out below:

Component	Comments
RMCH UN Joint Programme	Cost drivers: Procurement of medical equipment and ambulances took up 21%, followed by the supply of medicines and contraceptives (22%) and support for community health activities (19%).
PSI - Demand Side	Cost drivers: Milestone payments took up to 71% followed by trainings and community meetings with 17%.
UN – Rapariga Biz	Cost drivers: Trainings were the main cost driver with 19%, followed by costs in salaries with 16%.
WHO Support for Emergency Preparedness	Cost drivers: Direct Transfers to Governments Counterparts took up to 23%, followed by contractual services with 18%, procurement of medicines with 16% and salaries and transfers to grants with 11% respectively.

Over the last year, VfM indicators for all components except WHO were finalized.

UN Joint Programme
A selection of indicators was agreed to reflect the wide range of activities the programme supports throughout the year. A summary of these indicators is as follows:

Economy: The UN’s long-term agreements with suppliers allows them time to negotiate price/volume maintaining costs for goods and services within the inflation rates. For example, a birth control implant called implanon has remained at $8.50 over the last three years. The average cost of training a community health worker for a five-month course increased slightly by 8% from $1,520 in 2017 to $1,640 in 2018 commensurate an almost 8% fall in the local currency against the dollar.

Efficiency: Between 2017 and 2019 the proportion of health facilities with no stockouts of the five modern methods of contraceptives increased from 80% to just under 90%. This was made possible by efforts to regularly monitor the availability of contraceptives at all levels to get more coverage. The proportion of the budget that was executed according to the initial workplan has varied from 90% in 2017 to 76% in 2018, and back up to 82% in 2019. This demonstrates that at least 10% of the of the project has had to flex to respond to changes at the Ministry of Health or in the external context. One of the inefficiencies noted in the project is the lack of immediate contracting of qualified nurses after their training.

Equity: To improve the quality of service delivery by nurses, an on-the job mentoring scheme was introduced a year ago in Zambezia province. An independent assessment of the competencies of the nurses involved, showed a 35% improvement. The proportion of people with access to a community health worker has increased by 18% on average in the three provinces with most need: Zambezia, Tete and Nampula. Zambezia saw the largest increase from 27% in 2017 to 61% in 2018.

Rapariga Biz family planning project
The review indicated that overall the programme is good value for money with the cost per pregnancy averted at £142 (equivalent to $170) per girl. However, it also pointed out areas with little efficiency such as the female economic empowerment interventions.

The programme’s current reporting structure that requires different reporting and financing mechanisms for each donor (DFID, Sweden and Canada) has stretched the management team at UNFPA. There are now plans to align the funding arrangements in the next phase of programming starting in the second semester of 2020.

WHO Support for Emergency Preparedness
WHO’s efficiency improved during the cyclone response thanks to additional national and international staff. Draft VfM indicators were submitted recently, but these have not been populated by baseline indicators or milestones.

PSI
PSI will be moving to full implementation in the coming months and value-for-money indicators have been agreed.

Assessment of whether the programme continues to represent value for money

UN Joint Programme
The Programme Team assesses that this programme remains good value for money at output level. Tracking of purchased equipment and commodities once they are in-country has improved. The UN are also following up on the low absorption of nurses into the payroll and the maintenance of equipment, to ensure value for money. At outcome level, ensuring a successful exit to the GF ensure the value for money of this programme beyond output level.

Demand side for family planning (Rapariga Biz)
The lack of knowledge about which interventions are leading to delays in early pregnancy and marriage undermines the programme’s VfM. The review helped to see that the programme is delaying early pregnancy and marriage among 300,000 girls and young women. Sweden and Canada will continue to support the project. DFID should explore alternative approaches which may deliver results faster through a nimbler decision-making process.

Demand side for family planning (PSI)
PSI’s approach has delivered lessons about which interventions are effective at generating demand among different groups. The project promises to deliver even in areas where demand for family planning is low. If successful, this approach can be replicated across the country and have scale to have an impact.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The programme has been designed to strengthen systems and build capacity of the sector for service delivery. There are signs this is happening but at a slower pace than expected due to lack of engagement from the Ministry of Health and disruption to service delivery this year, from the cyclones and the elections.

UN Joint Programme: The programme has enabled delivery of basic health services to continue when the sector experienced several challenges. As the GFF support increases, the UN Joint Programme can phase out. The ten months left in the programme should enable a smooth transition for funding interventions from DFID to the World Bank.

The Emergency Preparedness and Response project has proven its importance for health system strengthening and maintaining routine service delivery. Continued support to this approach will be needed to keep the gains made over the last two years.

Demand for family planning (PSI) project will complement the supply side by reaching adolescents who are currently excluded. Lessons from the programme are needed to inform the UK approach to family planning in the demography business case.

Demand for family planning (Rapariga Biz) project has the potential for impact because it reaches so many girls and women. However, questions around the sustainability of the approach, the project’s ability to influence policy and the slow decision-making structure raise questions about continuing with this project.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Moderate (although the operating environment continues to be high).

Overview of programme risk
Despite the overall medium risk rating for the business case, the rating for the operating environment continues to be high.

Five main risks about the external environment include the fiscal crisis, fragmentation of donor support, reduced engagement from the MoH in policy dialogue, elections and the cyclones. The effect of the fiscal crisis on the maintenance of equipment and absorption of staff was also discussed with the MoH. Although no solution has been found, the willingness of the Government to discuss these shows a change from 2016 when there seemed little willingness to admit there was a problem. The UN will continue to have regular discussions with the MoH on how to minimise these risks.

Safeguarding
An enhanced due diligence of UNFPA concluded in September demonstrated that UNFPA have robust mechanisms to detect and address any arising safeguarding issues.

All UN Agencies do not have explicit safeguarding risks in their programme risk register even though safeguarding policies are in place and both the agencies and implementing partners are aware of the safeguarding issues in their programmes. Discussions between the programme team and UN agencies has shown safeguarding issues are picked up throughout the year. However, these are not systematically communicated to DFID either in reports or at briefing meetings. In the Rapariga Biz programme for example, UK support was used to strengthen psychosocial services for adolescent girls and young women who are victims of abuse or wish to report a case, even though the reports do not discuss any of these incidents. PSI on the other hand, continues to take a proactive approach to safeguarding as evidenced by safeguarding issue they reported to the Counter-fraud and Whistleblowing Unit in October. An investigation into the allegation is still being undertaken by PSI.

Recommendations on risk
Continue to discuss safeguarding with the UN so that they are more proactive at sharing any incidents in the programmes.

An updated programme risk matrix is included as an attachment to this annual review.

Update on partnership principles

Although the programme doesn’t channel any funding directly to Government, all the components rely on Government engagement to deliver results. The deterioration in Government engagement at national level over the last year has affected programme delivery as decisions have taken longer to be made. The debt scandal and subsequent revelations associated with corruption have raised questions about the Government’s commitment to poverty reduction. At the same time, at provincial level there has often been an openness to address bottlenecks and improve results.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

For all partners delivery is off-track against what had been planned for the year (see table 1 below)), although results targets were still met. All the projects were involved in the cyclone response from March until September. The UN agencies have continued to engage in the post-recovery period. Implementation was further delayed by lack of government engagement during the electoral campaign period just before the national elections in October.

The UN have struggled to meet DFID compliance requirements particularly on value for money, timeliness of reporting and accurate forecasting resulting in high transaction costs for the programme team. The UN are feeling more confident at using the risk register, having discussed it more often this year. UNFPA informed DFID that they had £916,000 underspend from the procurement of contraceptives and surgical equipment March 2019. This was re-allocated to the first cyclone response in Sofala, Manica and Zambezia provinces.

PSI has complied with the KPIs for the inception phase. Their proactive approach to risk and declaring any profit variances has contributed to their high score on DFID’s Strategic Relationship Management scorecard. There has been an eight-month delay in transitioning from the inception to the implementation contract as DFID’s procurement and commercial department (PCD) has tried to improve the contract to ensure the results-based approach remains value for money. Overall PCD have taken six months with negotiation while on the PSI side, consultations with the Legal Department on proposals from DFID took two months. The implications of this have been that PSI has had to implement at low scale as they could not sign contracts with their consortium partners. The contract should be signed by DFID and PSI by the end of November. Payments are made in arrears on a quarterly basis with the next payment expected in December after the contract is signed. Despite the delays outlined above, this component has spent more than any other.

WHO spend has picked up due to their involvement in the cyclone response and additional staff recruited to deliver on activities. The UK is paying for five staff to support project implementation including an Emergency Officer, a programme manager and two field officers.

DFID reduced the budget of the Rapariga-Biz programme by £200,000 early in the year due to the slow pace of implementation. Despite this, the programme will need additional time to implement this year’s workplan. A total of £2.9 million will be spent by the time the project closes.

Two agreements within the overall programme have been extended and one will close as planned. A decision about whether to extend the contract with PSI will be made early next year, to enable the one year needed if necessary. A summary of the programme’s agreements is set out below:
- UN Joint programme was extended for six months until the end of September 2020.
- PSI – may need to extend to make up for the eight-month delay in signing the implementation contract.
- Rapariga Biz – will extend by three months until the end of March 2020.
- WHO – will close as planned in March 2020.

Table 1: Comparison between the budget and expenditure for the programme in the assessed period

Project	Budget	Spend	Balance	%Spend
UN Joint Programme - Capital	11,470,856.	7,284,033	4,186,823	64%
PSI	2,084,430	1,547,705	536,725	74%
WHO	2,201,914	1,585,064	616,850	72%
Rapariga Biz	1,385,846	893,926	491,920	65%
Total	17,143,047	11,310,728	5,832,320	69%

Figure 1: The Flow of Funds of the UN Joint Programme

For all programmes involving the UN agencies, the fund flow has been to contractors for the procurement of medicines, equipment and services. A small proportion of funds are channelled from the UN to the Government at central and provincial level for operational costs. This acknowledges the fiscal constraints which many Government departments are facing.

PSI and its consortium members continue to pay contractors or service providers with no funds being channelled to the Government.

Performance of partnership (s)

DFID and the Government
Within the UN Joint Programme, DFID and the Government have met every six months to discuss progress and agree priorities for the next six months. The May meeting included the World Bank and the Health Common Fund enabling strategic discussions about the RMNCH Investment Case. The meeting in October was more difficult to organise as the MoH had conflicting priorities.

Overall this year, DFID staff have seen less of the Government, as Senior officials have preferred going only to the UN to resolve issues.

The UN’s technical support is valued at sub-national level where their inputs during field visits are appreciated. The Government has been feeling that the UN are taking their role as programme implementers rather than focusing only on technical assistance.

DFID and the main delivery partners
The relationship with the UN Agencies has been mixed. The UN have continued to be responsive to DFID feedback on the reports. However, they have struggled to comply with all the DFID reporting requirements with reports missing a value for money, potential risks and delivery mapping not being updated. The involvement of the technical teams made this worse. This also led to a deterioration in coordination of the agencies in the Joint programme, DFID paying for a coordinator. The six-month meetings provide an opportunity to discuss programme implementation and the strategic direction of the programme.

Discussions on Rapariga Biz have included Sweden and Canada. Unfortunately, the Steering Committee for the programme planned for June was cancelled by the Government.

DFID and other bilateral donors

Dialogue within the sector has focused on the revision of the Coordination Mechanisms. Within DFID the Health Adviser participated in some of these meetings. However, internal demands have constrained DFID involvement at these meetings. Progress in the discussions with the Government have been slow.

DFID has been invited to the GFF co-financier meetings which have enabled a joined-up approach between the UN Joint Programme and the GFF. DFID plans to join the GFF in April next year to continue supporting health system strengthening and the RMNCH Investment Case without adding to fragmentation in the sector.

Recommendation 7: Track how long UNFPA take to disburse to the other UN agencies by including this in the VfM matrix.

Date of last narrative financial report(s)	UN Joint Programme – October 2019 / Rapariga Biz – July 2019 / PSI – September 2019 / WHO – October 2019
Date of last audited annual statement (s)	UN – June 2019

G: MONITORING, EVIDENCE & LEARNING

Monitoring

UN Joint Programme: The SRO and Project Officer have been on three field visits this year. In December 2018 the visit to Moamba district in Maputo province included someone from the UK National Audit Office and the DFID Deputy Head as well. The visit involved discussions with community health workers, a visit to a district hospital and a district warehouse. In September 2019 the SRO and representatives from UNFPA and UNICEF, visited a total of five districts in Nampula and Zambezia provinces. The visits included rural hospitals, a Training Institute, a district warehouse and discussions with community health workers and health authorities at provincial and district level. The programme team also talked to beneficiaries to hear how the programme had made a difference in their lives and hear about any improvements that could be made. A debrief with the Provincial Health Directors was held at the end of each visit.

1UN Joint Programme – The UN provides six-month reports and, if necessary, informal briefs to the programme team if necessary. The reports are discussed with DFID, followed by a meeting with the National Directors of Planning and Public Health at the Ministry of Health. Plans to have regular informal quarterly briefs did not take place as most of the UN technical team were involved in the cyclone response between March and September.

PSI – Meetings between the programme staff and DFID have taken place after the submission of quarterly reports by the NGO. The SRO and Project Officers visited Gaza in May and the SRO visited Nampula in September. Both trips included visits to clinics where PSI delivers family planning and outreach activities in communities with health promoters.

Rapariga Biz – Meetings take place every six months after progress reports are received. The SRO undertook a field visit to Nampula province in September. The programme was also reviewed by Population Council between February and April 2019 to strengthen the evidence base, improve impact by reaching adolescents with disabilities and the poorest girls, improve coordination and understand which interventions are most cost-effective. Lessons from the review will be combined with the findings of the ongoing evaluation to inform the next phase of the programme.

WHO – the SRO went on a field visit to Sofala in March and June to view the cyclone response activities. The programme team met with the partner every six months after receiving progress reports.

Evidence

There is an ongoing independent assessment of the UN Joint Programme. The study was supposed to contribute to the annual review process. However, due to the elections it was difficult for the consultant to begin work before mid-October. Findings will contribute to the programme’s exit strategy including in discussions with partners about the UN’s role in the provision of technical assistance. A final report is expected at the end of December.

Sweden have commissioned an evaluation of the Rapariga Biz programme. DFID fed into the ToR for the evaluation which is expected to finish in February 2020. Lessons from the programme will influence the next iteration of the programme which will be designed from June next year.

Learning

The UN’s comparative advantage in technical support has been highlighted over the last year. There is a need to ensure that this support to the MoH continues in some form even though DFID support through the UN will phase out.

During field visits of cyclone affected areas, it was evident that excluded groups and the poorest were the most affected. This raises the importance of ensuring that support has to be inclusive to have a significant impact.

The UN agencies need support to comply with DFID requirements. Most donors in-country are not as demanding in programme management.

Progress on recommendations from previous reviews

Last year the AR had a total of 25 recommendations that sought to address issues that put in doubt the successful delivery of the programme outcomes. Two thirds (16) of the recommendations have been achieved while 7 (28%) were not achieved and two (8%) were partially achieved. There has been a lot of effort by the UN to address issues identified last year. This includes recruiting a logistician to support supply chain management and distribution of contraceptives, developing VfM indicators and WHO improving their performance to be taken out of the performance improvement plan.
The recommendations that were not achieved relied on other partners or programmes. For example, progress on making WASH facilities available in health centres has been slow because it required coordination between the Ministries of Public Works and the Ministry of Health. Plans to establish a formal method to get beneficiary feedback haven’t happened because the Governance Programme which was supposed to undertake this intervention, has experienced delays with the tendering process.

Annex I- Progress on the Recommendations from last year
	Recommendation	Responsible / Deadline
	Linked to Outputs 1 to 5
1	UNFPA to strengthen the delivery of long-term family planning methods in the maternal and child health (MCH) training curriculum.	Achieved. UNFPA have worked with the Training Institutes over the last year to ensure that nurses have practical experience at delivering long term family planning methods.
2	Discuss with the Ministry of Health how to ensure newly recruited MCH nurses are employed	Not achieved. This is an ongoing discussion that has not yet been resolved.
3	Revise the logframe indicator for output 1 to measure quality	Not achieved: Indicator needs to be revised to number of health centres for emergency obstetric and neonatal care with enough staff to deliver the minimum level of care necessary.
4	Hire staff to support supply chain and distribution– ensuring commodities are cleared from the port on time and then quickly distributed to where they are needed.	Achieved. A logistician hired by UNFPA has been supporting the supply chain at central and provincial level.
5	WASH and Health teams to work together to accelerate the implementation of WASH in health centres.	Not achieved. There were further delays with the WASH which made it difficult for the WASH and health teams to meet.
6	Discuss how to improve the regularity with which subsidies for community health workers are paid and increasing the quantity given with the Government.	Achieved. The shift to the World Bank funding from 2020 should enable the payment of subsidies to become more reliable.
7	Discuss prioritising supervision at the district level with the UN and Government	Achieved. There have been several discussions which has resulted in progress in Nampula province.
8	Ensure greater collaboration between PSI, Rapariga Biz and the UN Joint Programme.	Not achieved. The cyclone made coordination of the different components in the first half of the year difficult.
9	Raise concerns with WHO about the delays in contracting staff and request measures to accelerate programme implementation.	Achieved. WHO have contracted a Senior Officer and Project Manager who have supported implementation.
10	Expedite the speed with which UpScale is being rolled out in Zambezia province	Achieved. By December, half of the CHW will be using UpScale.
	General Recommendations
11	Revise the logframe to include the demand side components and reduce the number of outputs from the UN Joint Programme	Achieved. Output 3 reflects the two projects supporting demand-side interventions.
12	Assess whether the theory of change needs to be reworked and/or we take up the human resources issue at the highest levels and work with other partners to find a solution	Partially achieved: DFID and UN are discussing the human resources issue in different fora.
13	Evolve the theory of change to consider how the programme needs to flex to leverage results from other big funding channels	Not achieved. The theory of change wasn’t revived.
14	WHO Programme to be put on a three-month performance improvement plan after which a decision needed to be made with Management on whether the programme should continue	Achieved. The programme addressed all the actions agreed as necessary to improve performance. In March 2019 the Management decided to continue with the project.
15	Support the UN to improve their VfM indicators for the Joint and Emergency Preparedness programmes and include indicators to capture how under-served groups like people living with disability are benefitting from interventions.	Achieved. UN Joint Programme staff worked with the Commercial Adviser to suggest VfM indicators which the UN finalised in November. The cyclone disrupted plans to focus more on capturing how under-served groups have been benefiting.
16	Include better safe-guarding risks in the risk register for the UN Supply-Side ensuring they consider all the areas where there are vulnerabilities in the system. This should be updated once the enhanced due diligence is complete.	Partially achieved: Programme staff have discussed safe-guarding with the UN and we are sure they consider it in their programming. However, this is still not being adequately reflected in the reporting.
17	Discuss risks more regularly (at a minimum on a quarterly basis) with the UN and use the risk register as a management tool.	Achieved. Risk has been discussed more often, even at meetings with Government.
18	Update the risk register with the issues mentioned in the programme management section of the mid-year report (page 17).	Achieved. DFID shared suggestions which were incorporated into the risk register.
19	Have a discussion with management about revising the risk assessment from Medium to High given the issues mentioned in the business case	Achieved. Management decided to maintain the risk as medium overall, due to efforts by the UN to address them and the UN’s readiness to support the cyclone response.
20	UN to send the annual report and workplan to the Government at least a week before the Coordination meeting between the National Directors, UN agencies and DFID	Achieved. This was done in April and October 2019.
21	Programme team to discuss with management whether to extend the entire business case to August 2021 to align with the extension of the PSI Programme.	Achieved. The extension was approved in August 2019.
22	Programme team to develop a systematic plan for spot checks and field visits next year.	Achieved. Project Officer has been implementing the plan with partners.
Recommendations that still need to be acted on from previous annual review
23	Set up a Governance Structure for the RMNCH Investment Case that oversees the different funding streams for RMNCH including DFID’s. This will imply discussing with the World Bank about the GFF’s convening role	Achieved. The Steering Committee for the project in May included all the other projects that support the Investment Case. Steps are being taken to repeat this.
24	DFID to ensure strong links between the Demand for Family Planning (OJEU) component and the innovation and coordination component through MoU agreements if possible, and if not by informal coordination mechanisms.	Partially achieved. UNFPA and PSI had a meeting in early 2019 to discuss how to coordinate. This hasn’t happened due to the UN focus on the cyclone response.
25	DFID Health and Governance teams to agree an effective way to get beneficiary feedback to verify the performance of the programme.	Not achieved. Delays with the tender for the governance project has meant that this hasn’t happened.