Programme Completion Report

Review Date:	25 May- 5 June 2015

Title: United Nations Joint Programme on Population in Uganda
Programme Code: 201713	Start Date: 15 December 2010	Original End Date: 31 December 2014 / New End Date: 31 August 2015

Summary of Programme Performance

Year	2011	2012	2013	2014
Programme Score	3	B	B	B
Risk Rating	Medium	Medium	Medium	Medium

Financial Position

Original programme Value	GBP 30 million. / This budget was reduced to GBP 29 million in 2014 following a global DFID budget cut.		Key to Abbreviations / ADPR Annual District Performance Report / AIDS Acquired Immune Deficiency Syndrome / ASRH Adolescent Sexual & Reproductive Health / BCC Behaviour Change Communication / BEONC Basic Emergency Obstetric & Newborn Care / CPR Contraceptive Prevalence Rate / CSO Civil Society Organisation / CYP Couple Years of Protection / DDP District Development Plan / DFID Department for International Development / EmONC Emergency Obstetric and Neonatal Care / FP Family Planning / GBP Great Britain Pounds / GoU Government of Uganda / HC Health Centre / HCW’s Health Care Workers / HF Health Facility / HMIS Health Management Information System / ILO International Labour Organisation / JAR Joint AIDS Review / JPP Joint Population Programme / LTFP Long-Term Family Planning / M&E Monitoring and Evaluation / MAG Male Action Group / MOH Ministry of Health / MoH Ministry of Health / MSU Marie Stopes Uganda / MTR Mid-Term Review / NMS National Medical Stores / PCR Programme Completion Review / RHU Reproductive Health Uganda / SRHR Sexual and Reproductive Health & Rights / UNICEF United Nations Children’s Fund / VfM Value for Money / WB World Bank / WHO World Health Organisation / YFC Youth-Friendly Corner / YFS Youth-Friendly Services
Extensions / amendments	Extensions: 6 month extension to 30 June 2015 and an additional 2 months extension to 31 August 2015 to enable completion of close out activities. / Amendments: Following the 2012 annual review and an extensive consultation with stakeholders, the programme went through significant changes recognising that there was a need to streamline the number of UN agencies involved in implementation of the programme and the level and number of interventions.
Log-frame revisions (with dates)	Revision in 2013 and Jan 2014.
Total programme spend	GBP 29,022,888.47 by June 2015

Follow up actions required following closure:
- The UN Joint Team should ensure that lessons learned and best practices identified are clearly documented and disseminated to all relevant stakeholders at central and district levels.
  - The DFID Uganda Team should ensure that lessons learned are shared across the DFID network and are used to inform the design of any future support to addressing population challenges in Uganda.
  - Ensure that the DFID GAPP governance programme receives a copy of the municipal plans for Gulu and Arua to allow any future work to benefit from support through UN Habitat to these districts.
  - The UN Joint Team on Population should ensure proper disposal of assets.
  - The lessons on the joint UN programme and the extent to which it was able to achieve coherence around the delivering as one agenda should be shared with the UN and other donors.
  - Valuable lessons can also be drawn out from the implementation of this programme to inform DFIDs proposed support to poorer districts as a means to improve human development indicators.

A. Introduction and Context

DevTracker Link to Business Case:	Quest ref. number 2828461
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4945108.odt

Outline of programme and what it has achieved
The Government of Uganda/UN Joint Programme on Population (UNJPP) - supported jointly by DFID and the UN, set out to contribute to accelerating the onset of a beneficial demographic transition in Uganda, to achieve a downward trend in population growth. The programme was originally being implemented in 15 programme districts, and later expanded to 4 additional districts in Eastern Uganda. DFID’s original contribution amounted to £30 million over four years (2010-2014), later reduced to £29,020,000 in 2014 because of DFID global budget cuts.

The four outcomes of the programme and subsequent achievements were:

Fertility reduced in line with the choices of individuals and couples, especially young people

The programme supported the procurement of family planning (FP) commodities for the Ministry of Health (MoH) through an earmarked contribution. This contributed to a significant reduction in commodity stock-outs, with the proportion of health facilities with no FP commodity stock-outs in the 15 programme districts increasing from 59.5% in 2011 to 96.2% in 2014. Working through two models of delivery of family planning services, annually 20% more women were able to access family planning services. In addition, the development of national guidelines on adolescent-friendly services and family planning strengthened the policy framework for improving delivery of Adolescent Sexual and Reproductive Health (ASRH) and family planning services, and supported the national roll-out of the new ASRH guidelines. The UN supported 2 models of youth-friendly services, including through piloting of a new model of youth-friendly corners in health facilities and schools. However, there was no documentation of lessons learned from this new model. The UNJPP end-term evaluation shows that the programme did not attain the target of 15% of young people with accurate information on family planning, achieving 6.1% in 2013 and only 2.1% in 2014.[1] Whilst 80 health facilities had established youth friendly services in 2013, by the end of 2014 only 55 were still functional, and the overall contribution of these services to attainment of the goal of the programme was not clear.
[1] There were variations in the methods used to collect data on accurate knowledge of family planning among young people in the 2013 Mid-term evaluation and the 2015 end of programme evaluation, which may contribute to the inconsistencies in the results.

2) Prepared, protected and healthy mothers children and youth

The programme contributed to the increase in deliveries that took place in health facilities in the 15 programme districts from 38.0% in 2010 to 59.8% in 2014. The programme also supported provision of bursaries to 1,000 needy girls in secondary schools and technical institutions. In addition, in order to contribute to decreasing the number of girls dropping out of school (thus contributing to delayed marriage and child bearing), rehabilitation of washroom facilities and production of local sanitary materials was undertaken in some schools. The programme also contributed to strengthening the capacity of health centres to provide quality reproductive, maternal, newborn and child health (RMNCH) services. This included training health workers and village health teams in newborn care, community nutrition and infant and young child feeding; and providing equipment and supplies for Basic and Comprehensive Emergency Obstetric Care. Maternal health and ANC service attendance was improved through provision of fortified food to pregnant and lactating women in the Karamoja districts and through provision of expanded mama kits in 8 districts.

3) An improved policy context for youth employment and opportunities

This outcome area initially included a wide variety of interventions at community level such as training of youth in various districts by a number of UN agencies. However following the DFID annual review in 2012, which concluded that the district level activities were highly fragmented and not coherent, this support was restructured to focus on upstream policy development. Since mid-2013 the outcome has focused on assisting the Government of Uganda (GoU) to develop a number of key policy documents and tools on youth employment, such as the National Action Plan for Youth Employment recently approved by GoU, conducting of various labour market needs assessments, and the establishment of a labour market information system. Strong government ownership and involvement of the private sector are reported.

4) An adequately resourced, coordinated and managed national population programme

Activities were undertaken in the 15 districts to build the capacity of district biostatisticians, planning and administrative officers to improve the collection of quality data and to promote the use of district population data for decision making. A multisectoral district database to collect aggregated data was established in each district, and in some districts this information is being used to influence resource allocation. In addition districts were supported to integrate population issues into the district development plans and budget framework papers. However the functionality of the database’s is not yet optimal as districts continue to grapple with low human resource capacity, lack of resources for collection of data from primary sources and lack of standardised data collection tools for the different sectors.

Population champions are active at the central, district and community level and have contributed to changing attitudes on FP and population issues. The highest level of political leadership including the President, are now pro-family planning. District and central level stakeholders interviewed reported shifts in attitudes to family planning.

Overall achievements
The 2012 and 2013 Annual Reviews by DFID found that the programme – two and three years into its implementation was suffering from fragmentation and had achieved less than optimal results in some areas. Recommendations were therefore made to discontinue interventions which did not appear to be clearly linked to the achievement of the goal of the programme, and/or for which there was limited international evidence. At the beginning of 2014, the programme was put on a performance improvement plan to drive attainment of results during the last year of implementation.

Whereas the programme did not reach all of its original aims, it was able to: strengthen the policy framework around family planning and population issues including ASRH; to improve the availability and choice of family planning commodities; and to raise awareness about the value and importance of family planning among key stakeholders. This has contributed to the highest levels of government now taking a pro-family planning position, and building district level support for family planning.

Over 336,352 new users – most of them women - were able to access family planning methods and 383,236 deliveries took place in a health facility improving maternal and neonatal health outcomes. In addition, 1000 girls received bursaries for secondary school and vocational training. Following the refocus in 2013 of interventions under Outcome 3 on national level interventions, the programme was able to assist the GoU to develop key policy documents and tools on youth employment, and establish a labour market information system, thus contributing to the improvement of the national youth policy framework.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

The goal of the programme was to accelerate the onset of a beneficial demographic transition in Uganda. The target was to reduce the total fertility rate of 6.7 in 2006 to 6.0 in 2014; to reduce the young age dependency ratio from 99 in 2010 to 96 in 2014; and to increase the Human Development Index (HDI) from 0.422 in 2010 to 0.572 in 2014.

The most recent statistics show that the total fertility rate in Uganda has now dropped from 6.2 in 2011 [2] to 5.8 in 2015. [3] The HDI value for Uganda increased to 0.484 in 2013[4]. No data is available on the evolution of the young age dependency ratio.[5]
[2] Uganda Bureau of Statistics (2012): Uganda Demographic and Health Survey (UDHS) 2011.
[3] Bill & Melinda Gates Institute for Population and Reproductive Health, Johns Hopkins Bloomberg School of Public Health, Makerere University, School of Public Health (2015): Performance Monitoring and Accountability 2020 Project (PMA2020); PMA2015 Uganda Round 2 (R2).
[4] UNDP Human Development Report website. Next HDI report with 2014 data to become available in Dec. 2015.
[5] This should become available in the full Uganda population census report expected by Dec. 2015.

The purpose of the programme was to ensure that national, community, cultural and issue-based leadership are managing the acceleration of the downward trend in population growth. Following revisions to the programme logical framework (log frame) in 2013, the purpose was supported by 2 indicators: 1) increase in contraceptive prevalence rate (CPR) at national level from 18% in 2006 to 33.5% in 2014; and 2) and reduction in the teenage pregnancy rate at national level from 25% in 2006 to 20% in 2014.

The most recent statistics show that the national (all-methods) CPR for all reproductive age women has risen to 28.7 in 2015,[6] whereas the teenage pregnancy rate amongst 15-19 year old girls dropped to 23.8 in 2011, with updated figures expected in 2016.[7]
[6] PMA2015 Uganda Round 2 (R2).
[7] The 2011 figures are from the last UDHS. Updated figures for 2015 will become available in 2016 when the next DHS will be conducted. The PMA2020 Round 2 report states that the adolescent birth rate data in Uganda reduced from 134 in 2011 to 128 in 2015.
Overall Output Score and Description: B
Based on the progress made, the programme moderately did not meet its expectations. Feedback from government stakeholders at national and district level, as well as from development partners and civil society agencies indicates that the programme has contributed to strengthening policy frameworks for family planning and youth employment, has raised awareness on population issues, and has contributed to making family planning more acceptable. The programme has also contributed to increased availability of contraceptives and to strengthening the capacity of central and district-level stakeholders and services providers on family planning and reproductive, maternal and newborn health.

However there were less than optimal results on increasing young people’s knowledge of family planning and on establishing youth-friendly services in health facilities. Overall there was weak documentation of lessons learned that would have been instrumental in policy development and scale up in other districts.

Lessons and how these have been shared

- While joint UN programmes provide an opportunity to cohere around a single agenda, this was harder to achieve in practise. Implementation of the programme at district level remained agency-focused and was not standardised, resulting in a fragmented and non-cohesive programme, which was hard to manage and monitor. Following a consultative process, the programme design was revised in 2013 to reduce the number of interventions in order to increase focus on areas that were delivering results and decrease fragmentation. A stronger mechanism of coordination and accountability amongst the different agencies may have contributed to greater cohesion. It will be important to share these lessons with the UN agencies
- The shift in the attitude to family planning shows that consistent advocacy at high levels of central government, and with local government and community leaders, can contribute to changing attitudes on difficult social norms.
- Despite the numerous trainings of health care workers (HCW’s), there is still less than optimal provision of family planning services particularly long term methods through routine care outside the outreach approach. This suggests barriers beyond the technical competence of health care workers and more importantly challenges conventional methods of knowledge and skills transfer particularly through workshops.
- Technical capacity building in family planning and RMNCH concentrated on service providers in the facilities and some midwife supervisors for mentoring of service providers trained. However, the programme did not provide support to District Health Office (DHO) staff to strengthen supportive supervision. As a result, supervision of health facilities was observed to be irregular and inadequate in some districts visited. To strengthen service delivery, it is important to consider interventions that address gaps in the capacity of the district health team.
- Implementation of a tripartite model of engaging not only school management but parents and the community in tackling issues faced by adolescents resulted in positive outcomes including: an increase in acceptability by school authorities and district officials of pregnant girls remaining in school and girls returning to school after they had their babies. This has reportedly contributed to an increase in the numbers of young mothers who complete secondary school.
- Overall, there appears to have been a weak implementation of a continuous learning approach to inform and improve implementation of the programme. As a result, there were missed opportunities to document evidence for policy formulation and drive delivery of results.
## C: DETAILED OUTPUT SCORING

Output Title	Fertility reduced in line with the choices of individuals and couples, especially young people
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Proportion of young people (aged 10–24) with accurate information on family planning in target districts.	2011: 3%; / 2012: 5%; / 2013: 10%; / 2014: 15%	Achievements: 1.2% in 2012; 6.1% in 2013 and 2.1% in 2014. The final evaluation found that while general awareness on FP was high, accurate information as defined by knowledge on 3 key FP commodities was low. / Several interventions were used to reach young people, including through community mobilisation, radio programmes, Village Health Teams (VHT), health centres and schools.
1.2 Number of health centre IIIs and IVs providing youth-friendly services (YFS) in target districts	2011: 4 HCIV, 4 HCIII / 2012:8 HCIV, 35 HCIII / 2013: 10 HCIV, 60 HCIII / 2014: 15 HCIV, 80 HCIII	By 2013, 60 HCIII and 20 HCIV had set up YFS in the 15 districts. However by the end of 2014, only 55 of these were still functional (42 HC III and 13 HC IV). The overall contribution of these services to attainment of the goal of the programme is not clear and has not been assessed. / Health care workers and peer educators received training on the provision of YFS. Concerns of poor supervision, lack of a gender sensitive approach by staff and use of peer educators who often do not have sufficient level of knowledge to provide accurate information resulted in discontinuation of DFID support to Youth Friendly Corners (YFC’s), a model of YFS, in 2013.
1.3 Proportion of HF without stock-outs of pills, male condoms and injectables in the previous 3 months	2011: 60% / 2012: 65% / 2013: 70% / 2014: 75%	The programme supported a significant reduction in the proportion of health facilities in the 15 districts without stock outs of 3 key family planning commodities from 59.5% in 2011 to 96.2% in 2014 according to the final UNJPP evaluation. / FP commodities worth USD 7.3 million were procured by UNFPA with DFID funds and distributed via UHMG, the distribution mechanism complementary to the National Medical Stores. While there have been significant improvements in national stock levels, there are challenges at health facility level driven by poor ordering practises and a less than optimal demand for FP commodities for routine provision of services.

Key points
- Work under this output has made an important contribution to the policy environment on family planning and population issues, while supporting procurement of family planning supplies to increase the availability and choice of family planning commodities. Nonetheless there remain challenges including: the national supply chain system for family planning and indeed reproductive health commodities; and the limited capacity for health workers to administer particularly long term and permanent methods through routine care.
- Through routine service provision and two models of outreaches at health facilities, 336,352 new users were able to access family planning services. However it is not possible to make a judgement on which of the two outreach models was more efficient and effective in delivering services including the value for money given that data to make this assessment is not available.
- While there was an improvement in the policy framework for the establishment of YFS, the implementation of these guidelines did not always happen in the most evidence based manner. Two approaches were used to implement YFS and due to lack of data, it is not clear which approach led to greater improvements in access to health services by the youth if at all. The fragmented approach used to reach young people with information on family planning may well be the reason there was less than optimal achievement of this indicator.

Recommendations for future programmes
- Continue support to integrated family planning and RMNCAH programmes, with behaviour change communication and institutional strengthening efforts focusing on interventions targeting adolescents and young people.
- Capacity building efforts for health care workers to provide particularly long term and permanent methods should be based on evidence and best practice of approaches that achieve knowledge and skills transfer.
- A continuous learning approach should be integrated into implementation to ensure adaptive programming that drives delivery of results but also ensures that there are no missed opportunities to draw lessons from different service delivery approaches.

Output Title	Prepared, protected and healthy mothers children and youth
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1 Number of girls retained in school through secondary school bursary programme	2011: 500 girls; / 2012: 1,000; / 2013: 1,000; / 2014: 1,000.	1000 bursaries have been provided to disadvantaged girls in 8 districts to attend secondary school or vocational schools. By the end of 2014 a total of 854 girls had been retained in secondary school and 136 in BTVET (vocational) institutions. Of these, 747 had completed their studies by 2014 and the last 253 girls are expected to complete their studies by the end of 2015. Support was also provided for academic and sanitary materials and transport fees to facilitate transport from home for the girls.
2.2 Proportion of deliveries occurring in health facilities	2011: 34%; / 2012: 39%; / 2013: 46%; / 2014: 50%	Deliveries occurring in facilities in the 15 districts increased from 37.5% in 2012, to 40.9% in 2013 and 59.8% in 2014. The attendance of the 4th Ante-Natal Care (ANC) visit increased from 55,546 women in 2011 to 82,252 in 2014. / HCW’s were trained to provide integrated ANC, birth preparedness and peri-natal services and the new born care package. In addition, 22 midwives were supported in pre-service training through a bonding mechanism. Equipment and supplies worth USD 746,000 were provided by UNFPA for Basic and Comprehensive Emergency Obstetric Care.[8] Facilities for blood collection and distribution were also strengthened in 3 districts, which reportedly contributed to no blood stock-outs from 2014-2015 in Arua district. The programme contributed to improved maternal health and ANC attendance through provision of fortified food (specialised nutritious food) to pregnant and lactating women in the Karamoja districts. 95,472 expanded maama (delivery) kits were procured and distributed to 302 HFs in 15 districts in 2014. / Village Health Teams were trained on promoting ANC visits and assisted deliveries, on identifying high-risk pregnancies, and on post-natal follow-up / new born care, community nutrition and infant and young child feeding.
[8] Does not include costs of freight and distribution.

Key points
- Engagement by programme staff and champions made an important contribution to the acceptance by school and district authorities of pregnant girls and young mothers remaining in school. Advocacy by the programme at national level resulted in the Ministry of Education sending a circular out to schools notifying them to allow pregnant girls to sit for exams and return to school after having their babies which was previously unacceptable.
- Experiences and lessons from the bursary programme contributed to the revision of the National Strategy for Girls Education now being disseminated nationally with funding from other sources. In addition, lessons from the programme informed the development of the menstrual hygiene management reader.
- The combination of increased community mobilisation and improved quality of care provided resulted in an overall increase in ante-natal attendance and assisted deliveries across the 15 districts. However in some districts indicators for ANC and assisted delivery stagnated or even deteriorated during the programme period[9] possibly due to district specific challenges.
  [9] In Bundibugyo District visited during the PCR, deliveries in HFs decreased from 48.1% in 2011 to 27.5% in 2013 and increased to 42.7% in 2014. The number of pregnant women who attended the 4th ANC visit in 2014 decreased by 16.3% from 2013.
- HR shortages are a serious challenge to improving the quality of care delivered in health facilities. Health centres IIIs and IVs continue to suffer from shortages of midwives. The practise of bonding midwives – training them in exchange for the trained person agreeing to serve in a health facility in their district for at least 2 years following their training - contributes to improving service delivery in underserved areas.
- The UNJPP did not include support to strengthening capacity of DHO’s to plan and manage their work, conduct supportive supervision and monitor health service implementation. During the district visits, the PCR team observed variations in capacity of DHO’s, with some DHO’s not providing strong leadership and supervision to health facilities benefitting from quality improvement support by UNJPP.

Recommendations for future programmes
- A health system’s strengthening approach requires strengthening of capacity not only of facility level but also of the district health team. This will ensure that district authorities can ably plan and guide implementation of interventions in the district, conduct supportive supervision and monitor implementation.
- New RMNCH (incl. family planning) approaches and techniques need to be included in the pre-service (basic) training curriculums of all qualified health workers (midwifes, nurses, doctors etc.).

Output Title	An improved policy context for youth employment and opportunities
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1 Number of key policy documents developed on youth employment	2011: N/A / 2012: N/A / 2013: 4 documents / 2014: 4 documents	National Action Plan for Youth Employment has been developed and approved by cabinet. A Labour Force Survey has been conducted, report produced and disseminated. Labour market needs assessments were conducted in the food processing and hotel sector, information technology, construction and financial sectors, while a skills audit was conducted in the hotel sector. The assessments aimed to provide evidence on labour requirements for influencing of curricula in universities and vocational schools.
3.2 An institutional mechanism of collection, analysis and exchange of labour market information in place	2011: N/A / 2012: N/A / 2013: N/A / 2014: 1	The Labour Market Information System (LMIS) has been established at the Ministry of Gender, Labour and Social Development (MGLSD), with various modules, and with web portal and job matching tools. It has been designed taking into account the needs of the Ugandan labour market and the private sector.

Key points
- Initially this output focused on community level interventions including: providing youths with market and financial linkages to help increase their income base; and training women heads of households on farming and animal rearing. However, as it became clear that interventions were too fragmented with insufficient scale, following consultation with the UN agencies, in 2013 this component was reoriented to focus on upstream policy development.
- Achievements in central level policy work are impressive, particularly on national ownership and alignment. There is reportedly a high GoU ownership of the process of development of national policy documents and tools. This is largely due to the consistent technical support provided by the UN agencies and the time allowed for influencing central level policy processes. Close collaboration with the private sector has reportedly been important for achieving results.

Recommendations for future programmes
Support the consolidation and roll-out of the LMIS and related systems.

Output Title	An adequately resourced, coordinated & well managed national population programme
Output number per LF		4	Output Score	B
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Proportion of target districts allocating and disbursing funds to population issues	2011: 25%; / 2012: 60%; / 2013: 80%; / 2014: 100%	The proportion of target districts that allocated and disbursed funds for population issues increased from 47% (7 districts) in FY2010/11, to 67% (10 districts) in FY 2011/12, to 67% (10 districts) in FY 2012/13 and according to the final evaluation further increased to 87% in 2014. By 2014, 76.9% of district leaders were aware of a population phenomenon and could link them to a development process. The proportion of the total budget of all 15 districts allocated to population issues declined from 38.6% to 14.9% in FY 2013/14, with wide variations between districts.
4.2 Proportion of District Development Plans developed based on socio-economic, demographic and other sources	2011: N/A; / 2012: 60%; / 2013: 95%; / 2014: 100%	By 2014, 87% of district development plans had been developed based on population data. At central level the programme contributed to the development of the national population action plan and the draft guidelines on birth registration (which are now waiting for GoU approval). Technical Assistance was provided to the Uganda Bureau of Statistics (UBOS) for the nation-wide population census; the new electronic census system enabled census data to become available within 3 months.

Key points
- This output contributed to the development of key national documents and systems on population including: the National Population Act; the draft revised National Population Action Plan; the Birth Registration Act 2015 and guidelines on birth registration; the draft Uganda Civil Registration Policy; and the Mobile Vital Registration Database. In addition, issues of population formed a core part of the recently commissioned National Development Plan 2015/16 - 2019/20. Population champions supported advocacy at all levels on the fact that high fertility rates would slow down the pace towards achievement of Uganda’s vision to become a middle-income country by 2040.
- The programme supported the establishment of harmonised district databases in district planning offices to enable district authorities to produce development data. A system for quality assurance of district data was established, including quarterly data verification meetings, which resulted in the improvement in reliability of district data. District planning committees were trained in how to use this multisectoral data. However, the functionality of the database varies across districts, largely due to varying levels of capacity in the districts. The sustainability of the district data bases is not ensured following the close of the programme and given turnover of trained staff.
- The programme strengthened the capacity of central level institutions (Population Secretariat, Uganda Bureau of Statistics, and Uganda Registration Services Bureau) to support and monitor the performance of district offices to integrate population data and issues into overall district and sector plans.
- The programme supported the establishment of online vital registration functions in 135 hospitals; and supported the roll out of a manual vital registration system by sub-counties and district planning offices with use of mobile technology. As a consequence, national birth registration has increased, 277,106 children registered in 2014 as compared to 195,778 in 2013.
- Municipal physical development plans were developed for Gulu and Arua, with municipal planning officers interviewed reporting satisfaction with the plan’s quality.

Recommendations for future programmes
- Continued advocacy and support for improvement in capacity will be necessary to ensure use of the development data for decision making by district leaders.
- District Population Officers / District Planning Units will require continued support to ensure quality assurance of sector data and maintaining an up-to-date harmonised database.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Over the project period, a total of £29.02 million was disbursed from DFID for implementation of programme activities. The total amount of funding provided from UN core resources over the programme period is estimated at £35,453,149 based on work plan budgets. However it is not clear whether this is a reflection of funds actually received from UN core funds and expended on programme activities or anticipated funds. An analysis of the expenditure reports for 2011-2014 (see table below) shows that the procurement of supplies and commodities (including contraceptives) constituted the largest expenditure. The final financial report for 2015 that mainly constituted close out activities will be submitted by March 2016.

While UNFPA’s performance as an administrative agent is reported to have improved significantly over the project period, the final evaluation noted challenges with disbursements between agencies. Coupled with the low absorption capacity of some of the UN agencies, as well as challenges with the absorption capacity and governance structures of some implementing partners, this resulted in low execution of funding such as 80% spend in 2013.

Disbursements by individual UN agencies to their implementing partners varied, with disbursements by UNFPA to MoH reportedly being timely, whereas quarterly disbursements to NGOs were sometimes late, hampering implementation. In addition, UNJPP stakeholders reported that performance was affected by lower than anticipated UN core resources. Challenges in the absorptive capacity of some of the UN agencies, resulted in funds having to be carried forward to the next year of implementation. While the UN agencies would have preferred annual disbursements, a global DFID policy change to bi-annual disbursements was perceived to have increased transactional costs around management of the finances. However DFID viewed this as an opportunity to ensure that decisions to disburse additional funding were based on clear evidence of effective spend.

VfM performance compared to the original VfM proposition in the business case

It is difficult to assess the VfM against the original assessment during design given the lack of data required for the VfM analysis. Within the UN partners the culture of collecting VfM data and linking expenditure to results is still relatively weak as VfM analysis is not part of routine programme monitoring and evaluation. No system was included from the inception of the programme to monitor VfM. However UN partners have reportedly become more aware of the need to monitor the VfM aspect of interventions.

Assessment of whether the programme represented value for money

There seems to have been a clear positive role for the UN agencies in the areas of policy development and advocacy, which are their core mandates. During implementation of the programme, there were significant strides made in improving the policy environment for key population issues including family planning, ASRH and youth employment. In this respect, the programme provided significant value for money by strongly and positively influencing changes in the country context. The fact that the president embraced family planning was transformational and is likely to have a big impact in tackling barriers that a high population growth poses to growth.

The indirect procurement of contraceptives through UNFPA provided significant cost savings given the relatively lower rates at which UNFPA procures these commodities. However it is possible that some of the systemic challenges in the national supply chain system - including challenges with quantification and forecasting and a landscape of vertical procurements that are not always aligned - may have negated some of these efficiency gains. The procurement of the expanded mama kits through UNICEF was long and the decision making process questioned by partners. The expanded kits cost more because the kits contained more items and were imported from abroad. Product samples provided by local suppliers failed the UN standards test, leading to sourcing from outside Uganda.

The design of the joint programme was intended to reduce duplication amongst the UN agencies, strengthen the Delivering as One agenda and improve VfM. However, it was clear that this wasn’t necessarily happening during implementation with examples of the use of different approaches by different agencies to deliver similar outputs with no clear interlinkage or lesson learning from the different approaches embedded into the programme.

Quality of financial management during programme
As the administrative agent, UNFPA provided annual narrative and financial reports on programme implementation in line with the MoU agreements. From 2014, UNFPA made disbursements to agencies on the basis of actual spend and any underspends were re-allocated to agencies that needed the funds. This process was consultative and approved through the UNJPP Steering Committee. A final completion report will be produced by UNJPP by December 2015 and UNFPA HQ will produce a final certified financial statement by February 2016.

Date of last narrative financial report	Draft overview of budget and expenditure over 2014, dated June 2015. Financial report on 2015 to be provided by February 2016. / Annual narrative report over 2014, dated 28 May 2015. Narrative report on 2015 to be provided by December 2015.
Date of last audited annual statement	DFID does not require the UN agencies to submit audited statements. UNFPA have shared annual consolidated financial statements of the UNJPP in line with the MoU requirements, which reflect the funds received, disbursements to agencies and expenditure. Last statement received in 2014 covers 2013.

E: RISK

Quality of risk management over the life of the programme

The original risk of the programme at design was noted as medium and was maintained throughout the programme period and in the PCR assessment. Various systems were put in place to try to monitor and manage risks identified throughout the life of the programme. This included the development and monitoring of the programme risk matrix during the design of the programme. The effect of some of the identified risks, particularly around service delivery, was reduced to an extent by mitigation measures such as joint planning by the UN agencies to reduce fragmentation of the programme. Specifically:

Fiduciary risks were carefully monitored and managed. DFID funding was provided to UN agencies that were charged with managing and monitoring use of funds by their downstream partners, including district officials. The UNJPP reported challenges in the financial management capacities of some implementing partners. Some districts and implementing partners were blocked for non-accountability of the UN core funds which they had received to implement activities. UNFPA managed the disbursement of funds to agencies and where there were challenges with some downstream partners this was addressed by involving district level UN staff to provide hands on support with compiling of reports and ensuring financial compliance.
Delivery risks were monitored by both the UNJPP and DFID and to some extent managed through adapting to the contextual challenges and restructuring of the programme throughout its life. These decisions were informed by quarterly reports, field visits and discussions held during the Steering Committee meetings. General delivery challenges identified include:
- Continued deterioration of the roads in Karamoja affected programme delivery, supervision and monitoring.
- In 2014, the process to design and agree a performance improvement plan for the programme meant that some agencies received funding 4 months into the year. An 8 months no-cost extension was granted to the programme to enable completion of activities that had been delayed.
- Given that the UNJPP was designed around the need for strong engagement with district officials, the weak capacity of some district officials affected delivery of results in some districts. In addition, the high turnover of staff in government facilities and unfilled posts affected the capacity of some districts to deliver results.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme did not deliver against its planned timeframe in the first two years which prompted a review and re-structuring of the programme in 2013 as outlined above. However, by mid-2015, most of the revised programme targets had been achieved. The programme received two no-cost extensions to enable completion of activities including an end of project evaluation.

Performance of partnership(s)
The programme was designed to be largely implemented through government structures at both the central and district level. This was intended to strengthen leadership and ownership by government but more so to ensure a sustainable and systems strengthening approach. On the whole, cooperation between the UN agencies and national and district authorities has reportedly been very good. However, communication and coordination by individual UN partners to district authorities has not been regular or standardised across districts. Some district offices visited reported that they were involved during annual planning of UNJPP activities but did not receive regular updates from UN agencies and implementing partners on implementation of interventions.

Overall the approach by UN agencies of alignment to government systems was much appreciated by government counterparts interviewed. Support was co-planned with relevant district and central authorities. Training and mentoring of district staff was supported through district offices and procurement of equipment and supplies followed GoU specifications. While this approach may have proved to take more time, it was seen by most stakeholders as building national capacity and being more sustainable.

UN agencies implemented some activities themselves, including advocacy and policy development at central level, and sub-contracted national NGOs for service delivery and technical assistance in the districts. District authorities interviewed reported that these NGOs performed, collaborated and communicated well. NGOs that did not perform well had their contracts discontinued.

Programmatic management
The programme has been coordinated through the UNJPP Secretariat, and managed through a technical coordination team supported by 4 outcome working groups, making it reportedly one of the better managed compared to other Joint Programmes.[10] The UNJPP secretariat contributed to strong coordination, joint planning and M&E approaches, as well as joint reporting to DFID. Government participation in the Steering Committee meetings was regular but did not always have the more senior and decision making representatives.
[10] DFID (2015): DFID supported UN Joint Programmes in Uganda: Some Lessons Learned; Report of the DFID United Nations and Commonwealth Department. Updated draft of February 2015.

Management by DFID
The technical involvement of the DFID health team in the implementation of the UNJPP has been high. DFID Uganda reportedly felt the necessity to actively engage in the UNJPP strategic direction, planning and implementation, because of a perceived lack of results and management issues. The engagement between the UN team and DFID Uganda was generally limited to the DFID health team in spite of the programmes multisectoral approach, largely because of internal human resource constraints. Discussions on future programming by DFID will harness opportunities for a cross office working approach.

Asset disposal and value obtained by DFID
A few assets were procured by the UN agencies for their own use and these will be disposed in line with individual agency guidelines on disposal of programme assets, as specified in the MoU. All UN agencies (with the exception of UN HABITAT) that procured assets have submitted through UNFPA, an asset disposal plan including assets procured for implementing partners and districts to inform DFID of how assets are to be disposed. This will be followed by a final report 6 months following the closure of the programme (February 2016) on how these disposal plans have been executed. UNFPA is following up with UN HABITAT on finalisation of their asset disposal plan.
H: MONITORING & EVALUATION

Evidence and evaluation

The programme was originally designed to generate evidence on the effectiveness of a number of innovative family planning and RMNCH interventions. However, the baseline survey was only conducted in 2012 and monitoring methodologies varied throughout the programme period. In addition the baseline survey was undertaken in 8 of the 15 districts making comparisons with the mid-term evaluation conducted in 2013 in all 15 districts difficult.

The programme documented lessons learned from a number of interventions, including the Healthy Choice communication programme, the village health telephones initiative and on the expanded mama kits. However, there was no analysis of other important interventions piloted by the UNJPP and implemented through different approaches, such as the Youth-Friendly Corners in health centres and schools in comparison to the integrated Youth-Friendly Services approach of the MoH; and the FP outreach camps supported both directly through the DHO and through NGOs. This lack of analysis was a missed opportunity. In 2014, it was decided that the UNJPP final evaluation would document lessons learned from these various experiences. However, it would have been relevant to conduct a longitudinal analysis of these interventions to understand their contribution to the overall goal of the programme in order to influence policy making and implementation in Uganda and abroad. The final evaluation only provided a summary analysis of some aspects, and provides insufficient evidence for future decisions on scaling up of best practise.

Monitoring progress throughout the programme

Four annual reviews conducted in 2011, 2012, 2013 and 2014 documented the progress of the programme. The UN agencies carried out joint monitoring and support supervision visits, DFID participating in some of these visits. Steering Committee meetings that provided oversight for programme implementation were held at least twice per year - with representation from government. The regular receipt and review of six-monthly narrative and financial updates plus the annual reports from the UNJPP formed a key monitoring tool.