Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / PATH Meningitis Vaccine Project 2010-2018
Programme Value: £5,775,788		Review Date: October 2015
Programme Code: / 202045	Start Date: / 1 November 2010	End Date: / 31 March 2018

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	75/100	A	A	A	A
Risk Rating	High	High	High	High	High

Summary of progress and lessons learnt since last review

The Meningitis Vaccine Project (MVP) has continued the development of a next-generation, polyvalent meningococcal vaccine (covering serogroups A, C, W, X and Y) together with their partner, the Serum Institute of India Ltd. (SIIL). MVP is developing a thermostable, polyvalent meningococcal conjugate vaccine for use in low-resource countries, particularly those in the African meningitis belt.

During the reporting period:
- SIIL and PATH met with the World Health Organization (WHO) in early 2014 and received support for the proposed product and clinical development plans.
- SIIL renovated a manufacturing suite according to current Good Manufacturing Practice (cGMP) regulations for exclusive production of the pentavalent meningococcal conjugate vaccine (MCV-5) for clinical studies.
- SIIL successfully scaled up its production process from 2 L to 20 L (polysaccharide fermentation) and produced three GMP conjugate batches for toxicology and clinical studies. The SIIL quality assurance group officially released batches in January 2015.
- PATH and SIIL established a collaborative modelling team with Harvard University, Yale University, Imperial College, Cambridge University, the US Centers for Disease Control and Prevention (CDC), and the Norwegian Public Health Institute to model the effect of various introduction strategies of MCV-5 on meningococcal disease in the African meningitis belt.
- The PATH/SIIL team modified the clinical development plan to make up for delays and accelerate the initiation of the Phase 1 and 2 clinical studies. In early 2015, the team sought scientific advice from the Paul Ehrlich Institute (PEI) and received support for the accelerated clinical development plan and guidance that the potential benefit of inclusion of the adjuvant (aluminium phosphate) should be assessed in the clinic.

Summary of recommendations for the next year

The logframe, based on the performance framework, should be reviewed to take account of the significant achievements, with realistic goals for the programme extension period, by March 2016.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202045/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202045/documents/

The UK is supporting a product development partnership, the Meningitis Vaccine Project (MVP) to develop a polyvalent meningitis vaccine for Sub-Saharan Africa that will control the remaining 15% to 20% of meningococcal infections not covered by the existing meningitis A vaccine, MenAfriVac®. MVP engages private-sector collaborators to apply their development, manufacturing, and distribution strengths to innovate technologies that would not be a private-sector priority, and therefore achieve maximum sustainable benefit for public health in developing countries. DFID will provide £5,775,788 until March 2018 to this project.

There are currently research gaps into essential technologies, such as vaccines and medicines, to treat neglected diseases that affect the world’s poorest populations. This occurs where there are no current products or where those that exist are either too expensive, difficult to access, no longer produced, highly toxic or ineffective. These factors have resulted in a limited research base with MVP being one of only a small number of organisations engaged in this area.

Meningitis is a deadly and debilitating disease that causes an estimated 70,000 cases/year alone in an area of sub-Saharan Africa known as the “African meningitis belt”, which stretches from Senegal in the west to Ethiopia in the east and has the largest burden of meningitis in the world. Despite treatment measures, meningitis kills one in ten people who are infected and leaves one-quarter of survivors severely debilitated. If untreated 50% of those infected die. The number of cases of meningitis has dramatically reduced since the introduction of MenAfriVac® in 2010, but this vaccine does not target all the disease-causing serogroups. New vaccines are required to prevent the remaining 15% to 20% of meningitis infections caused by other meningococcal serogroups (C, W, X and Y).

MVP, based at PATH, is aiming to contribute to the elimination of meningococcal meningitis as a public health problem in Sub-Saharan Africa. The intended outcomes of the research are:

- Development of an affordable, thermostable, polyvalent meningococcal conjugate vaccine that has a four-year shelf life at room temperature and meets a target-price of between £0.82 and £1.65 per dose.
- Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrate the vaccine’s safety and immunogenicity, in partnership with the Serum Institute of India Ltd.

Support to MVP will, in the longer term, contribute to the impact of reduced poverty through improved and affordable prevention of a common disease among the poor in the African meningitis belt. The short term target is to develop and test a new polyvalent meningococcal vaccine that will build upon the successes of MenAfriVac®, which has provided such positive results in preventing meningitis in populations across the African Meningitis Belt.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment: A – Outcome met expectations

MVP is making good progress to meet its outcome – that is to develop a pentavalent, heat-stable meningococcal conjugate vaccine that will to eliminate epidemic meningococcal meningitis from sub-Saharan Africa.

Overall output score and description: A – Outputs met expectations

MVP has made good progress, making up time lost due to delays outside of their control in the previous reporting period. The clinical plans for the development of the polyvalent conjugate vaccine are more expensive than what was originally proposed, but this represents value for money because it will lead to faster product licensure and WHO prequalification.

Key lessons

MVP have revised their initial clinical plans to build more efficiently on the success of MenAfriVac®. Instead of a simple Phase 1, single-dose, safety trial in adults, the new plan includes a more complex Phase 1 and 2 multi-dose, age de-escalation safety and immunogenicity proof-of-concept studies in both adults and toddlers. This design will allow the potential to move directly into two parallel pivotal Phase 3 studies in Africa and India, which will meet the requirements for both licensure in India and WHO prequalification and remove the need for further trials. In addition, PATH and SIIL agreed that because of the difficult and constantly changing regulatory environment in India causing significant delays in the initiation of clinical trials, the initial Phase 1 and 2 trials should be conducted in the US and Africa, after obtaining an export permit from the Drug Controller General of India (DCGI) for the polyvalent MCV. The revised plan is now being implemented.

Preventing Group A meningococcal disease by comprehensively immunizing an at risk population with MenAfriVac® has been an unqualified success
  - Group A meningococcal disease has disappeared in all countries that have immunized 1-29 year olds.
  - Strong herd protection (no cases in the unimmunized).
  - No cases of Group A disease have occurred among vaccinated individuals (more than 217 million).

A polyvalent meningococcal vaccine (A, C, W, X and Y) has the potential to eliminate meningococcal meningitis from the African meningitis belt

Key actions
The logframe, based on the performance framework, should be reviewed to take account of the significant achievements, with realistic goals for the programme extension period, by March 2016.

Has the logframe been updated since the last review? Yes
The logframe was updated after the last annual review, to take account of the revised plans following the delays in progress.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Development of an affordable, thermostable, polyvalent meningococcal conjugate vaccine that has a four-year shelf life at room temperature and meets a target price of between £0.82 and £1.65 per dose.
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	75
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Group ACWXY meningococcal conjugate vaccine developed according to current good manufacturing practices (cGMP) for use in Phase 1 trials.	Polyvalent vaccine ready to go into GMP manufacture by 2014. GMP facility and equipment validated in 2014. GMP material released by the end of 2014.	Milestone achieved: the polyvalent vaccine is now ready for a phase 1 clinical trial

Key Points

The programme has met the milestones for this output, which is a considerable achievement. They overcame delays, due to technical hurdles and the resolution of the intellectual property issues.

During 2014, the partners at the Serum Institute of India Ltd. (SIIL) added a new Men X strain from Centers for Disease Control (CDC), and finalised the large scale production processes. This resulted in three final cGMP batches (a requirement for regulatory approval in due course) for toxicology and Phase 1 and Phase 2 clinical trials.

Summary of responses to issues raised in previous annual reviews (where relevant)

During the year MVP have kept DFID updated on progress. The programme was awarded a costed extension of £2.2m over 3 years to March 2018.

Recommendations

The logframe, based on the performance framework, should be reviewed to take account of the significant achievements, with realistic goals for the programme extension period, by March 2016.

Output Title	Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specification and demonstrates vaccine safety and immunogenicity, at Serum Institute of India Ltd, and conduct Phase 1 study.
Output number per LF		2	Output Score	A
Risk:		High	Impact weighting (%):	25
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Study stability characteristics of individual conjugate polysaccharides to successfully stabilise individual conjugates.	Stability studies conducted by 2013 / Toxicology studies completed by 2015	Milestone on track: / stability studies completed in 2013 / toxicology studies completed
Phase 1 clinical trial of pentavalent MCV completed.	Phase 1 study started by early 2016	Milestone on track: / Approval for phase 1 study now received and plans progressing

Key Points

The indicators are on track to meet milestones for this output. The milestone for the toxicology studies was updated during the reporting period, to take account of the earlier delays. The audited final report of the toxicity study is due before the end of 2015. The milestone for the clinical trial was also updated to take into account he processes required for submission to the Food and Drug Administration (FDA).

SIIL renovated a manufacturing suite, according to current Good Manufacturing Practice (GMP) regulations for exclusive production of the pentavalent meningococcal conjugate vaccine (MCV-5) for clinical studies. PATH and SIIL established a collaborative modelling team with Harvard University, Yale University, Imperial College, Cambridge University, the US Centers for Disease Control and Prevention (CDC), and the Norwegian Public Health Institute to model the effect of various introduction strategies of MCV-5 on meningococcal disease in the African meningitis belt.

In January 2014, SIIL and PATH presented the polyvalent product and clinical development plans to WHO, and received positive feedback. In January 2015, SIIL and PATH presented the polyvalent product and clinical development plans to Paul Ehrlich Institute (PEI), and received positive feedback. PEI recommended that MVP assess the use of an adjuvant in the clinical trial. The trial will start in Q1 2016, to take account the changes required in the clinical trial design.

Summary of responses to issues raised in previous annual reviews (where relevant)

During the year MVP have kept DFID updated on progress. The programme was awarded a costed extension of £2.2m over 3 years to March 2018.

Recommendations

The logframe, based on the performance framework, should be reviewed to take account of the significant achievements, with realistic goals for the programme extension period, by March 2016.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Vaccine development is a very costly process, particularly in the final stages of development. As new vaccines progress through the pipeline, they enter into successively more costly phases of development. MVP has a partnership arrangement with SIIL, who provide cost effective approaches to development of new vaccines.

The main drivers are staff time, together with laboratory equipment and consumables. MVP is managing costs appropriately and has been upfront regarding the potential additional costs associated with clinical testing in the US and Africa instead of India.

VfM performance compared to the original VfM proposition in the business case
Funding product development through a PDP structure such as MVP provides value for money through:
Efficiency:
Responsive organisational structures with small core teams and open research models, which reduce operating costs.
Effectiveness:
A robust pipeline of vaccines and provision of support for the most promising candidates, ensuring greater prospect of success. Early go/no go decision making using in-house Scientific Review Committees.
Economy:
- Leveraging contributions from the private sector and/or in-country funds. The relationship with SIIL demonstrates success in this aspect.
- Developing partnerships with other entities to support joint activities (e.g. clinical trial site development, development of assays).
- MVP staff constantly looking for better technical solutions to develop vaccines and are able to share knowledge and expertise with other vaccine development colleagues.

Additionally strong partnerships with other PATH PDP’s and global organisations including Gavi, the vaccine alliance, has greatly benefitted the likelihood of vaccine uptake. Knowledge sharing opportunities have also been enhanced significantly through MVP’s developed professional networks.

Assessment of whether the programme continues to represent value for money
MVP continues to represent value for money and a good investment for continued DFID funding.

Although the Phase 1 and 2 trials in the US and Africa will be significantly more expensive (and will take longer) than the originally proposed Phase 1 trial in India, this represents value for money overall because it will lead to faster product licensure and WHO prequalification. The increased cost is due to the complex nature of the trials and because conducting clinical trials in the US and Africa is more expensive than in India. PATH has considerable expertise in conducting clinical trials in the US and Africa.

Quality of financial management
MVP is core funded by DFID and although it is part of the PATH organisation, the funds are ring-fenced for meningitis vaccine development. Spend continues to be on-track and is disbursed in accordance with the agreed Memorandum of Understanding (MoU). PATH is routinely audited; annual audited statements have been submitted and have been assessed as satisfactorily.

PATH has a robust policy on Fraud, Corruption and Dishonesty and in addition provides protection to informants through its Whistleblowing policy, which reflects best practice and provides funders with a high level of assurance. To identify fraud and corruption, PATH has an internal audit team that conducts audits and has external auditors who conduct annual audits. No incidents of fraud or corruption were identified during the reporting period.

Date of last narrative financial report	May 2015
Date of last audited annual statement	28 may 2015

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk
Product development is high risk and potential vaccine candidates can fail at any stage in the development process. PATH staff have good experience in their fields of expertise and lessons learned from one programme are applied across the wider portfolio. The scientific basis and technical approach for the MVP approach is firmly grounded behind the success of a technically similar vaccine, MenAfriVac®. Technical and regulatory challenges continue to be overcome and there is a full expectation that the MVP candidate vaccine will be tested in a clinical trial where its success and impact can first be measured.

Even taking the delays into consideration, financial risk remains relatively low. PATH has well established internal and external audit procedures. An external audit is conducted annually and the results are used to determine the liquidity of the organisation. Each year DFID receives a copy of the Audit Statement which is reviewed carefully to ensure that DFID funds are correctly recorded and used for their intended purposes. The 2014 Audited Statement has been received and is “unqualified”.

A main partner of MVP is SIIL and MVP has a right of access to all SIIL’s project-related data, including all financial records. As in previous years, there has been no indication of impropriety nor have they reported any issues relating to SIIL’s financial management or performance under the programme.

An independent group at National Institute for Biological Standards and Control (NIBSC) in the UK are analysing the vaccine intermediates (e.g. polysaccharides and carrier proteins), drug substances (monovalent bulk conjugates) and final drug product to confirm the data generated at SIIL and further reduce risk. They have also helped with the analytical assays for the drug product because of the complex situation, with 5 vaccines mixed together in a single vial.

Outstanding actions from risk assessment
Risk is assessed by the DFID team regularly throughout the year and risk categories are changed to reflect current developments within the programme. The changes in plans, to conduct the Phase 2 clinical trial in Africa involves some risk. There are few African sites that have experience of conducting early stage trials. To mitigate the risk MVP has designed the study in two stages, the first to be conducted in USA and the second in Africa, to ensure learning across the two sites.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
During the reporting period MVP has worked steadily with its partners to overcome the delays experienced over the last couple of years. They are now on track with revised plans and although the new clinical trial plans are more expensive they will ultimately lead to faster licensure and WHO prequalification of the new pentavalent vaccine.

Performance of partnership (s)
The DFID-PATH relationship is strong and there is regular communication on issues affecting the programme. There is good coordination inside PATH and this helps to ensure a common understanding of how PDPs should operate and all responsibilities under the arrangement (e.g. reporting) are presented in a standard format.

Asset monitoring and control
PATH maintains an appropriate asset register which is closely monitored and updated regularly. DFID provides core funding to PATH which means that there are no significant assets that can be fully attributable to DFID disbursements. As a drug development programme the main funding flows are earmarked towards researcher costs and clinical consumables with the latter having a short shelf life and limited residual value.
G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable as DFID provides core funds to MVP, no support is provided through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The 2014 mass vaccination campaigns in Côte d’Ivoire, Ethiopia, Mauritania, Nigeria, and Togo resulted in an additional 64 million individuals immunized with MenAfriVac®, bringing the total number of vaccinees to over 217 million since the vaccine’s initial launch in 2010. Mass immunization campaigns will continue through 2016 to cover at-risk populations and additionally, starting in 2016, the vaccine will be integrated into country routine vaccination programs to protect new birth cohorts. In fact, of the millions of vaccinees, not one vaccine failure has been recorded to date. Importantly, MenAfriVac® has been demonstrated to prevent carriage of serogroup A meningococcus, resulting in herd immunity which has contributed to the substantial effect of the vaccine. The current WHO strategy envisions the continued roll out of MenAfriVac® across the African meningitis belt over the next five years.

Group A meningococci as a causative agent of meningitis in Africa has reduced (from 22 cases of Men A disease in 2013 to 5 cases of Men A disease in 2014). However Men C disease has increased (from 10 cases in 2013 to 48 cases in 2014 and 8500 cases with more than 500 deaths, most from Men C, highlighting the need for the polyvalent vaccine.

Monitoring progress throughout the review period

The review was carried out by members of the Human Development Team in DFID’s Research and Evidence Division, with input from other funders and PATH. Members of the review team met with MVP at the PATH headquarters in Seattle and had a number of teleconferences during the year, during which progress and challenges have been discussed. MVP staff met with DFID health advisers to discuss progress in November 2015.