Business Case

Summary Sheet

Title: CAR Humanitarian and Recovery Programme (CHURP)
Project Purpose: To save lives and reduce suffering of the population affected by the ongoing crisis in CAR, including refugees in the region.
Programme Value: £60million		Country: Central African Republic (and Cameroon)
Project Code: 205286	Start Date: / 1 May 2016	End Date: / 31 March 2019
Overall programme risk rating: High
Quest Number:

Table of Contents

# List of Acronyms / Abbreviations

ARD	DFID's Africa Regional Department
Bekou Fund	European Union Trust Fund for CAR
BINUCA	Integrated Bureau for the Consolidation of peace in CAR
BONUCA	UN Bureau for the Consolidation of peace in CAR
CAR	Central African Republic
CERF	Central Emergency Response Fund
CHASE OT	DFID's Conflict, Humanitarian and Security Operations Team
CHF	Common Humanitarian Fund
CHURP	CAR Humanitarian and Recovery Programme
CRRCA	Central African Republic Red Cross Society
DEVCO	European Union Directorate for International Cooperation and Development
DFID	UK Department for International Development
DRC	Danish Refugee Council
DSRSG	Deputy Special Representative to the Secretary-General
ECHO	EU Humanitarian Aid and Civil Protection directorate
EU	European Union
FACA	Central African Armed Forces
FAO	Food and Agriculture Organisation
FCO	Foreign and Commonwealth office
GNP	Gross National Product
HC	Humanitarian Coordinator
HCT	Humanitarian Country Team
ICF	Internal Climate Facility
ICRC	International Committee of the Red-Cross
IDP	Internally Displaced Person
IMC	International Medical Corps
IMF	International Monetary Fund
INGO	International non-governmental organisation
INSO / IPC	International NGO Safety Organisation / Integrated Phase Classification
KP	Kimberley process
L3	Level 3 disaster
M&E	Monitoring & Evaluation
MINUSCA	UN Mission for the Stabilisation of CAR
MISCA	African Union Mission for the Stabilisation of CAR
MoU	Memorandum of Understanding
MSF / NGO	Médecins Sans Frontières/Doctors Without Borders / Non-governmental organisation
OCHA	Office for the Coordination of Humanitarian Affairs
ODA	Official Development Assistance
PCR	Programme Completion Review
PHASE / SC	Providing Humanitarian Assistance in Sahel Emergencies / Save the Children
SGBV	Sexual and Gender-Based Violence
SI	Solidarites International
UN	United Nations
UNDSS / UNHAS	United Nations Department for Safety and Security / United Nations Humanitarian Air Service
UNHCR	United Nations High Commissioner for Refugees
UNICEF	UN International Fund for Children
VfM	Value For Money
WASH	Water, Sanitation and Hygiene
WFP	World Food Programme

# Intervention Summary

## What support will the UK provide?
The UK has provided £63 million since 2013 to address urgent humanitarian and protracted needs in the Central African Republic (CAR) and among CAR refugees. These funds have been provided through three business cases finishing in December 2016.

This new business case proposes a multi-year support package of £60 million for 2016-2019 to address humanitarian and recovery needs in CAR and among CAR refugees. Funding will be provided in CAR through the Common Humanitarian Fund (CHF), the International Committee of the Red Cross (ICRC), the Food and Agriculture Organization (FAO), UNHCR and two NGO consortia. Funding will also address the needs of CAR refugees in Cameroon through UNHCR and WFP. The business case will include a Contingency Facility of £24 million to enable a rapid scale-up in assistance when needed.

## What are the main CHURP activities?
The CAR Humanitarian and Recovery Programme (CHURP) will provide support to address urgent humanitarian gaps through the Common Humanitarian Fund and the ICRC in CAR. It will aim to cover protracted needs and address early recovery needs through the FAO, the ICRC, UNHCR and NGO consortia in CAR, and UNHCR and WFP in Cameroon. The CHURP will also include DFID advocacy to ensure effective coordination among humanitarian and development donors, early engagement of international financial institutions, and support to the cross-Whitehall CAR strategy in the fields of security, justice and governance through close cooperation with the Foreign and Commonwealth Office (FCO).

A full logframe for this programme will be produced after signature of all grant agreements and agreement on partner targets. The logframe will provide the exact DFID beneficiary reach in CAR and among CAR refugees.

## Why is UK support required?
The conflict that has affected CAR since 2012 has plunged the country and its population in a crisis of catastrophic scale. 50% of CAR’s population are in need of urgent humanitarian assistance in 2016.[1] Agricultural production shrank by almost 60% in 2013-14.[2] 50% of the population lived in food insecurity in 2015.[3] The health system has become entirely dependent on non-governmental organisations (NGOs). The gross national product dropped by 36% in 2013 and is still 30% lower than pre-war average in 2016.[4] The country was left dependant on external aid to pay its civil servants and on United Nations (UN), French and European Union (EU) military interventions to secure its territory. Whilst the worst of CAR’s violence has been curtailed, the country remains marred by sectarian tension, criminal violence, arms proliferation and armed groups. Around 900,000 people remain displaced internally and in neighbouring countries. Humanitarian needs are widespread.
[1] OCHA (2015), 2016 Humanitarian Response Plan.
[2] FAO/WFP (2014), Crop and Food Security Assessment Mission to the Central African Republic.
[3] WFP/FAO (2015), Evaluation de la securite alimentaire Novembre 2015.
[4] World Bank (2015), Central African Republic - Country Engagement Note, IDA R2015-0208.

1. UK funding has provided life-saving assistance in health, livelihoods, protection, food and nutrition since 2013. Need levels will remain extremely high in the next few years as CAR begins the painstaking process of rebuilding its institutions and basic services, and attempts to put a stop to the rapid deterioration in food security. UK aid will remain crucial in this transition phase to address urgent needs among people affected by violence and returnees, and to help stabilise livelihoods to lay the bases for a transition towards early recovery. Whilst the CHURP builds upon DFID’s experience in CAR in health, livelihoods, protection and refugee support, it seeks to do so in a more predictable and joined up manner by providing multi-year funding and increasing coordination with other donors and international financial institutions.
2. An indicative breakdown of UK funding is set out below:

Component / Partner	2016/17	2017/18	2018/19	TOTAL
CAR	8.25	8.25	8.25	24.75
CAR refugees	3.5	3.25	3.25	10
M&E	0.25	0.5	0.5	1.25
Contingency Facility	24			24
TOTAL	20	20	20	60

The Contingency Facility will be disbursed on an as needed basis, to respond to surges in need, and is subject to the availability of funds in ARD’s budget at the time it is drawn. Funding release will not be capped yearly, to provide the flexibility to delay or frontload the use of contingency funding depending on changing needs.

It is not foreseen that an evaluation will be undertaken as this is unlikely to add much to DFID knowledge in relation to humanitarian programming. An external review will however be implemented in the second year of implementation to assess DFID’s performance against the theory of change laid out in this business case. Given the risk context of the implementation of the programme a dedicated CHASE-OT advisor will support the routine monitoring and implementation of the programme including regular in-country visits.
## How does the project fit with the Africa Regional Department’s strategic objectives set out in the Bilateral Aid Review?

In the 2015 Bilateral Aid Review, the Africa Regional Department proposed that one of its key strategic objectives will be:

Supporting African leadership through comprehensive risk management for a stable, peaceful continent to address and avoid conflict, climate and economic shocks, contributing to greater security and prosperity (in Africa and beyond). We can save lives, reduce suffering and build peace by preventing, managing and resolving conflict; reduce vulnerability by investing in preparedness, early-warning & shock-response; meet humanitarian needs by addressing the drivers of conflict, instability and humanitarian crises.

Under this business case, DFID proposes to support this agenda by meeting humanitarian needs in CAR, reducing vulnerability and rebuilding resilience, and engaging alongside the FCO and multilateral partners to manage and address the drivers of conflict in CAR.

## What are the expected results?

A detailed logframe will be published once contractual arrangements have been finalised. Annex I outlines a draft results framework with indicative targets.

## What are the key risks to the success of the CHURP?

The risks associated with operating in CAR are high. Key risks include those associated with the current conflict, criminality, lack of conflict sensitivity, fraud, challenges linked to procurement and transportation, and partners’ capacity. These risks will be primarily mitigated through DFID’s due diligence process including quarterly reviews of partners’ compliance mechanisms, monitoring and evaluation processes and performance, flexible programming and advocacy.
# Strategic Case

## Context and humanitarian needs

The Central African Republic has been affected since 2013 by a conflict that has displaced up to a third of its population. Compounded by the state’s chronic fragility and some of the worst health indicators in the world, this crisis has pushed the country over the edge, leaving 50% of its population in need of urgent humanitarian aid. The country’s gross national product shrank by 36% in just one year in 2013 and agricultural production by 60%. It took the intervention of 2,000 French troops and a 12,000-strong peacekeeping force to quell the worst of the violence in its pre-genocidal state, but the country remains marred by violence and insecurity. Every sector (public and private) needs rebuilding. National elections were successfully implemented between December 2015 and March 2016 and formally marked the end of the transition, but it will take at least 10 years before the Central African population and the country can start recovering.

### Conflict

A loose coalition of rebel groups (the ‘Seleka’) hailing from Northern CAR, Darfur and Chad launched an advance on Bangui in December 2012, led by rebel leader Michel Djotodia. They charted a path of destruction and displacement as they marched through the country looting, pillaging and recruiting additional troops and ending in the battle of Bangui in March 2013 that culminated in Djotodia ousting President Bozize, seizing power and appointing himself President.

The Selekas mainly included Muslim troops among their members and many foreigners. CAR populations already had a loose understanding of national identity that allowed an Islamic identity to be at times conflated with foreign origins. These two elements allowed in turn for a growing popular tendency to equate ‘Muslim’ with ‘Seleka’, feeding into growing resentment towards CAR’s Muslim minority in 2013 given the extent of Seleka violence against the population.[5]
[5] International Crisis Group (2015), Centrafrique: les raciness de la violence. Rapport Afrique 230.

This widespread and systematic violence exerted against the population in 2013 fuelled the creation of a constellation of self-defence groups, the Anti-Balaka, which began fighting back against the Seleka. The conflict took a turn for the worse on 5 December 2013 when the burgeoning Anti-Balaka movement launched a brutal attack on Bangui and its Muslim population, with high levels of violence persisting in Bangui and some towns throughout the month. The attack on 5 December 2013 signalled the end of Seleka control in the Southwest of CAR and Bangui, forcing their withdrawal. This placed Muslim populations in a very precarious position and left undefended, they became the object of systematic punitive attacks perpetrated by Anti-Balakas and civilians, and designed to instil terror and force people to flee. Thirty mosques were destroyed in Bangui and 400 in the country.[6] This unprecedented level of violence took an increasingly sectarian turn. It forced the displacement of more than a million people in a matter of days and initiated a mass exodus of Muslims to Cameroon and Chad.
[6] Ibid.

Michel Djotodia was forced to resign on 10 January 2014 under intense pressure from the international community. Catherine Samba-Panza was sworn in as the interim President of CAR on 23 January 2014 and appointed to lead the transition. She drew wide support from the international community, which translated into substantial financial support in 2014 and 2015 to preserve the state from collapse. Elections took place fairly peacefully between December 2015 and March 2016. President Touadera was sworn in and appointed a new government in April. Despite this, the country remains extremely divided and marred with insecurity.

In 2002, the Economic Community of Central African States launched a small-scale peacekeeping operation that failed to stop two military coups (and yet survived them), until it was handed over to the African Union (AU) in December 2013 and reinforced. This force was re-hatted as a United Nations Peacekeeping force (‘MINUSCA’) in September 2014 and progressively increased with the aim to reach 12,870 troops by 2015. The African Union operation and the CAR population benefited from the rapid deployment of French troops under Operation Sangaris in December 2013, which alongside AU troops helped control a spiralling cycle of sectarian attacks which was rapidly developing into pre-genocidal violence. The EU also launched a military operation in 2014 to stabilise the capital Bangui. EU troops withdrew in 2015 and were replaced by a more modest EU Military Advisory Mission (EUMAM) designed to support Security Sector Reform.

Despite quelling the worst of CAR’s violence, the country remains largely uncontrolled. A mosaic of armed groups combined with small arms proliferation make any prospect of conflict resolution remote. Armed and sectarian violence continue to threaten the population and humanitarian actors. There is no reliable record on the number of casualties suffered since 2012. An MSF retroactive mortality survey conducted among refugees in Chad estimated that 8% of the population who had sought refuge in Southern Chad had died between November 2013 and April 2014[7]. 95% of those deaths were due to violence. Since 2014, humanitarians have suffered 366 security incidents and 22 humanitarian workers have been killed. MINUSCA has also been the direct target of armed group attacks, leaving 3 peacekeepers dead and at least 11 injured in 2015.
[7] 2,599 people. MSF (2014), Central African refugees in Chad and Cameroon: “Suitcase or coffin”.

### State fragility

CAR was affected by an enduring crisis of governance, corruption and marginalisation prior to 2012 and saw a significant deterioration under President Bozize. Successive governments not only proved unable to develop the country and improve the lives of its citizens, but played a major role in destroying the formal economy and the state. Manifestations included extremely poor financial management, nepotistic economic governance and widespread corruption; clientelism; deterioration of infrastructure and of all public services; almost total impunity for those with political protection; and a breakdown in the rule of law.[8]
[8] FCO/DFID (2014), CAR Joint Analysis of Conflict and Stability; World Bank (2016), CAR Fragility assessment.

The armed forces (FACA) and security sector had been weakened by a lack of investment and training, and President Bozize’s tendency to appoint personnel from his Gbaya tribe.[9] They lost further credibility when they failed to contain the Seleka attack and became systematic target for the armed groups, and when members became accused of collusion with Anti-Balakas. Security sector reform is necessary but has not begun yet. Meanwhile, armed groups have contested the government’s authority and competed over power for more than 15 years. Past peace and disarmament processes have been unsuccessful at resolving the situation.[10] Armed groups signed in 2014 a cessation of hostilities agreement in Brazzaville and later an agreement to disarm, demobilise and reintegrate (DDR) in 2015 in Bangui. A pre-DDR programme has begun, but has not yet led to a significant drop in the presence of fire arms and armed groups across the territory.
[9] Ibid.
[10] World Bank (2015), Central African Republic - Country Engagement Note, IDA R2015-0208.

CAR has also lagged behind in terms of official development assistance (ODA) in the past two decades. It received for instance £40 per capita in 2011 compared with £57 for the DRC and £123 for Liberia.[11] Lack of government investment towards development and low ODA combined to produce some of the worst development indicators in the world. CAR has been consistently among the bottom ten countries on the Human Development Index since 2005 and among the bottom 5 since 2010. CAR’s under-5 mortality was 134 in 2014.[12] Life expectancy was 49.5 years. Maternal mortality was at 890 per 10,000 births.[13] This placed CAR among the bottom 5 countries for these indicators.
[11] Ibid.
[12] World Bank, http://data.worldbank.org/indicator/SH.DYN.MORT.
[13] UNICEF, http://www.unicef.org/infobycountry/car_statistics.html.

The impact of the conflict that began in 2012 on an extremely fragile state was overwhelming. Most public services virtually collapsed. With substantial budget aid from the international community, the CAR government started a painstaking process of redeployment of its state officials in 2014 but has struggled with this task in the face of insecurity, absence of essential banking services and difficult working conditions. Essential services and in particular healthcare still mainly rely on humanitarian providers.

### Humanitarian and economic consequences

To date, 450,000 people are still internally displaced and 480,000 are refugees in neighbouring countries, of which 258,000 are in Cameroon, 102,000 in the DRC and 84,000 in Chad. Chad also welcomed 130,000 people of Chadian origin who were forced to flee CAR. 2.3 million people are estimated to require urgent humanitarian assistance in 2016, i.e. 50% of the CAR population.[14] Food insecurity affected 50% of the population in 2015.[15] The entire health system relies on humanitarian agencies to deliver services.
[14] OCHA (2014), 2015 Humanitarian Response Plan.
[15] WFP/FAO (2015), Evaluation de la securite alimentaire Novembre 2015.

The CAR Gross National Product (GNP) shrank by 36% in 2013 and rose by 1% only in 2014 and 4.5% in 2015.[16] Agricultural production had dropped by 60% in 2014 compared to the pre-war average, and the number of cattle has decreased by almost 70%.[17] Many traders and transporters were Muslim and forced to flee to neighbouring countries, bringing about a collapse of the commercial sector. CAR was suspended from the Kimberley process (KP), which is a joint governments, industry and civil society initiative to stem the flow of conflict diamonds. In 2015, the KP secretariat initiated a process towards CAR’s reintegration.[18]
[16] World Bank (2015) and IMF (2015).
[17] FAO/WFP (2014), Crop and Food Security Assessment Mission to the Central African Republic.
[18] EC (2015), Note for the attention of the members of the committee established pursuant to article 22 of Council regulation No 2368/2002, Ref. (2015)2786684.

Whilst there remains a basic structure of civil servants supporting the health, education and livelihood sectors, they have no resources to function, are often reluctant to deploy to their post and technical capacity is extremely weak. Most ministries need restructuring, starting with a mapping of available HR resources and capability and the adoption of strategic plans. Despite these challenges, there are opportunities to empower local authorities by closely associating them to humanitarian and early recovery programmes and co-opting them to deliver technical supervision.

The 2016 Humanitarian Response Plan requires £373 million to provide assistance to two million people (out of 2.3 million people in need). As of April 2016, it is funded at 0%.

CAR refugees
Cameroon and Chad welcomed a large number of refugees and Chadian ‘returnees’ in 2014, while the DRC already hosted a large caseload from the previous years. People arriving to the DRC travelled on shorter routes, and refugees and evacuees arriving in Chad often benefited from AU-escorted convoys to escape. In Cameroon, the first waves of refugees arrived on trucks, but ensuing waves arrived after journeying for months through CAR’s forests, where they were subjected to multiple attacks, to disease and lacked access to any assistance. Around 300,000 people left CAR in a few months following the December 2013 events. DFID found the humanitarian situation to be acute among refugees in Cameroon, where only 10% of refugees had arrived with any property. Global acute malnutrition rates exceeded 30-40% in early 2014 on some sites in Cameroon and severe acute malnutrition rates 15%.[19] [20] As much as 30% of refugees were separated from part of their family.[21] MSF estimated that refugee households in Southern Chad had lost 8% of their members to violence in the conflict.[22]
[19] MSF (2014), Briefing note – Cameroon: stepping up assistance to new refugees.
[20] The emergency threshold is respectively at 15% and 2%.
[21] DFID Information note on DFID’s support to the regional response to CAR refugees in Cameroon and Chad, 24 July 2014.
[22] MSF (2014).

Underfunding also hindered operations. In Cameroon, the refugee response in 2014 relied almost entirely on UN agencies and MSF’s own funding and on Central Emergency Response Fund (CERF) support in the first six months. Whilst Chad and the DRC had humanitarian communities better prepared to respond to needs on such a scale, a lack of preparedness left agencies in Cameroon initially unable to cope with this rapid influx of refugees and with such acute levels of malnutrition. MSF launched mobile clinics in early 2014 and took over several treatment centres to address the high mortality rate among malnourished CAR children in Cameroon. WFP declared a Level 3 crisis to access adequate internal resources to tackle the malnutrition crisis. UNHCR set up a large operation to register and assist refugees scattered along the CAR border and established sites that hosted around half of the refugee population (the other half remaining in host communities).

## Role of other actors

### Government
The transitional authorities appointed in 2014 have seen their role constrained to the extreme by insecurity, a low state budget and high external debt. CAR authorities have focused on the political transition, which has included the organisation of the Bangui forum and the planning of a constitutional referendum and national elections. Authorities also began in 2014 the redeployment of state officials, but this process has stalled due to insecurity, lack of essential and banking services and poor working conditions. With a tightly constrained budget, authorities have been dependant on humanitarian and development actors to support essential services such as health and education and assist with economic recovery. The state is likely to depend heavily on external support until 2020 to see its GNP recover from the shock according to the International Monetary Fund (IMF) to pave the way towards recovery.

### The UN
The UN Bureau for the Consolidation of peace in CAR (BONUCA) was established in 2000 (S/PRST/2000/5) and replaced in 2009 by an integrated office called BINUCA (S/PRST/2009/5). BINUCA was subsumed under the UN peacekeeping operation MINUSCA when it came into effect in September 2014 in accordance with UN Security Council resolution 2149 (2014).

UN humanitarian agencies withdrew much of their personnel at the height of the crisis in 2013. The UN Inter-Agency Standing Committee declared a level 3 (L3) disaster in December 2013 in the face of mounting needs, forcing agencies to bring back their teams and seek additional personnel and resources. The UN decided to end the L3 status in May 2015 as a reflection of improvements in humanitarian delivery. In December 2015, WFP announced it was considering triggering an internal L3 scale-up, in response to mounting food insecurity. UN presence has substantially increased across the territory, but remains limited in a large number of areas given the vastness of the territory and difficult logistical access.

### Red Cross Movement
The International Committee of the Red-Cross (ICRC) has been operational in CAR since 2006. It is active across all its sectors of intervention and has remained operational throughout the crisis, working across much of the frontline and in Bangui and providing ad hoc assistance in the west of the country. The ICRC has played a critical role in addressing humanitarian gaps during spikes of violence in 2013 and 2014, coordinating with other agencies to hand over activities once other actors had scaled up.

The Central African Republic Red-Cross Society (CRRCA) has a wide network of volunteers but limited capacity and resources. Successive support programmes have helped build its capacity in water, sanitation and hygiene (WASH), family reunification and in mortal remains management. With its wide geographical presence, the CRRCA is an attractive partner for many agencies, but still needs to consolidate its governance structure and technical capacity and requires adequate support when contracted as an implementing partner.

### NGOs and civil society
The number of international and national NGOs in CAR has risen dramatically since 2014 as funding increased in country. There are credible partners across sectors, and a number of them have expertise enabling them to transition from relief to recovery. Extremely high set-up costs combined with very poor road infrastructure mean that in practice humanitarian coverage remains limited compared to the scale of needs and is expensive to implement. This is especially true in the East of the country which has markedly fewer roads due to its very low population density.

CAR has a growing national charity sector, with some organisations with over a decade of experience in agricultural assistance and legal aid, among other sectors. A number of CAR NGOs have become UN partners and some have accessed funding from the Common Humanitarian Fund. Some weaknesses shared by many partners include low logistical capacity and fiduciary risks mechanisms that need consolidating. Technical expertise can widely fluctuate in quality.

CAR also has networks of churches and religious institutions that have historically provided substantial services in healthcare and education (with an element of cost recovery). These networks have also expanded their activities to include humanitarian support. Religious platforms have also been active in promoting peaceful conflict resolution and social cohesion.

### Humanitarian coordination
CAR has a Humanitarian Country Team (HCT) led by the Deputy Special Representative to the Secretary-General (DSRSG) who also functions as Humanitarian Coordinator (HC). The HCT includes donors and NGO representation. The HCT has at times faced significant delays in its decision-making process and has struggled to follow up on decisions. On the other hand, it has also several times taken a strong and principled stance in a complex context to protect and assist people in need. National and local NGOs attend cluster meetings. They run a national coordination platform and have no presence on the HCT. UNOCHA is endeavouring to reinforce coordination in the country by regionalising its positions and has signed agreements with partner organisations who will take the lead and coordinate where OCHA lacks presence.

UNOCHA has under its responsibility the Common Humanitarian Fund (CHF), which provides funding to international and national NGOs and UN agencies to address critical humanitarian gaps.

### Other donors
Key donors in CAR include the EU, the US, France, the World Bank, and the IMF. Germany, Sweden and Canada have been alongside the UK among the biggest humanitarian donors.

The EU has provided military assistance along with humanitarian, recovery, development and bilateral aid. Non-military assistance has been provided through a variety of channels, including ECHO, EuropeAid and an EU Trust Fund (the ‘Bekou Fund’) co-created with France and Germany. EU non-military aid reached £73 million in 2015.

France has made a huge contribution in CAR through its military operation Sangaris, which launched in December 2013 and was originally 2,000 troops strong. In 2014-15, France committed more than £51 million in humanitarian, recovery and bilateral aid in addition to their military contribution.

The US allocated £56 million in humanitarian aid in 2015 and £3 million in support of the political transition process.

The World Bank budget was around £27 million in 2015 for humanitarian and early recovery activities and budget support. The World Bank is launching in 2015 a reengagement process to access new funding and help the country out of the transition.

The IMF has provided substantial technical assistance to enable other donors to contribute in budget assistance and help authorities pay for public sector salaries. The IMF has also disbursed three rapid credit facilities since 2014 and aims to open an extended credit facility for CAR in 2016.

The Africa Development Bank has resumed operations in CAR, albeit on a modest scale. It has focused on budget aid and humanitarian and recovery assistance.

### Remaining gaps and role of DFID
The above assessment of the existing context and institutional framework has identified three main barriers to effective humanitarian aid delivery in CAR. These are set out below.

Challenge 1: A protracted crisis
The CAR humanitarian and refugee crisis will not go away. Despite a humanitarian response at scale since 2014, needs remain extremely high and food insecurity is worsening year on year, with 50% of the population food insecure in 2015 compared with 29% in 2014.[23] Even in a best-case scenario of steady progress towards stabilisation, the CAR population and refugees will require sustained support in the next five to ten years to provide basic services, stabilise food security and lay the foundations towards recovery. It could take 5 to 10 years of steady assistance before development initiatives and economic recovery have sufficiently kicked in to enable a significant drop in relief aid.
[23] WFP/FAO (2013, 2014, 2015).

CAR requires simultaneous effective intervention across all sectors for lasting recovery. Substantial UK assessed contributions will reach CAR through the EU, the UN and the World Bank in the next few years and it will be in the UK interest to closely monitor these multilateral partners’ strategy in CAR and that these funds contribute to sustainable solutions.

CAR’s extreme structural weaknesses, corruption and neopatrimonial governance have directly caused the current conflict, which has proven more divisive and violent than any before. CAR’s social cohesion has been shaken at its core and unless we help build the country back better, we should expect the country to relapse into war in a matter of years, and could fear that this time around, it might not be possible to prevent a further round of conflict from becoming genocidal.

The risk of CAR becoming an irreparably failed state in a matter of years without sustained assistance and engagement is real – hence the bold decision taken by international financial institutions, the EU and France to provide budget aid despite high fiduciary risks. An ungoverned state the size of France situated between Sudan, South Sudan, Chad, Cameroon, the Republic of Congo and the DRC would be bad news for regional stability and African prosperity.

Without adequate support in neighbouring countries to address the needs of CAR refugees, the CAR crisis threatens to undermine the economic development of Cameroon, Chad and the DRC and the host populations’ access to basic services, as well as become a source of social tension between host and refuge populations. A disenfranchised refugee population would also be at greater risk of recruitment by extremist groups.

Challenge 2: The need to link relief, recovery and development
Needs in each sector are so far reaching that any intervention must fit in a wider strategy towards recovery and provide immediate as well as structural support. This requires a new form of thinking and coordination, and close linkages between humanitarian and development partners and donors.

There is very limited multi-year humanitarian funding in CAR despite the protracted nature of the crisis. Longest funding windows are 18 months, precluding strong transitional thinking and strategies.

A stronger recovery and development strategy should not be detrimental to short-term response. There are still substantial spikes in instability leading to displacements and very short-term needs, which the humanitarian community must be able to address effectively.

Refugee assistance is also a priority and has been under-funded since the onset of the crisis. Helping refugees regain self-sufficiency will be essential to avoid the trap of aid dependency.

Challenge 3: The need for effective, coordinated aid that reaches remote communities
The humanitarian response has been uneven, with prefectures still under-served due to low humanitarian presence. This uneven treatment is exacerbated by the limited availability of reliable data on needs. Paving the way towards stronger coordination, response and development requires better information sharing.

The complexity of the CAR challenge has required new levels of creative thinking, including innovative programming in sectors such as protection and livelihoods. There is an urgent need to ensure that partners move to professionalise data collection and that evidence around what works be collected and shared.

The difficult operating environment in CAR is marked by poor access to conduct analysis, implementation and monitoring of programmes; a high level of risk for local and expatriate humanitarian staff; and a high risk of fraud and aid diversion.

The three types of challenges set out above have led to identifying four specific priorities that the CHURP will seek to address, while continuing to meet humanitarian needs:

The UK will need to engage and programme aid in a matter that is consistent with the protracted nature of the crisis;

UK aid and UK engagement will need to effectively address short-term humanitarian gaps and support the transition towards stabilisation and recovery both directly and through advocacy with multilateral partners;

We will need to support humanitarian coordination by increasing our engagement where possible;

We will support the improved disaggregated data collection (by geography, sex and age), analysis and generation of learning on what works well and less well to inform future programming, although are heavily reliant on partners changing their internal systems and processes around data collection, often at a central level.

We propose to structure DFID support under this business case to enable DFID to provide relief and recovery assistance and to engage with strategic issues, coordination, influencing and leadership in the humanitarian system in CAR.

#### Why DFID?

DFID reviewed needs arising from this crisis to determine what sectors if any should take priority in a potential response. In CAR, other donors such as the EU and the World Bank have existing programmes and demonstrated technical expertise in education, governance, public finance management and long-term economic recovery. DFID does therefore not propose to get involved in those sectors, where it does not have a demonstrated added value.

DFID has coordinated with other donors since 2013 to identify need gaps and sectors in which UK funding would have an added value. Health, protection and livelihoods were identified as critical, along with emergency support addressing surges in needs. In health, DFID-funded programmes helped keep global and under-five mortality rates under the emergency threshold in 2015.[24] In 2014 and 2015, DFID funding helped reach about a third of the 150,000 households assisted by the Food and Agriculture Organization with livelihoods support.[25] In addition, short-term assistance to displaced populations and returnees (such as water and sanitation, shelter and non-food items) helped plug critical gaps during mass displacements.[26]
[24] IMC (2016), Third quarterly report.
[25] FAO (2015), Final report; FAO (2016), Second quarterly report.
[26] DFID (2014), CAR 2013/14 Project Completion Review.

Among CAR refugees, DFID’s intervention in Cameroon helped bring malnutrition rates well below the 15% emergency threshold and bring water supplies on refugee sites around the Sphere standard mark [27]of 15l per person per day[28]; In Chad, the PHASE programme implemented in the Sahel will help address needs in 2016/19. In the DRC, DFID’s support to the Common Humanitarian Fund enables the humanitarian community to address aid gap among refugees. CAR refugees in Cameroon are however not supported by other DFID operations and substantial funding gaps have plagued the response since the beginning. DFID will therefore continue to have an added value in funding this response.
[27] The Sphere Project, http://www.spherehandbook.org/en/water-supply-sanitation-and-hygiene-promotion-wash/ The Sphere Project has identified a set of evidence-based standards in key life-saving sectors and describes conditions that must be achieved in any humanitarian response in order for affected populations to survive and recover in stable conditions and with dignity. The WASH standards are qualitative in nature and specify the minimum levels to be attained in humanitarian response.
[28] DFID (2015), CAR 2014/16 Annual review.

DFID has made a global policy commitment to remain a leading humanitarian donor and address priority needs. DFID’s 2011 Humanitarian Emergency Response Review (HERR) and subsequent Humanitarian Policy have shaped our approach to humanitarian response. ARD’s Business Plan 2016-21 (under preparation) will restate DFID’s commitment to providing humanitarian assistance including in tier-two countries and tackling the drivers of conflict.

Box 1 – linkages with the cross-Whitehall CAR strategy / The cross-Whitehall CAR strategy adopted in July 2014 and updated in March 2015, identified four areas of concern for UK intervention: security and justice, political transition, humanitarian aid and economic recovery. In the first two sectors under an FCO lead, the UK proposed to support the stabilisation of the country, in particular by supporting and monitoring MINUSCA’s operational delivery, and engaging on security sector reform, armed group demobilisation and on the transition process. In practice, UK engagement has primarily focused on advocacy through the UK mission to the United Nations in New York, participation in International Contact Group meetings, and bilateral interaction with other missions. / To address needs under the last two sectors, DFID has committed to providing fair and transparent humanitarian assistance in CAR and engaging with other donors to ensure they take a fair share of the response. DFID has also provided recovery aid and engaged with international financial institutions and the UN in support of a transition articulating between relief, recovery and development programmes. / DFID has also engaged with UN agencies to ensure there is a coordinated response to the regional refugee crisis. DFID will directly support refugees to ensure they progressively recover their self-sufficiency. / This proposed Business Case is therefore consistent with priorities identified under the cross-Whitehall strategy.

DFID has so far provided £63 million in humanitarian assistance since 2013 for CAR and CAR refugees. The UK was the third largest humanitarian donor in 2015 and the fourth in 2014. Our allocation was equivalent to 4% of the CAR appeal and 8% of the refugee appeal in 2014. In 2015, it was equivalent to 4.7% of the appeal in CAR and 5.3% of the refugee response plan.

DFID has some key advantages in CAR:

Capacity to fund longer term projects, which increases strategic coherence and promotes efficiency and effectiveness in achieving outcomes;

Flexibility to fund humanitarian and recovery activities together, adapting to context;

Risk appetite and ability to fund more innovative delivery options, with an ability to reach most vulnerable populations;

DFID as a major humanitarian and development donor allows cross-office working to build linkages between humanitarian, development and peacebuilding engagement (see theory of change).

## The CAR Humanitarian and Recovery Programme (CHURP)

Given the above analysis of DFID’s added value and the targeted challenges for improving humanitarian assistance, this section identifies what the CHURP will seek to achieve.

Planned impact: Reduce suffering of crisis affected people in CAR and among CAR refugees, and support to recovery.

Planned outcomes:

- Increased effectiveness of humanitarian action in protracted crises
- Improved quality and coverage of emergency response
- Enhanced focus on supporting simultaneous delivery of relief and recovery assistance at individual, community and country level.

### CHURP objectives

  - Improved protection and provision of basic services to vulnerable people living in protracted crises
Objective 1
  - Improved approaches to supporting simultaneous delivery of relief and recovery assistance
Objective 2
  - Better accountability, coordination and coherence of the humanitarian, development and UN system
Objective 3

Objective 1 – Improved protection and provision of basic services to vulnerable people living in protracted crises

The situation in CAR remains predictably unstable. There are and will continue to be surges in violence leading to spikes in needs as well as periodic movements of return. The CHURP will have to continue supporting a nimble, rapid and flexible humanitarian response to address those spikes in needs, including among conflict-affected and displaced populations. It will also need to be responsive to movements of return and assist with the rapid resumption of livelihoods, essential services and shelter provision.

Work in this area will therefore look at supporting actors with proven expertise in responding to spikes in needs. To retain a capacity for a flexible response, the CHURP will include a Contingency Facility enabling DFID to scale up aid where unusually large surges in needs occur.

Whilst the slow and painstaking process of rebuilding CAR institutions begins, delivery on the ground creates opportunities to cooperate with relevant authorities such as district, regional and national health authorities, and local agents of technical agencies attached to the Ministry of Agriculture. This cooperation can take the form of training, information sharing and targeted support where relevant. It will fall short of budget support, which falls within the remit of other donors’ development and budget aid programmes.

Objective 2 - Improved approaches to supporting simultaneous delivery of relief and recovery assistance

The CAR crisis will be a long-lasting and drawn-out one inasmuch as it requires the (re)construction of all sectors. In sectors such as health, livelihoods and protection, we need a response that goes beyond the strictly humanitarian to look at rebuilding resilience. CAR refugees have been displaced for two years and are unlikely to return to CAR until the deep-rooted sectarian tensions have been resolved and reconciliation has made substantial progress. Meanwhile, it is essential to help refugees regain some level of self-sufficiency and to strengthen Cameroonian authorities’ capacity to manage the existing load through their existing healthcare and education system.

The CHURP will therefore provide assistance that goes beyond humanitarian short-term aid and supports simultaneously longer-term delivery of essential services and recovery. The objective is to assist beneficiaries regain self-sufficiency and strengthen their resilience, and support the (re)construction and strengthening of essential services across CAR and the refugee response. The focus will be placed on sectors most affected by the crisis where aid is most likely to decrease vulnerability and aid dependency, including healthcare, livelihoods, and social cohesion.

Evidence demonstrates the greater effectiveness of predictable aid in protracted crises, particularly where building resilience is concerned. The CHURP will therefore provide multi-year funding over a period of 3 years to help lay the foundations towards recovery.

Objective 3 - Better accountability, coordination and coherence of the humanitarian, development and UN system

DFID will use its position within the CAR humanitarian fund board and donor coordination structures to influence the agenda and ensure there is cooperation between humanitarian and recovery funding. DFID will continue to strengthen its engagement with the Humanitarian Country Team and OCHA as well as ECHO to influence the humanitarian agenda. DFID will use CHASE OT to support strategic staff deployments into the UN. DFID will also engage and consolidate its strategy with regard to the World Bank, IMF and Africa Development Bank in CAR, the European Development Fund, the Bekou fund and through FCO with the UN peacekeeping operation.

### Cross-cutting themes
While there are many cross-cutting themes relevant to the CHURP that will be addressed through on-going management, the core themes are listed below, and will be considered in this business case.

There is a lack of evidence in CAR around equity in aid delivery. DFID will therefore work with partners to ensure that conflict and gender sensitivity is mainstreamed through all activities including at the assessment stage, through monitoring, evaluation and accountability mechanisms and reporting. This will help build an evidence base to steer the CHURP and inform future engagement.

Conflict sensitivity
Conflict sensitivity of the CHURP will be addressed through engagement with partners and appropriate risk management. Conflict sensitivity will be a requirement of DFID partners and will be monitored throughout the programme cycle. Risks of humanitarian assistance provoking conflict or doing unintended harm exist throughout. These can be mitigated through adequate consultation, design and strong accountability mechanisms.

Gender and Gender Equality (Compliance with UK 2014 Gender Equality Act)
Gender is always a critical issue in crisis situations. There is strong evidence internationally that crisis situations affect men and women differently and have a significant impact on gender dynamics.[29] Humanitarian crises often lead to a breakdown of health services (including sexual and reproductive services), detrimentally impact upon food security and nutrition, and rule of law/access to justice. Crises differentially impact upon poor men and women, girls and boys and other vulnerable groups including religions and/or ethnic minorities, the elderly and people with disabilities. In general, sexual and gender-based violence (SGBV) disproportionately affects women and girls though boys and men may also be victims, especially in conflict situations where SGBV can be perpetrated as a weapon of war. Men and boys may be more at risk of overt violence and forced recruitment into armed forces and groups[30], though again women and girls may be recruited too. In the context of CAR, child soldiers include both boys and girls.
[29] E.g., Oxfam (2013), “Humanitarian Policy Note: Gender Issues in Conflict and Humanitarian Action”; OCHA (2012), “Gender Equality in Humanitarian Action”.
[30] International Alert (2014), “Rethinking Gender in Peace Building”.

Humanitarian crises have a significant impact upon access to public health services with significant implications for women’s health. Eight of the ten countries with highest maternal mortality ratios in the world are in fragile circumstances[31], including CAR. Child mortality is also higher in humanitarian crises where again CAR has one of the highest rates in the world. Sexual and reproductive health services are critical to prevent and support recovery from SGBV, as well as vulnerability to HIV/AIDs and unmet need for contraceptives, especially for vulnerable women and girls. Women’s physical integrity in CAR is further undermined by the fact that abortion is illegal unless to save a woman’s life. It is not permitted in cases of rape or to preserve a woman’s physical or mental health.[32]
[31] World Health Organisation, 2012. Integrating sexual and reproductive health into health emergency and disaster risk management. A policy brief. WHO, Geneva.
[32] OECD, 2014. Social Institutions and Gender Index. OECD Development Centre.

In CAR, gender issues vary between different parts of the country, but women and girls occupy overall a weaker position in society.[33] SGBV is highly prevalent: in 2015, more than 60,000 survivors sought assistance in relation with SGBV issues.[34] Women and girls’ weaker social standing is reflected in a societal tolerance towards domestic violence (which is not criminalised), a lack of recognition for female head of households and discriminatory practices around inheritance particularly for widows. The legal framework addressing rape does not encompass marital rape. The 2014 Human Development Index reported mean schooling year for females at 2.3 compared to 5.6 for males.[35] The gross national income is $482 for females against $698 for males. This said, under 5 mortality was at 135 in 2012 for males against 122 for females[36] and life expectancy was 52.1 years for females in 2014 versus 48.3 for males.[37] The experience of DFID partners demonstrates that women and girls will access remedial services if they become available, which is also a means to improve assessment of the depth of the problem.
[33] This paragraph is based on the OECD Social Institutions & Gender Index, http://genderindex.org/country/central-african-republic.
[34] UNFPA (2015), UK advocacy event on sexual violence for the 16 days of activism against gender based violence organized by TEARFUND.
[35] UNDP (2014), Human Development Report 2014 Central African Republic. By contrast in Sub-Saharan Africa overall the result is 3.7 for females and 5.4 for males, a gap half that of CAR.
[36] UNICEF (2012), http://www.unicef.org/infobycountry/car_statistics.html.
[37] UNDP (2014).

Lack of enforcement of CAR laws prohibiting violence against women and under-reporting due to social stigma, contributing to the lack of data on the prevalence of SGBV, are significant challenges to developing humanitarian and civil prevention and recovery responses. Women are also targeted and detained by the authorities for the practice of witchcraft, punishable by prison and sometimes execution, with women also vulnerable to mob violence. Women’s access to public space is severely curtailed in CAR by forced displacement due to the crises and also by a legal system that gives the husband the right to choose the location of the family abode.[38]
[38] OECD, 2014. Social Institutions and Gender Index. OECD Development Centre.

Although DFID partners report gender-disaggregated results to DFID, there is overall a lack of evidence in CAR on how well programmes perform to mitigate gender inequalities and contribute to the prevention of SGBV. The approach under this business case will therefore be to work with partners to strengthen evidence gathering at the planning and implementation stage and through monitoring, evaluation and accountability mechanisms. This will include ensuring local gender analysis and assessment is undertaken, and that all projects meet standards of at least the mainstreaming of gender issues.[39] Gender considerations will be an explicit part of all projects and of monitoring and evaluation as well as accountability mechanisms. In programmatic terms the particular risk of violence in conflict environments will be addressed through gender mainstreaming and through protection programming, which will include a focus on gender-based violence, and differential consideration of the risks of men and boys and those of women and girls. Programming in reproductive health and nutrition will also address the needs of women and girls in particular.
[39] This will be assessed through the use of the IASC Gender Marker, with projects requiring a score of at least 2A, “demonstrating the potential to contribute significantly to gender equality.”

The Office for the Coordination of Humanitarian Affairs (OCHA) clusters, for which the CHF is a delivery mechanism, are mandated to include gender equality in their humanitarian response which should be informed by age and sex disaggregated data to meet the diverse needs of different age and genders in the population. Historically, this has been a weak area in the delivery of the clusters due to lack of data but also to lack of awareness and lack of gender expertise. In 2016, a gender specialist was invited to help clusters strengthen gender-mainstreaming. The CHF also raised requirements linked to gender for projects presented for funding and started incorporating gender into its wider monitoring work. Our support through CHF programming will seek to further strengthen these areas.

Sex and age disaggregated data will be collected throughout the CHURP, with a strong emphasis on improved gender sensitive analysis with all of our partners and learning on what works to improve future programme outcomes. Gender will be appropriately reflected in the logframe when it is developed. Monitoring and evaluation of the programme will rely on improved programme data collection and analysis.

Resilience
Supporting resilience at an individual and institutional level will be a priority under the CHURP. As a primarily humanitarian programme, the initial focus will be on building resilience of communities and individuals. Specifically this will mean moving focus from the delivery of relief items to interventions that promote the capacity of affected people to improve their situation in the longer term, for example:

Helping communities in CAR and CAR refugees address their food security needs and regain self-sufficiency to decrease their dependency on food assistance, while helping strengthen local markets and supporting locally the resumption of trade;

Ensuring populations have access to basic health services to ensure that mortality and morbidity are brought under control and that global acute malnutrition does not reach emergency level;

Building community self-protection capacity through strengthening of community networks and improving mental health and psycho-social support, recognising the emerging evidence base[40] of the long term impact of this issue and the limited attention this issue has received;
[40] See IASC advocacy paper for a summary of evidence and recommendations in this area https://interagencystandingcommittee.org/system/files/20150721_iasc_mhpss_rg_whs_advocay_paper_.pdf

Supporting CAR authorities at a grassroots level by ensuring that health, livelihoods and reconciliation initiatives closely associate local authorities and where relevant provide opportunities for capacity building and information sharing. Indirectly, DFID will aim to support CAR authorities in key sectors of intervention through advocacy and by contributing to donor working groups and coordinating with donors leading on technical assistance and budget support, including the EU, the World Bank and AFD.

Accountability to affected populations
Ensuring that the voice and opinions of crisis-affected populations is reflected in programming is essential to the effectiveness of the programme. DFID will ensure across its partnerships that accountability to beneficiaries is mainstreamed and feeds into partners’ programme management practices. There is a lack of evidence on equity and the impact of aid on various groups forming the CAR society. DFID will ensure that partners develop assessment tools and requirements along with monitoring, evaluation and accountability tools to strengthen the evidence base and foster better accountability.

#### Expected results
The theory of change below sets out the main anticipated outcomes of the CHURP. It shows how the actions of the Business Case fit within the cross-Whitehall CAR strategy.

### Assumptions
The critical assumption is that the CAR situation will not drastically deteriorate, and that assistance will be sufficient in quantity and quality to stabilise food security. It will be characterised by a lengthy transition process involving a drawn-out reconstruction of state authorities and very slow economic recovery, coexisting alongside many large pockets on instability where humanitarian needs will remain acute and widespread. Humanitarian assistance is likely to remain possible throughout the programme, though access might be severely constrained at times.

### Theory of change

Cross-Whitehall CAR strategy
Security & Justice
FCO lead
DFID advocacy
Governance

FCO lead
DFID advocacy
Humanitarian & recovery

DFID lead
Economic

DFID lead

Reduced suffering and improved resilience among CAR populations and refugees
To help create security, political and governance environment conducive to recovery through advocacy with FCO, the EU and MINUSCA.
Improved humanitarian coordination and flexibleresponseto surge in neds
Empower humanitarian coordination for rapid and effective decision-making
Provide rapid reponse to spikes in needs among CAR populations, IDPs and returnees.
Improved response to protracted needs and transition to recovery in CAR
Provide access to essential health services
Support early recovery in livlihoods and agriculture
Help reinforce social cohesion and support local reconciliation
Address urgent needs among CAR refugees
CAR refugees access food assistance
CAR refugees see other essential needs met
Ensure key development actors (WB, EU) are adequately linked up with humanitarian funding streams.
Ensure IFIs provide adequate support to economic recovery.
# Appraisal Case

## Design principles

The preceding analysis has considered the rationale for a DFID intervention based on the scale of humanitarian needs in CAR and the capacity of the existing system to address those needs. The 3 CHURP objectives summarise what the CHURP should do to deliver effective humanitarian assistance that supports a transition towards recovery.

The appraisal case will consider how the CHURP can best achieve the 3 objectives and deliver value for money. Together with analysis of performance of the existing DFID humanitarian portfolio in CAR[41], the conclusions are that the CHURP should demonstrate:
[41] DFID (2014), CAR 2013/14 Project Completion Review; DFID (2015), CAR 2014/15 Project Completion Review.

1. A streamlined and consolidated UK approach to humanitarian support in CAR. To allow DFID to scale up action we will need to design an efficient programme management structure, in line with the resources available in the Africa Humanitarian Unit.
2. Flexibility to scale up and down. The analysis in the Strategic Case suggests that the level of protracted needs is likely to remain high for the period of the business case with periodic spikes in humanitarian needs. The CHURP needs to have flexible capacity to respond to new or increasing needs and drastic funding gaps, or to adapt funding in case of an improving environment.
3. Capacity to deliver simultaneously humanitarian and early recovery assistance. DFID’s programmes since 2013 have supported life-saving interventions and programmes addressing early recovery needs in livelihoods and social cohesion. CAR’s protracted crisis will require sustained and predictable engagement along with programming and advocacy supporting early recovery assistance. Increased grassroots engagement with CAR authorities in priority sectors such as health and livelihoods will help lay the foundations to transition towards development assistance. The CHURP will not include any budget aid or state building element. DFID will implement a strategy of targeted advocacy with international financial institutions and development donors to underpin the CHURP and cross-Whitehall CAR strategy.
4. Multi-year support to address humanitarian needs. There is a growing body of evidence to suggest that multi-year funding is a critical tool for improving the effectiveness of humanitarian aid to protracted crises[42]. A number of donors have developed mechanisms to allocate funding in these contexts on a multi-year basis, channelling funding directly to NGOs, the UN and other multilateral agencies, and to country-level humanitarian response or emergency relief funds[43]. Multi-year funding is seen as useful because it increases predictability, provides implementing partners with greater flexibility, incurs lower operational costs and allows donors and their implementing partners to develop more strategic partnerships.
  [42] Venton (2013), “Value for Money of Multi-year Approaches to Humanitarian Funding”.
  [43] E.g. ODI (2015), “The development agency of the future: Fit for protracted crises?”; Development Initiatives (2015), “Think Piece: Humanitarian Financing”; OECD (2015), “Financing in Crisis? Making humanitarian finance fit for the future”, OECD Development Cooperation Working Paper 22.
There is limited evidence in CAR on equity, making it difficult to appraise options against this objective. We will however work with partners to make sure that equity is taken into account across their programmes, processes and reporting to help build the evidence base.

## Options appraisal

This section will identify and critically assess Value for Money (VfM) of the range of options available to address the need set out in the Rationale for Intervention. It will use the ‘3 Es’ VfM framework in line with DFID’s approach to value for money.

### Value for money methodological framework

The appraisal will assess the feasible set of delivery options against the questions set out in the framework below.

Table 1: VfM Framework
	Description	Appraisal questions
Effectiveness	Spending wisely – the option should have the ability to achieve the 3 CHURP objectives in order to realise the desired outcomes	To what extent is the option likely to achieve the 3 CHURP objectives?
Efficiency	Spending well – the option should ensure that DFID and our implementing partners convert inputs into outputs in the most efficient way, in line with the design principles we have identified for the CHURP	To what extent is the option consistent with the 4 design principles identified in the Strategic Case? (Streamlined support, flexibility, capacity to transition and multi-year funding)
Economy	Spending less / getting more for the money – the option should ensure adequate control over input costs and ensure we understand what drives them	What are the costs to DFID to manage and implement the CHURP under this option? / Does the option enable DFID to ensure that implementing partners are buying inputs of the appropriate quality at the right price? / In rapid onset crises, will DFID be able to measure speed, quality and cost sufficiently well?[44]
[44] DFID guidance sets out the criteria of speed, quality and cost as an alternative framework for measuring VfM in emergency response.

### Feasible options

The feasible options to address the needs described in the rationale for intervention are set out in detail below. The ‘do nothing’ option would be to halt DFID support to humanitarian assistance in CAR. This is dismissed as it does not address the needs set out in the rationale for intervention above. The feasible options for delivery of the CHURP are:

- Option 1: Do nothing. This will result in an immediate increase in needs where DFID currently provides healthcare assistance and among CAR refugees, and a drastic drop in overall livelihoods support. It will have an immediate negative impact on morbidity and mortality rates in areas of intervention. It would fail to address the rapid deterioration in food security, which presents a risk of famine among CAR’s most food insecure populations. Given its humanitarian implications, this option is not in line with good humanitarian donorship principles or the recommendations of the Humanitarian Emergency Response Review that DFID should strengthen its capacity to anticipate disasters, support local resilience and address the needs of the most vulnerable.[45]
  [45] Lord Paddy Ashdown (Chair) (2011), Humanitarian Emergency Response Review.
- Option 2: In line with the existing approach, DFID would deliver support through a series of Accountable Grants and Memoranda of Understanding to UN agencies, the ICRC and two NGO consortia in CAR and to CAR refugees. DFID would directly manage up to 7 agreements, as is currently the case. This would include support to the Common Humanitarian Fund (CHF).
- Option 3: Channel DFID humanitarian support through the multi-donor CHF and the EU Trust Fund (Bekou Fund) to address spikes in needs, recovery needs among CAR populations and provide predictable services. DFID would manage two agreements. Our programmes would likely not cover CAR refugees.
- Option 4: Is a mixed between Option 2 and 3. DFID would look at extending tried and tested partnerships with UN and non-UN agencies including the Common Humanitarian Fund and the ICRC, while channelling its NGO support in priority sectors through the Bekou Fund thus decreasing progressively the number of grants it manages. DFID would manage an average of 5 grants, of which 4 would be contributions to UN and ICRC appeals and one a memorandum of understanding with the EU Trust Fund.[46]
  [46] Under this option, DFID would aim to support health, livelihoods and protection through the EU trust fund. In the event that the EU trust fund did not comprehensively address protection needs, DFID would reserve the possibility of signing an additional grant through UNHCR (also contracted for refugees).
Under all of the options, the Contingency Facility[47] would provide a rapidly deployable capacity that increases DFID’s flexibility to respond to significant new needs arising during the period of the Business Case such as major spikes in conflict or epidemics. This would be channelled through the chosen delivery modalities of the CHURP.
[47] See paragraph 57-59 for more detail on the Contingency Facility

### Detailed options appraisal

Option 2 would demonstrate our commitment to our existing partners and enable us to contract partners that have performed best since 2013. It would provide support directly to the UN, the Red-Cross movement and NGOs, with predictable funding enabling more in-depth planning. Option 2 would leave a substantial management burden on the Africa Humanitarian Unit though as these are tried and tested partnerships, the programme management burden would be considered manageable. DFID programmes would remain primarily humanitarian in nature but multi-year programming would enable some strategic support to recovery initiatives, incoordination with other donors. DFID would also have a wide range of partners through which it could channel funds in case of spikes in needs.

Options 3 would address the need to streamline the number of grants managed by DFID. The decrease in number of contracts would be counter-balanced by a new partnership with the EU trust fund, which has not undergone central level due diligence review, leaving a substantial overall programme management burden. By providing funding through the Bekou Fund, it would also enable us to strengthen our humanitarian funding with recovery initiatives. On the other hand, this option would fail to support partners we have considered crucial in addressing spikes in needs, including the ICRC in CAR and WFP and UNHCR in Cameroon. This option would also most likely not encompass programming for the underfunded CAR refugee response and is therefore considered sub-optimal.

Option 4 would be a cross between Options 2 and 3. It would involve a portfolio of 5 grants, most of them appeal contributions, leaving us with one more complex grant to manage, the EU Trust Fund. The decrease in number of contracts compared to Option 2 would be counter-balanced by a new partnership with the EU trust fund, which has not undergone central level due diligence review, leaving a substantial overall programme management burden. This option would provide a range of potential partners through which we might channel funds, should needs suddenly increase. By supporting programmes addressing protracted needs through the EU Trust Fund, this option would ensure that support is also given to CAR authorities and that they are associated with implementation, creating conducive conditions for a phase-out strategy. Whilst the EU trust fund has performed well in its health response, evidence is still limited on its performance in other sectors. Option 4 would therefore have a more limited evidence base.

This section appraises the options against the methodological framework set out above. Under each of the cost effectiveness criteria the options will be allocated a score between 0 - 4, where 0 = unsatisfactory; 1 = weak; 2 = satisfactory; and 3 = good; 4 = excellent performance against the criteria.

### Effectiveness analysis

Table 2 below assesses the 3 feasible options against their expected ability to deliver against the 3 objectives of the CHURP:

- Better support to protect and provide basic services to vulnerable people living in protracted crises
- Improved approaches to supporting the transition from relief to recovery
- Better accountability, coordination and coherence of the humanitarian, development and UN system

Table 2 Effectiveness analysis
Criteria – expected ability of option to…	Option 2 (No change – 7 grants)	Option 3 (CHF and EU Trust Fund	Option 4 (5 grants including CHF and EU Trust Fund)
Better support to protect and provide basic services to vulnerable people living in protracted crises	Good (3) By providing support to organisations focussed on the challenges at hand, this option will deliver activities that protect and provide basic services to vulnerable people in CAR and to CAR refugees. / Recent Project Completion and Annual Reviews of the current DFID portfolio scored the response in CAR and among CAR refugees as A in 2013 and 2014, despite challenging conditions.	Satisfactory (2) This delivery mechanism would be satisfactory in addressing humanitarian gaps and supporting recovery, but would fail to support preparedness and address the needs of refugees. It would also provide less flexibility to address spikes in needs.	Satisfactory (2) This approach would make sure that adequate assistance is provided through proven partners while creating conditions to rebuild resilience. / UNHCR scored A and WFP B in the 2015 Annual Review. WFP has since addressed pipeline weaknesses that had affected overall scoring. Whilst the EU trust fund has performed well in its health response, evidence is still limited on its performance in other sectors. Option 4 would therefore have a more limited evidence base.
Improved approaches to supporting simultaneous delivery of relief and recovery	Good (3) This option would primarily focus on humanitarian response and protracted needs. By coordinating with other donors but involving limited support to CAR authorities it would moderately support a transition to recovery.	Good (3) This option would provide adequate support to recovery and predictable services through the Bekou Fund.	Good (3) This option would provide adequate support to recovery and predictable services through the Bekou Fund and the ICRC.
Better accountability, coordination and coherence of the humanitarian, development and UN system	Good (3) This approach would enable us to increasingly influence the humanitarian coordination through the CHF. It will also enable us to deliver on grand Bargain objectives through our dialogue with UN agencies and the ICRC. This Option would provide us with moderate opportunities to steer the development response, through close coordination with other donors and the EU trust fund.	Good (3) This approach would enable us to influence the humanitarian coordination through the CHF and key development actors through the Bekou Fund, and ensure both fora are well linked up. It would help us ensure we have a model of EU Trust Funds that is fit for purpose to deliver aid in protracted crises. It would provide us with fewer opportunities to influence agencies to deliver on Grand Bargain targets.	Excellent (4) This approach would enable us to influence the humanitarian coordination and key development actors through the Bekou Fund, and ensure both fora are well linked up. It would also enable us to influence UN agencies to ensure the CAR refugee response supports recovery and resilience. It would help us ensure we have a model of EU Trust Funds that is fit for purpose to deliver aid in protracted crises.
Total	9 of possible 12	8 of possible 12	9 of possible 12

Strength of evidence: medium. Our evidence of the limitations of these options is based on our experience in country.

### Efficiency analysis

Table 3 below assesses the three feasible options against the design principles of the CHURP. These state that the CHURP should demonstrate:

- A streamlined and consolidated UK approach to humanitarian support.
- Flexibility to scale up and down.
- Multi-year support to address humanitarian needs.

Table 3: Efficiency analysis

Criteria	Option 2 (No change – 7 grants)	Option 3 (CHF and EU Trust Fund)	Option 4 (5 grants including CHF and EU Trust Fund)
Streamlined and consolidated approach	Satisfactory (2) The current portfolio of DFID humanitarian assistance includes 7 Accountable Grants and MoUs. This model is tried and tested and the programme management burden considered manageable.	Good (3) DFID support to NGOs and UN agencies would be consolidated under the EU Trust Fund to provide predictable services and response to protracted needs, but DFID support to refugees would cease in the process. DFID would concentrate its support to humanitarian response through the CHF. There has not been any central level due diligence review of the EU trust fund, so the management burden might be initially higher for this new partner.	Satisfactory (2) DFID support to NGOs would be consolidated under the EU Trust Fund. DFID would continue to manage 5 appeal contributions to the UN and the ICRC, but as these have a lower management burden, it would overall decrease DFID’s burden. There has not been any central level due diligence review of the EU trust fund, so the management burden might be initially higher for this new partner.
Flexibility to scale up	Good (3) DFID would retain the flexibility to scale up in CAR and among CAR refugees through a variety of partners.	Weak (1) DFID would have one partner only enabling rapid scale-up and would provide no support to preparedness.	Good (3) DFID would retain the flexibility to scale up in CAR and among CAR refugees through a variety of partners.
Multi-year support to address needs	Good (3) DFID would have the capacity to support multi-year planning through NGO consortia, UN agencies and the ICRC. DFID will try and incentivise UNHCR and WFP to strengthen their multi-year strategy for refugees.	Satisfactory (2) DFID would be able to plan its EU Trust Fund support on a multi-year basis, with programmes there implemented over a window of 18 months or above.	Good (3) DFID would be able to support multi-year planning through the EU Trust Fund and the ICRC. DFID will try and incentivise WFP and UNHCR to strengthen their multi-year strategy for refugees.
Total	8 of possible 12	6 of possible 12	8 of possible 12

Strength of evidence: medium-strong. There is extensive experience of the efficiency of Option 1 and the CHF in country. CHASE has done substantial work on documenting multi-year humanitarian approaches and lessons learned.[48] Further evidence should be provided through on-going evaluation work of the impact of multi-year funding on resilience.[49]
[48] DFID CHASE guidance including: “Multiyear humanitarian Business Cases lessons Learned Feb 2015”, “Umbrella, Thematic and Partner specific approaches to multi-year humanitarian funding Feb 2015”
[49] “Building resilience and managing risk in fragile and conflict-affected states: A thematic evaluation of DFID’s multi-year approaches to humanitarian action in the Democratic Republic of Congo, Ethiopia, Sudan and Yemen”, Valid International, Inception Report 2015

### Economy analysis

The economy analysis considers:

- What are the costs to DFID to manage and implement the CHURP under this option?
- Does the option enable DFID to ensure that implementing partners are buying inputs of the appropriate quality at the right price?
- In rapid onset crises, will DFID be able to measure speed, quality and cost sufficiently well?

Table 4 Economy analysis

Economy criterion	Option 2 (No change – 7 grants)	Option 3 (CHF and EU Trust Fund)	Option 4 (5 grants including CHF and EU Trust Fund)
What are the costs to DFID to manage and implement the CHURP under this option?	Satisfactory (2) The costs remain high particularly with regard to NGO consortia and FAO. However, as these are tried and tested partnerships, the management burden has incrementally decreased, and will be further decreased through streamlined multi-year programming.	Satisfactory (2) The costs are lower though shift to EU Trust Fund involves substantial staffing commitment in the first year to ensure the EU Trust Fund becomes a model replicable elsewhere.	Weak (1) The cost is higher than Options 2 and 3. All non-EU Trust Fund grants will be appeal contributions to trusted partners. However the shift to the EU Trust Fund involves substantial staffing commitment in the first year including to conduct a due diligence review.
Does the option enable DFID to ensure that implementing partners are buying inputs of the appropriate quality at the right price?	Good (3) This provides us with strong level of scrutiny to monitor VfM for NGO partners especially as we can compare performance across the years. We would have more limited access to UN/ICRC budgets.	Weak (1) This provides us with the least scrutiny of these processes.	Satisfactory (2) This provides us with some scrutiny through the partner budgets, but these are unlikely to be presented in great detail.
In rapid onset crises, will DFID be able to measure speed, quality and cost sufficiently well?	Good (3) This provides us with detailed scrutiny of partners’ performance in rapid onset crises.	Weak (1) This provide us with very little scrutiny of their performance.	Satisfactory (2) This provides us with adequate scrutiny of the performance except the EU Trust Fund. DFID will strive to ensure UNHCR strengthens evaluation process.
Total	8 out of 12	4 out of 12	5 out of 12

Strength of evidence: medium-weak.

Summary
Summary
Efficiency
Economy

In the above analysis, Option 2 comes out with the most balanced results across parameters and scores best on Value for Money. It is on par with Option 4 on efficiency and effectiveness. Option 2 involves to continue working with tried and trusted partners including UN agencies, the ICRC and two NGO consortia, through streamlined longer-term programming, combined with stronger coordination across the humanitarian and development spectrum.

# Commercial Case

## Direct procurement
In this Business Case we are likely to use £1.25 million for ongoing programme monitoring and CHASE-Operations Team (CHASE-OT)-managed deployments, through the CHASE-OT contract. We will also use the CHASE-OT contract for secondments into the UN system and ‘in-kind’ support to agencies, should critical gaps arise.

The existing logistics/procurement team in the UK Government’s CHASE Operations Team has a proven track record of delivering complex and robust support for the delivery of ‘in-kind’ humanitarian support and for providing extremely effective support for the deployment of, and support to, DFID teams.

## Procurement/commercial requirements for intervention

For the CHF, a Letter of Arrangement will be agreed setting out indicative disbursements and a disbursement schedule. DFID will also agree with the CHF an annex laying out performance indicators. The contribution level will reflect DFID’s policy commitment to support humanitarian coordination structures. The amount of each disbursement will be determined by considering the CAR appeal and surges in needs.

The CHF also allows funding to a majority of humanitarian implementing partners, provides a common prioritisation process across humanitarian actors, and UNDP provides due diligence and administration support, handles risk management in cooperation with OCHA which oversees allocations and the monitoring of projects[50]. As such, for the type of projects for which the CHF is appropriate, it provides significantly better value for money than alternatives for DFID that would include significantly more advisory and programme management capacity.
[50] See para 134 for more detail on the governance of the MERF

With the ICRC, UNHCR, WFP and FAO, DFID will sign a Memorandum of Understanding agreeing a contribution to the country appeal (earmarked in Cameroon for CAR refugees) or to specific projects. Depending on agencies’ performance and strategy, DFID will choose to leave these funds unearmarked by sector, or agree with partners a specific logframe.

DFID will sign Accountable Grants with NGO consortia based on agreed project proposals. These proposals and accompanying logframes will set out performance indicators against which these partners’ performance will be assessed.

## How does the design use competition to drive commercial advantage for DFID?

Substantial funding will be channelled through the CHF, which relies on competitive tendering for allocations.

DFID will also provide direct funding to the ICRC, UNHCR, FAO and WFP. These agencies have demonstrated added value in their area of expertise in CAR and for CAR refugees, as demonstrated by the 2013/14 and 2014/15 Project Completion Reviews and by the 2014/15 Annual Review.[51] Early indications from the recent MAR suggest that these agencies continue to be strong performers.
[51] QUEST reference 2013/14 Programme Completion Review, 4704966; 2014/15 Annual review, 4850522; 2014/15 Programme Completion Review, 5177274; 2014/15 Annual review, 5177284.

DFID will provide direct funding to the projects of two NGO consortia based on negotiated proposals. These consortia were selected through a competitive appeal process in 2015. They have performed well in 2015/16 according to DFID quarterly monitoring reports. DFID will therefore negotiate to continue activities that have demonstrated impact and value for money.

## What are the key cost drivers? How is value added and how will we measure and improve this?

We will ensure good value for money by channelling funding through the CHF, which will provide funding after competitive processes (call for proposals and/or expression of interest calls). The CHF has demonstrated added value in disbursing rapidly funding to a wide range of partners to address humanitarian gaps. Performance monitoring of the ICRC, UNHCR, FAO and WFP has demonstrated their added value in their fields of expertise and particularly in rapidly addressing need gaps for the ICRC while planning to transition to recovery, addressing food security needs in CAR and among refugees for FAO and WFP and addressing refugee needs for UNHCR as well as providing a protection response. We will place particular emphasis with WFP and UNHCR on ensuring that their multi-year strategy contributes to resilience building among refugees and state-provided basic services.

Among NGO consortia, DFID will seek Value for Money by negotiating to expand activities where partners have demonstrated greatest impact, added value and Value for Money in 2015/16. Where relevant, multi-year programming will seek long-term economies and to increase impact through greater cooperation with local authorities, particularly in health.

Key cost drivers are procurement, staffing and transportation. Security is also a significant cost driver in CAR. The landlocked nature of CAR, its limited road networks, limited presence of wholesale suppliers in CAR and Cameroon along with insecurity affecting transportation costs are all significant cost drivers connected to procurement. The low human resource capacity in CAR requires substantial overseas human resources, also dramatically driving costs up. Finally insecurity is a substantial cost driver, requiring very strong passive security, communication capacity and risk mitigation measures (movements in convoys rather than single vehicles for instance).

Among the implementing partners considered, UNHCR and ICRC were found to have performed adequately in terms of pipeline management in 2014/15. WFP faced pipeline breaks in 2015 but has since endeavoured to strengthen their systems and transition to cash assistance.[52] FAO has also faced difficulties procuring agricultural supplies at the quality and on the scale needed while supporting local markets. Multi-year programming will enable us to ensure procurement begins earlier and is streamlined. The health NGO consortium faced drug supply challenges due to planning, customs and access challenges which it has endeavoured to tackle. The livelihoods NGO consortium also faced pipeline difficulties due to insecurity, but overcame this once security began improving.
[52] DFID (2015), 2014 Project Completion Review; DFID (2015), 2014/16 Annual Review.

DFID applies the standard appeal administrative fee to UNHCR at 7%, WFP at 7%, FAO at 8% and the ICRC at 6%. Administration fees for the CHF is calculated on the basis of actual costs, plus 5% to UNDP for the CHF as managing agent for NGO contracts, bringing the total fee to around 8% for the CHF. DFID will negotiate administrative fees with NGO partners, taking into consideration increased overheads for consortium management.

Approval for an advance funding process for managed grant costs may be preferable for all contributions. DFID guidelines for advance payment would be applied to implementing partner disbursement modalities, and any organisation wishing to claim in advance will be required to provide written justification during the award process and before a contract is signed.

## How will the contract be structured and how will performance be managed through the life of the intervention?

The Africa Humanitarian Unit will follow DFID’s best practice guidance for managing supplier performance as set out in the Smart Rules. Key Performance Indicators are generally spelled out in appeal documents. Where they are not, they will be included in the contract terms of reference and used to measure partners’ performance throughout the grant duration. Quarterly partner meetings to discuss results, value for money and performance will take place in CAR, in addition to ad hoc contacts. Outputs from these discussions will also inform the Annual and Programme Completion Reviews.

WFP, UNHCR, ICRC and the CHF will report twice yearly on their performance. FAO and NGO consortia will provide at a minimum three progress reports per year.
Contracts with implementing partners will to the largest possible extent be signed on a multi-year basis with all partners, spelling out expected allocations and disbursement dates. Where funding availability or administrative constraints preclude multi-year contracts, DFID will seek where possible to agree multi-year targets in writing and/or shift as soon as possible to multi-year contracting. We will work with WFP to see that they plan their operations on a multi-year basis with a strong strategy around cash and prevention of malnutrition. With UNHCR, depending on the availability of contingency funding, we may look into developing a multi-year logframe, placing emphasis on strengthening economic resilience among refugees and the integration of essential services where feasible under state-provided services. New disbursements will be agreed based on performance and findings of Annual Reviews. Funding top-up released through the Contingency Facility will be arranged through contract amendments. DFID will contract an external review in the second year of this programme to review overall programme performance and where required make adjustments in strategy and contracting.

# Financial Case

## Overview of costs

Fair share analysis indicates that our average share of bilateral humanitarian programming against the current assessed levels of humanitarian needs would place our contribution at around 4.0% of the CAR appeal and 3.8% of CAR refugee appeal in Cameroon.[53] Against current appeals, our contribution would cover 6.3% of the ICRC’s budget, 4.5% of the UNHCR refugee appeal and 8.4% of the WFP refugee appeal.
[53] Based on average planned spend (including contingency funding) and 2016 Humanitarian Response Plan and Regional appeal.

DFID’s bilateral spending in 2014/15 and 2015/16 on humanitarian programming has been £25-28m per annum, representing approximately 4.4-5% of the CAR and refugee appeals. Our proposed contribution at an average of £20m per annum or £60m over three years would represent a small decrease in our fair share contribution, whilst need levels have remained fairly similar.

This business case is based on a projection of sustained level of humanitarian needs in protracted crisis areas over the business case period. The proposed investment in recovery support and basic services are not at this stage expected to deliver a substantial improvement in country over these three years, but will contribute to slowing down and we hope stopping the ongoing deterioration in humanitarian indicators including food security.

The approach taken in this business case will include a certain level of spending allocated to Monitoring, Evaluation and Learning elements. The analysis of the business case is that this element will be offset by an improved quality of DFID humanitarian programming and the overall humanitarian response. This component will include technical monitoring support through contracted consultants, technical expertise support through contracted consultants along with expert assistance to UN agencies provided through standby personnel arrangements.

The Contingency Facility is intended to provide capacity for rapid scale up options in the case of significant surge in violence- or disaster-related needs, or exceptionally if the lack of funding from other donors leaves urgent gaps in the provision of support in protracted situations.

This business case (which spans financial years 2016/17 to 2018/19) will be principally funded through DFID’s Africa Regional Department. Elements of preparedness may be funded through ICF in future years. An indicative breakdown by year is provided below.

Table 7 Indicative breakdown of funds

#	Component / Partner	2016/17	2017/18	2018/19	TOTAL (BC budget)
1	CAR				24.75
	Health (NGO consortium)	1.5	3	3	7.5
	Livelihoods (FAO, NGO consortium)	1	1.75	1.75	4.5
	CHF	3.5	2.5	2.5	8.5
	ICRC	1.5	1	1	3.5
	UNHCR (Protection)	0.75	0	0	0.75
2	CAR refugees				10
	UNHCR	1	1	1	3
	WFP	2.5	2.25	2.25	7
3	M&E	0.25	0.5	0.5	1.25
	Sub-total	12	12	12	36
4	Internal Risk Contingency Facility	24			24
	TOTAL	36	12	12	60

## How will funds be disbursed?

The CHURP will have four main elements:

  1. A Memorandum of Understanding (MoU) with the CHF, ICRC, FAO, WFP and UNHCR setting out an annual disbursement, with annexed performance indicators when not provided in the appeal. Performance targets might include progress in key activities such as transfer to cash assistance. We will sign to the largest possible extent multi-year contracts with these partners. Where these partners’ operations are run on a yearly basis, we will inform via correspondence of our intent to sustain funding over 3 years, but will sign successive MoUs lasting one year. We will also work with WFP and UNHCR to ensure their strategy is planned on a multi-year basis with resilience building at its core.

  1. Accountable grants will be signed with NGO consortia. Depending on funding availability, these will be signed on a multi-year basis.

  1. Allocations from the Contingency Facility. These will in principle be made through the partners identified in this business case. Contingency funding will be flexibly allocated over the period 2016-19 and could be frontloaded on the basis of needs.

  1. M&E funding for consultancy support and standby personnel will be managed with the support of CHASE OT. CHASE OT will submit an assurance statement that all amounts claimed have been checked and verified by their finance team and that they are certifying the accuracy of the figures produced. They will also require fund recipients themselves to have certified the accuracy of all figures and that all advance amounts requested were appropriately justified. DFID will review the claims list and, where satisfied that all the necessary assurances had been received, issue a payment to the project account.

## What is the assessment of financial risk and fraud?

Delivering humanitarian assistance in fragile and difficult contexts such as CAR inevitably has a high level of risk associated with it, and DFID is prepared to take on some risk in order to meet the pressing humanitarian needs in these countries.[54] However, DFID has a zero tolerance policy on fraud.
[54] http://www.dfid.gov.uk/About-us/How-we-measure-progress/Resource-accounts/Risk-management/

We reported to ministers on instances of loss and fraud cases in 2014-16 in CAR.[55] In 2014-15, DFID partners reported 5 security incidents where funds or assets provided by DFID were stolen, mainly during violent robberies. DFID has agreed £21,711 in write-off costs for lost funds and assets. In 2014-16, partners reported 3 potential and 6 confirmed fraud cases affecting DFID programmes. Cases include the theft of assets and the diversion of funds intended for income generating activities. DFID requested the reimbursement of £114,590 in humanitarian funding on confirmed fraud cases.
[55] DFID (2016), Information note CAR cost extension; DFID (2015), Central African Republic (CAR): Humanitarian situation and funding submission.

Through engagement with implementing partner organisations’ audit processes, and scrutiny of their financial statements, DFID will ensure all spend under this business case is accounted for and work with implementing partner organisations to strengthen financial oversight. DFID will also ensure adequate fraud mitigation processes are in place including whistle-blowing mechanisms. If fraud is detected we will demand repayment in full. Continued disbursement of funds will be contingent upon adequate financial oversight mechanisms.

The CHF conducts a capacity and risk assessment of NGO partners to ensure that the partners receiving funds have the capacity to implement projects and have basic accountability mechanisms in place. The Advisory Board and the cluster coordinators are aware of the strengths and weaknesses of some of the implementing partners and poor performance along with audit results are taken into account at the time of project selection. One audit is carried out for each project, and the OCHA Humanitarian Funding Unit aims to visit 40% of all projects.

The CHF has also put in place the UN Harmonised Approach to Cash Transfers, which uses standardised UN tools to monitor the level of risk associated with each delivery partner.

The Africa Humanitarian Unit has undertaken due diligence reviews of the ICRC, UNHCR, FAO and WFP in CAR and Cameroon and of the two NGO consortia and found them to be satisfactory, both centrally and in country. Where operating through partners, UNHCR, FAO and WFP will be expected to operate a risk-based control framework that allows for tight controls and oversight on funding to organisations whose internal control systems are assessed to be weaker.

Assistance across CAR is constrained by insecurity and the absence of a DFID office. DFID therefore ensures that partners have solid evaluation and monitoring mechanisms in place but mainly relies on remote monitoring. This constitutes a key reason why DFID will channel part of its funding through the CHF which provides a more adequate monitoring and evaluation framework. We will also continue to organise at a minimum quarterly visits to CAR and CAR refugee programmes to review partners’ processes, progress and performance.

## How will expenditure be monitored, reported, and accounted for?

All implementing partners will be required to report on their expenditure and results achieved biannually at a minimum. The level of detail of information required from implementing partners will be proportionate to the level of funding and standard practices when responding to appeals.

Each CHURP contract with an implementing partner will contain clauses making continued funding contingent on delivery of agreed results or milestones, and adequate financial management mechanisms. Each contract will clearly state that in the case of fraud, resources must be returned to DFID. Results and milestones will be regularly reviewed to allow for adaptation and flexibility.

The CHF produces a detailed Annual Report with a comprehensive financial statement and a breakdown of results achieved every year, as well as a great deal of other management information. The CHF currently monitor 40% of their projects annually. DFID will seek to increase its engagement with the CHF through donor coordination meetings despite a lack of DFID presence in CAR.

DFID will complement partner monitoring with quarterly progress reviews with partners in country, the deployment of a CHASE OT humanitarian adviser in Cameroon and in London, and close scrutiny of partners’ finance reports and budgets. DFID will also contract an external review in 2017/18 to assess programme performance and adjust the programme accordingly.

# Management Case

CHURP Management arrangements

The CHURP will be implemented by the CAR team within the Africa Humanitarian Unit, under the responsibility of the AHU team leader, who will function as SRO. The release of Contingency Facility funding will be approved by Ministers above £5 million and at SRO/Head of Department level with an information note provided to ministers up to £5 million.

The CAR team includes a lead CAR adviser who leads on humanitarian and recovery files and cross-Whitehall engagement (A2), 50% of a CAR refugee humanitarian adviser based in Yaoundé, 25% of a programme manager and 50% of a Deputy programme manager (B1).

This team will include two consultants, one at 50% based in Yaoundé, the other in London, whose expertise will be called in to support M&E and response coordination.

DFID will monitor partners’ reports and conduct quarterly programme review in the field in CAR and Cameroon. In addition, DFID will conduct yearly Annual programme Review and a Programme Completion Review at the end of this project. DFID will receive external support through an externally contracted programme performance review, due for implementation in the second year of the programme.

## CHF

The Humanitarian Coordinator appointed by OCHA oversees the CHF. The CHF has an Advisory board, which validates its strategic decisions. It relies on proposals made at cluster level, which are vetted by the clusters and inter-cluster with technical advice of CHF staff on the selection process. Funds flow through UNDP to implementing partners. UNDP also has a supervisory role and in the CAR CHF Concept Note, UNDP is referred to not only as the Administrative Agent, but the Managing Agent.

The CAR advisory board meets at a minimum twice per year and acts as an additional quality control mechanism. The board reviews the submissions and makes recommendations as to their appropriateness. Whilst NGO representatives are members of the board, the head of the ECHO office is an observer. His presence is key as he has no vested interests in the CHF allocations, but has extensive knowledge of the agencies and the needs. Since December 2015, the CHF has coopted DFID and the Swiss cooperation as additional board members. In addition, DFID maintained bilateral contacts with the CHF throughout 2014 and 2015 to monitor performance and systems.

Fraud is reported by the CHF to the CAR CHF Advisory Board. In 2015 a decision was made that all projects would be audited given the high level of risk. In 2014 projects were audited based on size. The 2014 UNDP audit recommended moving towards a spot-check approach. The OCHA team monitors 40% of all projects in the field.

In 2014/15, OCHA began rolling out in CAR the Global guidelines on common and humanitarian pooled funding. OCHA and UNDP started developing a risk management framework, through which the reporting, financial and administrative performance of partners is recorded and rated, along with results of audits. This Partner Performance Index began to inform project selection in 2015.

## NGO consortia

The two NGO consortia will have a consortium coordinator who will oversee programme implementation, progress, reporting and financial management. Consortium coordinators will also conduct regular field monitoring visits to assess partners’ performance, along with light-touch compliance reviews.

## What are the risks and how will these be managed?

The overall risk level of this programme is High. CAR is a very challenging environment for partners to operate in. DFID has a tolerance to risk, but no tolerance to fraud. This aspect is therefore spelled out in all new funding grants.

Risk	Probability	Impact	Mitigating Actions
Conflict hinders access and delivery and leads to surge in needs	High – CAR is still characterised by relative lawlessness and witnesses localised surge in needs and frequent access challenges.	High	DFID liaises with FCO on MINUSCA performance and monitors other relevant security bodies (UNDSS, INSO, HCT). / DFID is flexible around need to revise/adapt programmes. The CHF implement programmes with flexibility. / Partners are selected on the basis of scale-up capacity, experience and contingency to rapidly respond to uprising needs. / Contingency Facility to provide rapid funding to address surge in needs.
Insecurity/criminality	High	Medium to High	Due diligence partner review ensures they have suitable security management processes. / DFID checks that partners have contingency plans in place. / DFID ensures that partners conduct do no harm analysis to keep beneficiaries safe.
Lack of gender sensitivity/conflict sensitivity/Do no harm analysis among partners	Medium	High	DFID ensures that all partners have adequate gender and conflict sensitivity assessment tools. / DFID work with partners to ensure that monitoring, evaluation and accountability mechanisms are all gender and conflict sensitive, and that reporting disaggregates data. / DFID ensure that relevant programmes in health livelihoods and gender and conflict sensitive. / DFID ensures that partners implement projects transparently in accordance with humanitarian principles. / DFID advocates with CHF and the HCT for adequate partner capacity building on do-no-harm.
Underfunding of the refugee response heightens local tensions and criminality	High	Medium	In Cameroon, DFID to closely coordinate with the EU and US to ensure assistance remains commensurate to the needs. / In Chad, CAR refugees are being integrated under DFID’s PHASE programme. In the DRC, DFID’s system-wide assistance to the CHF directly supports the humanitarian community to address gaps. / DFID to ensure that refugee programmes have a solid built-in do-no-harm component and address social tensions. / DFID to ensure refugee assistance include livelihoods assistance that progressively helps rebuild refugees’ self-sufficiency. / DFID to ensure resource availability for contingency reserve allocations.
Fraud	High	Medium	DFID due diligence review ensures that partners have adequate processes to mitigate and manage fraud risks. / DFID monitors compliance mechanisms in particular frequency of compliance checks, audits and M&E. / DFID to report all fraud and losses cases to DFID counter-fraud units.
Procurement and transportation challenges	High	Medium to high	DFID ensures partners have solid procurement planning and procurement processes in place – including surge support where necessary. / DFID monitors security on main supply roads and advocates with MINUSCA via FCO when necessary. / DFID to show flexibility on transportation and storage costs.
Partner capacity	High	Medium	DFID due diligence to review capacity to deliver including staffing and technical capacity. / DFID to incorporate lessons learnt from Annual Reviews, Project Completion Reviews and quarterly monitoring into programming. / DFID to show flexibility around staffing and training costs. / DFID establishes with partner action plans to address poor performance. DFID to work with the CHF to ensure similar partner performance monitoring processes remains in place and operational.
Constraints placed on humanitarian space by CAR authorities	Medium to low	Low	DFID to advocate through HCT, FCO, EU, UN.
Weak humanitarian coordination and strategy	Medium	Medium	DFID to advocate with OCHA (at country, regional and central level), CHF, HC, UNHCR and with relevant agencies. / DFID to support funding mechanisms that empower humanitarian coordination (CHF). / DFID to maintain contacts with key donors, including ECHO, OFDA/PRM, CHF, AFD, SIDA.
Poor linkage between relief and development	Medium	Medium	DFID to coordinate closely with development donors and international financial institutions.
Insufficient management capacity within DFID affects capacity to influence	Medium	Low	DFID to resort to surge capacity when necessary (through CHASE OT). / DFID to increase frequency of visits to CAR and engagement level. / DFID to plan programmes/partnerships with attention to management capacity.
Unintended negative impact of DFID aid	Low	Medium	DFID to ensure that partners have adequate conflict and gender sensitivity mechanisms. / DFID to ensure that partners have adequate risk management systems in place. / DFID to ensure that partners have adequate monitoring, evaluation and accountability mechanisms in place.

## How will progress and results be monitored, measured and evaluated?

We have adopted tentative indicators (see Annex 1) relying on DFID’s 2015 logframe indicators. A full logframe will be produced after signature of all grant agreements.

The results of the programme will be monitored through narrative and financial reports provided by partners, along with quarterly visits to CAR, the deployment of CHASE OT humanitarian advisers, and other regular partner meetings. All partners will be expected to report against their logframe or targets set in their appeal. Security in the field precludes a level of monitoring that is fully satisfactory, which contributed to programming being channelled through trusted multilateral partners and NGO consortia. DFID will closely monitor partners’ due process and in particular monitoring and evaluation mechanisms to ensure they are adequate.

The CHURP will be monitored and evaluated at 2 levels. At DFID programme level, the CHURP will be reviewed regularly against a programme level logframe through quarterly review meetings, annual reviews and a Programme Completion Review at the end of the project. The overall performance of the programme will also be assessed through an externally contracted mid-term review.

At partner level, DFID will review partners’ monitoring, evaluation and audit schedules and processes and ensure they are fit for purpose.

## Exit Strategy

We do not foresee at this stage a decrease in humanitarian needs, but hope that this intervention will contribute to stopping the current trend towards increasing needs. DFID will rely on its Annual Reviews to assess opportunities to gradually phase-out assistance or whether to maintain funding beyond this Business Case.
# Annex 1 – Results Framework

Targets indicated below are indicative only and based on DFID’s 2014/16 Business case. A complete logframe will be prepared based on partners’ appeals and results and updated on a yearly basis.

Impact	Reduced suffering and improved resilience among CAR populations and refugees	No. of individuals who are reached with DFID humanitarian assistance in CAR and among CAR refugees
		Crude mortality rate in prefectures of intervention does not increase.
Outcomes	Outcome 1 - Improved approaches to supporting simultaneous delivery of relief and early recovery assistance	No. of individuals reached yearly with DFID humanitarian assistance in CAR. (Cumulative)
	Outcome 2 - Better accountability, coordination and coherence of the humanitarian, development and UN system in CAR
	Outcome 3 - Address essential humanitarian needs among CAR refugees	Outcome 2 / No. of CAR refugees reached yearly with DFID humanitarian assistance.
Output 1.1.	The agro-pastoral production in the targeted areas is improved and reinforced	No. of people are reached through livelihood assistance
		60% of project beneficiaries are not induced to resort to negative mechanisms at least for six months after the end of the project.
Output 1.2.	Affected population have improved access to healthcare	No. of people who have access to essential healthcare.
		At least 80% of consultations are provided in accordance with national standards.
Output 1.3.	DFID helps reinforce social cohesion and support local reconciliation	Number of beneficiaries who benefit of social cohesion initiatives
		Number of beneficiaries encompassed by protection monitoring.
		Number of SGBV survivors who access remedial services.
Output 2.1.	DFID empowers humanitarian coordination for rapid and effective decision-making	85% of overall funding received from all donors by 30 June is allocated before 31 December.
		At least 40% of projects monitored through field visits within their project duration
Output 2.2.	Where rapid mechanisms (CHF, RRM, CERF) are unable to respond, DFID provides rapid response to spikes in needs for CAR populations and IDPs.	DFID to provide note to ministers within 4 weeks of any new displacement of 100,000 or above, identifying recommended measures.
Output 3.1.	Central African refugees access basic food assistance in Cameroon.	No. of people who have access to 3 months of complete food rations (or equivalent in cash).
		At least 10% of assistance is provided through cash assistance by 31 March 2017 and 30% by 31 March 2019.
Output 3.2.	Central African refugees see their basic needs met	No. of people with access to 15l of water /person/day by 31 March 2017 and by 31 March 2019.
		No. of CAR refugees in Cameroon who have access to adequate shelter by 31 March 2017 and by 31 March 2019.
		No. of refugees have benefited of livelihood intervention by March 2017, 2018 and 2019.
		Proportion of livelihood project beneficiaries who are not induced to resort to negative mechanisms at least for six months after the project.