Department for International Development

Nigeria

Scale Up of the State Partnership for Accountability, Responsiveness and Capability (SPARC) Programme

Business Case

        September 2012

Contents	Page number
Intervention Summary	5-7
Strategic Case	7-12
Need and context for DFID intervention	7-11
Impact and Outcome that we expect to achieve	11-12
Appraisal Case	12-25
What are the feasible options that address the need to set out in the Strategic case?	12-14
Theory of change and evidence base / Assessing the strength of the evidence base for each feasible option	14-21 / 22-23
What are the costs and benefits of each feasible option?	23
What measures can be used to assess Value for Money for the intervention?	23
Summary Value for Money Statement for the preferred option	23-25
Commercial Case – Direct Procurement	25-27
Clearly State the procurement/commercial requirements for intervention	25
How does the intervention design use competition to drive commercial advantage for DFID?	25
How do we expect the market place will respond to this opportunity?	25-26
What are the key underlying cost drivers? How is value added and how will we measure and improve this?	26
What is the intended Procurement Process to support contract award?	26
How will contract & supplier performance be managed through the life of the intervention?	27
Financial Case	27-30
What are the costs, how are they profiled and how will you ensure accurate forecasting?	27-29
How will it be funded?	29
How will funds be paid out?	29
What is the assessment of financial risk and fraud? / How will expenditure be monitored, reported, and accounted for?	29 / 29-30
Management Case	30-34
What are the Management Arrangements for implementing the intervention?	30
What are the risks and how will these be managed?	30-32
What conditions apply?	32
How will progress and results be monitored, measured and evaluated? / References	32-34 / 35-36
Annex / SPARC Logframe / SPARC Scale-up summary / SPARC Results Leaflet / SPARC Economic Appraisal / IMEP TOR / IMEP Logframe

Glossary

CBA	Cost Benefit Analysis
CBO	Community Based Organisation
CSO	Civil Society Organisations
DSA	Daily Subsistence Allowance
DFID	Department for International Development
DDIN	Deepening Democracy in Nigeria Programme
ENABLE	Enhancing Nigerian Advocacy for a better Business Environment Programme
ESSPIN	Education Sector Support Programme
EU	European Union
FGN	Federal Government of Nigeria
GDP	Gross Domestic Product
GEMS	Growth and Employment in States Programme
GoN	Government of Nigeria
HMG	Her Majesty’s Government (UK)
HRM	Human Resource Management
IMEP	Independent Monitoring and Evaluation Programme
IRR	Internal Rate of Return
J4A	Justice for All Programme
LGA	Local Government Area
MDAs	Ministries, Departments and Agencies
MDGs	Millennium Development Goals
MDGs CGS	Millennium Development Goals Conditional Grant Scheme
M&E	Monitoring and Evaluation
MNCH	Maternal, New-born, Child Health Programme
MTSS	Medium-Term Sector Strategy
M4M	Mobilising for MDGs Programme
NGF	Nigeria Governors Forum
NGO	Non-Governmental Organisation
NPV	Net Present Value
NSRP	Nigeria Stability and Reconciliation Programme
OECD	Organization for Economic Cooperation and Development
PATHS2	Partnership for Transforming Health Systems Phase 2 Programme
PDG & STL	Programme Development Group & State Team Leaders (SPARC)
PEFA	Public Expenditure and Financial Accountability
PRRINN	Partnership for Improving Routine Immunisation in Northern Nigeria Programme
SAC	State Advisory Committee
SAVI	State Accountability and Voice Initiative Programme
SG	State Government
SLPs	State Level Programmes (UK)
SP	Service Provider
SPARC	State Partnership for Accountability, Responsiveness and Capability Programme
SRP	Structural Reform Plan (DFID)
SPRM	State Peer Review Mechanism
SSR	Security Sector Reform
SUNMAP	Support to Nigeria Malaria Programme
TA	Technical Assistance
ToC	Theory of Change
USAID	United States Agency for International Development
VfM	Value for Money
## Intervention Summary
## Title: Scale Up of the State Partnership for Accountability, Responsiveness and Capability (SPARC) programme

What support will the UK provide?
State Partnership for Accountability, Responsiveness and Capability (SPARC) programme / How much funding does the UK expect to provide? / The UK will provide an additional £14.5 million to the State Partnership for Accountability, Responsiveness and Capability (SPARC) programme in Nigeria. This raises the total funding provided to SPARC to £60.4m. SPARC was originally approved by Ministers in 2007, as part of the joint approval of a suite of State Level Programmes (SLPs) for Nigeria’s Federal system of governance. SPARC will continue to focus on its core objectives of improving state planning, financial management and civil service performance in selected state governments. SPARC will scale up from the current five to a total of ten focus states. / Period of funding / Four years (2012-2015). This represents an extension of one year for the programme that has been operational since 2008. / Independent Monitoring and Evaluation Programme (IMEP) / This business case also requests an additional £2m to increase the scope of the Independent Monitoring and Evaluation Programme (IMEP), which provides independent monitoring and evaluation to all five State Level Programmes (SLPs) in Nigeria, including SPARC. IMEP was originally approved as a sub-component of the original SLP package. The request for additional funds for IMEP is included in this business case since IMEP does not have a separate approval document. The additional funding to IMEP is contracted separately to that of SPARC funding, and will increase the overall budget available for IMEP from £7.3m to £9.3m. This increase is needed to cover overall SLP expansion, to improve the quality of a key survey for the SLPs, and to allow more rigorous monitoring and evaluation of all SLPs.

Why is UK support required?
What need are we trying to address? / Of Nigeria’s 158 million people, 64% live in poverty. The poverty rate is 77% in northern Nigeria. Despite its oil revenues, Nigeria’s human development indicators are worse than in comparable lower middle-income countries.[1] Nigeria’s poverty and underdevelopment are widely attributed to poor governance. Although limited public resources is an issue in Nigeria particularly in northern states, the ineffective use of resources is the biggest impediment to sustained improvement in public services, and ultimately making progress towards Millennium Development Goals (MDGs). Nigeria is rated in the bottom 25th percentile globally on indicators of government effectiveness and control of corruption (lower than the Sub-Saharan average). Key challenges stem from the combination of patronage politics and weak systems. Poor governance and the unequal distribution of oil revenues are key underlying reasons for the significant levels of instability and violent conflict that Nigeria is currently experiencing, particularly in the North of the country.[2] / With a Federal system, effective public management at state level is essential for improved service delivery and poverty reduction in Nigeria. State and local government spending comprises around 50% of total government spending. Local and state level agencies are responsible for delivery of core public services such as basic healthcare and primary education. Unfortunately, however, state government is often ineffective. The situation in many states in Nigeria is characterised by low institutional capacities, including weak planning systems, poor budgeting and cash management, very poor human resource management, extensive corruption in procurement and very weak audit. The states are also subject to limited oversight or accountability – by the Federal Government, State Houses of Assembly, civil society or the media. / What will we do to tackle this problem? / Set up in 2008, the State Partnership for Accountability, Responsiveness and Capability (SPARC) Programme was designed to work with Nigerian state governments to tackle these problems by delivering improved a) policies and strategies; b) public financial management; c) state civil service performance, and d) Federal support to state governance. SPARC works currently in five focus states in a full-scale way (Kaduna, Kano, Lagos, Jigawa and Enugu). Nigeria has a total of 36 states. It was envisaged that the programme would expand and an inception phase has also been conducted since 2011 in the states of Katsina, Yobe and Zamfara. / The overarching logic of SPARC is that strengthening state government institutions will improve state governments’ ability to use their resources more effectively. We already have good evidence that SPARC has been able to make progress on improving the effectiveness of the use of resources. Together with other DFID interventions, SPARC will also contribute to improving public service delivery outcomes. / This reflects the broader research evidence base on the link between stronger institutions, in particular with good budget management, and improvements in service delivery outcomes. The extent of government effectiveness is a crucial determinant of the degree to which a country makes social and economic progress – or fails to do so. / The research evidence and Nigerian experience also point to the close interdependence of governance programmes and sector interventions in areas such as health and education in achieving improvements in developmental outcomes. SPARC was hence designed as one of a suite of State Level Programmes (SLPs) to leverage improved pro-poor service delivery. The other related programmes are: (i) State Voice and Accountability (SAVI); (ii) Education Sector Support Programme in Nigeria (ESSPIN); (iii) Partnership for Transforming Health Systems Phase 2; and, (iv) Growth and Employment in States. The overall collective goal is to increase the efficiency and effectiveness of utilisation of Nigeria’s resources to achieve the MDGs. / The rationale for scale-up is based on: / The main thrust of DFID Nigeria’s Operational Plan, approved by Ministers in 2011, to scale up DFID work in Northern Nigeria where poverty rates are the highest. Seven of the 10 proposed focus states (and four of the additional five) are in the North. / To date SPARC has been very successful in delivering important governance reforms with good value for Monday. In the mid-term review in 2012 SPARC achieved an A+. On one component alone, it has helped states to save £68m. / The pivotal position of SPARC in helping accentuate reforms in other DFID sectoral programmes in health and education in northern Nigeria. / There are also opportunities to expanding SPARC federal level work (through the Nigeria Governors Forum and MDG office) to help replicate lessons and lever broader impact across the country. / Extending the programme for an additional year to 2015 will enable reforms to be more fully embedded, particularly in the additional states. / The SPARC scale-up will involve: / Scaling up (roughly double) the intensity of governance support in two of the existing states where reform traction has proven greatest – Lagos and Jigawa. / Providing full governance support in Katsina, Yobe and Zamfara, following successful inception work. / Starting the programme in two new states, Anambra and Niger, that have more reformist governments. / The expanded SPARC will be operating in a total of 10 states (of which seven are in the North). / Extending the programme lifetime by an additional year (to 2015) in all states. / Scaling up (roughly double) the intensity of governance reform support to national level institutions within the Federal Government, particularly the Nigerian Governors Forum (NGF) and the Millennium Development Goals Office. / Expanding knowledge management initiatives to further promote reform across the country. / Who will be implementing the support we provide? / Implementation of SPARC is contracted out to a consortium of service providers led by HTSPE International Programme Management.
[1] UNDP (2011) Human Development Index 2011. http://hdrstats.undp.org/en/countries/profiles/NGA.html
[2] Aigbokhan, Ben. E (2008) Growth, Inequality and Poverty in Nigeria, Prepared for the United Nations Economic Commission for Africa (UNECA), Addis Ababa, Ethiopia.

What are the expected results?
The impact of the intervention is expected to be Nigeria’s own resources used efficiently and effectively to achieve the Millennium Development Goals (MDGs). The programmes outcome is the efficiency and effectiveness of selected state governments’ use of public resources is enhanced. / With additional funding and a 1 year extension SPARC will achieve the following additional outputs: / Output 1: Policy and strategy and monitoring and evaluation strengthened in an additional five states / Output 2: Public financial management improved in an additional five states. / Output 3: Civil service performance improved in five additional states. / Output 4: Strengthened Federal support to improve state governance. / How will we determine whether the expected results have been achieved? / SPARC’s performance will be assessed by internal monitoring of the programme and by an annual external monitoring by the Independent Monitoring and Evaluation Programme (IMEP). IMEP will also conduct an independent evaluation at the end of the programme.

State Partnership for Accountability, Responsiveness and Capability (SPARC)

Strategic Case
Context and need for a DFID intervention / Why is DFID intervention needed? / Of Nigeria’s 158 million people, 64 per cent live in poverty. In the North, the figure is 77 per cent. Despite its oil revenues, Nigeria’s human development indicators are worse than in comparable lower middle-income countries.[3] 42 per cent of children are malnourished. Nigeria still has one of the worst maternal mortality rates in the world (2nd highest in the world in 2008).[4] Just four per cent of girls complete secondary school in the north of the country.[5] / Nigeria’s poverty and underdevelopment are widely attributed to poor governance. The misuse of resources is one of the biggest impediments to sustained improvement in public services in Nigeria, and ultimately making progress towards MDGs.[6] According to the World Wide Governance Indicators, Nigeria is rated in the bottom 25th percentile globally on indicators of government effectiveness and control of corruption (and lower than the Sub-Saharan average). According to Transparency International Perception survey for 2010, Nigeria scored 2.4 out of 10 and was ranked 134 out of 138 countries for corruption.[7] Nigeria’s Open Budget Index score for 2010 is 18 out of 100, which is less than half the average score (42) for the 94 countries surveyed.[8] / Key challenges in governance stem from the combination of patronage politics and weak systems. Systems, including formal organisations, are weak in capacity and in their ability to manage and use resources effectively. The structurally-entrenched patronage-driven mechanisms mean that changes which are likely to improve the use of public resources to deliver pro-poor public goods are not likely to be popular amongst the people who hold positions of power and enjoy privileged access to state resources. The elite do have incentives for reform, in particular in improving Nigeria’s international standing (at federal level) and competition to demonstrate positive change (states). However, these incentives tend to be weaker than the incentives to preserve elite power and resource control, and this explains why change is difficult to achieve.[9] Poor governance and the inequality that results from the unequal distribution of oil revenues are key underlying reasons for the significant levels of instability and violent conflict that Nigeria is currently experiencing, particularly in the North of the country.[10] / With Nigeria’s Federal system, effective public management at State level is essential for service delivery and poverty reduction. State and local government spending comprises around 50% of total government spending, and they are responsible for delivery of core public services such as basic healthcare and primary education.[11] However, at the same time, the states are subject to limited oversight or accountability by the Federal Government. The State Houses of Assembly, the civil society or media have also been relatively weak in overseeing the work of the executive. / Unfortunately, State government is also often ineffective. Although some progress is being made, the situation in many states in Nigeria is characterised by low institutional capacities and systems in all key areas of public sector management, including weak planning, poor budgeting and cash management, very poor human resource management, extensive corruption in procurement, and very weak audit. In particular, recent diagnostic work on public financial management has revealed a number of common challenges that States face in Nigeria in managing their public finance relating to weaknesses in procurement procedures, lack of fiscal discipline and high fiduciary risk.[12] Nevertheless, Nigeria is a large country with widely varying histories and structures between places. The local details in terms of capacity vary widely from a state to state, as do the conditions for change. / How is SPARC addressing this challenge and how does this reflect the evidence? / Set up in 2008, the State Partnership for Accountability, Responsiveness and Capability (SPARC) programme was designed to work with Nigerian state governments to tackle these problems by delivering improved a) policies and strategies; b) public financial management; c) state civil service performance, and d) Federal support to state governance. SPARC works currently in five focus states in a full-scale way (Kaduna, Kano, Lagos, Jigawa and Enugu). It was envisaged that the programme would expand and an inception phase has also been conducted since 2011 in the states of Katsina, Yobe and Zamfara. / The overarching logic of SPARC is that strengthening state government institutions is expected to improve state governments’ ability to use their resources effectively. Further, together with other DFID interventions, SPARC is also expected to contribute to improving public service delivery outcomes. We already have evidence that SPARC has been able to make progress on improving the effectiveness of the use of resources by improving the public financial management and administration systems. There is also a growing academic research evidence base on the link between stronger institutions, in particular with good budget management, and improvements in service delivery outcomes.[13] / Public management is seen as a crucial determinant of the degree to which a country makes social and economic progress – or fails to do so. This set of issues has been of concern since the advent of centralized administration, but they have taken on particular significance to academics and practitioners alike since the work of Max Weber some hundred years ago.[14] In recent years, there has been increasing evidence, from case studies and cross-country empirical analysis, that bureaucratic performance is important for development performance.[15] / However, the evidence also suggests that success on public sector management reforms is in general dependent on rules that determine procedures in the bureaucracy, whether formal or informal, including political will and incentives for reform.[16] This consideration has therefore been integrated as a critical element in the SPARC theory of change. / Finally, the evidence points to the close interdependence of governance programmes and sector interventions in improving pro-poor service delivery outcomes. SPARC was designed as one of a suite of State Level Programmes (SLPs) to leverage improved governance for better service delivery. The overall collective goal of the SLPs is to increase the efficiency and effectiveness of utilisation of Nigeria’s resources to achieve the MDGs, which they all aim to achieve together. The other related programmes are: (i) State Voice and Accountability (SAVI); (ii) Education Sector Support Programme in Nigeria (ESSPIN); (iii) Partnership for Transforming Health Systems Phase 2 (PATHS2); and, (iv) Growth and Employment in States (GEMS). SPARC also increasingly works with other related DFID programmes at state level. / Why Scale-up SPARC? / The rationale for scale-up is based on: / The main thrust of DFID Nigeria’s Operational Plan, approved by Ministers in 2011, is to scale up DFID work in Northern Nigeria where poverty rates are the highest. Seven of the 10 proposed focus states (and four of the new five) are in the North. / To date SPARC has been very successful in delivering important governance reforms with good value for Money. In the mid-term review in 2012 SPARC achieved an A+. On one component alone, it has helped states to save £68m from a total SPARC spend of £29m so far. / The pivotal position of SPARC in helping accentuate reforms in other DFID sectoral programmes in health and education in Northern Nigeria. / There are also opportunities to expanding SPARC federal level work (through the Nigeria Governors Forum and MDG office) to help replicate lessons and lever broader impact. / Extending the programme for an additional year to 2015 will enable reforms to be locked in, particularly in the new states. / The SPARC scale-up will involve: / Scaling up (roughly double) the intensity of governance support in two of the existing states where reform traction has proven greater – Lagos and Jigawa. / Providing governance support in Katsina, Yobe and Zamfara, following successful inception work. / Starting the programme in two new states, Anambra and Niger, that have reformist governments. / The expanded SPARC will be operating in a total of 10 states, and at national level. / Extending the programme lifetime by an additional year (to 2015). / Scaling up (roughly double) the intensity of governance reform support to Federal level institutions within Federal Government that affect state governance: the Nigerian Governors Forum (NGF) and the Millennium Development Goal Conditional Grant Scheme which directly impact on all 36 states in the Federation. / Expanding knowledge management initiatives to further promote governance reform across the entire Federal Republic. / A scale-up by SPARC to additional states has the scope to achieve further results and address key governance challenges that also impact other DFID programmes. For example, in Northern Nigeria, the binding constraint of weak governance remains daunting. Unless the central government releases funds for essential drugs or posts health workers to areas where they are needed, there is only so far that a sector programme can go. DFID’s Programme for Reviving Routine Immunisation in Northern Nigeria/ Maternal, New-born, Child Health programme (PRRINN/MNCH) which operates in Zamfara, Katsina and Yobe (proposed SPARC additional states) is facing these same governance constraints. SPARC is in a position to support governance improvements in those states, so that the operational environment for PRRINN/MNCH can be made more conducive. SPARC has carried out detailed technical assessments of all three states and concluded that there are some opportunities to work on improving governance systems. / Without additional funding, SPARC would continue existing operations, but there would not be a scale-up to 10 states. This would adversely affect DFID Nigeria Operational Plan commitments to support Northern Nigeria. Four out of five SPARC’s additional states are in the North. This would also mean that planned synergies with the other DFID programmes in new states would be lost. For example, SAVI and the Justice for All programme (J4A) are expanding in the same states as SPARC. Lack of additional funding could also mean that SPARC is not only able to work on removing the governance blockages faced by other DFID programmes in the North, but it also unable to take advantage of the seemingly-fertile reform environments in Niger and Anambra (also proposed additional states). Finally, without additional funding, a deeper reform impact would also be missed in the existing SPARC states and at federal level where there already appears to be appreciable programme impact. / How does the proposed scale-up fit with the Nigerian Government and DFID Strategic priorities? / The programme is in line with the Nigerian Government’s Seven Point Transformation Agenda and Vision 2020, which emphasizes key governance areas as priorities. / The programme is in line with the joint Country Partnership Strategy FY 2010 -13 for Nigeria (with USAID, the World Bank and African Development Bank) which identifies improving governance as a core and cross-cutting theme. / The proposed activities will assist in achieving the results outlined in the DFID Nigeria Operational Plan 2011-2015, particularly scale-up plans for the North. There are strong links with other DFID programmes and it will be complementary to the activities undertaken by them. (See Table 1). / Table 1: Related DFID Programmes / Federal Public Administration Reform (FEPAR): Commenced in 2011 and builds on the work of the Public Service Reform (PSR) Programme to support improved government effectiveness and financial management at the Federal level. / States Voice and Accountability Initiative (SAVI). Works with Civil Society and State Houses of Assembly to improve State level advocacy and budget transparency. / Partnership to Transform health Systems (PATHS 2): This health system strengthening programme improves the planning, financing and delivery of sustainable pro-poor services for common health problems. Work of PATHS 2 includes health financing and budgeting, sustainable drug supplies and primary health care services and improving voice and accountability to help citizens to make informed choices. / Education Support Programme in Nigeria (ESSPIN): The six-year programme (2008 – 2014) supports federal and state governments – Enugu, Jigawa, Kaduna, Kano, Kwara and Lagos – to develop effective planning, financing and delivery systems that will improve the quality of basic education. / Growth and Employment in States (GEMS): A joint programme with the World Bank started in 2010 to support state and national level business environment reform, including work on land and tax administration and investment promotion. A major part of the programme will seek to raise growth and employment in 6 industry clusters. / Partnership for Reviving Routine Immunisation in Northern Nigeria – Maternal, New-born and Child Health for Reviving Routine Immunisation in Northern Nigeria (PRRINN/MNCH): Approved in 2006 to work at state level to improve maternal and child health; improved immunisation coverage; stronger health systems; and engaged communities.
Impact and Outcome that we expect to achieve / The impact of the intervention is expected to be Nigeria’s own resources used efficiently and effectively to achieve the MDGs. The programmes outcome is the efficiency and effectiveness of selected state level governments’ use of public resources is enhanced. / With a 1 year extension and additional funding SPARC will achieve the following outputs: / Output 1: Policy and strategy and monitoring and evaluation strengthened in additional 5 states as evidenced by: i) sector plans or medium-term sector strategies (MTSS) approved by State Government (SG) in at least the health sector and reflected in the 2015-2017 budget; ii) State development Plans conform to relevant standards and all MTSS’s are aligned with State Development Plan (SDP). / Output 2: Public financial management improved in 5 additional states as evidenced by: i) a less than +/- 20% variance between actual and approved budgets and actual releases and a Budget policy Statement has been prepared; ii) a basic cash forecasting model is being operated for Treasury and annual budgets for Health sector Ministries, Departments and Agencies (MDAs) are being profiled. / Output 3: Civil service performance improved in 5 additional states through i) state government has begun implementing a Human Resource Management (HRM) improvement plan and workforce plan in at least the health sector and ii) service charters are being adopted in an increased number of sector MDAs. / Output 4: Performance at Federal state government strengthened through deepening of supported reforms to strengthen the state peer review mechanism (SPRM), including in SPRM in operation in all 36 states and interstate lesson learning and replication of reforms supported through enhanced knowledge management systems and products. / The new logframe can be found at Annex 1. / Additional results by states are expected to be as follows: / Existing States (Lagos, Jigawa, Kaduna, Kano, and Enugu ) / There will be a deepening of supported reforms as a result of: a) maintaining programme budgets at higher than originally planned levels, and b) an additional years inputs. As a consequence, in at least three of all existing states, the following 2015 results will be delivered (compared to previously defined 2014 targets): / Development Plans and current medium-term sector strategies (MTSS) better meet relevant standards, alongside improved standards for policy and strategy development processes. / Annual budget process and documentation better meet PEFA standards alongside greater consistency between State Development Plan goals and 2015-2017 budgets. / Service Charters being adopted in an increased number of sector MDAs. / Increased and more sustainable capacity developed within State Governments to support sector MDAs implementation improved: a) policies, strategies and related M&E arrangements, b) budgeting and accounting processes and c) corporate planning and HRM processes. / New States (Katsina, Yobe, Zamfara, Anambra, Niger) / In at least two new states the following overall and specific results will be delivered, deepened by an additional years inputs: / Greater awareness of the importance of, and appetite for, governance reforms within State Government (SG). / Readiness of State Government for designing and implementing governance reform interventions. / Sector Plan or MTSS is approved by State Government in at least the Health sector and is reflected in the 2015-2017 budget. / There is less than ±20% variance between approved budgets and actual releases and a Budget Policy Statement has been prepared. / A basic cash forecasting model is being operated by the Treasury and annual budgets for Health sector MDAs are being profiled. / Corporate improvement plans have been implemented in the central planning MDAs and at least one sector MDA. / State Government has begun implementing a HRM improvement plan and workforce plan in at least the Health Sector. / Federal Component / Within the Federal Component, as a result of an additional years inputs, there will be a deepening and scale up of supported reforms in order to deliver the following 2015 results (compared to previously defined 2014 targets): / Strengthened State Peer Review Mechanism approach; / State Peer Reviews done or under way in all 36 states. / Strengthened MDG Conditional Grant Scheme processes in response to lessons learned; / Strengthened Nigeria Governors Forum (NGF) Knowledge Management processes. / Increased effectiveness of NGF human resource, knowledge management and communications systems and mechanisms for partnership development. / Inter-state lesson learning and replication of reforms supported though enhanced knowledge management systems and products. / Overall, delivery of governance reforms in an additional 5 states means that SPARC will be directly supporting 10 states which consist of 37% of the population (compared to the original 7 planned SPARC states, which consisted of 23% of the population). Indirectly through the Federal Component, SPARC will impact all 36 states. / How will we determine whether the expected results have been achieved? / SPARC’s performance will be assessed by internal monitoring of the programme. An independent service provider, the Independent Monitoring and Evaluation Programme (IMEP), will also monitor SPARC through annual and mid-term reviews and will provide an independent evaluation at the end of the programme.
[3] UNDP (2011) Human Development Index 2011. http://hdrstats.undp.org/en/countries/profiles/NGA.html
[4] Daily Independent, Lagos (2010), Nigeria: Reducing The Country's High Maternal Mortality Rate, http://allafrica.com/stories/201003110261.html, March 10, 2010
[5] All figures are from British Council (May 2012) The Gender in Nigeria Report 2012.
[6] The fundamental constraints to Nigeria’s ability to sustain change generally, and to meet the MDGs in particular have become so embedded that they have assumed structural characteristics: mismanagement of oil revenue; weak formal accountability; and the absence of non-oil sector economic growth in Heymans and Pycroft (2005) Drivers of Change in Nigeria: Towards Restructuring the Political Economy
[7] http://www.transparency.org/policy_research/surveys_indices/cpi/2010
[8] http://internationalbudget.org/what-we-do/open-budget-survey/
[9] Fennell, J (2007) Nigeria: Unity or Democracy – A Conflict Analysis
[10] Aigbokhan, Ben. E (2008) Growth, Inequality and Poverty in Nigeria, Prepared for the United Nations Economic Commission for Africa (UNECA), Addis Ababa, Ethiopia.
[11] IMF (February 2012) Article IV Report, February 2012.
[12] World Bank (2011) Programmatic Integrated Fiduciary Assessment Of Nigeria States (Pifans), State Procurement Assessment Reports (Spar) Of 6 States (Bayelsa, Delta, Edo, Lagos, Ondo And Rivers) Synthesis Report Volume 1, World Bank, PEMFARSs
[13] See for example: World Bank (2003). Making services work for poor people, World Bank Development Report 2003. World Bank, Washington DC & World Bank (2007) Strengthening World Bank Group Engagement on Governance and Anticorruption,World Bank, Washington DC.
[14] Weber, M., The Theory of Social and Economic Organizations. New York: Free Press 1947.
[15] See: D. Kaufmann, A. Kraay, and P. Zoido-Lobaton, “Governance Matters”, Policy Research Working Paper No 2195. Washington D.C.: The World Bank, October 1999; Peter Evans and J. E. Rauch, “Bureaucracy and Growth: A Cross-National Analysis of the Effects of ‘Weberian’ State Structures on Economic Growth” American Sociological Review, Vol. 64, No 5 (October 1999), pp 748-765; and, Peter Evans and J.E. Rauch, “Bureaucratic Structure and Bureaucratic Performance in Less Developed Countries”, Journal of Public Economics, vol. 75 (January 2000), pp. 49-71.
[16] See for example: Earle, L. et al., (2010), Assessing the Evidence of the Impact of Governance on Development Outcomes and Poverty Reduction, Emerging Issues Research Service, GSDRC.

Appraisal Case / A. What are the feasible options that address the need set out in the Strategic case? / The options considered in the appraisal are to continue SPARC operations as currently planned or to scale up and extend SPARC. The option for tendering for a new state level programme was considered but discarded. Our preferred option is to scale up and extend SPARC. / Option 1: Status Quo / The counterfactual is to continue with the status quo. Under this scenario SPARC would continue with the approved resource allocation of £45.9 million and with its activities in existing states. The programme would end in 2014. It is expected that SPARC would achieve the results agreed in the original SPARC programme logframe. / In this scenario, a scale-up of funding and an additional year’s extension would not occur. In particular, there would not be a scale-up up to ten states. This would adversely affect DFID Nigeria Operational Plan commitments to support Northern Nigeria, as four out of five SPARC’s additional states are in the North. / Overall, some of the expected benefits that would be lost are: / Policy and strategy and monitoring and evaluation would not be strengthened in an additional 5 states / Public financial management would not improve in 5 additional states / Civil service performance would not improve in 5 additional states / A deepened level of support would not be occur in existing 5 states / Synergies with other DFID programmes (health, education, governance and growth) would be missed. / There would be less lesson learning and knowledge dissemination process established to support states interested from learning from reforms. / Option 2: Scale-up of SPARC / DFID would expand SPARC programme funding by £14.5m, bringing the total to £60.4 million. The scale-up would expand engagement to five other states (Katsina, Yobe, Zamfara, Anambra, Niger), in line with DFID’s operational plan to expand support to the North. It would also continue momentum in existing 5 states (Lagos, Enugu, Kano, Kaduna, Jigawa), scaling up successful interventions particularly in Jigawa and Lagos states and at the Federal level. / The programme would also be extended by 1 year from 2014 to 2015. This would allow enough time for the states, particularly the new ones, to embed reforms more effectively. It would also allow a continuation of the programme over the election period in 2015 when the environment is not likely to be conducive for a new programme or new reform initiatives. It is nevertheless important that support for reforms will continue over this period, to ensure no momentum is lost. Although no plans for a successor programme for SPARC are in place, it is likely that one will be considered in due course given it is widely recognised that governance challenges in Nigeria are severe and governance reforms normally require a long-term approach. Other SLPs are also proposed to extend for a similar time-period. A longer extension is not possible due to EU procurement rules. The amount of the scale-up would go over the 50% threshold in increase in contract value, requiring a retender. This would disturb operations, delay the expansion by up to 12 months and increase procurement costs and reduce Value for Money. / Considered and Discarded Option / A third possible option would be to tender for a new State level public management programme to operate in the five additional States where SPARC is not yet fully operational. This option was discarded due to: / the strong overlap between SPARC’s work and potential duplication of work in any new programme (e.g. SPARC has already commenced inception in three of the five states); / the fact that SPARC has considerable experience and contacts at state level in Nigeria and has already achieved good results in existing states. Though approaches are tailored to suit each state, the areas of work will continue to be very similar; / it would delay expansion to North by at least 12 months, and add significant additional procurement costs. / Preferred option / The preferred option is option 2. With a scale-up, additional results would be achieved in five additional states, most of them in the North, whilst reforms would be deepened in existing five states (particularly in Lagos and Jigawa) and at federal level. An additional year would allow the states to embed the reform activities, particularly in the new states. / B. Theory of change and evidence base / The overarching logic of our invention is that intensifying efforts on strengthening state government institutions will indirectly improve service delivery outcomes through state governments’ increased ability to use their resources effectively. Although adequacy of public resources is an issue in Nigeria particularly in northern states, the ineffective use of resources is the biggest impediment to sustained improvement in public services, and ultimately making progress towards the MDGs. / Better ability to use resources effectively requires states to reduce leakage, increase budget predictability and more effective budget implementation, as well as better policy planning and civil service performance. DFID funding for technical assistance for selected state level governments is expected to address these issues by delivering stronger policies and strategies; improved public financial management; and a more capable public service management. But it is acknowledged that capacity building alone is not enough: support to federal agencies is expected to increase accountability and encourage change in state-level agent behaviour through use of consensus and incentives. / This theory of change is based on the evidence in implementing SPARC so far as well as academic research evidence. / The Problem / With Nigeria’s Federal system, effective public management at State level is essential for public service delivery and poverty reduction. They use about 50% of total general government spending, and are responsible for delivery of most basic services. However, unfortunately, the state governance is often ineffective and governments are also subject to limited accountability. Baseline PEFA/SEAT results[17] indicate that, across SPARC supported states: / a) policy guidance is not rigorous enough to guide strategic planning and decision-making is not evidence based; / b) annual budgets are not realistic, budget execution is weak and financial reporting is not credible; / c) the mandates of ministries, departments and agencies are unclear, structures are inappropriate, processes are ineffective, and human resources are underperforming. / These baseline results are consistent with Nigeria’s scores on the World Governance Indicators, and its performance on the Ibrahim Index and the African Peer Review Mechanism. / Governance in Nigeria is driven by patronage politics which means that changes which are likely to improve the use of public resources to deliver pro-poor public goods are not likely to be popular amongst many of the people who hold positions of power and leadership. Therefore, changing governance systems will not just require a change of attitude, but also a shift in the incentives that drive a wide variety of actors[18]. / Figure 1: The SPARC Results Chain / Inputs to Outputs / SPARC inputs are long and short- term technical assistance, with some relevant training and equipment, to selected state level governments. It is assumed that these TA inputs will lead to improvements in (a) policy, strategy and M&E; (b) public financial management and (c) civil service performance at state level. / SPARC (like the other SLPs) is focused on technical assistance, as it is recognized that the problem behind the poor poverty and human development indicators is mainly the quality of the governance systems that manage resources. SPARC approach to the provision of technical assistance is based on, and consistent with, the recognized “good practice” in capacity development such as the key principles of Accra Agenda for Action 2008.[19] / SPARC has been operating since 2008 and has evidenced that its TA inputs are meeting the expected outputs. The SPARC Mid-Term Review scored A+ in November 2011 in terms outputs achieved so far: Output 1 (Policy, strategy and M&E) scored A+, Output 2 (PFM) scored A+, Output 3 (civil service performance) scored A. The Mid-Term Review noted that: “SPARC appears to have made significant progress in promoting the gradual improvement in the state government’s ability to conduct medium-term development planning and budgeting at overall and sector levels. The combination of the effects of SPARC and ESSPIN and PATHS2 has resulted in greater progress in strategic planning processes in the health and education sectors. Progress has also been made towards the rationalization and restructuring of the state government and the strengthening of human resource management and service delivery management systems to ensure the effective and efficient implementation of medium-term plans.” / SPARC approach to TA at state level / TA inputs are focused on state level governments. The original five focal states for the suite of programmes, as well as the additional five, were identified on the basis of a number of criteria including need in terms of poverty levels and commitment to reform as assessed as part of the Government’s strategic planning processes. The selection was done in collaboration with the World Bank and USAID as part of the WB-DFID-USAID joint country strategy. / The SPARC approach in each state is determined by a balance of technical competence and institutional performance. This implies that increases in overall government competence would be delivered by SPARC-supported technical capacity improvements, only when associated with a corresponding increase in institutional capacity. The term ‘institution’ here is used in the sense of how things are done in a society. An increase in institutional capacity therefore requires ‘changes to the rules of the game’, which requires strong political will to achieve. This 'stepped approach' is shown in Figure 2, and is applied to ensure that a balance is achieved between the delivery of technical support by the Programme and associated institutional change on the part of the State Government – slowing or expanding support depending on evident institutional changes, using decision points in work programmes. / Figure 2: Incremental Stepped Approach / SPARC’s theory of change was designed to meet the circumstances of five original states where SPARC’s predecessor programme had already laid foundations. In these states, a degree of technical and institutional preparedness had already been established, and working relationships with State Government officials was already established. The planned expansion calls for SPARC to work with a much larger group of states which are inevitably at different stages of readiness. SPARC will adopt three general approaches to working in this extended variety of locations – building foundations (engagement type c) in new states which have limited governance reform experience; consolidating (engagement type b) in those states which have deeper understanding and record of governance reform; and going with the grain (engagement type A) in states which have demonstrated track record in implementing reform (and have their own reforms plans to which TA can be provided.) / Figure 3 below uses information yielded from diagnostic activities[20] to estimate the technical and institutional capacity of the 10 states, which in turn enables SPARC to tailor its approach to the 'readiness' of each state. It shows that the ten states fall broadly into three clusters. / Figure 3: A Typology of Approaches / When putting this into practice, where building foundations is most appropriate, SPARC will operate through a negotiated intervention plan which provides for specific (generally sector driven) technical assistance. Where consolidation is appropriate, SPARC will continue to operate through the vehicle of an overarching governance reform programme, using review and decision points to determine the best areas to support. Where going with the grain has become clearly possible, SPARC will align specific technical assistance to state governments own plans. With the adoption of a greater number of states, and in response to recommendations in the Mid-term Review in November 2011, SPARC has also adopted state level Logical Frameworks to ensure more increased state specificity in the design and monitoring of results. / Outputs to Outcome / The assumption is that improvements in public sector management translate into enhanced efficiency and effectiveness of selected state level government’s use of public resources – in better planning, increased budget predictability, reduced leakage and better performing civil service systems. / This assumption is based on broad research evidence that efficient management of public resources, including a functioning public administration and public financial management system, is important for improving government performance. For example, budget reform is thought to make expenditure more efficient and policy more effective by improving planning assisting in monitoring and evaluation, improving transparency and creating a forum for participation and greater accountability.[21] However, there is no clear consensus what works: reforms have not always been successful due to contextual and design factors. For instance, WB econometric work demonstrated that medium-term expenditure frameworks improve both allocative efficiency (by reducing volatility of spending) and fiscal discipline (by improving fiscal balance)[22] but their effectiveness is questioned by other studies. [23] / The SPARC Mid-Term Review in November 2011 identified two indicators as the best “proxys” to measure the achievement of the programme outcome in Nigeria: % of PEFA/SEAT dimensions that are improving and analysis of budget variance. PEFA and SEAT self-assessments are recognised to be effective standardised tools across states to identify reform priorities, as well as incentive and monitor their implementation on key public finance management, public administration and policy areas. Specifically, in order for the budget to be an effective and transparent tool for policy implementation, it is critical that it is realistic and that it is implemented as passed. The SPARC Mid-Term Review in 2011 identified this as a continuing key challenge in SPARC states in improving how resources are used. / Policy & strategy; public finance management & public sector management reforms / Based on repeat PEFA and SEAT self-assessments in early 2012, all states showed progress in improving PEFA/SEAT scores with Enugu, Jigawa and Lagos doing particularly well. Rough comparison between SPARC and non-SPARC supported PEFA/SEAT Dimension scores shows that performance in SPARC supported dimensions is higher in four out of five states by an average of 13%. / Table 2: Percentage of PEFA/SEAT Scores improving between baseline and 2012 assessments.[24] / Workstream Enugu Jigawa Lagos Kaduna Kano All / P&S/M&E 21% 56% 29% 29% 12% 29% / PFM 43% 25% 18% 14% 4% 21% / PSM 61% 15% 22% 22% 21% 28% / Totals 31% 42% 24% 23% 8% 25% / Budget variance / State governments have made some progress in reducing the variance between budgets and actual expenditure. The majority of SPARC supported states have demonstrated a broadly downward trend in the variance over the last three years; in part a consequence of developing more realistic budgets. / Table 3: Total Absolute Budget Expenditure Variance[25] / State 2009 2010 2011 / Enugu 27% 22% 5.2% / Jigawa 35% 13.5% 3.7% / Kaduna 53% 42% 44.7% / Kano 51.7% 18.7% 44.3% / Lagos 24.5% 11.1% 14.6% / Outcome to Impact / It is assumed that improved use of resources lead to more effective and efficient public service delivery, which in turn will ultimately also improve progress towards the MDGs. There is a growing academic evidence base on the link between stronger institutions, in particular with good budget management, and improvements in service delivery outcomes.[26] For example, institutional economics’ literature suggests that institutions are vital for the efficient allocation of resources, and argues that they are critical for the attainment of higher levels of development.[27] Rajkumar and Swaroop provided econometric evidence that differences in efficacy of public spending in health and education can be largely explained by the quality of governance (corruption and quality of bureaucracy).[28] Kaufmann and colleagues also found that government effectiveness is positively associated with per capita incomes and adult literacy and negatively associated with infant mortality.[29] Further, DFID review on substantial body of macroeconomic and case studies concluded that strong institutional frameworks are likely to cause growth. However, the research is less convincing in differentiating between the specific institutions that matter in a particular context. In particular, the form and effectiveness of institutions depends upon the political elites with the power to enforce them.[30] This is recognized as an inherent part of SPARC theory of change. / In line with this evidence, it is also assumed that SPARC’s programme impact, pro-poor improvements in public services, can only be achieved together with other DFID SLPs and with political as well as technical interventions. It is recognized by donors that problems in sectors such as health and education may have a common origin: weak PFM, accountability and capacity[31], and that an effective interplay between governance and sectoral programmes is required to achieve developmental impact. Similarly, the experience also finds that social accountability mechanisms are able to influence development outcomes and can help improve governance but they do not necessarily guarantee improvements in public services[32]. The DFID review concludes both demand and supply side must match and where they intersect will determine the quality of the institutional regime.[33] / Therefore, SPARC is unlikely to achieve success on service delivery without improvements in the main sectors supported by other DFID programmes. Similarly, sustainable improvement to service delivery in the health and education sectors, or successful implementation of policies to facilitate economic growth, is dependent on reforms in the central ministries and agencies supported by SPARC. Further, SAVI can help increase accountability and bringing external pressure for institutional change – while SPARC can improve capacity and systems for institutions to respond to citizens’ needs. / For instance, improving the way human development is managed requires both governance and sector programme inputs. As an example, without improvements in the global chart of accounts in use in the state, the efforts sector programmes make on medium-term sector strategies are unlikely to have real value and uptake. In the states where SPARC has worked alongside PATHS and ESSPIN, it has provided the technical architecture within the sector programmes gave been able to support medium-term planning and budgeting in their sectors within more realistic-resource envelopes. In the five additional states with SPARC will work, SPARC intends to provide similar architecture to support programmes like PRRINN/MNCH who were finding it difficult to secure budgetary releases that they need to further their sectoral work. / Recent evidence from SPARC focus states in Nigeria suggests that in very broad terms, aggregate budget disciple in states is linked with increasing expenditures in health and education sectors. Similarly, increases in health and education expenditures also map to the SPARC typology of engagement. Heath and education expenditures in SPARC type A states, Lagos and Jiwaga, increased by 31.97% and 10.47% respectively from 2010 to 2011. Broadly, SPARC analysis suggests that expenditure budget variation in health and education sectors is reasonable under Type A, unpredictable though with some positive movements under Type B, and high or volatile under Type C. [34] / Though the evidence seems to broadly validate the assumptions around the links between better governance systems, improved service delivery and poverty reduction, it will be some time yet before a full picture emerges of the development impact of DFID investment on public services. / Political commitment and incentives to public sector reform – federal level support / Changing governance systems on a sustainable basis will not just require political will, but also a shift in the incentives that drive a wide variety of actors. Evidence in the sections above indicate that success in public sector management reforms is overall dependent on the ability to adapt to local circumstances, and to influence incentives for reform. Evans and Rauch argue that “replacing patronage systems for state officials by a professional bureaucracy is a necessary (though not sufficient) condition for state to be developmental.”[35] This is particularly true in a country like Nigeria where governance is driven by patronage politics, and where improvements in public sector management are likely to threaten existing mechanisms of control. / Overall, SPARC engagement in States, as well as those of other SLPs, is based on robust political economy analysis, and is focused on areas where there is political will. SPARC has developed PE analysis for 9 out of 10 states in which it plans to work, and it is developing a tool with which to assess the political commitment to reforms and areas may have the most traction in each state. Specific strategies for each State are developed at the beginning of an engagement, based on the State’s own self-assessment of reforms it needs. In order to formalize and clarify the relationship between DFID and its partner state governments, a Memorandum of Understanding is agreed, covering all the programmes and expected results for each state. Joint reviews will be undertaken annually by SPARC and state government in reviewing progress against agreed reforms. Similarly, the political commitment to reform is continuously monitored to ensure SPARC focus is maintained where progress is realistic to achieve. / At state level, SPARC works closely with DFID State representatives, as well as SAVI and other sector programmes in building consensus around the necessary policy and reform decisions, including efficient and evidence based spending allocation and use. Political engagement is through regular meetings with Governors, Commissioners, State Houses of Assembly and other known champions of pro-poor development and is an on- going process. The SPARC MTR review noted that SPARC had established substantial credibility and effective engagement with its counterparts at both federal and state level. In addition, DFID State Representatives have been recruited since late 2011 and early 2012 to represent DFID in focus states. This is partly in response to the MTR of SLPs in 2011 that recommended that DFID should strengthen the quality of support to SLPs in states. The role of the DFID State Representatives is to help ensure political dialogue is robust with the state authorities and to assist and coordinate SLPs in their work. / Federal level work is a critical part of SPARC’s work on supporting incentives for change. In Federal systems like Nigeria, where states are virtually independent of the federal government, change in state behaviour is often only possible through use of incentives or consensus.[36] In an environment of constant contest for control of resources between federal and state governments, there is strong evidence that the use of incentive schemes can foster better federal-state relations and improve a country’s chances of achieving its development outcomes.[37]There is already considerable evidence from SPARC and other existing DFID programmes that process in one state acts as an incentive to neighbouring states to introduce similar reforms.[38] / SPARC’s federal support component scored A+ in the SPARC MTR in November 2011. The TA to Federal agencies is expected to improve the federal support to state level governments – which is expected to change state level behaviour through creation of consensus and incentives through peer-review. SPARC is supporting the MDGs Conditional Grants Scheme as a means of incentivizing improved state performance. All Nigerian states currently subscribe to this scheme. / On gaining improved development outcomes through consensus, SPARC works with the Nigerian Governors Forum (NGF). The NGF is an association of all 36 state governors, with a technical and professional secretariat. SPARC has supported NGF to develop a States Peer Review Mechanism (SPRM) through which states can access themselves in a non-adversarial way and learn from each other to raise performance in all states. Significant effort has been made also to distil and document results being demonstrated by SPARC and its partners. This knowledge management component of SPARC is proposed to be scaled-up in the acknowledgment that the work through the MDGs Office and the NGF will amplify the impact of SPARC’s work also beyond the SPARC focal states, and encourage lessons learning from the existing SPARC states to the new SPARC states. / The box 1 gives examples of SPARC’s work and plans forward on key legal and policy issues that support SPARC’s work. / Results already achieved against the SPARC logframe would indicate that SPARC, together with other SLPs, has been able to start to influence incentives for change. Nevertheless, although it is challenging, it will be important for DFID and its programmes to strive to better measure and track how DFID programmes can jointly influence incentives that will change behaviour. This will be considered as a part of the forthcoming SPARC internal research work as well as the independent evaluation of the SLP suite that will assess what sustainable impact SPARC and other SLPs have been able to deliver. / Box 1: Examples of SPARC’s work on legal and policy issues / Fiscal Responsibility and Public Procurement / The Federal Government passed a Fiscal Responsibility Act in 2007 and set up a Bureau of Public Procurement to improve due process in public procurement. Fiscal Responsibility laws help to enhance fiscal discipline, macroeconomic stability and the transparency and accountability of public expenditure. Similarly, it is understood that grand corruption in Nigeria is often perpetrated through the procurement of large infrastructure projects, often at inflated prices. Fiscal Responsibility and Public Procurement Laws (FRLs and PPLs), properly implemented, can therefore be key contributing factors for the achievement of SPARC’s main outcome: state governments using their own resources better to meet the MDGs. / SPARC has advocated for the passage of FRLs and PPLs by all 36 states, working with the Nigerian Governors Forum. The federal government cannot force states to pass legislation. Therefore, working through the NGF (an association of all 36 governors) presents the best chance of compliance since agreements are reached through consensus. The NGF, with SPARC support, currently maintains a database on the state of the legislation in all states. SPARC has also been the driving force behind an effort to get all the main donors operating in Nigeria to support the passage of FRLs and PPLs through the NGF. SPARC has already mapped the support requirements to states to include legislation drafting, sensitisation of the state houses of assembly, capacity building of finance officials, and support to implementation for the states that have already passed them. / In particular, SPARC has supported Lagos and Jigawa states to pass FRLs and PPLs. Budget realism has improved year-on-year in Jigawa, and Lagos has been able to meet the prior conditions for a Development Policy Operation (direct budget support) from the World Bank, and these achievements are consistent with the aims of these state laws. In the coming months, SPARC will work with DFID and SAVI to reinvigorate the joint donor effort to support more states to pass both laws in partnership with the NGF. / However, while FRLs and PPLs have had a positive impact in many countries, their impacts on oil-producing countries (like Nigeria) have been limited, given the high volatility of oil prices and the political economy factors that constrain the design and implementation of the laws. Consequently, SPARC’s efforts have additionally been focused on the procedural and fiscal rules that will enhance discipline and promote accountability and transparency. These include the introduction of fiscal projection and revenue models, detailed budget classifications and charts of accounts, call circulars with clear expenditure ceilings, medium term sector strategies linked to more realistic budgets, price intelligence, improvements in budget profiling, cash management and controls over cash releases, and the tracking of budgetary expenditure in collaboration with SAVI. We are working to institutionalise these procedures and rules in all SPARC states (including Niger and Anambra, two new SPARC states that have already passed the legislations), in addition to advocating for the passage of legislation in other states. / Freedom of Information / In 2011, the Federal Government passed a Freedom of Information Act. Under the FOI, all government bodies spending public funds will have to be open about their operations and expenditures and citizens will have the right to access records and ask questions about government activities. State Houses of Assembly are weak and the effectiveness of their Public Accounts Committees severely limited. Given that state governors currently have constitutional immunity from prosecution and large ‘security votes’ that are not subject to public scrutiny or audit, effective FOI laws can perhaps be the best tool through which transparency and accountability of government business can be promoted, and SPARC’s purposes achieved. SPARC’s main contribution is work from the inside to improve the accessibility of information. From 2012 onwards, SPARC will work with DFID, SAVI and the NGF to advocate for the passage of FOI laws by all 36 states, particularly in those states where there is little appetite for fiscal responsibility and public procurement laws, and the uptake of procedural improvements in PFM have been slow. / Meeting MDG Goals / SPARC has supported the design and implementation of a Conditional Grants Scheme to states. To date, this has led to the investment of more than £500 million in Health, Water and Sanitation and Malaria prevention. At inception in 2007, the CGS funds accounted for 30% of all debt relief gains. Given the proven success of the scheme, SPARC will work will DFID to advocate for an increase in the CGS share of the total debt relief gains, and the extension of the scheme to local governments. The governance improvements in the existing SPARC states have equipped them to be among the most successful states in accessing CGS funds. SPARC’s governance improvement support to the new states, some of which have very weak MDG indices, should improve their level of success in accessing the CGS funds both to states and LGAs and increase their chances of meeting the MDGs.
C. Assessing the strength of the evidence base for each feasible option / Option 1: Status Quo / There is a strong evidence base in SPARC’s ability to meet the programme outputs and outcomes. Evidence is based on a successful Mid-Term Review in November 2011 which awarded SPARC a score of A+ (performance has moderately exceeded expectation). An internal research study commissioned by SPARC at the end of 2011 concluded that SPARC had achieved all 2010 logframe outcome milestones. This progress is supported by broad research evidence that indicates that efficient use of public resources is important for improving government performance. / SPARC’s ability to contribute to programme impact, together with other DFID programmes, is based mainly on research evidence that argues that there is a link between stronger institutions, in particular good budget management, and pro-poor service delivery outcomes. Nevertheless, the causal link between the two is somewhat contested, and success is dependent on political will and incentives. Lack of political will or other political uncertainties can complicate delivery of SPARC results. However, SPARC has a relatively good evidence base on the current political economy context based on its Measures of Political Commitment and Political Economy (PE) Analysis that it updates regularly, uses to adapt its programming accordingly and aims to influence through its political advocacy work. / Overall, availability of good quality and timely data to monitor state level results in Nigeria is rather weak, but SPARC, with the help of independent service provider, has a very strong focus on ensuring robust data collection and M&E systems. / Option 2: Scale up of SPARC / The evidence base for SPARC scale-up and extension is very similar to that of the option 1. However, expansion to new states will naturally bring an element of uncertainty in the delivery of results as SPARC has less evidence on what works in the new states. However, a reasonable evidence base exists for SPARC to be able to amend its approach appropriately. It has already conducted a fair amount of diagnostic analysis in the proposed new states (including the North States Inception Report, SPRM study & Political Economy analysis). In addition, it has already undertaken inception work in three out of the five additional proposed states (Katsina, Yobe and Zamfara). The theory of change sets out clear evidence how SPARC has intends to define and apply a new ‘building foundations’ approach to new SPARC states. / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited: / Option Evidence rating / 1 Medium / 2 Medium / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / The environmental screening was completed as a part of the original programme approval. There is no evidence to suggest that the proposed programme will place a significant additional impact on the environment or climate change. / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C
D. What are the costs and benefits of each feasible option? / The economic appraisal (attached as Annex 4) supports the case for scaling up the programme. It concludes that SPARC, under option 2 (scale-up, under central scenario) is expected to have a substantial rate of return and net present value of £20m. When stress-tested against very conservative assumptions, including the main risks outlined in the risk matrix, the programme has a low negative return (net present value of £-2.5m) and when stress-tested against optimistic assumptions, the programme has a very high return (net present value of £58m). Several incremental benefits are expected as a result of scale-up. The cost-benefit analysis monetises those in allocative efficiency and fiscal discipline of the federal budget; as well as strengthening internal controls that are derived from improvements in PFM.
E. What measures can be used to assess Value for Money for the intervention? / We will carefully track SPARC’s progress in each component against results and milestones in the logframe as an overall guide to whether expected benefits are being achieved. This will include: / Evidence of the economy of inputs being sourced through SPARC procurement systems / Justification of management costs and further negotiations during contract amendment stage / Monitoring of output levels against agreed results framework
F. Summary Value for Money Statement for the preferred option / Overall we are confident that SPARC offers good value for money. This is evidenced by the strong results SPARC has leveraged. SPARC rated A+ in the Mid-Term Review with good results across all its components. One example where results were monetised: savings from better budget reconciliation and closing dormant bank accounts alone saved £68m already far exceed the total programme costs (£29m spent so far). These results indicate that SPARC has been already able to initiate changes in the governance systems, thereby reducing leakage and waste of public funds. / Specific examples include: / • Closing dormant bank accounts: By early 2010, the government of Jigawa State had reduced the number of bank accounts it had from 615 to 105. Unused funds from these accounts were returned to the treasury and amounted to £7.6 million. These funds were made available for the 2010 budget. Similarly in Kano State, the government reduced the number of accounts it operated from 756 to 92. The proliferation of bank accounts (many of which government was not aware) was a major avenue for fraud. In 2010 approximately £20 million was returned to the treasury in Kano. / • Reconciling bank accounts: At the end of 2009, Jigawa’s government instructed that all unspent funds in government accounts should be returned to the treasury. This was the first time in the history of the state this had been done, and it yielded £37 million (N9.3 billion). This annual clearance has now become standard practice and has closed another avenue for fraud. / • Making budgets more realistic: In 2010 in Kaduna State £169 million of non-existent funding was removed from the budget and £117 million in 2011. A similar revision occurred in Ekiti State in 2012 when £40.7 million was removed from the budget. / • Eliminating ghost workers: In Nigeria the subject of ‘ghost (government) workers’ is widely reported. Some state governments are trying to address this area. It was brought to prominence when the minimum wage of N18,000 per month was introduced in 2011, and resources became stretched. Work to verify workers in the civil service was undertaken in Kaduna and by the end of 2011, savings of £128,000 (N32 million) have been made. / • Due process: In 2007 the government of Jigawa State introduced a database financial management system to raise standards in awarding contracts in the state. Three years later, the head of the civil service announced that a total of £16 million (N4 billion) had been saved. / • Getting on top of state debt: Most Nigerian state governments have domestic and external debt on their books – and most external debt is well recorded and managed. Internal domestic debt is less controlled. In Kaduna a Debt Management Department was established, and a simple database introduced to monitor contracts, payments and arrears. From a peak of £48 million in 2010, arrears had been reduced to £16 million by the start of 2012. / Please see additional information in Annex 3. / The following examples also demonstrate SPARC approach to Value for Money. / Value for Money in Technical Assistance / Refusing to deploy large numbers of consultants at an early stage. Instead, SPARC preferred to gradually scale up its technical assistance work based on identified need and the likelihood of success. / Including Review and Decision Points in Annual Work Plans (down to activity level) which mean that SPARC does not spend money until the government partner demonstrates a commitment to the institutional changes necessary to move the work forward. / Showing a deliberate preference for using Nigerian consultants (and international-calibre consultants based in Nigeria) in preference to flying in expatriate consultants. / Encouraging in-country learning for state partners, rather than funding expensive overseas trips of questionable value. / Reducing the level of support by the Programme Development Group (comprised largely of international consultants) since the programme entered its implementation phase. / Investing in programme staff to ensure that they are able to participate in consulting assignments. / Negotiating a fee rate reduction based on the certainty of a longer term contract for the consultants, where DFID has instructed SPARC to fund a Technical Assistance post in a government organization. / Opting for a six month scoping process using just a Technical Coordination Manager (in place of a State Team Leader) when DFID instructed SPARC to move into three additional northern states, and twinning these states with the existing teams in Jigawa, Kano and Kaduna that provided supervision at no additional cost. / Negotiating with PRRRINN/MNCH to provide our staff with free office accommodation for the six month inception in Katsina, Yobe and Zamfara. / Value for Money in Procurement / Balancing initial cost against longer-term efficiency and effectiveness. Where a higher quote is preferred based on the balance between quality and price, written justification is provided, and always sought to negotiate down the preferred bidder. / Strictly adhering to internal procurement rules whereby three independent quotes must be obtained for purchases between Naira 100k and Naira 1m. Anything above this level must be procured through Crown Agents, in accordance with DFID rules. / Developing an IT Structured Approach Paper which expressed a preference for open source software when providing IT support to government. SPARC has rarely bought IT equipment for government partners and has not provided support to procure large IT management information systems that tend not to be used as part of normal government business. / Value for Money in Accommodation / Successfully negotiating significant savings with other SLPs where offices are shared in States. For example, SPARC does not pay office rent in Enugu and Kano and uses accommodation provided by the state government in Kaduna. / Gaining government approval in some states for SPARC to be accommodated in their offices, at no cost. / On the programme side, SPARC will continue to make deliberate efforts to retain the focus on those things that will contribute to its purpose of facilitating the improvement of Nigeria’s use of its own resources. This means that there will be greater effort on activities (such as procurement and clearing down bank accounts) that should release additional resources for state development. The planned use of state-level logical frameworks will be useful in this regard.
[17] State Evaluation and Assessment Tool (SEAT) and Public Expenditure and Financial Accountability (PEFA) self-assessments undertaken in SPARC supported States in 2008.
[18] Earle, L. et al., (2010), Assessing the Evidence of the Impact of Governance on Development Outcomes and Poverty Reduction, Emerging Issues Research Service, GSDRC.
[19] The key principles include ensuring technical assistance is demand-driven; use local resources and is incorporated in clients’ own development plans. http://www.oecd.org/dac/aideffectiveness/parisdeclarationandaccraagendaforactionfullrelateddocumentation.htm
[20] This is based on SPARC Measures of Political Commitment for existing states; Political economy assessments for all states, information from the Nigeria Governors Forum and self-assessment activities such as State Evaluation and Assessment Tool (SEAT) and Public Expenditure and Financial Accountability (PEFA) for existing states and Katsina, Yobe and Zamfara.
[21] Earle, L. et al., (2010), Assessing the Evidence of the Impact of Governance on Development Outcomes and Poverty Reduction, Emerging Issues Research Service, GSDRC. See also Foster, M., Fozzard A., Naschold F., and Conway, T. (2002) How, when and why does poverty get budget priority: poverty reduction strategy and public expenditure in five African countries, London, Overseas Development Institute Synthesis Paper.
[22] Jim Brumby, An Investigation into the Impact of the Medium-Term Expenditure Framework on Budgetary Outcomes, World Bank
[23] Similarly, although there is no consensus what works in PAR, there are successful examples where PAR initiatives have led to improved government improvements. For example, in Tanzania, the economic, social and political transformation that has taken place over the past decade has been underpinned by the reforms in its public service. Earle, L. et al., (2010), Assessing the Evidence of the Impact of Governance on Development Outcomes and Poverty Reduction, Emerging Issues Research Service, GSDRC.
[24] Source: SPARC comparison of baseline and 2012 PEFA/SEAT Assessments. Baseline PEFA/SEAT results are final and validated whilst 2012 PEFA/SEAT results are interim in some cases and subject to final validation.
[25] Source: Mix of 2012 PEFA Assessments and non-PEFA SPARC assessments of government budgets and accounts (which are not final or audited in some cases). 2009 Kano figure is an average of 2007-2009.
[26] See for example: World Bank (2003). Making services work for poor people, World Bank Development Report 2003. World Bank, Washington DC & World Bank (2007) Strengthening World Bank Group Engagement on Governance and Anticorruption,World Bank, Washington DC.
[27] North, D, (1990) Institutions, Institutional Changes and Economic Performance. Cambridge: Cambridge University Press; Kaufmann, D (2004) Governance Redux: The Empirical Challenge, Law and Economics (Economics working paper archive report no. 0405001).
[28] Andrew Sunil Rajkumar, Vinaya Swaroop (2007) Public Spending and outcomes: Does Governance matter? World Bank, August 2007. Also, Kaufmann et al (2002), Governance matters II: Updated indicators for 2000-01, World Bank Policy Research Paper No. 2772.
[29] Kaufmann, Aart Kraay, and Massimo Mastruzzi 2003. “Governance Matters III: Governance Indicators for 1996-2002”, Washington D.C.: World Bank (May).
[30] DFID (2002) DFID Evidence Product – Rapid Review: The Research Paper relating to a ‘Golden thread’ of international development: a rapid review.
[31] DFID (2007) Governance, development and democratic politics, DFID’s work in building more effective states.
[32] As summarized in GSDRC Helpdesk Research Report Evaluations of Voice and Accountability Instrument (April 2010).
[33] DFID (2011) A preliminary mapping of the evidence base for Empowerment and Accountability, April 2011.
[34] SPARC (September 2012) Health and education expenditures in SPARC supported states, for DFID.
[35] Peter Evans and J. E. Rauch, “Bureaucracy and Growth: A Cross-National Analysis of the Effects of ‘Weberian’ State Structures on Economic Growth” American Sociological Review, Vol. 64, No 5 (October 1999)
[36] Rodden, J., (2008) ‘Federalism’, in The Oxford Handbook of Political Economy, Wengast & Wittman, eds., Oxford University Press.
[37] Searle, B., (2008) Achieving Nigerian Policy Objectives through Conditional Grants: Scope for Greater Use of Incentive Based Instruments, prepared for DFID and World Bank.
[38] For example, the Zamfara State Government adopted a multi-year budgeting system following SPARC’s ‘twinning’ of that State with Kaduna, an existing SPARC state.

Commercial Case: Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / The procurement process has already been undertaken through competitive open tendering in accordance with the EU Public Procurement Directives. Contractually the preferred option would require a slight revision of the initial tender Terms of Reference to reflect an increase in scale as a result of increased target states. However, this would not necessarily require an increase in scope as the scale up aims to replicate the results being achieved in the current SPARC focus states without a change in methodology or broad approach. / The scale-up is within EU rules which specify that contracts awarded can be increased by up to 50% before they need to go out to tender again. In these circumstances, a direct single tender route with the existing supplier is justified unless poor performance indicates that fresh market advertisement and a change of supplier is required. However, further negotiations at contract amendment stage with input from the DFID Procurement Group will further ensure economy and efficiency of proposed additional funding.
B. How does the intervention design use competition to drive commercial advantage for DFID? / It does not. Instead, the intervention design anticipates that better value would be obtained by negotiating an extension to the current supplier’s contract. This judgement is based on: / the supplier’s performance so far; / the real and opportunity costs that would be incurred in returning to the market and potentially “changing horses in mid-stream”; / and the reality that unless it were common knowledge within the relevant market that HTSPE’s performance was below par, few if any other potential service providers would not judge the cost of bidding to be worth it, because we would be unlikely to make a change at this juncture in the life of the project and ultimately to do this would be at significant additional cost to DFID (e.g. set up costs , procurement).
C. How do we expect the market place will respond to this opportunity? / We assume HTPSE, who implements this programme, will welcome an opportunity to extend their service provision to SPARC, and that they will wish to at least maintain the value of current prices for services and goods. / We will propose to offer a single tender route. This means that for HTSPE, the significant cost of bidding and use of unproductive time is now a sunk cost reclaimed in fees over the first year of the project, and this project is now a lucrative part of HTSPE’s portfolio. In these circumstances, we will wish to negotiate revised prices for fees and expenses that represent a reasonable incentive for HTSPE in exchange for a single tender opportunity, free of competition. We will also make it clear that the extension should not be an opportunity for the company to renegotiate in the time scales and resources necessary for the existing programme. In negotiation we trust that they will see the sense of our position. / How successful we may be, remains to be seen. HTPSE may argue that the scale-up into new states carries new or increased risks, and that fee levels should be increased to reflect this.
D. What are the key underlying cost drivers? How is value added and how will we measure and improve this? / These are: / Consultancy fee rates, where the specific factors are levels of responsibility, duration of engagement, difficulty of the post, credentials and CV ands past performance, unique issues related to the market position of each professional group, and regional or local market factors for national consultants; / Direct consultant overhead costs relating to the provision of a consultant (e.g. medical insurance, visas, etc.) / Indirect overhead costs. These will include amounts within each fee to contribute to the costs of being in business, such as corporate operations, managed costs, recruitment, back office administration, headquarters, Nigerian office, etc.) / The profit margin. / Our ability to influence the cost drivers is limited, although we have made progress in the past year in strengthening our negotiating position with our key suppliers. But living costs in Nigeria are high, and while insecurity continues, these become higher factors and a major driver of consultancy costs, as is the perception of Nigeria as a difficult environment to operate in. / Many of the results expected in the extension period involve high level policy change, and in some cases legislative change. In this context the experience and effectiveness of key consultants is paramount, value for money is not driven simply by least cost, but by the best ratio of effectiveness to cost, and this has to be assessed on a case by case basis. Whenever interventions are not delivering the expected results, and we assess that this is due to the limited effectiveness of individual consultants, we will either agree personnel changes or discontinue the intervention.
E. What is the intended Procurement Process to support contract award? / We will liaise with the Procurement Group to write to HTPSE seeking a proposal for an extension to the existing contract, and emphasise that we are looking for a revision that reflects the factors set out above in section C. Once we have this we will meet to negotiate an outcome. Our emphasis will be on obtaining improved value for money for both parties (including proportional overhead costs, fee rates and expenses), without delaying the process of the next phase of work. We are prepared to return to the market if HTPSE refuses to make an offer that reflects a fair exchange for its single tender opportunity and lower tender costs. / Annual audit terms of reference require a review of SPARC’s procurement process. Annual audits of the SPARC programme currently present no issues on procurement. These audits also provide DFID assurance that SPARC follow the terms of conditions of the signed contract which requires all procurement above £100,000 be procured through DFID registered procurement agents Crown Agents (with which DFID has a core country agreement). This arrangement further ensures best practise and Value for Money in procurement.
F. How will contract & supplier performance be managed through the life of the intervention? / We will continue the quality-focussed approach so far deployed, but will seek HTPSE’s interest in an increased focus on payment by results, possibly by payment of higher fees for over-performance a mid-level fee range for standard delivery, and means to reduce fees in the event of under-performance and failure to meet the programme’s logframe targets.

4. Financial Case
A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / SPARC will require provision of additional financial support of £14.5m, bringing the total contract value to £60.4m. Table 4 below shows how the additional financial support of £14.5m will be allocated and phased, and how this maps to the existing funding allocations for the programme as a whole (total of £60.4m). [39] / Table 4: Total Programme Budget 2008-2015: a comparison of current and additional requested funds / Outline Programme Budget Current Funding Additional funds requested Total £m / 2012/13 £m 2013/14 £m 2014/15 £m 2015/16 £m Contin- / gency / [40] / Long Term Fees 10.3 0.3 0.4 2.3 0.2 13.5 / Short Term Fees 17.3 0.6 0.4 2.6 20.9 / Travel - LT & ST 2.7 -1.3 0.3 0.3 2.0 / Accommodation/Subsistence - LT & ST 5.0 0.9 0.9 1 7.8 / Local Offices 5.5 0.6 0.6 1.8 0.1 8.6 / Vehicle costs 0.4 0.1 0.1 0.6 / Programme Initiatives 3.8 0.5 0.4 0.9 5.6 / Finance costs 0.2 -0.2 0 / Crown Agents 0.7 0.2 0.9 / Total funds available 45.9 1.7 3.1 8.9 0.3 0.5 60.4 / Total Additional requested = £14.5 m / Annex 2 sets out the scale-up summary, including an overview of programme funding, outcomes and results matrix for additional funding. / Tables 5 and 6 below outline a total proposed Programme Budget for the remaining years. Table 5 gives a broad outline, whilst Table 6 details the allocation of technical assistance by state. Both Tables give provisional allocations for each of the forward years to 2015/16, all programmed to the SPARC Programme year August to July. / Table 5: Total Proposed Budget for remaining years 2012-2015, including Scale Up (all in £m) / Outline Programme Budget 2012/ / 13 2013/ / 14 2014/ / 15 2015/ / 16 Total / Programme technical assistance State and federal work plan expenditure (see table below for further details.) 5.5 5 4.5 15 / Operational costs Abuja & State office costs (incl. Security) 5.4 4.6 5 0.4 15.4 / Total £m Total funds available 10.9 9.6 9.5 0.4 30.4 / Table 6: Indicative Allocation of Programme Technical Assistance Funds for remaining years 2012-2015, including scale-up / Allocation of Programme technical assistance funds 2012/13 £m 2013/14 £m 2014/15 £m 2015/16 £m Total £m / New States Katsina 0.23 0.22 0.21 0.66 / Zamfara 0.23 0.22 0.21 0.66 / Niger 0.23 0.22 0.21 0.66 / Anamabra 0.23 0.22 0.21 0.66 / Yobe 0.34 0.33 0.31 0.98 / Existing States: extension Enugu 0.34 0.33 0.31 0.98 / Kaduna 0.34 0.33 0.31 0.98 / Kano 0.34 0.33 0.31 0.98 / Existing States: Scale up & extension Jigawa 0.70 0.64 0.64 1.98 / Lagos 0.70 0.64 0.64 1.98 / Federal Component Federal 0.80 0.64 0.64 2.08 / Others Knowledge Management 0.4 0.4 0.2 1 / PDG & STL 0.5 0.4 0.1 1 / Monitoring & Evaluation 0.2 0.2 0.4 / Total 5.60 5.10 4.30 0 15 / Independent Monitoring and Evaluation Programme (IMEP) / This business case also requests an additional £2m to increase the scope of the Independent Monitoring and Evaluation Programme (IMEP), which provides independent monitoring and evaluation to all SLPs, including SPARC. The additional funding to IMEP is contracted separately to that of SPARC funding, and will increase the overall budget available for IMEP from £7.3m to £9.3m.This increase is needed to cover overall SLP expansion, to improve the quality of a key survey for the SLPs, and to allow more rigorous monitoring and evaluation of all SLPs. (Please see section 4). The table 7 below sets out the total new IMEP programme funding, including the £2m additional proposed funding. IMEP was originally approved as a sub component of the SLPs, and is administered as a separate budget line. / Table 7: Total IMEP Budget, including £2m additional proposed funding / Spend until July 2012 Proposed spend 2012/13-2016/17 Total / To March 2010 To / 2011/ / 2012 To / July 2012 2012/ / 13 2013/14 2014/15 2015/16 2016/17 / Core delivery costs £211, / 620 £976, / 548 £297, / 721 £1,025,000 £1,480,000 £1,751, / 000 £1,412,000 £500,000 £7.654m / Project admin costs £46,453 £214, / 364 £64, / 629 £225, / 000 £324,900 £384, / 300 £288,000 £110,000 £1.658m / Total £0.258m £1,191m £0.362m £1.250m £1.804m £2.135m £1.7m £0.610m £9.3m
B. How will it be funded: capital/programme/admin? / The programme will be funded from programme resources and has been budgeted for in the Operational Plan for DFID Nigeria. / There are no contingent or actual liabilities.
C. How will funds be paid out? / All programme funds will be managed by the lead service provider. The contracted lead service provider will be reimbursed monthly in arrears on satisfactory performance and in accordance with contract terms and conditions.
D. What is the assessment of financial risk and fraud? / DFID will continue to conduct an independent annual audit of the programme. Assessment of the probability of financial risk and fraud is generally low. However, probability of reduced financial management oversight and monitoring is significantly increased in areas where complete audits may not be possible due to security concerns. However, SPARC head office is located in Abuja where majority of management and financial systems coordination takes place. / SPARC funds will not be passed directly through government and therefore reduces this potential fiduciary risk.
E. How will expenditure be monitored, reported, and accounted for? / Monitoring and accounting of expenditure will take place using the DFID’s ARIES financial management system and standard DFID Nigeria procedures for inspecting invoices to ensure VfM and compliance with agreed fees and reimbursement costs. DFID will rely on: / Quarterly progress reports covering programme and financial issues / Year-end statement of actual expenditure / Independent annual audits of the programme / Monthly invoice checks before payment. / Quarterly narrative and financial progress reports to DFID will include reports against the logical framework and agreed results. Expenditure will be monitored/validated against quarterly financial and progress reports. Progress and financial reports will be submitted within 15 calendar days of the end of each quarter. / DFID will conduct annual financial audits of the programme and ensure that SPARC maintain up to date asset registers. DFID will decide on the disposal of assets at the end of the programme.
[39] Note that the additional financial support in 2014/15 is relatively high – this is because this is the main extension year, and that the following year is very low, as it is a partial year to expected programme end.
[40] To cover any possible contingency (e.g. related to additional possible security costs), approval is sought for an additional £0.5m.

Management Case

A. What are the Management Arrangements for implementing the intervention? / Project management is primarily the responsibility of SPARC and the service providers, but with close collaboration between them and the DFID Governance Adviser. Technical coordination and direction of the programme will be managed by DFID Nigeria’s Governance Adviser. Project management support is provided by a Programme Officer within the Governance and Social Development (GSD) Team. / SPARC is part of DFID Nigeria’s State Level suite of programmes. Oversight is also provided by a DFID Steering Committee for the SLPs which meets on a quarterly basis and DFID State Representatives liaise closely with SPARC at state level. DFID State Representatives have been appointed since late 2011 to represent DFID in DFID focus states, to ensure robust political dialogue and engagement with state governments and other counterparts; as well as to coordinate and assist SLPs in their work. / SPARC has State Team Leaders (STLs) in each state who manage the programme and there are quarterly meetings of all SLP STLs at state level to ensure coordination between the different programmes.
B. What are the risks and how these will be managed? / The planned expansion of SPARC activities carries some risks. Given the challenging reform and security environment in Nigeria, particularly in the North, the overall risk rating for the programme is high. The main risks, and the plans to manage and mitigate them, are set out below. / Deteriorating security conditions make it very difficult to work in most parts of Northern Nigeria. / To mitigate the risk that security constrains programme delivery, SPARC is engaging a specialist Security Adviser to help set up its security management system and devise a business continuity plan. It is also engaging a full time Security and Logistics Manager to ensure that procedures are complied with at all times. DFID has also set up a risk management office to advice on risk and appropriate risk mitigation measures. / In addition to managing security risks for programme staff and partners, the programme also adapts conflict sensitivity in its approach. This means for example, that SPARC continues to ensure programme has a level of acceptance among local partners and populations; it works to maintain a strong credibility as an independent provider of high-quality technical assistance; and it aims to ensure that it does no harm by making beneficiaries more vulnerable to attacks as being seen as linked to a “Western agenda”. / Vested interests and weak political commitment impede reforms. Elections lead to a loss of momentum. / There could be insufficient political will, for example in Zamfara, Katsina and Yobe, for the reforms envisaged by the programme to take hold. 2015 general elections in Nigeria could lead to a loss of focus or momentum in the last year of the programme – and there are only three Governors who are in their first term out of the ten states – Kaduna; Zamfara and Yobe. 2014 elections in Anambra could lead to a loss of focus or momentum in that state. / To manage the risk of insufficient political will in some states, SPARC has developed a system through which it can assess the existence of political commitment to reform. The system called ‘Measures of Political Commitment’ entails an analysis of various sources of information to inform SPARC about the likelihood of success of various initiatives. This will inform the planning of work and the deployment of resources to ensure that there is no wastage of money and time on unproductive endeavours. Additionally, SPARC has is making arrangements to agree its reform programmes with various states. This will set out exactly what SPARC expects of them and what they can expect from SPARC. This sort of partnership agreement will help to ensure that there is no mismatch of expectations. Lastly, DFID has appointed State Representatives that will help to improve political engagement with state governments. / To mitigate the risk of loss of focus or momentum as a result of elections, SPARC intends to do its most substantive reform work between mid-2012 and mid-2014. This means that the most strategic interventions can take place while the environment for reform is still conducive. The last year of SPARC will then focus more on continuing & finalizing the already initiated reforms; learning and documenting lessons; policy engagement and preparing the ground for any possible follow-on programme. An additional emphasis will be placed on attempting to embed reform for sustainability during a transition of administration post elections. / The risks and assumptions concerning specific programme activities are set out in state level logical frameworks, as well as in the programme-level log frame. / Table 8: Risk matrix / Risk description Probability (3=high 1=low) Impact (3=high 1=low) Mitigation strategies for Programme and DFID Residual risk / Increased insecurity affects ability to implement the project. 3 3 SPARC: In response to increasing security concerns in the North, enforces updated security procedures by hiring a full time security manager. Modifies ways of working. / DFID: State representatives, advisers and DFID risk management office (RMO) proactively address potential security risks and mitigation responses. High / Vested interests and weak political commitment impede reforms. / Elections lead to a loss of momentum. 3 3 SPARC: Focuses on issues where there is demand for change; supports reformers; modifies approach depending on political environment. Intends to do most of substantive reform work before the general elections in 2015, while ensuring continued engagement over the elections. / DFID: Undertakes high level policy dialogue and advocacy; maintains close working relationships with partners on political analysis and response. Medium / Programme impact not sustained. 1 3 SPARC: Designs, reviews and amends reform plans in the light of capacity and reform willingness. Supports the institutionalisation of reform, where feasible, and advocates peer-review through the Nigerian Governors Forum. / DFID: Undertakes political and policy advocacy work mainly through DFID State representatives to ensure reforms are embedded on a sustainable basis. Understands governance reform needs long-term approach. Medium / Weak DFID’s State Level Programme (SLP/ other DFID programmes) coordination 1 3 SPARC: Works closely with DFID State Representatives and other DFID programmes in each state, seeking synergies and practical ways of cooperation to work towards the shared goal. / DFID: Ensures effective but strategic coordination mechanisms/processes between SLPs and other DFID programmes through SLP core group and other appropriate mechanisms. Medium / Fiduciary risk. 3 SPARC: Supports comprehensive and structured PFM reform, ensures good quality financial management controls and monitoring of financial implementation in programming. / DFID: Funds mostly TA which is not provided directly to state government. Undertakes regular financial audits and reviews. Low
C. What conditions apply (for financial aid only)? / N/A
D. How will progress and results be monitored, measured and evaluated? / Programme results will be monitored by the DFID programme team against the programme logframe. SPARC’s performance will also be assessed by internal monitoring of the programme; by independent monitoring through annual and mid-term reviews; and by an independent end-of-programme evaluation. / Internal Programme Research / SPARC implemented an annual Research Study in late 2011 and will continue to conduct an annual research over the remaining years of the programme, with an adjusted approach as required. The primary objective of this research will be to systematically review performance and provide lessons to decision-makers at both state and programme levels, as part of internal reprioritisation and adjustment of strategies, implementation plans and budgets. / The focus for the study will be to assess performance at the outcome and impact levels of state and programme logframes. In the context of SPARC’s operations, outcomes are defined as: “the responses and changes in the behaviour of state government, such as the adoption of governance reforms that are a direct consequence of SPARC’s technical and other support”. Here there is an important distinction made between the programme outputs (the technical assistance and other support provided by SPARC) and the adoption, use and institutionalisation of these outputs by the state government as part of the reform process. / The study will consist of an evaluative and systematic review of the evidence base and will contribute to internal learning and the better articulation of SPARC’s performance story. / Specific objectives of the study will include: / 1. To document where SPARC supported work has resulted, or is starting to result, in improvements in the efficiency and effectiveness with which supported state governments’ use public resources. / 2. As part of this, to provide a more evaluative basis for SPARC’s reported performance against the programme logframe. / 3. To selectively assess the efficiency and effectiveness with which SPARC has used resources to deliver outputs and achieve results. / The key questions which the study will seek to answer are: / What evidence is there of improved state effectiveness and efficiency? / What evidence is there of SPARC programme effectiveness? / What contribution has the SPARC programme made to state effectiveness and efficiency? / How can SPARC be assessed in terms of value for money? / How could SPARC M&E and MIS arrangements be improved to better support the programme? / How can political economy analysis be better used to support the programme? / The SPARC internal research will also feed into the independent reviews and evaluations undertaken by Independent Monitoring and Evaluation Programme (IMEP). / Independent evaluation / As with all the state level programmes (SLPs), the SPARC programme will be subject to annual Independent reviews, conducted by a separate shared service provider; the Independent Monitoring and Evaluation Programme (IMEP). IMEP will also provide an independent evaluation of the SLPs at the end of the programmes. / DFID Nigeria is intending to do an evaluation on both individual programmes and the suite as a whole. The original conceptualisation of the SLPs was for a suite of programmes that would act synergistically in each state to increase their collective impact. It is important therefore that they are evaluated both as individual programmes and against the collective impact that was envisioned for them. It has been chosen as candidate for evaluation using the criteria in the DFID Nigeria evaluation strategy. The principle rationale for this evaluation is to provide accountability, both to the UK taxpayer and the Government of Nigeria, for the £400 million that has been allocated for these programmes. It will also identify key lessons learnt to inform future programme development in Nigeria. / The primary stakeholders for this evaluation are DFID and the Federal Government of Nigeria. Additional stakeholders include state governments, local government authorities, beneficiaries and the SLPs themselves. / IMEP will act as an impartial evaluator in the evaluation of the SLPs. The Nigerian National Planning Commission will be invited to participate/observe, as it has done on previous evaluations. The evaluation will seek the views of a variety of stakeholders during implementation and on the draft report, and the final conclusions and report will be publically available and disseminated in an accessible format. / The evaluation questions are currently being consulted on. The evaluations will be undertaken against the OECD Development Assistance Framework framework, assessing the programmes against the standard criteria of relevance, effectiveness, efficiency, impact and sustainability. In the light of need to strengthen the evidence base across the suit of SLPs, the key evaluation questions are expected to focus on: / 1. Is there evidence that the suite of SLPs has had its anticipated impact? / 2. Do the changes appear to be sustainable? / 3. In the light of these two findings, does expenditure on the suite represent reasonable value for money? / Given the focus within the evaluation on impact, options for understanding the counterfactual (what would happen in the absence of the SLPs) are being explored. The counterfactual will be partial due to practical and technical limitations. / The evaluation will draw on and synthesise information from a number of sources. These will include the following, listed in order of importance: / IMEP final reviews of the each SLP, drawing on SLPs own internal reporting and evaluations the SLPs, and high quality well structure final reviews of each SLP. / A critical review and compilation of the SLP suite framework indicators and their trends in the SLP states. / A comparison with summary data for selected comparison states / A structured qualitative field study based around health and education facilities / A possible quantitative impact analysis based on household survey data (the Citizen’s Perception Survey) / There a number of limitations to the assessment of impact of both the individual SLPs and the suite of programmes. For example, the detailed consideration of how to conduct impact assessment has only started part-way through the implementation of the SLPs, so there was no opportunity to build evaluation strategies into the beginning of the programmes. The SLP suite MTR (in 2011) was the first attempt to develop an explicit, overall intervention logic for the suite of programme, and it has been further revised in this document following consultation with the SLPs and DFID. There are also some questions about the availability and/or quality of some of the baseline data, and some of the baselines will in practice need to be taken from the mid-point of the programmes. / The budget for whole SLP evaluation is currently being negotiated, and will affect the methodological options in the final evaluation. The current proposal in the region of £250,000. / Full evaluation questions, the SLP theory of change, and the methodological options being considered can be found in the draft design and approach paper (Quest number 364 2396). / Increase in IMEP scope / IMEPs outcome is “to increase the individual and collective performance and impact of the State Level / Programmes through the provision of independent monitoring and evaluation information and analysis to DFID and the federal and state governments of Nigeria”. / Its outputs are to: / • Conduct independent annual and mid-term reviews, and completion evaluations (including impact) of the individual SLPs; / • Quality assurance of the M&E systems of the individual SLPs including validating monitoring data, and providing technical advice on system development; / • Assess the effectiveness and efficiency with which the SLPs work together at state and federal levels, and the collective performance and impact of the combined ‘suite’ of SLPs; / • Support the development of the capacity of the national and state SLP counterparts in the area of Monitoring and Evaluation. / IMEP’s current TORs are attached as Annex 5. / IMEP was approved as a sub-component of the original SLP suite approval package in 2008. Funding for the current budget for IMEP comes from both SPARC and ESSPIN. £2m is requested in this business case to increase the scope of the IMEP. This funding is completely separate to that of additional funding for SPARC (£14.5m). The additional funding to IMEP will increase the overall budget available for IMEP from £7.3m to £9.3m.This increase is needed to cover overall SLP expansion, to improve the quality of a key survey for the SLPs, and to allow more rigorous monitoring and evaluation of all SLPs. Please see a separate table in the financial case on the requested IMEP funding.
Logframe / A summary SPARC logframe is attached in Annex 1. A complete logframe is available in Quest. / Quest No of logframe for this intervention: 3600831 & 3600859

References