Annual Review – post April 2018

Title: Special Development Fund 9th Replenishment
Programme Value £ (full life): £18,000,000		Review Date: 22/11/2019
Programme Code: 204675	Start Date: 29/11/2017	End Date: / 01/07/2022

Summary of Programme Performance
Year	2017	2018
Programme Score	A	A
Risk Rating	Minor	Minor

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204675
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204675

A. Summary and Overview (1-2 pages)

Description of programme

The 9th replenishment of the Special Development Fund (SDF 9) will contribute to economic and social development in the Caribbean’s poorest countries through support to core sectors that contribute to the achievement of the Sustainable Development Goals (SDGs): transport, education, water and sanitation, agriculture, climate change/environment and inclusiveness – leave no one behind, jobs and prosperity.

DFID will contribute up to £18 million (including up to £4.5 million as a performance-based tranche for 2020) towards the replenishment of SDF 9, running from 2017-2020. The SDF is the Caribbean Development Bank’s (CDB) concessional mechanism (soft loans below market rates, grants and technical assistance) supporting the most vulnerable and poorest people in the Caribbean region.

The SDF supports projects with a focus on basic social infrastructure such as roads and electricity, vocational training centres and schools, agriculture and climate change resilience (e.g. flood and hurricane protection) as well as support to poverty reduction through its Basic Needs Trust Fund (BNTF), which has focus on local vulnerable communities and gender equality. SDF has grant funding “set asides” for Haiti ($45 m), the Basic Needs Trust Fund (BNTF $45 m), disaster responses ($3 m) and regional collaboration ($4 m).

The CDB is expected to deliver both direct development results through the SDF 9 and internal reforms agreed as part of the SDF replenishment negotiations. These reforms, if implemented as planned, should strengthen its efficiency and effectiveness leading to improved performance during the SDF 9 period and beyond. The Bank has outlined the expected development outputs and results offer for the SDF 9 period 2017-2020. Examples include:
[note] Source: Replenishment of the Resources of the Special Development Fund Unified (SDF 9) Resolution and Report of Contributors, draft May 2016.

- 222 km of roads built or upgraded,
- 198,900 students benefiting from improved educational facilities and provision,
- 285 small businesses benefiting from credit,
- 248,768 beneficiaries of community citizen security interventions and
- 18,400 households with access to improved sanitation and water supplies

Summary supporting narrative for the overall score in this review

2018 saw the CDB deliver strong results in many areas but fall short in others. There was widespread success with regards the Bank’s operational quality and portfolio performance as well as its organisational effectiveness. There was notable progress in areas where the CDB has long struggled, including with regards the completion of Project Completion Reports (PCRs). Progress from previous years with regards administrative expenses was consolidated and the CDB continued to deliver considerably more approvals supporting climate change than was targeted. This excellent performance led to two of outputs, representing 50% of the overall weighting, scoring A+.
[note] Results taken from CDB Development Effectiveness Review 2018 - https://www.caribank.org/sites/default/files/publication-resources/DER-Report-2018-hiRez-final.pdf

However, this strong performance at the corporate level was matched by poor performance in the relation to the delivery of outputs, where a C was recorded. Whilst the CDB did perform better against many of the other 36 output indicators it reports on, there is still a clear need for the CDB to focus on getting the basics of project delivery right and to boost capacity both internally and within its members. The improvements in corporate performance must be translated into improvements in results; this will take time but is the crucial area where the CDB must focus in the near future.

Overall the strong corporate performance across outputs 3 and 4 is balanced out by the far weaker score for delivery of results under output 1. The two scores of A+, one of A and one of C result in an A overall, rather than an A+, which is the most common individual output score.

The other concern regarding the SDF is the under commitment of resources, where, at mid-term only 36% of resources had been committed. Whilst it is not uncommon for majority of resources to be committed during the second half of the replenishment the scale of this under commitment is risky. DFID raised this at the CDB’s Annual Meeting in June 2019 and the CDB provided assurance that it has a strong pipeline of projects and that it will closely monitor the SDF commitments. We will take this into consideration when discussing future replenishments of the SDF.

Recommendations for the year ahead

Over the year ahead the CDB must focus on delivering outputs. In order to do this is must identify and tackle capacity constraints both internally and within in borrowing members. Work to streamline internal processes and boost capacity is ongoing and will be stepped-up through the Transformation Programme. DFID should continue to engage in this and encourage the CDB to translate the progress on corporate performance into development outputs, outcomes and inputs.

With regards borrower capacity the CDB should consider how it can better use Technical Assistance to aid project design and delivery, but also to build sustainable borrower capacity. This should be a focus for DFID in future discussions around SDF replenishment.

DFID should also consider how the CDB’s new Strategic Plan 2020-2024 and Corporate Results Framework should be best reflected in the logframe for SDF 9. This may mean the addition of new priority indicators.
## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Project Outputs
Output number per LF		1	Output Score	C
Impact weighting (%):		30	Impact weighting % revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
1.1 Students benefiting from improved physical classrooms (Performance Tranche Indicator)	Planned: 66,000, / Achieved: 57,227	Target moderately not met
1.2 Land improved through irrigation, drainage, and/or flood management (hectares - cumulative)	Planned: 0, / Achieved: 0	No planned achievement in 2018
1.3 Energy: Conventional or renewable power generation capacity installed (MW- cumulative)	Planned: 0.02, / Achieved: 0	Target not met
1.4 Households with access to improved sanitation and water supply (number - cumulative)	Planned: 2,700 / Achieved: 30	Target substantially not met

Provide supporting narrative for the score

The Bank failed to hit any of the targets where they planned to deliver outputs in 2018, one by a substantial amount. Overall this merits an C.

Indicator 1.1 In 2018, the SDF supported the construction of 72 additional classrooms and provision of the necessary equipment and furniture, tools, and materials, bringing the total to 586 classrooms since the start of the strategic planning period. These initiatives have benefitted and continue to benefit about 128,445 students (including 57,227 students in 2018). This means that the CDB are well on track to hit the target of the performance tranche, despite slightly below target performance in 2018.

Indicator 1.2 The Bank did not plan to complete any projects in land improvements in 2018, and no projects from 2017 overran.

Indicator 1.3 The Bank did not complete any projects in energy in 2018, and no projects from 2017 overran. This is compared to a target of 0.02.I. In 2017, the Bank marginally overachieved compared to the target. CDB continued to work to in the energy sector to promote energy efficiency installing 400 km of transmission and distribution lines and saving of energy 4.2 GWh as a result of interventions in energy efficiency and renewable energy

Indicator 1.4 During 2018, approximately 2.6 km of water supply lines were installed or upgraded in The Bahamas. As a result, the quality of life of 30 households was improved through access to safe and reliable water and sanitation facilities. The Bank has been making reasonable progress on this compared to their overall targets and are 66% of the way to achieving their goal for 2015-2019 period.

Lessons identified this year, and recommendations for the year ahead linked to this output

Overall the CDB delivers and reports results against 32 different indicators and selecting any four always risks presenting a narrow view. Of these 32 indicators 16 were more than 75% of the way to achieving the overall goal for the end of the Strategic Plan period, in 2019, and 10 had already met or exceeded the target. The four indicators selected for this review, whilst representing priority areas, do not reflect the good progress of the Bank’s entire operations. DFID should consider how it can better reflect the breath of CDB delivery in its results monitoring, perhaps through a composite indicator.

That said, the CDB needs to focus on delivery as a priority. Efficient and effective delivery of outputs such as these selected indicators should be the minimum expectation of the CDB. In order to achieve this, the CDB must focus on building capacity, both internally and within its borrowers. This has been DFID’s key message throughout the discussions of the CDB’s new Strategic Plan 2020-2024 and will continue to be a key message in future SDF replenishment discussions.

For its part, the CDB is implementing a “Transformation Programme” to boost its efficiency and effectiveness. DFID is supportive of this endeavour and will continue to closely monitor its progress.

Output Title	Strategic Focus
Output number per LF		2	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
2.1 Approved projects with a gender-specific or gender mainstreamed rating (as a % of total projects)	Target: 76%, / Achieved: 74%	Target moderately not met
2.2 Approvals supporting environment, renewable energy/energy efficiency and climate change (as a % of total financing)	Target:16%-24%, / Achieved: 55%	Target substantially exceeded
2.3 Technical Assistance (TA) approvals supporting private sector development and PPPs (as a % of total TA financing)	Target: 6%-10%, / Achieved: 4%	Target moderately not met
2.4 TA approvals supporting regional cooperation and integration (as a % of total TA financing)	Target: 40%-50%, / Achieved: 36%	Target moderately not met
2.5 Financing directed to less developed BMCs (% 3-year average)	Target: ≥51%, / Achieved: 77%	Target substantially exceeded

Briefly describe the output and provide supporting narrative for the score

The CDB has substantially exceeded the targets for two indicators but has moderately not met three others. On balance the scale of the overperformance on two indicators balances the slight underperformance on the others; warranting an A overall for this output. The use of ranges for these indicators makes sense across the period of replenishment as the makeup of the portfolio will inevitably fluctuate over the years, driven by many factors including project demand. The range is intended to represent a reasonable lower bound and exceeding the upper bound of the range will be looked upon favourably.

Output 2.1 The CDB agreed stretching targets which go beyond those in their corporate results framework during the development of the SDF 9 logframe, the target, for 2019, in the CDB’s corporate results framework is a mere 40%. Whilst it is disappointing to see a fall in the percentage of projects with a gender mainstreamed rating, the CDB is starting at a high baseline and the fall has been very small.

In 2017, the CDB introduced a new indicator, “Projects reporting on gender results during implementation” to monitor effective supervision of gender results and activities, as well as effective integration of gender design features into project implementation plans. This was not added to the logframe as the CDB is yet to begin reporting on it due to the transfer to a new results reporting system.

Output 2.2 The CDB has substantially increased its approvals supporting environment, renewable energy/energy efficiency and climate change. At 55% this is now well above the 16-24% target agreed in the logframe (and even further above the 8-12% target in the CDB’s Corporate Results Framework) but below the 71% in 2017.

Output 2.3 The CDB just missed the target. However, as the target becomes more stretching in years to come it will be important that the CDB also expands its work. The new Strategic Plan 2020-2024 should help accelerate progress.

Output 2.4 At 36% the proportion of TA approvals supporting Regional Cooperation and Integration (RCI) was just outside the target range and down on the 47% in 2017.

Output 2.5 in 2018 the CDB directed 77% of financing to less developed BMCs, down from 81% in 2018. This is well above the target. The CDB defines its less developed BMCs in line with CARICOM’s Revised Treaty. These countries are Belize, Dominica, Grenada, Guyana, Haiti, Montserrat, St. Kitts and Nevis, Saint Lucia, and St. Vincent and the Grenadines.  Of these Haiti is by far the largest recipient. It is encouraging that the SDF is directing such a large percentage of its resources to the poorest members of the bank.

Lessons identified this year, and recommendations for the year ahead linked to this output

CDB’s increased focus on climate change related activities is welcome, however it means that the current target is too easy to achieve. DFID should consider increasing the target to a more challenging, yet reasonable, level for the next Annual Review.

One area where the CDB is consistently struggling to meet the target is in relation to the private sector. DFID has encouraged the CDB to increase its ambition and capacity with regards private sector as part of the discussions around its Strategic Plan 2020-2024. DFID should continue to engage with the CDB on this issue.

Output Title	Operational quality, effective portfolio performance and resource allocations
Output number per LF		3	Output Score	A+
Impact weighting (%):		30	Impact weighting % revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
3.1 Portfolio performance rating for implementation (% rated excellent to satisfactory)	Target: 90%, / Achieved: 98%	Target substantially exceeded
3.2 PCRs prepared/completed within two years of project completion (%)	Target: 65%, / Achieved: 95%	Target substantially exceeded
3.3 Average time taken from appraisal mission to approval (months)	Target: 3.5 months, / Achieved: 3.5 months	Target met
3.4 Average time taken from approval to first disbursement (months)	Target: 8 months, / Achieved: 4 months	Target substantially exceeded
3.5 Average length of project extension (months)	Target: 26 months, / Achieved: 33 months	Target not met

Provide supporting narrative for the score

The CDB has generally performed well across output three; only indicator 3.5 not meeting the target and three of the five indicators performing substantially better than the target. On balance this warrants an A+.

Output 3.1 The CDB once again exceeded the target for portfolio performance under implementation, with 98% of operations rated excellent to satisfactory. Since 2013 this score has never been below 95%.

Output 3.2 The CDB has substantially exceeded the target on PCR completion for the first time in many years, reaching 95% and up from 36% in 2017.Following the introduction of the performance tranche at the beginning of 2017, the CDB made improving the PCR completion rate a corporate priority. Unfortunately, due to the 2017 Hurricane season progress was initially slow. However, in 2018 this ambition has been realised. This provides some evidence of the SDF performance tranche driving improved performance.

DFID should encourage the CDB to maintain this strong performance as the target becomes rapidly more challenging over the course of the SDF 9 period, reaching 95% in 2020.

Output 3.3 In 2018 the CDB hit the approvals target of 3.5 months. This slightly down on the extraordinarily fast 1.6 months in 2017, though it should be noted that this was anomalous and driven by the Bank’s rapid response to Hurricanes Irma and Maria.

Output 3.4 The CDB met the 2018 target of months between approval first disbursement. Halving the time taken in 2017 and consolidating the improvement on 2016, where disbursement took 32.2 months. This improved performance is most welcome but DFID should continue to encourage the CDB to prioritise disbursement.

Output 3.5 Project extensions have been a major issue for the CDB over the years. In 2017 the average length of extension fell to 26 months, exceeding the target, however this year the length crept back up to 33 months. Though the number of projects under extension continued to fall, down to 45%. The Bank must work on improving both internal processes and borrower capacity to ensure that project extensions are minimised.
Lessons identified this year, and recommendations for the year ahead linked to this output

CDB’s excellent performance under output 3 should be welcomed. However, it is important that good progress in these areas is translated into the delivery of greater outputs, outcomes and, ultimately, impacts.

The strong performance also requires consolidation to ensure that targets, some of which increase in difficulty over the remainder of the SDF 9 period, continue to be met. Where targets are comfortably met year-in year-out, DFID should consider how to improve them in order to extract greater information as part of a review of the logframe following this Annual Review.

Output Title	Organisational effectiveness of CDB (administration and human resources)
Output number per LF		4	Output Score	A+
Impact weighting (%):		20	Impact weighting % revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
4.1 Administrative expenses per million US$ of project disbursements (3-year average) $000s	Target: Below 167, / Achieved: 140	Target substantially exceeded
4.2 Ratio of professional staff to support/administrative staff	Target: 1.64:1, / Achieved: 1.91:1	Target substantially exceeded
4.3 Vacancy rate at management and professional levels (%)	Target: ≤7%, / Achieved: 4%	Target substantially exceeded
4.4 Staff in management positions who are women (%)	Target: 42%-52%, / Achieved: 40%	Target moderately not met

Provide supporting narrative for the score

The second year of the SDF 9 period has seen the CDB perform well, three of four targets were substantially exceeded and the only target which was not met was missed, and by a small margin. This improved performance warrants an A+ score.

Output 4.1 Administrative expenses per million US$ of project disbursements were comfortably below the target at $140,000. Internally the CDB’s only target is to reduce administrative expenses below the 2014 baseline of $181,000. The target in the logframe to reduce administrative expenses below the 2015 baseline, of $167,000, is more challenging.

Output 4.2 The CDB have made excellent progress in improving the ratio of professional staff to support/administrative staff over the last 12 months, increasing from 1.78 to 1.91. This exceeds the target for 2018 and the increasingly challenging target of 1.72:1 in 2020. It is excellent to see recent progress consolidated.

Output 4.3 The CDB continue to maintain a low vacancy rate at management levels. Given the small size of the CDB it is important that it maintains a low vacancy rate as it has little room to carry gaps in staffing, particularly at a senior level.

Output 4.4 The Bank has highlighted that indicator 4.4 is not intended to represent a quota, but rather check that adequate consideration is given to gender equality at managerial levels when recruiting or considering promotions. At 40% compared with 44% recorded in 2017 shows a slight decrease, slipping outside of the target range for 2017.

Lessons identified this year, and recommendations for the year ahead linked to this output

The excellent progress under output 4 is very welcome and the focus should be on consolidation. Once progress has been consolidated DFID should engage with the CDB to consider the appropriateness of more stretching targets, likely over the SDF 10 period. Lower targets in these areas may not always be appropriate as it is vital that the CDB builds and maintains a quality service.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year

The theory of change for SDF 9 combines both the resources provided for the SDF 9 replenishment and the ongoing engagement with the CDB, through the Board and other channels. It has not changed over the last year and is set out below:

Input
Outputs
Key Assumptions
- Financial contribution
- Policy engagement during negotiations and delivery
- Other development partners provide resources
- Clients continue to engage positively with SDF projects and demand remains high
- Reform led from HQ in Barbados has an impact on ways of working in-country and at HQ
- Reforms are relevant, and do improve the Bank’s ability to deliver results through speedier and more effective project processes
- Projects are resilient to risks arising in country
CDB organisational and operational outputs e.g.

Around $350 m of concessional funding to SDF countries including $45m to Haiti

CDB joins International Aid Transparency Initiative (IATI)

Eradicate poverty and achieve the Caribbean Sustainable Development Goals
- The Bank is capable of having a sustained impact on the sectors and policy areas it programmes in
- There is the political will and capacity in partner countries to ensure bank projects have a sustained impact
- The UK is successful in influencing the shape of SDF 9
- The Bank implements and monitors the agreed organisational and operational changes

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Unfortunately, there is no recent data at the Impact level so it is not possible to say whether or not “Regional progress towards selected Caribbean-specific MDG targets and development outcomes” is on track.

However, there is some evidence of positive results at the outcome level. Of the eight outcome level indicators and sub indicators, six showed improvements over the baseline. Particular areas of success were % of population with access to improved sanitation and net enrolment ratio in basic education: Primary.

The areas where progress slipped were in urban access to improved water sources and female enrolment in secondary education. DFID will continue to emphasise the importance and benefits of girls’ education.

Explain major changes to the logframe in the past year

There have been no major changes to the logframe in the past year

Describe any planned changes to the logframe as a result of this review

This review, at the halfway stage of SDF 9, has highlighted the need for some minor adjustments to the logframe, to update some targets which have been overachieved and to consider how to reflect some of CDB’s good performance in sectors which are not currently measured. As such DFID will review the logframe and agree updates with the CDB before the publication of the next round of results.

The approval of the next Strategic Plan (for 2020-24) and associated corporate results framework update may also give rise to new indicators which it would be helpful to include in the logframe. However, we will ensure that the targets for the period remain appropriate.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year

The overall VfM statement in the SDF 9 Business Case was “The limited analysis possible suggests that the SDF represents VfM in addressing the development needs of the region, particularly in promoting economic development and resilience in the smaller and poorer members where other MDBs do not operate and given the limited capacity of DFID to manage projects directly.”

This year, and in keeping with the statement in the Business Case, SDF 9 has made commitments across several sectors which promote economic development and resilience in eligible countries, including Environmental Sustainability, Climate Change and Sustainable Energy, Regional Cooperation and Private Sector Enabling Environment. The themes of SDF 9 grants can be seen below.

However, 2018 saw lower-than-anticipated levels of commitments under the SDF at mid-term. Total approvals in 2018 amounted to $33.5 mn, compared with $95.9 mn a year earlier. This brings total commitments in the first half of the cycle to $129.4 mn or 36.5% of the approved programme. Performance in 2017was boosted by the one-off allocation of $40 mn for the BNTF, sizeable interventions in Haiti for education and disaster risk management, and to a lesser extent, commitments to support emergency disaster response. Loan commitments were virtually on par with 2017, but nevertheless reflected a subdued outturn mid-way in the cycle.

Also contributing to lower commitments, was the focus by the Bank on project preparation to ensure that interventions once approved can be disbursed more efficiently. Importantly, the Bank working closely with BMCs, has identified a pipeline of projects that will utilise resources available under SDF 9 to support the Bank’s mandate to reduce poverty. DFID will closely monitor SDF 9 commitments to ensure the resources granted by DFID are being used. Progress on commitments will inform any DIFD contributions to the next replenishment of the SDF.

Equity is also a critical pillar of Value for Money. SDF operations promote equity by operating in the countries with the highest poverty levels and working to reduce this poverty and stimulate inclusive growth. The SDF also has a strong focus on gender and delivers strong results; 74% of approved projects have a gender-specific or gender mainstreamed rating and the Bank is soon going to start reporting specifically on the success rates of these projects.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

Despite lower than anticipated commitments in 2018, the SDF continues to meet the value for money statement as set out in the Business Case.

At the portfolio level, the CDB has a geographic and technical remit which greatly complements the work of DFID Caribbean. Delivering through the SDF allows DFID to reach a wider range of countries than it would have otherwise been able to as well as operating at scale in a variety of priority sectors, including infrastructure, health and education. This complements the work of DFID Caribbean.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The SDF 9 Business Case identified risk across six categories:

External Context – The Business Case states that high debt levels in SDF countries could affect the levels of grant vs loan project undertaken by the SDF. These debt levels remain elevated and the risk remains live. The other significant element of external context for the SDF is weather related. In 2018 the Hurricane season was more benign than in 2017. However, there remains a risk that weather-related events could place a strain on SDF resources.

Delivery of Outcomes – SDF 9 performed poorly on its delivery of outputs in 2018. Combined with the lower than anticipated levels of commitments the risk that SDF 9 fails to deliver its expected outcomes has increased. However, the CDB has a strong pipeline of projects and is undertaking a wide range of efforts to boost capacity, both internally and in its members, to ensure that delivery speeds up and outcomes continue to be achieved. There is evidence already that internal processes are speeding up.

Safeguards- The Business Case assessed the CDB as having generally adequate safeguards policy and systems. The recent Central Assurance Assessment concurred with this assessment, finding that the CDB is developing a strong overall framework for preventing, identifying and mitigating safeguarding risks but could benefit from greater ownership at the senior level.

Operational – The Business Case ascribed a low probability to operational risks. The consideration of the Bank’s operational model under the Transformation Programme is important in identifying and mitigating operational risks. This is ongoing.

Fiduciary – The Business Case identified minor/moderate fiduciary risks, noting that fraud on certain projects is always a risk. The CDB has established and is expanding its Office for Integrity, Compliance and Accountability which seeks to strengthen the Bank’s processes and procedures to tackle fraud. 2018 saw ICA expand in terms of both staffing and activities resolving 35 matters and training 158 CDB staff.

Reputational – The Business Case assessed there to be a low reputational risk, whereby CDB projects could be subject to fraud or high-profile mismanagement. This remains a minor risk given the progress above. CDB also has risk mitigation systems in place to manage reputational issues.

The main challenge for the SDF is to increase commitments to meet projected levels and ensure that the maximum amount of donor resources are used to deliver critical projects in the region. Overall the risk rating for SDF 9 is minor.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues

The CDB’s recipient executed delivery model means that it carries out little direct procurement on SDF projects. The Bank provides oversight to ensure that procurement is carried out in accordance with the Bank’s procurement guidelines and the terms of the relevant financing agreement between the recipient and CDB. Further details on the CDB’s procurement process can be found in the 2018 Central Assurance Assessment, which found that despite good policies and procedures the CDB is lacking in expert staff capacity to engage in every project. Limited internal resource means the CDB must work to improve the capacity of its borrowers, an agenda which is increasingly central to the Bank’s work.
[note] Vault ID 31063886

DFID has deposited the first three Promissory Notes of £4,500,000 each as per the agreed schedule.

Date of last narrative financial report(s)	08/10/2019
Date of last audited annual statement (s)	05/06/2019

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

The Bank has good sources of evidence, including the Annual Development Effectiveness Reviews, the Annual Report, and the SDF Annual Report. Data collection however continues to be weak in borrowing countries where capacity remains weak overall. The Bank aims to conduct self-evaluations on all projects, which are verified regularly through its independent evaluation department. No DFID specific evaluations were conducted during the reporting period.

The CDB has made substantial improvements in its completion rate for PCRs, something which they have struggled with in previous years. This will help the Bank to develop a deeper understanding of its strengths and weaknesses, common challenges within its projects and solutions which are effective. This will allow the Bank to become an organisation which learns, hopefully improving its projects as a result.

Evidence

The CDB’s Office of Independent Evaluation (OIE) is the main source of independent evaluation and evidence with the Bank. In 2018, the its work focused on reviewing the Bank’s work responding to natural disasters, following the devastation brought by the 2017 Hurricane Season. This entailed:

- Validating Project Completion Reports (PCRs) for four Rehabilitation/Reconstruction Loans and five Immediate Response Loans
- Assessing CDB’s Disaster Management Strategy and Operational Guidelines (DiMSOG).

Going forward, the Bank is going to increase its support to preparatory and proactive measures that build resilience to the expected increased incidence of climate change induced hazards. There is evidence that the Bank is moving in this direction, through some of its recent PBL lending which encourages good policy and institutional measures in the area of disaster risk management. The next iteration of the DiMSOG will place more emphasis in this area, as well as on the intersection with the Bank’s recently approved Climate Resilience Strategy.

Learning

As part of the preparations for updating its Strategic Plan the CDB commissioned a “perceptions survey”. This survey engaged with a wide variety of CDB stakeholders and informed the design of the Strategic Plan 2020-2024. This was a valuable exercise which helped the Bank to understand how it was viewed by its stakeholders and where it needs to improve.

Much of the learning in this survey, and the SDF 9 Mid-Term Review, will be valuable for the Bank when thinking about future replenishments of the SDF. DFID should encourage the Bank to ensure that it draws on this evidence, and evidence from the SDF 9 Annual Report and the Office of Independent Evaluation when designing future iterations of the SDF.

Progress on recommendations from previous reviews

Recommendations from last year concentrate on two main ideas for DFID to pursue through the Board and from HQ.

1. Maintain pressure on the CDB to improve performance in remaining areas of underperformance
  1. PCR completion remains disappointingly low and as one of the three indicators in the DFID agreed Performance Improvement Plan it is important for the Bank, and DFID, that performance improves dramatically and quickly.
    1. As seen in this review, this pressure has paid off – with a dramatic improvement in PCR completion rates over the last year.
  2. Other targets, such as administrative expenses per $million disbursements only marginally missed the target. However, DFID should continue to encourage better performance
    1. There was also a significant improvement in targets including administrative expenses per $million disbursed. As part of its efforts to streamline its business processes the Bank has improved the ratio of professional staff to support staff, which contributes to lower administrative expenses.

1. Monitor the appropriateness of targets
  1. Approvals supporting environment, renewable energy/energy efficiency and climate change substantially exceeded the target range in 2017. This was put down to an exceptional year supporting the Hurricane response, but DFID should closely monitor the performance and ensure that target for this indicator remains appropriate in the context of the wider portfolio.
    1. This year saw approvals supporting environment, renewable energy/energy efficiency and climate change substantially exceed the target. DFID should review the logframe and engage with the Bank on the appropriateness of this target following this Annual Review.
  2. Indicators such as portfolio performance rating for implementation have been consistently above target levels for several years, which reduces their value. DFID should explore with the CDB the possibility and desirability of getting further information on the breakdown of projects rated satisfactory, good and excellent. This will enable more detailed analysis of the strengths and weaknesses of the CDB’s portfolio and help inform improved policy making.
    1. This year saw continued excellent performance against the portfolio performance targets. It also saw the development of a new corporate results framework, which DFID engaged with closely. Once this is finalised DFID will consider amendments to the logframe as a whole, including considering indicators which the Bank consistently outperforms.

Gender

In 2018, 74% of CDB’s approved projects had a gender-specific or gender mainstreamed rating. Whilst this is down very slightly from the previous year it is amongst the highest rating across the MDB system. The Bank has also committed to begin reporting on the success rates of these projects.

The Bank also recently completed the review and update of its Gender Equality Policy and Operational Strategy (GEPOS). DFID engaged closely in this process. The updated GEPOS sets out CDB’s high level of ambition on gender, grounded within borrower priorities, to ensure that CDB is working both for and with its members to deliver strong results. Key areas under the GEPOS include a welcome focus on economic empowerment, access to infrastructure services and education.