Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Ghana Oil and Gas for Inclusive Growth (GOGIG)
Programme Value: £17,315,596		Review Date: 30 November 2015
Programme Code: 204330	Contract Date: 12/03/2014 / Start Date: 22/10/2014	End Date: 31/03/2019

Summary of Programme Performance
Year	2014	2015
Programme Score	B	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

This annual review was brought forward to cover the period from March to November 2015 to coincide with the completion of the inception and early delivery phase (Dec 2014 – Sept 2015) and to reset the AR date to be able to in future review a full calendar year of implementation. This review also deliberately runs in parallel with the AR of the Western Region Coastal Foundation (WRCF)[1] programme to identify opportunities for one programme to strengthen the other.
[1] http://devtracker.dfid.gov.uk/projects/GB-1-202476/

The previous annual review covered the prolonged DFID procurement process. Whilst the delay remains in the minds of beneficiaries, the GOGIG team has moved beyond these issues, and is now on schedule against a revised log-frame. The team has learnt lessons, refined the programme approach during inception, and proactively addressed staffing to ensure the right team is in place to deliver the refined programme. Highlights of progress made over the period include:

- Establishing a solid foundation for delivering the programme. The GOGIG team has strengthened relationships with a core number of state and non-state actors, building trust and understanding of the technical and political context. This included facilitating progress on the relevant Memoranda of Understanding (MoUs) between DFID and Government of Ghana (one for each partner institution), and managing a difficult relationship with the Petroleum Commission (PC) caused by an initial misunderstanding of procurement processes.
- Building a healthy and balanced pipeline of projects for the coming months, closely tied to the logframe as well as providing technical assistance to the Ministry of Petroleum (MoP), the PC, and the Mines and Energy Committee of Parliament. All projects have been developed in a consultative manner with the institutions. This has been arduous and iterative – various delays (e.g. due to the change from Non-Budget Financial Aid (NBFA) to a flexible fund modality, the time taken to complete inception, in agreeing the MoUs) have meant that projects have needed to be revised as they became outdated which has required robust relationships with the partners.
- Consolidating the wider GOGIG team to encompass components which had started ahead of contracting the management agent (accountable grants to the Natural Resource Governance Institute (NRGI) & the Africa Centre for Energy Policy (ACEP) and provision of an adviser to MoP).

Key lessons learnt:
During the inception phase it has been clear that the following approaches have been key to the success of the programme to date:
- The need to continually invest in building trust with the state partners, whilst maintaining a neutral position, balancing relationships with political parties, and accountability actors and donors.
- Balancing an approach of being responsive to the expressed priorities of the state partners with a push towards more sector reform focused priorities.
- The need for regular political economy analysis, including beneficiary monitoring and feedback to ensure the programme continues to address priority needs.
- The need for agility and a mix of modalities to harness new opportunities and meet stakeholder requirements – a flexible fund with a project approach is essential for the programme to be flexible and agile, but maintaining indicative annual workplans is also required to fulfil DFID programme management requirements and allow a level of planning by partners.

Summary of recommendations for the next year
- Give consideration to increasing engagement with oil and gas companies, and particularly Ghana National Petroleum Corporation (GNPC), so that GOGIG networks are more sustainably aligned with the political settlement. This should be undertaken by the GOGIG team by July 2016. It will be important that the programme remain flexible to focus on emerging priorities and issues. GOGIG should conduct regular horizons-scanning exercises to explicitly capture this as part of the bi-annual in-depth PEA assessments.
- Consider how to keep balancing GOGIG relationships evenly across political parties, whilst maintaining neutrality (with state partners and accountability actors), so that election outcome will not deplete GOGIG influence. The GOGIG team should develop a strategy by March 2016.
- Foster cross-government strategic communications on key sector issues such as local content. The GOGIG team should pilot this approach on local content by July 2016.
- Continue to invest in linking to other programmes[2]. The Lead Adviser should attend the donor coordination meetings at GRA and consider other ways to improve coordination, such as regular coordination meetings or theme-focused meetings.
  [2] WRCF, but also - Strengthening Transparency Accountability & Responsiveness (STAR http://devtracker.dfid.gov.uk/projects/GB-1-201590/), - Strengthening Action Against Corruption (STAAC http://devtracker.dfid.gov.uk/projects/GB-1-204659/) and - Ghana Revenue Reform Programme (GRRP http://devtracker.dfid.gov.uk/projects/GB-1-204918/)
- The GOGIG team, with support from DFID and in collaboration with the Steerging Committee, should agree on a definition for inclusive growth that is applicable for the programme by March 2016 – clarity on how policy related activities link to inclusive growth, in particular mitigating the risk of conflict but also the elements leading to the ‘resource curse’ phenemonen. Where resources and availability of existing analyses permit, this could be underpinned by conducting a strategic analysis of the development needs of the country (taking a long term view), the needs of the oil and gas sector and ascertaining what areas to prioritise as part of a local content approach.
- The GOGIG team should finalise the logframe in its current form (i.e conduct the baseline activities, agree the definition of inclusive growth and allocate a risk rating to each output) by March 2016. The GOGIG team, with support from the DFID Results Adviser and Lead Adviser, should review the logframe again by July 2016, by which time the programme will have been implemented for sufficient time for the utlity of the logframe to be assessed.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4269520.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4640382.xls

Outline of the programme

DFID Ghana’s Operational Plan identified the oil and gas sector and its governance and management as a key issue - as a potential driver for development which could accelerate graduation from aid, and as a risk if managed poorly. This is addressed with a set of initiatives, including the Ghana Oil and Gas for Inclusive Growth (GOGIG) programme at national level and the Western Region Coastal Foundation (WRCF) in the local context of Ghana’s main oil and gas producing region.

The GOGIG programme is a five year programme commenced in January 2015 to support Ghana in managing its oil and gas resources for inclusive growth. The expected impact of the GOGIG programme is “inclusive economic growth and poverty reduction (through a well-managed Oil & Gas Sector)”.

The expected outcome is “effective management of oil and gas resources”. The programme intends to achieve this outcome through the delivery of four outputs:
Output 1: Regulatory mandate and policy coherence of the oil and gas sector enhanced
Output 2: Systems of oil and gas revenue capture improved
Output 3: Oil and gas revenue management improved
Output 4: Oil and gas sector oversight enhanced

The programme management is organised in three components:
1. A dedicated programme team, contracted to the service provider Oxford Policy Management (OPM), that manages the technical support to government institutions responsible for the governance of oil and gas resources, as well as to accountability actors active in the sector;
2. Two accountable grants managed directly by DFID – to the Natural Resource Governance Institute (NRGI) and the African Centre for Energy Policy (ACEP) for specific advocacy related activities;
3. A dedicated Advisor to the Minister of Petroleum (potentially extended to other institutions with proposals for demand driven technical assistance coming under the first component).

At present GOGIG works with five state institutions – the Petroleum Commission, Ministry of Petroleum (MoP), Ghana Revenue Authority (GRA), Ministry of Finance (MoF) and the Bank of Ghana (BoG) –to deliver its Government-facing objectives. However, based on political economy analyses during the inception phase, as the programme progresses, it has been determined that other relevant institutions within the sector, such as the State-Owned Enterprises (SOEs), will also be purposefully engaged and/or supported as part of overall efforts to improve governance in the sector. The same applies to the accountability component of the programme, where early contacts with other non-state actors have been started.

A key part of GOGIG’s engagement with government is the Steering Committee (SC), which provides an innovative forum for strategic guidance and the representation of government priorities for the programme. The SC consists of a Chair and Vice-Chair who are not from government, but at the same time are deeply respected for their past public service. The other members are senior representatives of the five main government counterpart agencies for GOGIG. Innovatively, there is no DFID involvement. This probably contributes to the fact that the SC carries legitimacy for engagement with official agencies that an outside programme would otherwise lack and has fostered a strong degree of government ownership of the programme objectives, priorities and activities.
The GOGIG programme was also designed to help deliver the G8-Ghana partnership on Extractives launched by President Mahama and the UK Prime Minister in June 2013.

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The programme’s outcome is effective management of oil and gas resources, as measured by improving scores in the Resource Governance Index, the Petroleum-Transparency and Accountability Index, and the value of additional oil revenues captured. It is difficult to assess whether the programme is on track to achieve the outcome by the end of the programme, partly because it is only the first quarter of implementation, and partly because some milestones are yet to be defined as the baseline is currently being set. Significant progress during inception and at output level suggests the outcome will be met, but the next 12 months of implementation will be more informative.

Overall output score and description

Score: A. The main project components are generally on track against a revised logframe, and in some cases performing above expectations (e.g output 4).

Key lessons

See section above.

Key actions

- By March 2016: Seek agreement between the Steering Committee, GOGIG team and DFID on the definition of inclusive growth so that the logframe and workplan can be orientated accordingly;
- By June 2016: Based on clarity of the programme’s interpretation of inclusive growth, ensure that the GOGIG partnership can be consolidated or extended in appropriate ways to engage with actors that will be identified as crucial to the inclusive growth objective. The GOGIG team should draft a paper on this.

Has the logframe been updated since the last review?

Yes, there has been extensive discussion on the logfarme during the course of the inception phase resulting in a revised version. However, further revisions are required. For example, it is recommended to agree at the earliest opportunity the definition of ‘inclusive growth’ with DFID, the programme team and other key stakeholders. This will help set the impact level indicators and inform other logframe revisions. We recommend engaging the DFID Results Adviser, and learning from other logframes of a similar nature. Also, each output requires an individual risk rating and the baseline needs to be assessed. These should be undertaken in the short-term, but a full review of the logframe should then be undertaken once implementation has progressed and the logframe can be road-tested.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Regulatory mandate and policy coherence of the oil and gas sector enhanced
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
1.1 Actions taken to address conflicts and overlaps in policy and mandates	Entry engagements completed and institutional cooperation secured; / Programme logframe revised wth partners' inputs and agreed with DFID; / Output interventions defined and agreed with partners	Achieved. / GOGIG secured MoP engagement early on, and this has been deepened through the work of the dedicated adviser: / MoP requested an institutional mapping project,building on an initial overview produced by the MoP adviser; and / The adviser has assisted MoP to review the petroleum bill now in parliament. / MoP directed the adviser to assist the PC as the newer institution with the greatest need. / Entry engagement with PC completed and cooperation secured. / Programme logframe revised with PC inputs and agreed with DFID / Output interventions defined and agreed with PC: / 7 project proposals, workplan and budgets jointly developed with institutional partners. Relevant MoUs submitted for formal endorsement.
1.2 Percentage of initiatives implemented to advance strategic priorities of the Ministry of Petroleum and the Petroleum Commission
1.3 Petroleum Commission's capability in sector regulation

Key Points

Output 1 will enhance the regulatory mandate and policy coherence of the oil and gas sector. The key partners are the Ministry of Petroleum (MoP) & Petroleum Commission (PC), and the focus thus far has included technical assistance to the Minister, through a dedicated in-situ advisor, and strengthening institutional, organisational and human capacity in the PC. Significant progress has been achieved particularly in engaging the PC, overcoming misunderstandings over assurances of support and other challenges. Planned future work supporting the MoP will avoid activities being too skewed towards the PC. In the long run, PC capability will also depend on sustained income (i.e. not from licence fees), which GOGIG should help to work towards.

A pipeline of seven projects (including developing standard operating procedures and a performance management system) and their corresponding budgets has been jointly developed by the PC and GOGIG workstream lead for Year One of programme implementation. Funds have been released for two consultants on local content, economics and project evaluation. Relevant mandatory MoUs between DFID and the Government of Ghana for the MoF, the PC and three other state institutions have been drafted and negotiated and the MoUs for all but the PC have recently been signed. The MoU for the PC needs to be agreed by the Board of the PC when it next meets on 8 December before it can be submitted. The GOGIG team has played an important role in facilitating progress and has utilised the process to deepen its relationships with partners.

The programme has revised its theory of change and logframe, following consultation and input from programme partners and DFID. The impact weighting has changed because sector oversight is now covered under the new Output 4 rather than as part of Output 1. The basic structure of the logframe has been agreed with DFID, but some indicators and milestones are subject to baseline activities being conducted.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation: to ‘refine milestones and agree by end of inception phase’.
Action taken: the Output (1) statement was redefined to clearly distinguish between the dual objectives of effective sector regulation and enhanced sector oversight. A new Output (4) “Oil and gas sector oversight enhanced” was introduced.

Recommendation: to balance trust building and technical support to the Petroleum Commission.
Action taken: the programme team has invested significant time and effort in the relationship, with regular communication at the working level and occasional higher level engagement with the Executive Director. The team also developed confidentiality agreements shared with the PC to build trust and address previous concerns.

Recommendation: to coordinate engagement with the PC with other DFID programmes.
Action taken: GOGIG has sought ways to coordinate with DFID’s WRCF programme, which is engaging the PC on effective use of company Corporate Social Responsibility (CSR) funds. GOGIG has supported WRCF’s efforts by advising on the best approach to take with the PC and arranging meetings. Shared office space in Accra and some shared consultants will ensure continued cooperation.

Recommendations

- During the first year of implementation, the GOGIG team should support the PC in developing a sustainable financial framework, and explore using wider GOGIG networks funding options so that they are not dependent on internally generated funds such as from licence fees.
- DFID should continue efforts to get the MOU for the PC signed as soon as possible. The GOGIG team should ensure that they are ready to implement immediately. The GOGIG team should consider recruiting a Programme Manager.
- By March 2016: The GOGIG team should seek agreement on the definition of inclusive growth for the programme – clarifying how policy related activities link to inclusive growth, in particular mitigating the risk of conflict but also the elements leading to the ‘resource curse’ phenomenon.. Where resources and availability of existing analyses permit, this could be underpinned by conducting a strategic analysis of the development needs of the country (taking a long term view), the needs of the oil and gas sector and ascertaining what areas to prioritise as part of a local content approach. The GOGIG team should consider options for how this should be best approached, drawing on complementary activities such as the development of Ghana’s 40 year plan by the National Development Planning Commission and political party manifestoes.
- By June 2016: The GOGIG team should develop a strategy for lobbying or engaging with Government on how oil and gas revenues are utilised (Annual Budget Financial Allocations - ABFA), and consider support to sector ministries to enable better understanding of Petroluem Revenue Management Act (PRMA), how funding is allocated, and entry points for them to engage on how it is used.
- By June 2016: the GOGIG team should review the Logframe, with support from the DFID Results Adviser and Lead Adviser, in line with recommendations in Section B above:
  - Indicator 1.1, the logframe should note whether or not the target is cumultative;
  - Indicator 1.2, the percentage of initiatives implemented is not a straightforward way to track progress, so the definition could explain the advantage of this over simply tracking the number of initiatives implemented;
  - indicator 1.3, the logframe could provide a link or explain how to access the capability assessment, and consideration could be given to an assessment more tailored to planned interventions rather than a generic approach (this also applies to the similar indicators in Outputs 2 and 3).

Output Title	Systems of oil and gas revenue capture improved
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
2.1 Ghana Revenue Authority's capability in revenue capture	Entry engagements completed and institutional cooperation secured; / Programme logframe revised wth partners' inputs and agreed with DFID; / Output interventions defined and agreed with partners	Achieved. / Entry engagement with the Ghana Revenue Authority (GRA) completed and cooperation secured. / Programme logframe revised wth GRA inputs and agreed with DFID. / Output interventions defined and agreed with GRA. / 3 project proposals, workplan and budgets jointly developed with partners
2.2 Systems put in place to facilitate revenue capture
2.3 Ghana Revenue Authority's scope of tax audits

Key Points

The Ghana Revenue Authority (GRA) is the primary partner for the delivery of Output 2. During this period, three GRA units (Petroleum, Custom Division and the Legal Department) have been identified for GOGIG support. Buy-in from the leadership of the Petroleum Unit in particular has resulted in high levels of commitment and cooperation with the programme team. Entry engagement activities include: working relationship established; a needs assessment conducted and validated with GRA; participation in all Steering Committee meetings; and GRA engaged in review and feedback process on draft programme MoUs between DFID and Government of Ghana. The latter is beyond GOGIG’s control but they have played an important role in facilitating progress.

Iterations on programme logframe (indicator and milestone setting) have been done through partner consultations and inputs. Further comments were received from DFID in October. The basic structure of the logframe has been agreed with DFID, but some indicators and milestones are subject to baseline activities being conducted.

Intervention ideas have been conceptualised with GRA, and three project proposals, workplan and budgets have been jointly developed. The projects will enhance capabilities of staff of the Petroleum Unit, develop regulations for the Petroleum Income Tax Law (PITL, 1987), and procure the Computer Assisted Audit Techniques system.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation: to review logframe.
Action taken: the Output statement was redefined from “Ensuring revenue capture” to “Systems of oil and gas revenue capture improved” to better reflect the extent of the programme’s influence and expected results. Indicators and milestones have been refined. The impact weighting has changed in order to accommodate the new Output 4 focused on sector oversight.

Recommendation: to coordinate closely with DFID’s upcoming tax programme.
Action taken: the GOGIG PFM workstream lead has been engaged with DFID and other potential partners on programme design, and GOGIG intends to strengthen these linkages now that the programme has been officially launched.

Recommendations
- Ensure value for money in procurement of accounting and audit systems by continuing efforts to coordinate GOGIG support to the GRA Petroleum Unit with wider GRA or GoG plans. In addition, continue the efforts to ensure complementarity with DFID’s support to GRA delivered through HMRC and other similar donor efforts, e.g. Norad providing input to the GRA Tax Unit to develop audit guidelines.
- By June 2016: The GOGIG team, with support from DFID, should revise the Logframe in line with recommendations in Section B above:
- For indicator 2.2, milestone 5 and the target should be completed, or an explanation provided as to why it is unnecessary (the same applies to the similar indicator for output 3).
- For indicator 2.3, the logframe should clarify whether the milestones are cumulative or not, and explain the lack of change between milestone 5 and the final target.

Output Title	Oil and gas revenue management improved
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
3.1 Capability of key institutions (Bank of Ghana, Ministry of Finance) in revenue management	Entry engagements completed and institutional cooperation secured; / Programme logframe revised wth partners' inputs and agreed with DFID; / Output interventions defined and agreed with partners	Achieved / Entry engagement with the Bank of Ghana and Ministry of Finance completed and cooperation secured; / Programme logframe revised with BoG and MoF inputs and agreed with DFID; / Output interventions defined and agreed with BoG and MoF. / 7 (MoF - 5, BoG - 2) project proposals, workplan and budgets jointly developed with partners
3.2 Systems put in place to facilitate fiscal oversight and investment decisions
3.3 Number of technical analyses produced to inform decision making on revenue management

Key Points
This output focuses on support to the Ministry of Finance (MoF) and the Bank of Ghana (BoG). The working relationship has been established, and a needs assessment conducted. BoG and MoF have consistently participated in Steering Committee meetings, and have both reviewed and fedback on draft programme MoUs between DFID and the Government of Ghana.

Iterations on programme logframe (indicator and milestone setting) have been done through partner consultations and inputs. The basic structure of the revised logframe has been agreed with DFID.

For the MoF, a pipeline of five projects has been developed, including a project to develop Regulations for the Petroleum Revenue Management Act (PRMA - Amendment), and a project to enhance the capabilities of the staff of the Energy, Oil & Gas Unit of the Ministry of Finance.

For the BoG, two projects have been developed, reviewed and approved by the GOGIG team and DFID. These projects will enhance capabilities of the staff of the Ghana Petroleum Funds Secretariat, the internal audit department, the finance department and selected senior level management of the BoG. The other project will procure Bloomberg’s Asset and Investment Manager Application for the Ghana Petroleum Funds Secretariat.
Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation: Review logframe.
Action taken: Output 3 indicators and milestones have been refined, and agreed by DFID. The main change was to expand the scope to incorporate support to the Ghana Petroleum Funds Secretariat of the Bank of Ghana. The impact weighting has changed in order to accommodate the new Output 4 focused on sector oversight.

Recommendation: to coordinate closely with DFID’s upcoming tax programme.
Action taken: GOGIG participated in an introductory meeting with the DFID implementing partners working with GRA to ensure coordination. GOGIG have also met the lead on donor coordination for GRA.

Recommendations
- Continue to synchronise GOGIG internal efforts (e.g. aligning this work with support to the Public Interest Accountability Committee (PIAC), and link externally with other relevant DFID programmes, e.g. WRCF.
- Increase GOGIG awareness of broader contextual issues, such as the public finance management framework, the macro-economy and the IMF support programme and ensure that these are reflected in Quarterly reports to DFID.

Output Title	Oil and gas sector oversight enhanced
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Capacity building interventions that facilitate oversight functions of accountability actors	Programme logframe revised and submitted for approval; / Stakeholder mapping and strategic framework developed; / Output interventions defined and agreed with DFID; / Strengthened coordination with accountability partners.	Achieved / Programme logframe revised and submitted for approval. / Stakeholder mapping and strategic framework developed. / Output interventions defined and agreed with DFID. / Strengthened coordination with accountability partners: / 7 Individual and joint engagements with ACEP and NRGI to enhance understanding and synergies across programme; / Programme modalities around quality assurance, joint reviews, and programme implementation established. / Exceeded: / 9 joint working and engagements on individual project activities/interventions (NRGI - PIAC Strategic Planning Meeting, Secretariat recruitment sessions, Forum on GNPC’s Audited Accounts and Investment Strategy, ACEP-Accountability Forum, Oil and Gas Governance Summit, etc); / 2-day workshop on the Exploration and Production (E&P) Bill with the Parliamentary Select Committee on Energy and Mines; / 5 pieces of analysis; / Institutional strengthening of PIAC.
4.2 Number of analyses, monitoring and advocacy initiatives that seek to hold government to account on oil and gas fiscal management
4.3 Percentage of step change actions achieved by targetted accountability actors
4.4 Number of engagements between government, accountability actors and citizen groups on key sector issues

Key Points

This is a newly formulated output focusing on improved oversight of the sector by accountability actors. The logframe has been revised and more indicators have been added to capture results from ACEP and NRGI’s projects. These results are exceeding expectations, and are set out in more detail further below. Each of these projects have individual logframes which feed up into the wider GOGIG logframe. DFID has approved the revised logframe.

A mapping of accountability actors in the oil and gas sector was completed in June 2015, and an initial implementation plan has been developed.

Output interventions have been defined and agreed with DFID. These have been developed on the back of engagements with CSOs active in the oil and gas sector, as well as engagement with Parliament (Mines & Energy, Finance, Public Accounts, Government Assurances Committees), and with peer programmes such as WRCF.

Strengthened coordination with accountability partners. A key accomplishment during the period under review has been the improved coordination between GOGIG and the accountable grant partners – ACEP and NRGI. Systems for joint reviews, quality assurance and coordinated programme implementation have been established. The GOGIG team has collaborated with NRGI and ACEP on several successful activities during the period, beyond what was anticipated – including the NRGI - PIAC Strategic Planning Meeting, Secretariat recruitment sessions, Forum on the Ghana National Petroleum Company’s (GNPC) Audited Accounts and Investment Strategy, the ACEP Accountability Forum, the Oil and Gas Governance Summit. Beyond NRGI and ACEP, GOGIG has developed wider links to accountability actors such as the Civil Society Platform on oil and Gas (CSPOG), the Institute for Economic Affairs (IEA), the International Growth Centre (IGC) as well as consolidating its relationship with the Africa Centre for Economic Transformation (ACET). GOGIG also held partnership meetings with WRCF to agree on the key areas of collaboration between the programmes.

The following results exceed expectations:
- Indicator 4.1: A two-day capacity strengthening intervention on the E&P Bill was organised by GOGIG in August 2015 for the Parliamentary Select Committee on Mines & Energy
- Indicator 4.2: 5 pieces of analysis, 1 monitoring initiative and 2 advocacy initiatives have been conducted. These include an analysis of the E&P Bill, the launch of ouroilmoney.org, and successful advocacy campaigns for PIAC funding and transparency of tender processes.
- Indicator 4.3: Institutional strengthening of PIAC, including more staff, a strategic plan, and progress in addressing current issues beyond meeting statutory requirements

The programme also has plans in place to support coordinated civil society organisation/media actions particularly during the Election period to enhance voice and greater demand for accountability. To complement these, the programme will also convene dialogues between state and accountability actors to foster collaboration towards common development goals.

Recommendations
- By March 2016: The GOGIG team should further develop their plans to use the upcoming elections as an opportunity to build sustained civil society support around key issues. This should be done in conjunction with the DFID Strengthening Transparency, Accountability and Responsiveness II (STAR II) programme;
- By March 2016: The GOGIG team should further explore and pursue options to work with political parties to offer balanced and neutral technical support for better understanding of the sector to inform electoral manifestoes;
- By June 2016: The GOGIG team, working with DFID, should revise the Logframe in line with recommendations in Section B above:
- For indicators 4.1, 4.2, and 4.4, the logframe should clarify whether the milestones are cumulative or not.
- For 4.3, the logframe definitions could explain the advantage of tracking the percentage of step change actions rather than the number.
- For 4.4, the baseline should be completed, and an explanation added for the dips in 2017 and 2019.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The largest cost driver has been the management cost which amounts to £264,666 (2.1% of the total cost). Key factors affecting the management costs include overheads of administering the programme, costs associated with a permanent office set up, and procurement of vehicles.

The second driver has been the provision of support to partners (costs of technical assistance to MoP, PC and support to Parliament). This amounts to £175,196 (1.4% of total programme cost).

Once MOUs are signed between DFID and the Government of Ghana, full implementation of projects will commence and will account for a greater proportion of programme spend.

VfM performance compared to the original VfM proposition in the business case
For the review period, the programme’s VFM performance was mainly related to economy measures:
- The programme has developed standardised rates based on extensive enquiries into key elements of project costs. This is being used to benchmark both programme and project budgets;
- Savings of £18,500 were made based on OPM’s decision to fund the cost of the E&P parliamentary support project as a “quick win” during inception instead of during implementation;
- Long term TA support to the Ministry of Petroleum is delivered at cost with no margin for OPM (saving approximately £16,000 per quarter);
- Vehicles for the programme were procured via Toyota Gibraltar’s CSR programme, saving GOGIG in excess of £10,000;
- GOGIG secure a 25% discount on 300 sqm of office space in a prime time central commercial location in Accra, saving DFID over £15,000. Sharing some of the additional space with the WRCF programme also provides further savings to DFID.

On efficiency, significant progress has been made on improved collaboration and coordination between relevant partners. GOGIG is also investing in coordination with other similar programmes which will improve efficiency. Once MOUs are signed and project proposals implemented, there will be further evidence of efficiency and effectiveness.

Assessment of whether the programme continues to represent value for money
The business case was approved on the basis of an estimated return of £5.50 for every £1 invested. The severe drop in oil price has made this target more challenging. Nevertheless, a good range of partner relationships have been established and mechanisms such as the Steering Committee set an excellent platform for further progress. If GOGIG interventions can be catalytic so that the positive effects are not limited to the oil and gas sectors but in the long term also benefit the wider economy, the programme value for money could be further enhanced.

The programme has developed a VfM framework with a broad set of indicators. The framework comprises of a mix of process, qualitative, and quantitative measures that relate to tracking economy, efficiency and effectiveness. This will be revised based on amendments that have been made to the logframe. Future assessments against the framework will provide further VfM data.

Quality of financial management
The programme team has put in place rigorous financial management procedures for effective operation of the programme. The team has developed a financial policy and procedures manual to guide its financial operations. In addition, it has put in place the following to tighten internal controls:
- A budget tracker that allows the programme to monitor the key cost drivers;
- An automated accounting system (SUN) for recording and reporting financial transactions and
- A milestone tracker that helps to monitor programme spend and invoicing to DFID
However, financial forecasting needs to improve so that there is less variance with actual spend. DFID should continue to work with the GOGIG team to ensure that forecasts are realistic and amendmments submitted in time to be reflected in the DFID forecast. Accuracy should improve as implementation gets underway and the pace of implementation with partners can be assessed and taken into consideration.
The main audit for GOGIG is due in June 2016, and this will include NRGI and ACEP. An expenditure verification exercise with NRGI is planned for December 2015 (ACEP completed one during the previous review period).
Date of last narrative financial report	30/10/15
Date of last audited annual statement	Not applicable – programme is yet to audited

E: RISK (½ page)

Overall risk rating:

The overall risk rating for the programme remains Medium.

Overview of programme risk

The business case identified the main risks as being in two clusters - political support and institutional incentives. Fiduciary and management risks were assessed as low following DFID’s decision not to provide non-budget financial aid to Government bodies. The overall level of risk has not changed, but the GOGIG team has updated the focus in line with current activities and issues, and developed a more detailed risk management strategy aligned with logframe outcomes and outputs. Risk strategies are also included in each project proposal.

One key issue is maintaining GOGIG’s neutrality – as stakeholder relationships develop, it will become increasingly important to invest in maintaining a balance of partnerships and avoiding any perceptions of politically-affiliated alignment. There may also be a risk of slowing of activities during the election year which may in turn impact on projected spend.

Outstanding actions from risk assessment

No outstanding actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The previous annual review noted significant procurement delays which delayed programme delivery, however progress against a revised log-frame is now on track, with output 4 making greater progress than expected. Any further delays in securing a formal endorsement of the MoUs between DFID and the Government may have an impact going forward.

Performance of partnership (s)

DFID’s partnership with the GOGIG team is strong, with the service provider staff being responsive and timely to address issues raised by DFID. Weekly meetings are held between the DFID lead adviser and GOGIG team leader, backed up by regular meetings with the MoP adviser. Formal monthly programme management meetings have been less needed during the inception phase; as the programme has moved into implementation phase these will occur routinely and involve the DFID Programme Manager.

Over the course of the inception phase, DFID has sought ways to improve the coordination between and strengthen the relationships between the core GOGIG team and the two accountability actors, ACEP and NRGI. This has included giving GOGIG a quality assurance role in reviewing the quarterly reports, enabling them to be better informed of planned activities and identify areas where they can provide support as well as better reflect the activities of “greater GOGIG” in the main programme reports. GOGIG now also participates in the monthly Programme Management Working Group (PMWG) meetings between PIAC, NRGI and DFID. Going forward, it has recently been agreed that quarterly reports will be shared with the two accountability actors and that a single monthly programme management meeting will be held with GOGIG, ACEP and NRGI. Relations between the partners are considered to be strong, as exemplified by the recent collaboration between ACEP and GOGIG on the Oil Governance Summit in November 2015.

Asset monitoring and control
DFID carried out a physical verification of assets held by GOGIG, ACEP and NRGI in February and March 2015 as part of the office-wide exercise and all the assets were available and being used for the purpose for which they were bought, with the exception of NRGI, which had not purchased any equipment at that time. In addition, an asset check was conducted for ACEP at the time of the financial expenditure verification exercise in August 2015. As part of DFID’s on-going monitoring and control, OPM submits an updated asset inventory for GOGIG as part of the quarterly report.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The GOGIG programme does not provide financial aid directly to the government. However, the programme is well-positioned to support progress against the partnership principles, particularly in the areas of concern, e.g. strengthening financial management and domestic accountability.

The partnership principles were assessed in July 2015. The Government of Ghana upheld all four partnership principles over 2014-15. However, this assessment notes continuing concerns about genuine political commitment to macroeconomic management, fiscal discipline, public financial management reform and fighting corruption. Performance in relation to the IMF programme will be monitored carefully as a means of assessing GoG commitment to the partnership principles. Maintaining fiscal discipline could be particularly challenging for the Government as it enters the election year.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

GOGIG has recruited a dedicated M&E officer, and the programme has made good progress towards developing its monitoring, evaluation and learning system. A monitoring, evaluation and learning (MEL) strategy was produced in July 2015. The MEL strategy notes that evaluation assignments will include end of project reviews, annual reviews, and the programme completion report.

The programme has revised its theory of change (ToC) and logframe, following consultation and input from programme partners and DFID. No significant new evidence was identified during the review period, and the basic premise in the Business Case still holds, but the ToC and logframe have both been further developed to reflect current engagements and inception period activities. For example, with GOGIG engaging on multiple fronts, in addition to developing an overall ToC for the programme, an ‘outcome mapping’ approach has been adopted which breaks the ToC down into individual outputs, using PEA to focus in on the specific pathways to potential change within each area.

The most significant change to the logframe was to separate out the sector oversight element of Output 1. A recent PEA workshop helped to refine and contextualise the theory of change for this specific output, noting the importance of finding the right balance between external advocacy and internal influencing and advisory work to MDAs.

Monitoring progress throughout the review period
DFID holds weekly meetings with the GOGIG programme team to monitor activities and to ensure appropriate linkages with related programmes. In addition there are meetings with advisers and consultants engaging on the programme on an ad hoc basis. Since the final inception report, the first quarterly report (July-September 2015) was submitted at the end of October.

Monthly meetings are held with ACEP and NRGI. Quarterly progress and financial reports have been produced. ACEP and NRGI submitted (in May and July respectively) an annual progress report covering the period up to the end of March 2015.

This Annual Review was undertaken by three DFID advisers – an extractives adviser from the central Governance and Extractive Industries Team in ARD; a private sector development adviser from PSD; and the Regional Extractives Industries Adviser for East Africa. The review took place simultaneously with that of the WRCF programme, consisted of desk review of documents submitted by the programme teams, followed by 10 working days in country. The time in country included initial briefings from the programme teams, followed by interviews with selected beneficiaries.