Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Assets to Adolescent Girl’s Programme (SPRING)
Programme Value: £16,436,037		Review Date: 17/11/2015
Programme Code: 203375	Start Date: 17/12/2013	End Date: 31/03/2022

Summary of Programme Performance
Year	2014	2015
Programme Score	A	A
Risk Rating	High	High

Summary of progress and lessons learnt since last review

SPRING was approved in December 2013, and contracting of the implementing team was completed in June 2014, with a a kick off meeting of the donor partners and consortium leads in July 2014. The programme started implementing activity in January 2015 with the launch of the website and call for first business venture applications.

Since the last Annual Review in December 2014, the SPRING programme has successfully launched and started implementation. Notably it has achieved the following in the past year:

 The programme website and in-country outreach activity for entrepreneurs started in January 2015, with a call for applications launched in February 2015.

Successful recruitment of 18 innovative and diverse business ventures from Kenya, Rwanda and Uganda forming the first SPRING cohort, from 146 eligible applications and 50 selection interviews. (May 2015)

Completion of girl consultation activities in the 3 countries is contributing to boot camp curriculum, entrepreneur understanding of girl challenges and integration of girls needs into business models. (May 2015)

SPRING’s first two-week boot camp in Nairobi using a Human Centred Design (HCD) approach with
strong positive feedback from entrepreneurs. (July 2015)

90% of grant agreements signed within 1.5 months after boot camp, with average disbursement of $15,000 for ventures to begin implementing their business prototyping plans. (August 2015)

Completion of Prototyping in Context (PIC) – country visits by human centred design specialists to follow up on implementation of business plans agreed at bootcamp and girl research in-country to enable entrepreneurs to build on HCD learning and test business plans and products with girls. (October 2015)

First corporate partnership established with Hogan Lovells, an international law firm, committing up to 300 pro bono hours of legal advice to entrepreneurs per year.

Thirty pieces of global media coverage for SPRING, appearing in outlets such as Mashable, FastCompany, Business Fights Poverty, Monocle, the Monitor, in addition to upcoming coverage in Vanity Fair.
The independent M&E team started work in February 2015. They have played a critical role in testing the theory of change and have finalised a results framework and monitoring and evaluation framework which will be used to monitor progress over the timeframe of the programme.

SPRING was designed to be an innovative and learning focused programme, testing new approaches to reaching girls with assets that help them learn, earn and save safely. Overall, the programme has done well in its first year – it has established an identity, attracted interest from a broad range of actors and designed and delivered intensive support through bootcamp to the selected enterprises to enable them to deliver for girls. There have been challenges as the implementing consortium has been testing the experimental design of the programme with realities on the ground, and finding ways of working that suit a geographically scattered team. A series of meetings in April 2015 with the Implementing, M&E and donor teams took place to refine the programme theory of change and take stock of lessons learned from the outreach and recruitment of cohort 1.

Based on lessons learned in Year 1, SPRING is currently in the process of a contract amendment to the TORs, as agreed with donors at Steering Committee meetings April 2015. Below is a summary of proposed changes in the coming year.

Ensure enhanced HCD and research support to all entrepreneurs and greater investment in cultivation of investor relations and technical assistance to entrepreneurs.

Change of scope to focus on a minimum of 58 ventures with current committed resources, ( 18 in Cohort 1, 20 each in Cohorts 2 and 3) and to fundraise for a Cohort 4 (additional 20 ventures), rather than the original programme design of 30 ventures in Cohort 2 and 40 in Cohort 3. To maximize programme learnings, South Asia will be brought forward, and covered earlier through Cohort 2, with expansion into Tanzania and Ethiopia in Cohort 3, and Cohort 4 as a second cohort in South Asia.

Relocation of the project team from Nairobi to London and hiring of the new team with revised roles and enhanced capabilities in communications, fundraising, knowledge and public policy learning, and accelerator management.

The rationale for these changes was to address the resourcing gaps identified by the implementing team, which in the original design were meant to be covered by fundraising efforts. In order to ensure the quality of support delivered to enterprises for all cohorts of the programme, the fundraising component has been earmarked for the final cohort, shifting the uncertainty around fundraising from the quality of deliverables to the total number of enterprises supported. The number of enterprises per cohort has also been reduced as it became clear from the first bootcamp that supporting more than 20 per cohort would affect the quality of personalised support, which has led to the addition of a cohort 4. The rollout to South Asia one year earlier than planned is to maximise learnings from different contexts, as the location of cohort 4 will be decided based on results from East Africa and South Asia in the first and second cohorts. The restructuring and relocation of the team reflects the need for much stronger programme leadership of a geographically dispersed consortium and the global nature of the programme.

Summary of recommendations for the next year

The design of the application, selection and due diligence processes for Cohort 2 should integrate learnings from Cohort 1. The approach to recruitment and selection of Cohort 2 should be finalised by February 2016.

Complete recruitment of the Implementing Partner’s London based team by January 2016.

Develop a fundraising plan with clear milestones by March 2016, with an explicit decision point in June 2017 on achievement of fundraising targets for Cohort 4.

The Implementing Partner should undertake context analysis, drawing on existing networks and information as well as landscaping visits starting by February 2016 to ensure that the rollout to South Asian countries is successful.

For Output 1 on entrepreneurs increasing the number of girls reached, the Implementing Partner should ensure that the KPI form collects this data reliably, establishing baselines and performance against progress indicators in time for the next AR.

The Implementing Partner should provide (1) the checklist and criteria used to assess investor readiness and (2) the criteria to decide whether enterprises are seeking external capital, by December 2015. This is necessary in order to establish a baseline for Cohort 1 and to be able to assess progress for the next AR. The checklist and criteria should be agreed by the donor and independent M&E Partner. For Cohort 2, the Implementing Partner should include investment readiness checkpoints in the grant agreements.

The Implementing Partner should revise the design of bootcamp for Cohort 2 – to reflect lessons and feedback from this first year. The grants process and information provided to entrepreneurs should be clear, breaks should be incorporated into the bootcamp schedule (so that it is not two weeks at one time), and customised support to entrepreneurs should be maintained by limiting the number of entrepreneurs to 20 at maximum per cohort.

The Implementing Partner and M&E Partner should agree criteria on quality, content and relevance for which communications from the programme meet the requirements of the output indicator on communication of evidence by January 2016

The M&E Partner should develop methodology for independently verifying the value of in-kind contributions to the programme by January 2016

The Implementing Partner should propose a set of indicators for monitoring value for money performance consistently over time for future Annual Reviews. These indicators should be agreed with the donor team and M&E Partner by March 2016.

A. Introduction and Context

DevTracker Link to Business Case:	203375 documents
DevTracker Link to Log frame:	203375 documents

Outline of the programme

SPRING is a 5 year accelerator programme funded by DFID, Nike Foundation, and USAID, supporting enterprises to develop products and services which could transform the lives of adolescent girls. The SPRING programme is being implemented by a consortium of partners led by The Palladium Group.

SPRING will identify and support early-stage business ventures across 8 countries through up to four nine-month accelerator programmes, providing grant funding and technical assistance to drive the business models forward and ensure that products reach girls directly and at scale. By doing so, the programme aims to reach 200,000 girls with products, services or opportunities for income generation which contribute to their economic and wider empowerment and kick-start the wider market for such products and services.

Expected Results

Over the five years, the programme aims to support at least 58 entrepreneurs in eight countries and is expected to deliver the following results by 2019:

- Delivery of entrepreneur’s products that enhance the economic outcomes of up to 200,000 girls
- Improved entrepreneur’s business performance e.g. new market entry
- An enhanced strategic evidence base to inform future girl programming and attract donor, government and private sector investment
- Effective communication and dissemination of evidence gathered

The programme began in Kenya, Rwanda and Uganda (Year 1) and will expand to an additional five countries across East Africa and South Asia including Ethiopia, Tanzania, Nepal, Bangladesh, and Pakistan.

Contribution to DFID’s Objectives

Economic assets are the building blocks of economic and social progress. An asset can generate
income, enhance productivity, facilitate access to capital and credit, and store wealth. It strengthens the owner’s capacity to cope with and respond to shocks by enabling them to diversify income and smooth consumption. Assets can also contribute directly to girls’ economic empowerment by reducing their time-poverty and enabling them to stay in school. Products, in the SPRING context, are assets.

The economic empowerment of girls and women, and their ownership of assets is a strategic priority for DFID. DFID’s Business Plan (2011-15) highlights the critical role of wealth creation and gender equality in poverty reduction. DFID’s Strategic Vision for Girls and Women highlights economic empowerment, and especially access to assets. The Economic Development Strategic Framework emphasises improved access to markets, finance, property and employment opportunities for girls and women.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

SPRING’s expected outcome is for enterprises to provide market-based solutions (i.e. products and services) that can benefit girls and contribute to their economic empowerment. Under this outcome, the SPRING logframe tracks (1) the number of enterprises that attract external investment attributable to participation in SPRING; (2) the number of adolescent girls accessing products and services or involved in the business operations, and (3) the number of entrepreneurs who have increased sales from products, services, or business models benefitting girls by 20% or more.

An outcome assessment is not possible at the time of this review, because the programme activities with the first cohort started in July 2015 and insufficient time has passed for outcome level changes to occur. The first milestones for SPRING outcome indicators are expected to be achieved in August 2016.

Overall output score and description

SPRING is now in the middle of its first year of implementation. Activities with the first round of business ventures began in late June 2015. By late October 2015 the first cohort had completed four months of their nine-month accelerator phase, including core support activities such as the two-week bootcamp and prototyping. The first cohort will graduate on 30 March 2016.

More evidence on outputs and outcomes will become available within the next year, as the first cohort completes their accelerator support. Of the 3 output indicators which were measurable at this stage, the related milestones for 2015 have all been successfully reached:

Output Indicator 3.1: Cohort 1 entrepreneurs’ satisfaction with the HCD and other technical assistance provided through SPRING (milstone target: 14 entrepreneurs (75 %) report satisfaction by August 2015).
- Output Indicator 4.1: on the number of eligible applications received for the first cohort (milestone target: 145 eligible applicants by August 2015)
- Output Indicator 4.2: SPRING to generate communication products with evidence and or lessons learned produced and disseminated by implementing partner (milestone target: 3 communication products by August 2015)
All other outputs will be measured once the first cohort completes their accelerator support. The 2016 Annual Review will report on progress against all outputs.

Key points to note, including main reasons for underperforming (if scoring C or subsequent B) or reasons behind strong / improved performance

The programme scoring an A can be attributed to consistency across all of the 3 output scores and expectations being met for each of them and for the programme overall at this stage.

Has the logframe been updated since the last review?

The Logframe was refined by Palladium following the SPRING inception phase in January 2015. It was revised following the Theory of Change workshop led by the SPRING M&E partner (Coffey International Development) in April 2015. Since then, the logframe has undergone several rounds of revision to ensure it is fit for purpose, involving inputs from the Implementing Partner, M&E Partner, and DFID. This has taken longer than expected, partly due to changes in the programme design which impact on Logframe targets and milestones.

## C: DETAILED OUTPUT SCORING

Output Title	SPRING grantees reach adolescent girls
Output number per LF		1	Output Score
Risk:		Medium	Impact weighting (%):	0
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
Number (% in brackets) of grantees that show an increase in number of girls reached with products and services or involved in business operations.	0	N/A

Key Points

The output “SPRING grantees reach adolescent girls” measures the immediate change that needs to occur (i.e. SPRING grantees refine their product, service or business models to better meet the needs of adolescent girls).

This output will have its first milestone in August 2016, which is why the impact weighting for this Annual Review is 0. It captures the increase in the number of girls reached by SPRING enterprises since they joined the programme. The first cohort started in July 2015 so progress against this indicator is not expected at this stage. This indicator will be measured using biannual reporting forms (KPI forms) completed by entrepreneurs. The baseline for this indicator is taken from the grantee’s self-reported estimates at time of application on the proportion of their customer base that is adolescent girls.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable.
Recommendations

The Implementing Partner, with support from the M&E partner, should ensure that the KPI form collects this data reliably, and that a baseline can be established retrospectively.

Output Title	SPRING grantees improve their investor-readiness
Output number per LF		2	Output Score
Risk:		Medium	Impact weighting (%):	0
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
2.1 Number (%) of grantees who have improved their investor readiness.	0	N/A

Key Points

This output relates to the outcome “Number of grantees that attract external investment attributable to participation in SPRING.”

This output will have its first milestone in August 2016, which is why the impact weighting for this Annual Review is 0. The first cohort started in July 2015 so progress against this indicator is not expected at this stage.

In order to measure against this indicator the Implementing Partner will use a screening checklist to assess the investor readiness of grantee businesses at the start and end of each cohort. The idea is to make businesses more 'investable' by addressing typical criteria that investors are looking at when making investment decisions. This applies only to those businesses who are seeking external capital.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable.
Recommendations

- The Implementing Partner should provide the checklist and criteria used to assess investor readiness and the criteria to decide whether businesses are seeking external capital. The Implementing Partner should include investment readiness checkpoints in the grant agreements.

Output Title	Grantees benefit from HCD and other forms of SPRING TA to improve business viability and develop products and services benefiting girls
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	67%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
3.1 Number of grantees (% in brackets) who report satisfaction with the HCD and other technical assistance provided through SPRING.	14 respondents report satisfaction with HCD (75% of C1)	14 respondents reported satisfaction with HCD.
3.2 Number of grantees who use HCD to refine their business model, product or service to meet the needs of target girls.	0	N/A – cannot be reported until August 2016

Key Points

The first SPRING Cohort (Cohort 1) kicked off from 28 June - 11 July 2015 with an intensive two week residential boot camp in Nairobi. A Human Centred Design (HCD) approach was used during the bootcamp to diagnose barriers to growth and refine business models during sessions with technical advisors, mentors, and peers. The bootcamp supported the entrepreneurs to develop a business prototyping plan which included identifying opportunities to better integrate girls into their product or service development or current business models as well as attracting investment to grow the business.

Milestone 1 for Indicator 3.1 is informed by the boot camp satisfaction survey conducted face-to-face by the M&E partner with 14 out of 18 grantees in July 2015 – there were 4 non-respondents to the survey. Feedback from this survey refers to satisfaction with the boot camp only, given the timing of this review. Milestones 2, 3 and 4 will be informed by an end-of-cohort satisfaction survey and HCD workshop feedback from all cohort grantees and capture satisfaction with the entire support package.

In the bootcamp survey, all 14 grantees interviewed said that boot camp had either met (4 grantees) or exceeded their initial expectations (10 grantees). All reported that they felt comfortable with the changes that had been recommended. Twelve out of 14 grantees surveyed stated that they left with a good understanding of HCD, and felt able to explain HCD to their colleagues.

When asked how SPRING was different from other accelerator programmes, respondents highlighted the exceptional quality of the SPRING accelerator team:
- “Calibre of the team is mindblowing, in-depth training especially on HCD, resources to implement, market-based comprehensive approach to girls' empowerment”
- “The SPRING experience was rich in content and deep. The support from world class experts immensurable”.
Source: Boot camp satisfaction survey conducted by the M&E partner, grantees from Uganda.
Other respondents praised SPRING for being more practical, better organised, and drawing on better expertise and knowledge than other accelerators in which they had participated.
It is too early in the cohort to assess whether grantees are actively applying HCD principles to refine their products, services and business models (indicator 3.2) – as they have just completed the in-depth HCD and prototyping workshop at the end of October 2015. This will be assessed in the next annual review, along with a more detailed assessment of indicator 3.1.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not Applicable

Recommendations

While feedback from the entrepreneurs on the boot camp was very positive overall, there were a few suggestions for improvement:
- Three entrepreneurs found the financial modelling module difficult to understand. There may be scope for simplifying the content or spending more time on explaining it.
- Eleven entrepreneurs stated that they would like more M&E support, if it was made available.
- The grants process should be decided and better organised prior to bootcamp. The implementing partner should ensure that entrepreneurs have clear information and expectations on the process for accessing the grant funds. At the July bootcamp, three entrepreneurs said that they did not find the grants manual helpful and two had not heard of the grants manual at all.
- A two week long bootcamp was a very intense experience for entrepreneurs; breaking this time up may improve the quality of learning. When asked how bootcamp could be improved, three entrepreneurs mentioned that it would be good to have more breaks and down time to reflect on the materials and absorb the content.
- Given the customised nature of how support is provided to each entrepreneur at bootcamp, it does not seem feasible to have this model of delivery for bootcamps of more than 20 entrepreneurs at a time. The feedback on the bootcamp is very positive, so rather than revisit the delivery model, it would make sense to limit the number of future cohorts to 20 each and allow for one additional cohort in the programme.
- The Implementing Partner and M&E Partner should ensure that feedback surveys for programme activities are well-designed, not overly laborious and that all entrepreneurs complete surveys.

Output Title	Market stimulation for products and services benefitting adolescent girls.
Output number per LF		4	Output Score	A
Risk:		High	Impact weighting (%):	33%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
4.1 Number of applications received that meet SPRING eligibility criteria.	145 eligible applications received	146 eligible applications received
4.2 Number of communications products with evidence and or lessons learned produced and disseminated by implementing partner.	3 communication products developed and disseminated	Completion of video on website, / Business Fights Poverty article / Girl Case Studies
4.3 Funds raised by SPRING implementing partner through cash and in-kind equivalent contribution	0	N/A – Funds expected to be raised in 2016

Key Points

Overall progress against Output 4 is as expected at this stage in the programme implementation.

During the Inception Phase, SPRING focused on implementing an outreach strategy to recruit high quality applicants for cohort 1. The application window for Cohort 1 opened on 30 January 2015 and closed on 1 March 2015. A total of 245 applications were received. 146 of these were deemed eligible for scoring. The eligibility criteria are.

- Businesses who have a legal, registered enterprise and are able to demonstrate a minimum of one year of revenue-generating operations;
- Business is able to demonstrate current operations or plans to secure representation in Kenya, Uganda and/or Rwanda by June 2015;
- The business’s product or service will increase adolescent girls’ ability to do one or more of the following:
  - Generate income
  - Save time or labour, giving girls more time to study or secure employment
  - Save and invest their earnings and assets
  - Feel safe and secure

According to the SPRING Annual Report, almost 70% of the final 18 enterprises selected were already known to, or pre-identified by a member of the SPRING team, demonstrating the importance of a local, targeted approach to outreach to ensure a high calibre of applications.

Regarding communication products, the team has developed the following:

1. Current website film: https://vimeo.com/119552076
The commissioning of a short film for SPRING’s launch earlier this year that focuses on girls as a catalyst for positive change, the issues facing East African entrepreneurs and what practical support they require to get their businesses off the ground. The website currently does not have an analytics function. The team is currently investigating the addition of this function to effectively measure key web statistics.

2. Business Fights Poverty blog: http://community.businessfightspoverty.org/profiles/blogs/annarichter-
the-business-case-for-girls
SPRING Programme Director Sachin Gupta wrote a 550 word blog post for Business Fights Poverty, the world’s largest online community of professionals harnessing business for social impact. The article was circulated via BFP social channels - BFP has 27.5k followers on Twitter, and 4.4k likes on Facebook.

3. Girl Case studies – Rebecca Calder developed girl case studies for the SPRING website drawn from the girl landscaping field research carried out in February 2015. The real life ‘stories’ of Esther and Edith were developed for the website to connect readers to the girls SPRING is trying to reach.

Initial fundraising has begun through networking and the communication outreach strategy. The first corporate partnership was established with Hogan Lovells, an international law firm, committing up to 300 pro bono hours of legal advice to business ventures per year. Fundraising will become an important priority moving into Cohort 2 in 2016. This indicator will be measured in the 2016 annual review.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not Applicable

Recommendations

The Implementing Partner will develop a comprehensive stakeholder communication plan to segment audiences, areas of learning, channels and appropriate reach. The strategy will include a system for tracking the numbers of views, shares and comments as applicable on communications products (February 2016)

The Implementing Partner and M&E Partner will agree criteria on quality, content and relevance for which communications from the programme qualify against this milestone by January 2016

The M&E Partner will develop methodology for independently measuring the value of in-kind contributions to the programme by January 2016

The Implementing Partner should ensure that every communications product puts adolescent girls at the center – what makes SPRING special is that it is testing out market-based solutions to economically empower adolescent girls in poverty.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

As of 31st October 2015 the programme has spent 22% of the total budget.
The key cost driver of the programme to date has been personnel expenses representing 51% of
the total programme spend so far, as teams are established and workplans set. 43% of our spend to date has come from programme activities. It is anticipated that this will increase as the programme continues through cohort 1 and into the following cohorts, particularly as grant spending and support to
entrepreneurs increases. The remaining 6% accounts for expenditures not related to programme activities, such as office equipment.

VfM performance compared to the original VfM proposition in the business case

Due to the early stage of the programme most of the VfM information available is on the economy level,
with some data available at the efficiency level and no data yet available at the effectiveness level.

Economy (minimising input cost)

The indicators in business case are against the service provider day rates benchmarked against rates from across DFID’s portfolio and attracting mentors and pro-bono services:

Monetised cost savings: are measured in terms of average unit costs for flights. At inception the benchmark unit cost for flights was set at £1,225. The average unit cost currently stands at £1,024, representing an overall cost saving of £9,247.

In kind contributions: Pro bono legal services have been secured from Palladium’s corporate partner, Hogan Lovells, estimated at over £200K. They hope to build on this partnership in the coming years as well as continue to attract other sponsors to deliver value. SPRING continues to seek opportunities to leverage pro-bono inputs both from the management
consortium and also from professional partnerships. The table below outlines the estimated costs of pro bono time donated by the programme team for the programme to date.

	Pro bono Days	Cost (GBP)
Fuse project staff	218	£ 341,569
Suzanne Biegel (Investment lead)	30	£ 27,000
Ramona Liberoff (Expert at Bootcamp)	15	£ 10,800
Jenny Williamson (Operations Associate)	84	£ 21,840
Total	347	£ 401,209

The investment lead, Suzanne Biegel has spoken about SPRING at almost 20 conferences and events and the programme has not been charged for the associated conference fees or related expenses. This has resulted in cost savings to the programme of around £22,000.

The total of the raised funds, pro bono work and unbilled expenses represents a saving of around
£700,000 to the programme so far. Further efficiencies are also anticipated over the coming months
resulting from the restructure through a centralised procurement review and the engagement of regional
coordinators whose responsibility it will be to drive efficiency wherever possible.

Efficiency (conversion of inputs to outputs)

At inception the benchmark Management/Admin costs as % of total costs was set at 8%. This
figure currently stands at 11% as of 30th September 2015 which is again attributable to higher
management costs during the start-up phase of the project. We expect this measurement to
decrease over the next year of the programme as the activities increase in light of the expansion
into different continents for cohorts 2 and 3.

Now that the logframe has been finalised, the Implementing Partner will submit proposed VfM indicators for consistent monitoring over time by the end of January 2016.

Assessment of whether the programme continues to represent value for money

There is limited information at this stage to do a full value for money assessment. From the evidence available, the programme continues to represent value for money. A set of Value for Money indicators will be agreed in January 2016 to consistently measure VfM over the programme lifetime.

Quality of financial management

Palladium maintains a best-practice variance tolerance benchmark between forecasting and actuals of
5%. Over the course of this annual report , the 5% variance benchmark has been exceeded twice due to unanticipated additional days in the run up to and follow on from SPRING’s first Boot Camp. SPRING has set a long term internal goal to reduce this variance tolerance to 2%. So far, this has been surpassed 5 times over the year. Bumps in forecasting are not unexpected in the first year of a project, as the team works to accommodate rapid changes and unexpected activities in the start-up period. Overall, an average variance of 2.4% has been achieved for the year and we anticipate that
individual monthly forecasting variances will decrease as lessons are learned and adjustments made
going forward.

Table 1: Actual vs forecasted expenditure
	Actual	Forecast	Variance	%
Nov-14	£177,246	£178,895	-£1,649	0.9%
Dec-14	£300,978	£307,724	-£6,746	2.2%
Jan-15	£86,255	£86,950	-£695	0.8%
Feb-15	£205,508	£202,846	£2,662	1.3%
Mar-15	£94,239	£93,343	£896	1.0%
Apr-15	£81,631	£84,244	-£2,613	3.1%
May-15	£80,514	£74,582	£5,932	8.0%
Jun-15	£392,294	£396,059	-£3,765	1.0%
Jul-15	£197,874	£191,955	£5,919	3.1%
Aug-15	£350,073	£341,212	£8,861	2.6%
Sep-15	£337,228	£317,480	£19,748	6.2%
Oct-15	£220,712	£222,499	- £1,787	0.8%
	Actual			%
Total	£2,303,840			2.4%

Date of last narrative financial report	31st August 2015
Date of last audited annual statement

E: RISK

Overall risk rating: High

The overall risk rating is High, though the risk rating of the two outputs scored in this annual review are medium. This programme is explicitly designed to test assumptions and build evidence in an area where the evidence base is weak. Using a private sector development approach to improve girls’ ownership of assets could lead to big returns, but remains a novel approach. Rigorous monitoring and evaluation, and continuous focus on research continue to be critical to the success of this initiative, given the experimental nature of programme design and the weak evidence base on interventions that work sustainably and at scale, to increase girls’ access to assets.

Overview of programme risk

TYPE OF RISK	P	I	POTENTIAL IMPACT	MITIGATION STRATEGY	OCTOBER 2015 UPDATE
Poor quality of applications from applicants	L	H	Team will not be able to fully disburse its target amounts and potentially not be able to hit targets.	The team will undertake pro-active targeting and marketing of the grantees before and during the application process and will work closely with pipeline partners as well as undertake a rigorous due diligence process and a finalist selection camp, evaluated by partners, investors and industry experts.	Lessons learned and key insights on outreach and application process presented by Context Partners at Steering Committee; these inputs among feedback from consortium and evaluation partner will support refinement of Cohort 2 design, outreach and selection process.
Poor Safeguarding of girls	L	H	Limited understanding or implementation of process to safeguard girls who are engaged through this programme.	Palladium takes the safety of girls very seriously. We will have a Girls Safeguarding Advisor in place to oversee the implemention of the girls’ safeguarding policy including a Code of Conduct and a set of minimum standards to ensure that girls are kept safe.	This risk remains low. Any staff member, subcontractor or consultant likely to come into contact with children and adolescents, as part of SPRING, are required to read and undergo face-to-face training on the SPRING child protection / safeguarding policy which was developed and approved in April 2015. / This policy details a comprehensive set of policies, protocols and reporting mechanisms which builds on the Palladium global child protection policy. / The first round of safeguarding training was delivered by Rebecca Calder prior to the Girl Consultations and Selection Camp. Entrepreneurs are required to commit to developing and implementing a girl safeguarding plan which will enable their own business to avoid or reduce risk to girls from business operations, products and services.
Limited traction of new-market based approach to reaching girls	M	M	Challenges in implementing new innovative girl-led approach by grantees creates barrier to programme expansion	Extensive landscaping/needs analysis will be undertaken prior to the second cohort and ongoing support and access to relevant expertise.	A detailed module about adolescent girls will be delivered at bootcamp and follow-on prototyping with girls and technical assistance to entrepreneurs aimed at supporting entrepreneurs to put girls at the core of their products, services and/or business models. This will continue into future cohorts.
Grantee business / models are not / commercially / viable or attract / insufficient / investor interest	M	H	Grantee / businesses are / unsustainable / and do not / reach goals on / the scale / targeted.	The programme selection strategy / identifies high-quality, commercially viable businesses and provide comprehensive, targeted support through boot camps, pitch camps, mentorship and support by local partners to continually refine their business model	Accelerator activities – bootcamp, TA, mentors - are targeted at enabling high potential businesses to be investment ready. We recognize that for some of our earlier stage businesses, this journey may take longer due to need to build capacity and generation of revenue. Suzanne, the Investment Director will be leading the / investment process alongside the Country Managers.
Delays/Slow / Implementation	M	H	Given the restructure, move to new countries, delivering cohorts 2 and 3 at the same time, and recruitment requirements, there is possibility of delays in implementation of cohort 2 which could result in SPRING not achieving results in the given timeframe	SPRING will adhere to the timeframe / detailed in the TOR and mobilise resources accordingly. Our approach in new countries will leverage existing networks and work with experienced partners who have delivered similar activities.	Cohort 2 launch and timeline will be finalized in November 2015. / Recruitment of team in London will be finalized by January 2016. / Context research and outreach in the new South Asian countries for Cohort 2 will begin in February 2016.
Funds will not be raised in time for Cohort 4	M	H	Not delivering a cohort 4 could result in SPRING not having the original scale of impact envisioned for the programme	A fundraising manager will be recruited by January 2016 and the M&E Partner will develop a methodology for assessing the value of in-kind contribution	A fundraising programme with clear milestones will be developed by March 2016.

Outstanding actions from risk assessment:
The risks on Grantees attracting investor interest and delays in implementation are both risks with medium probability and high impact. Recommended mitigation actions are suggested above and progress against these should be reviewed in February 2016.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

SPRING continues to deliver the programme to the planned timeframe.

Performance of partnership (s)

The performance of partnerships continues to be positive. In this next phase of implementation, particularly in light of forthcoming changes, there will be greater donor engagement for the first quarter of 2016.

A contract amendment is currently underway for reasons, outlined on page 1 and 2 of this annual review.

Asset monitoring and control

SPRING has not purchased many assets due to the diffuse nature of the SPRING programme across
multiple countries and the use of partner organisations where possible. A full asset register is maintained
in the Nairobi office, items are appropriately tagged and stored in secure locations. Once the office has
been relocated to London, the asset register will be split, with any items transferred to London recorded in a separate register to those maintained in Nairobi under the care of the East Africa regional coordinator. Palladium operates a policy of internal quarterly spot checks on operational processes in all programmes, including testing the asset management procedures which were found to be strong on the last spot check undertaken by the operations team in September 2015.

G: CONDITIONALITY

Update on partnership principles (if relevant)

No funding was dispensed to a government under this programme

H: MONITORING & EVALUATION

Evidence and evaluation

In February 2015 Coffey International Development (the M&E Partner) were contracted to provide independent Monitoring and Evaluation support to SPRING. The M&E Partner submitted their inception report in September 2015, outlining the overall evaluation approach and methodology. The draft evaluation questions and evaluation framework were shared for peer-review with the Implementing Partner’s internal M&E Partner to ensure that their information needs are met. Some final revisions to the Inception Report are in progress and will be completed in December 2015. In the meantime, evaluation activities are in progress.

In September 2015 the Implementing Partner developed the KPI data and business operation data forms to be filled in by all entrepreneurs on a biannual basis. The KPI baseline data was supposed to be collected before the start of SPRING activities (i.e. before the bootcamp) in early July 2015. However, due to staffing changes in the Implementing Partner’s M&E function, this data could only be collected retrospectively in October / November 2015. It is expected that the KPI baseline data for the second cohort will be collected before the start of the accelerator activites.Tailoring these forms to collect information for both the Implementing Partner and M&E partner will reduce the reporting burden on entrepreneurs significantly.

The M&E partner completed visits to Kenya, Rwanda and Uganda in October 2015. During these visits, members of the M&E Partner observed the Human Centred Design Workshops and one-on-one prototyping sessions with entrepreneurs to inform the design of business research activities for selected entrepreneurs (as part of the M&E partner’s Business Performance Evaluation). The M&E partner, in collaboration with the Implementing Partner, has selected six entrepreneurs to receive this additional research support before the end of March 2016.

As part of the entrepreneurs M&E support package within the accelerator, a diagnostic session to understand entrepreneurs’ current M&E practices and capacity was held with all entrepreneurs at bootcamp, and an M&E module was delivered at bootcamp so that entrepreneurs may develop M&E plans to track their progress around business performance and girl impact. Twelve of the 16 entrepreneurs who completed a bootcamp feedback form (administered by the implementing partner) found the M&E session “very useful” and 11 entrepreneurs said they would welcome more M&E support.

Process for this Annual Review

The Annual Review Assessment Period for SPRING is from 1st November 2014 to 31st October 2015. This year’s AR has been a desk-based review undertaken based on information provided in the Implementing Partner’s Annual Report and the independent M&E Partner’s assessment.

The Implementing Partner submitted their Annual Report in September 2015. This report provides information on the progress thus far and the activities delivered. The M&E Partner have also provided inputs into the Annual Review, ensuring that information and evidence gathered is included in the overall score. The M&E Partner’s contributions to this AR template incorporate findings from desk based research, in-country participation and observation of implementation activities, and a review of surveys conducted with SPRING entrepreneurs by the M&E Partner.
Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process