Annual Review (AR) - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Ghana - Western Region Coastal Foundation (WRCF)
Programme Value: £ 9,500,000		Review Date: 30 November 2015
Programme Code: 202426 / (PO 6608)	Start Date: 30/01/14 / (supplier contract start date: 22/10/14)	End Date: 31/12/19 / (supplier contract end date: 21/10/19)

Summary of Programme Performance
Year	2014	2015
Programme Score	C	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

This annual review was brought forward to cover the period from March to November 2015 to coincide with the completion of the inception phase (Dec 2014 – Sept 2015) and to reset the AR date to review in future a full calendar year of implementation. This review also deliberately ran in parallel with the AR of the Ghana Oil and Gas for Inclusive Growth (GOGIG)[1] programme.
[1] http://devtracker.dfid.gov.uk/projects/GB-1-204330/

The programme has made good progress overall through the inception phase. Most notably the programme:
Effectively established the Coastal Foundation including its registration and launch; the platform set up the Citizens Advisory Council (CAC) as well as a Board which has met several times, including active participation from Ghana Gas (GG) and Ghana National Petroleum Corporation (GNPC) amongst other stakeholders; a branding and a communications strategy is in place; a resource mobilisation plan has been developed, including partnership frameworks with Jubilee oil field partners, and a draft memorandum of understanding with the Petroleum Commission (PC).
- Made excellent progress in setting up the dialogue structure including achieving a good gender balance which required additional effort to encourage and accommodate those with children. Steps included setting criteria for facilitators and providing crèche areas. This led to engagement and satisfaction related milestones being exceeded.
- Completed an assessment of economic development opportunities for the Region with five priority value chains identified. From the five priority areas, two pilot interventions for agriculture (cassava) and aquaculture (fish farming) were presented to the Board and have been approved in principle.
- Monitoring, Evaluation and Communication: A number of knowledge, evidence and learning products have been developed, including internal reflection products. This has been complemented with publicity and outreach activities to enhance awareness.

Summary of recommendations for the next year

- By March 2016: The management of the Foundation should reflect on the resource mobilisation model and strategy to ensure it is sufficiently adaptive and leads to building a self-sustaining and viable Foundation that quickly starts to go beyond a livelihoods focus to broader economic development for the Western Region.
- By March 2016: The Foundation management should ensure appropriate guidance and monitoring is in place to mitigate the risk of conversation managers actually becoming or being perceived as the fixers of community issues.
- By June 2016: The WRCF team should consider how value chain analyses should be linked further to skills development. The DFID Lead Adviser should share learning from DFID’s Skills for Oil & Gas programme.
- By June 2016: The DFID Lead Adviser should explore new entry points for industry engagement now that foundational relationships in country have been established. This should strengthen coordination with industry participants.
- By June 2016: The WRCF team, with support from the DFID Lead Adviser and Programme Manager, should seek to strengthen the operational link between the WRCF and GOGIG, as well as the civil society stakeholders GOGIG is engaging with, and continue to learn from other initiatives e.g. DFID Ghana’s market systems development programmes, AgDevCo and CDC investments in the country and region.
- By June 2016: The WRCF team, with support from the DFID Results Adviser and Lead Adviser, should review the level of ambition and milestones of the logframe and Theory of Change, given progress to date, and make any revisions. The DFID Lead Adviser should determine whether the proposed revision by WRCF to the Outcome statement be accepted and seek approval for this.
- By June 2016: The WRCF team should provide further clarity of consortium roles and structures.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4269826.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4269768.xlsx

Outline of the programme

DFID Ghana’s Operational Plan identified the oil and gas sector and its governance and management as a key issue - as a potential driver for development which could accelerate graduation from aid, and as a risk if managed poorly. This is addressed with a set of initiatives, including the GOGIG programme at national level and the WRCF in the local context of Ghana’s main oil and gas producing region.

WRCF has set up a Coastal Foundation to make effective use of Corporate Social Responsibility (CSR) funds from international and domestic oil and gas companies for development, conflict-prevention and growth in the Western Region. An innovative structured dialogue mechanism brings together civil society, the private sector, regional and local governments. Ideas, suggestions and grievances from the concerned residents are channeled regularly through the Foundation’s dialogue structure to increase transparency and to deepen accountability between stakeholders. Funds will be used to support local development aimed at socio-economic and environmental benefits that improve inclusive growth and welfare.

The programme expects to achieve increased stability and inclusive growth, through:

- Reducing the risk of conflict, which also has major financial and environment returns in terms of safeguarding oil production[2] and mitigating its adverse impacts;
  [2] As at the end of year 2014, nearly US$ 3 billion (US$ 2.811 billion) has accrued to the State as petroleum revenues since first oil in 2010. - http://piacghana.org/2014PIAC.pdf
- Increasing growth and employment prospects, through better planning and development, addressing local barriers to growth and improved education. As local skills develop, industry value-chains will increasingly be localised, to the benefit of residents as well as companies;
- Mitigating adverse local socio-economic impact and improving the livelihoods of affected communities, through better targeted support and programmes from both CSR initiatives and government interventions.

The programme Outcome is for: Citizens to benefit from improved investments and for trust to be built between communities, government and industry. This will be achieved through four Outputs:
Output 1:	Coastal Foundation provides locally owned, sustainable platform for coordinated development in Western Region coastal districts.
Output 2:	Independent and inclusive dialogue structure promotes transparency, responsiveness and collective action on local development issues.
Output 3:	WRCF supports local development interventions.
Output 4:	Evidence generated and communicated to enhance stakeholder learning and inform programming.

Changing context: The WRCF business case envisioned a total of around £16 million in direct financial contributions to the Foundation from international oil companies (IOCs). Since its approval, no contributions have materialised, and the landscape of oil and gas investment and the political economy of the sector have changed substantially. Three critical changes now shape the environment in which the WRCF programme operates:
1)	The dramatic drop in the price of crude oil;
2)	The growing role of the new Petroleum Commission as regulator and of State Owned Enterprises (SOEs) as operators in the industry;
3)	Internal shifts in staffing, budgeting, and corporate priorities amongst and within the IOCs.

WRCF has internalised this information to restructure its approach to institutional and corporate engagement and expectations for resource mobilisation targets, and measurement of contributions. Whilst there are potential negative repercussions of the changing context, these also present an opportunity to recalibrate the focus to ensure the local development interventions made are directed at the most value-maximising activities for both communities and the region’s economic development. The first and third of the identified contextual changes are not uncommon to this sector, and this presents an opportunity to reinforce the strategic and long term approach of the Foundation to manage this uncertainty. Despite the changing context, there is certainly value in this programme and if recommendations are taken on board in addition to the Foundation’s own adaptive endeavours then it can still progress to achieving the initial theory of change in the Business Case. This includes leading to ‘reducing instability by addressing political settlement through dialogue, expectations through the delivery of a harmonised CSR strategy focussed on transforming the incomes and employment opportunities of those most vulnerable to social and economic impacts and creating jobs’. At the time of this review, the final settlement of Coastal Foundation financing, operational objectives and spending plan are still to be agreed. This is in line with expectation, however, this should be finalised as soon as possible to allow clarity in direction.
B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The programme outcome is to enable the building of trust between communities, government and industry and for citizens and the region to benefit from improved investment in socio-economic development. While progress has been made on setting up the Foundation and the dialogue structure, it is too early to tell if the programme is on track to achieve the intended outcome by the end of the programme, however, as the Theory of Change still holds it is expected the outcome will be met. This is in part due to the programme transitioning from inception to implementation, but also with changes in some milestones and the macro-economic environment. The next Annual Review period, following full implementation, will be a test of progress towards outcomes and ultimately impact.

Overall output score and description

Score A: The main project components are generally on track against a revised logframe, and in some cases performing above expectations (e.g. Outputs 2 and 4).

Key lessons
- Scenario planning – given the volatility in the oil and gas market, upon which budgets for non-core activities by corporates are based, stronger scenario planning could have been done at the Business Case stage to allow mitigating actions to be planned where external funds would not be forthcoming, including deeper engagement with senior stakeholders of the corporates in particular at Head Office level.
- Private Sector Development Adviser (PSD) input – the Foundation has a core economic development focus albeit within a governance based programme, and as such it would be useful to ensure that PSD adviser input is formalised and potentially goes beyond the 10% time currently allocated once implementation of the economic development activities commences.

Key actions
Proposed actions have been outlined in the document. The key action is to focus efforts on the resource mobilisation model and strategy to ensure these are able to adapt to the changing environment the programme operates in, whilst progressing towards building a self-sustaining and viable Foundation. The WRCF team should draft a plan and actions building on the mid-year brief on Industry Trends, Resource Mobilisation and IOC engagement prepared by the Foundation by March 2016. The Ghana Oil and Gas for Inclusive Growth (GOGIG) programme will be well-placed to help in this regard.

Has the logframe been updated since the last review?
The logframe was revised during the inception period, in particular to bring outputs and milestones in line with current programme activities. A new output (4) was created placing greater emphasis on generating evidence of the programme’s results and communicating more widely to enhance learning, to guide programme strategy and to inform the public. Output 1 has been refined to include language around transition to local ownership and sustainability of the Foundation, and output 3 was refined to reflect pilot funding as well as research, design and technical assistance.

A new outcome statement has been proposed to be more specific and measurable including an addition to incorporate citizens benefiting from investment being an explicit outcome. The change is thought to be useful, and makes the statement more specific and measurable, but the reviewers did not consider it to be a significant change from its initial version.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Coastal Foundation provides locally owned, sustainable platform for coordinated development in Western Region coastal districts
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Establishment and transfer of a Coastal Foundation to an independent and effective institution[3].	WRCF registered and launched. / Foundation Board formed and met. / Governance model and structure approved by the Board. / Citizens Advisory Council established. / Branding and communication plan established. / Resource mobilisation plan developed.	All six milestones have been achieved
Proportion of non-DFID funding of Coastal Foundation operations	0%	Preparatory steps completed and engagement of Oil, Gas, and Power (OGP) industry funding partners started.
[3] The wording is set out as an output/deliverable rather than an indicator, and should be reconsidered at the next logframe review.

Key Points
With the establishment of the Foundation a platform for partnership has been set. However, given the changing operating environment WRCF requires effective adaptation of the Foundation and of its strategic priorities to accomplish the intended aims. This is something that the programme team recognise and are already taking actions to adapt, e.g. refining the resource mobilisation model. While at the time of this review, the final settlement of Coastal Foundation financing, operational objectives and spending plan were still to be agreed, it is recognised that the WRCF team progressed in line with expectation and are still in learning mode. The team will need to continuously take an adaptive programming approach to maintain progress in a changing and uncertain environment.

Contextual changes including the drop in crude oil prices, increased presence of the Petroleum Commission and State-owned Enterprises (SOEs) and internal shifts in oil companies have led to a revision of the assumption that International Oil Companies (IOCs) would directly contribute a total of around £16 million to the WRCF. Therefore the focus of the WRCF resource mobilisation approach is evolving to coordinating, influencing and leveraging corporate social investments, “local content” and supply chain development activities of corporate partners. According to the programme team this will be achieved through partnerships, co-design or direct co-funding of projects, and service provision.

The WRCF team aim now is to leverage enough funding from the oil and gas industry to cover development interventions and 95% of the operational costs of the WRCF by Year 5 - translated to £0.5 million annually from corporate and other stakeholders. WRCF will mobilise these resources initially by targeting companies whose operations are most likely to benefit from its programmes including the dialogue platform, economic development activities and impact measurement such as Ghana Gas[4], Jubilee Partners led by Tullow Ghana Limited[5] and Atuabo Freeport[6]. The actions during implementation phase will reveal how tough this is, however, discussions with Tullow Oil reveal budget pressures mean long term commitment for contributions is not possible. However, there are an increasing number of stakeholders, and methods of mobilisation, as a result the risk register appropriately has designated the risk of being unable to mobilise resources as medium.
[4] Ghana Gas operations directly impact 55 communities along its pipelines and near its processing plant and it is the subject of many community conversations and grievances.
[5] Tullow Ghana Limited is keen to understand the full impact of its operations on coastal residents in the Western Region especially fishing communities and support any mitigation measures and has already initiated livelihood interventions.
[6] The Atuabo Freeport project will directly affect three communities in the Ellembele district and beyond, requiring a robust and sustainable livelihood programme that is regularly monitored and reported.

Summary of responses to issues raised in previous annual reviews

The logframe has been revised following recommendations in the last Annual Review. The Output statement has been refined to include language around transition to local ownership and sustainability of the Foundation. The individual indicators have also been updated to ensure alignment.

Recommendations

- By March 2016: The WRCF team should ensure the resource mobilisation model and Strategy reflects an adaptive approach that builds a self-sustaining and viable Foundation, maintaining an appropriate balance between ‘soft’ interventions i.e. research, analyses and ‘hard’ interventions i.e. pilots and investments to scale up and catalyse market development. This requires a clearly determined operating model for the WRCF either as an implementer of interventions or facilitator of planning / monitoring of social investment implemented by IOCs/SOEs with an appropriate remuneration/fee model built.
- By June 2016: The DFID Lead Adviser should explore new entry points for industry engagement now that foundational relationships in country have been established. This should strengthen coordination with industry participants. This includes pursuing top-level buy in, in particular with senior stakeholders that may already have a relationship with DFID HQ.
- By June 2016: Linked to the point above, there may be merit in WRCF conducting an analysis of new IOC entrants to the Western Region to identify opportunities and decision making windows for pursuing shared value through investments in developing the region and communities within it. This engagement plan should be actioned during the course of the year.
- By March 2016: the WRCF team should propose to the Board that a Finance Committee should be established as a sub-Committee focused on finance and investment matters to strengthen corporate governance of the Foundation. Further strengthen the operational link between the WRCF and GOGIG programmes. The WRCF team should leverage on the convening power of GOGIG (which has managed to build strong relationships with relevant GoG Ministries, in particular the Petroleum Commission (PC)). The WRCF team should also inform GOGIG of local community and government views and discuss ways in which these views can inform government policy.

Output Title	Independent and inclusive dialogue structure promotes transparency, responsiveness and collective action on local development issues
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes[7]
[7] Weighting changed to accommodate an additional output.

Indicator(s)	Milestones	Progress
#of Western Region coastal district residents engaged in the dialogue structure	5,400 direct / 21,600 indirect	Exceeded: / In excess of 46,500 direct; 186,000 indirect (44% women). This is approximately the cumulative expectation for up to 2018.
# of times community issues presented to the Citizens Advisory Council (CAC )	1	Achieved. / Data on community issues collected, analysed and CAC session facilitated to review and discuss with respondents.
# times industry and government responses to issues are fed back to community Area level meetings	1	Achieved / One round of feedback sessions per each community (90), area (18) and district (6), with 114 meetings in total.
Stakeholder satisfaction with dialogue process (%) (community members, government and industry)	50%	Exceeded: / Survey conducted showing 83% satisfaction levels amongst community members. / 60% industry satisfaction. / No government survey conducted yet.

Key Points
During the inception phase a strong dialogue structure and platform has been established. The organisational success is evident through the figures presented by the programme team and observations during the field visits. Highlights include:
- 46,500 people directly engaged (including 40% female) by 18 Community Facilitators (40% female) and the Dialogue Secretariat. Using crowd sourcing measures namely radio, television and social media circa 186,000 people were indirectly reached.
- Emerging issues aggregated at area, district and regional levels and prioritised into 7 broad categories (economic development, health, water, education, infrastructure, environment and governance). 4 priority issues presented to the CAC which made recommendations on 9 areas under the 4 priorities.
- Industry and government stakeholders received recommendations from the CAC. Where responses were received the dialogue structure has facilitated feedback to communities.
- Conversation Managers conducted 114 feedback and follow up-meetings in the communities.
- A stakeholder satisfaction survey conducted using random sampling of beneficiaries in the communities showed 83% of residents were satisfied with the dialogue process. 60% industry satisfaction based on a Survey Monkey online survey. Government has not yet been surveyed but there is a plan to do this by March 2016.

Proactive conversation managers and a well-designed dialogue structure have both contributed to milestones being exceeded, but the way that progress is measured is also important. The current measure counts all those attending sessions including people who have attended previous sessions to demonstrate continuous dialogue and engagement. This essentially gives a cumulative number instead of ‘new people engaged’. Tracking both figures will be useful.

Initial findings from community conversations show that while issues around employment and cost of living top the list, social development needs, particularly service delivery, are also high priority. There are also a number of issues that do not directly relate to WRCF or the Oil, Gas and Power industry responsibility. The team is considering how best to address these needs, looking at the risks involved and opportunities and interest from government and industry, in order to find the most promising areas where the WRCF can help broker a solution.

Notwithstanding the huge organisational success, substantial risk is also emerging in terms of two aspects, (1) potentially excessive expectations raised by WRCF with such a well-developed structure, especially if facilitation teams fail to bring in all stakeholders in direct dialogue and also (2) risk of actual or perceived allegiance to any one of the parties (IOC or SOE or Government) instead of the communities.

Summary of responses to issues raised in previous annual reviews

The logframe has been revised following recommendation from the last Annual Review. The Output statement has remained the same; however, the indicators to measure progress and success have been refined.

Recommendations

- By June 2016: the WRCF team should revisit the level of ambition in light of the excellent progress during inception phase which has resulted in achieving outputs expected by 2018. In particular, the team should assess whether to re-prioritise efforts to other outputs now that a strong dialogue structure has been built once sustainability of the platform is confirmed.
- By March 2016: The WRCF team should revisit the measurement criteria of milestones to ensure appropriate and to mitigate against the risk of double counting.
- By March 2016: The WRCF should develop a strategy for stakeholder satisfaction surveys, considering appropriate timing and frequencies, and using the data to inform risk assessments.
By March 2016: The WRCF team should ensure appropriate guidance and monitoring is in place to mitigate against the risk of conversation managers becoming or being perceived as the fixers of community issues instead of acting as a diplomatic function to facilitate dialogue.
- Continuous training (including on gender awareness) should be provided as part of the monitoring approach to strengthen facilitation capability as well as understanding of the petroleum sector.
- Further strengthen coordination with industry participants and other government stakeholders (Petroleum Commission etc) to ensure alignment and complementarity in particular to mitigate risk of replacing government in their functions.

Output Title	WRCF supports local development interventions
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes[8]
[8] Weighting changed to accommodate an additional output

Indicator(s)	Mile / stones	Progress
# of pilot intervention designs approved	2	Achieved. / Preparatory steps completed including economic and sector analysis and concept designs for 2 pilots (fish and cassava) approved by WRCF Board.
# of pilots demonstrating positive benefit and % scaled up	0	Targets to come into effect in the next phase when impact can be assessed as a basis for scaling up.
# of interventions receiving external support	0	Targets to come into effect in the next phase when results can be used as a basis to attract external support.
# of independent investments WRCF has influenced	1	Achieved. / WRCF has carried out analysis of economic development opportunities for the region with options outlined, for which two pilot interventions have currently been identified and received investment approval in principle by the Board. This is for a cassava production and fish/aquaculture project linking farmers/fisheries to end markets through aggregation system and processors.

Key Points
WRCF operations started as oil and gas operators in the region often had CSR investments already locked in. In acknowledgement of this, and intended as a ‘quick-win’, the team has been pursuing analyses to identify priorities focused on a livelihoods approach. However, this needs to be expanded and shifted towards a market systems development approach, i.e. developing the private sector to catalyse inclusive growth in the region[9]. An important element that tends to be missing or weak in most existing CSR investments is the development of technical skills (at TVET level) to increase the employability of local workforce, in particular in value chains directly related with oil & gas operations. WRCF could play an important role as a facilitator to help industry and Government to fill the gap.
[9] The Foundation is collaborating with Tullow on transport & logistics, another identified priority within the value chain analysis.

WRCF is unlikely to reach its target beneficiary numbers or to achieve measurable changes at outcome level without significant leveraging of resources. The expectation of the team is that once WRCF demonstrates successful results from pilot interventions, private sector organisations will support the Foundation to scale up interventions in the six coastal districts. This is an ambitious expectation in light of shifting priorities of the oil and gas companies operating in the region. The uncertainty around resource mobilisation poses significant challenge to the team’s ability to plan and programme, which is already reflected in the risk register.

Summary of responses to issues raised in previous annual reviews

The logframe has been revised following recommendations made in the last Annual Review. The Output statement has been refined to allow it to reflect pilot funding as well as research & design and technical assistance. The individual indicators have also been updated to ensure alignment

Recommendations

- By March 2016: The WRCF team should ensure that the resource mobilisation model reflects an approach that builds a self-sustaining and viable Foundation, requiring a clearly determined operating model for the WCRF either as an implementer of interventions or a facilitator of planning/monitoring of social investment implemented by IOCs/SOEs with an appropriate remuneration/fee model built.
- By June 2016: The WRCF team should implement economic development interventions. To achieve the ambition of developing the private sector (which is the engine for growth via job creation) in the region will require an approach that goes beyond focusing on livelihoods. Whilst actions taken now for short term solutions are important, actions should also be taken now for results that will crystalise in the medium term which is the time scale needed for developing appropriate private sector participants to support the petroleum sector as well as other sectors required for the future development needs of the Western Region e.g. the Atuaba Port development. These actions should include a horizon scanning exercise to determine the development needs of the industry, the Western Region and determine the mechanisms by which the Foundation can support in moving beyond livelihoods to economic development of the Region.
Continuous: The WRCF team should seek to drive synergies through further coordination with GOGIG who are also carrying out analyses assessing the needs of the oil and gas industry, development needs of the country and identifying opportunities for policy level interventions that could lead to inclusive growth. This will ensure VfM is enhanced.
By June 2016: The WRCF team should ensure that value chain analyses are linked further to skills development to ensure that enterprise development work being done is joined up with skills and capacity development to enhance employability of those in local communities.

Output Title	Evidence generated and communicated to enhance stakeholder learning and inform programming
Output number per LF	4	Output Score	A+
Risk:	Low	Impact weighting (%):	15%
Risk revised since last AR?	Yes (new output)	Impact weighting % revised since last AR?	Yes (new output)

Indicator(s)	Mile / stones	Progress
# of knowledge products produced	1	Exceeded: / Economic Opportunities Assessment report / Climate Change Strategy / WRCF Community Dialogue Survey Report
# of internal reflection products produced	3	Exceeded: / Dialogue Strategy / Communications Strategy / Value for Money (VfM) strategy / Operations Manual / Monitoring and Evaluation (M&E) Handbook / Resource Mobilisation Strategy and Utilisation Strategies / The quality of these products is reasonable. As the programme moves into implementation it will be important to monitor the use of these strategies and compliance with them by third parties.
# of publicity and outreach activites	2	Exceeded: / 7 engagement events with regional stakeholders / Website designed and ready to launch in implementation phase / WRCF Facebook page launched and regularly updated

Key Points
This output has been introduced since the last Annual Review. Its aim is to generate evidence of the programme’s results and communicate it widely to enhance stakeholder learning, guide programme strategy and inform the public. It provides cross cutting support and cohesion to WRCF’s different strands of activity but also aims at using communication of WRCF’s results to attract partners for scale-up. Publicity and outreach ensure that WRCF participants are accountable and provide accurate information about their responsibilities and activities.

Recommendations

By June 2016: The WRCF team, with support from the DFID Results Adviser and Lead Adviser, should review the logframe and revisit the level of ambition in light of the excellent progress, also assessing whether to re-prioritise efforts to other outputs as well as potentially focussing on assessing impact and the use of products developed.
- By March 2016: Recommend to collaborate with Africa Centre for Energy Policy (supported by GOGIG) who are pursuing studies supporting strengthening evidence base for initiatives such as “oil for agriculture” and “oil for education”, both possibly complementary to WRCF interventions.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The programme is output-based with key performance indicators and milestones driving payments to the suppliers.

The key cost drivers are unchanged from the business case and include:
- The cost of securing the appropriate level skill set for the core programme staff;
- Direct cost of organising programme activities – dialogue, registration and launch of the foundation and endowment fund related activities;
- Indirect overhead costs; office set-up, accommodation, transport and meetings with stakeholders;
- Cost of sub-contracted long and short-term technical advisers during the inception and implementation phase.

VfM performance compared to the original VfM proposition in the business case
On Economy the focus has been on ensuring appropriate value from procurements. Examples of value achieved include project vehicles procured at 40% comparative savings, office leased at the least cost, reduced per diems from £45 to £40, negotiated corporate rates for hotels, and negotiated discounts on event packages.

On Efficiency there has been progress made on achieving favourable outcomes on cost per beneficiary engaged in dialogue structure (direct/indirect and through mass media) where the dialogue structure cost per person achieved was £4.30 against an initial projection of £6.68 per person. Currently, the ratio of international to local short term consultancy inputs is in favour of locals, with 3 local consultants contracted, against international short term advisers limited to 1.5 full time equivalent positions.

On Effectiveness, the programme remains in its early stages so there is a limited amount of data to judge. However, both the outstanding outreach of community engagement and the stakeholder satisfaction ratings indicate positive progress at least in these areas.

Assessment of whether the programme continues to represent value for money

The progress on leveraging funds for development interventions from external sources has been challenged by the changing industry environment due to the low oil price and pre-existing prioritisation of social investment spending by oil and gas operators. This is a fundamental part of mainstreaming VfM and should be monitored closely to ensure progress is made in the forthcoming year with an appropriate pipeline of funds to be leveraged. However, as noted above, both the outstanding outreach of community engagement and the relevant stakeholder satisfaction have been better than expected. The number of interventions receiving external support should fall into place in the forthcoming year as the programme transitions from inception to implementation, and this will provide clearer evidence of VfM.

The VfM indicators set out in the Business Case have been reviewed and modified to link to the revised logframe and cover each of the four outputs. The following changes were recorded under Efficiency and Effectiveness:

Efficiency
1. Ratio of international to local short term consultancy inputs
2. Ratio of staff time spent on management to implementation activities
3. Funds leveraged for development interventions from external sources
4. Average rate of return for pilot and scaled-up projects
5. Success rate of pilot and scaled-up interventions
6. Efficiency gains in programme delivery as a result of programme reflection, learning and evidence products

Effectiveness
1. Ratio of Endowment/Activity Fund to operating costs
2. Quality of engagement (direct, indirect, and through mass media)
3. Extent to which WRCF has influenced independent industry and government initiatives.

Quality of financial management

- A detailed Finance Manual has been developed and largely followed to ensure consistency, effectiveness and transparency in all financial operations. However, a recent monitoring visit by DFID and internal audit conducted by DAI has highlighted a number of weaknesses and occasions when the procedures set out in the manual have not been complied with.
- There are largely good internal control procedures to help to minimise risk of theft, fraud and unintentional errors in recording accounting data. However, it will be important as implementation begins to ensure that these procedures are fully complied with. A project schedule of authority (PSOA) has been developed and followed to enhance staff awareness of authority levels and responsibilities of employees in all financial transactions, but the recent absence of the Team Leader has demonstrated the need for further delegation of authority to ensure that work is not affected by absences.
- Costs have been well managed and within budget. This is to be expected given that payments of fees are made on a milestone basis. Programme and expenses costs that are based on actuals have resulted in some savings in some budget items, which have been used to finance other budget items. For example, savings on the Takoradi office rent budget line have been used to cover the costs of the Accra office space.
- In general, there has been good budget monitoring and accurate quarterly reporting to DFID. Monthly forecast update and clear narrative feedback on the variances is provided, and variances have consistently been less than 10%. However, there have been some issues of concern during the inception phase. For example, neither DAI nor ITAD had budgeted for the costs of conducting a baseline, which should have been foreseen and was not proactively raised with DFID.
- The management of Conversation Managers has not been of the quality expected. This has included inadequate due diligence assessment, insufficient scrutiny of financial reports and instances of delayed payments from WRCF to the conversation managers due to issues including contracting and not complying with reporting timeframes, with the risk that conversation managers have to borrow money to ensure they have appropriate working capital.

It is recommended that, as part of due diligence assessments, a robust scrutiny process is introduced for the conversation managers to ensure appropriate adherence to policy and procedures. Currently each conversation manager is paid the same amount which is evenly disbursed. It would be beneficial to outline what determines this and perhaps have some requirements or triggers for disbursement to ensure appropriate incentives are in place. Appropriate evidence and records need to be maintained to show the chain of communication. Linked to payments, there is an opportunity to strengthen the Delegation of Authority, by setting appropriate authorisation levels for cheque payment to facilitate delivery of programme activities.

The first annual audit of the WRCF programme is planned for January 2016. Processes are currently underway to recruit an audit firm to conduct the assignment.

Date of last narrative financial report	30 September, 2015[10]
Date of last audited annual statement	N/A
[10] Financial narrative reports are not provided, but the quarterly programme report includes a section on finance.

E: RISK (½ page)

Overall risk rating: Medium (unchanged since approval)

Overview of programme risk
WRCF maintains a risk matrix and updates it monthly. Several persistent risks have been identified, or risks which have appeared in the registry several times previously with a medium or high probability or impact, as follows:

Risk: Traditional authorities will want to use the Programme to promote vested interests.
Mitigation strategy: The number of Board and CAC members mitigates against individuals using the WRCF to promote their own members (increased to 17 and 23 respectively, with 3 (18%) and 9 (39%) drawn from traditional leaders). Board and CAC decisions are made transparently and the WRCF publishes minutes of their meetings.

Risk: The WRCF unable to mobilise additional resources from the private sector.
Mitigation strategy: the management firm has expertise working with the extractives industry and will use specialist resource mobilisation staff with a history of working with OGPs. Shifted approach to development interventions enhancing flexibility and responding not only to community demands but also to industry opportunities.

Risk: The programme will lose crucial programme staff.
Mitigation strategy: open communication system and good teamwork within the programme team to enhance continuity in the case of loss of any team member. Database of good resumes for the various positions on the team to facilitate easy replacement.

Risk: The programme could lose credibility if the expectations of potential beneficiaries are not properly managed: Although the dialogue structure has shown high initial engagement from community, government, and industry, it may lose momentum if participants feel the WRCF has failed to address their concerns or is taking sides. This is particularly relevant for community issues raised through the dialogue structure, as they prioritise service delivery which is not in the direct remit of OGPs and which the government does not currently have the resources to address.
Mitigation strategy: The WRCF has established feedback loops so that citizens’ concerns are raised and responses by government and private sector companies can be presented. They have also built in flexibility to help address unexpected and emerging issues during implementation. The WRCF will also closely monitor the security situation in the Western Region, particularly around the time of the national elections in 2016, and will develop an early warning system to alert the WRCF and other stakeholders of potential unrest and potential violence.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
There were significant delays in the tendering and contract process resulting in the programme commencing 10 months after approval. However, work has progressed significantly since the implementing agent has been contracted. Having been extended by 5 weeks (up to 30 November 2015), the inception phase has not yet been approved. There have been some delays in milestone delivery but with prior warning given and approval granted.

Performance of partnership (s)
The relationship between the WRCF programme team and DFID is very good. The DFID team has developed a strong relationship with key programme staff, overcoming the distance between Takoradi and Accra, and the WRCF team is generally very cooperative and responsive.

The performance of the Consortium partnership has been mixed. DFID Ghana consistently raised concerns over the quality of the M&E products delivered by ITAD during the course of the inception phase. DAI made efforts to address this performance issue, including placing ITAD on a performance improvement plan but this was not the best approach and did not yield the positive response hoped for. DAI’s quality assurance role was not of the expected technical quality either, which along with the fact that neither DAI nor ITAD had budgeted for baseline activities, has been time-consuming for DFID to manage. As part of the discussions on the implementation phase, DAI has recently informed DFID that ITAD will not be part of the Consortia moving into the implementation phase and that the M&E function will be undertaken by dedicated M&E experts contracted through DAI. This is assessed as being the appropriate decision but an earlier decision, more consistently communicated to DFID would have been preferable. Corporate Citizenship’s contribution appears to have been largely limited to establishing the status of the Foundation. Corporate Citizenship has not had the relationships with oil industry players to add as much value as was anticipated, which has been taken up by DAI’s Extractives Team. Moving into implementation phase, the programme would benefit from more clarity of Corporate Citizenship’s role beyond supporting results measurement and reporting by corporates, including through the London benchmarking Group framework.

Asset monitoring and control
WRCF programme is not asset intensive. Assets consist of office furniture, office equipment, and vehicles. The supplier has ensured that assets acquired are clearly labelled and identified with the UKAID logo, are well maintained and used solely for the purpose of the programme. There is a comprehensive asset register which is regularly updated. The implementing team reported that regular assessments are carried out on the effectiveness of the control systems, and appropriate improvements guidance is produced. If possible this should be verified in the next monitoring visit report.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The project focuses on poverty reduction in the target area (the Western Region). There are no current plans for any funds to be provided directly to Government or through Government systems. The project does work alongside Government where appropriate in order to enable systemic changes. It does not have substantive links to human rights issues.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The recent significant drop in the price of crude oil stands to affect one of the Business Case assumptions that the OGP industry would contribute £16 million to the WRCF (ToR para. 28). However, this is neither evidence that the theory of change no longer holds, and nor is it a new risk. The programme still aims to leverage funding from the corporate sector to put towards interventions, but the resource mobilisation strategy and delivery models have had to adapt to the changed circumstance. The logframe continues to track the number of WRCF interventions receiving external support and proportion of non DFID funding of WRCF interventions.

An evaluability assessment conducted by the programme recommended an independent evaluation of the programmes as envisaged by the business case. The assessment recommended a hybrid of internal and external evaluation and learning. The programme and internal M&E team would undertake thematic reviews, case studies, annual learning forums, demand driven assessment of impact of corporate investments and component level impact assessment. The summative and formative evaluations would be contracted by DFID to an independent evaluator, who would use internally generated data supplemented with their own primary data collection. However, one of the evaluability report options was to rely on the programme team for evaluative and learning activities, and the review team considered this sufficient, based on the internal M&E strategy that is in place. Timing is also a key issue – one of the motivations for an evaluation is to inform other DFID programmes. Quicker findings, more likely achieved via internal work, would be more useful to inform programmes under design, rather than more comprehensive external analysis at a later stage which may be too late.

Based on the assessment, the overall project design and results structure has been revised to ensure that the programme design, logframe, monitoring system, and baseline provide evidence for evaluation and learning activities. This will further enhance internal M&E.

Monitoring progress throughout the review period

Programme monitoring is undertaken internally by programme M&E staff and externally by DFID through its regular meetings with the programme management team. The Lead Adviser holds a weekly catch-up conversation or meeting the WRCF Team Leader, along with more formal monthly programme management meetings which take place in Accra. In addition, the DFID Lead Adviser and Programme Manager have travelled to Takoradi on 8 occasions over the course of the inception phase.

Internal monitoring is undertaken through regular tracking of component level action plans and the use of monitoring tools and templates to track progress of work by the implementing partners. For output 2 in particular, monitoring of progress against milestones needs to be more closely aligned with logframe indicators. Regular field visits are conducted by M&E and dialogue secretariat to ensure quality delivery by conversation managers.

As part of eliciting stakeholder feedback, a satisfaction survey has been conducted to understand the perception of stakeholders on the dialogue process. A Survey Monkey online survey was also conducted to capture the satisfaction of industry partners and there is a plan to survey Government partners by March 2016.

Three quarterly reports and 8 monthly reports have been submitted. The programme inception report has also been submitted to DfID.

This Annual Review was undertaken by three DFID advisers – an extractives adviser from the central Governance and Extractive Industries Team in ARD; a private sector development adviser from PSD; and the Regional Extractives Industries Adviser for East Africa. The review took place simultaneously with that of the GOGIG programme, consisted of desk review of documents submitted by the programme teams, followed by 10 working days in country. The time in country included initial briefings from the programme teams, followed by interviews with selected beneficiaries.