Annual Review – post April 2018

Title: Ghana Oil and Gas for Inclusive Growth (GOGIG)
Programme Value £ (full life): £14,517,621		Review Date: 31/10/2019
Programme Code: 204330	Contract Start Date: 8/12/2014	End Date: / 14/12/2019 [extended to 30 Jun 2020]

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019
Programme Score	B	A	A	A+	A+
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4269520.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5584543.xlsx

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Ghana Oil and Gas for Inclusive Growth (GOGIG) programme was set up to deliver the G8-Ghana partnership on Extractives launched by the UK Prime Minister and the President of Ghana in 2013. It was meant to support Ghana to make the most of its then new-found oil and gas resources. The programme began in December 2014 and will end in December 2019.

The expected Outcome of the programme is effective management of oil and gas resources in Ghana to contribute to the overall impact of inclusive economic growth and poverty reduction through a well-managed oil and gas sector. The programme is designed to be delivered through five inter-related Outputs as follows;

- Output 1: Regulatory mandate and policy coherence in the oil and gas sector enhanced working with the Ministry of Energy and Petroleum Commission
- Output 2: Oil and gas revenue capture and oversight improved.
- Output 3: Oil and gas revenue management and oversight improved.
- Output 4: Enhanced public engagement and oversight of the oil and gas sector.
- Output 5: Non-revenue pathways (e.g. local impact, local business participation, gas to power) by which the oil and gas sector can contribute to inclusive growth identified and enhanced.

A new output (Output 6) on capturing and disseminating learning from the programme was added last year, reflecting that the programme should be seeking to disseminate lessons from its implementation model and experience in the sector to inform future engagement on extractives in Ghana, and the future design of technical assistance programmes.

The programme works in partnership with both state and non-state institutions, including the Ministry of Energy (MoE), Petroleum Commission (PC), Ministry of Finance (MoF), Ghana Revenue Authority (GRA), Bank of Ghana (BoG), Ministry of Environment, Science and Technology (MESTI), Environmental Protection Agency (EPA), Ghana Oil and Gas Service Providers Association (GOGSPA), Public Interest and Accountability Committee (PIAC), Ghana Extractive Industries Transparency Initiative (GHEITI) the Africa Centre for Energy Policy (ACEP) and Civil Society Platform on Oil and Gas (CSPOG), and other Civil Society Organisations (CSOs).

GOGIG’s package of support includes provision of technical assistance, grants, systems and tools, capacity building, commissioning of research and analyses, facilitating cross-agency coordination and cooperation and the convening of multi-stakeholder dialogues on critical sector issues

Summary supporting narrative for the overall score in this review (1/2 page)

The overall score is A – based on 7 indicators achieved, 3 exceeded and 2 partially met.

Output	Description	Weight	Score
1	Regulatory mandate and policy coherence in the oil and gas sector enhanced: / One indicator milestone substantially exceeded, one achieved	20%	A+
2	Oil and gas revenue capture and oversight improved: / Both output indicator milestones achieved	20%	A
3	Oil and gas revenue management and oversight improved: / One indicator achieved, one partially achieved	20%	B
4	Enhanced public engagement through, but not limited to, increased accountability actors' capability for oversight of the oil and gas sector: / One indicator milestone achieved, one exceeded	15%	A+
5	Non-revenue pathways by which the oil and gas sector can contribute to inclusive growth identified and enhanced. / One indicator milestone achieved, one exceeded	15%	A+
6	Documentation and dissemination of programme learning / Both indicator milestones achieved	10%	A

Some key developments in the Oil & Gas sector in Ghana this year, and GOGIG’s contribution:

The launch of Ghana’s first competitive bidding rounds for allocation of oil blocks – this first competitive process was launched in October 2018. GOGIG has supported the process both through technical inputs with the MoE and supporting civil society monitoring efforts.

Potential expansion of production from new Aker energy activity - In January 2019, Aker Energy, operator of the Deepwater Ta-no Cape Three Points (DWT/CTP) block announced that an initial reappraisal indicated that the Pecan4A well could hold some 450 to 550 million barrels of oil. That could add $640m to Ghana’s earnings from the sector by the next two years. GOGIG supported scrutiny of Aker’s Plan of Development for the fields submitted to government, working with CSOs to harmonise understanding and monitor revisions made to regulations. This is the first occasion that the Petroleum Commission (PC) made use of the Petrel software procured for them by GOGIG to review a company PoD for cost-effectiveness and assess the appropriateness of the technological approach proposed.

Completion of seismic studies in the Volta basin for on-shore development – GNPC completed its reconnaissance programme for 1700 square kilometres on the surface of the Voltaian basin. GOGIG joined the GNPC and PC team for some of its engagements with communities and has done extensive work this year on developing a local impact management framework for onshore activity.

The output milestones related to “number of initiatives” have been scaled back compared to last year, in recognition that the final year of the programme will be consolidating learning and gains made over the course of the programme rather than undertaking a large number of new initiatives.
However, the outcome level results have shown an acceleration in progress in this year – providing some evidence of the cumulative impact of interventions over the programme lifetime. Key outcome level results for this year include:
- GRA captured an additional USD177m of revenue, of which USD 63.84m was attributed to GOGIG interventions, as agreed with partners.
- A score of 83 on the Resource Governance Index, representing a 29% improvement on the baseline score of 64 in 2014
- The Ministry of Finance (MoF) for the first time compiled and published a list of projects to be funded by ABFA in the 2019 budget. The publication follows persistent advocacy over the years by GOGIG supported partners, notably PIAC and ACEP, alongside other civil society actors.
- Progress on developing legislation – this includes a bill related to the governance of the gas sector, and a new natural resource governance bill aimed at strengthening accountability in the use of revenues generated from both oil and gas and mining issues.

Recommendations for the year ahead (1/2 page)

The following recommendations are for the final six months of the programme. A more comprehensive Project Completion Review in April/May 2020 will look at broader lessons for future programming.

The programme team should develop a workplan for the next six months setting out the programme exit strategy - timeline for when implementation activities will be completed, milestones for learning events, closure of grant agreements and other closure activities. This programme exit strategy should draw on the Sustainability plan developed in response to last year’s Annual Review recommendations [programme team, Dec 2019]

Across all outputs, the programme team should focus on completion on projects and consolidation of results and lessons by March 2020, rather than initiating any further new initiatives.

The implementation of the Learning Plan should be accelerated, moving beyond completion of studies to synthesising and dissemination of lessons. The dissemination of lessons should include case studies of what drove success and also reflections on things that did not work well. [programme team, ongoing]

The Project Completion Review should give some consideration to assessing cumulative impacts over the programme lifetime and which output actions have contributed most to outcomes, given the acceleration in outcome level results this year

The DFID SRO should arrange for dissemination of lessons from the experienced GOGIG related to the effectiveness of technical assistance, use of political economy analysis for programme adaptation, and combining work with government and accountability actors - to inform the design and mobilisation of new programmes in DFID Ghana [SRO, February 2020]

GOGIG has demonstrated ability to adapt the programme as the political economy context shifts. The programme should continue to monitor risks to outcomes arising from political developments, particularly corruption and election-cycle related factors and adapt its approach as appropriate [programme team, ongoing]

As part of the non-revenue pathways for inclusive growth, the programme should consider how to bring a greater focus on climate change related issues – particularly on reducing dependence on fossil fuels and supporting GoG to adapt to a low-carbon future [programme team, ongoing]

A recommendation for future programming would be to consider how best to design a logframe that reflect the adaptive nature of the programme but also provide output indicators that can present meaningful progress towards outcomes.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Regulatory mandate and policy coherence of the oil and gas sector enhanced
Output number per LF		1	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y (↓)

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of initiatives that advance delivery of institutional mandates	5	Exceeded: 8 / Drafting of new legislation for gas sector / Support to develop provisional arrangement for delimitation of marine boundaries between Ghana and Togo / Expert review of plans for release of new acreage for petroleum exploration for second block licensing round / Developed a manual of operators costs to enable benchmarking against other petroleum producer countries / Support to the PC to formulate legal text related to stabilisation and dispute resolution clauses in agreements – identified as particularly difficult clauses for governments to draft effectively / Developed incident investigation protocol for Health, Safety, Security and Environment incidents at oil and gas facilities / Provided policy options for new licensing regime being developed for smaller (marginal) fields / Coordination of government and accountability actors for drafting of the Natural Resource Governance Bill.
1.2 Progress towards strengthening the government petroleum block allocation process and civil society's monitoring of the process	Expert Analysis and inputs provided to government on bid assessment framework / Facilitate civil society engagement with government on compliance with petroleum block allocation process	Achieved / Expert input into Invitation to Tender documentation and bid evaluation criteria / Analysis to support MoE to establish new fiscal thresholds as part of the bidding round / Support to CSOs to review the bidding process, compare with international best practice and provide recommendations to government

Provide supporting narrative for the score
This output captures the work that GOGIG does supporting the Ministry of Energy (MoE) and the Petroleum Commission (PC) to develop and implement policies and regulations for better governance of the sector. There have been gains made in key areas contributing to the outcome level objectives of the programme and this output is scored as moderately exceeding expectations – A+. Some key deliverables under this output have been:
1. Support for developing new legislation for the gas sector, the Gas Act. GOGIG technical assistance has input into the drafting of the bill and worked closely with the legal team at the MoE to set out the new legislation. This bill seeks to resolve overlapping and unclear mandates of government institutions involved in regulating the gas sector, addressing issues related to pipeline ownership and operations, and developing a predictable tariff setting mechanism.
2. Manual of operator costs across countries for Ghana and the New Producers Group[1]. A manual of operator costs was completed with GOGIG support through the provision of expert input in collaboration with Chatham House. The manual has been made available to the PC and regulators in NPG countries and will enable comparison of costs submitted/claimed by operators in Ghana against benchmark costs in other NPG countries.
  [1] The New Producers Group is a collaborative network of 31 countries that are in early stages of exploring or producing petroleum resources. It is convened by Chatham House and aims to support peer-to-peer learning on the sector.
3. Natural resource governance bill: This draft bill was produced through GOGIG’s coordination of government and accountability actors’ inputs. The bill seeks to provide a legal framework to enhance transparency and accountability in relation to the use of revenues from Ghana’s oil and gas and mining sectors.
The most intensive workstream in this area for the year 2019 has been support on strengthening the competitive bidding process for allocation of new blocks for petroleum exploration, captured in Indicator 1.2. Ghana started its first ever competitive bidding round in January 2019. GOGIG has been working on this licensing round in two main ways:
- Supporting GoG to improve its approach – expert input into the first Invitation to Tender, and on the bid evaluation criteria. This included provisions such as the fiscal thresholds in the evaluation criteria, to ensure that GoG policy to accelerate exploration still retains maximum value for Ghana.
- Working with civil society to review and monitor the bidding round – GOGIG supported CSO partners to review the bidding process, compare against international best practice, and provide constructive recommendations to government in two reports. The bid management team at MoE acknowledged the usefulness of these reports and will be using them to inform preparations for the next round of competitive licensing. The reports will also provide a reference for advocacy efforts in this next round.

Significant Achievements under this Output contributing to Outcomes
GOGIG’s support for the competitive process for allocation of oil blocks – the bidding round – has the potential to leave a valuable legacy for the future governance of the oil and gas sector.
The actual outcome of Ghana’s first-ever bidding round has been disappointing in terms of the level of competition and the number of new blocks actually allocated. However, GOGIG input helped to test the process set out in the legal framework, highlighted areas for improvement, and built capability both within government and with civil society partners.
The aspect of working with civil society and government in tandem received positive feedback from the Deputy Minister of Energy, as he highlighted that this has helped to build consensus and created a framework for civil society engagement in future rounds. The reports prepared by the CSOs with recommendations will also be useful to inform the process in future rounds.
As the next round of licensing is expected to be launched as early as February 2020, these improvements to the process will be tested soon.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lesson: Using an embedded specialist technical advisor has enabled GOGIG to make timely and impactful inputs on issues of national importance in the oil and gas sector. However, the risk of responsive support being stretched in too many different directions remains, and mitigating actions are needed to ensure that programme activities link clearly to outcomes.

Recommendation: for the period until March 2020, GOGIG should prioritise consolidating its inputs into key deliverables (such as the local impact framework and natural resource bill), rather than responding to further new initiatives with the MoE or PC.

Output Title	Oil and gas revenue capture and oversight improved
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y (↓)

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of initiatives that identify and improve revenue capture	4	Achieved: 4 / Finalised GRA Audit Practice Notes – guidelines to clarify issues that arise in audits / Online system for cost comparator database procured to enable transfer pricing unit to do risk assessments / Technical session for 10 accountability actors to improve advocacy for uncollected tax revenues / Developed “Petroleum List” – set of inputs that qualify for import duty exemptions, to reduce revenue losses from indiscriminate application of this exemption
2.2 Number of initiatives that support inter/intra agency coordination to avert and retrieve potential revenue losses	2	Achieved: 2 / Inter-agency collaboration on cost audits – cross-agency sharing of information on how cost data should be treated through GOGIG facilitation / Establishment of coordinated process and tools for Additional Oil Entitlement tax collection

Briefly describe the output and provide supporting narrative for the score

Output 2 focuses on ensuring clarity on how taxation of the oil and gas sector is administered, the technical capacity of authorities to collect revenues due to the state, and information sharing and coordination between agencies to improve revenue collection. The A score reflects stable progress on delivering the activities under this output and evidence of delivering results at outcome level. Some highlights from this year include:

Practice Notes for GRA petroleum sector audits: These audit guidelines, for GRA officers, tax consultants, companies and the general public, were produced with GOGIG support to clarify the acceptable application of tax regulations on calculation of royalties, surface rentals, capital allowances, and other detailed aspects of audits. The practice notes are meant to reduce contestation and disputes of audit results.

Cost Comparator database and risk assessment system for transfer pricing unit: a new digital system was procured and installed to support GRA to do risk assessments to identify oil companies that should be audited on transfer mispricing.[2] According to the GRA, the new system has reduced the time taken to undertake a company risk assessment from two days to two hours..
[2] Transfer pricing refers to the prices of transactions between a company and its affiliates or subsidiaries abroad. Transfer mispricing can be used as a tax avoidance strategy by multinational firms.

Development of the “Petroleum List” – working with the PC, GNPC and MoF to create a list of which imported inputs should be exempt from custom duties and taxes. Developing the list required technical expertise on the operations of upstream petroleum companies. This list has now been submitted to MoF to consider for inclusion in the 2020 Budget. In the absence of such a list, companies would mark many imported items as custom duty-exempt and there was no standardised approach.

Support for collection of Additional Oil Entitlement[3]– for this year, the work focused on AOE has included efforts to enhance the process of coordination among government agencies but also improving civil society understanding and advocacy on issues of slow pace of collection.
[3] A type of “windfall” tax collected when production and prices are above certain thresholds, set out in the agreements with each company

Significant Achievements under this Output contributing to Outcomes
The outcome level indicator associated with this output has shown remarkably strong performance in this year.
Ghana captured an additional $177m of revenue of which $63.84 million (£52.36million) was attributable to GOGIG, using an attribution methodology verified with GRA and other programme partners. This is equivalent to 7% of total petroleum revenue realised by the government in 2018.
Most of this result was achieved by more effective and efficient audits of upstream operators by GRA that revealed undeclared, unpaid and underpaid tax liabilities over the past four years. GOGIG has been supporting the GRA petroleum unit over the last three years with an audit manual, specialised software and, most recently, practice notes for guidance on potentially contentious issues. The results demonstrated for this year reflect the impact of these inputs used in combination, and the cumulative effect of three years of capacity building.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lesson: A slower pace of progress with government partners on collection issues has meant that it is necessary to work more closely with accountability partners on this issue. The design of GOGIG allows for this type of change in approach during implementation, which contributes to further success. However, it is possible that changing the approach earlier would have yielded better results. A better understanding of the political economy of the GRA and its relationships with the MoF and with oil companies could have been brought in earlier in the process. Clarity on the triggers for when to change approach would be helpful to facilitate future decision-making.

Lesson: The progress made on the outcome indicator demonstrates that there is a time-lag in outputs translating to outcomes in a technical assistance programme like GOGIG. It also shows the potential for cumulative impact of complementary interventions over multiple years, which may not be effectively captured in annual reviews.

Recommendation: The Programme Completion Review and final programme assessment should include an analysis of the cumulative impact of different interventions with the GRA petroleum unit, the factors enabling success in this case, sustainability of impact, and the lessons for other multi-year technical assistance initiatives.

Output Title	Oil and gas revenue management and oversight improved
Output number per LF		3	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Y (↓)

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of non-ABFA initiatives that identify and improve planning, allocation, utilization, investment and reporting of petroleum revenue	5	Partly Met: 4 / Policy brief with recommendations to government on improving GNPC spending / Convened a consultation with industry, GNPC and PIAC to improve practices for setting crude oil prices at different production fields to ensure fairer pricing / Review of the Petroleum Revenue Management Act – process led by MoF with GOGIG support to convene technical sessions with civil society, GNPC, GRA, PIAC and others / Improving investment of petroleum funds: policy briefs with recommendations to improve investment of Stabilisation and Heritage Fund
3.2 Number of initiatives that improve monitoring and learning on projects funded with Annual Budget Funding Amount (ABFA)	3	Achieved: 3 / Support to MoF to prepare and publish list of ABFA projects as part of 2019 budget / PIAC project on ensuring efficiency of ABFA in the agriculture sector / Development of resource application framework with MoF Budget team for allocation of ABFA

Provide supporting narrative for the score

Output 3 works with the Ministry of Finance (MoF) and partners to improve the allocation and utilisation of oil revenues – related to the Annual Budgeted Funding Amount (ABFA) which is used for current spending in the Budget, and also transfers of revenues to the Ghana National Petroleum Company (GNPC) and the Heritage and Stabilisation funds managed by Bank of Ghana. This output is largely performing as expected but a score of B has been given as the milestone indicator for 3.1 has been marginally missed. This is partly because the natural resource governance bill, which is an activity that cuts across Outputs 1 and 3 has been counted against output 1.

Key activities for this year include:

Support to the Institute of Fiscal Studies Ghana (IFS) to analyse GNPC’s spending and make recommendations for improvement. This work informed a policy brief submitted to government to suggest setting a limit on GNPC’s corporate social responsibility budget and review the law statutory status of GNPC.

Partnership with MoF to review Petroleum Revenue Management Act (PRMA) – GOGIG is providing technical inputs and support to coordinate across agencies. The first technical session convened by GOGIG included GNPC, PC, GRA, BoG, PIAC and a section of CSOs. This session made a series of recommendations to consider such as reviewing the Minister of Finance’s authority to appoint members of the PIAC, setting a legal ceiling for the Stabilisation Fund, and clarifying the process for compensation payments to communities for adverse impacts.

Significant Achievements under this Output contributing to Outcomes

Publication of list of projects to be funded by ABFA in 2019 Budget
For the first time, the Ministry of Finance accompanied the annual national budget with the list of projects to be funded with ABFA as a way of promoting effective monitoring and transparency in disbursement of funds. The ministry also prepared the projects’ workplans and cash flows for managing disbursements to line Ministries, Departments and Agencies (MDAs) implementing ABFA projects.

GOGIG supported the Budget Unit in the MOF to distil information on projects and contracts from all MDAs, and design a template setting out workplans and cashflows. This enabled publication of the list of projects to be funded by ABFA, and will also allow for tracking performance information during project implementation.

The knowledge and availability of the ABFA project list to the general public, is a critical step in maximizing transparency and effective scrutiny of ABFA funded projects to enhance petroleum revenue management. The open disclosure of the ABFA project list prior to implementation encourages transparency to ensure guidance on the efficient and effective spending of petroleum revenue. The work plan and project cash flows are now internal operational plans used by MOF and line ministries implementing ABFA projects.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lesson: Working with teams in the MoF beyond the Oil and Gas Unit – such as the Budget Unit – has been valuable for progress on improving allocation models and disbursements for ABFA. This broader collaboration with the MoF should be considered for future programme design.

Recommendation: The opportunity presented by the PRMA revision, natural resource governance bill, and new partnerships with teams in MoF beyond the Oil and Gas Unit should be used to draw out lessons from petroleum revenue management to improve Public Financial Management as a whole.

Output Title	Enhanced public engagement and oversight of the oil and gas sector
Output number per LF		4	Output Score	A+
Impact weighting (%):		15%	Impact weighting % revised since last AR?	Y (↓)

Indicator(s)	Milestone(s) for this review	Progress
Number of public engagements and advocacies that promote transparency and accountability in oil and gas issues.	6	Achieved 6 / Consultations organised with frontline oil communities on the PC’s draft social performance guidelines / Public presentation and workshop of IFS analysis of GNPC expenditure / Support to ACEP to engage with parliament on scrutiny of GNPC’s budget / Worked with IMANI Foundation to share research findings on the impact of upstream contracts on end-user electricity tariffs / Events for dissemination of Ghana EITI report on oil and gas and mining – events in Tamale, Kumasi, Sunyani, New Abirem and Tarkwa / Community level training in Western Region to enable ABFA beneficiary communities to access information on projects in their area
Number of changes that demonstrate increased technical and leadership competencies and organisational development of selected accountability actors.	4	Exceeded: 5 / Progress by graduates of the GOGIG leadership programme (OLP Fellows) to resolve disputes and develop organisational strategy / Increased media presence and representation on high level forums of OLP Fellows / OLP Fellow at IFEJ (Institute of Financial and Economic Journalists) has assumed a new role, editing articles on oil and gas for several media houses / OLP Fellow from PIAC developed an analytical paper which is the first independent assessment of government policy on petroleum funds investment / OLP Fellow from Citi FM created a new website dedicated to reporting media content on extractives

Provide supporting narrative for the score

This output captures GOGIG’s work to build long-term capacity of its civil society partners, and work with CSOs to engage citizens on issues related to oil and gas governance. There has been good progress made on this output, particularly on engagement of citizens in different parts of the country and evidence of a new set of civil society leaders emerging that GOGIG has helped to train and empower. Based on this evidence, and the contribution of this output across the other workstreams, it has been scored an A - meeting expectations.

Some highlights from this year include:

Community and citizen level engagement – there have been multiple initiatives to engage with frontline oil communities and citizens on different issues related to oil governance. For example, GOGIG has supported PIAC to deliver a community level training, attended by 160 people, on how to access information related to ABFA funded projects. This is a new strategy which recognises that local communities are best placed to provide oversight and ensure accountability for project implementation. GOGIG has also supported the PC to hold consultations with communities on its social performance guidelines, which set out the social and environmental obligations of industry working in the sector. These consultations were attended by 145 participants, with most of them coming from oil communities in the Western Region.

Emergence of a new group of civil society leadership – the GOGIG Oversight Leadership Programme was completed last year. The OLP recognised the importance of building a pipeline of leaders in civil society organisations who would invest in organisational development, as part of the sustainability strategy for the programme. The OLP Fellows have now initiated various organisational reforms, and taken on advocacy projects, demonstrating the impact that the programme has had. For example, the OLP Fellow at ACEP undertook analysis of GNPC’s expenditure and initiated advocacy which resulted in a USD 80m reduction in the 2019 GNPC budget as this was identified as going into non-core activities. The OLP Fellow at Citi FM has set up a website to provide a platform for oil and gas and natural resource governance issues. These changes provide confidence that GOGIG has had an impact on the civil society landscape and created a new set of leaders who will continue to advocate for transparent governance of the oil and gas sector beyond any individual donor programme.

Significant Achievements under this Output contributing to Outcomes

A key contribution that GOGIG has made on accountability has been the improved organisational capacity of PIAC.

PIAC now receives its core funding from GoG, as a percentage of petroleum revenues. However, GOGIG has continued to support PIAC with some individual projects which have been very important for advocacy on the use of petroleum revenues. This year it is estimated that the GOGIG supported PIAC initiatives have helped avert potential mismanagement of USD 93.5m of petroleum revenues. This includes $80 million ABFA revenue that was not accounted for by Ministry of Finance in its 2017 reconciliation report and $13.5 million petroleum revenues wrongfully paid by some upstream operators into the GRA account instead of the Petroleum Holdings Fund (PHC) as required by the law.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lesson: investing in the organisational development and future leadership of civil society partners is critical for the sustainability of impact for an accountability and governance programme like GOGIG. The impact of the OLP scheme was not clear last year apart from through participant testimonials. However, this year there is evidence of the initiatives and actions taken by the participants, showing that potentially there will be time-lags in the achievement of results for such capacity building activities.

Recommendation: The institutional strengthening of PIAC will be a major contributor to the sustainability of impact for GOGIG. The learning plan for GOGIG should include some learning on the evolution of PIAC – the factors that have led to it becoming successfully established as an accountability body and how GOGIG support has contributed.

Output Title	Non-revenue pathways of the oil and gas sector to inclusive growth enhanced
Output number per LF		5	Output Score	A+
Impact weighting (%):		15%	Impact weighting % revised since last AR?	Y (↑)

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of initiatives that promote government and public understanding and delivery of non-revenue pathways of the oil and gas sector to inclusive growth	3	Achieved: 3 / Establishment of “women in energy” platform to promote women’s visibility and leadership in sector / Industry consultation to feed into review of local content legislation / Documentary series to improve understanding of the potential to use gas for power generation and the constraints and enablers for this in Ghana
5.2 Progress made to develop local impact management framework	Local impact management framework for the oil and gas sector developed. / Socio-economic baseline data established for the oil and gas operation in six coastal districts in Western Region. / Lessons from implementation of offshore SEA findings distilled to inform onshore SEA.	Exceeded / All three of these initiatives have been completed. / In addition, the social performance guidelines of the PC have been completed which is a major contribution to programme outcomes (see box)

Provide supporting narrative for the score

This output captures pathways through which the improved governance of the oil and gas sector leads to inclusive growth, beyond issues related to revenue. There has been strong progress on issues related to local impacts, gender equity and local content. The output has been scored A+ – based on achieving indicator 5.1 and exceeding indicator 5.2 with the completion of the social performance guidelines, which are a significant achievement (see box below)

Key achievements for this year include:

Facilitating establishment of the “Women in Energy” platform - The platform specifically seeks to raise the voice and agency of women to advocate for greater visibility and participation in the sector; increase knowledge and skills on how to promote women’s participation and leadership in the sector. GOGIG convened a core team of women in prominent positions in the sector and supported them to organise a speaker series and develop a strategic plan for the first three years of the platform.

Feeding industry perspectives into the review of local content legislation – ACEP compiled experiences of Ghanaian companies in the sector to develop recommendations for the PC on the future direction of local content legislation. GOGIG also supported analysis by the Ghana Oil and Gas Service Providers Association to review how current local content laws affect them.

The management of local social and environmental impact has become an increasingly large area of focus for GOGIG’s work. This year, there have been some important achievements made in this work:

- Technical input and convening of consultations to develop the PC’s “social performance” guidelines, completed Sep 2019. The guidelines set out expectations for industry, local communities, regulatory agencies and other stakeholders in the design, implementation, monitoring, evaluation and reporting of Social Performance for the upstream petroleum industry, in respect of both onshore and offshore operations. The guidelines cover the areas of social impact assessment and management; community and social development; community and stakeholder engagement; grievance management; land acquisition and resettlement; human rights and cooperative governance and ethics.
- Local Impact Management Framework for onshore petroleum operations developed: This framework has been produced for the MoE and GNPC. It categorises preparations necessary at different phases of onshore petroleum operations, guidelines for how risks and impacts to communities onshore should be proactively managed, and the roles and responsibilities of different state institutions.
- Support to Environmental Protection Agency to develop a Strategic Environmental Assessment for onshore operations. This was done by supporting the EPA to adapt the existing off-shore SEA and supporting the MoE to take a greater role in the coordination of the SEA process and implementation of recommendations.

Significant Achievements under this Output contributing to Outcomes

The completion of the social performance guidelines this year is a major milestone contribution to GOGIG’s overall outcome.

The Social Performance Guidelines set the minimum standards for upstream operators in managing social issues associated with their operations. With this in place, it is expected to streamline practices in the sector among companies to achieve consistency and manage the expectations of beneficiary communities, local government and other institutions. They will foster partnerships between companies and communities, increase trust and improve communication. In particular, critical issues such as payments and donations to chiefs as part demonstrating respect of traditional institutions and customs of Ghana, and the types of projects which qualify as corporate social responsibility projects, have been clarified.

GOGIG has worked very closely with the PC to review existing guidelines and develop a new draft and arrange for an expert peer review. The programme has also convened stakeholder consultations with industry, civil society, government agencies and communities from the Western Region and Keta Delta to create awareness and ownership of the guidelines.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendation: GOGIG has worked on several different aspects of social and environmental impacts with different agencies. In the last six months of the programme, these strands of work should be synthesised to ensure that their impact is complementary.

Output Title	Documentation and dissemination of programme learning
Output number per LF		6	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	n/a new output

Indicator(s)	Milestone(s) for this review	Progress
6.1 Number of knowledge products and events to share learning from the programme	4	Achieved: 3 reports and 1 event / (details below)
6.2 Categories of stakeholders reached with knowledge products and learning events	All GOGIG partners and at least five non-GOGIG partner categories reached through learning events	Achieved (details below)

Provide supporting narrative for the score

A total of 7 learning studies are to be completed as part of the GOGIG Learning Plan. Six (6) have been commissioned and are at different stages of implementation. The first set of 3 commissioned for which draft reports have been completed cover the following areas;

- Regulatory mandates and policy coherence in the oil and gas sector
- Lessons from GOGIG’s work to improve revenue management
- Preparing Civil Society for future challenges in the oil and gas sector - lessons from GOGIG’s work and the evolution of civil society in Ghana and internationally

An engagement on the civil society study was also held with stakeholders using the draft report with the objective of not only sharing the findings but also as the basis to generate a conversation amongst stakeholders on the important issue of sustaining the vibrancy of CS efforts as petroleum activities move onshore. The outcomes from the discussion will inform finalisation of the report.

The learning event on the study on Civil Society was attended by participants representing the following categories of stakeholders;
- GOGIG Government and CS partners
- Non GOGIG government agency
- Donor agency - GIZ
- Other DFID funded programme - STAR GHANA
- Non GOGIG CSOs
- Disability Organisations - Ghana Association of the Deaf and Ghana Blind Union
- Academia - University of Exeter programme on environmental justice

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendation: The Learning Plan for GOGIG should include an effort to synthesise learning across different thematic areas, to mitigate the risk of this being a series of disparate studies and events.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The original logic of the GOGIG intervention as captured in the Business Case was to deliver inclusive growth and development (‘maximise the benefits for the people of Ghana’) by strengthening industry regulation and oversight, revenue collection and management. And as a result, GOGIG combined strategic projects with government counterparts with a responsive and opportunistic approach towards supporting accountability actors.
In 2017, the Theory of Change was expanded to look at inclusive growth issues beyond revenue – including issues of local business participation and management of potential negative social and environmental impacts.
There have been no major changes to this overall theory of change in the last year.
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The outcome indicators have shown accelerated progress in the last year and are on track to exceed milestone targets. This demonstrates the cumulative impact of interventions over the programme lifetime, and also the impact of specific good governance actions undertaken in 2019 that affect the scoring on the Resource Governance Index. The programme is on track to contribute to the expected outcome.

Outcome Indicator 1: RGI score for oil and gas (based on progress in the three index components; Value realisation, Revenue Management and The Enabling Environment)
Annual Milestone Target: 5% improvement over baseline score of 64 in 2014

Annual Result achieved: 29% improvement on baseline score (2019 score – 83)

The Resource Governance Index is published once every two years by the Natural Resource Governance Institute (NRGI), which captures overall quality of regulation and governance in the oil and gas sector. The NRGI have not yet published the 2019 score, but in order to make an outcome level assessment, GOGIG commissioned the same consultant used by NRGI for calculating the index in previous years, to make an assessment for this year. It should be noted that this score may differ from the official NRGI assessment expected next year, but the programme has taken steps to ensure independence in the assessment and a conservative approach to measuring progress.
The GOGIG-commissioned 2019 assessment revealed a score of 83, representing a 29% improvement on the baseline score of 64 in 2014. This scoring reflects the major reforms undertaken since 2016, many of which have had significant inputs from GOGIG. The passage of Exploration and Production (E&P) act and regulation, creation of an online petroleum register, the passage of a fiscal responsibility law and creation of a fiscal council have all had an impact on the score. However, over the same period, Ghana’s performance on rule of law and control of corruption recorded a marginal decline.
Regarding the three major components of the index, the country scored 88 on value realization (how production is organised), 90 on revenue management and 72 on enabling environment. Examining the pillar showing the greatest change, the major elements of improvement are:
- The sharp increase on valuation realization pillar was accounted largely by: the creation of the online petroleum register to promote contract transparency; disclosure of impact assessment reports; and the passage of petroleum exploration and production act and regulations mandating the publication of pre and post licenses rules. These reforms were influenced by GOGIG through provision of technical inputs and the advocacy of ACEP and other supported CSOs.
- The steady increment realised in the revenue management pillar of the index can be traced to: the passage of the fiscal responsibility law; the creation of fiscal council; and improved Tax Authority capacity and practices for auditing upstream petroleum companies. These reform areas that have been at the core of GOGIG interventions with government institutions over the past three years.
- A jump in the local impact indicator as a result of findings from Environmental Impact Assessments (EIA) being disclosed. Hitherto, EIA findings were not disclosed, and this had accounted for Ghana scoring a zero. The country also recorded an improved score on compliance with procedures governing rehabilitation and closure of oil and gas projects which was a development since the last RGI assessment.
Outcome Indicator 2: Value of Additional Revenue Captured
Annual Milestone Target: 5% additional oil revenue captured = $48,854,664.5
Annual Result achieved: $63.84millon (£52.36 million)
The programme definition of “revenue capture” is based on the issuing of a valid claim by the revenue authorities to the companies.
An estimated $63.84 mi (£52.36m) of Additional Revenue this year was attributable to GOGIG (as agreed with partners). This exceeds the annual milestone target for 2019 by $14.9m. The attribution value of $63.85m achieved in this fiscal year also translates to 7% of total petroleum revenue realised by the government in 2018.
The two main areas of intervention that have resulted in this additional oil revenue captured are:
Additional tax revenue from GRA Petroleum Unit (PU) audits of upstream operators
The audits of upstream operators led to the GRA Petroleum Unit (PU) identifying $159m in additional revenue. Of this figure, $55.3 million is attributable to GOGIG's intervention.
The tax revenues identified were traced to undeclared, non- payment, and underpayment of various tax liabilities of a number of named companies[4] from audits conducted by the GRA Petroleum Unit (PU) for 2016, 2017, 2018 and 2019[5].
[4] List of companies is available and has been excluded from the report as it is confidential information
[5] GRA PU audits have lagged behind the years they are due because of capacity limitations within the unit. This means some of the audits carried out in 2018-2019, from which the revenue was derived, were audits of previous years with arrears being paid in 2019.
Feedback from GRA partners was that the realisation of these previously hidden tax revenues was critically dependent on the understanding and application of technical knowledge and systems, which GOGIG helped to establish during the current and previous years. The results delivered in 2019 are the product of a combination of this year’s work alongside the accumulated effect of skills, knowledge and improved systems over several years.
In 2019 specifically, GOGIG supported the development of audit practice notes which provided clarity on the treatment of complex provisions in the law. GOGIG also facilitated the convening of an inter-agency cost audit case review session between GRA, GNPC and the PC which helped GRA understand the technical issues impacting on costs. In undertaking the audits, the PU also leveraged their increased capacity from GOGIG support in previous years.
The significant areas of increased capacity are: tax laws, petroleum audit practices notes, manual and computerized assisted auditing technique. As an illustration, the head of the petroleum unit at GRA, pointed out that the IDEA software GOGIG provided to the unit in 2017 and which marked the shift from manual to electronic data analysis, was used to analyse complex cost data and detect tax revenues in a way that would not have been possible with the former manual auditing process.

Tax recovery from transfer pricing audits

The GRA transfer pricing unit recovered revenue of $18.95m this year, of which $8.5m is attributable to GOGIG’s intervention. In 2018 GOGIG provided technical assistance to the transfer pricing unit of GRA to undertake its first ever strategic planning process, which clarified the unit’s mandate and set out approaches to improving operational delivery. The strategic planning process which was led by a team of seasoned transfer pricing experts engaged by GOGIG, created the learning space for the unit to acquire insights and skills in assessing risk levels of companies on transfer mispricing and utilizing such information to identify and target companies for auditing during the year being reported on.
As a result, the unit was able to select and appropriately target companies with higher transfer mispricing risks as compared to previous years. This led to the identification of major transactions with transfer mispricing in 2018 fiscal year and surcharges of approximately $84 million, an improvement in performance of 30% compared with 2017 fiscal year.

The risk analysis skills GOGIG helped the unit to acquire have been applied broadly to the audits of companies in the petroleum sector and beyond, hence the TP unit credited GOGIG for gains made beyond the petroleum sector. These non- Oil and Gas sector gains are included in the $8.5m attributed to GOGIG’s intervention.
Outcome Indicator 3: Number of state institutions’ actions positively influenced around the management of oil and gas resources
Annual Milestone target: 4
Annual result achieved: 6, listed below
The programme continued to perform strongly in shaping government policies, priorities and practices - contributing to six significant actions taken by the government and parliament this year to improve governance and transparency in the sector.

      1. Passage of Fiscal Responsibility law reflecting numerical rules as advocated by GOGIG and NRGI. In collaboration with NRGI, GOGIG convened technical meetings between CSOs which culminated is presenting recommendations to government for a numerical fiscal rule for budget deficits (between 3-5%) and the establishment of a fiscal council. The CSOs became engaged on the fiscal responsibility law as a result of their engagement with GOGIG supported analyses on ABFA utilisation - which pointed to the need for greater fiscal discipline.

      1. Ensuring transparency and scrutiny in ABFA disbursement: The Ministry of Finance (MoF) compiled and published a list of projects to be funded by ABFA in the 2019 budget for the first time ever. The publication follows persistent advocacy over the years by GOGIG supported partners, notably PIAC and ACEP, alongside other civil society actors. The list was made public by MoF and used by PIAC to inform their monitoring of ABFA projects and SEND-Ghana’s live tracking of ABFA budget performance

      1. GRA refund of approx. US$13.5m petroleum revenues that was wrongfully paid into GRA account instead of Petroleum Holding Fund (PHF). This resulted from an advocacy drive by PIAC to repost these funds into the PHF, after they detected it as part of their 2017 analysis of petroleum revenue. This was further evidence of PIAC’s effectiveness in holding government accountable, a cumulative result of GOGIG’s consistent support to PIAC over the years. Additionally, PIAC sustained pressure on the Minister of Finance for transparency in the allocation of unspent 2018 ABFA within the 2019 budget.

      1. Parliament reduces GNPC’s 2019 budget by $80m to curb expenditure on non-core areas. This resulted from ACEP’s analysis and advice to parliament on GNPC’s budget and expenditure on core and non-core activities. This analysis revealed that the corporation spent twice as much on non-core Corporate Social Responsibility (CSR) activities as it did on exploration, its central function. This effort influenced parliament decision to ensure that GNPC allocation of resources to finance its core operations and development of its competence as commercial player in the industry.

      1. $450 million cost savings identified on Aker Energy plan of development. This was achieved through the PC’s application of Landmark and Petrel software and technical knowledge provided by GOGIG to the Geoscience and Engineering units of the commission. This marks the first time PC would have been able use its acquired internal systems provided by GOGIG to review a plan of development received from an upstream company. GOGIG have also provided support to civil society monitoring of Aker’s activities in Ghana, to encourage an additional oversight mechanism.

      1. Government decision to replicate PIAC oversight function to cover upstream mining sector: Learning from PIAC’s performance in petroleum revenue management the government has taken the decision to scale up PIAC’s oversight to improve transparency, accountability, and efficiency in the management of mining revenues. This has culminated in the drafting of a Natural Resource Governance Bill to seek parliamentary approval on the new expended scope and objectives of PIAC. This is being jointly led by the Ministries of Finance and Energy with the active involvement of Deputy Ministers from the two ministries in the process.

Explain major changes to the logframe in the past year (1/2 page)

A new output, Output 6, has been included in the logframe to reflect the increasing focus of the programme on learning and dissemination of lessons from the programme. There have been no other major changes.

Describe any planned changes to the logframe as a result of this review (1/2 page)

There are no planned changes to the logframe as a result of this review. The current version of the logframe will be used to report on end of programme targets at the Project Completion Review stage.

A recommendation for future programming would be to consider how best to design a logframe that can reflect the adaptive nature of the programme but also provide output indicators that can present meaningful progress towards outcomes. More qualitative indicators at output level that communicate the programme activities, rather than indicators on “number of initiatives” should be considered.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The programme continued to maintain consistent performance against all the Economic, Efficiency, Effectiveness and Equity (4 Es) criteria underpinning our Value for Money (VfM) assessment. With improved performance on additional revenue captured by Ghana Revenue Authority (GRA) through the programme assistance, the VfM for the entire programme stands at £7.43 for every £1 spent, which exceeded the business case scenario of £5 for every £1 spent. It should moreover be noted that the revenue capture indicator only focuses on a proportion of the programme’s work, and other less quantifiable benefits also contribute strongly to programme value for money.

Summary of VFM performance against the 4Es

VfM criteria	Indicators	Summary Performance (2017-2018)	Summary of Performance (2018-2019)
EFFECTIVENESS	£ spent per additional £ of oil revenue captured	Additional revenue captured and attributed to GOGIG to date: £38,509,338.49 / FRF spending on Output 2 (revenue capture) up to date £403,827.31 / So far, £95.36 captured per £1 invested in Output 2 (based on FRF spend) and £4.18 realised from £1 invested on the entire programme. / Programme spending on implementation up to date is: £ 9,217,751	Cumulative additional revenue captured and attributed to GOGIG to date: £90,865,846.08 / FRF spending on Output 2 (revenue capture) up to date is £494,454.22, which means £183.77 has been captured from every £1 invested in Output 2. / Programme wide rate of returns is £7.43 for every £1 invested. This is based on up to date sending of £12,230,650.87.
	Case analysis of GOGIG contribution to effective management of the oil and gas sector	GOGIG contribution was demonstrated around the following two most significant changes: / Government delivery of policy commitment to set up online petroleum register / A blue print to accelerate oil and gas development put in place by the MoE.	In this assessment year, non-quantifiable benefits of the programme was demonstrated around the following two most significant changes. / Framework of guidelines on social performance developed for PC to regulate Upstream operators’ community level operations / Improved PIAC’s capacity to hold government accountable and elicit responsiveness on lapses in petroleum revenue management
EFFICIENCY	Flexible Response Fund (FRF) spend as % of total spend for year.	67.2%	57.36%
	Average cost per citizens enabled to make inputs and demand for transparency and accountability in oil and gas policies and issues	Overall, an estimated 3,760,117 citizens were reached at a cost of £96,567.32. This translates to an average cost of £0.03 per citizen reached.	Overall, an estimated 58,866 citizens were reached through 5 events at a total cost of £91,221.01. Average cost of £1.54 per citizen
VfM criteria	Indicators	Summary Performance (2017-2018)	Summary of Performance (2018-2019)
	% of GOGIG policy initiatives and recommendations absorbed by government and its agencies in the oil and gas sector.	30% of the 9 policy submissions made to the government were considered. The rest are still under consideration.	2 of the 4 policy submissions made to the government were considered. The rest are still under consideration. In addition, six policy briefs made in previous year were considered in this fiscal year.
ECONOMY	Value of partners’ input into FRF project planning and implementation	£96,974.82	£133,033.28
	Cost savings made on project expenses through adherence to financial safeguards and other cost cutting strategies.	£74,752.19	£27,132.19
	% of consultants’ fees within benchmark rate bands agreed with DFID	100%	100%
EQUITY	Percentage of policy making projects including voice of marginalized groups (frontline communities, women etc) on sector issues.	75%	50%
	% of programme participants at relevant events that are drawn from frontline oil communities	17% of the participants for 4 policy making events	71%
	The % of key programme resource persons on FRF project implementation initiatives who are women	23%	34%

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme has demonstrated strong VFM and should continue for the remaining six months. The figures presented in the table above demonstrate a generally positive trend on VFM indicators compared with last year. Some points to note from the VFM framework:
  1. There has been an acceleration in revenue capture this year, as noted earlier in this review
  2. Citizen engagement this year has focused more on direct community consultation rather than media outreach, which has resulted in a higher cost per citizen this year compared with last year, but also greater engagement with frontline oil communities reflected in the equity indicators.
  3. The proportion of programme spend coming from the Flexible Response Fund has declined, reflecting a slower pace of implementation in some output areas and also increasing contributions from partners (CSO and government) to GOGIG initiatives, captured in the economy indicators.
The programme is considered a credible partner to both government and accountability actors. It has maintained trusted and constructive partnership engagements, while remaining strategic about where to provide support and refusing requests where there are concerns about additionality or sustainability. For example, the work with MoF was scaled down in 2019 because GOGIG refused to provide support for activities related to petroleum revenue reporting that are statutory obligations of the Ministry, and new capacity building programmes that appeared to have limited additionality. Similarly, requests from the PC and MoE respectively for equipment and funding support for the Accelerated Oil and Gas Capacity Building Programme (AOGCP) were turned down.

GOGIG has collaborated well with other DFID programmes, such as the Ghana Revenue Reform Programme and the Strengthening Action Against Corruption programme to achieve joint objectives.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The programme’s risk rating remains ‘moderate’. The programme team has so far managed its risks well by leveraging the right incentives and its relationships with partners to deliver its objectives. There is a quarterly Political Economy Analysis discussion to keep updated on key changes in context and identify programme adaptation needed.

The programme risk register was updated in July 2019. Many of the risks being monitored have now been closed as the programme enters its final six months of implementation, and new context risks have been added as the Ghana 2020 elections draw closer. The major risks that are still active in the current register are set out below:

Description	Mitigation	Residual Risk rating
Slow down of government business due to key functionaries being unavailable as a result of upcoming parliamentary primaries and potential increase in patronage behaviour in the run up to elections [Context]	Set timelines for implementation of project activities with government partners and follow up to secure dates / Support effective oversight in the lead up and during election by making inputs into the design of other development partner projects based on programme's lessons from previous Election Support Project	Major
Competing demands and weak absorptive capacity of GoG partners, especially GRA, affects pace of implementation [Delivery]	Collaborate with partners to plan timing of interventions, incorporating lessons from peak periods of partner calendars / Continue to engage Deputy Commissioner for high level oversight of implementation of agreed projects / Rely on Technical Assistants to lead agreed initiatives with inputs from GRA	Major
Delay in signature of no-cost extension contract amendment results in uncertainty for last three months of implementation [Operational]	DFID SRO and programme manager to keep in close communication with Procurement and Commercial Dept. and facilitate contact with OPM team to ensure timely signature of amendment.	Major
Adverse political developments (corruption allegations, election related activity) compromise programme outcomes or reputation (Reputational)	GOGIG team to continue with regular political economy analysis, gathering information from civil society and other partners. Ensure that all programme activity and external communication is assessed for reputational risks related to political developments.	Moderate
Transparency and accountability work conflicts with rest of HMG objectives on promoting British business interests [Reputational]	DFID to manage relationships across other HMG partners to ensure that GOGIG continues to promote transparency and accountability in all business practice, including British business.	Moderate

Recommendation: Risk Register should be updated to include a risk on the timely implementation of the learning plan and programme sustainability plan given competing demands on the programme team’s time related to completion of existing projects and programme closure activities.

Update on partnership principles (1/2 page)

The Partnership Principles are not expected to be used in the management and monitoring of GOGIG given that it does not entail financial aid and use of country systems. The last update to the partnership principles done in Aug 2019 showed no changes in trend for government of Ghana’s commitment to poverty reduction, respecting human rights, accountability and improving public financial management, although concerns remain on fiscal responsibility and corruption.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The GOGIG programme has directly engaged with both state and non-state as key partners namely the MoE, PC, MoF, GRA, BoG, PIAC, GHEITI, ACEP, CSOs and others. GOGIG has continued to maintain the strong relationships with it partners and they have all expressed their appreciation for the GOGIG programme. GOGIG Leadership has also cemented a close working relationship with the DFID SRO and Programme Manager.

The programme spend stands at 84% of the total contract value, with 54% attributable to the Flexible Response Fund (FRF). The key driver of spend remains as FRF, which comprises 57.4% of total spend, while programme fees account for 29%, and expenses comprise of 13%. The rate of spend in the FRF has reduced in comparison to previous years, driven by a slowing down of spend in outputs 2 and 3 related to context factors.

The “Learn-Adapt” quarterly milestones were discontinued this year and replaced with a Learning Plan and Sustainability mapping – reflecting that the programme itself has limited time to do further adaptation, but will rather be focusing on capturing learning and ensuring sustainability instead.

Financial reporting and forecasting variance

In terms of financial reporting, GOGIG maintains good financial management practices and has consistently demonstrated good improvement in managing programme funds. Under the year of review, there have been some key challenges with their forecasting and financial report.

OPM submission of monthly invoices has been slow due to internal financial management system and this has affected the DFID’s internal forecast and financial management. The approval of invoices process has been streamlined, as there are headings provided for expenditures under individual FRF projects, and budget lines are clearly laid out.

OPM provides quarterly financial progress reports as part of the quarterly reporting to DFID. In these quarterly progress reports, GOGIG has continued to report on key budget lines as a percentage of monthly expenditure, and monthly actual versus forecast expenditure, as well as FRF expenditure breakdown by output area and by spend type.

OPM have been consistent with their report to DFID on monthly updates on forecasts and likely variances on the 25th day of every month. The team has been consistent in providing these updates as such gives DFID the opportunity to complete its own monthly forecast reporting system by end of the month. The variance in the report is largely caused by low spend in Output 2 (Revenue Capture). The expenditure under this output has reduced significantly due to challenges related to political and organisational issues with government partners, rather than factors within the programme’s control.

Generally, the programme has remained within the agreed variance limit of 10% but overall the variance for this year has been higher than in previous years. On average, variance has been 5%.
Monthly reported variances on expenditure versus forecast (October 2018 – September 2019)

	Oct -18	Nov-18	Dec-18	Jan-19	Feb-19	Mar-19	Apr-19	May-19	Jun-19	Jul-19	Aug-19	Sept-19
Var. (%)	-3.56%	-4.09%	4.87%	-8.58%	-9.02%	9.48%	9.85%	-3.81%	-6.50%	-0.45%	-9.02%	-9.12%

Expenditure verification and audit

DFID conducted expenditure verification and asset verification on the programme in July 2019. The draft report came back generally positive with few outstanding issues which will be addressed before the end of November.

An external audit for the programme was not conducted as at the time of this report. Given that the programme ends in June 2020 and an end of programme audit will take place at that time, an external audit in addition to the expenditure verification already conducted was not considered necessary.

Date of last narrative financial reports	31 Oct 2018
Date of last audited Annual Statements	N/A

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

Programme performance is monitored through quarterly and annual progress reports submitted by GOGIG for review and feedback. The Team Leader and SRO meet once every two weeks to share updates on progress, discuss issues relating to programme risk and delivery. The OPM management team maintains regular contact with the DFID SRO and PM, either in-person during regular visits to Accra, or via email/phone on a quarterly basis. The DFID SRO also keeps regular contact to discuss emerging PE developments that may have a negative bearing on the programme. The GOGIG team has been co-operative and very supportive in engaging with its partners as such is regarded as a strategic partner with high level of professionalism.

At the partner level, the programme began the year with partnership review meetings with both its government and accountability partners to jointly assess the quality of its relationships and to identify strategic priorities to work on for the year. The GOGIG Workstream leads work closely with partners to ensure the sustainability of GOGIG’s achievements following programme closure. A key aspect of this has been reducing the level of GOGIG funding/resourcing, requiring partners to contribute to costs and drawing in other collaborators (e.g. NRGI) both to co-fund as well as maintain support beyond GOGIG.

This annual review has been conducted by the SRO and programme manager and has included conversations with key GOGIG partners at the MoE, PC, MoF, and accountability partners ACEP and PIAC.

Evidence (1/2 page)

As at the time under review, there has not been any significant evidence which challenges the programme design or rationale. The programme was effectively designed and as it about to close, there are no modifications required.

The GOGIG programme has remained flexible and continued to adapt to the changing context. This is evidenced in the modifications it has made to its approaches and ways of working to remain relevant and effective in achieving its objectives. Its overall adaptive management approach has been effective in delivering support to both government and accountability actors to work towards achieving common objectives. The programme has designed and piloted innovative projects that are worth studying and replicating.

An independent review of the programme will be conducted as part of the end of Programme completion report.

Learning (1/2 page)

The programme has started implementation of a learning plan, capturing lessons from the programme lifetime, which is captured in the Logframe Output 6. The learning plan has four objectives:

Sustaining GOGIG’s Policy Influence and Developmental Impact. The primary purpose of the LP is to validate and highlight to key stakeholders, changes in the management of the Oil and Gas Sector influenced by GOGIG, which have helped to improve “effective management of the oil and gas sector”. The findings of the studies from the LP will be presented at learning summits involving participants from GOGIG partner MDAs, other MDAs, accountability and civil society actors including the media, other donor programmes, academia and industry, to publicly reflect on and recognise progress made. This material is also likely to be of interest to other extractives programmes internationally.

Methodological approaches with the potential for replication and adaptation: The second objective is to identify models of working from GOGIG (derived from the implementation of projects undertaken under Outputs 1 to 5) which could be applied both within and beyond the oil and gas sector to enhance the implementation and design of other programmes in Ghana and beyond.

Anticipating the changing context: GOGIG’s closure in 2020 coincides with a major change in the operating context for Oil and Gas in Ghana, as petroleum activities move onshore from sea waters, with the completion of seismic studies in the Voltaian Basin. This shift will raise opportunities and challenges, which some of the lessons from GOGIG can highlight and suggest policy responses for.

Contribute to the independent assessment for the Project Completion Review: Produce externally validated evidence to corroborate logframe results, and support DFID’s final evaluation and impact assessment of GOGIG. The use of external consultants in triangulating these Outcome-level results will not only be helpful in terms of ensuring objectivity and credibility in confirming GOGIG’s LF results, but also has the potential of generating fresh insights on the range of factors that determined GOGIG’s performance.

A sustainability mapping of all programme interventions has been completed, and an Organisational Development consultant has been contracted to support core accountability partners; ACEP and PIAC, to roll out agreed sustainability measures.

Progress on recommendations from previous reviews (1/2 page)

All recommendations from last year’s Annual Review were agreed and action has been taken to respond. The table below summarises programme level recommendations and progress made. Output level recommendations are not reported here.

Recommendation	Progress
GOGIG should develop and roll out a sustainability and exit plan. This should focus on influencing additional changes at the Outcome level targeted at sustaining the sector’s progress and mitigating risks of regression after programme closure (programme team, Apr 2019)	Ongoing. Sustainability mapping of all programme interventions has been completed. Sustainability considerations have been used in the assessment of new project proposals and activities for this year.
DFID should consider the feasibility of a follow-up programme/support to further build on the benefits that have been accrued from the GOGIG programme. A six-month no-cost extension to the project will allow for a smooth transition to the next phase of support.	A six month no-cost extension for the current GOGIG programme has been secured, and business case for GOGIG Phase 2 is under development.
There is a real risk of the annual amount allocated in the GoG Budget from oil revenues (ABFA) is being used for piecemeal and economically unproductive activities. There is evidence of this type of allocation of ABFA in the civil society monitoring and transparency initiatives supported by GOGIG. The programme should undertake a political economy analysis (PEA) looking at the drivers for this sub-optimal allocation, to be able to inform opportunities for advocacy and changes to the process.	Political economy analysis has been completed, the findings emphasise strong political incentive to initiate multiple projects resulting the thin spread of ABFA. It highlights the fact that there is little GOGIG can do to counter this political incentive beyond building strong public pressure through mechanisms like PIAC and the opportunity of elections
Ensure that the programme is keeping informed of political economy developments, especially in the run up to an election year. In working with DFID, the programme should continue to share political insights and also consider when and how best to use DFID and the BHC in Ghana to influence GoG actors to help achieve its objectives.	Ongoing. The programme continues with its environmental scans and assessments of political developments with implications for the programme and provide regular updates to the SRO and as part of its quarterly reports
Develop a framework that articulates the programme’s approach on inclusive growth and the four targeted non-revenue areas for interventions under the newly introduced Output 5.	Complete. Programme paper on inclusive growth articulates the contribution of different interventional areas in Output 5
GOGIG and DFID SRO should consider the level of ambition of the logframe and whether a review or update of the indicators and milestones are needed to ensure that the outputs and outcomes are clearly linked, with a focus on achieving inclusive growth. Any review of the logframe should be completed by February 2019.	Complete. Logframe update agreed in Apr 2019.
Identify strategies for capturing, distilling, and disseminating learning from the programme’s approaches, successes and challenges.	Done. Learning plan for programme has been developed and started implementation.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided