Type of Review: Annual Review

Project Title: Access to Family Planning Commodities in Nigeria

Date started:	01 October 2011

Date review undertaken: Feb/Mar 2014

## Introduction and Context

What support is the UK providing?
The UK will provide £18 million over 6 years (2011/12 – 2016/17) to the United Nations Population Fund (UNFPA) to procure Family Planning Commodities for the public health sector in Nigeria, providing the equivalent of 1 million Nigerian couples with modern family planning each year for 6 years.

What are the expected results?
The programme goal is to improve access to a mix of quality contraceptive commodities, through: / Adequate quantities of appropriate mix of quality contraceptives procured and distributed; / Efficiently managed national contraceptives supplies and logistics management system. / Outcome measures of success include: / by 2017 a cumulative total of 6 million Couple Years Protection (CYP) of commodities procured and distributed to public health facilities in Nigeria; and / by 2016, at least 50% of family planning service delivery points in 12 select States in Nigeria provide at least 3 methods of modern contraception. / Impact measures of success include: / an increase in modern Contraceptive Prevalence Rate (CPR) from 9.7% (2008 baseline) to 20% by 2016; / a reduction in the number of States with a CPR of less than 15%, from 24 States (2008 baseline) to 10 States by 2016; and / A reduction in adolescent (<19 years) birth rate from 126 per 1,000 (2008 baseline) to 114 per 1,000 by 2016. / In turn this will contribute to a reduction in Maternal Mortality Ratio from 545 per 100,000 live births (2008 baseline) to 136 by 2016.

What is the context in which UK support is provided?
An estimated 30,000 Nigerian women die each year during pregnancy and childbirth[1]. Family planning contributes to reducing maternal mortality by reducing the number of births and thus the number of times a woman is exposed to the risk of mortality[2]. In addition, family planning increases birth intervals which has a positive effect on outcomes for the mother, and both the child born and the older sibling[3]. At the time of project inception, the contraceptive prevalence rate (CPR) in Nigeria was only 10%, and almost six out of ten married women who wanted to use contraceptives did not have access to modern contraceptive methods1. / In 2011, the Government of Nigeria (GoN) established the National Reproductive Health Policy with an ambitious goal to increase CPR by 2% annually, reaching a target of 30% by 2015[4]. To help achieve this, the GoN announced the removal of user fees for contraceptives in public health facilities and established lines for reproductive health (RH) in their national budget for the first time, committing $3m to contraceptive procurement, and signing a Memorandum of Understanding with UNFPA to procure contraceptive products on their behalf. However, this commitment is far short of the estimated $11 to $16 million required each year to meet contraceptive procurement needs[5]. Additional challenges to attainment of the CPR goal include a complex delivery and decision making process, with fragmented funding and lines of accountability between federal, state and local government levels and limited capacity within the health system to deliver quality services and provide an effective oversight function. Furthermore, family planning is a sensitive issue in Nigeria, particularly in religiously conservative northern states, where family planning has been treated with resistance and suspicions, and where making inroads to increase CPR is particularly challenging. / The Global Programme to Enhance Reproductive Health Commodity Security (GPRHCS) is a leading UNFPA program to help ensure access to a reliable supply of contraceptives, condoms, medicine, and equipment for FP, sexually transmitted infections/HIV prevention, and maternal health services. Nigeria is one of twelve Stream 1 countries receiving multi-year support from UNFPA for Reproductive Health Commodity Security (RHCS). / To support GoN and UNFPA efforts both DFATD Canada and DFID agreed in 2011 to provide additional funding for the procurement of contraceptive commodities. A basket fund, held by UNFPA, was created to pool all funding for contraceptive commodities, including both donor and GoN funding. DFID’s £3 million annual contribution to contraceptive commodity procurement is administered through this fund. / In 2011, to guide the procurement and distribution of reproductive health commodities, the Federal Ministry of Health (FMoH) established a Reproductive Health Commodity Security Technical Working Group (RHCS TWG) which was mandated to provide guidelines on contraceptive forecasting, procurement and distribution to and within States. In January 2012 the TWG inaugurated a Procurement Supply Management (PSM) sub-committee to monitor and track procurement of contraceptives from the basket fund. / In addition to direct funding for the procurement of contraceptive commodities, technical assistance for procurement, supply chain management, service delivery and demand generation is provided by UNFPA and the USAID funded DELIVER project, both of which are members of the PSM and RHCS TWG. / Ensuring that women and girls have the ability to choose whether, when and how many children to have is a priority for the UK Government. DFID’s 2011- 2015 Business Plan sets out a global target to enable at least 10 million more women to use modern methods of family planning by 2015. This programme represents 10% of that target.
[1] Nigerian Demographic and Health Survey, 2008.
[2] Stover J, Ross J. How contraceptive use has reduced maternal mortality. Maternal Child Health J.2009; 14: 687-695.
[3] James Trussell and Anne R. Pebley: The Potential Impact of Changes in Fertility on Infant, Child and Maternal Mortality. Studies in Family Planning Vol. 15, No. 6 (Nov. - Dec., 1984), pp. 267-280
[4] National Reproductive Health Policy and Strategy to Achieve Quality Reproductive and Sexual Health for All Nigerians. FMOH, Abuja, Nigeria May 2011.
[5] USAID DELIVER project assessment

## Section A: Detailed Output Scoring

Output 1: Effectively managed national contraceptive supplies and logistical management system
Output 1 score and performance description: B Output moderately did not meet expectation / Progress against expected results: / To ensure the uninterrupted availability of a range of contraceptive commodities at service delivery points, an effectively managed contraceptive supply and logistics management system entails: / accurate forecasting of national contraceptive requirements; / timely procurement and contraceptive delivery at national level; / sufficient storage capacity at national and State levels; / timely distribution from federal level to States, and from States to facilities (service delivery points); and / a functioning logistics management information system to track commodity distribution, consumption, wastage and procurement needs. / A) Forecasting of contraceptive requirements / Forecasting of national contraceptive needs is carried out annually by the PSM Committee. Members of the PSM Committee include the Family Health Division of the FMoH, UNFPA, DFID, DFATD Canada and the USAID-Deliver programme. The PSM Committee functions well, meeting monthly to review annual forecasts, contraceptive procurement progress, distribution to States and service delivery points, consumption and stock outs, making amendments to forecasts and procurement plans as required. / B) Contraceptive procurement / UNFPA has in place a centralized pooled procurement process, using pre-qualified vendors. UNFPA places procurement orders on behalf of the GoN in accordance with procurement plans developed by the PSM Committee. / Although the project was intended to purchase contraceptive commodities only, as commodity supply increased, it became apparent that demand for long acting reversible methods (LARCs) was increasing, but access was limited due to a shortage of insertion/removal kits. Hence in 2013 DFID agreed to a request from the PSM Committee, to use a portion of DFID’s 2013/14 funds ($1,565,625) for the purchase of LARC insertion and removal kits. / C) Storage at national level / UNFPA is responsible to clear contraceptives through customs and deliver to the Central Contraceptives Warehouse (CCW). For maximum efficiency and to ensure uninterrupted commodity supply to States with minimum wastage, a minimum of 9 months and maximum of 18 months stock should be stored centrally at any given time. Following the removal of user fees in 2011, demand for contraceptives increased resulting in increased procurement requirements and a need for increased storage capacity. The GoN assigned an additional warehouse, ‘Shed 36’, for contraceptive commodity storage. / In 2012, an assessment of CCW and Shed 36 was undertaken by FMoH, UNFPA and USAID-Deliver. This assessment found that significant rehabilitation was required to upgrade these facilities to ensure secure and adequate capacity for the storage of contraceptive commodities. A request was made to DFID Nigeria, and it was agreed that $250,000 from the balance of DFID funds held at that time by UNFPA for contraceptive procurement could be used to fund the renovation. This work was completed in December 2013. / D) Transport and delivery from national to State level / The transport and delivery of contraceptives from national to State level is funded by the FMoH, and on the whole functions well. Each State is expected to store a minimum of 4 months stock. Every 4 months States submit a Requisition Issue and Report Form (RIRF) to the FMoH, summarizing contraceptive usage and placing a new order based on consumption over the past 4 months. Based on this order, FMOH distributes commodities from the CCW/Shed 36 directly to State stores. Overall, this process works effectively and stock outs at state level are uncommon. / E) Transport and delivery from State to service delivery points / The responsibility for the delivery of contraceptives from the State warehouses to service delivery points lies with each State. Prior to 2011, States raised money for distribution from the sale of contraceptives in public health facilities. However, the removal of user fees in 2011 resulted in a loss of income at State level, and as a result distribution stalled and stock outs at facility level increased. Lagos State responded by allocating a budget line for the distribution of contraceptives to SDPs, but no other State has done so to date. / To address this challenge in the short-term, since 2012, UNFPA Nigeria has utilized GPRHCS funds to support the distribution of contraceptive commodities from State stores to SDPs in 34 States[6] and FCT. Distribution to service delivery points takes place through regular ‘review-resupply meetings’. This approach was piloted by USAID in three States (Bauchi, Kano, Nassarawa), where regular review-resupply meetings led to improved reporting rates from 40% to 98% and reduced stock out rates to lower than 5%. At the review-resupply meeting, SDPs bring their remaining contraceptive commodities to State level and present their family planning activity records for joint review with the FMOH, State and LGA colleagues. At this meeting, challenges faced and quality control issues are discussed. The review-resupply meetings service as both a clinical/technical meeting and a logistics exercise. All SDPs use standardised RIRF forms and replenish their stocks based on validated usage figures. Commodities are carried in person by the health worker back to the service delivery point following the meeting. / Initially UNFPA planned to support review-resupply meetings in each State every two months (6 annually), in line with the Contraceptives Logistics Management System design agreed by the PSM committee. However, due to late availability of funds and conflicting schedules in the FMoH workplan, only 2 sessions were held in 2012 and only one in 2013. / As a result of these challenges, the number of SDPs that reported contraceptive stock-outs increased in 2013 compared to 2012 (see Output Indicator 1 below). / To forestall this, UNFPA has signed an MoU with PPFN, Axios and CHAI to support review meeting in 2014, and schedules have been fixed for March, May, July, and September. The March 2014 review-resupply meeting was conducted as planned. / Currently review-resupply meetings are funded by UNFPA. However, to ensure the regular distribution of contraceptive commodities to SDPs in the long-term, each State must establish and fund its own process for the distribution of contraceptive commodities to SDPs (see Recommendation 1 below). / F) Logistics Management Information System / UNFPA has supported the establishment of a Logistics Management Information System (LMIS) for contraceptive commodities (CHANNEL softwear). This has been introduced at State level in all States, and all the 37 State Family Planning Coordinators have been trained in its use with the support of UNFPA and USAID- Deliver. However roll out at LGA level is not yet complete. / It is worth noting that the entire procurement, storage, distribution and disbursement of contraceptive commodities is managed as a vertical programme from national to facility level, including separate storage facilities and separate distribution mechanisms. States are not keen to mix contraceptive commodities which are free with commodities procured through revolving drug funds. However this approach may reduce efficiencies in the system and opportunities to distribute contraceptives to facilities through existing supply chain mechanisms are lost (see Recommendation 1, below). / Progress against logframe targets / Output Indicator 1: Proportion of service delivery points with NO stock outs of contraceptives for more than 7 consecutive days in 3 months[7] / Family planning SDPs at primary health care level should offer at least 3 contraceptive methods, while secondary health care SDPs should offer at least 5 contraceptive methods at any point in time. Any SDP which has less than this number of contraceptives available for more than 7 consecutive days is considered to have a ‘stock out’. / In 2007, 30% of SDPs reported no stock-out of contraceptive commodities[8]. In 2011 (before programme inception), a national facility based survey showed that this had increased to 44%[9]. In 2012, following initiation of this project, the proportion of SDPs reporting no stock-out increased to 67%[10]. However, this decreased to 52% in 2013[11]. / In 2013, the two main reasons for stock-outs at SDP level were failure to requisition supplies and a lack of stock at State level to replenish SDP supply. Thus although commodity supply has improved during the project period, distribution to SDP level remains problematic and has worsened in 2013 when compared to 2012. / The most common types of contraceptives provided at primary health care SPDs are male condoms, injectables and oral contraceptive pills. Women who require an alternative method, particularly long-acting methods (intra-uterine contraceptive devices [IUDs] and long-acting reversible contraceptives [LARCs]) must be referred to a higher level. However, even at secondary care level the provision of long-acting methods is not universal, and it is not certain how many women are referred appropriately, nor the proportion of women who actually receive the contraceptive that is most suited to their need and in accordance with their choice. / Summary: / The numerical targets for Output Indicator 1 were exceeded in both 2012 and 2013. However, 2012 and 2013 targets were based on a 2007 baseline and were actually lower than the national stock-out level reported in 2011, prior to the start of the project. Although the achieved results in 2012 and 2013 were higher than 2011, and higher than target, the proportion of SDPs reporting no-stock decreased in 2013 compared to 2012. For this reason, this indicator is reported B ‘output moderately did not reach expectation’. / Table 1 Progress against Output 1 logframe targets / Indicator Baseline (2007) Milestone 1 (2012) Milestone 2 (2013) / 1.1 Proportion (%) of service delivery points with no stock-outs of contraceptives for more than 7 consecutive days in 3 months* Planned 30% 32% 37% / Achieved - 67.4% 51% / * This refers to only those facilities that provide FP services (both primary and secondary), rather than all facilities / This refers to available stock of 3 modern methods in primary health care SDPs and 5 modern methods in secondary health care SDPs / Recommendation 1 / UNFPA and partners should work with State Governments to establish a State-led and State-funded process for the distribution of contraceptive commodities to service delivery points. Options to improve efficiency, such as the integration of contraceptive supply and distribution with other commodities should be explored. DFID funded programmes, PATHS2 and MNCH2, should assist programme States to establish this process. / Recommendation 2 / The project logframe should be revised to include indicators that provide a better measure of the range of contraceptive methods available, including LARCs. The baseline should be reset to incorporate 2011 GPRHCS survey data, and targets revised accordingly. / Impact Weighting (%): 100% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[6] The distribution of contraceptive commodities in the remaining two States is funded directly by USAID
[7] The project log-frame States that this target will be measured in 12 States only. During project design it was decided that this would be an appropriate measure because UNFPA provides technical support to 12 States, in addition to the procurement of commodities for national distribution. However, the commodities procured through DFID funding are for nationwide use, and hence we would expect to see impact at national level. For this reason, during this project review, UNFPA and DFID agreed that it would be more appropriate to measure national stock-outs under this indicator. If this indicator only measures stock outs in States that receive technical assistance from UNFPA this would not be representative of the nation as a whole, and would not reflect results that could be attributed to DFID support.
[8] Contraceptive Logistics Management System Assessment Report, 2007.
[9] Facility Assessment for Reproductive Health Commodities and Services in Nigeria, 2011 Report. FMoH and UNFPA, 2012.
[10] Facility Assessment for Reproductive Health Commodities and Services in Nigeria, 2012 Report. FMoH and UNFPA, 2013.
[11] Facility Assessment for Reproductive Health Commodities and Services in Nigeria, 2013 Report. FMoH and UNFPA, Jan 2014.

Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? No / This is DFID’s first review of the UNFPA ‘Access to Family Planning Commodities’ procurement programme (although DFID, UNFPA and other partners have taken part in the Joint Annual Reviews led by the FMoH). Therefore this review has been undertaken against the original Business Case logframe, covering the period between programme inception in October 2011, to the end of March 2014 (2.5 years, reviewing progress against 2012 and 2013 milestones). / Reviews will be carried out annually in the future. / 1.2 Overall Output Score and Description: B outputs moderately did not meet expectation / Direct feedback from beneficiaries / The primary beneficiaries of the programme are women and men who have improved access to a mix of modern methods of contraception. / Client perspectives on the provision of family planning services were gathered, for the first time, through the 2013 GPRHCS Survey. Exit interviews were conducted with clients at 1021 facilities (one client per facility). The exit interview gathered information on the availability of contraceptives of the patients’ choice, provider attitude and behaviour, family planning counselling, privacy, facility cleanliness and waiting times. The majority of clients (93%) indicated they had been provided with the method of choice requested and the majority (93%) also indicated they felt they were satisfied with the service provided. / However, this survey only recorded outcomes from clients who had received a service, and did not capture information from those who did not. Additionally, only one client per facility was surveyed and although a high proportion of clients reported receiving the contraceptive of their choice, the survey did not assess whether clients had been appropriately counselled about different methods and offered a more suitable alternative if appropriate. Thus the findings of the survey should be interpreted with caution. / In 2014, UNFPA plans to conduct at least one focus group to collect more detailed information on user satisfaction and quality of service delivery.
1.4 Summary of overall progress / Through the Access to Family Planning Commodities Programme, significant volumes of contraceptive commodities have been procured and delivered to SDPs across Nigeria. Stock-outs are less frequent than in the period prior to DFID intervention. However, stock-outs were higher in 2013 than 2012, indicating continuing weaknesses in the supply chain and distribution system.
Key challenges / Storage Space / As procurement requirements increased, the need for storage space at federal level also increased. Although the FMoH made provisions for additional storage, the poor State of repair of federal stores (CCW and Shed 36) necessitated renovation, which was only completed in December 2013. Additionally, FMoH funds for the distribution of commodities to States were released late in 2013, which had an impact on central storage capacity. UNFPA used private warehouses to address short term storage needs. It is expected that this will no longer be necessary now that CCW and Shed 36 have been rehabilitated. / Supply chain management / As indicated previously, the distribution of commodities from States to SDPs remains problematic. The review-resupply meeting put in in place by UNFPA and USAID-Deliver provide a short term solution, but even these meetings have been infrequent due to late funding and poor coordination of plans with FMoH. FMoH and UNFPA continue to advocate to State Governments for the provision of funds to establish a State-led process for contraceptive commodities distribution. Concerted effort is required by FMoH, UNFPA and partners, including DFID and DFID programmes, to ensure that State Governments establish such measures (see Recommendation 1 above). / Consumption based forecasting / Current forecasting is based on the consumption of contraceptive commodities, which in turn depends on client demand for the different types of contraceptive methods, and the competence of health workers to provide each method. If clients are unaware of some contraceptive methods, and/or if providers are not skilled to provide a particular type then consumption patterns will not reflect the most appropriate distribution for the particular client group. To address this, UNFPA and partners are supporting provider training in family planning methods, with a particular focus on long acting reversible contraceptives (LARCs) and are supporting community awareness raising on different family planning methods (including through the DFID funded PRRINN-MNCH and PATHS2 programmes).
1.6 Annual Outcome Assessment / The project is on track to attain the desired outcome of procuring and distributing 6 million CYPs of commodities to public health facilities in Nigeria by 2017. However, the programme does not appear to be on track to ensure that at least 50% of all SDPs provide family planning services and offer at least 3 modern methods of contraception by 2016. / Outcome Indicator 1: Couple Years of Protection of commodities procured with DFID funds and distributed to public health facilities / Contraceptive commodities are procured in accordance with the national contraceptive procurement plan set by the PSM Committee. Additional considerations taken into account by UNFPA when determining the mix of contraceptives procured with DFID funds include: / Availability and timing of disbursement of DFID and other non-DFID partner funds (for instance, in 2013, DFID funds arrived later than other partners so a number of LARCs had already been procured using other funds); / DFID CYP targets (the longer acting methods have higher CYP per unit). / Table 2: Estimated CYP for DFID funded procurement in 2011, 2012, 2013 / Contraceptive Type CYP per unit Quantities procured Total CYP / (CYP per unit x quantities procured) / 2011 2012 2013 2011 2012 2013 / Depo Provera 0.25 365,000 0 803,000 91,250 0 200,750 / Exluton 0.067 270,000 1,282,079 0 18,090 85,899 0 / IUCD 3.5 115,000 450,000 0 402,500 1,575,000 0 / Noristerat 0.167 1,800,000 806,300 388,650 300,000 134,383 64,775 / Implanon 3.5 7,040 87,040 0 24,640 304,640 0 / Jadelle 3.5 7,000 0 111,000 24,500 0 388,500 / Microgynon 0.067 0 0 1,800,000 0 0 120,000 / Male condom 0.0083 18,288,000 0 11,300,0000 152,400 199,167 / Total CYP per year 1,013,380 2,099,922 973,192 / As shown in Table 3, the cumulative CYP from 2011 to 2013 is 4.1 million, significantly greater than the project target of 3 million by 2013. / Table 3 Progress against Outcome 1 logframe targets / Indicator Baseline (2011 after programme approval) Milestone 1 (2012) Milestone 2 (2013) / Couple Years of Protection (CYP) of commodities procured with DFID funds and distributed to public health facilities Planned 1 million 1 million 1 million / Achieved 1,013,380 2,099,922 973,192 / Cumulative CYP 1,013,380 3,113,302 4,086,494 / Outcome Indicator 2: Proportion of service delivery points providing at least 3 methods of modern contraceptives[12] / The 2012 and 2013 GPRHCS surveys found that nearly 90% of SDPs providing family planning services reported that they provided at least 3 modern methods. However, if the denominator used is ‘all health facilities’ (not only those known to be providing family planning services), this figure is reduced to 21% in both 2012 and 2013. Only around 7,000 of the 30,000 health facilities in Nigeria currently provide family planning. A major limiting factor is the availability of trained health providers. UNFPA and donor programmes (including the DFID funded PRRINN-MNCH and PATHS2), have provided family planning training to service providers, with an increasing focus on the use of LARCs. In 2012 government policy was changed to allow community health extension workers (CHEWs) to provide injectable contraceptives (although not IUD/LARCs). Between 2013 - 2015, UNFPA will train 5,500 health workers in a range of contraceptive methods, including CHEWs. This has the potential to increase the number of SDPs for family planning services, but whether these actions will be sufficient to reach programme targets is uncertain. / Although the logframe targets for 2012 and 2013 were exceeded, the targets were based on a 2007 baseline, which was not updated at project inception, and there was no increase in the number of SDPs providing family planning services between 2012 to 2013, raising doubt that the project is on track to reach a target of 50% by 2016. / Table 4 Progress against Outcome 2 logframe targets / Indicator Baseline (2007) Milestone 1 (2012) Milestone 2 (2013) / Proportion of service delivery points* providing at least 3 methods of modern contraceptives Planned 14%[13] 15% 20% / Achieved - 20.8%[14] 20.9%[15] / * This refers to ALL health facilities, not only those facilities that provide FP services / Recommendation 3 / UNFPA should continue to train health care providers, including CHEWs, in contraceptive service provision. DFID programmes (PATHS2, MNCH2 and PUMDUP) should continue to liaise with UNFPA when developing training plans to ensure the coordinated and rational selection of workers for family planning training. UNFPA and DFID programmes should also liaise in the development and implementation of supervision/mentoring schemes for health workers.
[12] The project log-frame States that this target will be measured in 12 States only. During project design it was decided that this would be an appropriate measure because UNFPA provides technical support to 12 States, in addition to the procurement of commodities for national distribution. However, the commodities procured through DFID funding are for nationwide use, and hence the project aims to increased access to FP commodities across all States. Hence during the review it was agreed by DFID and UNFPA that this indicator should report the national proportion of facilities offering at least 3 methods of modern contraception. If this indicator only measured availability in States that receive technical assistance from UNFPA this would not be representative of the nation as a whole, and would not demonstrate the impact of DFID support.
[13] Contraceptive Logistics Management System Assessment Report, 2007.
[14] Facility Assessment for Reproductive Health Commodities and Services in Nigeria, 2012 Report. FMoH and UNFPA, 2013.
[15] Facility Assessment for Reproductive Health Commodities and Services in Nigeria, 2013 Report. FMoH and UNFPA, Jan 2014.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / As shown in Table 5, DFID has disbursed £12m to UNFPA to date. The 2014/15 disbursement was brought forward to 2013/14 financial year to enable UNFPA to plan ahead for procurement. The next disbursement is planned for 2015/16 financial year. / Table 5 Summary of disbursement and use of DFID funds to UNFPA / Financial Year (FY) UNFPA Programme Year Date funds transferred to UNFPA Total DFID funds to UNFPA / 2011/12 Year 1 (2011) 05 Oct 2011 £3,000,000 / 2012/13 Year 2 (2012) 05 Mar 2012 £3,000,000 / 2013/14 Year 3 (2013) 13 Feb 2013 £3,000,000 / 2014/15* Year 4 (2014) 21 Nov 2013 £3,000,000 / 2.2 Key cost drivers / The main cost driver is the cost of commodities, which is determined by the mix of commodities procured together with the unit costs of the commodities. / The project business case anticipated that DFID funding would be used solely for the purchase of contraceptive commodities. However, on two occasions DFID has agreed to the use of unallocated funds held by UNFPA to be utilised for other activities. In 2012 DFID agreed that $250,000 (representing 5.6% of FY 2012/13 funding) could be used for the renovation of federal warehouses (CCW and Shed 36), and in 2013 DFID agreed that $1,565,625 (representing 35% of 2013/14 funding) could be used for the purchase of LARC insertion and removal kits. Although the use of funds for other purposes has reduced the amount of commodities and CYPs purchased with DFID funds, the cumulative CYP attained by the project remains above target, and the rehabilitation of storage facilities and procurement of LARC insertion and removal kits have addressed critical bottle-necks that would otherwise have limited the available of contraceptives to the end-user. / 2.3 Is the project on-track against original timescale: Yes / During the first three years of the project satisfactory progress has been made and commodities procured and distributed in accordance with the original schedule. However, as indicated above, the project needs to make additional effort to ensure that outcome targets are attained by the end of the project period.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The project was designed with the assumption that action to ensure a functioning distribution system and to build health worker capacity for the delivery of the required mix of contraceptives to the end user would take place alongside this project. However, this has not proven to be the case. / As indicated previously, UNFPA has initiated measures to improve distribution to service delivery points, and programme funding has been used flexibly to address critical bottlenecks. Additionally, UNFPA and other DFID funded programmes (PATHS2 and PRRINN-MNCH) have collaborated to train and supervise health workers in the provision of family planning services. / However concerted effort is required by UNFPA, DFID and other partners to ensure that State and Federal Government allocate sufficient resources for the procurement and distribution of family planning commodities and supplies, and that capacity for family planning service delivery is built across all levels of the health system, including at community level. / The Business Case also assumed that demand for family planning services would increase as supply increased. At this stage, since supply remains erratic, it is not possible to determine whether this assumption holds true. However evidence from other DFID funded programmes (PRRINN-MNCH and PATHS2) suggests that community level interventions (awareness raising, women’s empowerment) are also necessary to increase demand, even where supply is consistent. / The continuing poor functioning of the supply chain system from state to facility level, and persistent shortages of skilled health workers have significantly impaired the ability of this project to ensure the provision of quality contraceptives to the end user and hence to attain project impact. / To address some of these challenges UNFPA has planned a study tour to Niger in 2014 with State representatives, which may provide additional evidence to consider in effective models for delivery of FP commodities in Nigeria, particularly increasing demand at community level. Niger and Nigeria have similar populations, but Niger has successfully doubled its CPR over 2-3 years, using a model of ‘husband schools’ to enable communities to discuss health issues including Skilled Birth Attendants, immunisations, and having fewer children. / Although the study tour may provide lessons to improve the delivery of FP services in Nigeria, the evidence that has emerged since project inception indicates a need to take stock of this project and consider redesign to better address the underlying barriers to effective contraceptive provision. This should draw on lessons learned from DFID funded health system projects (PRRINN-MNCH, PATHS2 and MNCH2), and should strengthening collaboration with these projects in focal states.3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / Table 6 describes risks that were identified in the project business case and mitigating action taken to address them. / Table 6 Review of programme risks and impact / Risk identified in the BC Impact on results Likelihood Update on risk for this Annual Review in March 2013 Change to risk impact / likelihood levels? / Government / other key stakeholders resist scaling up family planning in Nigeria. High Low UNFPA and donor programmes (including DFID programmes) have engaged traditional, religious and political leaders in debates around family planning and resistance to scale up is minimal. No / Health services are too weak at the primary and community level to deliver family planning services Medium Low/ / Medium Health services are improving across most States. Policies such as Primary Health Care Under One Roof, GoN and donor support for health worker training and supervision, and task shifting to CHEWs to provide injectable contraceptives, are contributing to improved service delivery at primary and community level. No / Logistics management system fails to ensure commodities are moved from port to facilities at the right time in the right amounts High High Logistics systems in Nigeria are improving, but challenges remain particularly from State to facility level. Yes – increased to high in light of continuing problems with distribution from States to service delivery points / The incorrect method mix is procured leading to stock outs of some commodities and others going to waste. Low Low The monthly PSM enables responsive discussions about method mix and procurement requirements.. Contraceptive commodities have a long shelf life and there is no evidence of commodities going to waste. No
However, as the programme reaches its mid-point, there is a significant risk that the impact and outcomes of the project will not be sustained in the long-term, after the withdrawal of DFID funding. / As set out in the project business case, it was intended that DFID funding would stimulate GoN to increase funding for reproductive health and ensure a sustainable supply of contraceptives in the long-term. In 2011, the Federal budget included an allocation for reproductive health for the first time. However the budget allocation has remained constant at $3 million annually between 2011 to 2014. At the 2012 Family Planning Summit the President committed an additional US$8.35 million annually for 4 years (from a removal of the petrol subsidy/SURE-P funds); however this was not disbursed at all in 2012 due to the time it took to get the SURE-P committee to sign off the funds, and only US$2m was disbursed in 2013. UNFPA have been assured by GoN that the remaining US$6.35m will be disbursed in early 2014, and that the 2014 contribution will be forthcoming as FMoH signed an MOU with UNFPA in 2014 to cover 2013 and 2014 funds. However, with elections in 2015, it is unclear whether the full 4 year commitment will be realised. Additionally, provisions have not been made for increased GoN funding beyond 2016 when the additional funding provided through SURE-P is due to end. / Recommendation 4 / UNFPA, DFID and partners should advocate to the GoN at Federal and State levels to ensure adequate budgetary allocation for the procurement and distribution of family planning commodities. The RHCS TWG should develop a strategy to leverage increased government resources and should develop a risk management plan that establishes mitigation measures should GoN funds not be forthcoming. At State level UNFPA and DFID programmes should coordinate to present a consistent message to State governments on the need to support contraceptive services as part of wider health system strengthening efforts. / Risk of funds not being used as intended: Low / UNFPA is the sole Agency providing contraceptives to public health facilities in Nigeria, and is the procurement agent for the Federal Ministry of Health. / UNFPA country offices operate under centrally established policies and procedures, including policies on procurement practices. Contraceptives for this programme are procured based on identified need, in accordance with the procurement plan set by the RHCS TWG. Procurement requests are sent to UNFPA’s Procurement Services Branch who have expertise in procurement and buy in bulk on behalf of all Country offices in the international markets and so have the economies of large scale buying. Once commodities arrive in Nigeria they are stored in the central government warehouse for distribution to State level, and from there to facilities. / Each year the UN Board of Auditors conducts an audit of a select number of UNFPA country offices, and of UNFPA globally. Additionally, the UNFPA Division for Oversight Services audits a random number of countries offices each year, and is responsible to ensure that corrective actions arising from any audit are taken. In turn, UNFPA country offices commission external audits of all implementing partners in relation to the funding support they have received from the UNFPA country office. / Each year UNFPA separately and also jointly with other UN Agencies conducts anti-corruption, fraud and bribery training for implementing partners and anti-corruption Statements are included in the Letter of Understanding between UNFPA and implementing partners. / UNFPA policies and procedures establish a zero tolerance approach to fraud and set out clearly how staff can report such cases as well as the repercussions of being involved in fraud or corruption. All staff receive mandatory training on ethics and integrity. The policy document on fraud, corruption and whistleblowing policies is available to UNFPA staff and easily accessible in the UNFPA intranet where policy and procedure manuals are kept. To date, no cases of fraud or corruption have been identified in the UNFPA Nigeria country office. / In view of DFID’s commitment not to give financial aid to the Government of Nigeria, UNFPA confirmed that none of the funds provided by DFID to UNFPA for this programme are advanced to any State or FMoH controlled bank account. The funds are not jointly managed with Government, instead UNFPA uses the funds to procure contraceptives directly from manufacturers through UNFPA Copenhagen. UNFPA has confirmed that the funds used for warehouse renovations were paid directly to the vendors and suppliers. / 4.4 Climate and Environment Risk / As set out in the Business Case, there is evidence that family planning has a positive impact on carbon emissions: as the human population grows so does the demand for energy; as more energy from fossil fuel is used, more greenhouse gases are produced. Centralised procurement of family planning commodities is likely to have a more positive impact on climate change and environment than the alternatives (e.g. decentralised procurement). / Effective design of the rehabilitation of the CCW and Shed 36 with sections of clear plastic roofing means that there is sufficient light not to need electricity or a generator, which reduced cost of rehabilitation works (that would have been incurred if the warehouse had been reconnected to mains power) and will save on ongoing generator fuel costs. Extractor fans that do not need electricity have also been installed. UNFPA has allocated funds for 2014 to install solar panels in both CCW/Shed 36 to support implementation and sustainability of a computerised logistics management system.

5. Value for Money
5.1 Performance on VfM measures / No specific value for money indicators have been established for this programme. The main measure of success is the leverage of resources from GoN (and other partners). As shown in Table 7, GoN funding has increased to a limited extent and the DFID share of contraceptive procurement has reduced from 38% in 2011 to 33% in 2013. / However, as described under Section 4.2 above, the sustainability of increased GoN funding is uncertain (see Recommendation 4). / Table7: Source of funding for contraceptive commodity procurement (US$ millions)* / 2011 2012 2013 / Partner contributions to procurement GoN – Federal budget 3.0 3.0 3.0 / GoN (2012 FP Summit commitment, SURE-P funding) - - 2.0** / UNFPA 3.0 3.1 3.4 / DFID 4.5 4.5 4.5 / CIDA 1.2 1.2 0.9 / Total 11.7 11.8 13.8 / DFID share (%) 38% 38% 33% / *This table is based on the actual sums of money that were disbursed in each year. GoN FP Summit Commitment was higher, but funds were not released as per the commitment. / ** Only US$2m disbursed by end 2013, but MOU signed in 2013 for 2013 and 2014 funds. / When considering value for money across the results chain, the programme performs well on measures of economy, but performance is less strong at output and outcome level, where concerted effort is needed to improve efficiency, equity and sustainability of service provision. / Economy (the extent to which costs are minimised): / The procurement takes advantage of current centralised pooled procurement through UNFPA using pre-qualified vendors which therefore ensure that manufacturers of the pharmaceutical items and contraceptive commodities maintain the highest quality standards for lowest cost. This mechanism enables price advantages through bulk purchases internationally. / UNFPA HQ has worked with the Bill and Melinda Gates Foundation (BMGF) and the Reproductive Health Supplies Coalition (including DFID) to negotiate with manufacturers which resulted in a decrease in the cost of Jadelle LARC from US$24 in 2010 to US$8.5 in 2013. / Efficiency (the quality and quantity of outputs): / Commodities procured through DFID funds are guided by a procurement plan agreed between GoN, UNFPA and donors. This plan is based on consumption data and updated regularly through the PSM committee. Regular review and re-forecasting minimizes over-supply and the risk of wastage and minimizes drug stock outs. Since the establishment of the PSM, with improved oversight of the procurement process, the lead time for procurement has reduced from 12 months to 3.5 months. / However, supply chain challenges have not been fully resolved and stock outs still occur at facility level (see Recommendation 1). / Effectiveness (the extent to which the outputs achieve the desired outcome): / The provision of contraceptive commodities through this project, and the distribution to SDPs through GoN and partner efforts, has increased the availability of family planning commodities nationwide. However, only a small increase in the number of sites offering contraceptive services has been demonstrated, hence it is unclear the extent to which population coverage of family planning services has increased, with a risk that the national contraceptive rate may not be increasing as rapidly as desired. / A main limiting factor to increased service provision is insufficient numbers of skilled health workers. As outlined previously, GoN, UNFPA, DFID and partners are seeking to address this through programmes that train and provide supervision for health care workers. These efforts should continue and DFID funded programmes should ensure co-ordination with UNFPA and other partner efforts at State level (see recommendation 3). / Equity / The programme business case set out that the procured commodities were to be provided free in public facilities and the programme would focus on ensuring they reach women and girls most in need, those living rural areas and of the poorest wealth quintile. / Equity indicators have not been measured as part of this programme. However, preliminary data from the 2013 Nigerian Demographic and Health Survey, suggests that inequities in access to family planning persist. For example currently married women in urban areas are considerably more likely to use any method of contraception (27%) than women in rural areas (9%), contraceptive prevalence is higher in the Southwest (25%) than the Northeast (2.7%) and the proportion of currently married women who are using any method of contraception is only 2% among women aged 15-19 years, compared to 22% among women aged 40-44 years. Although these figures do not measure unmet need for contraception, the indications are that demand for, and access to contraceptive services remains inequitable across the country. / Recommendation 5 / Further work should be undertaken to better understand and address the remaining barriers to access to family planning services, and to measure unmet need for family planning across different population groups. UNFPA plans to conduct an in-depth regression analysis of the 2005, 2008 and 2013 DHS surveys to profile women who take up family planning and those who do not, to develop Behaviour Change Communication materials and better target messages to increase demand more equitably. The findings of this analysis should be shared with DFID and partners to ensure that lessons learned inform the design of DFID and partner programmes. / Sustainability: / The GoN has increased funding for contraceptive commodities. However, annual budget allocations are far short of the country’s procurement needs, and a substantial proportion of current GoN funding is committed until 2016 only, and comes from the non-budgetary SURE-P funds. No plans have been put in place by the GoN to continue this level of increased funding beyond 2016. / Additionally, State governments have not established funding nor processes to ensure the distribution of family planning commodities to SDPs and it is likely that stock outs will continue to increase if partner support is withdrawn. (see Recommendation 4) / 5.2 Commercial Improvement and Value for Money / Since UNFPA is the sole contraceptive procurement agent for the FMoH it was agreed through the project business case that DFID funds would be transferred to UNFPA to support GoN procurement needs. UNFPA central procurement processes continue to maximize value for money through price advantages attained by bulk procurement internationally. / The Multi-lateral Aid Review concluded that UNFPA builds strong partnerships with civil society, partner countries and other agencies. UNFPA has strengthened its oversight and financial resource management, with flexibility to respond to country needs. / 5.3 Role of project partners / UNFPA provides global technical leadership on sexual and reproductive health and rights (SRHR) and plays a critical role on to improve maternal health, to reduce HIV/AIDS and promote gender equality. The combination of expertise and experience provide by UNFPA at global and country provides an adequate combination that fits well to the needs and demands of this programme. / 5.4 Does the project still represent Value for Money : Yes / The project has procured over 4 million CYPs to date, substantially greater than the project target of 3 million by 2013. Substantial cost savings have been made and programme reach extended by embedding this project within the GoN led RHCS programme which has enabled commodities procured through DFID funding to reach a larger number of end users than could have been achieved by DFID acting alone. / 5.5 If not, what action will you take? / n/a

6. Conditionality
6.1 Update on specific conditions N/A

7. Conclusions and actions
The Access to Family Planning Commodities project has enabled the procurement of contraceptive commodities sufficient to provide over 4 million CYPs to date, exceeding by 30% the project target. However, significant challenges remain to ensure that commodities reach the end user and to ensure equity in service provision. Additionally, evidence to date suggests that project impact will not be sustained beyond the lifetime of this project unless significant financial resources are mobilized from GoN, and capacity is built across all levels of the supply chain and delivery system. / In light of the above, there is an urgent need to take stock of this project, and consider project redesign to better address the underlying barriers to achieve impact and sustainability. Specific recommendations to be considered in project re-design include: / Recommendation 1 / UNFPA and partners should work with State Governments to establish a State-led and State-funded process for the distribution of contraceptive commodities to service delivery points. Options to improve efficiency, such as the integration of contraceptive supply and distribution with other commodities should be explored. DFID funded programmes, PATHS2 and MNCH2, should assist programme States to establish this process. / Recommendation 2 / The project logframe should be revised to include indicators that provide a better measure of the range of contraceptive methods available, including LARCs. The baseline should be reset to incorporate 2011 GPRHCS survey data, and targets revised accordingly. / Recommendation 3 / UNFPA should continue to train health care providers, including CHEWs, in contraceptive service provision. DFID programmes (PATHS2, MNCH2 and PUMDUP) should continue to liaise with UNFPA when developing training plans to ensure the coordinated and rational selection of workers for family planning training. UNFPA and DFID programmes should also liaise in the development and implementation of supervision/mentoring schemes for health workers. / Recommendation 4 / UNFPA, DFID and partners should advocate to the GoN at Federal and State levels to ensure adequate budgetary allocation for the procurement and distribution of family planning commodities. The RHCS TWG should develop a strategy to leverage increased government resources and should develop a risk management plan that establishes mitigation measures should GoN funds not be forthcoming. At State level UNFPA and DFID programmes should coordinate to present a consistent message to State governments on the need to support contraceptive services as part of wider health system strengthening efforts. / Recommendation 5 / Further work should be undertaken to better understand and address the remaining barriers to access to family planning services, and to measure unmet need for family planning across different population groups. UNFPA plans to conduct an in-depth regression analysis of the 2005, 2008 and 2013 DHS surveys to profile women who take up family planning and those who do not, to develop Behaviour Change Communication materials and better target messages to increase demand more equitably. The findings of this analysis should be shared with DFID and partners to ensure that lessons learned inform the design of DFID and partner programmes.

8. Review Process
The review was carried out in February and March 2014 by Amy Potter (Health Adviser, Human Development Team), Ruth Lawson (Senior Health Adviser, Northern Nigeria Team) and David Ukagwu (Deputy Programme Manager, Human Development Team), DFID Nigeria. The Annual Review was informed by a visit to the CCW/Shed 36 in Lagos, where the review team met with representatives from UNFPA, the FMOH and warehouse management, and by a visit to Ikeja Primary Health Care facility in Lagos which provides Family Planning services to a catchment population of 9,138. Data summarising UNFPA activity against logframe targets was collected by UNFPA and discussed with DFID. / The final report and recommendations were prepared by DFID.