Type of Review: Annual Review

Project Title: South Sudan Health Pooled fund

Date started:	12.10.2012	Date review undertaken: October 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing £56 million over 3 ½ years (October 2012 - April 2016) to improve health outcomes in South Sudan. Four other donors (Australia, Canada, Sweden and the European Commission) are contributing £61m to the programme (as committed through Delegated Cooperation Agreement with DFID).

What are the expected results?
The impact of this programme will be Government led health systems that save lives. The overall outcome will be an increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. Three outputs this programme will deliver to achieve the outcome are: / Strengthened delivery of health services, particularly responsive to the needs of women and children / Increased ownership, governance and demand of communities for health service / Strengthened health systems at State and County level with detailed focusing on / Policy / Human resources for Health / Health Financing including strengthening of payroll and Local Services Support Framework / Health Information / Leadership and governance / The results attributable to DFID are: / 254,959 under five year olds are seen for a curative consultation / 21,853 women have at least four antenatal visits / 21,853 pregnant women receive at least two doses of intermittent presumptive treatment of malaria as part of their antenatal care / 10,926 additional people start a family planning method

What is the context in which UK support is provided?
South Sudan is one of the poorest countries in the world. Years of conflict causing erosion of physical and social infrastructure and death and displacement of millions of people have made South Sudan one of the most underdeveloped regions in the world. Poverty is widespread. Just over half (51%) of the 8.3 million South Sudanese live below the national consumption poverty line[1]. Most live in rural areas (92.5%). The country has continued to be challenged with escalating tension from both internal ethnic clashes and on-going disputes with Sudan over oil and other issues still unresolved following the 2005 Comprehensive Peace Agreement (CPA). / South Sudan’s health needs are vast and partly result from the high poverty and long history of conflict. War has left an already very basic health care system extremely weakened, with severe shortages of health workers and functional facilities. South Sudan has the highest maternal mortality rate in the world with an estimated 2,054 women dying for every 100,000 births (South Sudan Household Survey 2010). Only 44% of the population live within 5 kms of a health facility. User rates are low and estimated at 0.2 contacts per person per year. Other major challenges to delivering services include weak health systems, inadequate infrastructure and access, lack of trained human resources, dysfunctional referral systems and cultural and financial barriers. / The Government of the Republic of South Sudan (GRSS) have expressed their commitment to improving the health of its population. To realise this commitment, the Ministry of Health (MoH) has formulated a five year strategy, Health Sector Development Plan 2012- 2016 (the ‘HSDP’), which has a vision to ‘contribute to reducing maternal and infant mortality and improving the overall health status and quality of life of the South Sudanese population’. However this is much harder to achieve without adequate state finance. In the face of shutdown, since 2012, of South Sudan’s oil wells (which were providing around 98% of GRSS revenues), the international community have continued to finance the delivery of many health services, and helped prevent a breakdown in the health system and protect the most vulnerable. This has been vital to preventing excess morbidity and a further deterioration in the already poor humanitarian situation. Recently there has been agreement to resume oil production; however it is yet to happen on a full scale. / With four other donors the UK, through the Health Pooled Fund (HPF), is supporting the delivery of the GRSS’s five year health strategy (HSDP) and helping government start transition from an NGO led health service to a ‘government led health service that saves lives’. The HPF funds the delivery of a basic package of health services comprehensively, including referral level up to county hospitals, in six out of South Sudan’s ten states. This is done through contracting a central fund manager (referred to as Principal Implementer here) to sub contract service delivery agents at county levels in the six states. The programme also provides technical assistance (TA) and capacity building support to County Health Departments and the central and state level Ministries of Health to lead and manage the health systems and service delivery effectively. HPF is a government-led programme overseen by a steering committee chaired by MoH, co-chaired by DFID and represented by other government ministries and donors. The Principal Implementer of HPF (HPF PI) is a consortium of agencies led by Crown Agents with a mandate to deliver the programme in its entirety, which includes fund management and technical support. / To allow flexibility in the face of uncertainties of state financing and low government capacities to absorb TA to strengthen health systems, the programme was designed in three phases. / Phase 1: to focus primarily on sustaining essential health services in the absence of adequate government resources. / Phase 2: to be a transition phase focusing on health system strengthening activities, with a substantially enhanced government capacity-building and transfer of responsibility for health staff from NGOs to government. / Phase 3: to focus on strengthening public financial management for the transfer of health worker salaries from NGO to government payrolls. / Before the start of HPF, several NGOs supported service delivery through a health facility based model throughout the country, with funding from at least five major humanitarian funds/projects (Basic Services Fund, Common Humanitarian Fund, European Community Humanitarian Office, the US Office for Disaster Assistance and Multi Donor Trust Fund). Under this model, service delivery was fragmented and non-standardized, focusing on project specific health facilities only. As per the division of labour endorsed by the MoH, HPF was designed to support primary health care delivery in six of the ten states (Eastern Equatoria, Unity, Western Bahr el Ghazal, Northern Bahr el Ghazal, Lakes and Warrap) taking over from these different funding streams, most of which were coming to an end in December 2012. Delivery of primary health care in remaining states is funded by USAID and World Bank, each covering two states. The primary task of HPF at the start was to issue standardised service delivery bridging contracts to the existing NGOs to prevent any interruption in service delivery until long-term contracts were awarded competitively to NGOs to support health service delivery and systems strengthening in a county based model (hall mark feature of the HPF). In the county based model County Health Department, supported by its state and national ministries of health, take the overall leadership and management of health service delivery in the county. / The programme began in October 2012. The draft inception report, with action plan for the first year of main implementation phase, was submitted in June 2013. In December 2012, bridging contracts were issued to 16 NGOs to continue health services delivery in 281 facilities in the six states. Long term contracts to NGOs were issued through competitive commercial process in three states (Eastern Equatoria, Western Bahr el Ghazal and Unity) in July 2013. The competitive process for long term contracts in the remaining three states had been concluded at the time of this annual review but the contracts had not been issued pending Steering Committee endorsement.
[1] There is no direct internationally comparable data as yet

## Section A: Detailed Output Scoring

Output 1: Strengthened delivery of health services, particularly responsive to the needs of women and children
Output 1 score and performance description: A / Major focus of the programme in its initial phase was to ensure that delivery of health services continued without interruption, particularly during transition from the humanitarian health facility based model to a streamlined county based service delivery model. Not only was this critical to meeting the health needs of the intended beneficiaries in South Sudan, it was also extremely important to HPF’s and DFID’s credibility in the eyes of the MOH and other donors. HPF achieved this effectively because the HPF Principal Implementer mobilized its team swiftly after being awarded the contract. They were able to quickly set up project policies and systems and carry out the contracting process (including detailed examination of proposed activities, negotiations and due diligence assessments). They issued bridging contracts timely to all NGOs under five humanitarian funding streams in all six states and successfully forestalled any lapse in service delivery. The NGOs could continue their work into 2013 under one HPF umbrella without any break in health service delivery. In the fragile South Sudan context, where project deliveries are generally constrained and slowed down by multiple factors, accomplishing this in little more than two months was apparently unprecedented and hence a major achievement for HPF in its start-up phase. / Long term contracts to NGOs are already in place in three states since July 2013 (round 1) and they are expected to be issued soon in the remaining three states also (round 2). This will ensure that service delivery will continue in a more effective and standardized way throughout the six states. For the second round, the contracting process was delayed and contracts have not yet issued.. Bridging contracts were extended as required to prevent gaps in delivery. / Continuity of service delivery have meant that the results achieved for this output as of the end of September 2013 fully met those expected, and in a few cases exceeded the milestones.
Progress against expected results: / The logframe was expected to be finalised at the end of inception phase. However the logframe available at the time of review is still missing[2]: / baseline, milestone and target for many indicators, and / impact weighting for outputs / This made the annual review very difficult in terms of objectively measuring the actual progress against expected results/milestones. However, assessment of progress against the outputs has been made to the extent possible by making some rational assumptions and utilising available information (e.g. for indicator OP 1.5 in this section). Assumptions made and information underlying the assumptions and assessment has been explained in each of the three output assessment sections. ACTION: Logframe for HPF to be completed with baselines, milestones, targets and impact weighting as required by February 2014. / There are five indicators under this output, and the first four of them have quantitative milestones set for December 2013. HPF’s M&E specialists confirmed that the indicators are designed to measure annual figures, which means that the milestones are annual targets for the year 2013. This review considered the progress until September 2013 only (three-fourth of the year). So the expected results were assumed to be 75% of the December 2013 milestones for the purpose of this review. For the fifth indicator there were no milestones set, only targets for March 2016 given. So assessment has been made based on an assumption mentioned in the table below. / Indicator Baseline (2012) Milestone (Sep 2013) Achievement (Sep 2013) Comment / OP 1.1 Under5 OPD consultations curative (disaggregated by gender), under 5 consultations preventive/promotive services and total under 5 consultations Curative consultation, under5 male = 300,913 / Curative consultation, under5 female = 299,323 / Preventive consultation, under5 male and female = 172,818 / Total consultation, under5 male and female = 773,054 Curative consultation, under5 male = 300,000 / Curative consultation, under5 female = 300,000 / Preventive consultation, under5 male and female = 225,000 / Total consultation, under5 male and female = 825,000 Curative consultation, under5 male = 303,541 / Curative consultation, under5 female = 299,462 / Preventive consultation, under5 male and female = 275,967 / Total consultation, under5 male and female = 878,950 Met milestones – exceeded well in two of the four indicators / OP 1.2 Number (%) of children aged 6-59 months given Vitamin A supplements in the last 6 months 53,000 (3.5%) 75,000 90,891 Met milestone well / OP 1.3 Percentage of women who attended at least four times for antenatal care during pregnancy 20,500 (8%) 25,500 38,100 Exceeded even the milestone for Dec 2013 (34,000). / It has been felt that the target and milestones were set too low. Utilisation of antenatal care being an important factor for increasing skilled attendance at delivery (critical to reduce the very high maternal mortality in South Sudan), this results need to be aimed on higher side. This early achievement also shows that higher results are possible. / ACTION: Targets and milestones to be revised by Feb 2014. / OP 1.4 Number of acceptors new to modern contraception 3,500 4,500 4,760 Met milestone / OP 1.5 Number of facilities with capacity to offer Emergency Obstetric care (disaggregate BEmONC and CEmONC[3]) Not mentioned in logframe. / EmONC Needs Assessment Report, being finalised now by MoH, will provide a baseline. Not mentioned in logframe. / However target for 2016 is 15 BEmONC and 5 CEmONC. / It is assumed that preparatory work to strengthen PHCC[4] for BEmONC and county (or equivalent) hospitals for CEmONC is a reasonable milestone for the initial phase of the programme to achieve the target. HPF has concluded assessment of 17 county (or equivalent) hospitals and 7 PHCCs for EmONC. / The findings have been reflected in Terms of Reference / Request For Proposals to support hospitals and PHCCs to start or strengthen these services / It was reported that the RFP[5] was going to be issued within 2013. / County Partners (NGOs) in three states carrying out their assessment to select PHCCs for BEmONC Lower level activities and achievements indicate adequate progress in this result. / The assessment has shown that CEmONC is available in a number of hospitals already, though the functionality varied. So the indicator description need to specify if the results expected here are additional number of facilities strengthened by HPF to offer the EmONC services. / ACTION: Indicator description to be refined and Milestones/ targets to be finalised within Feb 2014. / Clear definitions of indicators are essential to avoid multiple interpretations. Such definitions, among other aspects, were expected to be elaborated in an M&E plan during the inception phase. The M&E plan has not been finalised as of the time of this review[6]. ACTION: M&E plan for HPF to be finalised by February 2014. / In a number of health facilities visited as part of this review, it was observed that the quality of services varied. In some cases quality was questionable. Achieving increased service coverage is not sufficient to improve the health of the population. Delivering standard and quality service is crucial. ACTION: Quality of care to be made central to planning, delivery and monitoring of the health services. / Recommendations: / Review and revise targets and milestones for two specific indicators (OP 1.3 and 1.5) by December 2013 as mentioned in the table above (Responsibility: HPF Team Leader) / General recommendation applicable to overall monitoring: Finalise / the M&E strategy and plan (Responsibility: HPF TL and DFID Stats Adviser), and / the programme logframe for HPF by February 2014 (Responsibility: HPF TL and DFID Health Adviser) / Rapidly assess quality of service delivery in selected facilities and recommend strategy for improvement by March 2013 (Responsibility: HPF TL) / Impact Weighting (%): 70% / Revised since last Annual Review? N/A / This is the first Annual Review (AR). As mentioned above, Impact Weighting for the outputs had not been finalised at the time of this AR. On the basis that the first output (effective health service delivery) was the most important and most of the resources and efforts were channelled in achieving this, an impact weighting of 70% has been assigned to this output for this AR. However, as the programme progresses the impact weighting of the outputs will be different. As focus on health systems strengthening and community mobilisation grows, the relative impact of output 2 and 3 will grow. ACTION: The impact weighting of outputs for the second year of implementation to be determined while finalising the logframe (recommended to be done by February 2014) (Responsibility: DFID Health Adviser). / Risk: Medium / Revised since last Annual Review? N/A
[2] The logframe approved with the business case was expected to be completed at the end of the inception phase. However, due to a lack of sufficient baseline information, baselines, milestones and targets were not completed for some results indicators. This was partly affected also by the staff changes in both DFID (Health and Statistics Advisers) and HPF team (M&E Manager) in the months following the inception phase.
[3] Basic and Comprehensive Emergency Obstetric and Neonatal Care
[4] Primary Health Care Centre
[5] Request for Proposals
[6] M&E plan is one of the deliverables from the HPF Principal Implementer that have seen delays in recent months. The issue of delays in the deliverables, and the likely reasons, is discussed below under section 5.3 (Role of Project Partners).

Output 2: Communities have increased ownership, governance and demand for health services
Output 2 score and performance description: B / Communities are a vital part of any health system and health systems strengthening efforts cannot be successful without effective ownership and participation of the communities whose health outcomes are to be improved. Involvement and empowerment of communities to manage health service delivery locally and create demand for services is an important component of the HPF. However, in the initial stage under the bridging contracts, major focus was placed on ensuring that the health facilities continued their service delivery, and community mobilisation was not given a priority. The county model, however, is expected to deliver community component from the beginning. / In the first three states where the county model has begun, the NGOs (county partners) have included the community component in their assessments and work-plans. However, little progress was made in technical support from the central HPF team to the NGOs and CHDs on community mobilisation. It was reported that a contract had not been issued at the time of review to the HPF PI consortium member responsible for providing technical support on community mobilization. / The results achieved for this output as of September 2013 were mixed. The preparatory works where county partners were deployed were on track to implement community mobilisation, whereas the central technical support for this component progressed little. Though the bridging contracts had an element of community work, no significant progress was observed during the field visits.
Progress against expected results: / The logframe did not have baseline, milestone and target for indicators under this output. This made it very difficult to objectively measure actual progress against expected results/ milestones. However, as mentioned in the section above, assessment of progress against the outputs has been made to the extent possible by making some rational assumptions and utilising available information. These are explained for each indicator in the table below. / Indicator Baseline (2012) Milestone (Sep 2013) Achievement (Sep 2013) Comment / OP 2.1 Number of health facilities with systems in place for communities to feedback regarding health services Not mentioned in logframe. Not mentioned in logframe. / It is assumed that preparatory work to mobilize communities to engage in local health service delivery is a reasonable milestone in the first year. It was observed in field visit that health committees existed in some health facilities, though their functionality was not entirely clear. No other mechanism of community feedback was obvious. The county partners had begun to work with these committees. It’s too early to assess actual progress, however the lower level activities and achievement reasonably indicate that there is reasonable progress towards achieving on this result. / HPF will not have to start from scratch in terms of improving community engagement and governance in health services delivery. It has to be carefully assessed how county partners can build on existing structures and mechanisms to mobilise communities effectively. / OP 2.2 Number of established health committees at facility level with the ability in providing feedback to service provider Not mentioned in logframe. Not mentioned in logframe. / Assumption for milestone same as OP 2.1 As explained under OP 2.1 As explained under OP 2.1 / OP 2.3 Number of training sessions attended by health facility committees on related issues of governance and community participation , using the standard training package Not mentioned in logframe. Not mentioned in logframe. / Assumption for milestone same as OP 2.1 County partners have considered health facility management committees in their local assessments. It was reported that their action plan would include strengthening of the committees (training, on-site support) Lower level activities and achievement at county level indicate reasonable progress towards achieving this result for the counties. / However, little progress on the central technical support to counties mean that the capacity building activities (including training) for communities/ committees may not start soon. Community mobilization is very crucial activity in second year when county model is implemented in all six states. / ACTION: Central technical support for community intervention to be expedited by HPF. / OP 2.4 Number of Community Health Mobilisers trained and active in mobilising community participation and ensuring good governance of health services, using the standard training package (disaggregated by gender) Not mentioned in logframe. Not mentioned in logframe. / The preparation for this is not very clear. Unable to assess. There were questions raised on whether Community Health Mobilisers will be a new and parallel cadre in the health systems. There were suggestions to instead promote and strengthen existing and recognised cadre within the system (e.g. Home Health Promoters, Community Drug Distributors, and trained Traditional Birth Attendants). / ACTION: HPF to clarify on this and make necessary modification in the indicator if required while finalizing the logframe (as recommended above to be done by February 2014) / OP 2.5 Number and percentage of community board/health facility committee representatives at county level that are women Not mentioned in logframe. Not mentioned in logframe. / Assumption for milestone same as OP 2.1 It was observed in the field visit that many of the village health committee members were women, though it was not clear what proportion they were. Some of the women members actively participated in the discussion. As explained above, county partners had begun to engage these committees. As explained under OP 2.1 / Recommendations: / Initiate central technical support to the counties (CHDs and county partners) to strengthen community engagement and governance in local health service delivery by December 2013 (Responsibility: HPF TL) / Ascertain if Community Health Mobilisers are the right cadre to promote or an existing community based cadre should be strengthened. Revise the indicator (while finalising the logframe) if a different cadre is chosen. (Responsibility: HPF TL and DFID Health Adviser) / Impact Weighting (%): 10% / Revised since last Annual Review? N/A / As stated above, Impact Weighting for the outputs had not been finalised at the time of this AR. First year of the programme had minimal focus on community mobilization, so the minimum figure of 10% has been assigned to this output for this AR. Second year onwards, programme inputs to achieve this output will considerably increase and the relative impact weighting of output 2 will have to be adjusted. ACTION: The impact weighting of outputs for the second year of implementation to be determined while finalising the logframe (recommended to be done by February 2014) (Responsibility: DFID Health Adviser). / Risk: Medium / Revised since last Annual Review? N/A

Output 3: Strengthened health systems at State and County level with detailed focusing on / Policy / Human resources for Health / Health Financing including strengthening of payroll and LSS Framework / Health Information / Leadership and governance
Output 3 score and performance description: B / In the HPF design, health systems strengthening, including support to improve public financial management (PFM), was envisaged to follow phase one (continued and strengthened service delivery) depending upon the state revenue situation and government’s readiness and willingness to accept capacity building. The HPF, however, has begun engaging with the government at state and county levels from an early stage of the programme. Embedding of HPF and county partner staff at these levels has played an important role. We observed signs of HPF’s initial success in winning their trust, fostering their ownership and leadership of the programme and establishing effective partnerships. It is a gradual but crucial achievement. Though there has been progress, similar level of trust, leadership and partnership of the government was not evident at the national level. / Most of the results expected under this output are dependent on the county model being fully operational. However, the county model began in first three states from July 2013 and, due to delays in RFP process and steering committee endorsement, it was yet to begin in the other three at the time of this review. The results achieved for this output are short of meeting the milestones. The lower level activities, however, indicate reasonable progress towards achieving the results when the county model becomes fully operational.
Progress against expected results: / The logframe did not have baseline, milestone and target for indicators OP 3.3 to 3.5. This made it very difficult to objectively measure actual progress against expected results/ milestones. However, as mentioned a section above, assessment of progress against the outputs has been made to the extent possible by making some rational assumptions and utilising available information. These are explained for each indicator in the table below. For OP 3.1 and 3.2, expected result for September 2013 was taken as 75% of the December 2013 milestone (as per the logic applied for milestones of Output 1). / Indicator Baseline (2012) Milestone (Sep 2013) Achievement (Sep 2013) Comment / OP 3.1 Number of HPF Steering Committee meetings chaired by the Government of the Republic of South Sudan and number of State Oversight Committee meetings held 1 HPF Steering Committee (SC) meetings chaired by GRSS and 0 State Oversight Committee (SOC) meetings held 5 HPF SC meetings chaired by GRSS and 18 (3/annual X 6 States) SOC meetings held 4 SC meetings held until Sep 2013. One meant for September was deferred and held in late October. / ToRs for SOC have been finalised and quarterly meeting schedules started in all six states in the last quarter. Milestone met for national level SC meetings, but partly only for the SOCs. / SOC ToR and meeting schedules were in place and SOCs established in all six states by Sep 2013, However, the number of meetings have not happened as expected. / OP 3.2 Number of facilities with quarterly integrated supportive supervision visits conducted by county health department using the QSC tool 0 % 19% 6% (between Jan and Sep 2013). Milestone not met. / Support to CHDs is part of the county model, which was implemented from mid-July 2013 and in three of the six states only. It’s yet to be implemented in remaining three states. So the full effect of the support is yet to be seen. / OP 3.3 Number of health facilities submitting HMIS reports through the DHIS (according to the data flow policy) Not mentioned in logframe. Not mentioned in logframe. / The activities to achieve this result are part of county model, which was implemented partially only at the time of this review. So it is assumed that preparatory work to strengthen monitoring and information system is a reasonable milestone in the first year of implementation. In the six HPF states, 51% of total expected monthly HMIS reports were sent through DHIS between Jan and Sep 2013. / Health Systems Strengthening assessments done in all states. / HMIS reviewed and data for 2012 reconciled from fragmented reporting instruments / M&E tools being piloted / County partners engaging with CHDs in coaching health facilities to improve the reporting during supervisory visits. Lower level activities and achievements at both central and county levels indicate reasonable progress towards achieving this result. / OP 3.4 Proportion of counties with one joined plan, one budget and one review system for all government and NGO health services Not mentioned in logframe. Not mentioned in logframe. / For the reason mentioned in OP 3.3., it is assumed that preparatory work to engage CHDs and strengthen them to manage health service delivery of the whole county is a reasonable milestone in the first year of implementation. No data available on the counties with one plan, budget or review system. / HPF teams were engaged in last budgeting and planning processes at different levels. / County partners engagement with CHDs progressing. / CHDs found to be committed to manage the overall health service delivery and appreciative of the HPF. Lower level activities and achievements at both central and county levels indicate reasonable progress towards achieving this result. / OP 3.5 Number of counties achieving PFM milestones and benchmarks to target schedule as outlined in the framework Not mentioned in logframe. Not mentioned in logframe. / For the reason mentioned in OP 3.3., it is assumed that preparatory work to engage CHDs and state MoH to strengthen their capacity in improving PFM system at county level is a reasonable milestone in the first year of implementation. PFM benchmarks for Local Service Support (Health) developed and agreed with government / PFM baseline and mapping done / County partners trained on electronic payment system / Analysis for salary harmonisation done Lower level activities and achievements at particularly at the central level indicate reasonable progress towards achieving this result. / HPF is government-led and the largest primary health care programme in South Sudan. Its aim to deliver basic health care services comprehensively in six of the ten states through a strengthened health systems in a context where service delivery was extremely fragmented for years and health systems very fragile makes HPF an ambitious and complex programme. Hence, the significance of good relationship-building, partnership and influence with the national MoH, for HPF to deliver its outcomes successfully cannot be overstated. / Unlike with state and county levels, the engagement of HPF team with the national MoH, however, has been judged to be less than expected. A substantial amount of work during the inception phase and urgency to put in place service delivery contracts while ensuring an acceptable degree of due diligence, may have resulted in a trade-off limiting the engagement between the HPF and the MOH in the start-up stage. The expectation in the terms of reference, however, was that the HPF Secretariat would be based in the MoH, allowing HPF to routinely and effectively interact with MOH counterparts. The lack of a MOH-based secretariat diminished the engagement between the HPF and government counterparts during the start-up period, when crucial planning and procedures were being developed. Consequently, while the terms of reference include ensuring that HPF policies and procedures align, or shadow align, with government procedures wherever possible, actual HPF procedures are based on the internal procedures of the HFP Principal Implementer rather than on government’s. There have been efforts made to embed some staff in the MoH lately, but without much success. The potential outcome of less engagement between the HPF and MOH than was expected is diminished government ownership and HPF alignment. This can lead to strategic failure to achieve the ambitious results - ‘Government-led health systems that save lives’. / ACTION: Proactive and rigorous efforts to be made to establish closer working relationships and effective engagement with the national MoH. / Recommendations: / Consider embedding HPF secretariat and experts in relevant MoH office(s) by March 2014 (Responsibility: HPF TL and DFID Health Adviser). / Impact Weighting (%): 20% / Revised since last Annual Review? N/A / As discussed in above sections, Impact Weighting for the outputs had not been finalised at the time of this AR. First year of the programme had some focus on health systems strengthening and partnership building. So a figure of 20% is has been assigned to this output for this AR. Second year onwards, the focus on this output will considerably increase to achieve the impact of a ‘Government-led health services that save lives’ and the relative impact weighting of output 3 will have to be adjusted accordingly. ACTION: The impact weighting of outputs for the second year of implementation to be determined while finalising the logframe (recommended to be done by February 2014) (Responsibility: DFID Health Adviser). / Risk: Medium / Revised since last Annual Review? N/A

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N/A / This is the first annual review. The logframe has been revised since the business case approval, with refined results descriptions and indicators. The revised logframe was submitted by HPF Principal Implementer with the inception report. However it was still incomplete with missing / baseline, milestone and target for many indicators, and / impact weighting for outputs. / For the purpose of this review, milestones have been set based on some rational assumptions and available information, and assessment of actual achievement has been made against them. Similarly impact weightings for outputs have been assigned for the first year of implementation. ACTION: The logframe to be completed with all missing elements by February 2014. / 1.2 Overall Output Score and Description: A / The overall score A shows that the outputs of this programme meet the expectations. Though the score for outputs 2 and 3 is B (outputs moderately did not meet expectation), relatively higher impact weighting of output 1, scored at A, resulted in an overall output score of A (this is automatically calculated in ARIES). / 1.3 Direct feedback from beneficiaries / No formal assessment or research has been done to collect beneficiary feedback. Direct interaction with beneficiaries (health care users and village health committee members) met in the visited health facilities revealed that they have high expectations from the HPF. The beneficiaries welcomed HPF’s support and had aspirations that all needs of their health facilities would be met by this support. Their expectations were mostly around better infrastructure, including water and sanitation facilities, increased availability of drugs and in some cases more health workers. / High expectation from HPF was evident amongst intermediate beneficiaries (health workers, and officials of CHDs and state MoH). In some states, there was general expectation, apparently reinforced by senior government officials, that HPF was going to provide for all requirements and fill all gaps in health service delivery throughout the state. HPF resources are limited and the programme is not designed to cover the costs of health services comprehensively throughout the state. The needs of health facilities are varied, not just across, but within the states and counties too. We observed a fully staffed facility that had very poor infrastructure and another had good infrastructure but lacked critical skills. ACTION: It has to be explained and advocated to CHDs and state MoH that the resources have to be intelligently used and support tailored to ensure all health facilities are able to deliver quality services at similar standards. The over-expectation has to be managed also through continuous dialogue with the beneficiaries at different levels. / Beneficiary assessment is an important feature of understanding the impact of a service delivery programme. A formal beneficiary assessment needs to be undertaken in the next annual review.
1.4 Summary of overall progress / Continuity of service delivery was crucial in the transition to this programme and it has been accomplished very effectively. Service delivery related outputs have met expectations well, in some cases even exceeded. Health systems strengthening interventions began earlier than expected and engagement at state and county levels progressed well. However the implementation of the county model was delayed and the engagement at national level to ensure MoH’s leadership in HPF delivery has fallen short of expectations. Despite slower progress in central HPF teams’ preparation to provide technical assistance for community mobilisation work, county partners have begun engaging with community structures already and have considered community strengthening in their initial assessment and planning. The programme overall has been scored at A (meeting the expectation) and is on track to achieve the expected results.
1.5 Key challenges / Human Resources for Health: There is a shortage of skilled health workers in most health facilities. Some facilities were found to have a high number of unskilled or non-essential staff while crucial skills (such as trained midwives) were missing. Salary differences between NGO and government paid health workers have been an issue, and the salary harmonisation directives have not been helpful. It is understood that there is general shortage of qualified health workers in the job market and while programmes such as HPF build capacity of health workers in-service only, there have been little donor and government investment in training new health workers. / Pharmaceuticals: There is an imminent shortage of essential medicines in many health facilities and the stocks at county stores are running out quickly. HFP is largely reliant, by design, on drugs from central MoH supply, although there is contingent provision to procure drugs. The MoH quarterly supply has not been provided since Jan 2013. MoH is yet to receive their full shipment of drugs. It is discussed in detail in the risk section below. / Infrastructure: In some health facilities infrastructure is very poor. We observed a well-functioning facility, which had full staff and high service utilisation rates, but services are provided literally in shanty huts without proper walls. The lack of decent workspace adversely affected staff morale as much as it did with maintaining of privacy for clients. Proper water and sanitation facilities were either absent or in poor shape in some of the facilities visited. / Quality of care: The challenges above affect the service quality ultimately. Inadequate attention to seemingly small management aspects, such as maintaining general cleanliness and hygiene, have contributed to poor quality. Poor quality service can have a detrimental effect on beneficiaries and can undermine HFP’s effort to increase demand for and utilisation of services. / Adapting to change: The county model is an innovation in South Sudan. This puts the local government department (CHD) in the leadership and county partners in a facilitation and supporting role. The model also allows for flexibility to provide needs-based tailored support so that facilities across a county deliver to the same standard. This is yet to be understood well, though there is some progress. Lack of understanding can lead to over-expectation from government and beneficiaries, creating pressure on HPF county partners to allocate resources irrationally.
1.6 Annual Outcome Assessment / Outcome: / Increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. / Indicator Baseline Milestone (Sep 2013)* Achievement (Sep 2013) Comment / OC 1 Percentage of 1-year olds vaccinated with the third dose of DPT vaccine (2012) / 18,000 (11%) 36,080 38,408 Achieved / OC 2 Proportion of children under 5 with fever in the last two weeks who were taken to a health facility (2011) / 15.3% Not mentioned in logframe / Target for 2016 is 30% Data expected to be available from LQAS planned for Nov/Dec 2013 This indicator aims to measure health care utilisation at health facilities. Programmes, such as Integrated Community Case Management (also funded by DFID), increase the availability of treatment for under5 children at home. Such programmes can affect the progress expected in this result (though not necessarily a negative effect). This has to be considered while interpreting the achievement on this result. / OC 3 Contraceptive Prevalence Rate (2011) / 6.5% Not mentioned in logframe / Target for 2016 is 14% Data expected to be available from LQAS planned for Nov/Dec 2013 / OC 4 Percentage of births attended by skilled health personnel (2012) / 7,311 (2.8%) 7,833 9,907 Achieved / * Expected result for September 2013 was taken as 75% of the December 2013 milestone (as per the logic applied to for milestones of Output 1 above). / Two of the four outcome indicators show that the expected results have been achieved. On the other two, data was not available at the time of this AR. These data will come from a survey (LQAS) planned to be conducted in Nov/Dec 2013. / First four of the Output 1 indicators also reflect that service coverage is increasing and on track to meet the expected milestones. Output indicator OP 1.4 particularly shows that new acceptors of modern contraception are increasing as expected. This will certainly contribute to increase in contraceptive prevalence rate (indicator OC 3) also. / The theory of change showed that strengthened service delivery, health systems strengthening and community mobilisation are expected to lead to increased access and utilisation of quality health services. The assumptions and evidences used in the theory of change still remain valid. The assessment as a whole reflects that expected results at outcome level are on track to be achieved. / With the transition to county based service delivery models completed in all six states and programme entering into the main implementation stage, the HPF, in its second year, needs to carefully rebalance its focus on all three phases (as envisioned in the BC). In order not to jeopardise the gains made in service delivery, and at the same time to ensure that health services are increasingly owned and led by the government and communities, HPF should: / Continue supporting service delivery, with increasing emphasis on quality; / Intensify its interventions to increase engagement and strengthen the health systems at all levels – national, state, county and local; and / Engage the communities in local health service delivery without further delay

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / The costs incurred to date have not met the level of forecast with current expenditure showing a substantial underspend to the forecast. / The reasons for the underspend are: / Slow flow of NGO invoices and financial reports for many bridging and long term contracts– In many cases this was because NGOs took time to understand financial requirements. / Delay in issuing of the long-term contracts to the NGOs and the slow approval by HPF team of the procurement plans meant that spending on goods and equipment has been affected. / Delay in contracting NGOs for the remaining 3 states (although existing contracts were extended) – This delay was due to the management consultants disqualifying bids for two lots which caused postponement of the steering committee meeting. A further SC meeting was convened but cancelled due to lack of MoH availability further delaying the process. / Extension of the programme inception phase by 2 months, with no additional management costs for this extension. / Slow response from the HPF team to move advance funding of NGOs, despite their request and DFID’s clearance. / An improvement in flow of invoicing has been seen in recent months. HPF team are engaging with finance teams of NGOs to improve the financial reporting. With the county model fully functional, the expenditure level is likely to improve. / ACTION: / Engagement with and support to NGOs to improve financial reporting to be continued / Procurement by NGOs to be facilitated and expedited / Procedures to be put in place for advance funding to NGOs by December 2013 / 2.2 Key cost drivers / Key cost drivers remain unchanged. They are: / Number, type, location and functional status of health facilities: / Salaries for health worker / Drugs / It was not very possible under bridging contracts to try innovations in managing the cost-drivers to utilise resources more efficiently because NGOs worked in fixed health facilities with given number of staff and other inputs. The county model is designed to support comprehensive service delivery in the county. This doesn’t mean that all health facilities should be supported using a blanket approach. It allows for tailored and targeted support to each facility, of course under the leadership of CHD. This provides the opportunity to make savings on one cost-driver and allow flexibility to support the other that requires higher inputs. However, we observed in the field visits in three counties where the county model had begun that not all county partners had thought through this well in their initial assessments. This is crucial for the projects’ success and to achieve the best results within the limited resource envelope and also to ensure maximum value for money. ACTION: All county partners to be oriented well to work with CHDs and come up with a tailored action plan to support health facilities. / 2.3 Is the project on-track against original timescale: Y (but with slight delay) / HPF has been on track largely in terms of continuation of health service delivery, the major focus in the initial phase. In the first stage of inception phase, bridging contracts were put in place quickly that helped forestall any lapse in service delivery. This was a major success, particularly in the context of South Sudan. / The programme has delivered many of the key milestones timely, but not all. The process of contracting NGOs for long term contract to implement county model ran behind schedule for three states of the six states. In the first three states (Eastern Equatoria, Western Bahr el Ghazal and Unity) the contracts were in place in July 2103, whereas in other three states (Northern Bahr el Ghazal, Lakes and Warrap) the contracts were yet to be signed (Steering Committee approved the second round RFP results in late October and contracts were going to be issued in December 2013). The delay was due to internal issues (complications and inefficiency resulting from a lack of clear division of role between the HPF Principal Implementer and their headquarters) as well as external (delay in securing Steering Committee meeting for approval, which could be improved with closer working with the MoH). Service delivery was continued through short-term extension of bridging contracts; however there was some frustration on the NGO side due to difficulty in retaining key staff and health workers for such short extensions. The inception report was submitted in June 2013, however some of the programme management plans guidelines and strategies, which were part of the inception phase deliverables, had not been delivered in its final form at the time of this review. Absence of finalised logframe and an M&E plan, disused above, are examples of the delayed deliverables. / ACTION: Capacity of in-country HPF team to be strengthened and more authority for programme decisions to be delegated to in-country HPF leadership.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The theory of change showed that strengthened service delivery, health systems strengthening and community mobilization are expected to lead to increased access and utilisation of quality health services. A light-touch review of the assumptions and evidences used in the theory of change showed that they still remain valid. The evidences have to be re-examined in more depth during the mid-term review of the programme, which will be carried out by evaluation service provider (see below). / 3.2 Where an evaluation is planned what progress has been made? / An independent evaluation component is planned for HPF. ToRs have been drafted and were reviewed by an external quality assuror (commissioned by London) and peers within DFID. The plan is to run a mini-competition, among technical agencies within the Evaluation framework agreement, in January 2014. The evaluation service provider will validate baseline information and monitoring data, and will conduct evaluations, including but not limited to mid-term review and final evaluation. They are also expected to provide inputs to future annual reviews. / It is recommended that the next Annual Review be undertaken in April 2014 to align with the project end date, April 2016.

4. Risk
4.1 Output Risk Rating: Medium / The business case described the programme as overall medium to high risk, attributable to factors outside of the HPF control such as security, pharmaceuticals, human resources for health and GRSS support. The logframe showed all outputs at Medium risk. / 4.2 Assessment of the risk level / The overall risk level remains the same at Medium. Risk mitigation measures have been applied by HPF as envisaged in the business case. Some examples of good practice are: / Fiduciary Risk Management Strategy was prepared / Due diligence of NGOs conducted even for the bridging contracts / Security situation in field operation and safety and security of staff has been incorporated as a regular agenda in the Steering Committee / The review observed one particular case of potential reputational risk for the HPF related to imminent shortages of drugs in many health facilities throughout the country. / The HPF is not a self-sufficient programme to deliver all primary health care services in its entirety throughout the six states. It is dependent on external inputs and resources, for example on quarterly supply of drugs from central MoH, for service delivery. Resources are allocated to county partners to manage drugs to prevent shortages and crisis; however they are not sufficient to cover round the year supply. Central MoH has not been able to send quarterly drugs supply for nearly 10 months now (the last supply was in Jan 2013) and health facilities, CHDs and SMoH reported imminent drug shortages in many primary care facilities. It was apparent that central supply was less likely to be available before the end of this year. Though central pharmaceutical supply is external to and beyond direct control of HPF and shortage affects not just HPF intervention areas but throughout, disruption of services due to lack of drugs is a reputational risk to HPF and DFID. So the HPF team should be vigilant and act timely to prevent such disruptions e.g. by engaging effectively with the MoH to push and facilitate timely supply; allowing and supporting NGOs to use contingent funds to efficiently procure and distribute drugs; using contingency funds to facilitate quick distribution of drugs from central stores to health facilities. ACTION: Proactive engagement with MoH and other partners to tackle this potential crisis to be intensified; Procurement strategy for subcontracted NGOs to efficiently procure drugs and equipment to be out in place by February 2014.
Risk of funds not being used as intended / The review didn’t find any such risk. The HPF Principal Implementer has a solid Anti-Corruption Strategy. They have also developed a Fiduciary Risk Management strategy and put in place rigorous financial and contract management measures to monitor and prevent any potential fraud or unintended use of UK funds channelled through sub-contracted NGOs. Their strategy also covers measures to strengthen public financial management systems in order to prepare for future channelling of funds through government mechanisms (longer-term aim of the programme). The HPF have also scrutinised NGOs procurement plan thoroughly. / Spend has been slower than expected, particularly in the inception phase (discussed above also). However in the main implementation phase this is likely to improve as county partners operate fully in all states and hospital component is also operational. / 4.4 Climate and Environment Risk / The review didn’t find any change in the risk assessment from what has been described in the business case. The likely environmental risks are related to the potential contamination of water supply source at or near health facilities with human and health care waste (Medium). Safe water and sanitation, and proper medical waste disposal were not optimal in some of the facilities we observed. / The programme is not intended to comprehensively cover water and sanitation issues in all facilities, but it does provide opportunities to ensure through county model that standards are put in place and practised to mitigate such risks (e.g. preparing standards for water and sanitation in new constructions). In some places the programme may also be able to support minor refurbishments that helps mitigate the risk. Observation and advice for safe water and sanitation in and around health facilities should be part of supportive supervision. Community mobilization can also include behaviour change communication on these issues. ACTION: Practical solutions to improve water and sanitation infrastructure and practices in health facilities to be considered in the package of county support

5. Value for Money
5.1 Performance on VfM measures / As given in the business case, HPF represents high value for money and is expected to cost between $244 and $255 per Disability Adjusted Life Years (DALY) averted, which is very cost effective as per WHO definitions. Measures to assess VfM identified in the business case are: / Direct costs per beneficiary / Indirect costs per beneficiary / Capital costs per beneficiary / Actual services delivered / Government health system capacity built / This annual review did not analyse the first three measures as it was deemed too early in the programme to do so meaningfully. Assessment of these measures will have to be done in the next annual review when beneficiary and costs data from the main implementation phase will be available. / It is notable that procurement was carried out in line with the principles of VfM and savings made in the bridging contracts (described below under commercial section). Assessment of service delivery outputs and outcomes (discussed in sections above) has clearly shown that the programme is performing to the expectation. Similarly there has been some progress on health systems strengthening starting from the inception phase itself Examples: Health Systems Strengthening assessment is complete in all six states; Training conducted on electronic payment system for county partners; PFM benchmarks established; HMIS reviewed and data reconciled; M&E tools piloted; etc. It was evident from the interactions during field visits that there is considerable buy-in, leadership and engagement of CHD and State MoH with regards to HPF. This is an achievement in the right direction. These examples reflect that programme is delivering effectively, though there remain areas to be improved. No apparent triggers to suspect that the programme was not delivering VfM have been identified. However, this has to be assessed in more details during the next annual review. / Apart from formal assessment of VfM against identified measures given above, VfM can be assessed through examples or case studies reflecting how better effectiveness, efficiency, economy and/or equity was delivered by an intervention or innovation and this can be included in regular monitoring and reporting. ACTION: HPF to include VfM examples possibly in quarterly reporting. / 5.2 Commercial Improvement and Value for Money / HPF team successfully carried out procurement in line with the principles of VfM and were able to negotiate with service providers, both for bridging and county contracts and made savings. For example: the estimated funding envelope for bridging contracts, based on costs from previous funding mechanisms and adjusted for inflation, was set as £9.9 million and the value of initially submitted budgets was £12.4 million. Following review and negotiations the contracts were issued at an overall value of £8.1 million. / HPF also applied innovation by issuing Request for Information and Expression of Interest from NGOs prior to the bid to understand the supply market and competitiveness. This was also targeted at identifying national NGOs who were interested but lacked capacity to compete with international NGOs. Investment in national NGOs is instrumental in building long term capacity in the country and hence sustainability of programme results. HPF’s efforts have resulted in two national NGOs being awarded the county contract. HPF is following up on their capacity building through a subsequent capacity assessment and an action plan. HPF’s work on national NGOs is a remarkable innovation. This is expected to strengthen the competitive edge of national organisations also in the commercial market. / 5.3 Role of project partners / The programme is designed to be led by the GRSS. The national MoH chairs the Steering Committee, which has endorsed major programme deliverables. Similarly the state MoH chairs the State Oversight Committees to ensure effective and consistent programme delivery in the state. The County Health Departments lead and manage overall service delivery in counties. There has been encouraging response from the government authorities at different levels. The HPF is recognised well by them to be a major primary health care programme contributing to achieve the government’s five-year health strategy. / The UK, the trustee and the lead donor for the HPF, represents as a co-chair in the HPF Steering Committee, manages the Principal Implementer and oversees the programme delivery on behalf of all HPF donors. In the first year, Canada have represented other donors (Australia, Canada and Sweden) as a member in the Committee. Australia and Sweden have also occasionally participated as observers in the Committee. Donors have monitored the programmes through meetings with key stakeholders and joint field visits. A team representing Australia, Canada and the UK recently made a joint visit to Western Bahr el Ghazal, the findings from which have been incorporated in this review. The European Union joined the HPF very recently. / The project implementer is a consortium led by Crown Agents. In this annual review report, they have been called HPF Principal Implementer, as opposed to Fund Manager used in the business case, to emphasise their overall role, which is more than just fund management. In the fund management role they award contracts to NGOs and manage them. They also have a key role to provide technical support to the government at different levels and NGO partners. / Overall the HPF team have performed satisfactorily in its first year, meeting some crucial deadlines for a hugely ambitious project in a fragile context. They achieved an early feat by awarding bridging contracts to 16 NGOs under five different funding streams with two different end dates and bringing them under one HPF umbrella within little more than two months. This prevented interruption in service delivery during a complex transition. / For the long term contract, they developed a high quality RFP document in consultation with major stakeholders and launched the first round of contracts, managing selection by working with government at national and state level. The RFP process included launching a unique but apparently successful “Request for Information” to identify and analyse potential gaps in service providers, the availability of services across the HPF-supported states, and establishing baseline data. Although health system strengthening was not considered a phase-one priority and capacity building at the central and decentralised levels was not expected to begin early in the programme, an HSS assessment was conducted in three of the six HPF-supported states and the findings of the HSS assessment report were subsequently incorporated in the RFP scope of work. Although unexpected, this was a thoughtful decision by HPF team, which understood that NGOs should be provided guidance related to addressing HSS priorities in the long-term contracting RFP process in order for support to be consistently measureable and responsive to identified needs. The RFP and contracting process overall was, however, delayed, among other reasons, due to slow quality assurance processes from the headquarters of HPF PI that were not well enough informed by the field. Managing the process required a lot of input from DFID. / The work of the HPF PI with State MoH and county health departments has been a success. The HPF team have managed to develop strong relationships with most states and counties and have engaged them in all major processes of establishing and delivering HPF. HPF team have also engaged in the governments’ planning and budgeting processes. HPF work-plan has been aligned to government’s HSDP which is an encouraging step forward. / They have also managed to develop strong relationships with NGOs and have really stepped up engagement and dialogue between NGOs and State officials, as well as between National and international NGOs. HPF team have been a pioneer in their work on National NGOs, assessing their challenges and planning to build their capacity. This is expected to go a long way in building local capacity. The team has regular communication with other major primary health care programme implementers. They participate in different committees and forums engaging with broad range of stakeholders. / The HPF State Co-ordinators, embedded within SMoH, have been a huge success. They are well regarded by NGOs and SMOH alike. Likewise, county partners have been well integrated into CHDs in most counties unlike HPF team at the national level. At the national level, the HPF team have engaged on specific technical areas well; however the level of trust and partnership for the overall HPF management and delivery needs to be strengthened (also discussed under Outcome assessment section above). / It has predictably taken a bit of time for the programme to settle but now the HPF team have a better complement of staff to deliver it. There was a delay in recruiting a Team Leader; however, once on-board the HPF team leadership has been very effective, improving the ways how the programme was being managed. The team has had a very close relationship with DFID. Communication has been good and very regular. The two have worked closely together to ensure successful delivery of the project. / Key challenges / The inception phase was prolonged by two months and the RFP process and long term contracting took longer than expected. As discussed above, the delay was partly due to capacity, but also due to decisions made by the Principal Implementer’s headquarters team members not well informed about the practical realities of operating in South Sudan. There were shortcomings in the first round of request for proposals (RFP) for long term contracts. This was brought to DFID’s notice at a very late stage but resolved through DFID’s input. In the second round of RFP, there were flaws in the procurement process that resulted in a last minute postponement of the steering committee. Again this was eventually resolved by DFID intervention in advising that a retender was required. The needs and challenges of working with government and NGOs with low capacity and in a fragile context have not been considered well by the key decision makers. Leadership from the headquarters has not been consistent. HPF’s in-country team, who understand the local context well to effectively steer the programme management, have not been kept in the forefront of key programme management decisions. If not addressed, this is likely to complicate and slow down programme delivery. / HPF PI have relied heavily on short term consultants to develop main guidelines and deliverables, and this in many instances posed a challenge in ensuring that all the documents spoke to the same ambitions and not to individual objectives. This probably has also contributed to delays. For example, all five compendiums of Inception Report finalised in June 2013 had not been submitted until the time of this review. Some of their strategies did not align with the expectation of the HPF. For example, their fiduciary risk management strategy focused too much on due diligence of NGOs and not on overall fiduciary risk of the programme. / The roles of consortium members have not been always clear. Delays in issuing contracts to consortium members have affected key areas of work, including on community and PFM components. Managing too many short-term inputs from consortium members in coherence with the overall programme delivery has been seen as a challenge at times. / 5.4 Does the project still represent Value for Money : Y / HPF has achieved, and occasionally exceeded, the expected service delivery results as outlined in the logframe. Service delivery has continued uninterrupted despite complex transition and health service coverage is increasing as expected. Work on health systems strengthening and community engagement, which has begun from the inception phase, has to be a key focus from the second year. Underlying assumptions and evidences in the theory of change, the risk, costs and VfM attributes of the programme remain largely unchanged from the appraisal made in the business case. There have not been any apparent triggers to suggest that the programme doesn’t or is failing to represent VfM. / 5.5 If not, what action will you take? / Not applicable.

6. Conditionality
6.1 Update on specific conditions / Not applicable - This is not a financial aid.

7. Conclusions and actions
The HPF is government-led and the largest primary health care programme in South Sudan. It is an ambitious and complex programme in a fragile environment. The review has found that in general the high expectations for the early start-up period were successfully met. The HPF has been successful thus far in many of its innovations, such as the introduction of a consistent scope of work in NGO RPFs, improved coordination with other donor programmes, and development of the County Model approach that includes some standardized health system strengthening activities. Even in complex transition, service delivery continued uninterrupted and expected results have been met. The programme represents good value for money. The risk context and operating environment largely remain unchanged since the start of the programme. Challenges remain in ensuring the right mix of skills in right numbers, optimal infrastructure and sufficient supplies to improve the access to and quality of health services. The programme aligned well with government’s five year strategy and has increasingly strengthened partnership with government and other key health sector actors. Acceptance and integration of the programme at state and county levels has been successful in most cases. More effort needs to be made to build effective relationships and integrate better with the health authorities at national level and increasing their leadership at all levels of HPF delivery. Principal Implementer needs to consider rationalising programme management roles to improve efficiency and ensure effective government leadership in programme delivery. / In order not to jeopardize the gains made in service delivery, and at the same time to ensure that health services are increasingly owned and led by the government and communities, HPF should rebalance its focus to: / Continue supporting service delivery, with increasing emphasis on quality; / Intensify its interventions to increase engagement and strengthen the health systems at all levels – national, state, county and local; and / Engage the communities in local health service delivery without further delay / Recommended actions identified in different sections above have been listed here. Details on timeline and responsibility are given in relevant sections above. / Improve the engagement and partnership with the national MoH and consider embedding HPF secretariat and experts in relevant MoH office(s) / Orient county partners well, assist CHDs in preparing a tailored action plan to support health facilities and manage expectations through continuous dialogue with the beneficiaries at different levels / Include practical solutions to improve water and sanitation infrastructure and practices in health facilities in county work plans / Rapidly assess quality of service delivery in selected facilities with a view to inform a strategy to improve quality of health services. Consider quality improvement in action plan / Expedite central technical support to the counties (CHDs and county partners) to strengthen community engagement and governance in local health service delivery / Proactively engage with MoH and other partners to tackle the potential drug shortages in counties / Continue engaging with and support NGOs to improve financial reporting / Expedite NGO’s current procurement plans and prepare procurement strategy efficiently procure drugs and equipment for counties in future / Establish procedures for advance funding to NGOs / Consider HPF investment in some new areas: / in training new health workers / in water and sanitation and health infrastructure / Shift major HPF programme management decision-making more from Programme Implementer’s headquarters to in-county leadership / Increase the capacity of in-country HPF team rationalising long-term versus short-term inputs / Finalise HPF M&E plan and logframe taking into considerations suggestions made in this review report / Include VfM examples in quarterly HPF reporting

8. Review Process
Main implementation phase of HPF began from mid-July in only three of the six states and was yet to be started in the other three at the time of this review (October 2013). Hence it was decided by the Essential Services Team that this review will be light touch and conducted in-house. The second annual review will be carried out, in April 2014 (review dates adjusted to fit in with project end date) supported by an Evaluation service provider, with full rigour, particularly around assessing VfM, evidence and beneficiary feedback. / This review was led by the new DFID Health Adviser, who joined DFID South Sudan in September 2013. The review helped the Adviser to quickly immerse in the flagship health programme of the office and also provided an opportunity to assess the progress with a fresh pair of eyes and a certain degree of independence. The HPF Programme Manager and a Programme Officer from the team supported the programme observation in the field and interactions with some key project stakeholders. The Health Adviser, who led on the programme from the late design phase to its implementation until August 2013, provided specific and detailed inputs on programme performance based on her own experience. An external consultant, who had been providing intermittent support to HPF from the design stage, contributed through an analysis of the programme’s progress in the inception phase. The Essential Services Team Leader quality assured the report. / The review involved a desk review of relevant documents, including background programme documents, project reports and deliverables. A series of meetings and interactions, mostly informal, were conducted with key stakeholders individually and in groups. The stakeholders included MoH, State MoH and CHD officials, donor partners, HPF central and state team members, NGO partners at central as well as county levels, health workers, and not the least, beneficiaries. The review also drew on discussions and views gathered in several health sector meetings, workshops or events. Two field visits were made covering three counties in two states, where the county model had been operational since July 2013. The field visit provided an excellent opportunity to observe and interact with key stakeholders and helped understand first-hand the status of facilities and service delivery, achievements and challenges on the ground.