Revised and approved March 2015
PPP Support Facility Revised Logframe

PROJECT NAME	PPP Support Facility
IMPACT		Impact Indicator 1				Baseline (2012)			Milestone 1 (End 2013)			Target (year mid-2015)					Assumptions
Increased private sector investment in infrastructure leading to improved infrastructure and access to infrastructure services		Volume of FDI investment in social sectors (health, education, waste water treatment, social work)		Planned		USD 246m			USD 269			Increased data of 2014
				Achieved
						Source
						FDI sections, GSO Annual Statistics Book
OUTCOME		Outcome Indicator 1			Baseline (2013)			Milestone 1 (End 2014)			Target (mid-2015)					Assumptions
Effective Enabling Environment for PPP established in Viet Nam, including Improved Institutional and Legal Frameworks		Improved PPP legal and institutional framework	Planned		Weak legal and institutional framework in place.[1]			Review and development of other PPP related laws and regulations undertaken, including the Investor Selection Decree / Development of PPP Guidelines and standardised procurement documentation			Government adoption of PPP Guidance and PPP Decree.					Strong support of relevant government agencies, particularly at the highest level / Effective support from DFID in terms of mobilizing international PPP expertise / Co-ordination among relevant PPP stakeholders in Viet Nam / PPP Office is able to approve draft guidance in a timely manner / Risks / Lengthy consensus building among Government agencies / Lack of political support for the PPP agenda / Lack of interest from the private sector / Non-compliance to the new legal and institutional framework produced. / On-going project bottlenecks, or delays to establishing the PDF, that will impact on the ability to bring at least one PPP deal to market by EoP.
			Achieved
					Source
					Government’s and donors’ reports, Project Progress Reports
		Outcome Indicator 2			Baseline (2013)			Milestone 1 (End 2014)			Target (mid-2015)
		More PPP deals screened and pre-feasibility studies completed	Planned		None			One			Three
			Achieved
					Source
					Government Reports, Project Progress Reports, Annual Review
		Outcome Indicator 3			Baseline (2013)			Milestone 1 (End 2014)			Target (mid-2015)
		Improved PPP intra-governmental co-ordination and / understanding of the PPP institutional and legal framework	Planned		Weak public sector PPP related co-ordination, knowledge and capacities			Capacities of relevant PPP staff strengthened and private sector PPP awareness raising activities undertaken			Capacity of PPP staff strengthened, Responsive and functioning Central Government PPP Unit and two others (ASA / Provincial)
			Achieved
					Source
					Progress Reports, Post-training Questionnaires, Project Case Studies, GoV / MPI Reports, Annual Review, training feedback and light touch interview of government beneficiaries.
INPUTS (£)		DFID (£)			Govt (£)			Other (£)			Total (£)					DFID SHARE (%)
			£1.2 million					100
INPUTS (HR)		DFID (FTEs)
			40% of PO & 20% of SPO

OUTPUT 1		Output Indicator 1.1			Baseline (2013)			Milestone 1 (End 2014)			Target (mid-2015)				Assumption
Support to the Government in PPP policy, legal and institutional frameworks		High quality and timely analysis and advice pieces provided to the MPI on the PPP legal and institutional framework	Planned		One-off work shop by UK embassy and UKTI, ADB PPP PDF legal and institutional framework preparatory work.			At least two specific recommendations adopted by MPI officials related to PPP, including PPP Guidance document			At least three recommendations adopted of at least one standardised bidding document for PPP projects by MPI officials				Strong engagement of relevant government agencies. / Availability and timely recruitment of competent consultants / Timely and responsive communications between relevant stakeholders and consultants / Demand for services across government throughout project cycle. / Vested interests do not impact on the adoption of recommendations. / Governmental and private sector interest and buy-in of the communications strategy / Risks / Intra-government agencies promote their own interests, stall progress or choose to by-pass improved legislative or institutional framework. / Competing mandates between DFID and other donor led work in this area / Consultants fail to integrate with Government officials and address correctly their needs
			Achieved
			Source
			Project Progress Reports, GoV Reports, Project Case Studies, independent assessments
		Output Indicator 1.2			Baseline (2013)		Milestone 1 (End 2014)			Target (mid 2015)
		High quality demand responsive PPP support to other Ministries (Central or Provincial) or ASAs.	Planned		One-off work shop by UK embassy and UKTI, ADB PPP PDF preparatory work		At least two specific project recommendations adopted by other ministries or provinces judged as high quality through independent feedback			At least three project recommendations accepted and at least one adopted PPP recommendation by Government officials.
			Achieved
			Source
			Project Progress Reports, Project Case Studies, independent assessments
IMPACT WEIGHTING (%)		Output Indicator 1.3			Baseline (2013)		Milestone 1 (End 2014)			Target (mid-2015)
50%		Communications activities undertaken to ensure buy-in from key stakeholders including the private sector	Planned		No clear communication strategy in place		MPI Communications Strategy drafted and disseminated, with at least four communications activities having taken place including at least one with the private sector			The Comms Plan implemented. Handover of PPP Viet Nam related knowledge to GoV.
			Achieved
			Source					RISK RATING
			Project Progress Reports, Communications Strategy, GoV / MPI Reports					High
INPUTS (£)		DFID (£)			Govt (£)		Other (£)				Total (£)					DFID SHARE (%)
			1100000					100
INPUTS (HR)		DFID (FTEs)

OUTPUT 2		Output Indicator 2.1			Baseline (2013)		Milestone 1 (End 2014)			Target (mid-2015)				Assumptions
Support to the Government in PPP project identification and screening, including social sectors		Additional pilot PPP projects identified and screened at pre-feasibility stage including social sectors	Planned		0		At least two additional pilot projects are identified and viability / pre-feasibility study completed			At least four pilot projects are screen for pre-feasibility (for inclusion on the PPP project list), including one social sector[1]				Committed and active participation of relevant stakeholders / Sector Master Plans are up to date and consistent with international best practice / Risk / Delays in consultants recruitment / Incomplete project data or other information / Lack of agreement among agencies on criteria for PPP projects
			Achieved
			Source
			Project Progress Reports, independent assessments
IMPACT WEIGHTING (%)		Output Indicator 2.2			Baseline (2013)		Milestone 1 (End 2014)			Target (mid-2015)
20%		Sector or Sub-sector strategies for PPP produced including social sector strategies / guidelines	Planned		No sector or sub-sector for PPP produced (TBC)		At least one sector or sub-sector strategies / guidelines for PPP produced, including one in a social sector			At least two sector or sub-sector strategies / guidelines for PPP produced, including one in a social sector
			Achieved
			Source					RISK RATING
			Project Progress Reports, independent assessments					Medium
INPUTS (£)
		DFID (£)			Govt (£)		Other (£)				Total (£)			DFID SHARE (%)
INPUTS (HR)			400000
		DFID (FTEs)

OUTPUT 3		Output Indicator 3.1			Baseline (2013)		Milestone 1 (End 2014)			Target (mid-2015)				Assumptions
Strengthened capacity of PPP Office, ministries and provinces, and awareness raising of the private sector in PPP implementation		Training courses provided to Government officials (at the central and provincial level) on PPP concepts, the legal framework, and roles and responsibilities of different parties	Planned		0		At least three training events take place for at least 100 participants with at least 60% of participants reporting improved knowledge			At least 150 participants trained, and at least 60% of participants reporting improved knowledge				Good trainers mobilised and active participation of relevant stakeholders / PPP Steering Group is established and functions with Deputy Prime Minister’s strong commitment and leadership / Private Sector interest in PPP process Risk / Relevant stakeholders are not interested in training / Delays in staff recruitment Central ministries (MPI & MoF) fail to build up their capacity / Failure of political will to support the PPP process resulting in lack of private sector interest in participating in PPP
			Achieved
			Source
			Project Progress Reports, Training Scorecards, independent assessments
IMPACT WEIGHTING (%)		Output Indicator 3.2			Baseline (2013)		Milestone 1 (End 2014)			Target (mid-2015)
15%		Awareness raising among private sector on PPP concepts, the legal framework, and roles and responsibilities of different parties	Planned		0		Development and dissemination of at least two PPP knowledge products among domestic private sector			At least one awareness raising workshop which includes private sector participants
			Achieved
			Source					RISK RATING
			Project Progress Reports, independent assessments					Medium
INPUTS (£)		DFID (£)			Govt (£)		Other (£)				Total (£)			DFID SHARE (%)
			300000
INPUTS (HR)		DFID (FTEs)

OUTPUT 4		Output Indicator 4.1			Baseline (2013)		Milestone 1 (End 2014)			Target (mid 2015)				Assumptions
Strategic programme monitoring and evaluation and high level UK/Vietnam exchange		High quality M&E and lesson learning on project performance	Planned		0		--			A light touch An independent review (covered by DFID Meta evaluation) completed by mid 2015 + a lesson learning note by the Fund Manager.				Smooth coordination of DFID Vietnam and iFUSE / Good independent experts identified / Committed and active participation of relevant stakeholders / Risk / Relevant stakeholders are not interested in lesson learning, and senior leadership is not interested or occupied with other agendas / Delays in consultants recruitment
			Achieved
			Source
			Annual Reviews, Evaluation reports and Project Completion Review.
IMPACT WEIGHTING (%)		Output Indicator 4.2			Baseline (2013)		Milestone 1 (End 2014)			Target (mid-2015)
15%		High level exchange between the UK and Vietnamese Governments on PPP related subjects	Planned		One visit by only the Ministry of Finance to the UK		A high level exchange event is organized with participation from several ministries			No further target on this as agreed in the 2014 AR.
			Achieved
			Source					RISK RATING
			High level exchange agenda and reports					Medium
INPUTS (£)		DFID (£)			Govt (£)		Other (£)				Total (£)			DFID SHARE (%)
			200000
INPUTS (HR)		DFID (FTEs)
[1] Boots (2013), Recommendations for consolidating PPP principles into a “Revised Decree” for infrastructure development in Vietnam, August 2013, Working Paper
[1] Social sectors include health, education, water and waste treatment.