Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Education Sector Support Programme in Nigeria (ESSPIN)
Programme Value: £134,600,000		Review Date: 12-30 October 2015
Programme Code: GB1104200	Start Date: July 2008	End Date: January 2017

Summary of Programme Performance
Year	2014/15	2013/14	2012/13	2011/12	2010/2011
Programme Score	A	A+	A	A+	MTR
Risk Rating	Medium	Medium	Medium	Medium

Progress and lessons learned since 2014 AR

1. Real progress has been made in generating State and LGEA capability to embed the school improvement model in all public primary schools in the focus states – close to 16,000 schools in all.
2. It is notable that this progress has been sustained in what has been an atypical year, dominated by changes at all levels of government following the March election outcomes. At one level, primary schools have continued to function, but the discontinuities of funding from states have undoubtedly been significant. Nevertheless, ESSPIN, associated strongly with DFIDN programmes such as SPARC and SAVI, has been able to work steadily with transitional structures and new leadership faces at all levels. At the time of this review, there remain plenty of residual challenges for the ESSPIN State teams.
3. The eventual publication of the 2014 Composite Survey 2 (CS2) has cast a significant shadow. It contains a number of very positive messages about ESSPIN’s work, particularly in those schools which have been associated with ESSPIN for a long period. For these schools identified as ‘ESSPIN schools’, these map on well to the progress documented in Outputs 3 and 4. But the introduction into the analysis of the distinction between ‘ESSPIN schools’ and ‘Non-ESSPIN schools’ (the status of which should be seriously considered ahead of CS3 in 2016) generates a somewhat different picture, specifically in relation to children’s learning in the fields of literacy and numeracy. All of the results from measurements at Grade 2 and Grade 4 show very weak performance, with ‘ESSPIN schools’ achieving somewhat better than the larger population. The important implications for ESSPIN relate directly to the possibility of achieving the 2016 targets for Impact Indicator 1, as they are based on extrapolations from the 2014 CS2 data; but more profoundly, whether actions can be taken to turn around the literacy/numeracy figures on any ‘within-programme’ time-frame, which seems unlikely. Much of the onus for school improvement now rests with the large numbers of SSIT members, SSOs and SMOs deployed across each of the states. The review team were unconvinced of the capabilities of the small number of SSOs with whom they engaged,to make significant contributions to sufficiently changing classroom practice before the project closure. (See Recommendation 5 below).

Progress measured

1. There have been significant gains in the number of schools creating and using school development plans (SDP) to a total of 5,007, or 32% of all engaged schools (Output indicator 3.1).
2. Outcome Indicator 4 shows that just less than 5.2 million children in public primary schools are benefitting from the school improvement programme. Within this population, it is notable that there is nearly a gender balance (2.5 million girls; 2.7 million boys). At Impact level (Impact Indicator 3), numbers of supported children in primary schools in 2015 shows a completion rate of 73%, over a target of 58%; again showing near gender equity.
3. The development of the roles of SBMCs proceeds apace (Output 4), with 11,023 schools achieving a functioning SBMC, with 3,775 achieving ‘advanced’ functionality, although functionality as defined in the logframe is a low hurdle. Simultaneously, the promotion of SBMCs at national level is dynamic, with leadership from FME/UBEC at both policy and dissemination levels.
4. The number of headteachers assessed as effective (Output Indicator 3.2) has risen to 7,459 (47%) and the number of teachers assessed as competent in teaching literacy and numeracy has also risen, to 58,126 (42%).

Summary of recommendations for the next year

1.Strengthen existing links with other DFIDN programmes, inside (TDP, DEEPEN, GEP3) and outside (SPARC,SAVI: although these State-level programmes will soon close) the Education sector, in order to further embed ESSPIN principles and practice in the thinking and practice of senior officials, at both Federal and State levels.
2. Prioritise, as per agreed approaches, work to strengthen all aspects of the work of LGEAs, specifically in relation to school improvement practices.
3. Do not significantly alter the present logframe for the remaining 14 months of the programme, except to adjust targets where they have already been surpassed. If a decision is taken to implement a no-cost extension to mid-2017, this judgement may need to be revisited, specifically in relation to targets.(see Section H).
4. Promote clearer understanding of the concepts, practice and measurement of inclusion and inclusiveness.
5. Attempt to understand and clearly document the multiple factors which appear to contribute to the very low and largely stalled levels of literacy and numeracy acquisition recorded across all of the focus states. These include at least the following: literacy learning, particularly reading, attempted in English rather than in the pupil’s first language; chronically overcrowded classrooms; teachers barely competent in English and Maths; teachers having weak pedagogic skills; serious shortages of books and other learning materials; shortage of real time for learning; limited support for teacher development. Charting a way through this formidable list of well understood challenges may come too late for ESSPIN but is a precursor to further work in the sector by Federal and State governments and their international development partners. The emphasis in this recommendation should be on its better contributing to the growing evidence base of what might better enable children to learn in such challenging contexts, especially in Northern Nigeria – include systematic independent review of ESSPIN’s approach to Teaching and Learning and what could have been be done differently.
6. Create an independent review of the ESSPIN lesson plan booklets against the practicality of their use (i) in seriously overcrowded classrooms, (ii) with teachers whose own English language skills are extremely limited.
7. DFIDN and ESSPIN should quickly conclude discussions on the draft Sustainability Plan, as priorities articulated in that document could, and should, significantly affect programme focus in 2016 and beyond.
8. Mount an independent scrutiny of the state reporting processes, focusing on their robustness and fitness for purpose.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

ESSPIN contributes to better learning outcomes for children of primary school age in the Nigerian States of Enugu, Jigawa, Kaduna, Kano, Kwara, and Lagos. It is designed to improve access to, and the quality of, basic education, equitably and sustainably. It is a major contributor to DFID’s headline operational target of enabling 800,000 more children to benefit from a primary education of good quality by 2015. It is an investment in a country with an estimated 8.7 million out of school children, and where learning outcomes are unacceptably low. Two-thirds of primary Grade 6 children in Nigeria’s Northern States are unable to read in any language.

ESSPIN interventions are underpinned by an integrated approach to school improvement. This encompasses: building capacity (teachers, headteachers and school based management committees); establishing advisory and quality assurance school support systems; helping to review and re-structure State systems (Ministries of Education, State Universal Basic Education Boards [SUBEBs] and Local Government Education Authorities [LGEAs] to deliver meaningful primary education in all public schools; and engaging politically to leverage resources for sustainable school improvement. By 2015 each of the six States had rolled-out state-wide school improvement programmes, investing a total of £19.3m between July 2012 and end of July 2015.

In addition, ESSPIN supports initiatives in Northern States to provide educational opportunities for children from nomadic communities (Jigawa) and those attending Islamiyya, Qur’anic and Tsangaya schools (Jigawa, Kaduna and Kano).

Against the backdrop of State-led reform, ESSPIN has been extended to the end of January 2017, with an additional budget of £33m. This has allowed the project to continue to assist the six States technically, and through direct project support, to consolidate, deepen and embed their own school improvement reforms and strategies. Timely budget releases and high utilisation rates for basic education will remain important indicators of the depth of State commitment. Policies and plans will be strengthened by quality assessed data and timely evidence.

DFID agreed provisional targets using ESSPIN-based estimates of State scale up in August 2013. It originally aimed to support 3.31m children by mid 2016, but due to the rollout the programme is now supporting - directly and indirectly - 5.7m children. It also aimed to improve learning outcomes for 1.83 million children in primary grades 2 and 4 in state public schools; at least 57% of whom were girls. An additional 134,000 disadvantaged and vulnerable children will be given the opportunity to benefit from basic education. Emphasis will be placed on: improving literacy and numeracy in all classrooms; reading with comprehension, understanding numbers and undertaking basic calculations. Particular attention will be given to the effective use of lesson plans.

In achieving its stated outcomes, ESSPIN is confronted, directly and indirectly, by the challenge of increasing levels of instability and conflict in Northern Nigeria. In addition to the risks associated with direct project management and output delivery, the ability of States to maintain their own school improvement reforms will be tested, both by migration of displaced families resulting in hikes in pupil numbers, and by within-state communal conflict.

The results of the 2015 Nigerian elections, and changes in government in most states, has led to a lack of continuity at all levels of the Education sector, which may well pose challenges related to sustaining political commitment and appropriate levels of financing for basic education, the latter being problematic in the context of declining oil prices and resulting stresses for the economy. Active, carefully gauged political engagement strategies, have been developed and their implementation is in progress, with encouraging early results.
EDOREN (2015) commissioned a study of capacity building in ESSPIN’s work, a draft report of which was made available to the AR team. The Narrative Report will carry more detail, but the overall conclusion of the study is that ESSPIN has effectively supported a significant strengthening of organisational capacity within the basic education system, particularly at state level. At the school level, the study finds considerable evidence of enhanced capacity. For instance school development plans are being regularly prepared, head teachers recognise that pedagogical support and supervision are a key part of their role, and SBMCs are actively monitoring teacher attendance and encouraging participation of previously excluded groups. However the impact of this has been limited by continuing institutional constraints and uneven high level political commitment. The main implications of the study are given below. Linkages between these findings and the recommendations of the Annual Review are shown in brackets.
- A need for continued engagement and advocacy to encourage high-level political commitment to improving basic education and tackling institutional constraints in the system [Recommendations 1 and 8];
- A stronger focus on enabling LGEAs to enable them to perform the critical role they have within the system, particularly through effective decentralisation of functions and control of resources, balanced by strengthened accountability [Recommendation 2];
- Greater attention to capacity development at the critical teacher – classroom interface, recognising that sustained day-to-day support likely rests with the leadership and mentoring skills of the head teacher and their senior colleagues [Recommendation 5];
- Greater attention to issues of teacher training at all stages of their careers, including recruitment, deployment, professional development and promotion, which relate to the low levels of basic knowledge and skills amongst teachers which are presently the core constraint on ESSPIN’s performance [Recommendation 5].

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

ESSPIN’s Outcome Statement reads: Quality of, and access to basic education improved equitably and sustainably. Its primary indicator is benchmarked, good quality schools.

Targets for 2014/2015 were further revised during the programme year to reflect full state-led and state-funded rollout of the school improvement programme to all schools in the six focus states. Although results for Impact Indicator 1 and Outcome Indicator 1 are not reported in 2015, results for Outcome indicators 2 and 3 demonstrate that ESSPIN is making a difference at outcome level in terms of increased access to education and increased state funding to school improvement. The absence of reporting on Impact Indicator 1 deserves further explanation - the CS2 data for 2014 has already been referenced as showing weak performance in learning outcomes, across the programme. CS2 data is presented in the logframe under achievement of Impact Indicator 1. Because a comparable study will not be undertaken until 2016, the 2015 year has been skipped and targets set for 2016 based on extrapolations of between two and three times the 2014 figures. This is a big ask in the context of weak classroom performance and support.

An additional Outcome indicator (2a) measuring access to education for children with disabilities was added to the logframe for increased visibility of this neglected area. The results show a decline based on figures from 2013/14 despite an overall increase in children in schools – a pointer to likely flaws in available data for tracking children with disability.

Outside of logframe targets and indicators, all six states rolled out ESSPIN’s school improvement model to all of their public primary schools (15,830) and are contributing their own funds to support its implementation. In the year under review, with elections and an ensuing transition period, states have not always matched fund release to their budget commitments. Overall, however, this is a positive development which demonstrates commitment to the programme’s aims and bodes well for sustainability. It does mean, of course, that the intensity of the ESSPIN service delivery efforts is inevitably diluted, with increased dependence on the growing skills of SSIT members, SSOs and SMOs.

The revised (2015) logframe has introduced a super impact level and added additional indicators at Impact and Outcome level. As was pointed out in the last AR, assessing progress at the Outcome and Impact levels is as important as monitoring the progress against Output targets. The majority of ESSPIN’s results at Impact level will be reported in 2016 following the third Composite Survey and publishing of survey results from MICS (2016) and NEDS (2015). Impact Indicator 3 measures primary school completion. In 2015, the primary completion rate (PCR) stood at 73%, exceeding the 58% target by a considerable margin. According to the ASC, 447,258 children (208,366 girls) completed primary 6 in the 2013/14 academic year. It is possible that these numbers only present part of the picture, given a growing phenomenon whereby many children transit direct to junior secondary from completion of primary 5, whereas the PCR is calculated based on children in primary 6.

A brief overview of progress at the Outcome level is provided for indicators 2 and 3. Indicator 1 uses results from the biennial Composite Survey and will next be reported in 2016.

Indicator 2a Number of Additional Children in Public Primary Schools Disaggregated by Gender and Disability, in Focus LGEAs (DFID OP Headline Indicator 1): Following further analysis of the ASC, the 2014target was revised downwards to 308,628 (still far in excess of the logframe target). In June 2015, the additional children in school has increased to 378,367 (197,881 females) exceeding the 2015 target by 60,000. The measure of the number of additional children with disabilities has decreased from the 2014 baseline of 5,906 to -1,698, which is meaningless. There is clearly a lack of clarity over the measure; it should be noted that the current version of the ASC contains no clear guidance on definitions of disability.

Indicator 2b Cumulative number of marginalised children with improved access to basic education through IQTE, and nomadic community schools disaggregated by gender: In June 2015, 60,691 children (33,177 girls) had improved access to education through IQTE work in Jigawa,Kano and Kaduna. This meets the overall target for marginalised children and is an increase of more than 14,000 on the 2014 figures. The target for nomadic education was met, with approximately equal participation of girls and boys. Participation of girls in specifically focused girls’ education initiatives was significantly below target at 12,647 (target 18,000).

Indicator 3 Level of Resources Available for School Improvement Measured by the Annual Percentage Change (in real terms) in the Release/Utilisation of State Funding: This continues to be measured by state budget release rates based on available data. The 2014 average budget release rate (the 2015 measure) was 67% for the six focus states against a 2013 average figure of 63% (2014 measure). In addition to the year-on-year increase, this exceeds the expected milestone of 55% by over 12 points. All states except Jigawa improved on performance from 2013. Jigawa’s release fell dramatically from 93.5% in 2013 to 25% in 2014. Kwara’s release increased strongly from 43.7% in 2013 to 73.4% in 2014. There is enormous variation in releases across States through the financial year. Enugu, Kaduna and Lagos all started the year well, but slowed down as it went on. By quarter 3, Kwara had released just 30% of the budget, but released a massive 43% in the final quarter. It is instructive that the substantial increase in Kwara’s budget release rate did not translate into increased funding for SIP activities, suggesting that funds released to SUBEB were used for other purposes.

Indicator 4 Number of children to benefit from SIP in public primary schools disaggregated by gender. ESSPIN uses an average school size per state to calculate this figure but in the future will use actuals from the ASC. By June 2015, 5.2m children (2.5m girls) in 15,830 schools were benefiting from the programme. The target was missed by approximately 30,000 children but the result represented an increase of over half a million children on the 2014 figure, including 238,000 girls

Overall output score and description

The separate Output scores emerge as:

Output	Impact Weighting	Output Score	Risk
1	10%	B	Medium
2	15%	A+	Medium
3	45%	A	Medium
4	30%	A+	Medium

Overall Score: A

ESSPIN has made good progress against three of the Output indicators, with three [1, 2 and 4] being equal to the 2014 scores. The B score for Output 1 simply reflects the considerable challenges in effecting change at the federal level ESSPIN’s self assessment for Output 3 is based on reporting from SSO. This includes the judgement that nearly 60,000 ESSPIN-influenced teachers ‘….can deliver competent lessons in literacy and numeracy’ with nearly 50% of these being identified as ‘advanced effective’. This means that, on average, four teachers per school meet the first criterion, and two teachers per school the second. It is necessary to hypothesise a connection between the competencies described above and the learning of children in the classes of these teachers. Unfortunately, this simply does not square with the findings of CS2 on children’s learning in the core skills of literacy and numeracy. And the AR team was specifically tasked to use the CS2 results as comparators where appropriate. Given admitted fragility in the SSO reporting skills, the team concluded that there had been significant over-scoring in this key sub-indicator. The logframe actually uses CS2 data from 2014 to extrapolate literacy/numeracy targets for 2016. There will inevitably be debate about how to reflect in a 2015 AR these results of research carried out in 2014, but the AR considers that the data presented by ESSPIN for 2015 must be set against likely one year projections of the CS2 data, which is presented in more detail in the Output 3 section..

Key actions

These are documented as Recommendations in Section A.

Has the logframe been updated since the last review?

Yes, significant changes were made in 2015. The logframe is a very complex and sophisticated document, as befits such a large and extensive programme. The evolution of the logframe over 7+ years means that many aspects have been reviewed (changed), resulting in difficulties in looking at a full time sequence. This will become a particular issue at the point of programme closure in 2017, when construction of a meaningful PCR will be challenging.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened Federal Government Systems Supporting States’ Implementation of School Improvement
Output number per LF		1	Output Score	B
Risk:		Low/Medium/High	Impact weighting (%):	10%
Risk revised since last AR?		Y/N No	Impact weighting % revised since last AR?	Y/N No

Indicator(s)	Milestones	Progress
1.1 Disbursement rate of UBE Intervention Fund funds for basic education (3-year rolling) for programme states compared to non-programme states	Planned 2012-2014 rolling / ESSPIN States 80% / Non-ESSPIN State 70% / No State Level Baseline Targets	Actuals 2012-2014 rolling / ESSPIN States 66% / Non ESSPIN States 62% / (Enugu 17% Jigawa 58% / Kaduna 74% Kano 100% / Kwara 74% Lagos 74%)
1.2 Quality of national systems established for: / a) Monitoring of learning achievement (MLA) / b) Quality assurance / c) SBMC implementation	Planned June 2015 / B / B / B	Actuals June 2015 / C / C / A

Key Points

1.The disbursement of the UBE IF is predicated on the capacity of each state to budget for and release the 50% matching grant. Although the planned milestone for IF disbursement rate had been reviewed downwards following the 2014 AR, from 95% ESSPIN States and 85% Non-ESSPIN States for the rolling total (2011-2013), to 80% for ESSPIN States and 70% for Non-ESSPIN States for the rolling total (2012-2014), both failed to reach the planned milestone achieving only 66% for ESSPIN States and 62% for Non -ESSPIN States. However, for both cycles the proportion of releases to ESSPIN states was higher than to non-ESSPIN states. The disbursement rate showed a decline from 77% in 2013/14 to 51% in 2014/15 in ESSPIN states and from 63% to 32% in non-ESSPIN states (according to the VfM self-assessment report). This is presumably related to the uncertainty arising from the elections and delay in appointment of State Commissioners and SUBEB chairs.

The breakdown of allocations by states indicates that Enugu state had the lowest releases, decreasing from 23% to 17% between both rolling totals as the state government did not access the UBE IF 2013 and 2014 for non-release of 50% matching grant. The UBEC website shows that Kano was the only ESSPIN State that was up-to-date on assessment of the IF achieving a 100% disbursement for both rolling totals. Kwara state improved by 11% reporting that it had also accessed its IF for 2014 while Lagos, Jigawa and Kaduna states had apparently not. The implications for support at State level to school improvement are clear enough.

2.ESSPIN supported the establishment of a national system for the monitoring of learning achievement (MLA) and the articulation of a Draft National Framework by the national Ministerial Committee on MLA, which is to be presented to the Joint Consultative Council on Education (JCCE). ESSPIN also facilitated improved collaboration of the Federal Ministry of Education (FME) and the Universal Basic Education Commission (UBE) with FME in the leadership position with respect to MLA. The arrangement has slowed down the administration of the MLA resulting in UBEC planning a National Assessment for 2016 without any input from the FME. This may be due to the perceived weak capacity of the FME to steer a national MLA system.

3.ESSPIN supported the FME/UBEC with the development, through a bottom up approach, of a draft national SBMC Policy which is awaiting ratification by the National Council on Education (NCE). Although UBEC has rolled out the national SBMC framework developed with ESSPIN support to all 36 States and the FCT, only six States have achieved full domestication. UBEC is planning to embark on a high level advocacy visit to outstanding States to accelerate the process and has allocated 10m naira for SBMC development to each state. The A score is amply justified.

4.The FME-UBEC collaboration on national Quality Assurance reform, facilitated by ESSPIN, with roll out support to 36 States and the FCT, has supported joint inspection visits with the Federal Education Quality Assurance Service (FEQAS) and State quality assurance agents. A National Quality Assurance and Evaluation schedule has been updated with assistance from ESSPIN. A final draft of this worthy document was shown to the review team. However, the current arrangement on quality assurance at basic education level has created an overlap of functions of some SUBEB QA Officers and State Ministry of Education Quality Assurance agents that needs to be resolved. While FEQAS is constrained by the non-release of funds, UBEC has allocated 10 million naira to each State for quality assurance. Meanwhile, UBEC has barred Lagos state from accessing its share of this allocation because of continuing overlap of functions of Lagos State SUBEB and the Education Quality Assurance Agency. The SUBEB Chair in Enugu State evidenced the same issue, which suggests that, nationally, we are dealing with a system in a state of flux. The team supports the self-assessed C grade.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. ESSPIN has complied with AR 2014 recommendation for cross referencing and alignment of Output indicator 1.1 and Outcome indicator 4 to determine whether improved levels of accessing IF funding is matched by the efficient release and utilization of State funds for school improvement. With the review of the logframe, Output 1.1 no longer relates to Outcome 4 but to Outcome 3. ESSPIN has aligned Output 1.1 of the revised log frame to Outcome 3 ‘Level of financial resources available for school improvement; measured by the annual percentage change (in real terms) in the release/utilisation of state resources’ in addressing the recommendation.
2. AR 2014 also suggested that ESSPIN should investigate whether MLA, QA and SBMC reforms could have stronger appropriate topic specific, target delivery related indicators not withstanding that these cannot be attributed directly to ESSPIN. New performance criteria for 2015 and 2016 were developed for the National Systems indicators to inform the annual Self-Assessment measurements.

Recommendations
1. DFIDN to support ESSPIN to press for greater political engagement on disbursement rate of UBEC IF, focusing on States with low IGR that are likely to default on release of matching grant in the current economic context.
2. Reflect on how capacity of MLA in FME to take a leadership role to deliver on its mandate could be strengthened.
3. Support FEQAS to address overlapping of QA functions where they exist in SMOEs and SUBEB, for example in Lagos and Enugu.
4. Develop systematic tracking of releases of TPD funds, which do not require matching grants from State resources. This would provide a proxy indicator relating to capacity to access and use TPD funds for SIPrelated activities.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased Capability of State and Local Governments for Governance and Management of Basic Education at State and LGEA Levels
Output number per LF		2	Output Score	A+
Risk:		Low/Medium/High	Impact weighting (%):	15%
Risk revised since last AR?		Y/N No	Impact weighting % revised since last AR?	Y/N No

Indicator(s)	Milestones	Progress
2.1 Quality of strategic and operational planning and budgeting, budget execution, performance monitoring and reporting at State and LGEA level (LGEA targets in brackets)	Planned 2015 / EN JG KD KN KW LG / B [D] A [D] A [D] B [D] A [D] A [D]	Actuals 2015 / EN JG KD KN KW LG / C [D] B [C] A [C] A [B] C [B] A [C]
2.2 Quality of service delivery systems and processes at State and LGEA level	EN JG KD KN KW LG / B [D] B [D] B [D] B [D] B [D] A [D]	EN JG KD KN KW LG / B [D] B [C] B [C] B [C] B [B] A [C]
2.3 Quality of school support and quality assurance services at State and LGEA level	EN JG KD KN KW LG / B [D] B [D] A [D] B [D] A [D] A [D]	EN JG KD KN KW LG / B [C] B [C] A [C] A [B] B [C] B [C]
2.4 Level and quality of State/LGEA engagement with local communities on school improvement	EN JG KD KN KW LG / B [D] B [D] A [D] B [D] A [D] A [D]	EN JG KD KN KW LG / B [C] B [C] B [C] B [B] B [C] B [A]
2.5 Quality of inclusive policies at State and LGEA levels	EN JG KD KN KW LG / B [D] A [D] A [D] B [D] A [D] A [D]	EN JG KD KN KW LG / A / [C] B / [B] A / [C] B / [C] A / [C] A / [C]

Key Points

1.At LGEA level, all targets were met or exceeded, but starting from a low base of ‘D’ across the board. At state level 70% indicators met or exceeded targets. There was variation across the states as follows:

1.1 Kaduna, Kano and Lagos achieved an A in 2015. Jigawa achieved a B. Enugu and Kwara failed to meet their target and achieved Cs.
1.2 Lagos achieved an A while others achieved Bs, all indicators met or exceeded target, although performance on these depends on government working with reforms initiated by ESSPIN.
1.3 Kano exceeded its target (B) and scored A. Enugu, Jigawa and Kaduna met their targets. Kwara and Lagos missed their target (A) and scored Bs.
1.4 All states achieved Bs but Kaduna, Kwara and Lagos missed their A targets.
1.5 Only Jigawa missed its target of A and scored a B, other states (Enugu, Kaduna, Kwara and Lagos) achieved an A.

2.In response to the 2014 AR recommendation, indicator 2.5 has been moved to Output 2 from Output 4 as contained in the revised logframe. Evidence shows that only 43% met or exceeded targets when indicator achievements in 2014 and 2015 are compared, although 2015 targets were revised.
3.ESSPIN influence is more at state level (SUBEB and MOE), although efforts are now being made to focus on LGEAs. Some identified gaps at LGEAs are: EMIS is operational in less than one-quarter of LGEAs in most states, some LGEAs still name QA officers as ‘supervisors’ and conduct school inspection rather than quality assurance.

4. Many SSOs, SSIT members, and SMOs are former teachers recruited from different schools, including junior secondary schools, to LGEAs and SUBEB without replacement. While the initiative to recruit experienced and successful teachers to these roles is applauded, it is not always the case that existing mechanisms deliver adequate teacher replacements.

In interviews, stakeholders could fluently articulate the reforms and are well used to presenting evidence regarding improved planning. The quality and strength of evidence varies across sub indicators:

- Progress is strongest at SUBEB level. They have more freedom to adopt ESSPIN-led reforms (e.g. restructuring as a result of functional review). In comparison, SMOEs are guided or bound by state-wide reform processes e.g. teacher deployment, which requires whole civil service reform.
- Some scores appear generous, especially at LGEA level. Lower scores for analysis and aggregation of school development plans is an example of weak capacity at school and LGEA level.
- Where ESSPIN and SPARC work together, there are synergies that strengthen DFID’s overall contribution, as, for example, in developing tools and systems for use in planning and budgeting at LGA and state levels.
- The elements of planning, HR, financial management and QA systems are in place. However, on-going diligence will be needed to ensure that they contribute in a co-ordinated way to effective service delivery and measurable school improvement.

Summary of responses to issues raised in previous annual reviews

There has been an attempt to focus on LGEAs and to strengthen school improvement in the period under review. However, this has not yet yielded appreciable achievement based on information gathered during interviews. Although the logframe has been revised as recommended in 2014 AR, the modality of target setting at LGEAs seems unclear, and the situation whereby all output indicators for LGEAs were met or exceeded appears too generous when compared with the observed situation on the ground.
The draft synthesis report on the research study under EDOREN on capacity development within the ESSPIN programme provides evidence to support deeper lesson learning about what is working, how and why. It concludes that ESSPIN has been effective in building capacity, particularly at the state level, but that this has not yet led to significant improvements in learning outcomes. The report also explores the reasons for this apparent disconnect. It is important to understand both the contributions and the limitations of ESSPIN-led reforms within wider governance reform initiatives. Here, there is an opportunity for ESSPIN to engage with, and contribute to, DFIDN’s wider public sector reform portfolio.
ESSPIN’s existing collaboration with SAVI involves the use of CSOs which have skills to offer in relation to education budget expenditure tracking, AESPR reporting and M&E processes at lower levels. These CSOs are encouraged to communicate with those already working at community/SBMC levels.

Recommendations

1. Continue to emphasise, throughout the remainder of the programme, the focus on improving the performance of LGEAs in supporting schools and strengthening school improvement. Everything that can be done to strengthen the understanding and practice of the cadre of SSOs would be a priority, alongside strengthening the leadership capacity of headteachers.
2. Continue to pursue greater internal integration between output-led work to facilitate better departmental linkages across SUBEBs and SMOEs.
3. Encourage DFIDN state-level representatives to support ESSPIN staff in political engagement, especially in relation to state budgets, release of funds, and disbursements from UBEC.
4. Encourage SUBEBs and SMOEs to maintain the practice developed under ESSPIN of producing annual state self-assessment reports on their own capability and capacity to govern and manage the school system.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened capability of primary schools to provide improved learning outcomes
Output number per LF		3	Output Score	A
Risk:		Low/Medium/High	Impact weighting (%):	45%
Risk revised since last AR?		Y/N No	Impact weighting % revised since last AR?	Y/N Yes / (down from 55%)

Indicator(s)	Milestones	Progress
3.1 Number (and percentage) of public primary schools using school development planning	Planned 2015 / Effective: 1833 (13%) / Advanced effective: 2730 (20%) / Total: 4,563 (30%)	Actuals 2015 / Effective: 2,007 (12.8%) / Advanced effective: 3,000 (19.1%) / Total: 5,007 (31.8%)
3.2 Number (and percentage) of head teachers in public primary schools operating effectively	Effective: 5,022 / Advanced effective: 2,837 / Total: 7,859 (53%)	Effective: 2,955 (18.8%) / Advanced effective: 4,504 (28.6%) / Total: 7,459 (47.4%)
3.3 Number (and percentage) of teachers in public primary schools who can deliver competent lessons in literacy and numeracy	Effective: 27,826 (20%) / Advanced effective: 10,915 (8%) / Total: 38,741 (28%)	Effective: 31,218 (22.4%) / Advanced effective: 26,908 (19.3%) / Total: 58,126 (41.8%)
3.4 Number of inclusive schools	Effective: 3,750 / Advanced effective: 2,730 / Total: 6,480	Effective: 2,504 (15.9%) / Advanced effective: 3,804 (24.2%) / Total: 6,308 (40.1%)

Key Points
At the advanced effective level, all indicators have been exceeded and for three indicators by a large margin. However at the total level, the targets for 3.2 and 3.4 were missed. There is variation across the four indicators by states.

The review team wishes to draw attention to apparent inconsistencies in relation to data presented in Output 3, viewed against that for 2014 (CS2) in Outcome1a. There, the number of ‘good quality schools’ is reported as: EN – 26%, JG – 3%, KD – 0.4%, KN – 4%, KW – 25%, LG – 31%. The three Northern states have very low returns. It is probably fair to suggest that indicators 3.1, 3.2 and 3.3, taken together, have something to say about a ‘good quality school’. The data presented, generated by SSO reports, albeit in 2015, produces dramatically higher figures, for the Northern states in particular. It suggests over-reporting by SSO.

1. The particular difficulty is with Output 3.3. On the basis of SSO reports only (as the logframe source of evidence) the targets have been achieved or even over-achieved. The 2014 achievement level was nearly 38,000. This suggests an increase of competence in one year of 20,000 teachers, of whom 16,000 have achieved ‘advanced effectiveness’. These gains sit uncomfortably with the findings of both the review team and CS2, both of which posit a relationship between ‘advanced effectiveness in delivering competent lessons in literacy and numeracy’ and ‘pupil scores on literacy and numeracy tests’. Again, it suggests over-reporting by SSOs, who are acknowledged to be learning challenging new skills.
2. In the following sections, the first commentary is that provided by ESSPIN to substantiate the progress figures. The second commentary, in [ ], references in each case the CS2 findings, recognising they relate to research carried out in 2014, not 2015. In relation to each of the four indicators, the same question applies: Is the net overall gain claimed by ESSPIN in one year from the CS2 study realistic?

3.1 Overall, this milestone is achieved. In the previous three years, it was missed, so this represents overall good progress. However at state level, Enugu and Kano missed their targets.[CS2: SDP is improving over time and much faster in ESSPIN-influenced schools (20% cf 3%). More schools are creating SDPs that include 3+ activities focused on improving teaching and learning, but some SDPs are simply short wish-lists].

3.2 The overall milestone has been missed by 5%. At state level only Kano and Lagos missed their milestones (Lagos by only 1%). In Kano this is probably due to the later start of the head teacher
component, the initial priority being on teacher training (hence the Kano Teaching Skills Programme). Better reporting by SSOs might also be a factor. Enugu and Kaduna significantly exceeded their 2014 achievement. At least as important as the overall total for each state is the number of those attaining the ‘Advanced’ standard. Significantly, 5 out of 6 states met their Advanced standard milestone. [CS2: HTs performance is improving with time, and the more ESSPIN support, the faster the improvements. Effective HTs at 14% in non-ESSPIN schools, 37% for those having received ESSPIN training]

3.3 As in 2013 and 2014, this milestone has been exceeded: this year by 50%. Is it plausible that 15,993 teachers reached ‘advanced effective’ level against this indicator in a single year? There are differences between the states, but most of the excess is attributable to Kaduna, Kano, and Kwara, which exceeded their milestones by some distance. Lagos did not achieve its milestone. The relatively low attainment of the advanced indicator in Kaduna and Lagos is probably a more realistic assessment than those offered by the other states, as little work has taken place to date to support state and school staff to understand what behaviours should be associated with these criteria and how to inculcate them in all schools. [The CS2 assessment of teacher competence does not exactly match the logframe descriptors. However, “overall findings with respect to teachers suggest no significant change in teacher competence overall between 2012 and 2014.” Again, there is a positive effect of ESSPIN training. Teachers meet the the competence standard as follows: Non-ESSPIN: 19.5%; ESSPIN schools: 33%; ESSPIN trained: 43%]

3.4 In line with the progression through 2013 and 2014, achievement has increased significantly but the milestone is still, just, missed. Kano and Kwara met their overall milestone. [CS2: The number of inclusive schools declined between 2012 and 2014. 25% of ESSPIN schools meet inclusiveness criteria but only 8% of other schools.]

The table below shows the relationship between ESSPIN assessments for these four indicators for 2014 and 2015, set against the comparable CS2 data.

Indicator	ESSPIN 2014 Score / (SSO reports)	CS1 2012	ESSPIN 2015 Score / (SSO reports)	CS2 2014 (approximately equivalent score)
3.1 SDP	21%	4%	32%	ESSPIN schools 20%; non-ESSPIN schools 3% / [Overall: 7%]
3.2 HTs	47%	14%	47%	Non-ESSPIN 14%; ESSPIN trained 34% / [Overall: 20%]
3.3 Teachers	27%	No equivalent measure	42%	Meet competence standard: / Non-ESSPIN 19.5%; ESSPIN schools 33%; / ESSPIN trained 43%
3.4 Inclusive schools	27%	19%	40%	25% of ESSPIN schools and 8% of non-ESSPIN / schools meet standard, which has declined / since CS1, but much less so in ESSPIN schools / [Overall: 13%]

It is in relation to Output 3.3 that there is a significant, and crucial, gap between statements about the competence of teachers in the areas of literacy and numeracy, and the CS2 findings of very weak learning of basic skills. If there were nearly 60,000 teachers reaching a level of effectiveness in these skills (with nearly 50% of them being ‘advanced’ effective), that would mean that, on average, every school in the six states would have four teachers at this level. Of course, it is well understood that taking on board all of the public primary schools in a state is a huge challenge – to skills, to resources, to time. Is it realistic?

Summary of responses to issues raised in previous annual reviews (where relevant)

1.Reference to SDPs has been removed from Output 4 on the logframe so that Output indicator 3.1 is the only remaining reference to the planning function.

2.Output 3.5 has been moved to Output 4, as Indicator 4.2, with a more functional indicator description.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved Community Participation in School Improvement
Output number per LF		4	Output Score	A+
Risk:		Low/Medium/High	Impact weighting (%):	30%
Risk revised since last AR?		Y/N / No	Impact weighting % revised since last AR?	Y/N Yes / (up from 20%)

Indicator(s)	Milestones	Progress
4.1 Number of public primary schools with functioning SBMCs	PLANNED 2015 / Effective: 6,727 / Advanced effective: 3,773 / Total 10,500	ACTUAL 2015 / Effective: 6,984 / Advanced Effective:4,039 / Total: 11,023
4.2 Number of SBMCs in public primary schools that take measurable actions based on issues raised by women and children.	Effective: 7,063 / Advanced effective: 3,437 / Total: 10,500	Effective: 7,248 / Advanced effective: 3,775 / Total: 11,023
4.3 Quality of CSO and community demand for quality and inclusive education	B	B
4.4 Number of SBMCs supporting inclusive education	Effective: 6,714 / Advanced effective: 3,786 / Total: 10,500	Effective: 7,030 / Advanced effective: 3,993 / Total: 11,023

Key Points

This Output and the corresponding indicators were reconfigured in 2015 to reflect the recommendations of the 2014 Annual Review. The Output focuses on improved community participation in education and assesses it through indicators on the performance of SBMCs and CSOs.

Overall targets were met in 2015, despite not all states reaching the target, due to a higher number of schools than expected entering the mentoring/monitoring stage of the SBMC development process; thus 523 additional SBMCs making the total of 11,023 surpassing the 10,500 that were targeted. The actual number of primary schools with fully functioning SBMCs is 4,039 as against 3,483 in 2014. The figure of 11,023 primary schools with effective SBMCs appears in 4.1, 4.3 and 4.4. This is understood as a basic level of functionality: the SBMC has been activated and received some training. The number of SBMCs attaining advanced effectiveness across the same indicators has reached around 40%, so there is plenty of work to do to ensure that most SBMCs/schools are effective in supporting inclusion and taking action on issues raised by women and children.

In the following sections, the first commentary is that provided by ESSPIN to substantiate the progress figures. The second commentary, in [ ], references the CS2 findings, recognising they relate to research carried out in 2014, or the findings of the 2015 AR team.

4.1 Enugu, Lagos and Jigawa have met their targets on SBMC Functionality. Kano is just below its target and Kwara and Kaduna did not meet the target. For example, there were significant increases in the proportion of schools meeting the SBMC functionality - in Enugu from 9% to 23%; in Kwara from 30% to 75%. [CS2 reported that 62% of ESSPIN schools and 13% of non-ESSPIN met the functionality standard. This can be attributed to the time-gap between the CS2 and present ESSPIN reports since a series of activities were conducted to increase SBMC functionality].

4.2 Enugu, Lagos, Kano, Kaduna and Jigawa have met their targets, however the Kwara results dipped, although the 685 SBMCs meeting the target still represent 79% of the total 902 schools monitored in 2015. Only 3,775 out of 11,023 were identified as advanced effective SBMCs in that they took measurable actions based on issues raised by women and children. [CS2 looked at inclusiveness of women and children in SBMCs; 48% of ESSPIN schools met the standard compared to only 2% of non-ESSPIN Schools.]
While the submitted data shows a very significant increase in the extent to which SBMCs are inclusive of women’s and children’s concerns, the pattern is not even across the focus states. [The CS2 report shows that in Jigawa State, the proportion of SBMCs that met ESSPIN’s standard for inclusion of women and children remains low, at 14% for women and 4% for children. In Kano state women’s participation worsened with only 2% meeting the standard, with little change in the extent of children’s participation; with almost none meeting the standard]. The review team, while noting low levels of participation in the main SBMC, recognises that the setting up of sub-committees for women and children is having a positive response, with the voices of both groups being more clearly heard. This was clearly expressed in an inspiring meeting in a school in Kaduna.

4.3 The overall indicator for CSOs was met, with all states achieving a Self-Assessment B, except Kano which achieved a C. This indicator measures three areas of capacity development for CSOs: emerging and strengthening partnership with State governments; community mobilisation; and, advocacy based on their experience of working with SBMCs and schools in harnessing community demand for improved primary education. The AR team encountered a number of examples of engaged CSOs forming new relationships with government. CSOs have an important role in assisting SBMCs in their pursuit of additional resources for their schools. In many communities, demand for quality education is high and inclusive education awareness has been created but, as yet, there is limited understanding and interpretation of the latter concept.

4.4 Enugu, Jigawa and Lagos exceeded their targets. In Kwara, the results were lower than planned due to weak monitoring processes as a result of lack of state commitment and resources, and lengthy delay in the start of the ESSPIN consolidation work for Year 7 of the programme. In the twelve schools visited by the AR team, there was only limited awareness of inclusion issues, usually restricted to the special needs of disabled children.

The overall assessment of the Annual Review team 2015 shows the development of School Based Management Committees (SBMC) in a positive light, with increasing ownership of primary schools by local communities. Support for SBMCs by CSOs and Social Mobilisation Officers is high. Significant results include increased community action in support of: school development planning; fundraising; and inclusion of out-of-school children.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers in ESSPIN are the direct costs of Programme Support Activities (PSA) and the costs of Technical Assistance (TA). The main components of PSA costs were the provision of toilet facilities and clean water in schools (which amount to 22% of total cumulative PSA costs over the life of the project) and the costs of teacher and head-teacher training (18% of the total). ESSPIN managers routinely monitor and report on these costs in quarterly and annual reports. Similarly, the balance between national and international TA, and short-term and long-term TA costs, are monitored in accordance with the contract for the management of the programme. The average daily cost of TA in Year 7 of ESSPIN was £634 for short term posts and £261 for long-term staff. These fee rates could usefully be compared with equivalent figures from the other State Level Programmes of DFID in Nigeria, as recommended in the IMEP Common Framework for VfM Analysis. Overheads amounted to 26% of total DFID spend on ESSPIN in 2014-15, but this ignores the fact that 27% of total operational costs of the programme were covered by funding leveraged from state budgets.

VfM performance compared to the original VfM proposition in the business case

DFID defines VfM in terms of the ‘3 E’s’ – Economy, Efficiency, Effectiveness – following the guidelines of the National Audit Office (NAO). A fourth ‘E’ – Equity – may be added in VfM assessments. The 2014 AR of ESSPIN recommended that the programme managers should produce a ’self-assessment’ of VfM for validation in the 2015 review. This current AR assessment is based on evidence presented in the self-assessment report (and accompanying spreadsheets), in the ESSPIN Annual Report for 2014-15, in the ‘VfM strategy’ of ESSPIN as set out in the Learning and Evidence Framework, and in the 2014 Composite Survey report, dated April 2015.

ESSPIN has tracked unit costs on seven specific Economy indicators in each of the last four years. This data shows a positive trend of consistent reductions in unit costs, with the greatest economies being in the the most costly interventions, notably head-teacher training and school development planning. Declining unit costs within ESSPIN are the result of several factors, including deliberate efforts to drive down costs in the interests of economy, but more particularly the scaling up of the School Improvement Programme (SIP) and the gradual transfer from DFID funding through ESSPIN to funding of activities and staff from state budgets, including funds from federal sources. There has been hardly any attempt to compare unit costs in ESSPIN with costs in similar programmes and/or in other contexts, ostensibly because benchmarking data on economy indicators is reported to be too ‘thin’. There are some standard indicators and comparators, at education sector level, that could be used for this purpose, including the ten DFID VfM Metrics in Education and similar indicators of ‘Financial commitment to education’ in the UNESCO Global Monitoring Reports.

In the ESSPIN VfM self assessment report, Figure 4 seeks to present trends over time in five key output or Efficiency indicators as ‘Improvements in ESSPIN input conversion rates’, with somewhat misleading labels and captions on the bar charts. The data shown for 2012-13 and 2013-14 is the same as the data reported on these output indicators in the logframe. But the bar charts show a larger increase in 2014-15 in the proportion of schools undertaking proper planning (from 21% to 37%) than is shown in the 2015 logframe (from 21% to 32%) from the SSO reports. The reported increases in 2014-15 in the proportions of schools with ‘advanced effective’ functioning SBMCs and with SBMCs reflecting women’s and children’s concerns, from the SMO reports, are even larger and do not correspond with the numbers in the logframe. This data cannot be considered as reliable evidence of improved efficiency in the ESSPIN School Improvement Programme, although the logframe does provide evidence of more modest improvement. The Composite Survey report (CS2) provides more robust evidence on these five key output and efficiency indicators. In each case, ‘ESSPIN schools’ performed better than ‘non-ESSPIN schools’, and they performed better in 2014 than in 2012. ESSPIN has also leveraged resources from state budgets, obtained significant cost savings in operations, and established synergies with other DFID programmes, as further ways of increasing efficiency. The six ‘ESSPIN states’ are consistently more effective than other states in securing disbursements from the UBEC Intervention Fund and TPD Fund.

Effectiveness relates to how well outputs are converted to outcomes. Three indicators of effectiveness are used by ESSPIN, two of which relate to school quality, as measured in Composite Survey 2. ‘ESSPIN schools’ improved from an average school quality score of 39% in 2012 to 55% in 2014, whilst control schools improved only slightly, from 38% to 40% (CS2, p.41). The proportion of public primary schools that met the benchmark for ‘a good school’ in the six states increased from 4% in 2012 to 10% in 2014 (CS2, p.39). This provides solid evidence of school improvement and programme effectiveness, from a robust source. The third indicator of effectiveness is the number of learners benefitting from SIP. The 2015 logframe indicates that the number of male and female pupils in schools covered by SIP exceeded the 2014 target (set in 2012) but was slightly below target in 2015, with 5.2 million children benefitting by August 2015 (approx. 2.7m boys and 2.5m girls).

On Equity, the Annual Report indicates that the poorest children benefit more from ESSPIN than the richest, and that boys and girls attain similar scores in tests of learning achievement, whether they are in ‘ESSPIN schools’ or not. Children in urban schools achieve higher test scores than those in rural schools, and this differential is smaller in ESSPIN schools than in other schools on the numeracy tests, but larger on the literacy tests.

The Business Case for the extension of ESSPIN in 2013 stated that two headline cost-effectiveness indicators would be monitored during the extension period: 1) the cost per additional student reaching proficiency in numeracy and literacy at P2 and P4, and 2) the cost per additional student achieving improved learning outcomes. There are real challenges in measuring these unit costs and it has not been possible to do so. Instead, the main indicator of cost-effectiveness that has been calculated by ESSPIN and presented in the VfM self-assessment report is the cost per child benefitting from the SIP. This cost is measured by the total spend on Outputs 3 and 4 (the service delivery outputs) divided by the total number of children enrolled in ‘focus schools’. The unit cost has fallen from £15.00 in 2013, to £14.10 in 2014, and to £13.75 in 2015. This can be considered an indicator of reasonable cost-effectiveness. The cost per child is expected to decrease as the numbers of schools and of pupils enrolled increase, and as state funding partially replaces DFID funding.

Assessment of whether the programme continues to represent value for money

There are some positive results and benefits of the ESSPIN programme, notably in state level capability, in school quality, in headteacher effectiveness, in SBMC functionality, and in social inclusion. There are also less positive results, particularly in local government capacity, in teaching skills, and in learning outcomes. The Composite Survey showed such limited improvements in teacher competence and in pupils’ learning, even in ‘ESSPIN schools’, that most children do not properly acquire the basic skills of literacy and numeracy, which are so fundamental to all subsequent learning. CS2 has clearly raised doubts during the past year regarding the overall Value for Money achieved in terms of learning outcomes through the School Improvement Programme. But the conclusion of this VfM assessment, as part of the 2015 AR, is that significant gains have been achieved at reasonable cost and that ESSPIN continues to represent good value for money for DFID.
Quality of financial management
Expenditure on the programme is monitored and reported quarterly, and in annual reports. Expenditure during the past year, and over the lifetime of the project, has been close to the budgeted figures. There is a good track record of sound financial management.

Recommendations

1. Consider using additional system wide indicators of economy (such as the average cost of a teacher’s salary, of a primary textbook, or of one child in school for a year) and of efficiency (such as grade repetition and primary completion rates, and pupil:teacher and pupil:classroom ratios) .
2. Consider making more comparisons of unit costs in ESSPIN and the SIP with other education projects in Nigeria and other countries (using standard UNESCO indicators).
3. IMEP to compare consultancy fees and overhead costs in the final evaluation of the suite of DFIDN’s State-Level Programmes.

Date of last narrative financial report
Date of last audited annual statement

E: RISK (½ page)

Overall risk rating: Medium (Unchanged)

Overview of programme risk

The key elements of programme risk for ESSPIN are:

- Failure of States to maximise the use of available Federal funds (UBEC IF and TPD) in pursuit of school improvement
- In the aftermath of the 2015 elections, a raft of new senior State-level appointments in the education sector, bringing with them uncertainty about priorities
- On-going uncertainties over different aspects of insecurity and conflict, particularly in some Northern States
- The low global price of oil over the past year, and the implications for FGN revenues and for state budget allocations
- Extremely low levels of teacher subject knowledge, literacy levels and skills at the outset of the programme (evidenced by TDNA reports)

The management of security-related risk, on behalf of ESSPIN personnel, remains of a high standard.

The failure of some focus states to access all of the Federal funds available to them has been documented under Output 1. This could be seen as a weakness of prioritisation in respect of investment in basic education and school improvement. This appears to be the case, with potentially serious implications for ESSPIN’s programme of school improvement going forward, and to the strength of State commitment to the enterprise beyond 2017.

Since the 2015 election results were announced, there has been a steady replacement of senior officials at all levels of the State education structures: Education Secretaries at LGEAs; Chairman and Executive Secretary at SUBEB; Commissioners for Education at MoE. Some of these are not yet in place at the time of the 2015 review (October). This has created a significant new political agenda for ESSPIN, to which it has responded with smartness. In several states it was able to contribute to hand-over notes and to transition committees. In Kaduna it has been involved in the restructuring of LGEAs, including writing job descriptions and interview processes for Education Secretaries. In the three Northern States, relationships between the State Teams and the new Education Commissioners are excellent. The support of DFID State Representatives and SPARC/SAVI personnel adds significant value to relationships.

The Boko Haram insurgency has not impacted directly on the delivery of primary schooling in the focus states, although it has created additional logistical difficulties. What has resulted is a significant increase in the numbers of pupils in primary schools, resulting from IDPs moving into states like Jigawa. There is continuing communal strife between pastoralists and farmers, particularly in Jigawa and Kaduna, but also affecting other states. Some schools in Kaduna were temporarily used as hostels for IDPs.

Outstanding actions from risk assessment

There needs to be continued ESSPIN alertness to possible tensions with the very large numbers of Islamic schools which sit outside the main government system in states like Kano, Kaduna and Jigawa. In numbers, they far exceed the public primary school provision. The ESSPIN pilots with IQTE are progressing well but they remain small in scale, except in Kano.
The low levels of pedagogical skills and teacher competency call for greater attention to be paid to teacher training, both pre-service and in-service, and to the potential role of headteachers in providing more direct supervision and support to classroom teachers.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The project is on track to deliver according to the agreed timeframe.

Performance of partnership (s)

Cambridge Education - Mott MacDonald has performed strongly as the lead partner of the ESSPIN consortium which includes the British Council, Oxford Policy Management, Save the Children, and Social Development Direct. Their last contract performance review in April 2015 as part of the key supplier management process assessed their performance at 74%, under the category described as “Delivery criteria being efficiently and effectively met in line with contractual and customer expectations”.

Asset monitoring and control

Programme funded assets are all fully recorded in the assets register maintained by Cambridge Education – Mott MacDonald which is updated on a regular basis to reflect additions and disposals during the year as authorised by DFID. An assets verification exercise in Abuja and the six focal states is usually conducted as part of programme financial audit exercise. The 2015 financial audit is ongoing at the time of this Annual Review and the final report is due out in early 2016.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The Partnership Principles were not considered within the project extension business case. In September 2014, DFID Nigeria conducted an assessment of the FGN commitment to the Partnership Principles which reconfirmed the UK’s declared policy that that no UK aid money should go directly to the Government of Nigeria: as an anti-corruption measure and to avoid substituting for the country’s own resources. ESSPIN is consistent with this policy. As the programme is delivered directly by an implementing partner with no funding through government channels, the Partnership Principles are not relevant for the direct management and monitoring of this project. However to attain impact and sustainability ESSPIN needs to leverage government resources and ensure that project interventions are scaled up through government systems.

Following the turbulence caused by the 2015 elections, it is appropriate to reiterate the point made in the 2014 Annual Review in relation to the extent of commitment of State governments to reducing poverty and attaining the MDGs, to strengthening financial management and minimizing corruption, and to strengthening domestic accountability when determining the level of investment that the programme makes in each State, with greater resources directed to those States that demonstrate greater commitment to the partnership principles. Specifically, as previously detailed in the text of Output 1, the extent to which a State prioritises investment in basic education, as indicated by its providing matching funds in order to access the UBEC Implementation Fund (IF) should inform ESSPIN’s response, as with its prompt retiral of spend on the first tranche of the UBEC TPD fund in order to access the second tranche.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

ESSPIN has updated its logframe and set new milestones for 2015 and targets for 2016. Weaknesses identified in the 2014 Annual Review have been addressed. Targets and results have been disaggregated by state wherever appropriate. The logframe is comprehensive and complex, and valuable as a monitoring tool, but frequent changes in indicators and targets are not always helpful for tracking progress over time on a consistent basis. The ESSPIN Annual Report records that 97 of the 125 targets (78%) set for 2015 have been met or exceeded.

Three successive rounds of the Composite Survey (in 2012, 2014 and 2016) constitute a more robust means of assessment and evaluation of improvements in teaching and learning over time. CS2 revealed that standards are deteriorating overall, but 'ESSPIN schools' are doing better than ‘non-ESSPIN schools’ in almost all respects. This distinction becomes more challenging as all schools in some states, and most schools in others, are now involved in the School Improvement Programme pioneered by ESSPIN, but increasingly ‘owned’ by the states themselves. This will make comparisons between ESSPIN and other schools more problematic in future, particularly in CS3.

Internal monitoring in ESSPIN and the SIP, and for government, relies on routine data collected by SSOs and SMOs and on various ‘self-assessment’ exercises. External monitoring of the more independent and robust sort typified by the Composite Surveys tends to yield less positive reported results. Both are valid and valuable as M&E tools, and serve somewhat different purposes.

IMEP’s view on evidence and data is that the variability in the data from the different sources of evidence (eg. CS2, SSO and SMO reports, and Self-Assessments) means that caution is required when interpreting the data and drawing conclusions. As noted by the Annual Review team, there is an uncertain picture on how many teachers are ‘competent’, headteachers are ‘effective’, and how many SBMCs are truly ‘functional’ in each state. This has important impact on assumptions and on how to address the need to improve learning outcomes. The Composite Survey is a rigorous method for collecting data and should be given due attention – CS3 results will be an important source of data and evidence in 2016.

Monitoring progress throughout the review period

This Annual Review was conducted by a team of six people, including national and international consultants, plus staff of IMEP and the NPC. It involved field visits to schools and offices in all six states, interviews and meetings with a wide range of stakeholders, and a critical review of the large number of documents and reports.

It is recommended that, since ESSPIN may be extended to mid-2017, another AR or a light touch review may be required in late 2016, before a PCR in 2017 and any possible post-project evaluation.