Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Supporting Economic Transformation
Programme Value: £4.467m		Review Date: 18 December 2015
Programme Code:	Start Date: 18/11/14	End Date: 31/7/2018

Summary of Programme Performance
Year
Programme Score
Risk Rating

Summary of progress and lessons learnt since last review

This is the first annual review of the SET programme. Most outputs have progressed as anticipated with the only delays being agreed with DFID. There is also early indication of impact.

In the first year, ODI have progressed or completed all outputs as per the logframe. These include: analyses on Nigeria, Tanzania and Kenya involving significant stakeholder engagement (substantively completed), work on data for analysing economic transformation (completed and to be deepened during implementation phase) and anchor and baseline papers (first drafts received, now being finalised). A number of successful events have been held in UK, Tanzania and Nairobi, including a high profile seminar and workshop with Dani Rodrik in June 2015.

The quality of ODI’s engagement with stakeholders has been high; they have brokered excellent opportunities with DFID Nigeria, the Planning Commission in Tanzania and with a set of actors involved in services in Kenya and India (including private sector). The inception phase was extended to give time to strengthen drafts of reports of these engagements and the anchor paper, drawing on the depth of ODI expertise and their partners.

The only output not to be progressed as originally anticipated is the Comms strategy which DFID has asked ODI delay until the inception phase is concluded. Substantial inputs have been made on the data portal component, although DFID has also asked that a full launch of this platform also await the implementation phase.

At the annual review stage, there is progress against outcomes. Work in Nigeria has supported DFID’s Inclusive Growth Diagnostic, informed WB & DFID discussions on approach to economic development and resulted in policy notes that have been shared with the new Government. In Tanzania, ODI has supported the Ministry of Planning strengthen its next 5 year plan. Work in Tanzania and in Kenya has been engaged a range of stakeholders. The Rodrik event had good press coverage on the topic of economic transformation.

There is a strong pipeline of work going forward, including working with the Africa Centre for Economic Transformation, with DFID Burma on the role of China in Burma’s economic transformation and on trade policy with DFID/BIS Trade Policy Unit. There is unmet demand for work under the programme in an implementation phase.

Summary of recommendations for the next year

Recommendations for next year are:

- Focus on getting high quality reports of SET activities and start putting these into the public domain (April 2016)
- Deepen and expand work with partners, including from developing countries (Ongoing)
- ODI to draw on a broader set of internal and external resources including on political economy (Ongoing)
- Once the implementation phase starts (from May 2016):
  - increase the number of engagements with DFID depts, governments and other donor partners;
  - develop and implement a light touch comms strategy;
  - launch the data website/portal with a good VFM solution for its design and maintenance

The work plan to April 2016 provides good opportunity to act on these recommendations.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	204254
DevTracker Link to Log frame:	204254

The Supporting Economic Transformation project (SET) is is a 4 year Accountable Grant, to support DFID and development partners respond on economic transformation. It locks together country level policy and advisory work, high quality policy analysis, support to DFID growth diagnostics, knowledge and learning management and communications on economic transformation.

It has three interdependent outputs:
(a)	Policy advice to DFID, governments and other development partners
- Support to DFID country offices and central departments with analysis to inform policy and programme work
- Analysis to help understand potential patterns of transformation and how to orient policies and programmes to unlock this potential;
- Support to country governements on strategies to accelerate economic transformation
- In-depth and comparative analyses focused on specific issues proposed by DFID and other partners
- Periodic anchor papers on major economic transformation issues

(b)	Promoting economic data for transformation including a portal to sources of data bases on economic transformation (housed in various IFIs and academic institutions) and new analyses based on these sources including that undertaken in component 1; and

(c)	A communication component to promote evidence from the programme and important policy issues on the quality of growth processes.

3.	Economic transformation is essential for creating jobs and raising incomes in developing countries on an adequate scale. At present only 16% of work in DFID countries is in waged employment in modern, productive sectors. The bulk of people work in unproductive or subsistence work in rural and urban areas. Changing this picture significantly even by 2030 would require accelerated economic transformation. There are opportunities for significant improvements in patterns of inclusive growth if resources were to reallocate between sectors and to higher value techniques in existing sectors.

3.	This intervention is intended help to bridge the gap between DFID’s aspirations on transformation, and the practical actions needed to achieve change. Analyses under SET will inform policy dialogue with partner governments, help shape economic development portfolios and contribute to new growth and poverty diagnostics by DFID and those undertaken by governments and other donors.

4. in terms of the external environment, since the approval of the Business Case, the SDGs have now been agreed with a strong transformation focus: Goal 8 includes ‘Achieve higher levels of economic productivity through diversification, technological upgrading and innovation, including through a focus on high-value added and labour-intensive sectors; and Goal 9 concerns about industrialisation, manufacturing, firm growth and high value agriculture. African governments were especially keen on Goal 9, which shows the relevance of the objectives of this programme.

5. Internally within DFID, the Inclusive Growth Diagnostics were done by country offices and regional departments between end-2014 and mid-2015. The Concept Note for the IGDs invited offices to think about opportunities for ‘transformational growth’ including higher value agriculture, services and manufacturing. The guidance also required thinking about the political economy of economic development strategies. SET engagements helped some country offices with there analyses and may have contributed to a higher demand for support from SET than can be met at this early stage.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome Title	DFID , governments and other donors design and implement economic development investments to foster structural economic transformation in order to give rise to stronger, more inclusive growth and poverty reduction in the long term.

Indicators	Milestone (2015)	Progress
1.1 Number of DFID country portfolios influenced by SET research and advice, in design or delivery	1 by October 2015	Expectations substantially exceeded. SET has indirectly influenced the portfolios for DFID (Nigeria and Tanzania and to some extent Kenya).A meeting in Abuja and contributions to a World Bank Conference in Paris has facilitated thinking in DFID and WB on both institutions’ economic development investments. / SET is helping to shape DFID Tanzania’s economic development programme, through work done with the President’s Office Planning Commission (POPC). DFID Tanzania staff attended a workshop convened by SET with the POPC on the Second Five Year Development Plan (FYDP II). / The ‘Supporting Economic Transformation in Nigeria’ paper influenced DFID Nigeria’s Inclusive Growth Diagnostic (IGD). SET has also assisted three other DFID COs with IGDs (Occupied Palestinian States, Kenya, Tanzania).
1.2 Number of DFID centrally managed programmes influenced by SET research and advice.	1 by October 2015	Expectations moderately not met. Too early for evidence of influence, but SET has written a briefing on trade and economic transformation for DFID’s Trade Policy Unit (TPU). Research is underway on three agreed research themes and is likely to help future programming of TPU. Positive feedback was received on the work provided, but at this early stage it is too early to see the impact of this support.Members of DFID TPU also attended an event hosted by SET at ODI on 2 July on trade and global value chains. TPU also provided positive feedback on SET services data.

Outcome Title	2. Private sector and business engaged on the role of economic transformation in policy dialogue. Better coordination between firms on economic transformation dialogue.

2.1 (i) Policy processes influenced by private sector participation / (ii) Private sector firms/associations operations/plans influenced by interaction with the SET programme	1 case by October 2015	(i) Expectations met. The Tanzania Private Sector Foundation was consulted on the Phase 1 report. A public consultation/workshop was held in October 2015 on the government of Tanzania’s Five Year Development Plan II with public and private sector stakeholders to discuss sectoral prioritisation. Unlike the first FYDP this involved private sector actors, including the Tanzania Private Sector Foundation (TPSF) who were also interviewed prior to and contributed to the workshop. / (ii) Expectations met. The workshop in Nairobi on 28 April 2015 - “Kenya as a services hub: The role of services in economic transformation” - involved public and private sector stakeholders discussing services and government policy to boost Kenyan private sector services. Following the workshop 70% of participants said it was likely/very likely to influence their future work.

Outcome Title	Better global knowledge on how policies can support growth by accelerating economic transformation

3.1 SET programme demonstrates it is a centre for knowledge on economic transformation by the global community (NGOs, thinktanks, academia).	Develop baseline on ET by June 2015	Expectations met. A baseline containing stakeholder views on economic transformation was developed (in draft form) in June 2015. SET has engaged with a number of centres of expertise and international experts on data. These include Harvard University, the IMF, the World Bank, University of Groningen, ACET, New Climate Economy (NCE) and local think tanks such as REPOA and CSAE. Also several blogs have been written for SET by international experts, such as Gaaitzen de Vries, Morten Jerven and Pedro Martins. Following a lecture by Dani Rodrik on 23rd June a number of blogs mentioned the event including Oxfam, the Financial Times and South East Asia Globe. / An anchor report on economic transformation is being finalised and shared with DFID for comments. / ODI has hosted excellent events (such as the Rodrik seminar) and in Nairobi which have attracted significant academic, civil society, government and press attention. Along with a strong webisite, this event capability provides a good platform for communicating impact of SET in the future.

Overall Outcome score and description

A – met expectations

Key lessons

The SET programme is proving to be highly relevant at the country office level and there is strong interest from at least one central department (Trade Policy Unit). There is sufficient demand from country offices for further work and SET has now begun work for a paper to support DFID Burma (with an interest from DFID China). It has aslo scoped demand from DFID country offices in Ethiopia, India and Uganda.

The programme is assessed as performing well, given the progress made to influence country portfolios. Over the next year, the SET programme needs to address the milestone that moderately did not meet expectations and, in meeting other milestones, have even greater impact. Initial progress is being made in influencing DFID’s central programmes and policy making and influencing the private sector, but more is needed. Going forward into the implementation phase, it will be of particular importance that SET should make better progress in becoming a centre of knowledge on economic transformation and be able to demonstrate its added value in the international architecture.

Key actions

Finalised reports of excellent quality need to be disseminated within DFID and also with development partners. The communications strategy will need to agreed with DFID, conditional on SET progressing to the Implementation phase.

The expectation is that research underway for DFID’s Trade Policy Unit will influence future planning and SET can provide excellent reports generally.

Evidence that measures how SET has successfully influenced the private sector needs to be agreed.

Has the logframe been updated since the last review?

Not applicable. This is the first annual review of the programme.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Policy advice to DFID, governments and other development partners.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	70%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
1.1 DFID country offices and central departments policies and programmes supported by SET research outputs, including support with growth diagnostics;	2 country offices by June 2015 / 1 central department by December 2015	Output moderately exceeded expectations / DFID Nigeria (programming) / DFID Tanzania (government support research, IGD) / DFID Trade Policy Unit (research) and GRD / DFID Occupied Palestinian States, Nigeria, Uganda, Tanzania (IGDs)
1.2 Support to country governments on strategies to accelerate economic transformation.	1 country govt by June 2015	Output moderately exceeded expectations / Tanzania Planning Commission (POPC) plus Zanzibar Planning Commission (ZPC) / Nepal Parliamentary Committee on Water Resources / Kenya Vision 2030 Delivery Secretariat
1.3 In-depth and comparative analyses focused on specific issues proposed by DFID and other partners	1 comparative analysis by October 2015	Output moderately exceeded expectations / Paper: the role of services in economic transformation (final paper in draft form, background paper for conference available online) / Paper: supporting economic transformation anchor paper (currently in draft form) / Paper: gender and economic transformation, available online. / Paper: trade policy and economic transformation, available online.

Key Points

DFID Tanzania confirmed that the programme is doing important work with the Tanzanian Planning Commission in producing a strong 5 year plan and the SET programme has helped open doors to an institution that DFID/UK has had little contact with to date.

DFID Nigeria thought SET’s high level macro paper on structural transformation was highly relevant and their work on strategic options informed DFID Nigeria’s thinking on the internal growth diagnostic (IGD). A policy brief has been shared with Ministers of Agriculture and of Trade and Investment. The brief has been published online which was retweeted by Former Nigerian Finance Minister Dr Ngozi Okonjo-Iweala. Experts were engaged from international and local expertise (e.g. Danny Leipziger and CSEA). DFID Kenya thought the quality of SET’s paper on Kenya as a service hub was of good quality and their thinking on the IGD was informed. SET looks highly relevant and there is strong CO interest.

However, feedback from DFID Nepal on SET’s work directly with the government on hydropower was less positive. It found the quality of reporting to government presented was not well thought-out and so missed an opportunity for stronger impact. This engagement was also not a good fit with SET objectives as the topic was not sufficiently about transformation – rather about unlocking a major constraint to growth.

ODI has shown that it can respond to requests, assemble good teams with internal and external resources and deliver tailored products and advice within short time frames (e.g. within 6 months). But more time needs to be taken, in order to get the TORs, team and required outputs right at the outset. SET can really contribute to other DFID centrally managed programmes and country offices in a new way if this initial discussion is got right.

Following the engagement with the Tanzania Planning Commission, a request has come to the SET team to support the President Delivery Bureau (PDB) with the Big Results Now (BRN) policy initiative, coordinated through the DFID Tanzania office.

ODI has engaged an international expert on gender dynamics in economic transformation. Following comments from DFID Central Departments and ODI gender experts, a final paper has been produced and published online. This paper was also presented at the United Nations University UNU-Wider and is being taken forward in the case of Tanzania.

In October 2015 it was confirmed that SET would be working with ACET on a number of joint papers for the first Africa Transformation Forum in Kigali, March 2016. Work has also begun on a paper with the New Climate Economy programme (NCE).

SET engagements were useful for DFID country offices in preparing their IGDs in Occupied Palestinian States, Nigeria, Uganda Tanzania and Kenya.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable

Recommendations

That all activities should have a sponsoring DFID department that agrees the TORs, team etc. This doesn’t mean that ODI cannot broker oppportunities with government directly – they should and we are seeing the value of this. The Tanzania approach and the discussions that went into the revised work plan to the end of the implementation phase reflects a good approach going forward.

The quality of ODI’s reports needs to improve. ODI need to have the capacity to draft excellently, bringing together different outputs where there are several authors. Reports should be drawn together coherently and not feel as if they have multiple authors and different analyses.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Data portal to promote better use of economic data in analysis on economic transformation and a website for sharing knowledge
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?

Indicator(s)	Milestones	Progress
2.1 Quality of portal	Portal live by December 2015.	Expectations met / Simple portal launched / In discussion with DFID on the development of a more complex data portal post 2016

Key Points

A SET data portal with economic transformation data for 27 countries and blogs by data experts has been included on the SET website. Data was produced in partnership with a wide range of organisations included Harvard University, the World Bank, Groningen University and the IMF. Data has been used to inform several DFID Country Office IDGs. It has also been used for a comment in a Financial Times article.

Discussions with DFID, the ODI communications department and SET central management teams led to a decision for a more complex data portal. There has been work done with external development agencies to develop various options for the development of a more interactive data portal and has been put on hold until after April 2016. The existing data and statistics part of the website has been produced as a simple series of webpages.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable

Recommendations

The way forward on the data website/portal will be agreed as the project moves to the implementation phase. Different options in terms of functionality of the portal have different set-up and ongoing costs that will be assessed for VFM.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Implementation of a communication strategy including events to promote understanding of economic transformation.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	A

Indicator(s)	Milestones	Progress
3.1 Development and implementation of communication strategy	Development of communication strategy by June / Setup of website	Moderately did not meet expectations / SET website developed / Guidance from DFID in June 2015 to not include a communications strategy in the inception report, new date for communications strategy tbc however SET has implemented several parts of the draft strategy with DFID approval.
3.2 Results of multi-event assessment tool show good responses from participants	7 out of 10 people surveyed rated the event as 'good' and higher	Moderately exceeded expectations / Quarterly reports provide details on strong positive feedback from all events held by SET so far (all above 70%). / Examples include feedback from Rodrik event in June - 96% respondents agreed or strongly agreed the presentations were engaging and data workshop in January - 100% respondents felt the quality of presentations and discussions was excellent / very good.
3.3 Uptake of SET products (including anchor papers, themed papers, comparative analyses) by the global community, including via the media	1 Case	Moderately exceeded expectations / International Commonwealth Parliamentarians meeting included transformation work / An article on SET included in TPU Trade Think Tank Open Ideas Meeting background notes / 7 cases of SET events in online media, 5 cases in print media / 2 cases of SET data being used in media (Financial Times and South East Asia Globe article)

Key Points

A draft communications strategy for SET has been developed and DFID advised that this could be finalised at a later date. However, significant progress has been made towards the draft strategy:

- Branding: SET logo is in use.
- Website: A specification for the website was developed, agreed with DFID Communications Department, commissioned and SET supervised a website developer. Google analytics data shows over 500 users on the website from over 75 countries. Data shows 150 downloads from the website. This is reasonable performance given the website was launched in late July 2015.
- Data portal: A specification was developed for a data portal, and agreed with DFID. Data has been developed and published online in a simple portal on the SET website. The SET team have invited bids for further development of the data portal which has been postponed until after the inceptin phase (April 2016)
- Social media: Twitter account active and regularly tweeting/being re-tweeted on SET materials and general economic transformation.
- Public events: SET has hosted high quality public events and closed roundtables during the Inception Phase. There have been public workshops in Nairobi and London, including high level speakers such as Dani Rodrik and Morten Jerven

Given that SET is in the relatively early stages of the programme (and has been slowed down for two months during the extended Inception Phase), it has already generated a strong interest in the public space for knowledge and awareness of how policies can help accelerate economic transformation.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable.

Recommendations

The next draft of the communications strategy should consider how to develop the website further, implement a public relations strategy and finalise key messages for the programme. These should be in line with the core SET offer to DFID, currently under discussion. This should be finalised by end of Inception phase and the data portal strategy should be finalised at the same time.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The table below shows a breakdown of the costs for the SET programme for Year 1. An update on major activities involving major budget decisions is sent to the DFID programme management team ahead of monthly meetings to ensure VFM can be monitored.

	FY14-15 Q3	FY14-15 Q4	FY15-16 Q1	FY15-16 Q2
0 Core costs	£15,750.00	£27,100.00	£31,500.00	£31,500.00
1 Policy Advice and Research Support	£22,387.00	£128,492.00	£150,844.73	£51,310.88
2 SET Portal website	-	£9,779.40	£720.00	£4,889.14
3 Networking / Public Affairs	£2,376.88	£2,576.42	£14,577.35	£12,696.10
Total	£40,513.88	£167,947.82	£197,642.08	£100,396.12

Total spend to end of FY 2015-16 Q2: £506,499.90

Number of outputs: 65

Total value of outputs according to average cost in VfM proposition in business case: £681,115

The total spend to date to produce 65 outputs is significantly lower than the cost compared to the average costs outlined in the DFID business case (around 25% less).

Benchmark fee rates are used which offer good value for money for ODI researchers. The programme has demonstrated value for money by making use of synergies between data portal development, country work and advice.

Role	Level	Average Daily Rate	Equivalent call down rates for EPS PEAKS
Super specialist	RF3	£850	£825-£985
Principle researcher / Consultant	RF2	£755	£605-£875
Senior researcher / Consultant	RF1	£650	£430-£655
Research Officer / Junior Researcher	RO	£552

Output type	Number of outputs	Outputs to date
Policy brief	2	Nigeria briefing / Tanzania policy summary
Indepth /comparative analysis sector/thematic analysis	3	Services draft / TPU paper / Gender and ET
Full policy report/note/Working Paper	4	Nigeria long paper / Tanzania draft paper / Hydropower and ET in Nepal / Data sources and methods
Case study	1	Nigeria Booth paper
Blog/opinion piece	9	6 blogs on SET website / IFC / BFP / FT piece
Other (written) output	34	Tanzania workshop report / Tanzania workshop paper / Data workshop report / Baseline report / Chinese SEZs in Africa / Morten Jerven report / G20 and ET, by UNDP / Using social accounting matrix / 26 data country files in word and excel (more databases online)
Public event	4	Kenya services / Rodrik public event / Jerven event / Turner event
Other event e.g. workshop/roundtable	6	Trade in value chains / Tanzania FYDPII / Rodrik roundtable / Chinese SEZs in Africa / Gender and ET workshop / Data workshop January
(ODI participation in) external events to disseminate policy findings	2	CDC in Sept 2015 / CPA in Nov 2014

Assessment of whether the programme continues to represent value for money

Analysis of the cost drivers above show that the project delivers good value for money.

Economy: At the input level, unit costs are shown to be acceptable by the benchmarking fee rate exercise that ODI has undertaken.

Efficiency: At the output level, the challenge for ODI is to ensure that costs for each output are minimised and quality maximised on research products and the quality of final reports delivered, which needs to be brought up to an excellent standard. DFID and ODI are managing this by discussing TORs, team composition and purpose of assignments in more depth. These discussions should benefit from lessons learnt, including getting clarity on the outputs of each assignment and ensuring time is built into allow different authors contributions to be brought together into a single, coherent report.

Cost effectiveness: There is early evidence that the programme has been cost effective by getting traction on policies and programmes of far higher value (e.g. working with the Preseident’s Office Planning Commission in Tanzania on the second Five Year Development Plan). By the second Annual Review it should be possible to assess the impact of SET outputs and to make comparisons with similar interventions (e.g. the International Growth Centre). Assessing VFM for these types of assessments will require comparators across other programmes in DFID that are delivering policy change through application of evidence, new analysis and policy dialogue.

Quality of financial management

The quality of financial reporting has been satisfactory and there have been no issues to date with invoices submitted. Best value for money is discussed with DFID during programme management meetings (e.g for the development of the SET website and sponsoring events). Updated spending forecasts can be slow to arrive (e.g. for up to the end of this financial year) and ODI should ensure these are sent when significant changes are likely.

Date of last narrative financial report	October 2015
Date of last audited annual statement	31 March 2015

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

The main risks highlighted in the Business Case were as follows:

ODI analysis/policy advice is not aligned with with DFID and partner govrnments requirements (Medium)

There was instance where the DFID Nepal office felt its comments were overlooked. This risk has been managed by ensuring DFID offices and teams for all assignments (including those where ODI work to government) are consulted on the TORs.

ODI’s policy advice and analysis is not implemented by DFID country offices and partner governments (Medium)

The quality and relevance of advice is critical for this as well as strong stakeholder engagement throughout assignments. The relevance of advice is good but the quality of reports up to August 2015 was mixed and we have discussed this with ODI, who have responded to our concern. Progression to the project implementation phase would be dependent on the delivery of excellent reports.

Giving ODI the flexibility to continue engagements may prove to be important in some cases, in order to get traction on policies and programmes; SET has provision for extending engagements if this will be VFM and help convert analysis into real change.

ODI’s communication strategy is not effective (Medium)

The communication strategy will be finalised and put into practice when the implementation phase starts.

ODI’s on-line web portal is not good and receives few unique visitors (Medium)

The online data website/portal will go live when the implementation phase starts. The final functionality and design will be informed by analysis of who the target users need to be.

Outstanding actions from risk assessment

Ensure all engagements have a lead or sponsoring department in DFID that agrees TORs and teams

Increase clarity on how quality of engagements will be assessed (i.e. asking lead departments ‘would you recommend SET for another country/government’)

Allow flexibility to extend duration of engagements where this will be good VFM to achieve a real change.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

SET is on track to deliver outputs and meet milestones within agreed timeframes. Given the high demand for SET services, a number of activities and discussions have been postponed until the Implementation Phase and as highlighted in the Inception Phase report and discussed with DFID. There may be a case to expand the core management team during the Implementation Phase due to level of demand for SET outputs.

Performance of partnership

ODI is delivering against six-monthly workplans, agreed with DFID, setting-out the key project activities and deliverables. Following some concerns identified during the review of the first six months, the second workplan (October 2015 – April 2016) was formally ageed to monitor the quality of final reports delivered to DFID, ensure the ODI was using of a broad range of technical experts and to clarify SET’s core offer to DFID. ODI has been very receptive to DFID’s feedback on performance, continues to make good progress and the partnership is working well. The latest workplan will be used to assess whether we progress to full implementation, when the project will be managed by a Steering Committee.

Asset monitoring and control

There are no DFID assets held by this project.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not relevant.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The Business Case includes a budget for an evaluation. An evaluation process should be set up at the beginning of the implementation phase to assess impact independently.

Monitoring progress throughout the review period

ODI and DFID meet monthly to monitor progress against the six-monthly workplan, discuss any issues and agree going forward. Narrative and financial reports are submitted to DFID quarterly. Progress is reviewed by requesting feedback from 1) DFID offices by GRD; 2) ODI seeking feedback continually from SET stakeholders.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process