## LOGFRAME
PROJECT NAME | SCIENCE FOR HUMANITARIAN EMERGENCIES AND RESILIENCE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (Nov 2016) | Milestone 3 (Nov 2017) | Milestone 4 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+) | Assumptions
Greater and more effective investment in disaster resilience, preparedness, response and recovery, leading to reduced impacts from natural disaster | Number of policies, plans and investments informed by the improved risk information and tools, supported by capacity development. | Planned | Low level of use of risk information and tools in decision making | Programme on track to deliver impact - SHEAR Apps commissioning high-quality projects with strong user engagement and reflecting a good understanding of user needs. | Evidence of the use of data, tools and products commissioned by SHEAR Apps to inform disaster risk management and adaptation policies, plans and investments from SHEAR in at least 3 DFID priority countries, documented in deep-dive impact case studies. SHEAR Research Pilot case studies initiated working with at least 12 users across 4 countries | SHEAR Research: Users from 4 countries involved in co-design of products. Pilot case studies developed to faciliate co-production and demonstration. Effective impact monitoring strategy in place. | SHEAR Research: Interim evaluation of impact reports projects are on track. Briefing on learning in co-production finalised. | SHEAR Research: At least four pilot studies of application of SHEAR outputs in planning, policymaking and investments | SHEAR Research + SHEAR Apps: Enhanced understanding of risk applied within planning and investment processes in at least 4 countries | Decisions based on improved data, knowledge and products lead to ‘better’ decisions that reduce the risks from natural hazards
Achieved
Source
SHEAR Apps Monitoring and Evaluation Study (3 deep-dive case studies + self assessments from 10+ projects); SHEAR Research Impacts Monitoring
| Impact Indicator 2 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (Nov 2016) | Milestone 3 (Nov 2017) | Milestone 4 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+) | Assumptions
| Operational systems utilising SHEAR improved forecasting and risk monitoring methods, data and tools. | Planned | 0 | None [This component of SHEAR is not operational until June 2016] | SHEAR Research on track to deliver impact through commissioning at least two projects on forecasting and risk monitoring; all of which involve stakeholders in co-production of systems. | Development of sub-seasonal and seasonal forecasting products for drought and flood co-designed with users | Users from 4 countries, NGOs and international donors/multilaterals engaged in co-design and testing new products and tools | At least two pilot studies of operational use of SHEAR outputs | At least two operational systems activitly using outputs from SHEAR | Decisions based on improved data, knowledge and products lead to ‘better’ decisions that reduce the risks from natural hazards
Achieved
Source
SHEAR Apps Monitoring and Evaluation Study (3 deep-dive case studies + self assessments from 10+ projects); SHEAR Research Impacts Monitoring
OUTCOME | Outcome Indicator 1 [SHEAR Apps] |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (Nov 2016) | Target (Nov 2017) |  |  |  | Assumptions
New high quality and relevant data and tools accessed by decision makers and applied in practice (& established processes and partnerships toward greater accessibility and availability of data and tools to support resilience in developing countries) | (a) Number of decision makers accessing and using SHEAR applicants products, data and tools; (b) % success rate in first round challenge fund = % of projects that lead to a useable and used tool in first round; (c) tools available on open platform; (d) # downloads of data and tools | Planned | 0 | SHEAR Apps commissioned 3-6 co-designed, co-developed projects targetted at informing real DRR challenges (at least 50% in DFID priority countries). | SHEAR Apps: (a) 20 beneficiaries involved co-developed of tools and accessing these regularly.(b) at least 50% success rate in phase 1 (c) Tools are openly available to the broader user community on an appropriate platform and training provided by project teams. | SHEAR Apps (a) Evidence of data and tools being accessed by decision makers, specifically 20 beneficiaries; (c) Tools are openly available to the broader user community on an appropriate platform and training provided by project teams; (d) for 5 top projects at least 2 downloads per month from users of data and/or tools. | SHEAR Apps ends in December 2016 | n/a | n/a | Challenge fund projects deliver demand-led products and tools and engage users in co-production process. Projects make products available to the right people who have the capacity and demand to use them
Achieved
Source
|  |  | SHEAR Apps Progress report and Final report; project self-assessments and deep-dive case studies |  | SHEAR Research M&E Reports
| Outcome Indicator 2 [SHEAR Apps] |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (Nov 2016) | Target (Nov 2017)
| Number of partnerships established, joint publications and documented follow-on activities | Planned | 0 | SHEAR Apps: Established concensus on shared vision and partnerships through the production of the high-profile report | SHEAR Apps: Establish two private/public partnerships driving a major open data for resilience platform initiative. Delivery of a pilot open platform/interface. | Strengthened open data for resilience initiative including through establishing key partnerships and community of practice around open data for resilience. Delivery of recommendations set out in the report.
Achieved
Source
project documents
| Outcome Indicator 3 [SHEAR Research] |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (Nov 2016) | Milestone 3 (Nov 2017) | Milestone 4 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
| (a) At least 30 decision makers accessing and utilising SHEAR outputs; (b) demonstrated value of information through case studies and research | Planned | Low availability and accessibility of risk information and tools | None [Component not operational until June 2016] | Well targetted projects are funded with right mix of expertise and stakeholder links. User needs analysis underway. | Target users, research and engagement methodologies and pilot studies devised. | Tools and products co-designed with users (at least 12 from 4 countries) | Suite of robust, tailored risk info and tools available to all on open platform | High-quality and relevant disaster risk data and tools accessed and used by 30 decision makers
Achieved
Source
project documents
| Outcome Indicator 4 [SHEAR Research] |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (Nov 2016) | Milestone 3 (Nov 2017) | Milestone 4 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
| (a) More reliable sub-seasonal to seasonal forecasts available to users and independently evaluated by an honest broker and applied in practice; (b) new science operationalised in the field and (c) demonstrated value for decision making | Planned | Early warning systems regarded as only 'moderately effective' or 'ineffective' in many developing countries | None [Component not operational until June 2016] | Well targetted projects are funded with right mix of expertise and stakeholder links. User needs analysis underway. | Monitoring, evaluation and learning framework in place to evaluate impact and being applied in case studies. | Trials of new technologies in at least 2 operational systems with robust and independent evaluation | demonstrated value of pilots through improvements to decision making. | More reliable early warning systems and real-time risk monitoring taken up more broadly; Greater confidence in the value of early warning systems to inform action
Achieved
Source
project documents
SHEAR APPLICATIONS (Apps)
OUTPUT 1 [Challenge Fund] | Output Indicator 1.1 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) | Target (Nov 2016) | Assumption
New toolkit of demand-led, open data, tools and products for resilience, preparedness, response and recovery | Number of new datasets and tools developed (including in DFID priority countries) | Planned | 0 | Inception report to DFID by January 2015. Develop and share consultation document on challenge fund and hold 2 open consultation workshops by end of February 2015. Launched challenge fund in March 2015 and first round projects funded by August 2015. At least 10 new datasets and tools in development (50% in DFID priority countries). | First round of challenge fund yields at least 10 new datasets and tools. Second round of challenge fund projects evaluated and funded. | In total, at least ten new datasets and tools developed, with 50% for DFID priority countries | Challenge fund delivers high-quality, demand-led products, data and tools. M&E framework is successful in drawing lessons
Achieved
Source
Programme inception report. Consultation documents. Progress reports. Final project report.
| Output Indicator 1.2 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) | Target (Nov 2016)
Improved capacity of the community to deliver demand-led, co-produced products that have an impact in practice | (a) Number of new partnerships developed across disciplines that support the development of demand-led products; existing (b) % projects with co-design and co-development approach with users |  | 0 | (a) Challenge fund designed to incentivise development of new innovative partnerships and (b) human-centred design of products; 10 beneficiaries involved | (a) 10 new partnerships developed between delivery partners (including 50% local partnership). | (a) 10 new partnerships developed between delivery partners (including 50% local partnership) and (b) 50% of products co-designed and co-developed with users
Achieved
Source
Monitoring and evaluation report
| Output Indicator 1.3 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) | Target (Nov 2016)
Role of gender considered in project design and delivery | Number of project plans considering gender in risk identification, outreach and capacity development plans | Planned | 0 | Inception report lays out gender strategy and challenge fund documentation creates incentives to consider gender | All second round projects considering the role of gender in delivery plans | All second round projects considering the role of gender in implementation
Achieved
Source
Monitoring and evaluation report
| Output Indicator 1.4 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) | Target (Nov 2016)
Improved capacity of target beneficiary users to apply data, products and tools in practice | Number of targetted beneficiaries that receive training during the project | Planned | 0 | 10 during the first round of challenge fund projects. | 20 | 20
Achieved
Source
Monitoring and evaluation report
| Output Indicator 1.5 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) | Target (Nov 2016)
New evidence on what works in developing demand-led data, tools and products to support resilience and demonstrating the value of risk data and tools for decision making. | Evidence on what works and the value of information gathered through M&E and communicated through progress and final reports | Planned | 0 | M&E Framework finalised and applied to first round of challenge fund. Progress report delivered. | Evaluation of first round projects completed and deep-dive case studies of second-round projects in progress using rigorous M&E framework | 3 deep-dive case studies completed documenting project outcomes and impacts and 10 - 20 M&E project-level assessments. Final report communicating examples of value of information for decision making.
Achieved
Source
Project documents
IMPACT WEIGHTING (%) | Output Indicator 1.6 |  |  | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) | Target (Nov 2016)
80% of SHEAR Apps; 20% of SHEAR | Leverage from private sector investment in projects (and other activities related to project) | Planned | 0 | Activities in place to incentivise private sector leverage and system for monitoring established. Projects report on leverage in application and reporting. | £500,000 private sector | £1million private sector
|  | Achieved |  |  |  |  | RISK RATING
Medium
Monitoring and evaluation report
Assumptions
OUTPUT 2 [SCOPING PROJECT] | Output Indicator 2.1 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) | Target (Nov 2016)
Improved understanding user needs, feasibility and roadmap for delivering more accessible and coordinated risk data and tools for developing countries. | Shared vision on the needs of users and roadmap, supportive partnerships and set of recommendations on next steps | Planned | 0 | Convene at least 3 consultation workshops leading to a working group to deliver the report. Publication of high-profile joint report with shared vision on the needs, recommendations and options by November 2015. | Launch of the report and follow-up dissemination activities. Dissemination plan to be delivered by June 2016. | Delivery of a set of recommendations and selected recommendations demonstrated by pilots.
Achieved
Source
project documentation and reports on consultation meetings
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  |  | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) | Target (Nov 2016)
20% of SHEAR Apps; 5% of SHEAR | Demonstration (pilot) activities delivered, informing the long-term roadmap | Planned | 0 | Scoping report on track to deliver recommendations on pilot projects | Deliver at least one demonstration project. | Findings from demonstration project reported.
|  | Achieved |  |  |  |  | RISK RATING
Medium
project documentation
SHEAR Research
OUTPUT 3 (SHEAR Research) | Output Indicator 3.1 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+) | Assumption
Improved understanding of risk and more reliable predictions of hazards like floods, droughts and landslides across SA and SSA, evaluated by ‘honest broker’ | Advances in risk assessment, monitoring and forecasting: new methods, more comprehensive assessments and increased robustness and reliability | Planned | 0 | Research consortia commissioned with strong potential to meet Dfid objectives and strong research plans and methodologies. Big data projects (SHEAR AI) demonstrate potential applications of big data to deliver advances in this area. Nepal and El Nino projects demonstrate advances in monitoring and predicting risks. | 5 working papers | 5 articles submitted and 5 new working papers | 15 articles submitted | At least 20 high-profile academic papers demonstrating advances in risk assessment, monitoring and forecasting | High quality research activities will be implemented on time and will be successful.
Achieved
Source
[MAKE MORE SPECIFIC ON SCIENTIFIC GOALS ONCE PROJECTS COMMISSIONED] |  | Project documents
| Output Indicator 3.2 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
| Improved understanding of multi-hazard risk in two regions (risk maps, multi-hazard risk assessments) | Planned | 0 | Commissioned projects have good range of hazards and locations and strong research methods. Scoping report on use of cat risk modelling in EQ assesssment in Bangladesh delivered by August 2015. Big data projects demonstrate potential applications of big data to strengthen multi-hazard risk assessment. | Research methodologies devised |  | New risk analyses available | More accurate and detailed multi-hazard risk maps and data for Sub-Saharan Africa, particularly for flood and drought; New assessment of risk from ‘cascading’ hazards, like landslides due to flooding and earthquakes in south Asia;
Achieved
Source
Project documents
| Output Indicator 3.3 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
| Greater reliability of sub-seasonal to seasonal forecasts of drought and flood risk across two regions of Sub-Saharan Africa | Planned | Current skill level to be quantified | Commissioned projects are well targetted with strong methodologies. Teams are active in quantifying existing skill and making improvements. SHEAR AI Project on forecast-based finance is effective in demonstrating how seasonal forecasts can trigger humanitarian action. | Quantification of current levels of reliability |  |  | [Agreed monitor for reliability - e.g. skill at 30 days]
Achieved
Source
Project documents
| Output Indicator 3.4 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
| Strengthened systems to track and predict changing risk from natural disasters to enable earlier interventions in two countries | Planned | 0 | Research consortia are well targetted to deliver strengthened systems and to enable earlier intervention. Initial report on forecast-based financing delivered in August 2015 and used to inform future activities. SHEAR AI Big Data project demonstrates potential applications of big data in this area. | Research methodologies devised |  |  | 2 countries benefit from improved systems
Achieved
Source
Project documents
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
35% OF SHEAR | Developing country actively engaged in research projects and SHEAR contributing to capacity development | Planned | 0 | At least 5 developing country research institutions involved in SHEAR research consortia and AI projects | 8 | 10 | 10 | 12
Achieved
Source
Low
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+) | Assumptions
Better understanding what works in getting the right knowledge and tools to the right people in the right way, demonstrated on the ground with impact | New understanding of risk communication and and factors determining the impact of science in disaster resilience and response | Planned | 0 | Consortia have in place strong teams to deliver new insights into risk communication. Learning from SHEAR Apps projects integrated to deliver new understanding. | 2 working papers | 2 submitted, 4 working papers | 8 submitted | At least 10 high quality papers on risk communication and factors determining the impact of science in disaster resilience and response
Achieved
[MAKE MORE SPECIFIC ON SCIENTIFIC GOALS AS PROJECTS ARE FUNDED] |  | Source
Project documents
| Output Indicator 4.2 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
| Four pilot studies co-designing products and tools with users and demonstrating application and impact on the ground |  | 0 | Consortia to deliver at least four pilot projects with good coverage of regions, applications and hazards, strong partnerships and methods. | research and engagement methodologies devised | 4 pilots established and M&E framework in place | 4 pilot studies concluded and initial impact evaluation complete | 4 pilot studies with demonstrable impact
Achieved
Source
| Output Indicator 4.3 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
| New evidence on the value of improvements in risk information and warnings for decision making |  | 0 | SHEAR KM and Consortia devised methods to quantify and demonstrate the value of information to decision making | Initial results from research on value of risk information | Working paper and policy briefing on value of risk information | 3 working papers | 3 peer-reviewed papers
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 4.4 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
30% |  | Planned | 0 | Methods by SHEAR KM to learn from and evaluate co-production activities and implementation started with consortia. | Workshop and initial learning report on best practice | Guidance on best practice and mainstreaming into projects | Demonstration projects | All projects reflect best practice
| Establishing best practice in co-design and co-production and mainstreaming this into all projects | Achieved
|  | Source | [6 empty] | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+) | Assumptions
Effective management of the research programme, including M&E of impact and value for money, and effective management of capacity building opportunities | Number of recommendations by Independent Advisory Group leading to measures taken to improve programme | Planned | 0 | Independent Advisory Group established and providing advice on potential second call for research | 1 | 2 | 3 | 4
Achieved
Source
Panel minutes
| Output Indicator 5.2 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
| Capacity of 30 users enhanced | Planned | 0 | Capacity development strategy finalised and approved | Establish tracking system and target users | 6 users trained% | 20 users trained | 30 users trained%
Achieved
Source
Secretariat
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 1 (Nov 2016) | Milestone 2 (Nov 2017) | Milestone 2 (Nov 2018) | Milestone 3 (Nov 2019) | Target (2019+)
10% | Cross-programme outreach: including briefings, stakeholder workshops | Planned | 0 | SHEAR Knowledge Manager established and working effectively toward approved work plan. | 2 | 4 | 6 | 10 cross programme reports and briefings
Achieved
|  | Source | [6 empty] | RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Note on C103: Helen O'Connor: http://www.whymap.org/whymap/EN/Downloads/Global_maps/globalmaps_node_en.html

## Record of Adjustments
First draft: | June 2014 (at time of submission)
Updates:
20th March | Update for SHEAR Applications nested logframe following their inception phase - outputs 1 and 2
2015 | Adjusted output numbering to group SHEAR Apps and SHEAR Research outputs
5th August | SHEAR Research Milestones adjusted to reflect start of Research Projects in April 2016 and timing of annual review in December
2015 | New milestone added for November 2017 to allow monitoring and reporting in 2015 review
Activities related to SHEAR Applied and Innovation Projects added to November 2017 milestone
Added new output indicator on measuring the value of risk information for decision making.
Combined impacts and outcomes from nested logframes of SHEAR Research and SHEAR Apps into single logframe

## Sheet3
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (Nov 2016) | Milestone 3 (Nov 2017) | Target (2017+) | Assumptions
Greater and more effective investment in disaster resilience, preparedness, response and recovery, leading to reduced impacts from natural disaster | Number of policies, plans and investments informed by the improved risk information and tools, supported by capacity development. | Planned | Low level of use of risk information and tools in decision making | SHEAR Apps commissioned 3-6 co-designed, co-developed projects targetted at informing real DRR challenges (at least 50% in DFID priority countries). | Evidence of the use of data, tools and products commissioned by SHEAR Apps to inform disaster risk management and adaptation policies, plans and investments from SHEAR in at least 3 DFID priority countries, documented in deep-dive impact case studies. SHEAR Research Pilot case studies initiated working with at least 12 users across 4 countries |  | Use of data and tools from SHEAR Apps leads to more robust and evidence-based policies and plans and more effective investment in DRR | Decisions based on improved data, knowledge and products lead to ‘better’ decisions that reduce the risks from natural hazards
Achieved
Source
SHEAR Apps Monitoring and Evaluation Study (3 deep-dive case studies + self assessments from 10+ projects)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) |  | Target (Nov 2016) | Assumptions
New high quality and relevant data and tools accessed by decision makers and applied in practice | (a) Number of decision makers accessing and using SHEAR applicants products, data and tools; (b) % success rate in first round challenge fund = % of projects that lead to a useable and used tool in first round; (c) tools available on open platform; (d) # downloads of data and tools | Planned | 0 | 0 | (a) 20 beneficiaries involved co-developed of tools and accessing these regularly.(b) at least 50% success rate in phase 1 (c) Tools are openly available to the broader user community on an appropriate platform and training provided by project teams. |  | (a) Evidence of data and tools being accessed by decision makers, specifically 20 beneficiaries; (c) Tools are openly available to the broader user community on an appropriate platform and training provided by project teams; (d) for 5 top projects at least 2 downloads per month from users of data and/or tools. | Challenge fund projects deliver demand-led products and tools and engage users in co-production process. Projects make products available to the right people who have the capacity and demand to use them
Achieved
Source
SHEAR Apps Progress report and Final report; project self-assessments and deep-dive case studies
| Outcome Indicator 2 |  | Baseline | Milestone 1 (Nov 2015) | Milestone 2 (June 2016) |  | Target (Nov 2016)
Established process, partnerships and concensus toward greater accessibility and availability of data to support resilience in developing countries | Number of partnerships established, joint publications and documented follow-on activities | Planned | 0 | Established concensus on shared vision and partnerships through the production of the high-profile report | Establish two private/public partnerships driving a major open data for resilience platform initiative. Delivery of a pilot open platform/interface. |  | Strengthened open data for resilience initiative including through establishing key partnerships and community of practice around open data for resilience. Delivery of recommendations set out in the report.
Achieved
Source
project documents
Note on C24: Helen O'Connor: http://www.whymap.org/whymap/EN/Downloads/Global_maps/globalmaps_node_en.html