Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Burma Education Programme
Programme Value: £11.3		Review Date: December 2015
Programme Code: 202267	Start Date: 6/12/2010	End Date: 31/12/2016

Summary of Programme Performance
Year	2015	2014	2013	2012
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review
An £800,000 costed extension to the Burma Education Programme was approved in September 2015 to ensure continuity of support to the education sector up to December 2016. This is a critical time for the education reform process and the extension provides flexibility for DFID Burma to respond to opportunities presented by the transition to a democratically elected government in early 2016. The logframe is currently being revised with implementing partners and this review therefore reports on the existing logframe.

Newly available data for outcome indicators has enabled tracking of performance at the outcome level for the Quality Basic Education Programme (QBEP) in direct response to the recommendations raised in the 2014 Annual Review. These indicators reveal that QBEP is on target for outcomes related to expanding access to education in targeted townships (primary school enrolment and children beginning school with prior Early Childhood Development experience). Tentative data on learning outcomes presents a mixed picture, which requires further analysis. Improvements in Myanmar language competency are above target, but there have been much smaller increases in maths performance (from a much lower base). Whilst 91% of grade 5 students in QBEP townships are now reaching the required standard in Myanmar language only 26% are reaching maths standards (against a target of 30%). This learning outcomes data was collected as part of an in-depth evaluation of QBEP, which will explore the results in more detail (due December 2015).

The Burma Education Programme scored an A rating in 2015, with outputs meeting expectations. The programme has outperformed targets for the majority of outputs including the number of children accessing early childhood development centres, teachers trained and demonstrating improved practice, and out of school children accessing non formal education programmes. The programme has however missed the target for improved school management and accountability despite intensifying capacity building at the school and township level. Progress on this indicator continues to be hampered by the slow pace of supporting decentralisation reforms.

The Burma Education Programme operates in a rapidly changing context, in which education reform remains a contested priority among all major stakeholders (including current and new government, ethnic armed groups). In 2015, DFID has worked closely with both Myanmar Education Consortium (MEC) and UNICEF to respond to last year’s Mid Term Review recommendations. These recommendations aimed to help both programmes respond more effectively to emerging opportunities presented by reforms in Burma. QBEP has developed and implemented a Joint Performance Improvement Plan (JPIP) which includes a significant increase in ambition on evaluation, more strategic policy engagement with government (Ministry of Education is now a non-voting member of the steering committee) and a shift away from direct service delivery to building government capacity and systems (e.g. technical support on curriculum and materials development for new Kindergarten year). The MEC Mid Term Review identified MEC as an organisation with strong potential, but one which needs to be incentivised to sharpen its focus on the areas of greatest need in order to maximise its impact on education, as well as broader development and peace building outcomes. MEC are currently undertaking an overhaul of their strategy, which is expected to focus on strengthening complementary education systems and supporting convergence to build transition pathways for children through the education system.

The transition to a democratically elected government in 2016 presents major opportunities for education reform and it will be essential that the Burma Education Programme continues to build on the developments of the past year to respond effectively to these opportunities (as well as challenges).

Summary of recommendations for the next year
- DFID to monitor in liaison with co-funders Australian Department of Foreign Affairs and Trade (DFAT) that MEC develop and implement a new strategy focused on strengthening complementary education systems, including ethnic education departments. Continue and deepen engagement of peacebuilding, humanitarian and health advisers in DFID on support to ethnic education departments.
- DFID to use its voice on MEC’s Steering Committee to ensure transition plans are in place in areas where it is exiting, including children with disabilities. MEC should work with their current partners in the remaining period to strengthen the evidence base, identify innovative practices and draw out lessons learned.
- DFID should press for UNICEF to engage in broader policy discussions with Ministry of Education (MoE) on Kindergarten (KG) roll out, including linkages with ongoing reforms at primary level, how to monitor quality of KG interventions and sustainability of KG roll out (including teacher deployment plans, ongoing training/certification)
- Human Development team to liaise closely with Conflict and Governance advisers around opportunities for service delivery arising from National Ceasefire Agreement and transition to new government.
- DFID to participate in discussions on sector coordination to reduce risks of fragmentation as the Multi Donor Education Fund comes to an end. Dialogue with the new government should include strengthening the donor coordination mechanism.
- DFID to respond to opportunities to support new government during transition through partners and Technical Assistance.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3719331.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3704004.xls

Outline of the programme
DFID is providing £11.3 million over five years (2011-2016) to increase educational access, improve systems efficiency and raise learning levels in basic education. The intended outcome is 200,000 children (4 % of estimated eligible school age population[1]) supported to remain in school with an increase in completion rates[2] during early years of primary school and to Grade 5 (aged 5 - 9 years). It is comprised of three components, covering both government and non-state education providers[3]. In September 2015 an £800,000 costed extension to December 2016 was approved, details are provided by component below.
[1] http://data.worldbank.org/country/myanmar Year: 2010
[2] The survival rate was not set in Education Programme, Burma Approved Business Case. The target needs to be set with UNICEF in early 2015.
[3] The programme included a component in 2011-13 on Creating an Improved Learning Environment (CILE) targeting community schools and schools under cease-fire administered areas. There was also a separate component for Save the Children New Generation Programme from 2011-13. In July 2013 DFID support to Save the Children Myanmar continued through the MEC component.
1. Quality Basic Education Programme (QBEP) – UNICEF: Launched in January 2012, this is a joint partnership between Australia, Denmark, DFID, EU and Norway (the Multi Donor Education Fund “MDEF” donors) and UNICEF. The programme builds upon the success and experience of the partnership with UNICEF under MDEF I. The programme aims to expand the number and proportion of children who access and complete quality basic education in the 37 core townships (11% of townships in Burma), strengthen systems for education delivery and build the evidence base for national policy making through the Comprehensive Education Sector Review (CESR).[4] The QBEP Steering Committee agreed to a 6 month no cost extension to June 2016 to align the programme with the Burmese school year, provide continuity in support to the costed National Education Sector Plan that is currently under development and ensure effective spend of unallocated funds. New activities agreed under the extension for QBEP satisfy MTR recommendations and will include supporting government toward reaching their target of training an additional 100,000 teachers for Kindergarten, as part of the government’s curriculum reform.
  [4] The coverage of QBEP activities varies across township i.e. quality of teaching interventions are carried out in 25 townships, school based ECCD in 11 townships, community based ECCD in a further 14 townships and non-formal/second chance components (NFPE and EXCEL) operate in 45 and 41 townships respectively.
2. Myanmar Education Consortium (MEC): Provides support to complementary (non-government) education systems, community and school based early childhood development and non-formal education programmes for youths outside the mainstream education system. The programme provides direct funding and extensive capacity development to local non-state education providers (Ethnic Education Departments, civil society and non-state organisations) through calls for grant proposals. Current funding comes jointly from DFID, Denmark and Australia with a joint commitment to date of over $ 26 million. Total DFID contribution is £ 4.1 million (approximately $6.3 million), following a £300,000 extension to December 2016. MEC are currently developing a revised strategy to address the 2014 MTR recommendations. It is expected to focus on strengthening complementary education systems and supporting convergence to build transition pathways for children through the education system.
3. Technical Assistance: a £500,000 component was added under the cost extension to enable DFID to respond to opportunities afforded by a change in government following the election and respond to requests from government and non-state actors for support on policy development, capacity building and implementation in education. The recent elections represent significant opportunities for DFID to work with a democratically elected government in Burma with a commitment to education reform. There is a potential role for UK expertise in education (e.g. assessment systems, data management) to support emerging government policy over the coming months.
Performance of the education sector: Burma has significantly expanded access to schooling, but remains off track to meet the MDG 2 for universal primary enrolment, with a Net Enrolment Rate of 86.4% in 2013/14. Data availability and reliability remain issues in Burma, but best available estimates suggest that over 1 million children are out of school, 533,906 at primary level; 252,932 at lower secondary level, and 228,502 at upper secondary level. Socioeconomic status remains the major determinant of access to education in Burma. Decades of underinvestment by government in the education sector meant that household expenditure on education in Burma was well above international level in 2009/10. Subsequent commitments to free primary education and the introduction of school grants mean it is likely that this burden will have been somewhat reduced, but parents still face indirect costs (e.g. travel, materials) and in some cases direct costs (e.g. payments to teachers, tuition). Gender parity in access to schooling has been reached at the national level, but amongst the poorest (and most educationally marginalised) children in Burma, girls face even greater barriers to education. Out of school rates for girls in the poorest quintile are 7 percentage points greater than for boys. The examination system in Burma is in urgent need of reform and there are currently no standardised assessments in Burma to provide a robust measure of what children know. A nationally representative Early Grade Reading Assessment is planned for 2016. This builds on the 2014 pilot in Yangon region, which found low average reading scores in grades 2 and 3 that indicate reading competency in Burma is well below curriculum expectations. Poor reading fluency and comprehension will undermine students’ abilities to follow the curriculum and progress through the system.

Non-state education providers: Although government is the main provider of education services in Burma, a number of non-state actors serve the hardest to reach communities, including low socio economic groups (monastic schools) and children living in remote and conflict affected areas (ethnic education departments, faith based organisations). In remote and contested areas services are often fragmented and of varying quality. These schools face funding constraints (which in turn impact on quality of schooling), difficulties with teacher retention, and a lack of formal recognition between the government and non-state system, which limits transition pathways for children through the education system. MEC and its partners have worked with a number of non-government providers to try to strengthen coordination and oversight mechanisms (e.g. adoption of shared standards across monastic schools) and begin to build trust between non state actors and government through policy dialogue.

Changes in policy environment: An addendum was added to the National Education Law (NEL) in June 2015 following a period of political contention that culminated in violent clashes at a demonstration between students and police. A joint donor (including DFID) response to the amendment was delivered to Parliament, with some key points incorporated into the final amendment including a stronger focus on education for children with disabilities (though a lack of clear definitions and conceptual clarity remain); a provision on the use of ethnic languages in classrooms (although there is no detail on what this practically means); reference to the celebration of diversity of all national races, a provision for civil society participation in policy and planning; and a commitment to aim for 20 percent national budget allocation for education (it is unclear that this would be enforceable). The degree of ambiguity in the law disappointed many stakeholders. These may be resolved through the sub-sector laws which are currently under development, though it is unclear how the change of government will affect this process (3 sub-sector laws are now with Parliament: private, basic and vocational education).

The first draft of the National Education Sector Plan (NESP) was completed in parallel to the legislative process by mid-2015. This represents a major achievement, but significant issues remain with prioritisation, ownership and policy commitments that will need to be defined in the sub-sector laws or by governing bodies established under the NEL which have yet to be formed. With a new government due to take office in March 2016, it will be important to understand the transition process and work with the incoming government during this period to ensure that the team are able to draw on the robust technical analysis underpinning the NESP and draw out linkages to the NLD manifesto.

National Ceasefire Agreement: a partial National Ceasefire Agreement was signed in October 2015. It remains to be seen how this will evolve, but as some signatories may be future partners for MEC, it is likely to impact on how MEC can work to support children in (at least some) conflict affected areas. Ongoing conflicts continue to impact on children’s education opportunities and have impacted on MEC’s work in Kachin, Northern Shan State and Kayin State in 2015. MEC’s Education in Emergencies fund was able to respond to short term interruptions to education in Shan, Wa and Karen areas.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Newly available data for selected outcome indicators has enabled tracking of Quality Basic Education Programme (QBEP) outcomes for the first time. This was in direct response to the recommendations raised in the 2014 Annual Review. The programme is on track to reach outcome targets for expanding access to education in targeted townships with respect to enrolment and the proportion of children who are “school ready” (i.e. begin school with prior Early Childhood Development experience). Expansion in school enrolment was 30% higher in QBEP townships than for the nation as whole from 2011/12 to 2013/14. On learning outcomes, a large scale baseline and endline assessment undertaken by UNICEF and MoE reveals a mixed picture, with significant improvements in Myanmar language, but much smaller increases in maths (from a much lower base). Whilst 91% of grade 5 students in QBEP townships are now reaching the required standard in Myanmar language only 26% are reaching maths standards (against a target of 30%). These learning outcome indicators are only tentative and will be fully analysed by a team at the University of York who are currently undertaking an in-depth evaluation of school, pupil and teacher data over the life of the programme.

Data quality and availability remain an issue in Burma. DFID and partners will need to press UNICEF and MEC to access more outcome indicators at the township level (including survival rates). The upcoming education module in the World Bank Myanmar Poverty and Living Conditions Survey due in early 2016 will be an important data source to triangulate Education Management Information Systems (EMIS) and population census data on education.

Overall output score and description

The Burma Education Programme has scored an A overall, with many outputs exceeding expectations. It is clear from the output results that the programme has continued to make improvements to the teaching and learning environment in supported schools, increased the number of children who are equipped with the skills they need to learn through early childhood care provision, and has expanded valuable learning opportunities for those children who have dropped out of school or never attended through non formal primary education and life skills programmes. The programme has made progress on improving management and accountability, by intensifying capacity building at the school and township level, but continues to be limited by the pace of decentralisation within the Ministry of Education (MoE).

Key lessons and actions
- DFID monitor in liaison with co-funders DFAT and Denmark that MEC develop and implement a new strategy focused on strengthening complementary education systems, including ethnic education departments. Continue and deepen engagement of peacebuilding, humanitarian and health advisers in DFID on support to ethnic education departments.
- DFID to press MEC to ensure transition plans are in place in areas where it is exiting, including children with disabilities. MEC should work with their current partners in the remaining period to strengthen the evidence base, identify innovative practices and draw out lessons learned.
- DFID, together with co-funders DFAT and Denmark to encourage MEC to work with UNICEF on lesson learning around UNICEF’s approach in Mon State and success in building linkages between government and non-state systems. MEC and UNICEF should also liaise on future plans to ensure coordination.
- DFID should press for UNICEF to engage in broader policy discussions with Ministry of Education (MoE) on Kindergarten (KG) roll out, including linkages with ongoing reforms at primary level, how to monitor quality of KG interventions and sustainability of KG roll out (including teacher deployment plans, ongoing training/certification).
- QBEP to develop strong communication tools for teacher education evaluations. This should form part of a dialogue with MoE around teacher effectiveness. Teacher policies introduced since 2012 have focused explicitly on increasing the number of teachers in the system, with less regard for quality. This may be sufficient for expanding access to education, but to deliver a labour force with the skills that Burma needs to take advantage of burgeoning economic opportunities will require joined up policies around recruiting, training and holding teachers to account.
- QBEP and MEC Steering Committees to continue to press UNICEF and MEC to access more outcome indicators at the township level (including survival rates).
- Human Development team to liaise closely with Conflict and Governance advisers around opportunities for service delivery arising from National Ceasefire Agreement and transition to new government.
- DFID to participate in discussions on sector coordination to reduce risks of fragmentation as the Multi Donor Education Fund comes to an end. Dialogue with the new government should include strengthening the donor coordination mechanism.
- DFID to respond to opportunities to support new government during transition through partners and Technical Assistance.
- Any new programming in education should draw on lessons learnt from current programming including importance of building M&E and learning into implementation of the programme.

Has the logframe been updated since the last review?
Yes, in line with recommendations from the 2014 Annual Review following the Mid Term Review. Output 2.1 “Number of children in targeted townships provided with essential supplies and textbooks, including humanitarian support” has been removed as QBEP shift resources away from direct service delivery. The logframe is currently under review following the extension and will be updated when the MEC strategy has been agreed, by end of 2015.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved Early Childhood Care and Development (ECCD) service delivery and coverage, particularly in poorer, rural areas.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
No. of children who have benefited from ECCD services	95,488 / QBEP: 85,000 / MEC: 10,488	112,571 / QBEP: 103,480 / MEC: 9,091
% of ECCD centres that meet minimum quality standards / (School and Community Based)	School based: 20% / Community based: 60%	School: available Dec 2015 / Community based: 87%
Multisector ECCD national action plan/policy in place	Multi-sectoral five year ECD National Policy designed	ECCD policy printed and disseminated at all levels.

Key Points
- This output scored an A+, with targets reached or exceeded for most indicators available. School based quality standards for Early Childhood Care and Development (ECCD) will be available in December 2015, as this indicator is being collected as part of the endline data collection exercise for QBEP.
- The overall number of children accessing early childhood development support has surpassed the target for 2015. MEC was below target. This was driven by lower reach for Save the Children’s founding partner project (due to delay in obtaining government authorisation and underestimating the extent of migration) which has now ended. MEC’s local development fund partner projects (which will continue to 2016/17) exceeded their target.
- Quality of community based ECCD provision has continued to improve, with 87% reaching minimum quality standards, well above target. Save the Children’s evaluation found positive development traits in children, but longer term impacts on learning are more difficult to discern, with limited sample sizes and difficulty tracking children.
- Save the Children’s evaluation found that their participatory model of ECCD (which includes parental education) was successful in ensuring ownership and sustainability, with 96% of ECCD centres opened since 2006 still operational. There was also a positive effect on household income (higher for marginalised households) as ECCD centres enabled parents to engage in income generating activities.
System strengthening:
- The Government of Burma’s National ECCD Policy has been disseminated to stakeholders at all levels and relevant departments of government. Although this plan covers children from 0 to 8 years, DFID successfully advocated for QBEP to focus its ECCD activities in the remaining period on rolling out the new Kindergarten (KG) year from 2016/17. This is in line with recommendations from last year’s Annual Review, capitalises on QBEP’s strong relationship with MoE (which has responsibility for implementing KG) and supports the critical first stage of the government’s curriculum reform process.
- UNICEF is still working with MoE to finalise plans for KG roll out (together with other ECD specialists, including Save the Children). QBEP has allocated $6.2m for cascade training of KG teachers (at centre, states/regions and township level), development of training, teaching and learning materials, as well as provision of KG kits. QBEP support has also ensured that teacher modules have been developed for ethnic language teachers and bilingual teaching materials developed in 65 local languages.
Summary of responses to issues raised in previous annual reviews (where relevant)
- QBEP and MEC to support government in roll out of KG: on track (see above)
- Save the Children to produce a synthesis paper on lessons learned from ECCD: yet to be completed, evaluation on Save programme delayed, should be undertaken in early 2016 (see below).
- MEC and UNICEF to continue advocacy for ECCD: see above.

Recommendations
- QBEP to continue working closely with MoE to finalise teaching guides, resource materials, thematic lesson plans and training guides for KG.
- DFID should press for UNICEF to engage in broader policy discussions with MoE on linkages with ongoing reforms at primary level, how to monitor quality of KG interventions and sustainability of KG roll out (including teacher deployment plans, ongoing training/certification).
- MEC’s strategic refresh (due December 2015) will involve a reduced focus on ECCD in line with Mid Term Review recommendations. MEC should use their current partnerships to strengthen the evidence base and draw out lessons learned. This could be undertaken together with the upcoming Save the Children research synthesis and broader evaluation.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved access to quality teaching and learning in schools
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
% of primary teachers applying improved teaching methods as defined by classroom observation criteria	QBEP: 35% sampled teachers / MEC: 30% of trained teachers	QBEP: Available December 2015 / MEC: 30%
No. of Primary teachers receiving training	2,280 / QBEP: 1,000 / MEC: 1,280	14,306 / QBEP: 7,664 / MEC: 6,642

Key Points
This output has scored an A+. Both programmes have expanded their provision of teacher training and MEC teachers have demonstrated improvements in teaching practice. QBEP teacher performance data will be available in December 2015, as this indicator is being collected as part of the endline data collection exercise for QBEP.
- In line with the 2014 Annual Review recommendations output indicator 2.1 “Number of children in targeted townships provided with essential supplies and textbooks, including humanitarian support” has been removed as QBEP shifts resources away from direct service delivery. QBEP has however distributed existing learning packages in stock to 188,228 children in emergency settings, both in IDP camps and in areas affected by the recent flooding. QBEP has also supported 4,724 children to regularly access temporary learning spaces in IDP camps in Sittwe and Pauktaw. In 2015 95% of these students were able to participate in a State government sponsored exam.
- QBEP has exceeded targets for teacher training through adoption of more cost effective school based models (e.g. school based in service teacher education). MEC’s enhanced reach has predominantly been due to the work of an innovative coalition of organisations providing teacher training in non-state and community schools in ethnic areas (East Burma Community Schools).
System strengthening:
International evidence shows that teacher effectiveness is the single greatest determinant of student learning. The recent influx of untrained daily wage teachers in Burmese schools (new teachers account for 25% of all primary teachers) together with the increased demands that curriculum reform places on teachers, will require a major programme of in service teacher training. MoE has traditionally relied on mass teacher trainings, but cost effective models like SITE provide valuable examples of potential new approaches. Teacher training models are currently being evaluated under QBEP and these findings can be used to determine how they could contribute to a planned certification framework for daily wage teachers.
- QBEP have continued work on multilingual teaching and learning, a critical area for improving learning outcomes for children who do not speak Burmese as their mother tongue. This has included partnerships with the regional UNICEF office and University of Melbourne to hold facilitated dialogues on developing a language policy with Ministry staff, technical experts and language and culture groups. This group has also established linkages with the curriculum reform team.
- Preliminary findings from an evaluation of the UNICEF Peacebuilding Education and Advocacy programme by the University of Amsterdam indicate that QBEP support to teacher training and work on language policy helped to build linkages between the Mon National Education Committee (MNEC), MoE and Mon State Government. This directly led to the decision by the State Minister for Mon Affairs to invite MNEC join a specially formed Task Force to develop Mon Language curriculum and learning materials for use in government schools, which will be taught as a subject for 30 minutes during regular school hours. MNEC Head Teachers were invited to participate in QBEP Head Teacher training and the Mon State Government has officially agreed to provide Myanmar language textbooks to MNEC schools. MEC should work closely with UNICEF on lessons learned from this approach, both for any future work in Mon State and with other ethnic education departments.
- MEC has worked closely with its local partners to raise civil society issues at national and local levels. Successes include the regional office of the Department of Social Welfare in Pathein now providing bursaries to students with disabilities as a direct result of MEC’s partner’s work engaging with communities and officials.

Summary of responses to issues raised in previous annual reviews (where relevant)
- Teacher survey data to be made available more quickly: this was not possible in 2015 as the teacher data was collected and analysed as part of QBEP’s endline evaluation. This highlights the importance of a broader shift in approach for any new DFID education programming, where learning should be built in more explicitly to the implementation of the programme.
- Support government in developing teacher training approaches: ongoing, see above. DFID and JICA also set up a working group on teacher training which was asked to feed into the teacher education sub-law.

Recommendations
- MEC to work with UNICEF on lesson learning around UNICEF’s approach in Mon and success in building linkages between government and non-state systems. MEC and UNICEF should also liaise on future plans to ensure coordination.
- QBEP to develop strong communication tools for teacher education evaluations currently underway for government and broader education stakeholders. This should form part of a dialogue with MoE around teacher effectiveness. Teacher policies introduced since 2012 have focused explicitly on increasing the number of teachers in the system. This may be sufficient for expanding access to education, but to deliver a labour force with the skills that Burma needs to take advantage of burgeoning economic opportunities will require joined up policies around recruiting, training and holding teachers to account.
- Any new programming in education should ensure that ongoing M&E is built into the implementation of the programme.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved access to quality non-formal, alternative and life skills education
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
No. of children who have accessed non-formal, alternative or life skills education	10,925 / QBEP: 6000 / MEC: 4925	13,702 / QBEP: 10,422 (NFPE) + 3,022 (EXCEL) / MEC: 258
Percentage of reached out of school adolescents completing EXCEL in targeted townships	85%	94.5%

Key Points
- Non formal education opportunities provide critical skills and pathways back into mainstream schooling for the large population of out of school children in Burma.
- Targets for children accessing non formal opportunities were well above target overall, but significantly below target for MEC, which were set before the MEC development fund grants were allocated. The development fund was an open call for proposals across all MEC priority areas and fewer grants than anticipated were made to non-formal education projects. The MEC logframe will be updated in December 2016 following the outcome of the strategic refresh.
- QBEP trained 1,035 new facilitators to implement non formal primary education programmes (NFPE) in 89 new townships. Additional training was provided to 695 non formal centre heads (primary school head teachers) to provide mentoring to new facilitators.
- 3,022 out of school children were provided with life skills education through the EXCEL programme, although this represents a reduction on 2014. Following the Mid Term Review recommendations QBEP has shifted focus away from life skills programming to NFPE, which provides a full primary school equivalency that is intended to be of greater value to out of school children.
System Strengthening:
- A standardised test for non-formal education students to re-enter mainstream education has been developed and the procedures/guidelines for administering tests have been shared with 1,100 primary school heads. A workshop on the test was also held with senior policy makers from MoE (examinations board, Department of Basic Education), NFPE focal persons at State/Region level and Township Education Officers from 89 townships.
- QBEP have continued to support translation and adaptation of NFPE materials in local languages with an additional 3 Kayin ethnic languages developed in 2015.
- As part of the sustainability plan for QBEP, of the 89 townships in which NFPE was rolled out, 42 were fully funded by QBEP, 16 were funded by MoE and 31 in partnership with private sector providers.
- MEC’s new strategy has yet to be finalised but it is likely that there will not be a specific focus on non formal education. Although this is an important area, to be effective MEC need to prioritise on areas in which they have a comparative advantage. MEC should however consider how non formal education could be used within any future work with complementary systems and work with their current non-formal education partner to capture and communicate lessons learned as an alternative and sustainable model for providing non formal education opportunities in urban areas. MEC’s current partner project (Scholarships for Street Kids, Myanmar) is small in scale, but the project aims to address some of the challenges experienced by MEC’s founding partner project by establishing links with a microcredit NGO to support families to supplement their livelihoods and reduce opportunity costs of education for out of school youth.
Summary of responses to issues raised in previous annual reviews (where relevant)
- QBEP/MEC coordination on capacity building: with only one partner project working on non-formal education there has been less scope for coordination around capacity building than originally envisaged.
- MEC to play a greater role in convergence between government and ethnic systems: this is a key focus of MEC’s new strategy that is currently under development.

Recommendations

MEC will most likely not have an explicit focus on non-formal education, but should consider opportunities for providing non formal programmes in ethnic areas, particularly the new middle school equivalency programme that is under development by UNESCO. This may be a critical transition strategy before pathways between government and ethnic systems can be formalised or provision of middle schools in ethnic areas expanded.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved management of schools and accountability to local communities.
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Proportion of schools with operationalized SSAs/SIPs in targeted townships	35%	22%
# of townships with Township Education Management Information Systems (TEMIS) fully operational	TEMIS fully operational in 8 townships	TEMIS partially operational in 12 townships.

Key Points
- Indicators for management and accountability have improved since last year, but remain below target. This was to be expected, as the activities at township level continue to be impeded by the slow pace of decentralisation of decision making and authority in Burma. The recent doubling of education staffing at township and state/region level suggests that this may be changing. Innovations in the sector (e.g. World Bank and Australian Department of Foreign Affairs and Trade supported MoE school grants programme) however suggest that to strengthen decentralised systems will require a departure from QBEP’s traditional intervention based approach.
- QBEP is no longer providing school grants to government schools due to the national roll out of the MoE school grants programme and from this academic year no QBEP schools will be undertaking the more comprehensive school improvement plans developed under QBEP. The government programme uses a much simpler planning tool, but it is hoped over time this could be expanded and made more rigorous using lessons from QBEP. UNICEF has established a partnership with the Mon National Education Committee (MNEC) and Township Education Offices in 4 QBEP townships, which will enable 104 non-government schools to apply for school grants under QBEP in this academic year.
- The introduction of township level Education Management Information Systems has continued in 12 townships, but issues remain with delays and data quality. Based on these limitations no new TEMIS activities have been approved under QBEP since the Mid Term Review and will not be until the evaluation is complete. TEMIS activities are restricted to ongoing activities, including data analysis of previously collected data.

System strengthening:
- UNICEF’s partnership with the Mon National Education Committee (MNEC) and Township Education Offices to deliver school grants for non-government schools under QBEP is an interesting development in drawing closer linkages between the government and non-state system. UNICEF should explore options with World Bank and DFAT on how this could potentially be incorporated into the government school grants programme.
- Despite the limitations faced in trialling new systems at the township level, QBEP has amassed some critical learning on strengthening planning and management capacity at the township level. By taking a holistic view, the evaluations of township planning and data management activities under QBEP will provide critical lessons for new policies and programmes that may be expected based on the increase in staffing.
QBEP supported the development of a pilot web based EMIS solution, which has not been implemented at the Township level due to connectivity constraints. The software is however being trialled at the central level to merge the Human Resource Information System, which includes all the teacher data as part of the Ministry’s EMIS Master Plan.

Summary of responses to issues raised in previous annual reviews (where relevant)
Ensure evaluations of township and school level management support inform government systems: evaluations are underway, but the creation of reference groups for each evaluation (which includes government participation) will help to ensure that the findings are taken up by government.
UNICEF need to ensure that management capacity is increased at township level to sustain improvements brought by programme even if interventions are not rolled out/sustained. 2,203 head teachers and 14,540 Parent Teacher Association members have received school management training in QBEP core townships QBEP are supporting a rapid assessment of capacity building needs and initial training in MoE, including at the Township level. Township level capacity building under QBEP will be undertaken in late 2015.
Recommendations
- As part of QBEP’s transition strategy UNICEF should explore options with World Bank and DFAT on expanding school grants programme to MNEC.
- Girls Education Challgenge (GEC) Fund Manager should ensure that lessons learnt through the Strategic Partnership with Ericsson in Burma are shared with Ministry of Education and wider stakeholders, including on connectivity issues.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

QBEP expenditure January to December 2014 USD				MEC expense July 2013 to June 2014 USD
	USD	%			USD	%
Output 1: Early Childhood Care and Development (ECCD)	441,555	3%		Early Childhood Care and Development (ECCD)	8,691,010	31%
Output 2: Quality Education	6,071,642	35%		Complementary education	7,916,610	29%
Output 3: Second Chance Education	3,063,472	18%		Policy Dialogue	958,661	3%
Output 4: Education Leadership and Management	1,359,517	8%		Alternative for out of school	1,469,094	5%
Support to special targeted townships (Rakhine)	769,607	4%		Education in Emergencies	760,438	3%
Staffing costs and technical support	1,893,636	11%		Capacity Building	799,434	3%
Local office costs	735,073	4%		Monitoring and Evaluation	1,170,413	4%
Comprehensive Education Sector Review and National Planning	1,456,124	8%		Programme management	3,416,609	12%
Indirect cost recovery	970,952	6%		Sub contract management	71,467	0%
Monitoring and Evaluation	455,391	3%		Indirect cost recovery	2,435,510	9%
Total	17,216,970	100%
				Total	27,689,246

QBEP: UNICEF developed a Joint Performance Improvement Plan (JPIP) in 2014 to respond to the findings of the Mid Term Review, which included a shift away from direct service delivery (including provision of learning supplies) and move towards strengthening government systems and building government capacity. Budget allocation has already shifted in line with these recommendations. The share of funds allocated to Output 2 “Quality Education” has fallen from 51% to 35% of total expenditure, with the decision to stop procuring learning supplies. Expenditure on sector planning and policy engagement (Comprehensive Education Sector Review and National Planning) has increased from 3% to 8%. Monitoring and Evaluation costs now account for 3% of total expenditure, but this will increase further in the final year of the project, as there was a long lead time in tendering contracts and procuring consultants. Allocations to second chance education have also increased, with the expansion of non-formal primary education to new townships. The share of ECCD costs have reduced without the development of new ECCD facilities, but this will increase significantly in the last year of the programme as QBEP supports roll out of Kindergarten education. Staffing costs have reduced slightly, but remain a significant cost driver in the programme. Following Mid Term Review recommendations UNICEF have provided a full breakdown of all staffing roles and allocations to QBEP and UNICEF country programmes respectively. For the cost extension staffing levels and costs have been reduced as part of the project’s transition and exit strategy.

MEC: Expenditure has increased significantly in June 2014 to July 2015, as MEC completed three founding partner projects, the first year of 13 development grants with local organisations and three Education in Emergencies projects. Early Childhood Care and Development continues to be the major cost driver in MEC’s projects, although the share to complementary systems has increased as grants to ethnic education providers have come on budget. The education in emergencies window remains a small share of MEC funds, even after the recent floods when only one partner made use of the facility. It is likely that this emergency component will not be continued as a distinct component in a refocused MEC. It is expected that expenditure will shift in the coming year as MEC shifts away from open calls for proposals across a range of education issues, to more deliberate targeting of key focus areas. MEC’s strategy is still under development but will likely result in a greater share of resources allocated to complementary education systems and policy dialogue. Monitoring and evaluation continues to be an important part of MEC’s mandate, in drawing out lessons learned, and accounts for 4% of project expenditure, in line with DFID guidance.

VfM performance compared to the original VfM proposition in the business case
The Business Case includes a set of unit cost measures for early childhood development services and provision of learning materials to assess value for money performance. QBEP no longer provides learning supplies and the financial reporting system means that it is not possible to identify unit costs for individual activities, so a quantitative assessment of value for money is only possible for MEC. The Business Case did not include any unit cost guidelines for the non-formal or complementary education components, but these are considered against new benchmarks established in the 2014 Annual Review.

Table 1: Early Childhood Care and Development Unit Costs	USD per child per year
Business case guidance: ECCD provision: 8%-15% of per capita GDP	73 - 132
Save the Children New Generation - ECCD centres	33
Save the Children – New Generation Parenting education	66
Save the Children – New Generation Alternative Parenting education	92
Development Fund unit costs for ECCD services	66

All three early childhood development models implemented by Save the Children are below or within the business case guidelines on value for money. The Save the Children early childhood centres and parenting education programmes are both less expensive than the business case guidance for unit costs and represent significant cost savings from the original Save the Children programme unit costs ($81 and $86 respectively). The Alternative Parenting Education programme unit cost is higher, which is to be expected as it targets hard to reach communities, but still remains within the guidance. Development fund ECCD services compare favourably with Save the Children on a cost per child basis (66 USD per child). The models under the development fund programmes include formal school based ECD (delivered through Pinnya Tazaung Association and includes capacity building of government counterparts) and community based ECD centres established in remote communities where there are no other means of accessing education (METTA foundation).
It is difficult to compare the unit costs across ECCD programmes without calibrating for differences in intervention objectives, design, quality, and intensity.[5] It would be useful for MEC to support development fund partners to develop more detailed unit costs measures to enable assessments of cost effectiveness.
[5] Direct comparisons of ECCD programs, both to each other and to primary education programs, must be calibrated to compensate for differences in program objectives, design, quality, and intensity (Levin and Schwartz 2006). Unit cost data is rarely given in research and evaluations, limiting options of comparison. In a recent rigorous literature review commissioned by DFID on ECCD found that “Very few studies reported on the costs of the interventions, and the unit costs vary widely due to factors such as economies of scale, geography, income and price levels, and integration in other programmes.”
Non Formal Education costs for World Vision are higher at $124 per child, with construction of centres driving costs[6]. Unit costs for the development fund non formal education project were calculated using the same assumptions, and were slightly lower at $100 per child[7]. To assess value for money, the cost for 2 years of non formal provision is compared with 5 years of standard government schooling, as graduates from the accelerated non formal programme should reenter formal schooling at grade 6. At $248 and $200 the MEC founding partner and development fund non-formal programmes compare favourably with the cost of $440 for a full cycle of primary education. The main complementary education programme under MEC, supporting monastic schools, has a unit cost of $65 per child per year. This is below the cost for 1 year of government schooling ($88) [8]. More detail is needed on the content and impact of both the non-formal and complementary programmes, but the unit cost analysis suggests that they represent good value for money.
[6] The construction of NFE centres are usually the biggest expense in NFE projects. Due to the rising cost of living in Myanmar, and specifically Yangon, World Vision and S4SK have opted for renting buildings to serve as NFE centres rather than constructing new buildings in some locations. These kinds of project amendments assist in keeping the costs down in NFE projects to make it more cost effective. In the projects, MEC also encourages community contributions, for example some kind support to volunteer NFE facilitators, repairs to NFE centres and provision of supplies for learners.
[7] Assumptions for unit cost analysis are based on MEC’s founding partner project value for money analysis: (i) centres operate for 10 years and (ii) a 90% sustainability rate.
[8] Unit cost for primary education of 88,264 kyat in 13/14, increasing from 63,199 (2012/13) and 33,038 (2011/12).

QBEP financial management systems do not enable unit cost analysis but a brief qualitative VfM analysis is presented below:

Economy	Framework agreement for 5 evaluation studies tendered with Montrose/EMPOWER Myanmar. / Umbrella contracts established with 4 partner organisations for Non Formal Primary Education implementation and with 3 partners for WASH in schools programme.
Efficiency	UNICEF is currently piloting a new approach to independently monitor and verify activity level results by implementing partners and is developing improved monitoring tools for internal use, with a greater focus on output and outcomes (piloted in October to December 2015).
Effectiveness	QBEP support to roll out of Kindergarten education (curriculum design, teacher training modules, design and development of teaching materials) increases effectiveness of not only QBEP but also government resources required for an additional year of schooling.
Equity	Situational analysis on children with disability due early 2016. / Non Formal Primary Education (NFPE) materials developed in 4 additional ethnic languages. / Kindergarten learning materials developed in 65 languages.

Assessment of whether the programme continues to represent value for money

The unit cost analysis used to measure value for money in the Business Case suggests that the MEC programme continues to deliver value for money. It would be useful to develop more detailed measures for the new areas of MEC focus pending the strategic review. One of the key drivers of MEC’s strategic refocusing is to have greater impact on higher order outcomes, which should improve value for money in the longer term. The Mid Term Review identified potential opportunities to improve efficiencies in overhead financing at the point of contract renewal. This will be considered at the end of MEC’s next phase in 2017/18.

In line with recommendations from the Mid Term Review UNICEF have made greater use of umbrella contracts (some examples cited in table above) and more efficient methods of supply to townships within the sourcing and procuring strategy. Upcoming evaluations of project components should calculate unit costs and assess cost effectiveness where possible. The end of project evaluation is currently under design with other MDEF partners and it is planned that this will include an in depth focus on vfm.

Quality of financial management
QBEP: Following concerns raised in the Mid Term Review around UNICEF’s financial management framework the QBEP Steering Committee has worked closely with UNICEF to clarify information requirements and receive more regular assessments of the financial status. The cumbersome financial management framework makes it difficult to disaggregate expenditure by programme component, and has delayed decisions around unallocated funds. The extension of QBEP to mid-2016 will however enable these unallocated funds to be spent effectively and in line with Mid Term Review recommendations. There are concerns that execution may be lower than expected in the transition period to a new government and QBEP has agreed to provide monthly status updates on the budget to the Steering Committee.

MEC: The findings from the MEC Mid Term Review have not raised any concerns with the financial management system, beyond potential inefficiencies in overhead financing arrangements that could be addressed at the contract renewal stage. Although MEC is working with local partners, the model is based on providing extensive capacity and organisational development support, including in financial management. Average expenditure rate across development fund partners is 86%, just below the budgeting target of 90% and two organisations accounted for half of this variation (one of which has now ended, and the other was due to re-emergence of conflict).

Date of last narrative financial report	QBEP: October 2015, MEC: October, 2015
Date of last audited annual statement	QBEP: UNICEF Country Office audit March 2014, MEC: First audit planned for 2015[9].
[9] Follow up for update

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

Political risk: The first quarter of 2015 was dominated by student protests around the National Education Law. The protest was led by the Student Unions and the National Network for Education Reform (NNER). The protests culminated in violent clashes between student demonstrators and police, but an amendment was agreed and approved by Parliament in June 2015. While the protests were highly political they raised issues that are relevant to DFID, particularly the governance of education policy, mother tongue as a language of instruction, financing of education and the role of inclusive education for children with disabilities. Although the amendment included provisions in these areas the degree of ambiguity disappointed many stakeholders. These may be resolved through the sub-sector laws which are currently under development, though it is unclear how the change of government will affect this process. The recent elections represent significant opportunities for DFID and partners to work with a democratically elected government in Burma with a commitment to education reform. It remains to be seen how the transition period until the new government forms in March 2016 will affect MoE performance and therefore QBEP implementation. In the run up to the election key implementation decisions usually taken by Director Generals were referred to the Minister for guidance, slowing down actions and fund utilisation. It was intended that the role of Permanent Secretary would provide continuity in decision making, but as a new post it is not clear that this will be the case. With a major change in government expected the sector planning process will be interrupted, but the technical work underpinning the National Education Sector Plan should provide a foundation for NLD education plans. The signing of a partial NCA In October 2015 will result in signatory parties being removed from the illegal organisations list which could potentially have a significant impact on MEC’s approach to working to support children in some conflict affected areas.

Human capacity risk: QBEP has supported long and short term technical assistance (international and national) for planning, coordination and sub-sectoral support, embedded in the CESR office. In the remaining period it will be important to ensure that capacity is built with MoE counterparts. QBEP is also currently funding a capacity gap analysis in the Ministry of Education as part of the recent restructure, which will include trainings on five priority areas identified with MoE. The influx of untrained teachers through the daily wage programme has placed a major need for on the job training for this large cadre of teachers.

Contextual risk: As the Multi Donor Education Fund (MDEF) comes to an end in June 2016 it will be essential that there is a suitable mechanism for donor coordination in the sector to prevent fragmentation.

Fiduciary risk: DFID payments to partners are made in arrears and cash flow situations were monitored before disbursement. A Joint Performance Improvement Plan has been developed by UNICEF to respond to the 2014 Mid Term Review and MEC is currently developing a new strategy.
Conflict Risk: Conflict in Kachin, Northern Shan State and Kayin State impacted on MEC’s work in 2015. In Kachin, planned longer term development activities were postponed as emergency support was prioritised. MEC is currently developing a revised strategy that will include more targeted support to ethnic education departments. This has been informed by conflict and peacebuilding experts from DFID and DFAT, as well as a dedicated consultancy. It will be essential that conflict specialists continue to feed into the design process and that MEC recruits a conflict specialist.

Climate and Environmental Risk: Severe floods occurred during the rainy season across Myanmar especially in Rakhine, Sagaing, Magway, Chin, Arrawaddy and Bago regions, with 250,000 school children’s education disrupted and over 300 schools damaged. QBEP has allocated $2 million to the flood response programme.

Outstanding actions from risk assessment
MEC is currently developing a new strategy, which will include an updated risk assessment.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

QBEP: The restructuring of departments within the MoE (announced in August 2014 but only completed in April 2015) have been a major challenge to QBEP programming and budget utilisation. QBEP’s Ministry counterpart, the Department of Educational Planning and Training (DEPT) was abolished as part of the restructure and replaced by the new Department of Basic Education (DBE). This has resulted in lower than planned expenditure rates in the first half of 2015 (34%). The Permanent Secretary has since agreed for other key Departments to handle funds directly from QBEP. Expenditure has increased in Q3 of 2015, but an underspend for 2015 was still envisaged, with the run up to the election expected to slow implementation. Issues with delayed implementation were exacerbated by the issue of unallocated funds, arising from the decision to stop some activities following the Mid Term Review and additional funding provided by Denmark to the Multi Donor Education Fund (MDEF) in 2014. DFID together with MDEF donors agreed in September 2015 to a 6 month no cost extension for QBEP in order to provide consistent support to the education sector at a critical time for the reforms (the final NESP due to be completed in mid-2016), to align activities with the Burmese school year and ensure that unallocated funds can be spent effectively and in line with the MTR recommendations (roll out of Kindergarten, capacity gap analysis and training for Ministry of Education). QBEP has agreed to provide monthly status updates on the budget to the Steering Committee to enable close monitoring of expenditure for the remainder of the programme.

MEC: Overall financial expenditure and programme delivery is progressing largely as expected. Founding partner projects completed project activities on time (Burnet Institute was given a no cost extension) but slightly under budget ($290,000). The average expenditure rate for development fund partners was 86%, close to the budgeting target of 90%. Two partners (MILI and Shalom) accounted for more than half of this underspend. MILI had challenges in project management and the partnership was not continued to a second year, whilst Shalom had to curtail activities following renewed conflict in their programme areas. The Steering Committee approved a proposal to carry forward Shalom’s under expenditure into the second year of their project. MEC non-grant expenditure was lower than forecast for the period, mainly due to restructuring of the management team, which meant that some positions were vacant, but the restructure will be completed later this year with the approval of the new strategy. An additional funding round had been planned for 2015 but has been delayed pending the finalisation of a revised strategy. In 2015 DFID approved a costed extension of £300,000 (approximately $450,000) to December 2016 to support MEC’s strategic refocusing.

Performance of partnership (s)

QBEP: The 2014 Mid Term Review highlighted important recommendations for both UNICEF and MDEF partners to improve the effectiveness of the partnership. Temporarily increased staffing resources to education in DFID Burma have enabled DFID to provide greater oversight and technical inputs to the partnership, including significant support in developing the Joint Performance Improvement Plan and to engage in the national planning process. The QBEP programme has demonstrated progress in a number of areas identified in the Mid Term Review in 2015 including greater visibility of DFID and MDEF donor support, improved documentation and lesson learning, and a shift in programming from direct service delivery toward building government capacity and improving quality of government interventions. However, as highlighted in the 2014 Annual Review, given the scope of change required and short timeframe some issues remain, despite strong oversight. MDEF donors are currently designing the end of programme evaluation for QBEP, which will include an assessment of how the programme has responded to Mid Term Review recommendations.

MEC: The MEC Mid Term Review identified MEC as an organisation with strong potential, but one which needs to be incentivised to sharpen its focus on the areas of greatest need in order to maximise its impact on education, as well as broader development and peace building outcomes. MEC has responded positively to the challenges identified in the Mid Term Review and concerns around the culture shift required for both MEC and Save the Children (as fund manager) have not materialised yet. There has been a change in senior management, including recruitment of a new Director (DFID participated in the recruitment process), which has been crucial in supporting the commitment for change in MEC. MEC is currently developing the new strategy which will focus on strengthening complementary education systems and supporting convergence with the government system, to build transition pathways for children and teachers through the system. DFID has provided a costed extension of £300,000 to end of December 2016 to support this process.

Asset monitoring and control
To date no issues have been identified with asset management practices. MEC have installed asset monitoring and control guidelines for all three asset types: MEC Management team; founding partner projects and development fund partner projects.[10] UNICEF has a global asset monitoring and control policy which every country office must be compliant with. The policy is published on their website.
[10] Assets purchased for MEC management team: The MEC management team is directly responsible for the assets purchased for use by the MEC management team. These mainly comprise computers and other communications devises. These are all managed in line with Save the Children asset management policy, with all assets being tagged and logged at purchase. We have conducted an asset inventory check in 2014. Assets purchased for founding partner projects Founding partner projects (World Vision, Save the Children and Burnet Institute) are operating at scale and are supported by a range of assets types including vehicles and communication equipment. These three organisations are internationally recognised and are also DFAT accredited organisations. As such their organisational policies, including asset management, have been approved as meeting recognised standards of best practice. Assets purchased for development fund partner projects Development Fund partners comprise the 13 new partners that entered into project implementation projects in 2014. The projects and organisations range in size, value and organisational capacity. The MEC management team reviewed partner proposals across a range of factors, including experience and organisational capacity. Prior to selecting partners all organisations conducted an organisational assessment which included review of financial policy including asset management practices. All partners have signed contracts which include all relevant donor conditions applicable to MEC, including asset management. All partners are required to maintain asset registers and compliance is monitored through quarterly reporting and monitoring by the MEC management team.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The DFID Burma partnership principles have been updated in October 2014 (Quest No: 4654477). In line with these principles the education programme does not provide any funds direct to government. QBEP provides funds to Township Education Offices but all funds are channelled through QBEP Township bank accounts to ensure that partnership principles are not contravened.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Following the Mid Term Review recommendations UNICEF have recruited an evaluation specialist and are undertaking an ambitious set of evaluation studies across the programme. UNICEF have successfully tendered a framework agreement with a consortium of consultants Myanmar to carry out 5 evaluation studies, to streamline the contractual process as well as benefit from institutional knowledge acquired over multiple studies. There have been some delays with individual studies this year, including issues with poor performance of consultants, which has meant that two team leaders were replaced (on the teacher training and disability studies) to ensure that quality was not compromised. This has delayed the publication of findings. The no cost extension for QBEP will however ensure that there is adequate time for lessons learnt from the evaluations to be communicated effectively to government and other stakeholders. UNICEF have established reference groups for each study (which include MoE technical staff and MDEF representatives) to build ownership of the evaluations with government. In discussions with MoE staff it is clear that they value the evaluations, and have cited the need to wait for findings in areas where there is interest for scale up (e.g. teacher training).

MEC have published a baseline report for the development fund partner projects and end of programme evaluations have been completed for the three founding partner projects.

Monitoring progress throughout the review period

Mid Term Reviews were completed for both programme components in 2014. DFID has worked closely with both partners to ensure that the findings are incorporated in QBEP’s Joint Performance Improvement Plan and in MEC’s evolving strategy.

UNICEF has adopted two activities to strengthen the quality of QBEP monitoring in line with 2014 MTR recommendations. UNICEF is currently piloting a specific protocol for UNICEF to independently monitor and verify activity level results by implementing partners. UNICEF are also piloting improved monitoring tools for internal use in October to December 2015, which aim to place a greater focus on measuring outputs and outcomes.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process