Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	July, 2015

Title: Support to the civil society in Tanzania: Foundation for Civil Society Programme
Programme Code: 113540-102	Start: June, 2011	End Date: March, 2015

Summary of Programme Performance

Year	2011	2012	2013	2014
Programme Score	A+	A+	A+	A
Risk Rating	Low	Low	Low	Low

Financial Position

Original programme value	£8m (June 2011- March 2015)
Extensions/ amendments	First cost increase of £0.8m approved in October 2011 / Second cost increase of £1.84m approved in November 2014
Log-frame revisions	There were no amendments to the logframe during the project cycle.
Total programme spend	£10.64m

Follow up actions required following closure

DFID has made a decision to continue support to the FCS, subject to the formulation of a Business Case (BC) based on further appraisal of the following key issues:

  - Identify a sharper functional focus of FCS, possibly defined by: a) contextualized regional/zonal themes; b) managed themes and open windows; c) retained focus on gender equity, social inclusion, communal conflict prevention, and more institutionalization of PETS & SAM; d) develop/strengthen focus on: parliamentary work and enterprise development for youth and women;
  - Sharpening the FCS strategic role: FCS needs to re-conceptualise its strategic role, given the changing local political and international development landscape. It needs to re-vision its role as a professional service provider, consolidating its unique strength in affecting ‘soft’ democratic change by working at the intersection of three policy frameworks: government policies on citizen engagement and enhanced public accountability; donor interest in public accountability and improved service delivery in particular sectors; and FCS’s own commitment to deepening democracy and pro-poor development;
  - Sharpen the ToC to further demonstrate how FCS will seek to support grantees to “work with the grain”, set modest attainable targets and secure positive changes in terms of institutionalising public accountability.
  - Construct a shared FCS-donor logframe/results framework which is updated annually in line with actual donor commitments and disbursements;
  - FCS to make a regular PEA so that it can locate and calibrate its strategy in the context of historic drivers and contemporary dynamics of democracy and public accountability.

FCS to submit a formal application to DFID to request a total write-off of irrecoverable bad debts by some of its grantees as at Dec 2014 (see attached annex one for more details).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	FCS Business Case
DevTracker Link to Log frame:	FCS Logframe

Outline of programme and what it has achieved

Programme objectives: This Project Completion Report on DFID support to the Tanzania Foundation for Civil Society (FCS) covers the period June 2011 to March 2015. DFID has provided £10.64 m over this project cycle to support Civil Society Organizations (CSOs) in Tanzania through FCS to ensure that increasing numbers of citizens, especially the poor and marginalized, are empowered to influence and monitor policies that meet their development needs, and participate in the budgeting processes for improvement of service delivery. This support is an extension of programme started in 2009. The logframe for the current programme of support sets out the following objectives: The expected impact is “Tanzania is democratically governed and has achieved its 2025 vision in the fight against poverty and a better quality of life for all its citizens.” The expected outcome is “More citizens (especially the poor and marginalized) are more empowered to participate, influence and monitor pro-poor policies and budgeting processes for improvement of service delivery in Tanzania by 2015.”

These higher-level goals are to be achieved through delivering of five outputs:

1. More citizens are aware of their civic rights and responsibilities.
2. Increased CSOs role in contributing to improved transparency at a local level i.e. how Local Government Authorities (LGAs) / Government of Tanzania (GoT) allocate and utilize resources.
3. Increased CSOs involvement on empowering women, addressing gender inequalities and issues affecting other vulnerable groups.
4. Strengthened CSOs organizational capacity and policy engagement effectiveness.
5. Foundation for Civil Society (FCS) delivers high quality services and is efficiently and effectively managed and governed.

Summary of Programme Achievements: There is broad consensus among key stakeholders, and especially government partners and grantees who were consulted by external reviewers, that FCS has established itself as vital agency in advancing principles central to the historical process of democratisation and embedding systems of public accountability by educating citizens on their rights, empowering them to engage with structures of governance, and encouraging the formation of community groups as CSOs with purposive developmental objectives.

FCS main success can be summarised as:

Creating and nurturing the nascent ecosystem of plural democracy and processes of democratisation which engage citizens, enabling the emergence of formal ‘modern’ civil society structures. This provides the essential foundation for the vibrancy of national CSOs and complements programmes such as the DFID-financed Accountability in Tanzania (AcT) programme;

The summary tables below vividly illustrate the range and depth of FCS’s work: over 25 million people reached, and over 1,700 CSOs supported and strengthened to undertake work, notably in the areas of

  - Governance & Accountability (Public Expenditure Tracking System (PETS) and Social Accountability Monitoring (SAM);
  - Political and development rights: Voter education; participation in constitutional review process; entitlement to services (esp. Health, Education, Agriculture) in line with National Strategy for Poverty Alleviation & Vision 2025; gender equity and social inclusion

FCS Key Result Area
YEAR	Policy Engagement	Governance	CS Capacity Building	Total
2011	813,474	2,037,152	273,100	3,123,726
2012	3,740,511	4,306,289	66,063	8,112,863
2013	6,797,366	5,193,137	40,870	12,031,373
2014	528,398	284,152	1,890	814,440
Jan – Mar 2015	5,410	1,024,135	686	1,030,231
No of people reached	11,885,159	12,844,865	382,609	25,112,633

Summary results compiled by FCS for the PCR review, July 2015

FCS has pioneered a Theory of Change (ToC) based on working with government, based on its legitimacy as a uniquely Tanzanian body, by supporting CBOs / CSOs (and their networks) to work with LGAs, on common causes aligned with government policy objectives. At the national level it has worked with the House of Representatives in Zanzibar and the National Assembly. The latter offers potential for expansion in the future.

Institutionalising tools to hold governance structures to account, i.e. through PETS & SAM, and doing this in collaboration with government partners by aligning this work with government development priorities.

Organisational development of CSOs, addressing the core issue of the operational capacity and effectiveness: planning and financial management; anti-corruption; and increasing the use of ICT.

Advancing the discourse on issues of gender equality, women’s rights and social inclusion, particularly in the areas of land rights, Gender based violence (GBV), Female Genital Mutilation (FGM) & inheritance rights, and discrimination of people with disabilities.

Climate Change and Environment. Funding to this thematic area covered issues central to tacking climate change, including: fishery policy, environmental policy, forest policy, and wildlife policy

Although MKUKUTA (the government’s official poverty reduction strategy) foresees a role for Non-State-Actors in the reduction of poverty in Tanzania, understandably, there are no formal institutionalised arrangements which compel ministries, departments and agencies (MDAs) to engage with CSOs over matters to do with resource allocation and service delivery. This is the space into which FCS has added value, as a constructive broker especially at the local government level, between Government institutions and local CSOs & community based organisations (CBOs). Tanzania’s ‘modern’ civil society movement appears eager to play a more active role in the country, and consolidate the democratic gains and values of the multi-party liberal model of democracy adopted by the country in early 1992. This reflects similar trends on the media front, which too has grown rapidly and vigorously since the mid-1990s.

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The outcome of the programme is “more citizens are more empowered to participate, influence and monitor pro-poor policies and budgeting processes for improvement of services in Tanzania by 2015.” To achieve this outcome, FCS interventions are focusing on three key results areas (KRA) namely:

- Policy Engagement: Citizens are able to influence and monitor policy processes
- Governance and Accountability: Citizens are aware of their rights and responsibilities, and able to demand accountability from public resources
- Civil Society Capacity Strengthening: Having in place a creative, imaginative, effective, sustainable and accountable civil society sector

FCS’s own assessment of its achievements of outcome during the implementation of its strategic plan is as shown below:

Key Results Area (KRA)	Outcome Indicators	Baseline (2010)	Target	Achievement
KRA 1: Policy Engagement	OUTCOME (1) Proportion of citizens saying that they have influenced a policy	20%*	100%*	87.86%**
	OUTCOME (2) Percentage of citizens saying that they make a difference by publicly expressing their views on local issues that affect them	53%	65%	87.76%**
KRA 2- Governance and Accountability.	Outcome(1) Proportion of citizens expressing satisfaction on the quality of delivered basic services by the government institutions (increased from 44% in 2007 to 60% in 2014)	44%	60%	54.55%**
KRA 3- Civil Society Capacity Strengthening	OUTCOME (1) Increased proportion of citizens trust of CSOs/CSOs officials	51%	70%	59%
	OUTCOME (2) Percentage increase of grantee with audited accounts	31.46%	50%	54.3%
	OUTCOME (3) Percentage of CSOs producing annual report and circulating to stakeholders	54%	100%	79.77%**
	OUTCOME (4) Proportion of FCS supported CSOs with overall impact capability	55%	70%	85%
KRA 4- Capacity of the FCS improved	OUTCOME (1) Percentage of grantees who are very satisfied or satisfied with FCS services	40%	90%	73%
	OUTCOME (2) Percentage of CSOs supported by FCS that implement projects in rural areas	40%	75%	51%

Note: ** data collected through a survey done by the FCS. Methodology used was an online survey using QuestionPro survey software. Purposive sampling approach was used and the survey was sent out to 1300 respondents composed of grantees and non-grantees (but organizations that have applied for grants from FCS at least once).

Independent reviewers of FCS strategy 2009 – 2013 concluded that: ‘Overall, there are changes within the Tanzanian society - however small - where citizens are becoming more active politically for instance, by starting to voice dissatisfaction with various governance challenges. There is a strong belief amongst different actors that FCS’s work has contributed to this political evolution’.

Output Score and Description. A+

The table below summarises the historical performance of FCS against annual and cumulative targets over four years. The results are very positive, and where success has been below expectations it can reasonably be attributed to two factors: the volatility and eventual reduction in donor funding; and structural factors outside the control of FCS which ought to have been better understood in the ToC (e.g. the number of women elected to leadership positions, a result which is contingent on overcoming structural and cultural barriers).

Table 1 Output Scores => Overall Score A+
	OUTPUT	2011	2012	2013	2014	PCR
1	More citizens are more aware of their civic rights and responsibilities	B	A	A++	B[1]	A+
2	Increased CSOs role in contributing to improved transparency at a local level i.e. how LGAs/GoT allocate and utilize public resources.	A+	A+	A++	B[2]	A+
3	Increased CSO involvement in empowering women, and addressing gender inequalities and issues affecting other vulnerable groups	A+	A+	A	B	A
4	Strengthened CSOs organizational capacity and policy engagement effectiveness	A+	A	A+	B[3]	A+
5	FCS is delivering high quality services and is efficiently and effectively managed and governed	A++	A++	A++	A	A+
[1] In 2014 FCS approved very few new grants; instead it concentrated on disbursing funds for ongoing contracts.
[2] FCS didn’t approve new grants in this area for 2014 but the target was already surpassed since 2013
[3] Again FCS didn’t approve new grants in this area for 2014 BUT the target was already surpassed since 2013 except for indicator number one less by 20 number of new CSOs supported

In summary, FCS’s performance was above expectations in the first 3 years. Thereafter, the termination of funding from SIDA, Ireland and Holland reversed the trend of exceeding targets.

Lessons and how these have been shared

Numerous lessons have been learnt from the FCS is programme:

FCS has established itself as a respected, independent Tanzanian foundation in the civil society landscape, uniquely placed to work with emerging and established CSOs and, critically, with government (at the national and local levels) on processes of deepening democracy. It reaches groups that other donor programmes do not reach. Notwithstanding its dependence on external donor funding – mostly from bilateral ODA partners - it has unrivalled credibility and legitimacy with government because it is an indigenous organisation;

Assumptions in the ToC that ‘Increased voice and accountability (V&A) lead to greater political accountability’ needs to be further tested and better nuanced. The ToC needs to be sharpened with a better understanding of the contextually specific dynamics of institutional change - the form and focus of demand and the loci of response i.e. structural drivers and incentives on the supply side.

“Working with the grain”. A key finding from external review of FCS and emerging from discussions with stakeholders is that – an effective way for civil society to secure positive changes in terms of institutionalizing public accountability is to work with government policies and partners; align the progressive initiatives of CSOs with government policies by providing ‘on side’ advocacy and support. Arguably this has been a more effective approach to promoting change than adversarial advocacy;

Actively facilitating the creation of CSO coalitions may seem to be a logical, attractive strategy to amplify demand. However, creating space for CSOs to meet, find common causes and for coalitions to emerge organically, may be an equally effective and sustainable strategy for mobilizing public demand for improved service delivery, alongside supporting spontaneous movements that emerge in the public space (and on social networking sites)

FCS’s outputs/results are ‘soft’ processes of democratisation, not immediately translating into hard structural changes enshrined in laws that define advanced democracies. However, significantly, these changes invariably provide the socio-cultural impetus, for ultimate ‘hard’, sustained change. In other words they are essential constituents of the process of democratisation, which leads to the system of democracy: the gradual accretion of democratic values on which the legal and structural architecture of democracy rests.

Sharing Lesson Learnt.

- FCS’s annual reports and regular newsletter are made widely available to showcase success stories and lessons to strengthening civil society. FCS should consider extending this to web-based approach using other social media such as WhatsApp to expand its audience.
- The joint monitoring visits with government officers have been very useful in educating them in the benefits of drawing in CSOs when government policies seek to enhance public accountability and citizen participation.
- FCS annual conferences have proved to be successful platforms for sharing learning amongst CSOs, involving both actual and aspiring grantees. Consideration should be given to holding one annual conference and one zonal/regional event annually.
- FCS’s unique role and effectiveness, based on its standing as an independent foundation, with a record for zero tolerance to corruption, has inspired other civil society support V&A programmes in other parts of Africa. (Notably STAR Ghana intends to graduate to an independent foundation, inspired by FCS).
- C: DETAILED OUTPUT SCORING (1 page per output)
Output Title	More citizens are more aware of their civic rights and responsibilities
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Base / line	Y1	Y2	Y3	Y4	End of Project Milestone	Actual Achieved
Number and quality of new CSOs supported to promote civic and human rights	0	Planned 15	15	15	15	60	153
		Achieved 13	33	104	3
Number of citizens enabled to access information on services, rights and entitlements	0.5m	Planned 1m	1m	1m	1m	4m	6.85m
		Achieved 0.94m	2.74 m	2.36m	0.81m
Number of new CSOs supported to increase citizens involvement in local government planning and budgeting exercises	0	Planned 15	15	15	15	60	42
		Achieved 26	11	5	0

Key Points and recommendations

Targets for 2 of the 3 indicators have substantially exceeded expectations. Both pertain to ‘information and rights’ interventions. The first indicator is a quantitative assessment of support from FCS to ‘rights’ promoting CSOs, and the second goes further, to number of citizens reached. Essentially both measure ‘citizens reached’ and the results are strong: >70% higher than expected; 6.85 m people educated against a target of 4 m. Two issues arise here

  1. Rights-focused information work is relatively straight forward, with the ToC offering a linear causal path, and the risks and accompanying assumptions manageable;

  1. Most of these interventions covered the constitutional review process, which excited enormous public and civil society. The fact that this massive nationwide information and consultation process ultimately resulted in minimal constitutional change confirms yet again the need to further sharpen the ToC. The assumption that amplifying public interest and demand for change will inevitably lead to State responsiveness and structural reform is particularly unlikely as the results have profound Political Economy consequences - in this case the revision of national, legally binding frameworks, based on the re-distribution and more open access to political power and public information.

Interrogating the successes of indicator three revealed that when there had been positive engagement with LGAs this required astute political lobbying by established credible, local CSOs, and linking these collaborative initiatives to current government policies and administrative directives which encourage MDAs to involve citizens (mostly) in planning (rather than budgeting) processes.

Summary of responses to issues raised in previous annual reviews (where relevant)
The guidance from previous ARs recommended increased FCS support to the constitutional review process. Clearly, this was seen as an indispensable opportunity to affect the fundamental democratic governance architecture of the country in a positive way, enshrining more open and democratic political and civil rights. The results of FCS’s educational and public engagement were very impressive in this respect, both in terms of CSOs supported, people reached and strategies deployed.

Output Title	Increased CSOs role in contributing to improved transparency at a local level i.e. how LGAs/GoT allocate and utilize public resources.
Output number per LF		2	Output Score	A+
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Base / line	Y1	Y2	Y3	Y4	End of Project Milestone	Actual Achieved
No. of new CSOs supported to mobilise citizens through the implementation of Public Expenditure Tracking Systems (PETS) at local levels	0	Planned 9	9	9	9	36	44
		Achieved 10	12	22	0
No. of new CSOs supported to mobilise citizens through the implementation of Public Service Delivery Surveys, including Social Accountability Monitoring (SAM), at local levels	0	Planned 5	5	5	5	20	34
		Achieved 12	7	15	0

Key points and recommendations
1. The striking point of note is that the cumulative targets were achieved and exceeded a year before the end of the project. In such a case the logframe would normally be revised, and new targets set. But as is apparent from the table above, the notional target was maintained, and no new grantees were identified – not because of a failure of endeavor, but because the drop in funding led to a planned reduction of the FCS portfolio.
2. The introduction and institutionalisation of PETS and SAM instruments has been one of the most noteworthy successes of FCS’s work, exemplifying the importance of ‘working politically’, i.e. taking into account political economy analysis (PEA). The lesson here is that if CSOs are to facilitate citizen engagement with LGAs / GoT they need to have legitimacy and credibility with government partners, know the political landscape, and locate PETS / SAM training and application within the framework of a sympathetic government policy framework. These opportunities have mostly been facilitated by the Ministries Community Development, Education, Health and Agriculture.
3. Three positive externalities are reported by stakeholders from such collaborative projects: (a) Citizens trained in successful PETS / SAM projects have carried this experience to other contexts (e.g. from Health to a school Parent-Teachers Association); FCS figures suggest that more than 0.3m[4] citizens have been trained in PETS & SAM technologies. (b) The relevant MDA has come to see the facilitating CSOs in a positive light and sought partnership on other development projects. (c) Success has inspired the formation of new CBOs[5].
  [4] “more than 352,523 Citizens have increased their knowledge on SAM and PETS following PETS/SAM trainings conducted countrywide” Figure obtained from FCS.
  [5] Findings from field visits undertaken by the PCR consultants and workshops held with stakeholders
4. The potential and power of CSOs working with media, especially at the local level, to promote transparency is absent from the logframe. In consultations with CSO representatives in Mwanza (during the pcr review) this was presented as an effective strategy to be pursued alongside PETS & SAM. Experience from similar projects in Nigeria and Ghana support this view – especially if this is preceded by training on budget analysis techniques.

Summary of responses to issues raised in previous annual reviews: Previous reports recommended “that FCS needs to continue to strengthen its monitoring and information system to better aggregate results under different outputs and themes e.g. PETS, SAM etc. to clearly articulate overall achievements and results.” Our finding is that FCS’s M&E systems have been sub-optimal through the project cycle. We comment on this issue in the section on M&E at the end of this report.

Output Title	Increased CSO involvement in empowering women, addressing gender inequalities and issues affecting other vulnerable groups
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Base / line	Y1	Y2	Y3	Y4	End of Project target	Actual
1. Number and quality of new CSOs supported to sensitize women on their rights	0	Planned 36	36	36	36	144	118
		Achieved 38	44	36	0
2. % of women enabled to take up leadership positions in CSOs/communities	0	Planned 35%	35%	50%	50%	50%	36%
		Achieved 36%	36%	36%	36%
3. Number and quality of CSOs supported to address issues affecting people with disability, pastoralists and other minority groups	0	Planned 20	20	20	20	80	134
		Achieved 25	45	55	9

Overview: the overall assessment is that FCS work in this area is progressive and commendable, despite the scores from the indicators used. We have therefore awarded an A for this Output for two reasons:
Progress against the target for Indicator 1 was consistently above the milestone for the first three years of the project cycle. The funding crisis precipitated by the reduction in donor funding meant that no new projects were funded in this area in the final year, resulting in the cumulative target not being achieved. Clearly it is unreasonable to hold FCS responsible for this eventuality.

Indicator 2 is flawed from a ToC perspective. Enabling women to take up leadership positions in organisations is not a matter of advocacy only; it usually requires structural drivers and fundamental change in social beliefs. (For examples from work around the world and regionally cf. local government initiatives in Rwanda and Uganda, guaranteeing women representatives a proportion of seats in governance structures – supported by law).

Key points and recommendations
The detailed data in FCS’s portfolio suggests that FCS has not been afraid to address challenging gender equity and social inclusion issues, and has supported CBOs / CSOs even in areas with pronounced normative resistance. 6 issues stand out: GBV (including FGM); inheritance and land rights for women; access to education for girls; issues affecting Persons with Disability (PWD); de-stigmatizing of people infected with HIV; and tackling discrimination against albinos. This work should provide valuable ToC lessons for the wider CSO community at future learning events.

Many of these challenging initiatives supported emerged from discussions with nascent CBOs which were nurtured into CSOs. Any future funding strategy that moves away completely from funding small and embryonic CBOs / CSOs presents the danger of losing this imperceptive but vital edge of social reform.

FCS’s own governance structures and senior management team are interesting in their gender profile:

- 6 Members in total: 2 are women and 4 are men. The President is a woman
- 7 people on the Board of Directors: 3 are women and 4 are men. The Chair is a woman
- 7 on the Senior Management Team: 4 are women; 3 are men. The Executive Director is a man

Summary of responses to issues raised in previous annual reviews. Nil

Output Title	Strengthened CSOs organisational capacity and policy engagement effectiveness
Output number per LF		4	Output Score	A+
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Base / line	Y1	Y2	Y3	Y4	End of Project target	Actual
Number and quality of new CSOs supported on institutional and organizational capacity	0	Planned 90	100	100	100	390	370
		Achieved 171	92	107	0
% of policy dialogues with active participation of CSOs	25%	Planned 60%	35%	80%	80%	80%	82%
		Achieved 30%	76%	82%	82%
Proportion of FCS-supported CSOs with improved overall impact capability	55%	Planned 60%	65%	65%	65%	65%	85%
		Achieved 61%	68%	85%	85%

Key Points and recommendations
All the three indicators’ targets were achieved for this output.
As the chart below illustrates, Organisational Capacity of supported CSOs has improved over the project cycle, over all dimensions except one, with governance and financial management among the main areas.

There have been three important consequences of this success:

(a) Informal CBOs have matured into formal CSOs. Without exception, those met by external reviewers on field visits said that their success had inspired greater local community volunteerism and the formation of CBOs and formal CSOs.

(b) As CSOs have matured through FCS’s capacity-building support, they report achieving greater impact. Further, they have achieved this with the incorporation of VfM principles and systems. This represents a profound change in the way CSOs are beginning to conduct themselves across Tanzania.

(c) Several CSOs reported that FCS-led organisational development had enabled them to secure funding from other sources.

FCS work in enabling policy dialogue has been particularly promising. Two areas offer potential strategic impact in future:

  1. Linking Citizens, CSOs and Legislatures. Earlier work on organising CSOs around 4 Bills which potentially reduced democratic space were followed up by facilitated meetings between specialist CSOs and parliamentarians.

  1. FCS’s standing as a local Foundation and its network of CSOs provided the platform to organise policy dialogue sessions countrywide on the constitutional review process. The machinery can be readily mobilised for other similar pro-democracy campaigns and structured governance processes such as the conduct of free, fair and peaceful elections.

Output Title	Foundation for Civil Society is delivering high quality services and is efficiently and effectively managed and governed
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of monitoring visits to grantees	Total planned over four years: 1,260	Achieved over four years: 1,329
Number of applications received and processed on time	Target over four years: 7,000	Achieved over four years: 7,975
% of CSOs supported by FCS that implement projects in the rural areas	Target 2011: 50% / Target 2012: 65% / Target 2013: 75% / Target 2014: 75%	Actual coverage 2011: 59% / Actual coverage 2012: 61% / Actual coverage 2013: 51% / Actual coverage 2014: 53% / (based on disbursements)

Key Points
Indicators (1) and (2): FCS exceeded its targets for Indicators (1) and (2)

Indicator 3: Programme inclusiveness measure: The indicator arises from the statistic that 75% of Tanzanians live in rural areas. The target was not achieved despite considerable efforts. FCS targeted those rural districts from which few fundable applications had been received with information sessions and invited local CSOs to attend. Despite this, the application rate did not significantly increase, and the quality of those received was low compared with urban-based CSOs; in particular they had low implementation capacity. Some urban-based CSOs proposed to implement projects in rural areas but they too frequently failed to demonstrate either their capacity to implement there or how their work would be sustained after they left the project area. In 2014, only 54 grants were approved following a policy decision to reduce the portfolio size. Given the small size of the sample, a percentage based on percentage of disbursements utilised for projects in rural areas was considered a more accurate measure.

Summary of responses to issues raised in previous annual reviews (where relevant)
None

Recommendations for future programmes

Suitable FCS performance measures should be considered under VfM measures rather than as a programme output.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Year	Total Funding m USD	Expenditure			Total Expenditure m USD	Overhead %
		Grants	CD	Overhead
2011	10.0	7.2	2.0	1.6	10.8	15%
2012	14.3	9.1	2.2	1.9	13.2	14%
2013	9.8	6.7	1.9	2.2	10.8	20%
2014	9.1	5.4	2.2	1.7	9.3	18%
Total	43.2	28.4	8.3	7.4	44.1	17%

Economy
FCS total spend over 2011 – 2014 was $44.1m. FCS successfully managed to maintains an overall overhead ratio of 17% as outlined above. Average costs during 2011-2014 were:

- Staff salaries/benefits (36% of total overhead);
- Office rental and service charge (11% of total overhead)
- FCS-commissioned audits of grantees (6% of total cost of grant making and capacity development activities)

FCS overhead costs are driven by: a) number of grantees. Grant portfolio at year end was as follows. 2011: 733; 2012: 890; 2013: 1,067; 2014: 653; and b) Number and quality of grantee visits (due diligence, capacity development, monitoring, audit). The 2011 BC focussed on overhead costs. It did not anticipate the rapid increase in the grant portfolio or the increased significance of audit costs, driven by a greater focus on grantee financial scrutiny in 2013 and 2014.

Quality of inputs: Headline findings of a PwC review[6] are consistent with the PCR reviewers’ findings that FCS has highly committed and competent staff and strong leadership. The quality of both the FCS staff and the external consultants who provide training, due diligence, monitoring and audit of CSOs was highly praised by a sample of 28 CSO chief executives (W: 10; M: 18). The office is of good quality. No concerns were raised about the quality of forums, conferences and exhibitions.
[6] Partner Risk Assessment of the Foundation for Civil Society, PwC, commissioned by SDC, 3rd February 2015, page 19.

The Procurement Process: The procurement process was reviewed in detail by PwC and judged proportionate to the ‘rudimentary’ level of procurement undertaken by FCS. Guidelines were described as ‘comprehensive’ and ‘in line with good practices’ (page 27), and ‘most of the procurement undertaken by the Foundation corresponded to the needs thereby achieving Value for Money’ (page 28). Only minor recommendations were made. The PCR reviewers’ findings concur: FCS appears to have an effective Procurement Committee that categorizes purchases using suitable materiality criteria, gets competitive quotes where appropriate, benchmarks costs, weighs cost/quality trade-offs and gets user feedback on quality.

Benchmarking: Staff salaries are benchmarked against market rates for Dar-based CSOs (ignoring some high outliers). Significantly, salary offers have sometimes been made below market rates under pressure from the overheads percentage VfM measure; this is discussed below. Office rent is at a market rate for the location but high compared with other city locations, such as Masaki. Venues at a suitable quality for the annual conference are few; cost/quality assessments are made of plausible venues; the rate paid reflects the strategic importance of this event.

Cost Savings: As a well-established organisation with mature systems and a portfolio of grantees growing faster than planned, there was no scope for savings on staff, the principal cost. There is potential for a significant saving on office costs either by renting in a cheaper area of town or by moving into FCS’s own premises, once these have been extended and refurbished. FCS has commissioned two business process reviews, of grant-making and finance; both should result in more streamlined systems.

Efficiency
A topline indicator of efficiency is the overall output score A+. Outputs generally exceeded targets while inputs were held to budget. Various sources of evidence[7] confirm the PCR reviewers’ finding view that systems generally, while well thought through and efficient, were often under-resourced. From an external perspective, CSOs reported that the due diligence, training, capacity assessment and audit tools used by FCS staff and consultants were well-designed and administered. Productivity of staff has been very high (considerably exceeding their activity targets), but at the cost of a number of (mostly minor) deficiencies. The PCR reviewers probed areas of organisational weakness identified both by the PwC report, the KPMG review of the grant-making system, and internal audit reports. The principal weaknesses arose from under-resourcing[8].
[7] The PwC review mentioned above, a KPMG review of the grant making system (2014) and various internal audit reviews (2013 and 2014)
[8] FCS: Review of Grant Making System, KPMG, 2014: Key Improvement Area, page 4; PwC Risk Assessment, page 35

Equity
FCS’s record on equity is discussed positively above under Output 3.

Effectiveness
A topline indicator of effectiveness is the overall outcome score which was A. From a VfM perspective, the key effectiveness issue is whether FCS manages for effectiveness, or to put it another way, whether it is results-focused. By this is meant: that FCS has a convincing ToC on which is based a clear results framework; that it manages its activities to achieve the results in its results framework; and that it has good M&E and accounting systems to track and report on its activities, outputs and costs. Finance systems are good, as noted above; the other issues raise larger questions discussed elsewhere in the report.

VfM performance compared to the original VfM proposition in the business case
The BC’s core VfM proposition has been vindicated:
1. The donor basket funding mechanism has low transaction costs; DPs confirm this.
2. FCS is an efficient and effective grant-making and capacity development organisation that has proved capable of controlling its overhead costs while delivering against targets. This remains the case.

The BC’s specific business standards expectations have also been met
1. Develop and implement a HRD plan; this was done.
2. Continue the Foundation’s adherence to International Financial Reporting Standards and commission an annual external audit; this was done.

The BC’s specific VfM Indicators have been exceeded.
1. Overheads as a percentage of total costs cost for the period were 17% (Target: 18%)
2. Total number of applications for the period was 7,975 (Target: 7000)
3. Total number of grant disbursement for the period was 1,496 (Target: 1,200).

Assessment of whether the programme represented value for money
The PCR concludes that the programme represented good value for money. The core proposition of the BC was vindicated: a range of evidence supports the conclusion that FCS is an economical, efficient, effective and equitable organisation. Transaction costs with DPs have been low. Specific business standards set in the BC have been met. Financial management has been good. Overhead costs have been controlled. Finally, quantitative VfM targets have all been met. In addition, FCS results are impressive: reaching over 25 million citizens country wide; advancing the discourse on issues of gender equality, women’s rights and social inclusion, particularly in the areas of land rights, women’s issues (Gender based violence (GBV), Female Genital Mutilation (FGM) & inheritance) and discrimination of people with disabilities; and addressing the core issue of the operational sustainability and effectiveness: planning and financial management; anti-corruption; and increasing the use of ICT.

Performance against budget. Overhead costs have not shown significant variances from budget. Grant disbursements and grantee capacity development (CD) have shown significant variances in response to opportunities (specifically the constitutional consultation) and grantee CD needs, in a context of volatile donor funding.

Basket Funding (contributions in USD$ millions)
Year	DFID	SDC		Dutch Embassy	Norway Embassy	CIDA	DANIDA	Comic Relief	Total: Basket Fund	Basket Funding as % of Total Funding
2011	3.0	0.9	2.6			0.5	1.8	0.9	9.8	98%
2012	4.9	1.5	1.9		2.6	0.4	1.7	0.9	13.9	97%
2013	3.3	0.7			2.4		1.7	0.8	8.9	92%
2014	6.5					1.8		8.2	90%
Total	17.7	3.1	4.5		5.0	0.9	7.0	2.6	40.9	95%

Total funding Contrib.	41%	7%	10%		12%	2%	16%	6%	95%
Contrib. to basket	43%	8%	11%		12%	2%	17%	6%	100%

1. DFID has been the largest and most consistent funder to FCS, contributing 43% of the basket funds and 41% of total funds, and over 70% of FCS’s funding last year.
2. The % of funding from the ‘basket donors’ (6 ODA agencies + Comic Relief) as a % of total funding reduced every year. The contributions of 4 small funders, AJWS (2011-14); Trade Mark East Africa, ILO & IRC, (2013 & 2014), though small, became progressively more valuable to FCS in the last two years of the project cycle.

Quality of Financial Management during the programme
Financial management of the programme has been good. FCS submits narrative and financial reports on time and produces a very detailed annual report. FCS was externally audited on schedule each year by a Big 4 auditor, received clean audit reports and raised no major accounting or audit issues. The PwC report states: ‘The financial management and control systems at FCS appear to be robust’[9]. FCS was on budget for overhead costs. Successive reviews of the Finance and Administration function have found a number of mostly minor deficiencies in both systems and compliance[10]. A full business process review is now underway to install an Enterprise Resource Planning (ERP) system and revised procedures; FCS’s Executive Director (ED) is addressing specific lapses noted by the 2014 audit management letter.
[9] The SDC/PwC risk assessment, Section 4.1, page 51, first line
[10] The SDC/PwC risk assessment; FCS Internal Audit of Finance and Administration, 2013; the KPMG 2014 audit management letter.

## E: RISK (1/2 page)

Quality of risk management over the life of the programme
Risk management has generally been good. The BC risk assessment was low. The following risks were recognised by the BC; and where they materialised they have been managed as follows:
1. Restriction of political space through legislation or reduced state responsiveness. This materialised progressively through the project cycle and has been difficult to manage. FCS facilitated progressive CSO coalitions over the constitutional review process and contact between select CSOs and Parliament over 4 regressive Bills. State responsiveness to demand has not been straightforward at national and local levels and requires a re-thinking of this aspect of the ToC in future.
2. Members or directors bring a political agenda, undermining governance/management. This did not materialise.
3. Competing grant-making programmes attract funding away from FCS. This did not materialise: there is no comparable body capable of effectively reaching a wide range of CSOs of all sizes in all districts.
4. Funders reduce or fail to provide agreed predictable funding to FCS. Funding surged in 2012 then fell back to a level 26% below the BC funding forecast in 2013, and dropped again in 2014. This hampered resourcing and forced a reduction of 90% in grant-making in 2014. Funding volatility remains the major threat to FCS: its probability must be reckoned as medium/high, with high impact.
5. Members and the Board of Directors fail to adequately discharge their duties. This did not materialise. Meeting records and interviews confirm that both bodies discharged their duties well.
6. Professional malpractice in the grant selection cycle. This did not materialise. Grant-making systems and controls are strong with one structural defect: the absence of an Audit Subcommittee at Board level. This was rectified in 2015. The Narrative Report discusses FCS integrity measures. Grantee misuse of funds or failure to account for funds is at a low level (below 2% of the portfolio), and FCS energetically pursues non-compliers.
7. Financial mismanagement. This did not materialise. See the relevant section of the Narrative Report.
8. Inability to demonstrate results due to inadequate capacity and complexity around monitoring a small grants portfolio of over 700 projects. This risk has materialised. Due to inadequate capacity the M&E department failed to capture and analyse results in a sufficiently systematic way to provide a sound basis for judgements on programme impact; it is now under new leadership and is reforming its processes.
9. The BC did not anticipate the risk arising from under-resourcing. As discussed above, FCS was persistently understaffed and overworked. This led to slip ups in staff performance noted both by internal audit and external systems reviews

Risk Management – Looking Forward
As discussed above, FCS risk management has been very good. Looking forward, FCS clearly recognises that there are two major risks, only one of which it can control:
(A) Funding volatility for reasons of donor policy outside FCS’s control.
(B) Loss of its excellent reputation for integrity, leading to loss of confidence among donors and in Civil Society generally.

Funding Uncertainty
Funding uncertainty has been pervasive and remains so. Several FCS donors ceased funding in the period due to internal policy changes; FCS is exposed to this happening across its entire donor base. While attempting to diversify its funding base and take measures to acquire its own assets (a building), FCS remains entirely donor funded. Donor funding volatility thus remains a high and continuing risk to FCS’s existence, with high potential impact. ‘Sustainability’ as currently conceived remains a mirage; however, a change in the funding relationship to a more business-like footing as recommended below would provide FCS with the opportunity to increase reserves and hence strengthen itself financially.

Maintaining FCS integrity
The paramount importance of maintaining FCS’s integrity, and its reputation for integrity, was a theme of the 2011 BC and remains a central concern for FCS. Members, directors and senior managers have generally performed well, in some cases outstandingly well. The governance structure is sound with one significant structural deficiency, and members and directors appear to have discharged their duties well and without apparent political bias. The deficiency was related to Internal Audit. Internal Audit reports have been of high quality. However, until 2015, Internal Audit reported to the ED; from mid-2015, it will report to an Audit Subcommittee of the Board of Directors. A three person subcommittee has been appointed and new charters for the Audit Committee and the Internal Audit function are in draft at date of writing.

External financial scrutiny has been strong. FCS is subject to annual external audit by a Big 4 firm; the audit ToR extends to an audit of the larger grantees (those with ‘Strategic Grants’). All audit reports have been clean. The 2014 management letter was comprehensive and drew attention to a number of deficiencies; these are being acted upon; none were of a significance to qualify the audit report.

External systems scrutiny has also been strong: KPMG made an exhaustive review of the grant-making function; PwC made an exhaustive review of administrative systems. It is recommended that FCS has periodic external systems audits both for its own learning and to provide donors with value-for-money assurance in the context of a redefined funding contract

Internally, systems are well thought through with a high degree of separation of duties. A grant partner may be visited and assessed by staff from any or all of the grant-making, capacity development, M&E, and Internal Audit departments. Effective due diligence seems to have largely forestalled funding of unsuitable or corrupt CSOs. There are strict financial reporting requirements.
In addition to the strategic grantee audits conducted as part of the FCS external audit, many of the medium and small CSOs grantees are audited by FCS using an external firm. The external firm was chosen by competitive tender and reports to Internal Audit. Audit queries are followed up by Internal Audit; some grantees are re-audited. In 2014, a total of 354 grantees were audited out of a portfolio at year end of 653; from 2015 all large and medium grantees will be audited.

Anti-corruption incentives seem to be strong. Any attempt by a grantee or grant applicant to bribe an auditor or a member of staff invariably results in immediate termination of the relationship. Occasional attempts by grantees to bribe auditors appear to be promptly reported to FCS. The audit firm (Keppler) is clear that if an auditor were to accept a bride this would, at a corporate level, jeopardise their (substantial) contract with FCS, and at a personal level might lead to the disbarment of the auditor in question by their professional association. Finally, many grantees now commission their own external audits, the reports of which are made available to FCS. It seems clear that both FCS and its grantees will soon be as comprehensively audited as it is possible to be.

## F: COMMERCIAL CONSIDERATIONS
Delivery against planned timeframe: Programme delivery has exceeded expectations. FCS received, processed and approved considerably more grant applications than planned, as noted above. Where a substantial opportunity arose and donors came forward with funding, as happened with the constitutional consultations, FCS seized the opportunity and delivered results. Conversely, in 2013, funding did not reach planned levels and some approved grants were disbursed late or not at all as a consequence.

Performance of partnership(s). Partnership with the DPs has been smooth, as anticipated in the BC, with low transaction costs. A major stressor for FCS has been timeliness of donor disbursements which need to be much more closely linked to the FCS planning and implementation cycle.
FCS partnerships with grantees seem to have been generally good. This is attributable to a number of factors:
- Transparent and participatory tools and processes for CSO due diligence, capacity assessment, monitoring and audit, all of which involve debriefing the CSO and reaching agreement on findings.
- Annual open forum for grantees and non-grantees at which criticisms can be aired and discussed
- There is a strong sense of mutual respect between FCS and CSOs: FCS is willing to be open about its GM and CD criteria and practices, and willing to listen to the views of CSOs. This has been vital as a context in which to manage the considerable friction arising from late disbursement of funds to CSOs by FCS, who were in turn awaiting donor disbursements.
Asset disposal and value obtained by DFID
There is no asset disposal; the programme is continuing.
## H: MONITORING AND EVALUATION (1/2 PAGE)
Evidence and evaluation
A key finding of this PCR emerging from discussions with FCS stakeholders – officers from relevant MDAs and grantees – is that an effective way for civil society to secure positive changes in terms of institutionalising public accountability is to work with government policies and partners; align the progressive initiatives of CSOs with government policies by providing ‘on side’ advocacy and support. Arguably this has been a more effective approach to promoting change than adversarial advocacy.

FCS work at the local level exemplifies this. Three overlapping and inter-related government policy frameworks, which FCS grantees worked with, were remarked on by government partners: the decentralisation policy; the historical encouragement to communities to participate in development planning processes; and more recent pronouncements by the ruling party asking citizens to hold their local governments to account.

Three approaches supported by FCS through local level CBOs have been crucial in this respect: a) Education on rights and entitlements– especially in the areas of health, agriculture and education; b) Empowering citizens to engage in planning processes; and c) the use of PETS and SAM instruments. These approaches – notably PETS & SAM – have led to positive externalities, with citizens trained in these tools applying them to disparate other contexts, e.g. carrying the learning accessed through membership of farmers group supported by an agriculture focussed intervention to a parent-teacher association in a school.

Two assumptions in the ToC need to be further tested and better nuanced: a) ‘Increased V&A lead to greater political accountability’ has become a simplistic truism. The ToC needs to be sharpened with a better understanding of the contextually specific dynamics of institutional change - the form and focus of demand and the loci of response i.e. structural drivers and incentives on the supply side; b) actively facilitating the creation of CSO coalitions may seem to be a logical, attractive strategy to amplify demand. However, creating a space for CSOs to meet, find common causes and for coalitions to emerge organically, may be an equally effective and sustainable strategy for mobilising public demand for improved service delivery, alongside supporting spontaneous movements that emerge in the public space (and on social networking sites).

Monitoring progress throughout the review period
Progress has been monitored through regular DPs meetings with FCS management and periodic joint reviews of implementing partners undertaken by FCS, DPs and invited government partners. The PCR review process was conducted by independent consultants. A conventional mix of documentary evidence and consultations was used to arrive at the findings and recommendations in this report and the accompanying narrative (detailed) report. These included: Previous DFID Annual Reviews (AR) of FCS; The FCS Strategic Plan; Programme and organisational reports covering the period under review assembled for the review team by FCS, inter alia, FCS’s published Annual Reports, 2011, 2012, 2013 and draft 2014 report; memo and Articles of Association; Minutes of Members and Board Meetings; Internal Audit Review; Internal Audit of Grants Process; Internal Audit of M&E system; and Internal Audit of HR Section; External reviews of FCS systems: a KPMG review of the grant-making system and a PwC systems review and risk assessment of FCS management and governance; Interviews and workshops with key stakeholders including: DFID, senior management team of FCS, FCS Board Members; workshops with a cross section of FCS’s grant partners (GPs) held in Dar Es Salaam, Mwanza and Mtwara[11], and individual meetings with FCS staff members; and A presentation of preliminary findings and recommendations was made to DFID and also discussed with the Executive Director of FCS at the end of the review, to test, validate and shape the findings.
[11] The meeting with GPs in Mtwara actually took place in July during the course of fieldwork on developing a Business Case for continued DFID support to FCS. However, we revised this report taking into account views from that workshop.

Key recommendations going forward: FCS and DFID have monitored progress on the basis of two separate results frameworks. Once FCS has defined its new Strategic Plan in September 2015, a common logframe should be collectively developed by FCS and funding partners. This should be based on reduced outputs (ideally no more than three which should be distinct with no possibility of overlap); reduced indicators; and refined ToC. The logframe should be reviewed annually, and if necessary revised on the basis of regular annual PEA, annual reviews, and up to date projections on funding commitments and reliability or otherwise of transfers from DPs.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process