Project Completion Review – post April 2018

Title: Western Region Coastal Foundation (WRCF)
Final Programme Value £ (full life): £9,500,000	Review Date: May-Sep 2019
Programme Code: 202476	Start Date: 30/01/2014	Final End Date: 30/04/2019

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2019
Programme Score	C	A	A+	A	B	B
Risk Rating	Medium	Medium	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202476/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202476/documents

A. Summary and Overview (1-2 pages)

Important Note: The WRCF programme was closed six months early in April 2019. This was because harnessing private sector financial commitments into the foundation for sustainability was not forthcoming. These achievements include the set-up of a dialogue mechanism to provide a platform for community engagement on the impact of oil and gas operations and facilitating conversations on the Technical and Vocation Training (TVET) framework and its impact on local employment prospects in the oil and gas industry. The logframe used in scoring the final PCR compared progress on the cumulative targets for both 2015 – 2018 and 2015 – 2019. This recognises the fact that the programme was closed earlier than planned and provides a balanced scoring of what should have been achived at time of closure. In this context, Section B of this review highlights important Lessons Learnt from the WRCF programme. These Lessons are comprehensively covered in a separate report that was compiled with the objective to inform and guide similar future DFID programmes. The Lessons learnt report will be published in addition to this PCR.

Description of programme and what it has achieved

The WRCF programme was designed in the context of helping to deliver the G8-Ghana partnership between the Government of Ghana and the UK Prime Minister agreed in June 2013. The programme was set up to achieve the impact: “To improve stability and inclusive development prospects in Western Region”; and the following outcome: “Expectations managed and met, and constructive relationships built between; communities, government and industry, thereby improving stability and inclusive development prospects in the region”.

The Business Case specified that the programme was set out to achieve this impact by means of two core objectives: (1) Reducing the risk of conflict – through increasing transparency and by deepening accountability between stakeholders; and (2) Strengthening local economic development – through improving the impact of available development funds by means of helping communities earn more income and more local businesses to supply the oil industry. To deliver these two core objectives, the programmes was designed to be set up and delivered in the form of a foundation. The Business Case’s theory of change and result matrix rested on the key assumption that the oil and gas (O&G) companies invested in Ghana would allocate parts of their Corporate Social Responsibility (CSR) budgets to a development fund managed by WRCF. It was assumed that a DFID contribution of £9.5 million would be complemented by an industry contribution of £16 million in the first five years of operation for the foundation. After five years, it was anticipated that the foundation would continue to receive industry funds to operate independently of DFID funding for a minimum of five additional years and with the expectation that it would do so until the end of O&G activities offshore the Western Region. The contract value with DAI was £8,428,419.

The programme set out two main delivery channels for achieving its two core objectives:
1. A dialogue platform aiming to bring together civil society, the private sector, regional (subnational) and local governments. Ideas, suggestions and grievances from the concerned residents were channelled regularly through the foundation’s dialogue platform to increase transparency and to deepen accountability between stakeholders.
2. Under its original design, the programme was envisaged to establish a Development Fund as the key vehicle to deliver and coordinate corporate social investments. It was assumed this delivery channel would generate better value for money (VFM) from CSR investments and alternative livelihood interventions (e.g. developing business value chains and skills development).

During the Inception Phase it became clear that the scale of a development fund under the foundation, co-funded by international oil companies (IOCs) could not be realised given the decline in oil prices and other factors. Notwithstanding, there was still a clear case for the programme achieving its planned impact based on engagements during the inception phase. This prompted the programme to alter its original strategy by aimimg to leverage corporate social responsibility spend from oil and gas companies towards community gain and development. Throughout the Implementation Phase, the programme retained the ambition to raise cash directly from the O&G industry to cover its operational costs by the time DFID funding seized. This endeavour was also complemented by specific activities targeting technical and vocational education and training (TVET), aspiring to plug the skills gap for direct and more indirect employment opportunities linked to the wider extractives sectors.

Setting up the Foundation: After the Design Phase and during the Inception Phase, the programme successfully established WRCF. The foundation was set up in compliance with Ghana law and is now independently managed and operated. As an independent organisation the Foundation is now left with the opportunity to prove itself as an independent entity shaping the delivery of oil and gas corporate social responsibility for community gain.

Delivering ‘voice’ to Coastal Communities: As noted in the programme’s MTR, the dialogue platform set up by WRCF to deliver ‘voice and accountability’ has indeed given voice to local communities in the Western Region. It has also collected quality information on social and economic issues of concern and fed these back to government and the industry to take into consideration for their potential responses. This mechanism reached over 90,000 Coastal community residents directly and engaged over 350,000 residents indirectly.

WRCF’s dialogue platform developed a trusted mandate amongst stakeholders who have perceived the platform as a means for raising company social performance issues (negative local impacts from O&G industry and grievances and claims for compensation arising from these) and community development needs. WRCF argues it has laid the foundation for more equal dialogue to take place through strengthening the capacity of Western Region communities to engage with O&G companies and government authorities. Stakeholders from industry, government and traditional leadership agree that WRCF’s dialogue platform served as a pressure vault for venting concerns and that it contributed towards ‘killing misguided perceptions’. Even if issues did not get resolved, its empowered community members’ who otherwise would not have had a voice. Continuing as an independent entity in the WRCF has been awarded a contract of $77,000 from Aker energy for a community needs assessment to inform Aker Energy’s CSR.

Establishing a reputation as an impartial actor in the Western Region on O&G sector related issues: Post-DFID funding WRCF remains perceived by most as an impartial and independent body that is recognised for having the convening power to bring together industry players and stakeholders. A testimony to this is the board structure and the Citizens Advisory Council.

Local economic development interventions were considered successful in two areas: (1) TVET training – in collaboration with Ghanaian education institutions, WRCF organised the delivery of training to industry employees, course instructors, and artisans. This activity stream received funding from industry and government; and (2) An aquaculture pilot project scaled up by industry – one of WRCF’s economic development pilots was taken to scale by ENI under its wider ‘Economic Diversification project in the Western Region’.

Key Programme developments

The programme comprised three phases: (1) Two-year Design Phase: started in 2011, and concluded with the approval of the DFID Business Case in December 2013; (2) One-year-plus-three months Inception Phase: started in October 2014, with DAI being awarded the implementation contract, and concluded in December 2015. It was during the Inception Phase that the programme was registered as a Foundation with a board of directors drawn from industry, government and traditional leaders; and (3) Three-year-plus-four months Implementation Phase: commenced in November 2016 and ended six months early in April 2019.

Table 1 show key changes to the logframe, Theory of Change (TOC) and reviews:
August 2016	The first amendment to the logframe. Key changes included amending the target of £16million cash leveraged from the O&G industry CSR funds. It was replaced by a dedicated indicator for non-cash resources leveraged from industry and a target focused on raising direct funding from industry to cover the foundation’s operational costs.
August 2017	Second amendment to the logframe, providing minor changes to output indicators moving to a focus on job creation and climate change mainstreaming.
Late 2017-Spring 2018	A mid-term review (MTR) of WRCF undertaken in November 2017 concluded that contributions from industry to WRCF were very unlikely to happen at the scale assumed in the Business Case. WRCF outputs were being met, but the missing ‘glue’ of CSR funding to the foundation raised questions on the assumptions underpinning the ToC, VfM, and sustainability. In December 2017, DFID and DAI agreed to revisit the Business Case. The MTR and extended MTR[1] suggested that WRCF increased its emphasis on ensuring financial sustainability.
September 2018	A final amendment to Logframe and ToC was approved. This was done to ensure the fundamental element of establishing a sustainable foundation was kept at the core of the programme ahead of the planned closure in October 2019. To take account of revisions to logframe and ToC, a business case addendum was approved by the DFID Ghana Head of Office in September 2018.
March 2019	An internal DFID KPI Assessment concluded that KPIs agreed in 2018 were not sufficiently met. It was assessed that 3 out of the 5 KPIs (selected logframe indicators) were met. The unmet KPI related to financial sustainability which was core to future of the foundation. DFID took the decision to close the programme six month ahead of its planned closure, given the financial uncertainty of the foundation. This was in accordance with the Business Case addendum and the contract with DAI.
April - May 2019	The WRCF programme was closed and the WRCF transitioned into an independent NGO.
[1] The mid-term and extended mid-term reviews was informed by a feasibility study conducted by KPMG in late 2017 (with the final report submitted in March 2018).

Note: Annex A and B outline in more detail the KPI assessments and its recommendation as well as three revision to the logframe.

Fundamental design challenges

The WRCF programme faced challenges from the Inception Phase. These challenges affected the programme’s ability to meet the expectations and objectives associated with its implementation. The remainder of this review and the overall scoring should be viewed in recognition of these challenges. In summary, these challenges have been:

- the implicit assumptions in the Business Case related to the critical expectation that private sector funding would sustain WRCF and accept its unilaterally pre-defined role as a ‘CSR delivery agent’;
- the failure to define ‘CSR’ in recognition of the private sector’s role and responsibilities in relation to corporate social performance and internationally recognised standards and good practices;
- the early decision to establish a foundation.

Comments on the reporting framework for this review

Results presented in Section B are assessed against two targets – (1) the cumulative logframe targets for 2015-2018 and (2) targets for 2015 -2019. This was done to provide a balanced view of progress at the time of shut down. In assessing these results, it should further be recognised that the WRCF logframe (revised in 2017 and 2018) includes revised outcome and output indicators. This was in line with the approved BC addendum. Thus, for the period prior to 2018 some indicators have not captured results. It is further noted that in many instances achievement of the envisaged results has not progressed since the Annual Report. Following that report, WRCF focused primarily on delivering the agreed five KPIs set for January 2019. DFID’s March 2019 decision to close the programme prompted WRCF to focus on achieving the KPI assessment recommendations and prepare for its transition to become an independent organisation from 1 May 2019 onwards.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	An independent, self-sustaining, open and inclusive dialogue platform for communities, government and industry established
Output number per LF		1	Output Score	B (assessed against Oct 18 target: B)
Impact weighting (%)?		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / 2015-October 2019 / (2015-October 2018)	Progress
1.1 WRCF MoU for funding executed (Government, Industry and donors) [New indicator 2018] / Linked to KPI 2 (not met): At least x1 MoU (or equivalent) signed with the Petroleum Commission, Industry or donors to fund continued dialogue platform work	Funding for the dialogue for at least one-year cycle. / (One MoU signed)	Output substantially did not meet expectation. Indicator Score: C / (Indicator Score assessed against Oct 18 target: C) / The driver for seeking an MoU with the PC was to secure corporate funding for the dialogue platform. The WRCF tried three times to put an MoU with the PC in place. The objectives of these efforts were: / In 2015 – “To establish a framework for cooperating on the achievement of the deliverables of Programme under the Commission’s mandate for Community Relations.” / In April 2018 – “To establish a framework for cooperating on the achievement of the deliverables of Programme under the Commission’s mandate for Community Relations”. / In Feb 2019 – “Request for formal endorsement through a Memorandum of Understanding (MoU) between the Petroleum Commission and WRCF” / By early 2019, it was confirmed that the PC would not sign an MoU. Its reason was that it could not endorse one local supplier above others. / Achieving endorsement by the PC was seen as a pre-requisite to secure funding commitments from O&G companies and other donors. Therefore, no dialogue-focused MoUs were submitted to industry or other donors[2].
1.2 No. of CSR interventions informed and influenced by WRCF dialogue data to address community needs [New indicator 2018]	15 / (5)	Output moderately did not meet expectations. Indicator Score: B / (Indicator Score assessed against Oct 18 target: A+) / There is no change respective this indicator since the Annual Review 2018. / In 2018, 10 CSR interventions were informed by data collected as a result of the 2016/2017 dialogue: / Three Economic Livelihoods enhancement activities funded by Jubilee Partners / Seven Water access interventions through boreholes funded by Cirrus Oil, Volta River Authority (VRA), Ghana National Petroleum Company (GNPC)
1.3. Non-DFID funds raised to sustain the dialogue [New indicator 2018] / Linked to KPI 3 (not met): At least £100,000 non-DFID funds raised/ committed in 2018 to sustain the dialogue platform in 2019	£500,000 (total committed by end of November 2019) / (£100,000 (committed by Jan 2019))	Outputs substantially did not meet expectation. Indicator Score: C / (Indicator Score assessed against Oct 18 target: C) / There is no change in this indicator since the Annual Review 2018. / Proposals were also submitted to industry: Vitol, Aker Energy, Kosmos, and Tullow Oil. Funding was not secured from any of these O&G companies at the time of PCR data collection. WRCF received approval for the AKER energy proposal in October 2019.
1.4 No. of relevant data sets collected and disseminated to partners as a result of community dialogue [New indicator 2018, but some data available for previous years]	6 / (3)	Output exceeded expectations. Indicator Score: A+ / (Indicator Score assessed against Oct 18 target: A+) / In 2018, three community conversation data sets were collected and disseminated to 13 O&G companies, the six Coastal District Assemblies and the PC. These have included: / Profiling and Mapping of Social and Economic Corporate Social Investments in 100 fishing communities / Community Satisfaction ratings and assessment of Corporate Social Investments / Assessment of safe access to sea by all users and livelihood issues among fishermen and fish traders. / In 2016, seven data sets were collected and disseminated. Four data sets from the 2016 citizens’ perception survey (PS) and three data sets from the 2016 dialogue (D) were shared with four O&G companies and all six district assemblies. These covered: / Poverty data (PS) / Citizens perception of O&G sector data (PS) / Political stability and development equity, and constraint to doing business in Western Region data (PS) / Demographic and socio-economic data (D) / Trending community issues data (D) / Community needs data (D)
1.5 No. of Western Region coastal district residents engaged in the Dialogue Structure (disaggregated by sex -50% male and 50% female and youth - 50% under the age of 30 years old) [New indicator 2018, but some data available for previous years]	66,720 directly reached 266,880 indirectly reached / (64,110 people directly reached 256,440 indirectly reached)	Output met expectations. Indicator Score: A / (Indicator Score assessed against Oct 18 target: A) / The number of residents reached exceeded the target, however, the gender and demographic composition targets were not met.[3] / The WRCF programme reached directly 91,727 and indirectly 366,908 coastal district residents through the Dialogue Platform. / Gender disaggregation of the data shows that 46.1% of the directly reached coastal district residents where female. / Youth disaggregation of the data is not possible across years as the definition of youth was 18-35 in 2016 and 2017 and 18-30 in 2018. There was not youth disaggregation in 2015. Individual youth figures are: 2016 48%; in 2017 40%; 2018 30%.
[2] Four MoU signed were signed with 4 industry partners mainly related to potential collaboration in the TVET space.
[3] Figures here are averages across Annual Reviews from 2015, 2016, 2017, and 2018.

Provide supporting narrative for the score

This output is aimed at ensuring the foundation raises funds to become sustainable and independent, as well as establishing a trusted and sustainable platform. The main purpose of the platform is to provide the six coastal districts residents with an channel to voice issues of concern and agree on priorities, and for these to be documented, analysed and shared with the O&G companies and local government to inform their decisions on CSR investments and government expenditure. Annex C outlines the full supporting narrative for this output.

Lessons identified this year linked to this output and recommendations for future programmes

- All stakeholders have seen some value in the dialogue platform, if only in terms of providing the residents of the six targeted coastal districts with a means to spell out their priorities, vent their concerns and raise their social and economic needs. There is some evidence that the discussions and meetings held have informed both local government and corporate decision-making on community-level (social) investments.
- The non-targeted nature of the dialogue platform was one of the elements that provided an unconvincing case to corporate budget holders to provide general funding for the platform. For the industry, it is therefore not surprising that WRCF failed to provide a clear value proposition on how the dialogue platform (as structured under the DFID programme) would contribute to companies meeting their social performance responsibilities. For example, these responsibilities relate to directly and indirectly ‘impacted’ communities and residents (i.e. not all six coastal districts), hence, WRCF did not appropriate ‘read’ the corporate responsibilities and conditions for effective community engagement.
- The suggestion from earlier years that WRCF should draw on the upstream regulator, the PC, and diplomatic channels to nudge companies into funding the dialogue platform, was shown to be misguided.

Output Title	Community livelihoods improved through Industry CSR support for economic development interventions
Output number per LF		2	Output Score	C (assessed against Oct 18 target: A)
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / 2015- October 2019 / (2015- October 2018)	Progress
2.1 No. of OGPs and other funders committing finance above £25,000 ($32,500) for scaling-up livelihood and economic development initiatives [New indicator 2018] / KPI 4 (met): At least x1 OGP and/or other funders/donors committed to finance over £25,000 ($32,500) for scaling-up livelihood and economic development initiatives	3 / (1)	Output substantially did not meet expectations. Indicator Score: C / (Indicator score assessed against Oct 18 target: A) / There is no change in this indicator since the Annual Review 2018. / Under the Off-shore Cape Three Points (OCTP) JV Project (ENI, Vitol and GNPC) through Technoserve, sponsored the construction of 43 aquaculture ponds, using the WRCF pilot model in their design. Per adopted pond model cost projections, x1 pond costs £800, the cost of 43 ponds was £34,000.
2.2. No. of beneficiaries trained on new aquaculture, climate smart agriculture and other economic development practices supported by industry [New indicator 2018]	160 / (60)	Output substantially did not meet expectations. Indicator Score: C / (Indicator score assessed against Oct 18 target: B) / The ENI livelihood project supported 56 beneficiaries with aquaculture intervention in 2018 and all beneficiaries received training from ENI.
2.3 No. of relevant economic development publication reports produced and shared with stakeholders [New indicator 2018]	5 / (2)	Output meet expectations. Indicator score: A. (Indicator score assessed against Oct 18 target A+) / In 2018, two evaluation publications produced on the aquaculture intervention and climate smart agriculture intervention. Both evaluation publication has been shared with stakeholders through the WRCF board (covering government, industry and traditional leaders). / In 2017, the WRCF produced two reports focused on “Opportunities for Oil and Gas Corporate Social Investment in the Fisheries Sector of Ghana’s Western Region”, and a Cassava test harvesting report. The first report was presented at the CAC and distributed electronically via email. The latter report was disseminated to its target audience (Tullow Oil, B-Bovid, and the Ministry of Agriculture) / In 2015, the WRCF produced the report ‘Leveraging economic opportunities for the six coastal districts of the Western Region’. It was disseminated to local government, industry and academia.

Provide supporting narrative for the score

This output aimed to improve community livelihoods through industry CSI interventions. It measures WRCF’s contribution to shaping and delivering such interventions. WRCF maintain that through a capacity building and mentoring approach, it facilitates socio-economic interventions to increase household incomes and to provide sustainable livelihoods to communities adversely impacted by the activities of O&G companies. Annex D outlines the full supporting narrative for this output.

The idea behind Output 2 was for IOCs to collaborate and co-design DFID funded pilot project and subsequently take these to scale. Designing and front-loading community development projects was in part informed by the dialogue platform’s economic and social database.

Lessons identified this year linked to this output and recommendations for future programmes

- This output emerged from the Business Case vision of the WRCF setting up a development fund co-funded by O&G companies. However, as the development fund did not materialise, WRCF decided to test the idea of developing economic development interventions for industry to take forward and scale up. The idea was to ‘show the way for industry’ similar to the idea that the development fund would improve the effectiveness and impact of poorly designed CSR spend. At the end, ENI scaled up the WRCF pilot on aquaculture. The uptake with industry could have been strengthened if WRCF strengthen partnerships, co-designed and co-created these pilots with industry partners.
- ENI’s decision to scale up the aquaculture pilot under their wider Economic Diversification project gives an indication that WRCF can potentially play a positive role in scoping, developing and managing corporate funded livelihoods projects, if companies decide to outsource to a third party.
- An assumption made early on during the pilot interventions was that industry would provide further direct funding to scale-up the interventions, making reproduction much easier and cheaper for new up-takers. While it did happen in the ENI case, the scale of it is nowhere near the envisaged level.

Output Title	Community TVET skills enhanced by facilitating dialogue and coordination with public and private educational and training institutions using a self-sustaining revenue stream to generate funds derived from industry
Output number per LF		3	Output Score	B / (assessed against Oct 18 target: A+)
Impact weighting (%)?		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones / 2015- October 2019 / (2015- October 2018)	Progress
3.1 No. of people trained on TVET skills related to the O&G sector and allied industries - disaggregated by students and artisans and industry employees (90% male, 10% female) [New indicator 2018]	600 / (200)	Outputs moderately exceeded expectation. Indicator score A+. / (Indicator score assessed against Oct 18 target A+) / Annual Reviews 2017 and 2018 report[4] : / 1053 people trained / 87 industry employees and artisans (from Takoradi Kokompe) trained in TVET skills related to oil and gas sector. / 966 students/welding students trained and benefitting from improved instructor capacity and curriculum. / 14% of beneficiaries in 2018 were female.
3.2 No. of Oil & Gas related courses supported by industry [New indicator 2018]	7 / (3)	Output moderately did not meet expectations. Indicator score B. (Indicator score assessed against Oct 18 target A) / There is no change in this indicator since the Annual Review 2018. / WRCF started the facilitation of training for welders in 2016. In 2018, four O&G related training programmes were supported by industry including welding, electrical, mechanical and hydraulics. / Greenline Logistics, Klloyds, Takoradi Gas provided support for welding through the CSI skills program, training of employees and provision of consumables. Support was also provided for electrical, mechanical and hydraulics through support for instructor capacity and corporate training programs by Siapem, Metka, AMS, Harlequin, Mantrac and Group 5.
3.3 No. of instructors trained to industry standard in OGP skills [New indicator 2018]	62 / (20)	Output moderately did not meet expectations. Indicator score B. (Indicator score assessed against Oct 18 target A+) / 52 instructors trained. / 22 welding instructors from Takoradi Technical Institute, Kikam Technical Institute, Regional Maritime University and College of Technology, University of Education have been trained to industry standards. / 30 instructors have been trained in other skills (to industry standards) including; mechanical, electricity and hydraulics.
3.4 Total finance secured from industry and other donors to support skills development [New indicator 2018] / Linked to KPI 5 (met): At least £200,000 secured from industry and other donors to support the technical skills development activity	£800,000 / (£200,000)	Output substantially did not meet expectations. Indicator score C. / (Indicator score assessed against Oct 18 target A+) / £286,474 ($381,260) from Greenline Logistics, Siapem, Modec, Seaweld, Yinson, Newmont, AMS, Integrity Logistics, Marine Master Services, IPMC, Kkloyds, Takoradi Gas, Ministry of Energy, and Golden Star Resources. / This was made up of 17 contracts including for example: / $13,500 from Siapem for Welding, pipefitting, and rigging assessment for 120 people; / $18,310 from Newmont for employee training in metallurgy and blueprint reading. / $220,275 from the Ministry of Energy for their Oil and Gas Capacity programme training Welding instructors.
[4] This is taken the figures from the Annual Review 2017 under Output 3.2 (Number of people acquiring skills for employment as a result of training undertaken or influenced by the Foundation (disaggregated by sex and age category).

Provide supporting narrative for the score

This output aimed to capture the opportunity that the WRCF had identified around engaging with the extractive industries to improve the skills of the local labour force. It fitted with its overall objective of creating prosperity for local communities impacted by O&G. Skills training was an avenue that offered an opportunity to create shared growth and prosperity for communities adversely impacted by the extractives sector and potentially as a long-term solution to industry’s local content obligations under Ghanaian law. It also provided a link to the Dialogue Platform, where one reoccurring issue from community conversations was the low employability of citizens in the coastal areas. Annex E outlines the full supporting narrative for this output.

Lessons identified this year linked to this output and recommendations for future programmes

- .
- Securing industry support for TVET interventions requires long term engagement to build trust, including discussions with various departments within companies and a clear focus on identifying and analysing concrete gaps and devising effective interventions.
- DFID should explore how its decision to close the DFID programme affected WRCF’s ability to pursue its TVET pipeline. With the close of the DFID programme, WRCF is not continuing to engage Corporate Professional and Industrial Training (CPIT) to deliver TVET work which has implications on its ability to secure new contracts.
- Industry involvement in development of training programmes is key to ensure graduates meet corporate and the extractives sector needs.
- The mining sector tends to provide more low-skilled job opportunities for residents in and around its projects than the O&G sector does, in particular if it is located off-shore. Thus, WRCF should continue to explore business opportunities with both mining and O&G companies.
- Based on its strong platform for convening stakeholders, WRCF hosted the first edition of the National Developing Industry Standards conference in 2018. This led to the launch of the Corporate Social Investment Skills Programme, which has succeeded in creating a common platform to discuss industry-government-educational institute linkages. The conference showed that the partnerships required between industry, government, TVET implementers and technical institutes can be built through facilitating dialogue and providing TA, as described in the TVET ToC (see also Outcome 2).

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The overall outcome being targeted by WRCF is ‘Expectations managed and met and constructive relationships between communities, government and industry built’. This review assesses the combined outcome score to be moderately did not meet expectations (assessed against Oct 18 target it is met expectations). The table below outline the scoring for each outcome indicator[5] and Annex F outlines the full assessment and narrative.
[5] It is noted that when the logframe changed in 2018, the new outcome indicators put less focus on the dialogue platform. Outcome indicator 1 to 3 were set to fit the reality of limited industry interest and funding reflecting the success of WRCF’s activities in TVET. That being said, Outcome Indicator 3 has strong links to the original indicator focused on securing operational funding for WRCF post-DFID funding. Lastly, the current outcome indicator 4 essentially survived the various logframe revisions.
Outcome Indicator 1	% of TVET graduates and economic intervention beneficiaries with increased income (disaggregated by sex / youth)	Outcome did moderately not meet expectations (assessed against Oct 18 target: Outcome did moderately not meet expectations)
Outcome Indicator 2	WRCF facilitates government, industry and technical institutes to adopt industry training standards and international accreditation in oil and gas related programmes.	Outcome substantially did not meet expectations. (assessed against Oct 18 target: no target).
Outcome Indicator 3	Sustainable foundation established and functioning [variation of old output indicator]	Outcome met expectations (assessed against Oct 18 target: Outcome met expectations)
Outcome Indicator 4	VFM - Activity Fund Leverage: Non-DFID funding for WRCF supported interventions [variation of old outcome indicator]	Outcome moderately did not meet expectations (assessed against Oct 18 target outcome exceeded expectations)

## Observations on impact-level achievements
From the onset, the logframe has included two impact indicators. The data reported in the logframe shows: (1) a reduction in poverty; and (2) positive changes in citizen’s perceptions of local stability, development equity and economic prospects in the Western Region. Little change has been observed in perceptions of equity, and perceptions around political stability and economic prospects has remained unchanged since 2016. For the WRCF programme, the question that remains is whether any of the changes can realistically be attributed to its existence? (Annex G outline the available data associated with the two impact indicators).

Impact indicator 1: district poverty rate
Although poverty rates are improving, it is not possible to attribute this improvement to the WRCF programme, as the factors contributing to the poverty reductions are numerous. Had the programme been able to raise and spend effectively the £16m originally envisaged, then it might have been possible to argue a stronger link with poverty improvements. In addition, the scale of reach of WRCF TVET and pilot interventions makes such conclusion difficult.

## Impact indicator 2: citizens perception of local stability, development equity and economic prospects.[6]
[6] Measured by Afrobarometer (2014 and 2020) and Citizen Perceptions and Socio-Economic Survey (CPSES, 2016 and 2018).
In line with the MTR, this review concludes that it is not possible to decisively establish the extent to which the increasing or unchanged positive perceptions in the Western Region can be attributed to WRCF, and in particular the dialogue platform. However, it seems plausible that the dialogue platform has had a positive influence on citizens’ perceptions of local stability, development equity and economic prospects in the Western Region. All stakeholders have expressed that the platform served as an effective and innovative intervention that gave voice to citizens and helped to build relationships between communities, local government and industry. It also developed a comprehensive database of social and economic issues covering 300 communities across the six coastal districts.

During the implementation of WRCF, there were no civil unrests in the Western Region. Stakeholders from industry, government and traditional leadership agree that the WRCF’s dialogue platform served as a pressure vault for venting concerns and that it contributed towards ‘killing misguided perceptions’. It provided an avenue for communities to air frustrations with IOCs and government authorities alike. Even if issues did not get resolved, its empowered community members’ who otherwise would not have had a voice. Reportedly, the dialogue platform also helped to raise awareness of the IOCs operations, as well as inform about government planning processes and enabled at least some self-help projects to gain knowledge on and tap into where public funds are coming from. The counterfactual level of local conflicts and potential civil unrest had the programme not existed is nearly impossible to establish. This review is not able to venture deeper into the nature of potential conflicts and conflict fault lines.

Summarise the programme’s theory of change and major changes to it in the past year (1/2 page)

The theory of change set out at the beginning of the programme was built on the assumption that the WRCF programme would establish a successful dialogue mechanism and a sizeable development fund. Improved stability and inclusive development prospects were expected to be delivered through citizens benefitting from independent and inclusive dialogue twinned with WRCF’s managing effective local economic development interventions funded by the private sector. The level of price during the design impacted the anticipated level of industry contribution to CSR. Given this dropped considerable, the ToC along with the logframe changed to focus on strengthening WRCF as an independent, self-sustaining entity, influencing the CSR spending of O&G companies and directing government interventions towards community needs.

In 2018, a revised ToC was developed to reflect the fact that the foundation was facing challenges in its transition towards a self-sustaining independent organisation. The revised ToC linked the three logframe outputs (i.e. the Dialogue Platform (output 1), Economic Development Interventions (output 2) and TVET interventions (output 3)) to the intermediate outcome of a sustainable foundation. By means of delivering services on skills, livelihood enhancements, and inclusive community development through a multi-stakeholder dialogue, it was assumed that the foundation could contribute towards the outcome statement and sustain itself. And ultimately, this would be in support of the impact statement of improved stability and inclusive development.

Explain major changes to the logframe in the past year (1/2 page)

A third and final revision to the logframe was approved in 2018 to respond to the recommendation of the programme’s MTR and extended MTR. The aim was to ensure the programme adjusted to changes in the operation environment as well as promoted the sustainability of the foundation after DFID funding would seize. Section A and Annex B outline the full detail of this and previous logframe changes.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

The VfM proposition in the Business Case was developed for a programme worth an expected £25.5m (£9.5 DFID funding and £16m O&G industry funding). The Business Case noted that this kind of programme would not be amenable to VfM measurement given that outputs and outcomes could not be easily compared with other DFID programmes; however, it does make key VFM statements - one of them was later revised to reflect the amended ambition of the WRCF programme:

- Efficiency (input leading to outputs): the dialogue structure would reach 364,000 residents in five years with a cost of £6.86 per resident reached.
- Cost effectiveness (resources leading to impact): the business case calculated in a cost benefit analysis that the foundation and Dialogue Platform could leverage a discounted US$160 million (£103 million) in benefits against the estimated $1.8 billion (£1.16bn) in social and conflict-related discounted costs likely to be produced through oil and gas development in the coastal districts of the Western Region. It concluded that contributing 9% towards the total costs of ameliorating these secondary impacts meant a significant contribution. In 2017, this cost benefit analysis was updated, and the cost benefit ratio revised down to one. In other words, the programme was expected to break even with discounted benefits equal to discounted costs.
- Equity: unequal distribution of benefits was identified as one of the potential drivers of conflict in the Western Region (although not directly mentioned under VfM in the Business Case).

The VfM framework was updated in September 2018, following the revisions to the logframe, in line with changes suggested at the programme’s MTR. The new framework also captured common VfM indicators which had previously not been reported on. Furthermore, in previous reviews, general concerns were raised around WRCF’s VfM. These concerns related to WRCF’s calculations for some indicators, the categorisation of certain indicators and the availability of indicators covering effectiveness and equity – as well as uneven reporting on progress which was in part due to poor data availability. The comprehensiveness of reporting is illustrated in the table below.

WRCF VfM indicators and Reporting in Annual Reports[7]
[7] 2016 and 2017 figures were produced as part of the WRCF VFM Report October 2018 and are based Annual reports submitted by DAI to DFID.
	Economy	Efficiency	Effectiveness	Equity	All
Total Indicators in original VFM framework	3	6	3	3	15
2016 Annual Report	2	2	2	1	7
2017 Annual Report	2	3	2	1	8
Total indicators in revised framework	3	3	4	4	14
2018 Annual Report	3	3	3	1	10

VfM assessment

The full VFM assessment of each E can be found in Annex H.

In summary, economy has improved over the lifetime of the programme, whilst efficiency and effectiveness are weaker due to the performance of the programme against its latest logframe. However, efficiency and effectiveness obviously vary depending on the Logframe targets applied to undertake the assessment (as pointed out in Section A).

The updated CBA from 2017 has been viewed as critical for assessing WRCF’s VfM proposition. The latest 2018 VfM report noted with regards to achieving the returns set out in the updated CBA that: “Value for money depends crucially on achieving the revised targets captured in the updated log-frame and adjusted work plans and on the fulfilment of expectations in a range of areas including: funds secured for the Foundation’ operations; funds leveraged from other donors and industry; the employment of WRCF beneficiaries and the increased incomes they receive; and the extent to which the dialogue structure in practice improves the investments of local government and oil and gas companies.”

Furthermore, the Annual Review 2018 concluded that the programme’s VfM performance was positive and that results suggested a moderately positive return for investment. It suggested that achieving the programme’s objective of establishing a sustainable self-financing foundation would further strengthen the VfM proposition of DFID’s investment into the programme. There were, however, significant concerns around WRCF’s ability to raise industry resources to fund the sustainability of the foundation by the January cut-off date. Leveraging industry resources for the TVET intervention in 2019 was critical for an overall positive outlook for CBA and for ensuring the programme would continue to represent VfM.

Quality of VFM reporting: it is not clear how reporting on VfM has improved in the revised framework - apart from alignment to a new logframe. For example, many additional indicators could have been reported under economy (such as flight costs and a more detailed breakdown of fee rates by seniority) improving the capture of VfM progress and achievements.

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

Risk management process: The overall risk rating of the WRCF programme is Major.[8] WRCF maintains a risk register and updates it on a quarterly basis as part of the quarterly progress reporting process. The last time it was updated was September 2018. The final programme risk matrix had no ‘severe’ risks at the residual risk level (post mitigation assessment). In the latest register, five risks were identified as severe prior to their respective mitigation strategies. No severe risks were identified around delivery, reputational, safeguarding even before respective mitigation strategies.
[8] This has been the risk rating since 2016 when the programme adopted the new DFID risk rating. The 2017 and 2018 Annual Review rated the programme as Major Risk reflecting the uncertainties surrounding the sustainability of the Foundation beyond DFID funding, as well as the novel nature of the programme. This review does not change the existing risk rating.

Risks and mitigation strategies: Changes to the assumptions underpinning the Business Case as discussed earlier have severely impacted the programme risks. These assumptions were linked to the assumed level of engagement from O&G companies and their funding contributions to the programme during and after DFID funding. Annex I outline a summary of the risk mitigation approach taken by the programme.

It should be noted that risks and their associated mitigation strategies linked to the dialogue function was well managed. Throughout the programme the WRCF team continued to maintain a neutral position in the dialogue discussions and past reviews credit the programme for its achievements around dialogue.

Update on partnership principles (1/2 page)

The Foundation focuses on poverty reduction in the target area (the Western Region). There are no current plans for any funds to be provided directly to Government or through Government systems. Where appropriate, the programme does work alongside Government in order to enable systemic changes.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Financial
DFID contracted PWC to audit the WRCF programme from December 2018 to April 2019 after it was agreed by both DFID and DAI to end the programme due to the failure to meet the Key Performance Indicators.

PwC concluded an independent audit in October 2019. The audit was satisfactory and had no findings against DAI. There are no recommendations for DFID to follow up on. PwC identified all events that occurred between the reporting date and the date of approval of the financial statements which may require adjustment of, or disclosure in, the financial statements, and have affected such adjustment or disclosure. PwC also confirmed that the financial statements are free of material misstatements, including omissions.

Asset Monitoring and Control

The assets for disposal under this programme had an initial value of £118,225 at their acquisition date at various times from 2015 to 2019. DFID usually only requires an asset register for items with a purchase value of above £500, however items included listed as consumables (under £500) as well, to provide a comprehensive overview. The depreciation applied varies across assets. A 20% deprecation is applied to furniture and fixture, 25% to computers and 10% to the vehicles. The deprecation is applied on the straight-line basis. The most expensive assets are the two vehicles bought at the beginning of the programme with an original total value of £46,751. They now retain a net worth of £27,960. The total value of all assets after applying their respective depreciation is £41,101. All programme assets were used for project implementation at the WRCF offices in Accra and the Western Regions. An asset register had been created and maintained for all assets purchased. DFID periodically monitored these assets during programme implementation.

During the programme closure it was decided that all assets be transferred temporarily to the Foundation for 12 months, who will have oversight to ensure the assets are used for official purposes. DFID will decide on the utilisation of assets after the 12-month period.

The decision was because the Foundation intended to carry on with the support of the WRCF Board. A letter indicating DFID’s oversight for a minimum period of 12 months whilst we take a decision was issued to the Foundation

Date of last narrative financial report
Date of last audited annual statement

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

Programme monitoring has been conducted satisfactorily and drew data from several sources. Annex J summarises the key reviews that took place throughout the review period.

Evidence (1/2 page)

There are currently no plans for DFID Ghana to carry out an evaluation of this programme. The WRCF monitored the impact of its activities through the baselines and endline Community Perceptions and Socio-Economic Surveys in 2016 and 2018. The two economic pilot interventions have also been monitored through intervention evaluations.

Learning (1/2 page)

A DFID-internal Lessons Learnt report identified the following nine learning conclusion on the programme and for DFID’s wider development work in and around the extractive and other large-scale private sector investments:

When testing new ground, programmes are best designed as pilots that allow for flexibility and adaptations. DFID decided early in the Design Phase that a Foundation should serve as the vehicle for delivering two types of envisaged interventions. This decision resulted in a prescriptively applied framework that was too ambitious on the causal connection between spending corporate CSR funding and DfID’s overarching and pre-set logical framework objectives. It also did not provide enough flexibility to adapt the programme as soon as it became apparent that several of the design assumptions did not hold. If the programme had been designed as a pilot, it would have come with the explicit understanding that adaptations and innovations are allowed and that the shared objectives of the collaborating partners would drive the contents.

Partnering with the private sector requires that target companies are fully engaged from the design phase through to implementation and that the programme focus on shared objectives. The WRCF programme set out to work with O&G sector companies to deliver economic development benefits to the people of the Western Region. But it failed to fully engage and partner with the industry from the start to ensure that individual companies would be able and willing to commit to a co-created approach and to justify availing financial or other resources. This failure undermined the programme’s understanding of corporate drivers, responsibilities and needs, not least to lay out a corporate Business Case for engaging in a strategic partnership or some other form of collaboration.

For developing and implementing community-focused interventions it is indispensable to clarify and track the context-specific institutional set-up and the legal and regulatory framework that governs the relationship between national-level public authorities and companies, and between local-level public authorities, companies and impacted communities. A key driver for the WRCF programme was the good intention to support Ghana’s good governance of its nascent O&G sector. But the design and inception phases were not informed by a thorough understanding of the institutional set-up of the public authorities and the socio-political stakeholders invested and impacted by the sector. Although several political economic analyses had been conducted, these failed to delineate the potential role that the WRCF could take in relation to the roles and responsibilities that national and local public authorities as well as the invested O&G companies hold vis-à-vis the impacted local communities

New programmes aimed at partnering with industry should hold off final decisions on form until the feasibility and effectiveness of interventions have been piloted and tested. DFID Ghana’s Design Mission paper laid out examples from within and outside Ghana to inform the early decision on the form through which the programme was expected to achieve its objectives. However, deciding on the form (i.e. the Foundation model) did not provide clarity with respect to the function that the WRCF was expected to deliver. Thus, its role was split between that of a facilitator and convenor and that of an implementing non-profit service delivery agency. Without a deeper analysis of the pros and cons and the actual versus intended achievements of the benchmarked reference cases, taking this decision later undermined the flexibility and innovative adaptability that the programme would have needed.

Private companies expect partnership programmes to add value in corporate terms. Corporate stakeholders could not be persuaded that the WRCF adds value and were left with the impression that the Foundation asked them to give something for free without them being able to justify internally what value the WRCF could add to the fulfilment of standard corporate responsibilities. The absence of a clear value proposition can also be linked to the lack of clarity around WRCF’s role and the expertise it could bring to support better corporate social performance management.

A local governance programme (i.e. multi-stakeholder dialogue) should not be vested with the same entity that is also expected to deliver the contents of social investment projects. WRCF’s experience has shown the same entity cannot at the same time serve as (i) a neutral dialogue-focused third parties that convenes and facilitates discussions on complex issues that may require tough trade-offs, and (ii) a delivery-oriented NGO (or private company) that conceptualises and implements effective social risk mitigation and management interventions and social investments programmes. Moreover, these two activity sets require quite distinct skills sets and, arguably, operational set ups. The WRCF faced significant challenges in its endeavour to deliver both. More thorough analysis of the drivers for and the achievements and outcomes of other extractive-sector related Foundations could have offered a more differentiated picture on whether and how to combine a dialogue mechanism with long-term economic development focused social investment. It would also have alerted to common pitfalls experienced in Ghana’s mining sector.

Programme designers and implementers need to make good efforts and invest in understanding the industry and its objectives, incentives and responsibilities. In the Ghanaian offshore context, the programme should have (i) established how the invested companies are operating on the ground (i.e. what EIA/ESIAs and other assessments were undertaken, what plans were developed on the back of these etc.) and (ii) appraised the Ghanaian legal and policy framework and the institutional arrangements for its O&G sector management to identify potential gaps, inconsistencies and/or overlaps. If respective knowledge is not available at the onset, programmes need to build ‘learning-by-doing’ into their design and governance arrangements.

Programme governance and results monitoring needs careful consideration. Good programme governance is based on clear roles and mandates. DFID’s management tools building on the logframe methodology did not naturally resonate with industry partners. Therefore, they should not have been front and centre to the way the programme was presented. Several industry actors expressed frustration that the WRCF consultants had engaged them in the programme’s need to fulfil logframe targets. The logframe methodology is not intuitive and cannot be prescribed to industry partners. These stakeholders rather appreciate working out a shared understanding of shared objectives, developing a strategy to achieve these and then to put in place a plan for implementation, drawing in the expert technical advice and resources required to deliver. This means that companies expect strong technical counterparts on the side of the development partner and delivery-oriented expertise from consultants engaged in implementation. The Foundation’s Board could also not function effectively, partly because of DFID’s dominance and the accountability of the WRCF Team Leader to the main service provider and partly because the Board’s mandate remained unclear and presented a weak and ambiguous voice in providing direction.

Increasing ‘voice’ in communities creates value in and of itself. The Dialogue Platform gave communities ‘voice’, collected useful information on social and economic issues, and provided some feedback on what the industry and the national government were doing in response to community concerns. Local government authorities at the district level were particularly appreciative of the WRCF’s support to communicate with communities, gather data, inform district planning, and manage relationships. There is some evidence of the Dialogue Platform triggering self-help initiatives in response to specific issues that emerged as part of the conversations. Non-corporate interviewees have also expressed a clear appreciation of the Dialogue Platform and that it has helped to build stronger accountability between local citizens and their local government representatives. This itself was seen as valuable in an environment where expectations around O&G exploration and production remain high.

Progress on recommendations from annual reviews for this programme (1/2 page)

As highlighted in Section A, the WRCF were faced with some severe implementation challenges given the original design of the programme. It does therefore not come as a surprise that previous Annual Reports have put forward recommendations which relate to certain themes or elements of the WRCF, and which the WRCF faced challenges in responding to:
- Strengthen coordination and strategic partnerships with industry and government, in particular, the Petroleum Commission;
- Adapt, strengthen, improve the WRCF resource mobilisation model to an approach that builds a self-sustaining and viable Foundation; and
- Seek synergies and collaboration with the DFID Ghana extractives programme the Ghana Oil and Gas for Inclusive Growth (GOGIG).

The recommendations from the annual review 2018 have been followed up in part as these recommendations had strong links to the KPI assessment. The decision to close the programme earlier than originally planned does not provide a strong foundation for assessing responses to those recommendations.
## Smart Guide
## The Project Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.
The Project Completion Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it aimed to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. You should assume that readers may not go beyond this summary. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. There needs to be a record of any follow up actions that may be required after completion of this review (eg related to final payments, audited statements etc – see the extension and closure section in the Smart Rules). These may sit best in the Delivery Plan – but you should agree them with the person signing off the PCR and include them in this (publicly available) report or the Delivery Plan.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the PCR for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review (Business Case approval if the programme is under 15 months and hasn’t had an AR) and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in Section A. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress against outcomes
Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved? Review this in view of the overall programme score; but it is possible that outputs were delivered but the envisaged outcomes or impact were not – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact. You should refer to the indicators in the logframe. Did any unexpected outcomes emerge? Were there any significant changes in the planned timetable for delivery of the programme? Were there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact were valid e.g. did the ToC logic, supporting evidence and assumptions hold up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications were for the programme. Ideally changes should not have be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started.
D: Value for Money
Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme You should refer to VfM measures and metrics from the Business Case and/or ARs. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind. You should note any formal extensions or amendments to the programme giving brief details about cost, duration and the reasons why. Signifcant changes to logframe indicators or targets may also be relevant.

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) during the past year and over the life of the programme / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context in the past year and how they impacted on the programme and were mitigated. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review (remember that projects remain open until they are archived, even after the PCR is complete). / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences?
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could have been a more effective partner to help deliver the programme (key points could be included in Section G too). / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how they engaged with the programme implementer(s) and DFID. Briefly describe the PCR process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Include any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned or has taken place set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications or follow-up actions of that learning for this programme may be best captured in Section A / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from ARs (especially the last one) should be provided.